## Sheet1
2018 Project Status Report
Rows 1 - 300
Request Number | PJ Description | PJ Manager Name | PJ Status | Enter Date | WO Description | Bldg Number | WO Status | Estimated Total Cost | Committed PO | Actual Costs | Total Project Cost
PJ0005952 | INVESTIGATING POTENTIAL TO RE-PURPOSE 2005 SOLAR HOUSE BLD C7 | PROJECT UNASSIGNED | TRIAGE | 2018-04-03 | CP: PROJECT CONTINGENCY | P-C07 | OPEN | 0 | 0 | 0 | 0
PJ0005952 | INVESTIGATING POTENTIAL TO RE-PURPOSE 2005 SOLAR HOUSE BLD C7 | PROJECT UNASSIGNED | TRIAGE | 2018-04-03 | PM:INVESTIGATING POTENTIAL TO RE-PURPOSE 2005 SOLAR HOUSE BLD C7 | P-C07 | OPEN | 0 | 0 | 0 | 0
PJ0005952 | INVESTIGATING POTENTIAL TO RE-PURPOSE 2005 SOLAR HOUSE BLD C7 | PROJECT UNASSIGNED | TRIAGE | 2018-04-03 | SM:INVESTIGATING POTENTIAL TO RE-PURPOSE 2005 SOLAR HOUSE BLD C7 | P-C07 | OPEN | 0 | 0 | 0 | 0
PJ0005952 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | CA: SUPPORT FOR FAKE NEWS PANEL - APRIL 26 | 042 | ASSIGNED | 0 | 0 | 361.53 | 361.53
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | CP: PROJECT CONTINGENCY | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | CU: SUPPORT FOR FAKE NEWS EVENT - 4/26 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | EL: SUPPORT FOR FAKE NEWS EVENT - APRIL 26 | 042 | COMPLETE | 0 | 0 | 966.42 | 966.42
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | LA: SUPPORT FOR FAKE NEWS PANEL - APRIL 26 | 042 | OPEN | 0 | 0 | 1160.244 | 1160.244
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | MO: SUPPORT FOR FAKE NEWS PANEL - APRIL 26 | 042 | OPEN | 0 | 0 | 26.255 | 26.255
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | PA: FAKE NEWS PANEL GRAFFITI SUPPORT - APRIL 26 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005951 | SUPPORT FOR FAKE NEWS PANEL EVENT (PROJECT) | POPHAM, DONALD J. | IN_CONSTR | 2018-04-18 | PL: SUPPORT FOR FAKE NEWS PANEL - APRIL 26 | 042 | ASSIGNED | 0 | 0 | 1331.688 | 1331.688
PJ0005951 Total | [7 empty] | 0 | 0 | 3846.137 | 3846.137
PJ0005949 | ARCE ROOM REFRESH - BLD 21 RM 122C, 122D | PROJECT UNASSIGNED | TRIAGE | 2018-04-06 | CP: PROJECT CONTINGENCY | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005949 | ARCE ROOM REFRESH - BLD 21 RM 122C, 122D | PROJECT UNASSIGNED | TRIAGE | 2018-04-06 | PM: ARCE ROOM REFRESH - BLD 21 RM 122C, 122D | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005949 | ARCE ROOM REFRESH - BLD 21 RM 122C, 122D | PROJECT UNASSIGNED | TRIAGE | 2018-04-06 | SM: ARCE ROOM REFRESH - BLD 21 RM 122C, 122D | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005949 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005946 | M&R H/C 18/19: SPACE ASSESSMENT - HC 27 DESIGN ONLY | DILLON, JEFFREY | SCOPE_DEV | 2018-03-29 | CP: PROJECT CONTINGENCY | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005946 | M&R H/C 18/19: SPACE ASSESSMENT - HC 27 DESIGN ONLY | DILLON, JEFFREY | SCOPE_DEV | 2018-03-29 | PM: M&R H/C 18/19: SPACE PROGRAMMING ASSESSMENT - HC 27 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005946 | M&R H/C 18/19: SPACE ASSESSMENT - HC 27 DESIGN ONLY | DILLON, JEFFREY | SCOPE_DEV | 2018-03-29 | SM: M&R H/C 18/19: SPACE PROGRAMMING ASSESSMENT - HC 27 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005946 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005945 | CONFERENCE ROOM REFRESH - BLD 47 RM 24B | MACDONALD, WENDY | SCHEDULING | 2018-03-26 | CP: PROJECT CONTINGENCY | 047 | OPEN | 0 | 0 | 0 | 0
PJ0005945 | CONFERENCE ROOM REFRESH - BLD 47 RM 24B | MACDONALD, WENDY | SCHEDULING | 2018-03-26 | PM: CONFERENCE ROOM REFRESH - BLD 47 RM 24B | 047 | OPEN | 0 | 0 | 0 | 0
PJ0005945 | CONFERENCE ROOM REFRESH - BLD 47 RM 24B | MACDONALD, WENDY | SCHEDULING | 2018-03-26 | SM: CONFERENCE ROOM REFRESH - BLD 47 RM 24B | 047 | COMPLETE | 0 | 0 | 0 | 0
PJ0005945 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005944 | INSTALL PAINT BOOTH - BLD 34 RM 144 | PROJECT UNASSIGNED | TO_CANCEL | 2018-02-28 | CP: PROJECT CONTINGENCY | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005944 | INSTALL PAINT BOOTH - BLD 34 RM 144 | PROJECT UNASSIGNED | TO_CANCEL | 2018-02-28 | PM: PAINT BOOTH INSTALLATION - BLD 34 RM 144 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005944 | INSTALL PAINT BOOTH - BLD 34 RM 144 | PROJECT UNASSIGNED | TO_CANCEL | 2018-02-28 | SM: PAINT BOOTH INSTALLATION - BLD 34 RM 144 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005944 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005943 | MJ: SUPPORT FIRE ALARM & SPRINKLERS - S. MTN. BLDS 106-108, 110 | PROJECT UNASSIGNED | TRIAGE | 2018-03-14 | CP: PROJECT CONTINGENCY | S. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005943 | MJ: SUPPORT FIRE ALARM & SPRINKLERS - S. MTN. BLDS 106-108, 110 | PROJECT UNASSIGNED | TRIAGE | 2018-03-14 | PM: INSTALL FIRE ALARM AND SPRINKLERS - BLDS 106-108, 110 | S. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005943 | MJ: SUPPORT FIRE ALARM & SPRINKLERS - S. MTN. BLDS 106-108, 110 | PROJECT UNASSIGNED | TRIAGE | 2018-03-14 | SM: INSTALL FIRE ALARM AND SPRINKLERS - BLDS 106-108, 11 | S. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005943 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005941 | DM 17/18: FIRE ALARM REPAIRS - CAMPUS WIDE | POLVI, STEVEN | SCOPE_DEV | 2018-03-13 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 12343.96 | 0 | 0 | 0
PJ0005941 | DM 17/18: FIRE ALARM REPAIRS - CAMPUS WIDE | POLVI, STEVEN | SCOPE_DEV | 2018-03-13 | EL: Repairs Fire Alarm Systems in Bldgs. 007, 011, 026, & 034 | GENERAL | OPEN | 123439.7228 | 0 | 0 | 0
PJ0005941 | DM 17/18: FIRE ALARM REPAIRS - CAMPUS WIDE | POLVI, STEVEN | SCOPE_DEV | 2018-03-13 | PM: CAMPUS-WIDE FIRE ALARM REPAIRS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005941 | DM 17/18: FIRE ALARM REPAIRS - CAMPUS WIDE | POLVI, STEVEN | SCOPE_DEV | 2018-03-13 | SM: CAMPUS-WIDE FIRE ALARM REPAIRS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005941 Total | [7 empty] | 135783.6828 | 0 | 0 | 0
PJ0005940 | ADD A/C TO LABS - BLD 20 RMS 100,112,113,121,146,147,148,149 | NORTON, DAVE | DESIGN | 2018-03-12 | AD: GOSS ENGINEERING | 020 | OPEN | 10379 | 0 | 0 | 0
PJ0005940 | ADD A/C TO LABS - BLD 20 RMS 100,112,113,121,146,147,148,149 | NORTON, DAVE | DESIGN | 2018-03-12 | CP: PROJECT CONTINGENCY | 020 | OPEN | 1037.9 | 0 | 0 | 0
PJ0005940 | ADD A/C TO LABS - BLD 20 RMS 100,112,113,121,146,147,148,149 | NORTON, DAVE | DESIGN | 2018-03-12 | PM: AIR CONDITIONING LAB ROOMS - BLD 20 RM 100 | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005940 | ADD A/C TO LABS - BLD 20 RMS 100,112,113,121,146,147,148,149 | NORTON, DAVE | DESIGN | 2018-03-12 | SM: AIR CONDITIONING LAB ROOMS - BLD 20 RM 100 | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005940 Total | [7 empty] | 11416.9 | 0 | 0 | 0
PJ0005939 | INSTALL RESIDENTIAL SECURTIY SYSTEM - BLD 51 | ULM, AARON | SCOPE_DEV | 2018-03-08 | CP: PROJECT CONTINGENCY | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005939 | INSTALL RESIDENTIAL SECURTIY SYSTEM - BLD 51 | ULM, AARON | SCOPE_DEV | 2018-03-08 | PM: INSTALL RESIDENTIAL SECURTIY SYSTEM - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005939 | INSTALL RESIDENTIAL SECURTIY SYSTEM - BLD 51 | ULM, AARON | SCOPE_DEV | 2018-03-08 | SM: INSTALL RESIDENTIAL SECURTIY SYSTEM - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005939 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005938 | M&R ASI 17/18: TECH LOUNGE DESIGN ONLY - UU 65 RM 221 | PROJECT UNASSIGNED | TRIAGE | 2018-03-08 | CP: PROJECT CONTINGENCY | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005938 | M&R ASI 17/18: TECH LOUNGE DESIGN ONLY - UU 65 RM 221 | PROJECT UNASSIGNED | TRIAGE | 2018-03-08 | PM:17/18 M&R ASI TECH LOUNGE DESIGN | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005938 | M&R ASI 17/18: TECH LOUNGE DESIGN ONLY - UU 65 RM 221 | PROJECT UNASSIGNED | TRIAGE | 2018-03-08 | SM: 17/18 M&R ASI TECH LOUNGE DESIGN | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005938 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005937 | SUPPORT FOR MJ0077 (OCOB BUILDING ANNEX) DESIGN ONLY | CREEL, AUSTIN | SCHEDULING | 2018-03-07 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005937 | SUPPORT FOR MJ0077 (OCOB BUILDING ANNEX) DESIGN ONLY | CREEL, AUSTIN | SCHEDULING | 2018-03-07 | PM: OCOB BUILDING ANNEX - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005937 | SUPPORT FOR MJ0077 (OCOB BUILDING ANNEX) DESIGN ONLY | CREEL, AUSTIN | SCHEDULING | 2018-03-07 | SM: OCOB BUILDING ANNEX - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005937 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005934 | MJ: IN HOUSE SUPPORT: SATRC | BROWN, CARLA | SCOPE_DEV | 2018-03-06 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005934 | MJ: IN HOUSE SUPPORT: SATRC | BROWN, CARLA | SCOPE_DEV | 2018-03-06 | EL: CB - PRECONSTRUCTION SUPPORT FOR SATRC | GENERAL | LONG_TERM | 0 | 0 | 283.488 | 283.488
PJ0005934 | MJ: IN HOUSE SUPPORT: SATRC | BROWN, CARLA | SCOPE_DEV | 2018-03-06 | ES: CB - PRECONSTRUCTION SUPPORT FOR SATRC | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005934 | MJ: IN HOUSE SUPPORT: SATRC | BROWN, CARLA | SCOPE_DEV | 2018-03-06 | PL: CB - PRECONSTRUCTION SUPPORT FOR SATRC | GENERAL | LONG_TERM | 0 | 0 | 0 | 0
PJ0005934 | MJ: IN HOUSE SUPPORT: SATRC | BROWN, CARLA | SCOPE_DEV | 2018-03-06 | PM: MJ: IN HOUSE SUPPORT: SATRC - BLD 181 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005934 | MJ: IN HOUSE SUPPORT: SATRC | BROWN, CARLA | SCOPE_DEV | 2018-03-06 | SM: MJ: IN HOUSE SUPPORT: SATRC - BLD 181 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005934 Total | [7 empty] | 0 | 0 | 283.488 | 283.488
PJ0005933 | CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | CREEL, AUSTIN | SCHEDULING | 2018-02-27 | AD: CANNON | U-SEWR | OPEN | 18560 | 0 | 0 | 0
PJ0005933 | CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | CREEL, AUSTIN | SCHEDULING | 2018-02-27 | AD: FPCP MANAGEMENT/DESIGN | U-SEWR | OPEN | 2800 | 0 | 0 | 0
PJ0005933 | CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | CREEL, AUSTIN | SCHEDULING | 2018-02-27 | CP: PROJECT CONTINGENCY | U-SEWR | OPEN | 1091.04 | 0 | 0 | 0
PJ0005933 | CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | CREEL, AUSTIN | SCHEDULING | 2018-02-27 | PL: CAMPUS SEWER STUDY | U-SEWR | WORKING | 7649.6 | 0 | 220.34 | 220.34
PJ0005933 | CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | CREEL, AUSTIN | SCHEDULING | 2018-02-27 | PM: CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | U-SEWR | OPEN | 0 | 0 | 0 | 0
PJ0005933 | CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | CREEL, AUSTIN | SCHEDULING | 2018-02-27 | SM: CAMPUS SEWER CAPACITY EVAL - GEN CAMPUS | U-SEWR | OPEN | 0 | 0 | 0 | 0
PJ0005933 Total | [7 empty] | 30100.64 | 0 | 220.34 | 220.34
PJ0005932 | REMODEL DRC SPACE - BLD 124 RMS 120,121,122,123 | DUNN, TRAVIS | DESIGN | 2018-02-23 | CP: PROJECT CONTINGENCY | 124 | OPEN | 0 | 0 | 0 | 0
PJ0005932 | REMODEL DRC SPACE - BLD 124 RMS 120,121,122,123 | DUNN, TRAVIS | DESIGN | 2018-02-23 | PM: REMODEL DRC SPACE - BLD 124 | 124 | OPEN | 0 | 0 | 0 | 0
PJ0005932 | REMODEL DRC SPACE - BLD 124 RMS 120,121,122,123 | DUNN, TRAVIS | DESIGN | 2018-02-23 | SM: REMODEL DRC SPACE - BLD 124 | 124 | OPEN | 0 | 0 | 0 | 0
PJ0005932 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005931 | M&R HOUS 17/18: BBQ & ACCESS VBALL COURT - PCV (SEE 5667) | ULM, AARON | SCOPE_DEV | 2018-02-28 | CP: PROJECT CONTINGENCY | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005931 | M&R HOUS 17/18: BBQ & ACCESS VBALL COURT - PCV (SEE 5667) | ULM, AARON | SCOPE_DEV | 2018-02-28 | PM: M&R HOUS 17/18: BBQ AND ACCESS AT VOLLEYBALL COURT - PCV | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005931 | M&R HOUS 17/18: BBQ & ACCESS VBALL COURT - PCV (SEE 5667) | ULM, AARON | SCOPE_DEV | 2018-02-28 | SM: M&R HOUS 17/18: BBQ AND ACCESS AT VOLLEYBALL COURT - PCV | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005931 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005930 | M&R HOUS 17/18: INSTALL PLUG-IN STATION - PCV (SEE 5669) | ULM, AARON | SCOPE_DEV | 2018-02-28 | CP: PROJECT CONTINGENCY | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005930 | M&R HOUS 17/18: INSTALL PLUG-IN STATION - PCV (SEE 5669) | ULM, AARON | SCOPE_DEV | 2018-02-28 | PM: M&R HOUS 17/18: INSTALL PLUG-IN STATION - PCV | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005930 | M&R HOUS 17/18: INSTALL PLUG-IN STATION - PCV (SEE 5669) | ULM, AARON | SCOPE_DEV | 2018-02-28 | SM: M&R HOUS 17/18: INSTALL PLUG-IN STATION - PCV | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005930 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005929 | VP_SA MOVE AND MINOR REMODEL - BLD 1 RM 206 | NORTON, DAVE | SCOPE_DEV | 2018-02-22 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005929 | VP_SA MOVE AND MINOR REMODEL - BLD 1 RM 206 | NORTON, DAVE | SCOPE_DEV | 2018-02-22 | PM: VPSA MOVE AND MINOR REMODEL - BLD 1 RM 206 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005929 | VP_SA MOVE AND MINOR REMODEL - BLD 1 RM 206 | NORTON, DAVE | SCOPE_DEV | 2018-02-22 | SM: VPSA MOVE AND MINOR REMODEL - BLD 1 RM 206 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005929 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005928 | MOUNT NETWORKED MONITOR/PC - BLD 52 ACROSS FROM D27 | PROJECT UNASSIGNED | TRIAGE | 2018-02-19 | CP: PROJECT CONTINGENCY | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005928 | MOUNT NETWORKED MONITOR/PC - BLD 52 ACROSS FROM D27 | PROJECT UNASSIGNED | TRIAGE | 2018-02-19 | PM: MOUNT NETWORKED MONITOR/PC - BLD 52 D27 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005928 | MOUNT NETWORKED MONITOR/PC - BLD 52 ACROSS FROM D27 | PROJECT UNASSIGNED | TRIAGE | 2018-02-19 | SM: MOUNT NETWORKED MONITOR/PC - BLD 52 D27 | 052 | COMPLETE | 0 | 0 | 0 | 0
PJ0005928 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005927 | MOUNT AND HANG PROJECTOR - BLD 3 RM 114 | PROJECT UNASSIGNED | HOLD | 2018-02-15 | CP: PROJECT CONTINGENCY | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005927 | MOUNT AND HANG PROJECTOR - BLD 3 RM 114 | PROJECT UNASSIGNED | HOLD | 2018-02-15 | PM: MOUNT AND HANG PROJECTOR - BLD 3 RM 114 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005927 | MOUNT AND HANG PROJECTOR - BLD 3 RM 114 | PROJECT UNASSIGNED | HOLD | 2018-02-15 | SM: MOUNT AND HANG PROJECTOR - BLD 3 RM 114 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005927 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005926 | LEED MASTER SITE CERTIFICATION - GENERAL | ELLIOT, DENNIS K | SCOPE_DEV | 2018-02-20 | CP: PROJECT CONTINGENCY - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005926 | LEED MASTER SITE CERTIFICATION - GENERAL | ELLIOT, DENNIS K | SCOPE_DEV | 2018-02-20 | PM: LEED MASTER SITE CERTIFICATION - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005926 | LEED MASTER SITE CERTIFICATION - GENERAL | ELLIOT, DENNIS K | SCOPE_DEV | 2018-02-20 | SM: LEED MASTER SITE CERTIFICATION - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005926 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005924 | REPLACE FLOOR, BLINDS, SCREEN, MOVE PROJECTOR - BLD 46 RM 6 | ULM, AARON | SCOPE_DEV | 2018-02-12 | CP: PROJECT CONTINGENCY | 046 | OPEN | 0 | 0 | 0 | 0
PJ0005924 | REPLACE FLOOR, BLINDS, SCREEN, MOVE PROJECTOR - BLD 46 RM 6 | ULM, AARON | SCOPE_DEV | 2018-02-12 | PM: REPLACE SPRUNG FLOOR IN DANCE STUDIO - BLD 46 RM 6 | 046 | OPEN | 0 | 0 | 0 | 0
PJ0005924 | REPLACE FLOOR, BLINDS, SCREEN, MOVE PROJECTOR - BLD 46 RM 6 | ULM, AARON | SCOPE_DEV | 2018-02-12 | SM: REPLACE SPRUNG FLOOR IN DANCE STUDIO - BLD 46 RM 6 | 046 | OPEN | 0 | 0 | 0 | 0
PJ0005924 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | AD: FPCP MANAGEMENT/DESIGN | 171 | OPEN | 700 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | AD: PRINTING AND SHIPPING | 171 | OPEN | 100 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | AD: STATE FIRE MARSHAL | 171 | OPEN | 2137.2 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | CP: PROJECT CONTINGENCY | 171 | OPEN | 229.61 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | IN: SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 | 171 | HOLD | 58.87 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | PM: SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005923 | SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 (NO OH) | HOGAN, MIKE | PLAN_CHECK | 2018-02-02 | SM: SFM DOUBLE OCCUPANCY IN APARTMENT BEDROOMS - BLD 171 | 171 | OPEN | 0 | 0 | 0 | 0
PJ0005923 Total | [7 empty] | 3225.68 | 0 | 0 | 0
PJ0005922 | RESIDENCE HALL TRIPLE OCCUPANCY EGRESS EVALUATION - BLD 114 | HOGAN, MIKE | SCOPE_DEV | 2018-02-02 | CP: PROJECT CONTINGENCY | 114 | OPEN | 0 | 0 | 0 | 0
PJ0005922 | RESIDENCE HALL TRIPLE OCCUPANCY EGRESS EVALUATION - BLD 114 | HOGAN, MIKE | SCOPE_DEV | 2018-02-02 | PM: RESIDENCE HALL TRIPLE OCCUPANCY EGRESS EVALUATION - BLD 114 | 114 | OPEN | 0 | 0 | 0 | 0
PJ0005922 | RESIDENCE HALL TRIPLE OCCUPANCY EGRESS EVALUATION - BLD 114 | HOGAN, MIKE | SCOPE_DEV | 2018-02-02 | SM: RESIDENCE HALL TRIPLE OCCUPANCY EGRESS EVALUATION - BLD 114 | 114 | OPEN | 0 | 0 | 0 | 0
PJ0005922 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005921 | EGRESS ANALYSIS - BLD 172 YTT | HOGAN, MIKE | SCOPE_DEV | 2018-02-02 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005921 | EGRESS ANALYSIS - BLD 172 YTT | HOGAN, MIKE | SCOPE_DEV | 2018-02-02 | PM: EGRESS ANALYSIS FOR YTT - BLD 172 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005921 | EGRESS ANALYSIS - BLD 172 YTT | HOGAN, MIKE | SCOPE_DEV | 2018-02-02 | SM: EGRESS ANALYSIS FOR YTT - BLD 172 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005921 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005920 | UH DEPOT EXPANSION DESIGN - BLD 371B | PROJECT UNASSIGNED | TRIAGE | 2018-02-05 | CP: PROJECT CONTINGENCY | 371B | OPEN | 0 | 0 | 0 | 0
PJ0005920 | UH DEPOT EXPANSION DESIGN - BLD 371B | PROJECT UNASSIGNED | TRIAGE | 2018-02-05 | PM: UH DEPOT EXPANSION DESIGN - BLD 371B | 371B | OPEN | 0 | 0 | 0 | 0
PJ0005920 | UH DEPOT EXPANSION DESIGN - BLD 371B | PROJECT UNASSIGNED | TRIAGE | 2018-02-05 | SM: UH DEPOT EXPANSION DESIGN - BLD 371B | 371B | OPEN | 0 | 0 | 0 | 0
PJ0005920 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | AD: GOSS ENGINEERING | 105 | OPEN | 30709 | 18425.4 | 12283.6 | 30709
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | AD: ITS | 105 | OPEN | 1000.0006 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | AD: JOC 18.043 KINYON CONSTRUCTION | 105 | OPEN | 581315.9023 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | AD: MCKENNA | 105 | OPEN | 17729.9 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | AD: STATE FIRE MARSHAL | 105 | OPEN | 4280 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | ANTS: | 105 | OPEN | 413.4336 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | CP: PROJECT CONTINGENCY | 105 | OPEN | 62649.7 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | EH&S: | 105 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | EL: | 105 | OPEN | 141.7416 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | ES: PROVIDE SUPPORT & REMOVE COORDOR DUCTWORK | 105 | OPEN | 1877.9904 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | IN: TRINITY FIRE SPRINKLERS - BLD 105 | 105 | ASSIGNED | 353.22 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | LA: | 105 | OPEN | 220.176 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | PA: | 105 | OPEN | 1268.0988 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | PL: PROVIDE CONTRACTOR SUPPORT FOR FS INSTALLATION | 105 | OPEN | 1844.3568 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | PM: TRINITY FIRE SPRINKLERS - BLD 105 | 105 | OPEN | 0 | 0 | 0 | 0
PJ0005919 | TRINITY FIRE SPRINKLERS - BLD 105 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-02-08 | SM: TRINITY FIRE SPRINKLERS - BLD 105 | 105 | OPEN | 0 | 0 | 0 | 0
PJ0005919 Total | [7 empty] | 703874.3249 | 18425.4 | 12283.6 | 30709
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | CA: SUPPORT FOR RODEO: APRIL 13 & 14 | 061 | ASSIGNED | 0 | 0 | 3209.649 | 3209.649
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | CP: PROCECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | CU: SUPPORT FOR 2018 RODEO | 061 | OPEN | 0 | 0 | 2916.9124 | 2916.9124
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | EL: ELECTRICAL SUPPORT FOR 2018 RODEO-APRIL 13 & 14 | 061 | LONG_TERM | 0 | 0 | 8355.948 | 8355.948
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | EL: REPAIR OF DAMAGED CONTROL BOX - SPANOS STADIUM | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | GR: IRRIGATION REPAIR OF MAINLINE - SPANOS STADIUM | 061 | COMPLETE | 0 | 0 | 1290.5605 | 1290.5605
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | GR: SUPPORT FOR 2018 RODEO (APRIL 13 &14) | 061 | OPEN | 0 | 0 | 508.8029 | 508.8029
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | MC: MOVE MATS AT TO SPANOS STADIUM FOR RODEO - 4/12 | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005918 | SUPPORT FOR RODEO 2018 IN HOUSE LABOR- BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-02-08 | PERMIT: 2018 POLY ROYAL RODEO - APRIL 13 & APRIL 14 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005918 Total | [7 empty] | 0 | 0 | 16281.8727 | 16281.8727
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | AD: BKM | 052 | OPEN | 29869.4459 | 29869.4459 | 0 | 29869.4459
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | AD: CLASSROOM TECH | 052 | OPEN | 10700 | 0 | 0 | 0
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | AD: ITS | 052 | OPEN | 7827.05 | 0 | 0 | 0
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | CP: PROJECT CONTINGENCY | 052 | OPEN | 2746.17 | 0 | 0 | 0
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | LO:DILLON P.M. BLDG 52 LOCK REPLACE | 052 | ASSIGNED | 748.0656 | 0 | 335.082 | 335.082
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | PA:DILLON P.M. 52-D WING | 052 | CLOSED | 860.988 | 0 | 563.688 | 563.688
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | PM: MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005917 | MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | DILLON, JEFFREY | IN_CONSTR | 2018-01-26 | SM: MODIFY FORMER EMBASSY ENGLISH SPACE - BLD 52 RM D27 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005917 Total | [7 empty] | 52751.7195 | 29869.4459 | 898.77 | 30768.2159
PJ0005916 | COMPLETION OF QL+ LAB RENOVATION - BLD 192 RM 130 | BROWN, CARLA | SCOPE_DEV | 2017-10-29 | CP: PROJECT CONTINGENCY | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005916 | COMPLETION OF QL+ LAB RENOVATION - BLD 192 RM 130 | BROWN, CARLA | SCOPE_DEV | 2017-10-29 | PM: COMPLETION OF QL+ LAB RENOVATION - BLD 192 RM 130 | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005916 | COMPLETION OF QL+ LAB RENOVATION - BLD 192 RM 130 | BROWN, CARLA | SCOPE_DEV | 2017-10-29 | SM: COMPLETION OF QL+ LAB RENOVATION - BLD 192 RM 130 | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005916 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005915 | SAND VOLLEYBALL COURT INSTALLATION - BLD 42 RM 104A | PROJECT UNASSIGNED | TRIAGE | 2018-01-25 | CP: PROJECT CONTINGENCY | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005915 | SAND VOLLEYBALL COURT INSTALLATION - BLD 42 RM 104A | PROJECT UNASSIGNED | TRIAGE | 2018-01-25 | PM: SAND VOLLEYBALL COURT INSTALLATION - BLD 42 RM 104A | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005915 | SAND VOLLEYBALL COURT INSTALLATION - BLD 42 RM 104A | PROJECT UNASSIGNED | TRIAGE | 2018-01-25 | SM: SAND VOLLEYBALL COURT INSTALLATION - BLD 42 RM 104A | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005915 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005914 | SUPPORT MEN'S LACROSSE GAME - BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-01-30 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005914 | SUPPORT MEN'S LACROSSE GAME - BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-01-30 | CU: SUPPORT FOR LACROSSE GAME: 2/23 | 061 | OPEN | 0 | 0 | 229.5979 | 229.5979
PJ0005914 | SUPPORT MEN'S LACROSSE GAME - BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-01-30 | LA: SUPPORT FOR MEN'S LACROSSE GAME - FEB. 23 | 061 | OPEN | 0 | 0 | 320.256 | 320.256
PJ0005914 | SUPPORT MEN'S LACROSSE GAME - BLD 61 | POPHAM, DONALD J. | CONST_COMP | 2018-01-30 | SM: SUPPORT MEN'S LACROSSE GAME - BLD 61 | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005914 Total | [7 empty] | 0 | 0 | 549.8539 | 549.8539
PJ0005913 | INSTALL COMMUNICATION CONDUIT - BLD 170 | DUNN, TRAVIS | ESTIMATING | 2018-01-25 | CP: PROJECT CONTINGENCY | 170 | OPEN | 0 | 0 | 0 | 0
PJ0005913 | INSTALL COMMUNICATION CONDUIT - BLD 170 | DUNN, TRAVIS | ESTIMATING | 2018-01-25 | PM: INSTALL COMMUNICATION CONDUIT - BLD 170 -LABOR TRACKING | 170 | OPEN | 0 | 0 | 0 | 0
PJ0005913 | INSTALL COMMUNICATION CONDUIT - BLD 170 | DUNN, TRAVIS | ESTIMATING | 2018-01-25 | SM: INSTALL COMMUNICATION CONDUIT - BLD 170 | 170 | OPEN | 0 | 0 | 0 | 0
PJ0005913 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | CA: SUPPORT FOR 2018 OPEN HOUSE (APRIL 14, 2018) | GENERAL | ASSIGNED | 0 | 0 | 311.5675 | 311.5675
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | CU: SUPPORT FOR 2018 OPEN HOUSE (APRIL 13 &14) | GENERAL | OPEN | 0 | 0 | 1185.1086 | 1185.1086
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | CU: SUPPORT FOR 2018 OPEN HOUSE (APRIL 14,2018) | GENERAL | OPEN | 0 | 0 | 852.1 | 852.1
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | EL: SUPPORT FOR 2018 OPEN HOUSE (APRIL 14, 2018) | GENERAL | LONG_TERM | 0 | 0 | 2630.81 | 2630.81
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | LA: SUPPORT FOR 2018 OPEN HOUSE (4/13-4/14) | GENERAL | COMPLETE | 0 | 0 | 4679.9653 | 4679.9653
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | PERMIT: 2018 OPEN HOUSE BEER & WINE - APRIL 14 | 197 | COMPLETE | 0 | 0 | 0 | 0
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | PERMIT: OPEN HOUSE 2018 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | PL: SUPPORT FOR 2018 OPEN HOUSE (APRIL14, 2018) | GENERAL | COMPLETE | 0 | 0 | 2133.2608 | 2133.2608
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | RE: SUPPORT FOR 2018 OPEN HOUSE (4/14/2018) | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005911 | SUPPORT FOR 2018 OPEN HOUSE - GENERAL | POPHAM, DONALD J. | CONST_COMP | 2018-01-26 | SM: SUPPORT FOR 2018 OPEN HOUSE - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005911 Total | [7 empty] | 0 | 0 | 11792.8122 | 11792.8122
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | AD: MEATHEAD MOVERS | 035 | OPEN | 3306.3 | 0 | 0 | 0
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | AD: STATE FIRE MARSHAL | 035 | OPEN | 535 | 0 | 0 | 0
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | CP: PROJECT CONTINGENCY | 035 | OPEN | 409.63 | 0 | 0 | 0
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | IN: MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | 035 | OPEN | 70.644 | 0 | 0 | 0
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | MO: | 035 | OPEN | 184.338 | 0 | 0 | 0
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | PM: MOVING GLASS EXHIBIT CASES - BLD 35 RM 409 | 035 | OPEN | 0 | 0 | 0 | 0
PJ0005910 | MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | KOLEGRAFF, KENNETH | SCHEDULING | 2018-01-11 | SM: MOVING GLASS EXHIBIT CASES TO - BLD 35 RM 409 | 035 | OPEN | 0 | 0 | 0 | 0
PJ0005910 Total | [7 empty] | 4505.912 | 0 | 0 | 0
PJ0005908 | LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | DUNN, TRAVIS | CONST_COMP | 2017-12-19 | AD: FPCP MANAGEMENT/DESIGN | 042 | CLOSED | 560 | 0 | 560 | 560
PJ0005908 | LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | DUNN, TRAVIS | CONST_COMP | 2017-12-19 | CA: DUNN - LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | 042 | CLOSED | 489.456 | 0 | 111.24 | 111.24
PJ0005908 | LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | DUNN, TRAVIS | CONST_COMP | 2017-12-19 | CP: PROJECT CONTINGENCY | 042 | OPEN | 194 | 0 | 0 | 0
PJ0005908 | LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | DUNN, TRAVIS | CONST_COMP | 2017-12-19 | EL: DUNN - LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | 042 | CLOSED | 1450.4496 | 0 | 430.062 | 430.062
PJ0005908 | LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | DUNN, TRAVIS | CONST_COMP | 2017-12-19 | PM: PUMP INSTALLATION - BLD 42 RM 115 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005908 | LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | DUNN, TRAVIS | CONST_COMP | 2017-12-19 | SM: LAUNDRY CHEMICAL PUMP INSTALLATION - BLD 42 RM 115 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005908 Total | [7 empty] | 2693.9056 | 0 | 1101.302 | 1101.302
PJ0005905 | DM 17/18: LANDSCAPE ENHANCEMENT AT TURF REMOVAL - CAMPUS WIDE | FLEDDERMAN, JUDE | SCOPE_DEV | 2017-12-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005905 | DM 17/18: LANDSCAPE ENHANCEMENT AT TURF REMOVAL - CAMPUS WIDE | FLEDDERMAN, JUDE | SCOPE_DEV | 2017-12-19 | PM: DM 17/18: ENHANCE LANDSCAPE AT TURF REMOVAL - CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005905 | DM 17/18: LANDSCAPE ENHANCEMENT AT TURF REMOVAL - CAMPUS WIDE | FLEDDERMAN, JUDE | SCOPE_DEV | 2017-12-19 | SM: SPACE DATA MANAGEMENT | GENERAL | COMPLETE | 0 | 0 | 0 | 0
PJ0005905 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005904 | DM 17/18: LANDSCAPE ENHANCEMENT - BLDGS 47 & 33 | DILLON, JEFFREY | SCOPE_DEV | 2017-12-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005904 | DM 17/18: LANDSCAPE ENHANCEMENT - BLDGS 47 & 33 | DILLON, JEFFREY | SCOPE_DEV | 2017-12-19 | PM: LANDSCAPE ENHANCEMENT OF 47/33 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005904 | DM 17/18: LANDSCAPE ENHANCEMENT - BLDGS 47 & 33 | DILLON, JEFFREY | SCOPE_DEV | 2017-12-19 | SM: DM 17/18: LANDSCAPE ENHANCEMENT - BLDGS 47 & 33 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005904 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | AD: DECKTECH INC | 001 | OPEN | 39962.36 | 39962.36 | 0 | 39962.36
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | AD: STATE FIRE MARSHAL | 001 | OPEN | 283.55 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | AD: TEIXEIRA WELDING | 001 | OPEN | 20116 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | CA: | 001 | OPEN | 1578.912 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | CP: PROJECT CONTINGENCY | 001 | OPEN | 8269.57 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | CU: PJ5903 - DUNN - DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 894.7296 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | EL:PJ5903 - DUNN - DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 4133.9328 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | IN: DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | 001 | ASSIGNED | 1130.304 | 0 | 70.644 | 70.644
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | LA: PJ5903 - DUNN - DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 760.128 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | LO:PJ5903 - DUNN - DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 7072.2624 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | PA:PJ5903 - DUNN - DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 1209.5808 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | PL:PJ5903 - DUNN - DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 5553.7248 | 0 | 141.888 | 141.888
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | PM: DECK REPLACEMENT ADMIN PROVOST AREA - BLD 1 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005903 | DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | DUNN, TRAVIS | SCHEDULING | 2017-12-19 | SM: DM 17/18: DECK REPLACEMENT- BLD 01 OUTSIDE RM 305A SEE 5833 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005903 Total | [7 empty] | 90965.0544 | 39962.36 | 212.532 | 40174.892
PJ0005902 | DM 17/18: REPAIR/REPL HVAC ECONOMIZERS - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005902 | DM 17/18: REPAIR/REPL HVAC ECONOMIZERS - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | PM: DM 17/18: REPAIR/REPL HVAC ECONOMIZERS - CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005902 | DM 17/18: REPAIR/REPL HVAC ECONOMIZERS - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | SM: DM 17/18: REPAIR/REPL HVAC ECONOMIZERS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005902 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005901 | DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 3757.67 | 0 | 0 | 0
PJ0005901 | DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | CPE: PURCHASE & INSTALL NEW UNIT FOR DANCE STUDIO | GENERAL | OPEN | 26667.648 | 0 | 70.944 | 70.944
PJ0005901 | DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | EL: WIRING FOR NEW DANCE STUDIO UNIT | GENERAL | OPEN | 5452.248 | 0 | 0 | 0
PJ0005901 | DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | PL: GAS FOR NEW DANCE STUDIO UNIT | GENERAL | OPEN | 5456.208 | 0 | 0 | 0
PJ0005901 | DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | PM: AC REPLACEMENTS TO PHASE OUT R22 - CAMPUS-WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005901 | DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | ULM, AARON | SCOPE_DEV | 2017-12-19 | SM: DM 17/18: A/C REPLACEMENTS TO PHASE OUT R22 - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005901 Total | [7 empty] | 41333.774 | 0 | 70.944 | 70.944
PJ0005900 | DM 17/18: ROOF REPAIR GRAPHIC ARTS - BLD 26 | DUNN, TRAVIS | ESTIMATING | 2017-12-19 | CP: PROJECT CONTINGENCY | 026 | OPEN | 0 | 0 | 0 | 0
PJ0005900 | DM 17/18: ROOF REPAIR GRAPHIC ARTS - BLD 26 | DUNN, TRAVIS | ESTIMATING | 2017-12-19 | PM: ROOF REPAIR GRAPHIC ARTS - BLD 26 | 026 | OPEN | 0 | 0 | 0 | 0
PJ0005900 | DM 17/18: ROOF REPAIR GRAPHIC ARTS - BLD 26 | DUNN, TRAVIS | ESTIMATING | 2017-12-19 | SM: DM 17/18: ROOF REPAIR GRAPHIC ARTS - BLD 26 | 026 | OPEN | 0 | 0 | 0 | 0
PJ0005900 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005899 | DM 17/18: EXTERIOR PAINT SCIENCE BLDG - 052 | POLVI, STEVEN | SCHEDULING | 2017-12-19 | CP: PROJECT CONTINGENCY | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005899 | DM 17/18: EXTERIOR PAINT SCIENCE BLDG - 052 | POLVI, STEVEN | SCHEDULING | 2017-12-19 | PM: DM 17/18: EXTERIOR PAINT SCIENCE BLDG - 052 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005899 | DM 17/18: EXTERIOR PAINT SCIENCE BLDG - 052 | POLVI, STEVEN | SCHEDULING | 2017-12-19 | SM : DM 17/18: EXTERIOR PAINT SCIENCE BLDG - 052 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005899 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005897 | CONFERENCE ROOM REMODEL - BLD 01 RM 133 | NORTON, DAVE | SCOPE_DEV | 2017-12-12 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005897 | CONFERENCE ROOM REMODEL - BLD 01 RM 133 | NORTON, DAVE | SCOPE_DEV | 2017-12-12 | PM: CONFERENCE ROOM REMODEL - BLD 01 RM 133 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005897 | CONFERENCE ROOM REMODEL - BLD 01 RM 133 | NORTON, DAVE | SCOPE_DEV | 2017-12-12 | SM: CONFERENCE ROOM REMODEL - BLD 01 RM 133 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005897 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005896 | VENTILATION IN PAINTING STORAGE - BLD 34 RM 145B | PROJECT UNASSIGNED | TRIAGE | 2017-12-06 | CP: PROJECT CONTINGENCY | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005896 | VENTILATION IN PAINTING STORAGE - BLD 34 RM 145B | PROJECT UNASSIGNED | TRIAGE | 2017-12-06 | PM: VENTILATION IN PAINTING STORAGE - BLD 34 RM 145 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005896 | VENTILATION IN PAINTING STORAGE - BLD 34 RM 145B | PROJECT UNASSIGNED | TRIAGE | 2017-12-06 | SM: VENTILATION IN PAINTING STORAGE - BLD 34 RM 145B | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005896 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005895 | VENTILATION ENHANCEMENT/TEMPERATURE - BLD 34 1ST FLR | PROJECT UNASSIGNED | TRIAGE | 2017-12-06 | CP: PROJECT CONTINGENCY | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005895 | VENTILATION ENHANCEMENT/TEMPERATURE - BLD 34 1ST FLR | PROJECT UNASSIGNED | TRIAGE | 2017-12-06 | PM: VENTILATION ENHANCEMENT/TEMPERATURE - BLD 34 RM 168 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005895 | VENTILATION ENHANCEMENT/TEMPERATURE - BLD 34 1ST FLR | PROJECT UNASSIGNED | TRIAGE | 2017-12-06 | SM: VENTILATION ENHANCEMENT/TEMPERATURE - BLD 34 1ST FLR | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005895 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005894 | CLIMATE/HUMIDITY CONTROL FOR GALLERY - BLD 34 RM 171 | PROJECT UNASSIGNED | TRIAGE | 2017-12-13 | CP: PROJECT CONTINGENCY | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005894 | CLIMATE/HUMIDITY CONTROL FOR GALLERY - BLD 34 RM 171 | PROJECT UNASSIGNED | TRIAGE | 2017-12-13 | PM: CLIMATE AND HUMIDITY CONTROL-- BLD 34 RM 171 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005894 | CLIMATE/HUMIDITY CONTROL FOR GALLERY - BLD 34 RM 171 | PROJECT UNASSIGNED | TRIAGE | 2017-12-13 | SM: CLIMATE/HUMIDITY CONTROL FOR GALLERY - BLD 34 RM 171 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005894 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: EARTH SYSTEMS PACIFIC | 065 | OPEN | 2591.54 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: FLOOR CONNECTION | 065 | OPEN | 8178.01 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: FPCP MANAGEMENT/DESIGN | 065 | OPEN | 3500 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: ITS | 065 | OPEN | 11770 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: JOC 16.042 KOERBER | 065 | OPEN | 427619.08 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: MCKENNA ENVIRONMENTAL | 065 | OPEN | 7886.97 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: SIMPLEX GRINNELL | 065 | OPEN | 5350 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | AD: STATE FIRE MARSHAL | 065 | OPEN | 2675 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | ANTS: NECESSARY PROGRAMMING FOR NEW FA DEVICES - KOLEGRAFF | 065 | OPEN | 74.5536 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | CA: | 065 | OPEN | 61.182 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | CP: PROJECT CONTINGENCY | 065 | OPEN | 54925.19 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | EH&S: | 065 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | EL: SUPPORT AND ELECTRICAL SYSTEM INSTALATION - KOLEGRAFF | 065 | OPEN | 59718.3443 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | ES: SUPPORT FOR UU MCC RENOVATION - KOLEGRAFF | 065 | OPEN | 722.304 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | IN: M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | 065 | OPEN | 706.44 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | LO: PROVIDE SUPPORT REPLACE CORES - KOLEGRAFF | 065 | OPEN | 1270.164 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | PA: FULL PAINT FOR RENOVATION BLDG 65 RM 111F - KOLEGRAFF | 065 | OPEN | 6206.916 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | PL: SUPPORT, DEMO, AND INSTALLATION OF NEW PL SYSTEM - KOLEGRAFF | 065 | OPEN | 14350.5329 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | PM: 18/19 ASI M&R -RENOVATE UU MCC - BLD 65 RM 111F | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005893 | M&R ASI 18/19: RENOVATE UU MCC - BLD 65 RM 111F | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-12-05 | SM: 18/19 ASI M&R - RENOVATE UU MCC - BLD 65 RM 111F | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005893 Total | [7 empty] | 607677.0316 | 0 | 0 | 0
PJ0005892 | VILLAGE MARKET MOVE - 171 PCV | DUNN, TRAVIS | SCOPE_DEV | 2017-11-27 | CP: PROJECT CONTINGENCY | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005892 | VILLAGE MARKET MOVE - 171 PCV | DUNN, TRAVIS | SCOPE_DEV | 2017-11-27 | PM: SUMMER 2018 PROJECT PLACEHOLDER - BLD 65 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005892 | VILLAGE MARKET MOVE - 171 PCV | DUNN, TRAVIS | SCOPE_DEV | 2017-11-27 | SM: STARBUCKS (& VILLAGE MARKET) - UU 065 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005892 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005891 | COMPUTER LAB REMODEL - BLD 003 RM 0303 | PROJECT UNASSIGNED | TRIAGE | 2017-10-03 | CP: PROJECT CONTINGENCY | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005891 | COMPUTER LAB REMODEL - BLD 003 RM 0303 | PROJECT UNASSIGNED | TRIAGE | 2017-10-03 | PM: UPGRADE CLASSROOM - BLD 003 RM 0303 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005891 | COMPUTER LAB REMODEL - BLD 003 RM 0303 | PROJECT UNASSIGNED | TRIAGE | 2017-10-03 | SM: COMPUTER LAB REMODEL - BLD 003 RM 0303 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005891 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005890 | SPACE ANALYSIS (DESIGN ONLY) - BLD 01 2ND FLR | NORTON, DAVE | DESIGN | 2017-10-04 | AD: MODE ASSOCIATES | 001 | OPEN | 5885 | 5885 | 0 | 5885
PJ0005890 | SPACE ANALYSIS (DESIGN ONLY) - BLD 01 2ND FLR | NORTON, DAVE | DESIGN | 2017-10-04 | CP: PROJECT CONTINGENCY | 001 | OPEN | 588.5 | 0 | 0 | 0
PJ0005890 | SPACE ANALYSIS (DESIGN ONLY) - BLD 01 2ND FLR | NORTON, DAVE | DESIGN | 2017-10-04 | PM: RENOVATION OF ADMISSIONS AREA - BLD 1 2ND FLOOR | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005890 | SPACE ANALYSIS (DESIGN ONLY) - BLD 01 2ND FLR | NORTON, DAVE | DESIGN | 2017-10-04 | SM: SPACE ANALYSIS (DESIGN ONLY) - BLD 01 2ND FLR | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005890 Total | [7 empty] | 6473.5 | 5885 | 0 | 5885
PJ0005889 | CHASE OFFICE SPACE REMODEL - BLD 115 (BOTH FLRS) | NORTON, DAVE | SCOPE_DEV | 2017-11-28 | CP: PROJECT CONTINGENCY | 115 | OPEN | 0 | 0 | 0 | 0
PJ0005889 | CHASE OFFICE SPACE REMODEL - BLD 115 (BOTH FLRS) | NORTON, DAVE | SCOPE_DEV | 2017-11-28 | PM: SPACE PLANNING FOR CHASE HALL - BLD 115 | 115 | OPEN | 0 | 0 | 0 | 0
PJ0005889 | CHASE OFFICE SPACE REMODEL - BLD 115 (BOTH FLRS) | NORTON, DAVE | SCOPE_DEV | 2017-11-28 | SM: CHASE OFFICE SPACE REMODEL - BLD 115 (BOTH FLRS) | 115 | OPEN | 0 | 0 | 0 | 0
PJ0005889 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005888 | RODEO HAY BARN REPLACEMENT - BLD 77 | ULM, AARON | DESIGN | 2017-11-28 | AD: ENGLEKIRK AND SABOL - SEISMIC PIER REVIEW | 077 | OPEN | 3263.5 | 1631.75 | 1631.75 | 3263.5
PJ0005888 | RODEO HAY BARN REPLACEMENT - BLD 77 | ULM, AARON | DESIGN | 2017-11-28 | AD: M6 - PLAN CHECK | 077 | OPEN | 4280 | 0 | 4280 | 4280
PJ0005888 | RODEO HAY BARN REPLACEMENT - BLD 77 | ULM, AARON | DESIGN | 2017-11-28 | AD: STATE FIRE MARSHAL (NO OVERHEAD) | 077 | OPEN | 0 | 0 | 213.72 | 213.72
PJ0005888 | RODEO HAY BARN REPLACEMENT - BLD 77 | ULM, AARON | DESIGN | 2017-11-28 | CP: PROJECT CONTINGENCY | 077 | OPEN | 0 | 0 | 0 | 0
PJ0005888 | RODEO HAY BARN REPLACEMENT - BLD 77 | ULM, AARON | DESIGN | 2017-11-28 | PM: RODEO HAY BARN REPLACEMENT - BLD 77 | 077 | OPEN | 0 | 0 | 0 | 0
PJ0005888 | RODEO HAY BARN REPLACEMENT - BLD 77 | ULM, AARON | DESIGN | 2017-11-28 | SM: RODEO HAY BARN REPLACEMENT - BLD 77 | 077 | OPEN | 0 | 0 | 0 | 0
PJ0005888 Total | [7 empty] | 7543.5 | 1631.75 | 6125.47 | 7757.22
PJ0005887 | PG&E CYBER SECURITY LAB - BLD 13 RM 202 | PROJECT UNASSIGNED | HOLD | 2017-11-22 | CP: PROJECT CONTINGENCY | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005887 | PG&E CYBER SECURITY LAB - BLD 13 RM 202 | PROJECT UNASSIGNED | HOLD | 2017-11-22 | PM: PG&E CYBER SECURITY LAB - BLD 13 RM 202 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005887 | PG&E CYBER SECURITY LAB - BLD 13 RM 202 | PROJECT UNASSIGNED | HOLD | 2017-11-22 | SM: PG&E CYBER SECURITY LAB - BLD 13 RM 202 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005887 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005886 | FILL IN DOOR, PATCH & PAINT, NEW LIGHTS - BLD 01 RM 310 | NORTON, DAVE | ESTIMATING | 2017-11-08 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005886 | FILL IN DOOR, PATCH & PAINT, NEW LIGHTS - BLD 01 RM 310 | NORTON, DAVE | ESTIMATING | 2017-11-08 | PM: FACELIFT TO ROOM - BLD 1 RM 310 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005886 | FILL IN DOOR, PATCH & PAINT, NEW LIGHTS - BLD 01 RM 310 | NORTON, DAVE | ESTIMATING | 2017-11-08 | SM: FILL IN DOOR, PATCH & PAINT, NEW LIGHTS - BLD 01 RM 310 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005886 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005885 | SP 17/18: DEVELOP WAYFINDING STANDARDS | NORTON, DAVE | SCOPE_DEV | 2017-11-14 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005885 | SP 17/18: DEVELOP WAYFINDING STANDARDS | NORTON, DAVE | SCOPE_DEV | 2017-11-14 | PM: SP17/18 DEVELOP WAYFINDING STANDARDS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005885 | SP 17/18: DEVELOP WAYFINDING STANDARDS | NORTON, DAVE | SCOPE_DEV | 2017-11-14 | SM: SP 17/18: DEVELOP WAYFINDING STANDARDS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005885 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005884 | 2017 HILLSIDE FIRE (TRACK COSTS) | PROJECT UNASSIGNED | TRIAGE | 2017-11-14 | AD: CANNON | GENERAL | OPEN | 0 | 31.3403 | 7431.9097 | 7463.25
PJ0005884 | 2017 HILLSIDE FIRE (TRACK COSTS) | PROJECT UNASSIGNED | TRIAGE | 2017-11-14 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005884 | 2017 HILLSIDE FIRE (TRACK COSTS) | PROJECT UNASSIGNED | TRIAGE | 2017-11-14 | PM: 2017 HILLSIDE FIRE - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005884 | 2017 HILLSIDE FIRE (TRACK COSTS) | PROJECT UNASSIGNED | TRIAGE | 2017-11-14 | SM: 2017 HILLSIDE FIRE (TRACK COSTS) | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005884 Total | [7 empty] | 0 | 31.3403 | 7431.9097 | 7463.25
PJ0005883 | TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-14 | AD: CAL POLY PM FEE | 208U | OPEN | 1050 | 0 | 0 | 0
PJ0005883 | TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-14 | CP: PROJECT CONTINGENCY | 208U | OPEN | 119.13 | 0 | 0 | 0
PJ0005883 | TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-14 | IN: TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | 208U | ASSIGNED | 141.288 | 0 | 70.644 | 70.644
PJ0005883 | TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-14 | PM: MODIFY T-MOBILE ANTENNA - BLD 208U | 208U | OPEN | 0 | 0 | 0 | 0
PJ0005883 | TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-14 | SM: TI: MODIFY T-MOBILE CELL ANTENNA - BLD 208U RADIO HILL | 208U | OPEN | 0 | 0 | 0 | 0
PJ0005883 Total | [7 empty] | 1310.418 | 0 | 70.644 | 70.644
PJ0005881 | TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-09 | AD: CAL POLY PM FEE | 208U | OPEN | 1050 | 0 | 0 | 0
PJ0005881 | TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-09 | CP: PROJECT CONTINGENCY | 208U | OPEN | 119.13 | 0 | 0 | 0
PJ0005881 | TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-09 | IN: TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | 208U | ASSIGNED | 141.288 | 0 | 70.644 | 70.644
PJ0005881 | TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-09 | PM: MODIFY SPRINT ANTENNA - BLD 208U | 208U | OPEN | 0 | 0 | 0 | 0
PJ0005881 | TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-11-09 | SM: TI: MODIFY SPRINT CELL ANTENNA - BLD 208U RADIO HILL | 208U | OPEN | 0 | 0 | 0 | 0
PJ0005881 Total | [7 empty] | 1310.418 | 0 | 70.644 | 70.644
PJ0005880 | OFFICE SPACE REDESIGN - BLD 1 RM 125 | NORTON, DAVE | ESTIMATING | 2017-10-30 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005880 | OFFICE SPACE REDESIGN - BLD 1 RM 125 | NORTON, DAVE | ESTIMATING | 2017-10-30 | PM: OFFICE SPACE REDESIGN - BLD 1 RM 125 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005880 | OFFICE SPACE REDESIGN - BLD 1 RM 125 | NORTON, DAVE | ESTIMATING | 2017-10-30 | SM: OFFICE SPACE REDESIGN - BLD 1 RM 125 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005880 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005878 | M&R ASI 17/18: STRUCTURE CODE ANALYSIS -BLD 65 (DESIGN ONLY) | PROJECT UNASSIGNED | HOLD | 2017-11-07 | AD: PMSM ARCHITECTS | 065 | OPEN | 81855 | 0 | 0 | 0
PJ0005878 | M&R ASI 17/18: STRUCTURE CODE ANALYSIS -BLD 65 (DESIGN ONLY) | PROJECT UNASSIGNED | HOLD | 2017-11-07 | CP: PROJECT CONTINGENCY | 065 | OPEN | 8185.5 | 0 | 0 | 0
PJ0005878 | M&R ASI 17/18: STRUCTURE CODE ANALYSIS -BLD 65 (DESIGN ONLY) | PROJECT UNASSIGNED | HOLD | 2017-11-07 | PM: 17/18 M&R ASI - BLG 65 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005878 | M&R ASI 17/18: STRUCTURE CODE ANALYSIS -BLD 65 (DESIGN ONLY) | PROJECT UNASSIGNED | HOLD | 2017-11-07 | SM: M&R ASI 17/18: STRUCTURE CODE ANALYSIS -BLD 65 (DESIGN ONLY) | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005878 Total | [7 empty] | 90040.5 | 0 | 0 | 0
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | AD: FPCP MANAGEMENT/DESIGN | 002 | OPEN | 450 | 0 | 0 | 0
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | AD: STATE FIRE MARSHAL | 002 | OPEN | 0 | 62.3703 | 0 | 62.3703
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | CA: INSTALL UPS CABINET 02-126A | 002 | CLOSED | 591.456 | 0 | 443.595 | 443.595
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | CP: PROJECT CONTINGENCY | 002 | OPEN | 202.54 | 0 | 0 | 0
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | EL: ADD ELECTRICAL OUTLET 02-126A | 002 | CLOSED | 1433.9328 | 0 | 602.412 | 602.412
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | PM: INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005877 | INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | KUENTZEL, DOUGLAS A. | CONST_COMP | 2017-11-02 | SM: INSTALL ELECTRICAL OUTLET & MOUNT CABINET - BLD 2 RM 126A | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005877 Total | [7 empty] | 2677.9288 | 62.3703 | 1046.007 | 1108.3773
PJ0005876 | INSTALL A/C IN LAB - BLDG 24 RM 104B | ULM, AARON | SCOPE_DEV | 2017-10-23 | CP: PROJECT CONTINGENCY | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005876 | INSTALL A/C IN LAB - BLDG 24 RM 104B | ULM, AARON | SCOPE_DEV | 2017-10-23 | PM: INSTALL AIR CONDITIONING - BLDG 24 RM 104B | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005876 | INSTALL A/C IN LAB - BLDG 24 RM 104B | ULM, AARON | SCOPE_DEV | 2017-10-23 | SM: INSTALL A/C IN LAB - BLDG 24 RM 104B | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005876 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005875 | CREATE CSC/SE OFFICE SPACES IN PORTABLES - BLD 14 | MACDONALD, WENDY | SCOPE_DEV | 2017-10-26 | CP: PROJECT CONTINGENCY | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005875 | CREATE CSC/SE OFFICE SPACES IN PORTABLES - BLD 14 | MACDONALD, WENDY | SCOPE_DEV | 2017-10-26 | PM: PURCHASE & INSTALL CSC/SE OFFICE SPACES - BLD 14 | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005875 | CREATE CSC/SE OFFICE SPACES IN PORTABLES - BLD 14 | MACDONALD, WENDY | SCOPE_DEV | 2017-10-26 | SM: CREATE CSC/SE OFFICE SPACES IN PORTABLES - BLD 14 | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005875 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | AD: CANNON | 042 | OPEN | 19260 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | AD: DIVISION OF STATE ARCHITECT | 042 | OPEN | 1070 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | AD: SLO COUNTY PERMIT FEES | 042 | OPEN | 5885 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | AD: STATE FIRE MARSHAL | 042 | OPEN | 1134.2 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | CP:PROJECT CONTINGENCY | 042 | OPEN | 2734.92 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | PM: GOLF FACILITY ENHANCEMENT@DAIRY CREEK - BLD 42 RM 125A | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005874 | GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | DUNN, TRAVIS | DESIGN | 2017-10-27 | SM: GOLF FACILITY ENHANCEMENT AT DAIRY CREEK - BLD 42 RM 125A | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005874 Total | [7 empty] | 30084.12 | 0 | 0 | 0
PJ0005873 | PURCHASE & INSTALL MEMORIAL BENCHES FOR DUNN & YOUNG BLD 124 & 3 | POPHAM, DONALD J. | CONST_COMP | 2017-10-24 | AD: QUICKRETE | GENERAL | OPEN | 2747.76 | 0 | 2960.7114 | 2960.7114
PJ0005873 | PURCHASE & INSTALL MEMORIAL BENCHES FOR DUNN & YOUNG BLD 124 & 3 | POPHAM, DONALD J. | CONST_COMP | 2017-10-24 | CA: INSTALL PLAQUE ON CONCRETE BENCHES | GENERAL | CLOSED | 244.728 | 0 | 333.72 | 333.72
PJ0005873 | PURCHASE & INSTALL MEMORIAL BENCHES FOR DUNN & YOUNG BLD 124 & 3 | POPHAM, DONALD J. | CONST_COMP | 2017-10-24 | CP: PROJECT CONTINGENCY | 003 | OPEN | 312.46 | 0 | 0 | 0
PJ0005873 | PURCHASE & INSTALL MEMORIAL BENCHES FOR DUNN & YOUNG BLD 124 & 3 | POPHAM, DONALD J. | CONST_COMP | 2017-10-24 | MC: MOVE BENCHES FROM 81 --> CARP SHOP & TOSEMITE | GENERAL | OPEN | 110.6028 | 0 | 36 | 36
PJ0005873 | PURCHASE & INSTALL MEMORIAL BENCHES FOR DUNN & YOUNG BLD 124 & 3 | POPHAM, DONALD J. | CONST_COMP | 2017-10-24 | PM: MEMORIAL BENCH PURCHASE/INSTALL - BLD 3 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005873 | PURCHASE & INSTALL MEMORIAL BENCHES FOR DUNN & YOUNG BLD 124 & 3 | POPHAM, DONALD J. | CONST_COMP | 2017-10-24 | SM: PURCHASE/INSTALL MEM. BENCHES FOR DUNN & YOUNG BLD 124 & 3 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005873 Total | [7 empty] | 3415.5508 | 0 | 3330.4314 | 3330.4314
PJ0005872 | SR 17/18: REPAIR GUTTERS - BLD 18J & 18K | POLVI, STEVEN | CONST_COMP | 2017-10-18 | CA: REPAIR GUTTERS ON FREE STALLS AT DAIRY - BLDG 18J & K | 018 | CLOSED | 2856.642 | 0 | 6487.0106 | 6487.0106
PJ0005872 | SR 17/18: REPAIR GUTTERS - BLD 18J & 18K | POLVI, STEVEN | CONST_COMP | 2017-10-18 | CP: PROJECT CONTINGENCY | 018J | OPEN | 933.34 | 0 | 0 | 0
PJ0005872 | SR 17/18: REPAIR GUTTERS - BLD 18J & 18K | POLVI, STEVEN | CONST_COMP | 2017-10-18 | PL: REPAIR GUTTERS ON FREE STALLS AT DAIRY BLDG 18 J&K | 018 | CLOSED | 6476.5128 | 0 | 3928.2 | 3928.2
PJ0005872 | SR 17/18: REPAIR GUTTERS - BLD 18J & 18K | POLVI, STEVEN | CONST_COMP | 2017-10-18 | PM: REPAIR GUTTERS - BLD 18J & 18K | 018J | CLOSED | 0 | 0 | 0 | 0
PJ0005872 | SR 17/18: REPAIR GUTTERS - BLD 18J & 18K | POLVI, STEVEN | CONST_COMP | 2017-10-18 | SM: SR 17/18: REPAIR GUTTERS - BLD 18J & 18K | 018 | OPEN | 0 | 0 | 0 | 0
PJ0005872 Total | [7 empty] | 10266.4948 | 0 | 10415.2106 | 10415.2106
PJ0005871 | TI: MODIFY T-MOBILE (CROWN) CELL ANTENNA - R01 PARKING LOT | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-10-18 | CP: PROJECT CONTINGENCY | P-R01 | OPEN | 0 | 0 | 0 | 0
PJ0005871 | TI: MODIFY T-MOBILE (CROWN) CELL ANTENNA - R01 PARKING LOT | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-10-18 | PM: MODIFY T-MOBILE ANTENNA - P-R01 | P-R01 | OPEN | 0 | 0 | 0 | 0
PJ0005871 | TI: MODIFY T-MOBILE (CROWN) CELL ANTENNA - R01 PARKING LOT | KUENTZEL, DOUGLAS A. | SCHEDULING | 2017-10-18 | SM: TI: MODIFY T-MOBILE (CROWN) CELL ANTENNA - R01 PARKING LOT | P-R01 | OPEN | 0 | 0 | 0 | 0
PJ0005871 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | AD: FPCP CONTRACT OVERSIGHT | 006 | OPEN | 1680.05 | 0 | 1400.04 | 1400.04
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | AD: INTERTEK | 006 | CLOSED | 1444.5 | 0 | 1444.5 | 1444.5
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | AD: STATE FIRE MARSHAL | 006 | OPEN | 535 | 0 | 73.509 | 73.509
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | CP: PROJECT CONTINGENCY | 006 | OPEN | 251.32 | 0 | 0 | 0
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | EH&S: | 006 | OPEN | 257.472 | 0 | 0 | 0
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | IN: CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | 006 | CLOSED | 423.864 | 0 | 317.898 | 317.898
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | LO: | 006 | CLOSED | 182.772 | 0 | 121.848 | 121.848
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | PM: CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005870 | CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | ULM, AARON | CONST_COMP | 2017-10-16 | SM: CERTIFY OVERSIZED DOOR - BLD 6 RM 11 | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005870 Total | [7 empty] | 4774.978 | 0 | 3357.795 | 3357.795
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: CT/A-TOWN | 013 | OPEN | 1000 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: FPCP MANAGEMENT/DESIGN | 013 | OPEN | 2800 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: ITS | 013 | OPEN | 1271 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: NEW STUDENT DESK AND FACULTY DESK | 013 | OPEN | 7958.17 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: STATE FIRE MARSHAL | 013 | OPEN | 250 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: WHITEBOARDS | 013 | OPEN | 3600 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | AD: WINDOW TREATMENT | 013 | OPEN | 3030 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | CA: | 013 | OPEN | 7761.84 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | CP: PROJECT CONTINGENCY | 013 | OPEN | 3552.85 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | CU: | 013 | OPEN | 736.824 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | EL: | 013 | OPEN | 2720.8992 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | IN: FLIP CLASSROOM - BLD 13 RM 109 | 013 | ASSIGNED | 388.542 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | LO: | 013 | OPEN | 1136.1312 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | MO: | 013 | OPEN | 553.014 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | PA: | 013 | OPEN | 3923.952 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | PM: FLIP CLASSROOM - BLD 13 RM 109 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005869 | FLIP CLASSROOM - BLD 13 RM 109 | BROWN, CARLA | SCHEDULING | 2017-10-09 | SM: FLIP CLASSROOM - BLD 13 RM 109 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005869 Total | [7 empty] | 40683.2224 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: A-TOWN AUDIO | 061 | OPEN | 267500 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: CANNON ENGINEERING | 061 | OPEN | 36380 | 246.1 | 31853.9 | 32100
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: ENGLEKIRK & SABOL | 061 | OPEN | 535 | 0 | 535 | 535
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: JOC 16.041.5868 MAINO | 061 | OPEN | 24092.5908 | 23631.7739 | 460.8169 | 24092.5908
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: PRINTING & SHIPPING PROJECT PLANS | 061 | OPEN | 267.5 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: QUAGLINO ROOFING | 061 | OPEN | 428 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: SOWDEN & ASSOCIATES | 061 | OPEN | 35310 | 16906 | 17334 | 34240
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | AD: STATE FIRE MARSHAL | 061 | OPEN | 1070 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | CA: SPANOS STADIUM PROJECT | 061 | ASSIGNED | 5101.464 | 0 | 367.128 | 367.128
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | CP: PROJECT CONTINGENCY | 061 | OPEN | 29009.06 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | EL: INSTALL ELECTRICAL AT SPANOS STADIUM | 061 | LONG_TERM | 28950.1259 | 0 | 10537.158 | 10537.158
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | IN: SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | 061 | ASSIGNED | 777.084 | 0 | 70.644 | 70.644
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | PA SUPPLY PAINT FOR CONTRACTOR'S USE | 061 | ASSIGNED | 420 | 0 | 244.116 | 244.116
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | PM: SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005868 | SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | ULM, AARON | IN_CONSTR | 2017-10-11 | SM: SR 17/18: SPANOS SOUND SYS SPEAKERS - BLDG 61 | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005868 Total | [7 empty] | 429840.8247 | 40783.8739 | 61402.7629 | 102186.6368
PJ0005867 | SR 18/19: CLASSROOM REFRESH - BLD 10 RMS 124,125,126 | NORTON, DAVE | SCOPE_DEV | 2017-10-06 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005867 | SR 18/19: CLASSROOM REFRESH - BLD 10 RMS 124,125,126 | NORTON, DAVE | SCOPE_DEV | 2017-10-06 | PM: SR 18/19: CLASSROOM REFRESH - BLD 10 RMS 124,125,126 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005867 | SR 18/19: CLASSROOM REFRESH - BLD 10 RMS 124,125,126 | NORTON, DAVE | SCOPE_DEV | 2017-10-06 | SM: SR 18/19: CLASSROOM REFRESH - BLD 10 RMS 124,125,126 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005867 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005866 | MASTER PLAN CAL POLY PIER - BLD 228 (DESIGN ONLY) | ULM, AARON | DESIGN | 2017-10-03 | CP: PROJECT CONTINGENCY | 228 | OPEN | 0 | 0 | 0 | 0
PJ0005866 | MASTER PLAN CAL POLY PIER - BLD 228 (DESIGN ONLY) | ULM, AARON | DESIGN | 2017-10-03 | PM: MASTER PLAN CAL POLY PIER - BLD 228 (DESIGN ONLY) | 228 | OPEN | 0 | 0 | 0 | 0
PJ0005866 | MASTER PLAN CAL POLY PIER - BLD 228 (DESIGN ONLY) | ULM, AARON | DESIGN | 2017-10-03 | SM: MASTER PLAN CAL POLY PIER - BLD 228 (DESIGN ONLY) | 228 | OPEN | 0 | 0 | 0 | 0
PJ0005866 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005864 | SITE PREPARATION FOR STEEL SHIPPING CONTAINER - BLD 27 | PROJECT UNASSIGNED | HOLD | 2017-09-26 | CP: PROJECT CONTINGENCY | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005864 | SITE PREPARATION FOR STEEL SHIPPING CONTAINER - BLD 27 | PROJECT UNASSIGNED | HOLD | 2017-09-26 | PM: SITE PREPARATION FOR STEEL SHIPPING CONTAINER - BLD 27 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005864 | SITE PREPARATION FOR STEEL SHIPPING CONTAINER - BLD 27 | PROJECT UNASSIGNED | HOLD | 2017-09-26 | SM: SITE PREPARATION FOR STEEL SHIPPING CONTAINER - BLD 27 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005864 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005863 | MJ: IN HOUSE SUPPORT: GOLD TREE SOLAR PROJECT | SODERIN, ERIC | IN_CONSTR | 2017-09-29 | CP: PROJECT CONTINGENCY | 400 | OPEN | 7500 | 0 | 0 | 0
PJ0005863 | MJ: IN HOUSE SUPPORT: GOLD TREE SOLAR PROJECT | SODERIN, ERIC | IN_CONSTR | 2017-09-29 | EL: SUPPORT FOR GOLD TREE SOLAR FARM PROJECT | 400 | LONG_TERM | 0 | 0 | 1088.844 | 1088.844
PJ0005863 | MJ: IN HOUSE SUPPORT: GOLD TREE SOLAR PROJECT | SODERIN, ERIC | IN_CONSTR | 2017-09-29 | PL: SUPPORT FOR GOLD TREE SOLAR FARM PROJECT | 400 | ASSIGNED | 0 | 0 | 99.96 | 99.96
PJ0005863 | MJ: IN HOUSE SUPPORT: GOLD TREE SOLAR PROJECT | SODERIN, ERIC | IN_CONSTR | 2017-09-29 | SM: MJ: IN HOUSE SUPPORT: GOLD TREE SOLAR PROJECT | 400 | OPEN | 0 | 0 | 0 | 0
PJ0005863 Total | [7 empty] | 7500 | 0 | 1188.804 | 1188.804
PJ0005862 | CONVERT 235B/C INTO TWO OFFICES - BLD 14 RM 235B | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-09-20 | CP: PROJECT CONTINGENCY | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005862 | CONVERT 235B/C INTO TWO OFFICES - BLD 14 RM 235B | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-09-20 | PM: CONVERT 235B/C INTO TWO OFFICES - BLD 14 RM 235B | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005862 | CONVERT 235B/C INTO TWO OFFICES - BLD 14 RM 235B | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-09-20 | SM: CONVERT 235B/C INTO TWO OFFICES - BLD 14 RM 235B | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005862 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | AD: (SL543) ITS- DATA | 070 | OPEN | 984.4 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | AD: (SL543) PROJECT MANAGEMENT/DESIGN | 070 | OPEN | 300 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | AD: (SL543) TRI COUNTY | 070 | OPEN | 1282.54 | 951.3263 | 0 | 951.3263
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | AD: ITS | 070 | OPEN | 267.5 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | AD: STATE FIRE MARSHAL | 070 | OPEN | 278.2 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | AD: TRI COUNTY OFFICE FURNITURE | 070 | OPEN | 14631.5866 | 0 | 14631.5866 | 14631.5866
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | CA: DIASSEMBLE FURNITURE- BLDG 70-104 | 070 | CLOSED | 636.81 | 0 | 625.278 | 625.278
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | CP: PROJECT CONTINGENCY | 070 | OPEN | 1947.89 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | CU: | 070 | OPEN | 147.3648 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | EL:(SL543) INSTALL POWER TO NEW DESK- 70-107 | 070 | CLOSED | 926.9664 | 0 | 225.498 | 225.498
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | IN: OFFICE FURNITURE- BLD 70 RM 201 | 070 | ASSIGNED | 141.288 | 0 | 70.644 | 70.644
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | LO: | 070 | OPEN | 67.0164 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | MO: REMOVE FURNITURE FROM BLDG 70-104 | 070 | CLOSED | 221.2056 | 0 | 174 | 174
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | PA: BLDG 70-201,203,104- PAINT TOUCH UP | 070 | CLOSED | 2319.642 | 0 | 2293.854 | 2293.854
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | PM: RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005860 | RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | NORTON, DAVE | IN_CONSTR | 2017-09-20 | SM: RELOCATE STAFF & RENOVATE OFFICES- BLD 70 RMS. 104, 201, 203 | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005860 Total | [7 empty] | 24152.4098 | 951.3263 | 18020.8606 | 18972.1869
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | AD: FASULO DRYWALL | 001 | OPEN | 3638 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | AD: FLOOR CONNECTION | 001 | OPEN | 12736.21 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | AD: FPCP DESIGN | 001 | OPEN | 1500 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | AD: ITS DATA WORK | 001 | OPEN | 6259.5 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | AD: STATE FIRE MARSHAL | 001 | OPEN | 642 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | AD: TRI COUNTY OFFICE | 001 | OPEN | 56282 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | ANTS: BLDG 1-128/129 SBS REMODEL- RELOCATE PHONES AND COMPUTERS | 001 | OPEN | 1800 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | CA: BLDG 1-128 DEMO AND NEW CONSTRUCTION FOR OFFICE REMODEL | 001 | ASSIGNED | 20522.0922 | 0 | 11512.4803 | 11512.4803
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | CP: PROJECT CONTINGENCY | 001 | OPEN | 12127.41 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | CU: | 001 | OPEN | 736.824 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | EL: BLDG 1-128/129 SBS REMODEL- ELECT PER NEW PLAN LAYOUT | 001 | LONG_TERM | 15556.9103 | 0 | 1111.392 | 1111.392
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | ES: BLDG 1-128/129 SBS REMODEL- RELOCATE T-STAT, SUPPLY AND RETU | 001 | ASSIGNED | 817.8432 | 0 | 819.036 | 819.036
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | IN: SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | 001 | ASSIGNED | 388.542 | 0 | 141.288 | 141.288
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | LO: BLDG 1-128 SBS REMODEL- REMOVE LOCK- 128I | 001 | ASSIGNED | 67.0164 | 0 | 91.386 | 91.386
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | MO: BLDG 1-128/129 SBS REMODEL- MOVE FURNITURE | 001 | OPEN | 1106.028 | 0 | 204 | 204
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | PM: SP 17/18 RENOVATE STRATEGIC BUS SVC - BLD 1 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | 001 | ASSIGNED | 4958.3232 | 0 | 2289.684 | 2289.684
PJ0005859 | SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | NORTON, DAVE | IN_CONSTR | 2017-09-19 | SM: SP 17/18: RENOVATE STRATEGIC BUS SVC - BLD 1 RM 128 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005859 Total | [7 empty] | 139138.6993 | 0 | 16169.2663 | 16169.2663
PJ0005858 | EMERGENCY EXIT SIGNAGE - CAMPUS WIDE (NO OVERHEAD) FAC_OPS | MACDONALD, WENDY | PUNCH_LIST | 2017-09-19 | AD: SRB TECHNOLOGIES | GENERAL | OPEN | 38150 | 0 | 0 | 0
PJ0005858 | EMERGENCY EXIT SIGNAGE - CAMPUS WIDE (NO OVERHEAD) FAC_OPS | MACDONALD, WENDY | PUNCH_LIST | 2017-09-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 1907.5 | 0 | 0 | 0
PJ0005858 | EMERGENCY EXIT SIGNAGE - CAMPUS WIDE (NO OVERHEAD) FAC_OPS | MACDONALD, WENDY | PUNCH_LIST | 2017-09-19 | PM: EMERGENCY EXIT SIGNAGE - CAMPUS WIDE | GENERAL | WORKING | 0 | 0 | 0 | 0
PJ0005858 | EMERGENCY EXIT SIGNAGE - CAMPUS WIDE (NO OVERHEAD) FAC_OPS | MACDONALD, WENDY | PUNCH_LIST | 2017-09-19 | SM: EMERGENCY EXIT SIGNAGE - CAMPUS WIDE (NO OVERHEAD) FAC_OPS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005858 Total | [7 empty] | 40057.5 | 0 | 0 | 0
PJ0005857 | SP 17/18: FIRE/LIFE SAFETY TESTING & INSPECTIONS | MACDONALD, WENDY | SCOPE_DEV | 2017-09-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005857 | SP 17/18: FIRE/LIFE SAFETY TESTING & INSPECTIONS | MACDONALD, WENDY | SCOPE_DEV | 2017-09-19 | PM: SP 17/18: FIRE/LIFE SAFETY TESTING & INSPECTIONS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005857 | SP 17/18: FIRE/LIFE SAFETY TESTING & INSPECTIONS | MACDONALD, WENDY | SCOPE_DEV | 2017-09-19 | SM: SP 17/18: FIRE/LIFE SAFETY TESTING & INSPECTIONS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005857 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005856 | OFFICE SPACE PLAN - BLD 38 RM 215 | NORTON, DAVE | SCOPE_DEV | 2017-09-19 | CP: PROJECT CONTINGENCY | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005856 | OFFICE SPACE PLAN - BLD 38 RM 215 | NORTON, DAVE | SCOPE_DEV | 2017-09-19 | PM: SPACE LAYOUT PLAN - BLD 38 RM 215 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005856 | OFFICE SPACE PLAN - BLD 38 RM 215 | NORTON, DAVE | SCOPE_DEV | 2017-09-19 | SM: OFFICE SPACE PLAN - BLD 38 RM 215 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005856 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | AD: GOSS ENG | 082 | OPEN | 23128.05 | 23128.05 | 0 | 23128.05
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | AD: PRINTING & SHIPPPING | 082 | OPEN | 160.5 | 0 | 0 | 0
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | AD: REA LUCKER ARCH | 082 | OPEN | 31939.5 | 31939.5 | 0 | 31939.5
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | AD: STATE FIRE MARSHAL | 082 | OPEN | 535 | 0 | 0 | 0
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | CP: PROJECT CONTINGENCY | 082 | OPEN | 5578.26 | 0 | 0 | 0
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | PM: RENOVATE FOR ITS - BLD 82 | 082 | OPEN | 0 | 0 | 0 | 0
PJ0005854 | RENOVATE FOR ITS - BLD 82 | DILLON, JEFFREY | APPR_PEND | 2017-09-11 | SM: RENOVATE FOR ITS - BLD 82 | 082 | OPEN | 0 | 0 | 0 | 0
PJ0005854 Total | [7 empty] | 61341.31 | 55067.55 | 0 | 55067.55
PJ0005853 | CREATE BEACH VOLLEYBALL LOCKER ROOM - BLD 42 RM 120 | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-09-06 | CP: PROJECT CONTINGENCY | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005853 | CREATE BEACH VOLLEYBALL LOCKER ROOM - BLD 42 RM 120 | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-09-06 | PM: CREATE BEACH VOLLEYBALL LOCKER ROOM - BLD 42 RM 120 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005853 | CREATE BEACH VOLLEYBALL LOCKER ROOM - BLD 42 RM 120 | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-09-06 | SM: CREATE BEACH VOLLEYBALL LOCKER ROOM - BLD 42 RM 120 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005853 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005852 | PROVIDE UTILITIES CONNECTIONS - BLD 13 RM 125 | BROWN, CARLA | ESTIMATING | 2017-08-30 | CP: PROJECT CONTINGENCY | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005852 | PROVIDE UTILITIES CONNECTIONS - BLD 13 RM 125 | BROWN, CARLA | ESTIMATING | 2017-08-30 | PM: PROVIDE UTILITIES CONNECTIONS - BLD 13 RM 125 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005852 | PROVIDE UTILITIES CONNECTIONS - BLD 13 RM 125 | BROWN, CARLA | ESTIMATING | 2017-08-30 | SM: PROVIDE UTILITIES CONNECTIONS - BLD 13 RM 125 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005852 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005851 | VARIABLE FLOW HOT WATER PUMPING RETROFITS - CAMPUS WIDE | ULM, AARON | DESIGN | 2017-09-06 | AD: (GD005) GOSS ENGINEERING | GENERAL | OPEN | 41462.5 | 41462.5 | 0 | 41462.5
PJ0005851 | VARIABLE FLOW HOT WATER PUMPING RETROFITS - CAMPUS WIDE | ULM, AARON | DESIGN | 2017-09-06 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 4146.25 | 0 | 0 | 0
PJ0005851 | VARIABLE FLOW HOT WATER PUMPING RETROFITS - CAMPUS WIDE | ULM, AARON | DESIGN | 2017-09-06 | PM: VARIABLE FLOW HOT WATER PUMPING RETROFITS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005851 | VARIABLE FLOW HOT WATER PUMPING RETROFITS - CAMPUS WIDE | ULM, AARON | DESIGN | 2017-09-06 | SM: VARIABLE FLOW HOT WATER PUMPING RETROFITS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005851 Total | [7 empty] | 45608.75 | 41462.5 | 0 | 41462.5
PJ0005849 | INSTALL A/C IN DEAN'S SUITE - BLD 47 RM 31A | ULM, AARON | SCOPE_DEV | 2017-08-31 | CP: PROJECT CONTINGENCY | 047 | OPEN | 0 | 0 | 0 | 0
PJ0005849 | INSTALL A/C IN DEAN'S SUITE - BLD 47 RM 31A | ULM, AARON | SCOPE_DEV | 2017-08-31 | PM: INSTALL A/C UNIT - BLD 47 RM 31A | 047 | OPEN | 0 | 0 | 0 | 0
PJ0005849 | INSTALL A/C IN DEAN'S SUITE - BLD 47 RM 31A | ULM, AARON | SCOPE_DEV | 2017-08-31 | SM: INSTALL A/C IN DEAN'S SUITE - BLD 47 RM 31A | 047 | OPEN | 0 | 0 | 0 | 0
PJ0005849 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005847 | PIGEON/BIRD REMEDIATION 2017 - BLDGS 5, 21, 35, & 41 | FLEDDERMAN, JUDE | CONST_COMP | 2017-08-23 | AD: AVIARY MANAGMENT PROFESSIONALS | GENERAL | CLOSED | 39055 | 0 | 39055 | 39055
PJ0005847 | PIGEON/BIRD REMEDIATION 2017 - BLDGS 5, 21, 35, & 41 | FLEDDERMAN, JUDE | CONST_COMP | 2017-08-23 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 3931.27 | 0 | 0 | 0
PJ0005847 | PIGEON/BIRD REMEDIATION 2017 - BLDGS 5, 21, 35, & 41 | FLEDDERMAN, JUDE | CONST_COMP | 2017-08-23 | EL: ELECTRICAL CLEARANCE FOR 21-116 TROLLY | GENERAL | CLOSED | 257.712 | 0 | 32.214 | 32.214
PJ0005847 | PIGEON/BIRD REMEDIATION 2017 - BLDGS 5, 21, 35, & 41 | FLEDDERMAN, JUDE | CONST_COMP | 2017-08-23 | SM: PIGEON/BIRD REMEDIATION 2017 - BLDGS 5, 21, 35, & 41 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005847 Total | [7 empty] | 43243.982 | 0 | 39087.214 | 39087.214
PJ0005846 | DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | ULM, AARON | DESGN_COMP | 2017-06-09 | AD: FPCP CONTRACT OVERSIGHT | 006 | OPEN | 874.99 | 0 | 874.99 | 874.99
PJ0005846 | DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | ULM, AARON | DESGN_COMP | 2017-06-09 | AD: STATE FIRE MARSHAL | 006 | CLOSED | 135.8793 | 0 | 135.8793 | 135.8793
PJ0005846 | DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | ULM, AARON | DESGN_COMP | 2017-06-09 | CP: PROJECT CONTINGENCY | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005846 | DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | ULM, AARON | DESGN_COMP | 2017-06-09 | IN: DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | 006 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005846 | DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | ULM, AARON | DESGN_COMP | 2017-06-09 | PM: CHANGE THE DESIGNATED USE OF - BLD 006 RM 17 | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005846 | DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | ULM, AARON | DESGN_COMP | 2017-06-09 | SM: DESIGN: CHANGE OF USE/WELDING & FAB - BLD 006 RM 17 | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005846 Total | [7 empty] | 1152.1573 | 0 | 1152.1573 | 1152.1573
PJ0005844 | REFURBISH SOE TECHNOLOGY LAB - BLD 2 RM 114 | BROWN, CARLA | ESTIMATING | 2017-08-16 | CP: PROJECT CONTINGENCY | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005844 | REFURBISH SOE TECHNOLOGY LAB - BLD 2 RM 114 | BROWN, CARLA | ESTIMATING | 2017-08-16 | PM: REFURBISH SOE TECHNOLOGY LAB - BLD 2 RM 114 | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005844 | REFURBISH SOE TECHNOLOGY LAB - BLD 2 RM 114 | BROWN, CARLA | ESTIMATING | 2017-08-16 | SM: REFURBISH SOE TECHNOLOGY LAB - BLD 2 RM 114 | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005844 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005843 | LANDSCAPE DESIGN STANDARDS - GENERAL | PALAZZO, ANTHONY | SCOPE_DEV | 2017-08-16 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005843 | LANDSCAPE DESIGN STANDARDS - GENERAL | PALAZZO, ANTHONY | SCOPE_DEV | 2017-08-16 | PM: LANDSCAPE DESIGNS STANDARDS PROJECT - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005843 | LANDSCAPE DESIGN STANDARDS - GENERAL | PALAZZO, ANTHONY | SCOPE_DEV | 2017-08-16 | SM: LANDSCAPE DESIGN STANDARDS - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005843 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005840 | CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | NORTON, DAVE | HOLD | 2017-07-20 | CA: REMOVE SIGNAGE- BLDG 81 | 081 | CLOSED | 183.546 | 0 | 305.94 | 305.94
PJ0005840 | CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | NORTON, DAVE | HOLD | 2017-07-20 | CP: PROJECT CONTINGENCY | 081 | OPEN | 51.85 | 0 | 0 | 0
PJ0005840 | CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | NORTON, DAVE | HOLD | 2017-07-20 | IN: CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | 081 | ASSIGNED | 70.644 | 0 | 70.644 | 70.644
PJ0005840 | CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | NORTON, DAVE | HOLD | 2017-07-20 | PA: PATCH WALL- BLDG 81 | 081 | CLOSED | 264.2964 | 0 | 61.908 | 61.908
PJ0005840 | CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | NORTON, DAVE | HOLD | 2017-07-20 | PM: REMOVE SIGNAGE- BLD 81 | 081 | OPEN | 0 | 0 | 0 | 0
PJ0005840 | CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | NORTON, DAVE | HOLD | 2017-07-20 | SM: CREATE & INSTALL EXTERIOR DEPARTMENT SIGN - BLD 81 | 081 | OPEN | 0 | 0 | 0 | 0
PJ0005840 Total | [7 empty] | 570.3364 | 0 | 438.492 | 438.492
PJ0005839 | RE- ARRANGE DIRECTION OF CLASSROOM - BLD 192 RM 120 | BROWN, CARLA | SCOPE_DEV | 2017-08-08 | CP: PROJECT CONTINGENCY | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005839 | RE- ARRANGE DIRECTION OF CLASSROOM - BLD 192 RM 120 | BROWN, CARLA | SCOPE_DEV | 2017-08-08 | PM: REARRANGE DIRECTION OF CLASSROOM - BLD 192 RM 120 | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005839 | RE- ARRANGE DIRECTION OF CLASSROOM - BLD 192 RM 120 | BROWN, CARLA | SCOPE_DEV | 2017-08-08 | SM: RE- ARRANGE DIRECTION OF CLASSROOM - BLD 192 RM 120 | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005839 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005838 | SR 17/18: LEAK REPAIRS - BLDG 43A | ULM, AARON | TO_CANCEL | 2017-08-04 | CP: PROJECT CONTINGENCY | 043A | OPEN | 0 | 0 | 0 | 0
PJ0005838 | SR 17/18: LEAK REPAIRS - BLDG 43A | ULM, AARON | TO_CANCEL | 2017-08-04 | PM: LEAK REPAIRS - BLDG 43A | 043A | OPEN | 0 | 0 | 0 | 0
PJ0005838 | SR 17/18: LEAK REPAIRS - BLDG 43A | ULM, AARON | TO_CANCEL | 2017-08-04 | SM: SR 17/18: LEAK REPAIRS - BLDG 43A | 043A | OPEN | 0 | 0 | 0 | 0
PJ0005838 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005837 | INSTALL DIGITAL SIGNAGE - BLD 13 RM 113, 117, 266 (SEE 5620)) | BROWN, CARLA | APPR_PEND | 2017-07-28 | CP: PROJECT CONTINGENCY | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005837 | INSTALL DIGITAL SIGNAGE - BLD 13 RM 113, 117, 266 (SEE 5620)) | BROWN, CARLA | APPR_PEND | 2017-07-28 | PM: INSTALL DIGITAL SIGNAGE - BLD 13 RM 117, 113, 266 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005837 | INSTALL DIGITAL SIGNAGE - BLD 13 RM 113, 117, 266 (SEE 5620)) | BROWN, CARLA | APPR_PEND | 2017-07-28 | SM: INSTALL DIGITAL SIGNAGE - BLD 13 RM 113, 117, 266 (SEE 5620) | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005837 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005836 | SEAL COATING PARKING LOT - CAL POLY PIER - BLD 228 | ULM, AARON | CONST_COMP | 2017-08-02 | AD: KNOW HOW | 228 | CLOSED | 2407.5 | 0 | 2407.5 | 2407.5
PJ0005836 | SEAL COATING PARKING LOT - CAL POLY PIER - BLD 228 | ULM, AARON | CONST_COMP | 2017-08-02 | CP: PROJECT CONTINGENCY | 228 | OPEN | 240.75 | 0 | 0 | 0
PJ0005836 | SEAL COATING PARKING LOT - CAL POLY PIER - BLD 228 | ULM, AARON | CONST_COMP | 2017-08-02 | PM: SEAL COATING PARKING LOT - CAL POLY PIER - BLD 228 | 228 | CLOSED | 0 | 0 | 0 | 0
PJ0005836 | SEAL COATING PARKING LOT - CAL POLY PIER - BLD 228 | ULM, AARON | CONST_COMP | 2017-08-02 | SM: SEAL COATING PARKING LOT - CAL POLY PIER - BLD 228 | 228 | OPEN | 0 | 0 | 0 | 0
PJ0005836 Total | [7 empty] | 2648.25 | 0 | 2407.5 | 2407.5
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: COLLINGS & ASSOC | 050L | OPEN | 1498 | 0 | 1498 | 1498
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: DSA | 050L | OPEN | 1070 | 0 | 1070 | 1070
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: ENGLEKIRK | 050L | OPEN | 1348.2 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: M6 CONSULTANTS | 050L | OPEN | 4280 | 1070 | 3210 | 4280
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: MAINO JOC | 050L | OPEN | 0 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: MOVE EL SHOP MATERIALS TO NEW LOCATION | 050L | OPEN | 0 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: PMSM ARCHITECTS | 050L | OPEN | 42800 | 13690.65 | 23063.85 | 36754.5
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: SOIL ENGINEER | 050L | OPEN | 2675 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: STATE FIRE MARSHAL | 050L | OPEN | 1070 | 0 | 413.555 | 413.555
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | AD: WILLDAN | 050L | OPEN | 2140 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | CP: PROJECT CONTINGENCY | 050L | OPEN | 494733.32 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | EL: LOCATE UNDERGROUND ELECTRICAL FEED FROM TRANSFORMER | 050L | CLOSED | 8343.54 | 0 | 64.428 | 64.428
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | IN: PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | 050L | ASSIGNED | 706.44 | 0 | 105.966 | 105.966
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | LO: | 050L | OPEN | 2068.0656 | 0 | 335.082 | 335.082
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | PL: ROSE FLOAT SUPPORT | 050L | LONG_TERM | 709.368 | 0 | 64.488 | 64.488
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | PM: SOLAR DECATHLON PLACEMENT - BLD 50L | 050L | OPEN | 0 | 0 | 0 | 0
PJ0005835 | PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | ULM, AARON | DESIGN | 2017-08-03 | SM: PLACE MODULAR OFFICE NEAR ROSE FLOAT TRAILER - 50L | 050L | OPEN | 0 | 0 | 0 | 0
PJ0005835 Total | [7 empty] | 563441.9336 | 14760.65 | 29825.369 | 44586.019
PJ0005834 | CONVERT INTO OFFICE SPACE - BLD 10 RM 138 | BROWN, CARLA | HOLD | 2017-07-27 | CP: PROJECT CONTINGENCY | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005834 | CONVERT INTO OFFICE SPACE - BLD 10 RM 138 | BROWN, CARLA | HOLD | 2017-07-27 | PM: CONVERT INTO OFFICE SPACE - BLD 10 RM 138 | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005834 | CONVERT INTO OFFICE SPACE - BLD 10 RM 138 | BROWN, CARLA | HOLD | 2017-07-27 | SM: CONVERT INTO OFFICE SPACE - BLD 10 RM 138 | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005834 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005832 | REMODEL/UPGRADE FACULTY OFFICE - BLD 2 RM 215/215A | BROWN, CARLA | APPR_PEND | 2017-07-05 | CP: PROJECT CONTINGENCY | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005832 | REMODEL/UPGRADE FACULTY OFFICE - BLD 2 RM 215/215A | BROWN, CARLA | APPR_PEND | 2017-07-05 | PM: REMODEL/UPGRADE PT FAC OFFICE - BLD 2 RM 215/215A | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005832 | REMODEL/UPGRADE FACULTY OFFICE - BLD 2 RM 215/215A | BROWN, CARLA | APPR_PEND | 2017-07-05 | SM: REMODEL/UPGRADE FACULTY OFFICE - BLD 2 RM 215/215A | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005832 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005831 | INSTALL LAB EQUIP STANDBY GENERATOR - BLD 33 | KOLEGRAFF, KENNETH | TO_CANCEL | 2017-07-14 | CP: PROJECT CONTINGENCY | 033 | OPEN | 0 | 0 | 0 | 0
PJ0005831 | INSTALL LAB EQUIP STANDBY GENERATOR - BLD 33 | KOLEGRAFF, KENNETH | TO_CANCEL | 2017-07-14 | PM: INSTALL LAB EQUIP BACKUP GENERATOR - BLD 33 | 033 | OPEN | 0 | 0 | 0 | 0
PJ0005831 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005829 | SR 17/18: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE III | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-07-24 | AD: HORIZON IRRIGATION | GENERAL | OPEN | 34630.3039 | 0 | 35158.6913 | 35158.6913
PJ0005829 | SR 17/18: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE III | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-07-24 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 3463.03 | 0 | 0 | 0
PJ0005829 | SR 17/18: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE III | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-07-24 | SM: SR 17/18: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE III | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005829 Total | [7 empty] | 38093.3339 | 0 | 35158.6913 | 35158.6913
PJ0005827 | SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | BROWN, CARLA | CONST_COMP | 2017-07-18 | CA: BROWN - PJ5827 SMOKE & TOBACCO FREE CAMPUS | GENERAL | CLOSED | 8933.4 | 0 | 5885.916 | 5885.916
PJ0005827 | SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | BROWN, CARLA | CONST_COMP | 2017-07-18 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 1204.33 | 0 | 0 | 0
PJ0005827 | SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | BROWN, CARLA | CONST_COMP | 2017-07-18 | MO: BROWN - PJ5827 SMOKE & TOBACCO FREE CAMPUS | GENERAL | CLOSED | 884.8224 | 0 | 372 | 372
PJ0005827 | SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | BROWN, CARLA | CONST_COMP | 2017-07-18 | PCVCA: | GENERAL | CLOSED | 2224.8 | 0 | 753.192 | 753.192
PJ0005827 | SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | BROWN, CARLA | CONST_COMP | 2017-07-18 | PM: SMOKE AND TOBACCO FREE CAMPUS - GENERAL | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005827 | SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | BROWN, CARLA | CONST_COMP | 2017-07-18 | SM: SMOKE & TOBACCO FREE CAMPUS - SIGNAGE & ASH TRAY REMOVAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005827 Total | [7 empty] | 13247.3524 | 0 | 7011.108 | 7011.108
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | AD: HILTI | 052 | CLOSED | 588.5 | 0 | 588.5 | 588.5
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | AD: JOC 16.042.5826 RF KOERBER | 052 | CLOSED | 34764.4819 | 0 | 34764.4819 | 34764.4819
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | AD: STATE FIRE MARSHAL | 052 | CLOSED | 0 | 0 | 189.3044 | 189.3044
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | CP: PROJECT CONTINGENCY | 052 | OPEN | 587.32 | 0 | 0 | 0
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | IN: DATA RACEWAY INSTALLATION - BLD 52 | 052 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | PM: DATA RACEWAY INSTALLATION - BLD 52 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005826 | DATA RACEWAY INSTALLATION - BLD 52 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-07-18 | SM: DATA RACEWAY INSTALLATION - BLD 52 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005826 Total | [7 empty] | 36010.9459 | 0 | 35612.9303 | 35612.9303
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | AD: JOC 16.041.5825 MAINO | 051 | CLOSED | 6165.2758 | 0 | 6165.2651 | 6165.2651
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | AD: OVERSIGHT FEE FOR LEASURE CONCEPTS CONTRACT | 051 | CLOSED | 1359.36 | 0 | 1359.36 | 1359.36
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | AD: STATE FIRE MARSHAL | 051 | CLOSED | 0 | 0 | 133.3969 | 133.3969
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | CP: PROJECT CONTINGENCY | 051 | OPEN | 1894.16 | 0 | 0 | 0
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | EL: BLDG 51: EXTEND UTILITIES FROM HOUSE FOR BBQ - AARON ULM | 051 | CLOSED | 3926.124 | 0 | 2869.866 | 2869.866
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | PL: BLDG 51: EXTEND UTILITIES FROM HOUSE TO BBQ - AARON ULM | 051 | CLOSED | 7490.5872 | 0 | 7488.2128 | 7488.2128
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | PM: EXTEND UTILITIES TO RESIDENCE - BLD 51 | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0005825 | EXTEND UTILITIES TO RESIDENCE - BLD 51 | ULM, AARON | CONST_COMP | 2017-07-13 | SM: EXTEND UTILITIES TO RESIDENCE - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005825 Total | [7 empty] | 20835.507 | 0 | 18016.1008 | 18016.1008
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | AD: BKM - FURNITURE | 065 | OPEN | 11015.9389 | 0 | 11015.9389 | 11015.9389
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | AD: FLOOR CONNECTION- CARPET | 065 | OPEN | 1428.45 | 0 | 989.75 | 989.75
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | AD: ITS - RELOCATE CABLE ADD 3 DATA DROPS | 065 | OPEN | 4151.6 | 0 | 2871.1845 | 2871.1845
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | AD: SANTA MARIA ACOUSTIC | 065 | OPEN | 2771.3 | 0 | 2771.3 | 2771.3
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | AD: STATE FIRE MARSHAL | 065 | OPEN | 278.2 | 0 | 68.6084 | 68.6084
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | CA: BLDG 65-209: DEMO SPACE | 065 | CLOSED | 1957.824 | 0 | 2020.7986 | 2020.7986
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | CP: PROJECT CONTINGENCY | 065 | OPEN | 2340.24 | 0 | 0 | 0
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | CPE: BLDG 65- 209: INSTALL NEW HVAC GRILS | 065 | COMPLETE | 2020.1472 | 0 | 776.748 | 776.748
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | CU: | 065 | OPEN | 147.3648 | 0 | 147.36 | 147.36
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | EL: BLDG 65-209: INSTALL NEW LIGHTS AND POWER | 065 | CLOSED | 6587.8656 | 0 | 9303.168 | 9303.168
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | IN: PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | 065 | ASSIGNED | 155.4168 | 0 | 141.288 | 141.288
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | LO: INSTALL ORANGE CORE | 065 | CLOSED | 60.924 | 0 | 60.924 | 60.924
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | MO: BLDG 65-209: MOVE FURNITURE TO SURPLUS | 065 | CLOSED | 368.676 | 0 | 24 | 24
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | PA: BLDG 65-209: PAINT WALLS | 065 | CLOSED | 3023.952 | 0 | 1423.884 | 1423.884
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | PM: PRIDE CENTER RENOVATION - BLD 65 RM 209 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005824 | PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | NORTON, DAVE | PUNCH_LIST | 2017-07-12 | SM: PRIDE CENTER RENOVATION - BLD 65 RM 209 (SSF) | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005824 Total | [7 empty] | 36307.8993 | 0 | 31614.9524 | 31614.9524
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | AD: ASAP REPROGRAPHICS | 197 | OPEN | 200.0044 | 0 | 225.5667 | 225.5667
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | AD: EARTH SYSTEMS | 197 | OPEN | 5350 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | AD: GOSS ENGINEERING | 197 | OPEN | 26643 | 5328.6 | 21314.4 | 26643
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | AD: MAINO | 197 | OPEN | 287365.62 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | AD: SFM | 197 | OPEN | 4815 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | ANTS: | 197 | OPEN | 74.5536 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | CP: PROJECT CONTINGENCY | 197 | OPEN | 44893.22 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | CPE: | 197 | OPEN | 144.4608 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | EH&S: | 197 | OPEN | 141.6096 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | EL: SUPPORT AND ELECTRICAL SYSTEM INSTALLATION - KOLEGRAFF | 197 | OPEN | 52655.2823 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | ES: | 197 | OPEN | 433.3824 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | IN: REPLACE & RELOCATE COMPRESSOR IN BONDERSON - BLD 197 RM 211 | 197 | ASSIGNED | 430.9284 | 0 | 70.644 | 70.644
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | LO: INSTALLATION OF ORANGE CORES - KOLEGRAFF | 197 | OPEN | 268.0656 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | PA: PAINT STRUCTURAL STEEL & T/U COURTYARD PEMB - KOLEGRAFF | 197 | OPEN | 5966.916 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | PL: SUPPORT AND INSTALLATION OF PUMBING SYSTEMS - KOLEGRAFF | 197 | OPEN | 66643.1098 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | PM: REPLACE & RELOCATE COMPRESSION IN BONDERSON - BLD 197 RM 211 | 197 | OPEN | 0 | 0 | 0 | 0
PJ0005823 | BONDERSON PEMB INSTALLATION - BLD 197 | KOLEGRAFF, KENNETH | PROCUREMNT | 2017-07-11 | SM: REPLACE & RELOCATE COMPRESSOR IN BONDERSON - BLD 197 RM 211 | 197 | OPEN | 0 | 0 | 0 | 0
PJ0005823 Total | [7 empty] | 496025.1528 | 5328.6 | 21610.6107 | 26939.2107
PJ0005822 | REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | DUNN, TRAVIS | CONST_COMP | 2017-07-12 | AD: COASTAL DEMOLITION | 035 | CLOSED | 5243 | 0 | 5243 | 5243
PJ0005822 | REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | DUNN, TRAVIS | CONST_COMP | 2017-07-12 | CP: PROJECT CONTINGENCY | 035 | OPEN | 584.84 | 0 | 0 | 0
PJ0005822 | REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | DUNN, TRAVIS | CONST_COMP | 2017-07-12 | IN: REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | 035 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005822 | REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | DUNN, TRAVIS | CONST_COMP | 2017-07-12 | PM: LIBRARY SHELF REMOVAL PROJECT - BLD 35 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005822 | REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | DUNN, TRAVIS | CONST_COMP | 2017-07-12 | SM: REMOVE 12 ROWS OF METAL SHELVING STACKS - LIBRARY BLD 35 | 035 | OPEN | 0 | 0 | 0 | 0
PJ0005822 Total | [7 empty] | 5898.484 | 0 | 5313.644 | 5313.644
PJ0005821 | 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-14 | AD: COASTAL JANITORIAL INVOICES | 051 | OPEN | 0 | 0 | 561.75 | 561.75
PJ0005821 | 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-14 | AD: RAYNE WATER | 051 | OPEN | 588.5 | 118.235 | 470.265 | 588.5
PJ0005821 | 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-14 | CP: PROJECT CONTINGENCY | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005821 | 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-14 | CU: FURNITURE PAD MATERIAL ORDER | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005821 | 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-14 | PL: GAS LINE MAINTENANCE AT PRESIDENT'S RESIDENCE | 051 | CLOSED | 0 | 0 | 3195.384 | 3195.384
PJ0005821 | 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-14 | SM: 17/18: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005821 Total | [7 empty] | 588.5 | 118.235 | 4227.399 | 4345.634
PJ0005820 | SR 17/18: PLUMBING MAIN LINE REPLACEMENT - BLD 27 | SINE, MARK | SCOPE_DEV | 2017-07-12 | CP: PROJECT CONTINGENCY | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005820 | SR 17/18: PLUMBING MAIN LINE REPLACEMENT - BLD 27 | SINE, MARK | SCOPE_DEV | 2017-07-12 | PM: SR17/18 PLUMBING MAIN LINE REPLACEMENT - BLD 27 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005820 | SR 17/18: PLUMBING MAIN LINE REPLACEMENT - BLD 27 | SINE, MARK | SCOPE_DEV | 2017-07-12 | SM: SR 17/18: PLUMBING MAIN LINE REPLACEMENT - BLD 27 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005820 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | CA: SUPPORT FOR 2017 FALL COMMENCEMENT - 12/9 | 043 | CLOSED | 0 | 0 | 4744.0925 | 4744.0925
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | CP: PROJECT CONTINGENCY | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | CU: SUPPORT FOR 2017 FALL COMMENCEMENT | 043 | CLOSED | 0 | 0 | 514.39 | 514.39
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | EL: SUPPORT FOR 2017 FALL COMMENCEMENT - 12/9 | 043 | CLOSED | 0 | 0 | 579.86 | 579.86
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | ES: SUPPORT FOR 2017 SPRING COMMENCEMENT - 12/9 | 043 | CLOSED | 0 | 0 | 619.68 | 619.68
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | LA: SUPPORT FOR 2017 SPRING COMMENCEMENT | 043 | CLOSED | 0 | 0 | 617.16 | 617.16
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | LO: SUPPORT FOR 2017 FALL COMMENCEMENT 12/8 | 043 | CLOSED | 0 | 0 | 710.78 | 710.78
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | MC: SUPPORT FOR 2017 FALL COMMENCEMENT - BEG. 12/5 | 043 | CLOSED | 0 | 0 | 333.6 | 333.6
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | PA: SUPPORT FOR 2017 FALL COMMENCEMENT | 043 | CLOSED | 0 | 0 | 308.15 | 308.15
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | PERMIT: 2017 FALL COMMENCEMENT - DEC. 9, 2017 | 043 | CLOSED | 0 | 0 | 206.045 | 206.045
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | PL: SUPPORT FOR 2017 FALL COMMENCEMENT - 12/9 | 043 | CLOSED | 0 | 0 | 1360.04 | 1360.04
PJ0005819 | SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-07-12 | SM: SUPPORT FOR 2017 FALL COMMENCEMENT - BLD 43 RM 100 (MAINT) | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005819 Total | [7 empty] | 0 | 0 | 9993.7975 | 9993.7975
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 044 | OPEN | 0 | 0 | 0 | 0
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SPANOS THEATRE EVENT SUPPORT (4K MILES) | 044 | CLOSED | 0 | 0 | 257.88 | 257.88
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SPANOS THEATRE EVENT SUPPORT-END OF CASSINI-9/16 | 044 | CLOSED | 0 | 0 | 92.79 | 92.79
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SPANOS THEATRE SUPPORT - CYBERSECURITY | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SPANOS THEATRE SUPPORT- DREAM BIG (2/7) | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATER EVENTS (SNOW QUEEN)-12/17 | 044 | CLOSED | 0 | 0 | 95.2907 | 95.2907
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATER INTERNAL. EDU. 11.15 | 044 | CLOSED | 0 | 0 | 82.89 | 82.89
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE (ORCHESIS DANCE)-1/27 | 044 | CLOSED | 0 | 0 | 36.84 | 36.84
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE - MOVEMENT ARTS ENS. | 044 | CLOSED | 0 | 0 | 36.84 | 36.84
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENT - JAN. 20 | 044 | CLOSED | 0 | 0 | 47.2826 | 47.2826
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENT (APRIL 14) | 044 | OPEN | 0 | 0 | 0 | 0
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENT (RHYTHMS)-3/18 | 044 | OPEN | 0 | 0 | 93.8135 | 93.8135
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENT - 4/20 | 044 | OPEN | 0 | 0 | 0 | 0
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENT KORESCH DANCE | 044 | OPEN | 0 | 0 | 55.26 | 55.26
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON MARCH 8, 2018 | 044 | OPEN | 0 | 0 | 0 | 0
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE EVENTS-LA GUITARRA (9/22-9/25) | 044 | CLOSED | 0 | 0 | 18.42 | 18.42
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE- DELORES FILM | 044 | OPEN | 0 | 0 | 55.26 | 55.26
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR SPANOS THEATRE: ARTURO UI | 044 | OPEN | 0 | 0 | 239.46 | 239.46
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT SPANOS THEATER (DEF. AMERICA ADDRESS)-9/20 | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT SPANOS THEATRE EVENT(KEOLA BEAMER)-1/28 | 044 | CLOSED | 0 | 0 | 76.89 | 76.89
PJ0005818 | 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 RM 227 | 044 | OPEN | 0 | 0 | 0 | 0
PJ0005818 Total | [7 empty] | 0 | 0 | 1409.9569 | 1409.9569
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CA: SUPPORT FOR BASEBALL | 160 | CLOSED | 0 | 0 | 91.782 | 91.782
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: TAILGATING/ MUSTANG BBQ SUPPORT | GENERAL | OPEN | 0 | 0 | 1281.8674 | 1281.8674
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: INSTALL 1 SPIDER BOX FOR CONCESSIONS TRAILERS- CONCOURSE | 160E | OPEN | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: INSTALL BREAKER FOR 50 AMP SPIDER BOX - 061 BY 8/26 | 061D | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: INSTALL GENERATOR FOR BBQ TRAILER - PARKING LOT H-15 | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: SUPPORT FOR FOOTBALL EVENTS - 2017 SEASON | GENERAL | OPEN | 0 | 0 | 1336.881 | 1336.881
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: MOVE IRRIGATION AT SPANOS STADIUM | 061 | COMPLETE | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: SUPPORT FOR MUSTANG BBQ EVENTS- | GENERAL | COMPLETE | 0 | 0 | 827.5124 | 827.5124
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | PERMIT: ATHELTICS FOOTBALL TAILGATING - 2017 | 061 | HOLD | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | PERMIT: MUSTANG BBQ BOUNCE HOUSE- 8/26, 9/23,10/21,11/4,11/11 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | PERMIT: SFM PERMIT FOR BEER SALES - 061 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | RE: SUPPORT FOR FOOTBALL BBQ 2017 | GENERAL | OPEN | 0 | 0 | 1435.654 | 1435.654
PJ0005817 | 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005817 Total | [7 empty] | 0 | 0 | 5038.1248 | 5038.1248
PJ0005816 | 17/18: SUPPORT FOR SOFTBALL - BLD 161 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 161 | OPEN | 0 | 0 | 0 | 0
PJ0005816 | 17/18: SUPPORT FOR SOFTBALL - BLD 161 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: 17/18 - SUPPORT FOR SOFTBALL | 161 | OPEN | 0 | 0 | 223.656 | 223.656
PJ0005816 | 17/18: SUPPORT FOR SOFTBALL - BLD 161 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: SOFTBALL GAMES & PRACTICES SUPPORT (SEASON) | 161 | OPEN | 0 | 0 | 6877.2263 | 6877.2263
PJ0005816 | 17/18: SUPPORT FOR SOFTBALL - BLD 161 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR SOFTBALL - BLD 161 | 161 | OPEN | 0 | 0 | 0 | 0
PJ0005816 Total | [7 empty] | 0 | 0 | 7100.8823 | 7100.8823
PJ0005815 | 17/18: SUPPORT FOR BASEBALL - BLD 160 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CA: SUPPORT FOR BASEBALL V. CSULB TELEVISED GAME-4/20 | 160 | COMPLETE | 0 | 0 | 83.43 | 83.43
PJ0005815 | 17/18: SUPPORT FOR BASEBALL - BLD 160 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 160 | OPEN | 0 | 0 | 0 | 0
PJ0005815 | 17/18: SUPPORT FOR BASEBALL - BLD 160 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: 17/18 - SUPPORT FOR BASEBALL | 160 | OPEN | 0 | 0 | 761.1159 | 761.1159
PJ0005815 | 17/18: SUPPORT FOR BASEBALL - BLD 160 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: SUPPORT FOR BASEBALL V. CSULB - TELEVISED (4/19) | 160 | CLOSED | 0 | 0 | 354.354 | 354.354
PJ0005815 | 17/18: SUPPORT FOR BASEBALL - BLD 160 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: BASEBALL PRACTICES & GAMES SUPPORT (SEASON) | 160 | OPEN | 0 | 0 | 8517.4449 | 8517.4449
PJ0005815 | 17/18: SUPPORT FOR BASEBALL - BLD 160 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR BASEBALL - BLD 160 | 160 | OPEN | 0 | 0 | 0 | 0
PJ0005815 Total | [7 empty] | 0 | 0 | 9716.3448 | 9716.3448
PJ0005814 | 17/18: SUPPORT FOR WRESTLING - BLD 42 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005814 | 17/18: SUPPORT FOR WRESTLING - BLD 42 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | PM: 17/18: SUPPORT FOR WRESTLING - BLD 42 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005814 | 17/18: SUPPORT FOR WRESTLING - BLD 42 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR WRESTLING - BLD 42 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005814 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CA: SUPPORT FOR M. SOCCER V. UCSB - 10/28 | 061 | CLOSED | 0 | 0 | 1533.666 | 1533.666
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CENTRAL PLANT: M. SOCCER V. UCSB-10/28 @ 7PM | 061 | COMPLETE | 0 | 0 | 288.912 | 288.912
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR MENS SOCCER | 061 | OPEN | 0 | 0 | 8842.3972 | 8842.3972
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: SUPPORT FOR M. SOCCER V. UCSB - 10/28 @ 7PM | 061 | CLOSED | 0 | 0 | 460.668 | 460.668
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: SUPPORT FOR M. SOCCER GAMES (SEASON W/O) | 061 | OPEN | 0 | 0 | 2412.336 | 2412.336
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: SUPPORT FOR MEN'S SOCCER PRACTICES(SEASON) | 061 | OPEN | 0 | 0 | 1501.2 | 1501.2
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | PL: SUPPORT FOR MENS SOCCER V. UCSB - 10/28 @ 7PM | 061 | COMPLETE | 0 | 0 | 886.0796 | 886.0796
PJ0005813 | 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR MEN'S SOCCER - BLD 61 | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005813 Total | [7 empty] | 0 | 0 | 15925.2588 | 15925.2588
PJ0005812 | 17/18: SUPPORT FOR WOMEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005812 | 17/18: SUPPORT FOR WOMEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: SUPPORT FOR WOMEN'S SOCCER (SEASON W/O) | 061 | OPEN | 0 | 0 | 3684.3915 | 3684.3915
PJ0005812 | 17/18: SUPPORT FOR WOMEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: WOMEN'S SOCCER GAMES SUPPORT (SEASON) | 061 | OPEN | 0 | 0 | 2568.852 | 2568.852
PJ0005812 | 17/18: SUPPORT FOR WOMEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: WOMEN'S SOCCER PRACTICE SUPPORT (SEASON) | 061 | OPEN | 0 | 0 | 760.608 | 760.608
PJ0005812 | 17/18: SUPPORT FOR WOMEN'S SOCCER - BLD 61 | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR WOMEN'S SOCCER - BLD 61 | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005812 Total | [7 empty] | 0 | 0 | 7013.8515 | 7013.8515
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CA: 17/18 SUPPORT FOR FOOTBAL | 061 | CLOSED | 0 | 0 | 2269.2581 | 2269.2581
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CPE: 17/18 FOOTBALL SUPPORT | 061 | ASSIGNED | 0 | 0 | 1813.728 | 1813.728
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | CU: 17/18 SUPPORT FOR FOOTBALL | 061 | OPEN | 0 | 0 | 10712.075 | 10712.075
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | EL: 17/18 SUPPORT FOR FOOTBALL | 061 | CLOSED | 0 | 0 | 5184.294 | 5184.294
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: 17/18 SUPPORT FOR FOOTBALL GAMES-SEASON W/O | 061 | COMPLETE | 0 | 0 | 7441.5926 | 7441.5926
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: 17/18 SUPPORT FOR FOOTBALL SCRIMMAGES/PRACTICES | 061 | OPEN | 0 | 0 | 1118.568 | 1118.568
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | LA: FOOTBALL SUPPORT | 061 | OPEN | 0 | 0 | 21438.752 | 21438.752
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | PL: 17/18 SUPPORT FOR FOOTBALL | 061 | ASSIGNED | 0 | 0 | 1716.682 | 1716.682
PJ0005811 | 17/18: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | IN_CONSTR | 2017-07-12 | SM: 17/18: SUPPORT FOR FOOTBALL | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005811 Total | [7 empty] | 0 | 0 | 51694.9497 | 51694.9497
PJ0005810 | SR 17/18: GAS LINE REPLACEMENT - BLD 40 | SINE, MARK | CONST_COMP | 2017-07-11 | AD: HPS MECHANICAL | 040 | CLOSED | 26750 | 0 | 25145 | 25145
PJ0005810 | SR 17/18: GAS LINE REPLACEMENT - BLD 40 | SINE, MARK | CONST_COMP | 2017-07-11 | CP: PROJECT CONTINGENCY | 040 | OPEN | 3045.11 | 0 | 0 | 0
PJ0005810 | SR 17/18: GAS LINE REPLACEMENT - BLD 40 | SINE, MARK | CONST_COMP | 2017-07-11 | CPE: SUPPORT FOR S/D AND INSTALL OF PIPE | 040 | OPEN | 2311.3728 | 0 | 0 | 0
PJ0005810 | SR 17/18: GAS LINE REPLACEMENT - BLD 40 | SINE, MARK | CONST_COMP | 2017-07-11 | PA: PAINT NEW PIPE | 040 | CLOSED | 1389.5808 | 0 | 532.416 | 532.416
PJ0005810 | SR 17/18: GAS LINE REPLACEMENT - BLD 40 | SINE, MARK | CONST_COMP | 2017-07-11 | SM: SR 17/18: GAS LINE REPLACEMENT - BLD 40 | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005810 Total | [7 empty] | 33496.0636 | 0 | 25677.416 | 25677.416
PJ0005809 | 17/18 SP, 17/18 ASI M&R: SUPPORT LED UPGRADE CAMPUS WIDE | SODERIN, ERIC | SCOPE_DEV | 2017-07-12 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005809 | 17/18 SP, 17/18 ASI M&R: SUPPORT LED UPGRADE CAMPUS WIDE | SODERIN, ERIC | SCOPE_DEV | 2017-07-12 | PM: UPGRADE CAMPUS LIGHTING - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005809 | 17/18 SP, 17/18 ASI M&R: SUPPORT LED UPGRADE CAMPUS WIDE | SODERIN, ERIC | SCOPE_DEV | 2017-07-12 | SM: 17/18 SP, 17/18 ASI M&R: SUPPORT LED UPGRADE CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005809 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | AD: BKM OFFICE ENVIRONMENTS | 010 | CLOSED | 10670.6178 | 0 | 10670.6178 | 10670.6178
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | AD: HERTZ FURNITURE | 010 | CLOSED | 47822.58 | 0 | 47822.58 | 47822.58
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | AD: MEATHEAD MOVERS | 010 | CLOSED | 10178.0433 | 0 | 6449.6925 | 6449.6925
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | AD: STATE FIRE MARSHAL | 010 | CLOSED | 1070 | 0 | 133.3969 | 133.3969
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | CP: PROJECT CONTINGENCY | 010 | OPEN | 1846.02 | 0 | 0 | 0
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | CU: | 010 | CLOSED | 736.824 | 0 | 922.434 | 922.434
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | IN: | 010 | CLOSED | 353.22 | 0 | 141.288 | 141.288
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | MO: | 010 | CLOSED | 737.352 | 0 | 60 | 60
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | PM: DESK RENOVATION - BLD 10 | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0005808 | RENOVATE/REPLACE DESKS - BLD 10 | BROWN, CARLA | CONST_COMP | 2017-07-12 | SM: RENOVATE/REPLACE DESKS - BLD 10 | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005808 Total | [7 empty] | 73414.6571 | 0 | 66200.0092 | 66200.0092
PJ0005806 | UPGRADE CLASSROOM TECH - BLD 03 RM 111 | BROWN, CARLA | ESTIMATING | 2017-06-08 | CP: PROJECT CONTINGENCY | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005806 | UPGRADE CLASSROOM TECH - BLD 03 RM 111 | BROWN, CARLA | ESTIMATING | 2017-06-08 | PM: PHASE II-CLASSROOM TECHNOLOGY UPDATES - BD 3 RM 111 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005806 | UPGRADE CLASSROOM TECH - BLD 03 RM 111 | BROWN, CARLA | ESTIMATING | 2017-06-08 | SM: UPGRADE CLASSROOM TECH - BLD 03 RM 111 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005806 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | AD: BKM | 034 | OPEN | 14716.4269 | 1611.955 | 13104.4719 | 14716.4269
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | AD: ITS/CT - CT - MOBILE CARTS FOR 5 BLDGS 10, 34, RED BRICKS | 034 | OPEN | 27285 | 26298.995 | 986.005 | 27285
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | AD: PURCHASE WHITE BOARDS | 034 | OPEN | 1470.5438 | 0 | 0 | 0
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | AD: STATE FIRE MARSHAL | 034 | OPEN | 267.5 | 81.4698 | 186.0302 | 267.5
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | CA: BRENNAN CREATE CLASSROOM SPACE - BLDG 34 RM 159A | 034 | CLOSED | 2074.7622 | 0 | 2074.284 | 2074.284
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | CP: PROJECT CONTINGENCY | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | CU: BRENNAN, 34-159A CLEAN AND WAX FLOORS | 034 | OPEN | 1484.1888 | 0 | 0 | 0
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | EL: BRENNAN,34-159A ABANDON PLUG ON WALL | 034 | CLOSED | 161.07 | 0 | 161.07 | 161.07
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | IN: CREATE ADDITIONAL CLASSROOM SPACE - BLDG 34 RM 159A | 034 | ASSIGNED | 282.576 | 0 | 141.288 | 141.288
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | LO: BRENNAN 34-159A - CHANGE CORE TO CLASSROOM | 034 | CLOSED | 30.462 | 0 | 30.462 | 30.462
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | MO: BRENNAN 34-159A REMOVE TABLES | 034 | CLOSED | 201.096 | 0 | 72 | 72
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | PM: CREATE ADDITIONAL CLASSROOM SPACE - BLDG 34 RM 159A | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005805 | CREATE ADDL CLASSROOM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | SM: CREATE ADDL CLSRM SPACE-BLD 34 RM 159A& FURNISH BLD 2 RM 213 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005805 Total | [7 empty] | 47973.6257 | 27992.4198 | 16755.6111 | 44748.0309
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | AD: BKM | 010 | OPEN | 17594.1063 | 17594.1063 | 0 | 17594.1063
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | AD: STATE FIRE MARSHAL | 010 | OPEN | 267.5 | 203.9741 | 63.5259 | 267.5
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | CA: BRENNAN CREATE ADDITIONAL CLASSROOM SPACE - BLDG 10 RM 125 | 010 | CLOSED | 2419.572 | 0 | 2419.56 | 2419.56
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | CP: PROJECT CONTINGENCY | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | CU: BRENNAN 10-125 CLEAN AND WAX FLOORS | 010 | COMPLETE | 0 | 0 | 0 | 0
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | EL: BRENNAN - 10-125 REMOVE STRUCTURED WIRE SYSTEM FROM TABLES | 010 | CLOSED | 418.782 | 0 | 418.782 | 418.782
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | IN: CREATE ADDITIONAL CLASSROOM SPACE - BLDG 10 RM 125 | 010 | CLOSED | 176.61 | 0 | 176.61 | 176.61
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | LO: BRENNAN 10-125 CHANGE CORE | 010 | CLOSED | 274.158 | 0 | 274.158 | 274.158
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | MO: BRENNAN - 10-125 - REMOVE SHELVES, DESK & MISC | 010 | CLOSED | 228.244 | 0 | 228 | 228
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | PM: CREATE ADDITIONAL CLASSROOM SPACE - BLDG 10 RM 125 | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005804 | CREATE ADDL CLASSROOM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | BROWN, CARLA | PUNCH_LIST | 2017-06-30 | SM: CREATE ADDL CLSRM SPACE-BLD 10 RM 125 & FURNISH BLD 2 RM 213 | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005804 Total | [7 empty] | 21378.9723 | 17798.0804 | 3580.6359 | 21378.7163
PJ0005803 | REROUTE GAS LINE - UNIVERSITY HOUSE 51 | GONZALES, ALBERT | CONST_COMP | 2017-06-23 | AD: COASTAL DEMO | 051 | CLOSED | 1070 | 0 | 604.55 | 604.55
PJ0005803 | REROUTE GAS LINE - UNIVERSITY HOUSE 51 | GONZALES, ALBERT | CONST_COMP | 2017-06-23 | AD: GARCIA AND SONS | 051 | CLOSED | 8025 | 0 | 7715.6416 | 7715.6416
PJ0005803 | REROUTE GAS LINE - UNIVERSITY HOUSE 51 | GONZALES, ALBERT | CONST_COMP | 2017-06-23 | CP: PROJECT CONTINGENCY | 051 | OPEN | 1455.14 | 0 | 0 | 0
PJ0005803 | REROUTE GAS LINE - UNIVERSITY HOUSE 51 | GONZALES, ALBERT | CONST_COMP | 2017-06-23 | PL: REROUTE GAS LINE AT PRESIDENT'S RESIDENCE | 051 | CLOSED | 5456.208 | 0 | 10570.8123 | 10570.8123
PJ0005803 Total | [7 empty] | 16006.348 | 0 | 18891.0039 | 18891.0039
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | AD: STATE FIRE MARSHAL | 013 | OPEN | 283.55 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | CA: PJ5802 ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | 013 | OPEN | 1398.912 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | CP: PROJECT CONTINGENCY | 013 | OPEN | 634.52 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | EL:PJ5802 - ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | 013 | OPEN | 1433.9328 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | ES:PJ5802 - ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | 013 | OPEN | 2885.5296 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | IN: ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | 013 | ASSIGNED | 141.288 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | PL: PJ5802 - ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | 013 | OPEN | 201.8736 | 0 | 12.0125 | 12.0125
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | PM: ELECTRICAL UPGRADE: BLD 13 RM 101 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005802 | ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | DUNN, TRAVIS | SCHEDULING | 2017-06-08 | SM: ASSIST DEPT. W/NEW EQUIP INSTALL - BLD 13 RM 101 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005802 Total | [7 empty] | 6979.606 | 0 | 12.0125 | 12.0125
PJ0005801 | RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | NORTON, DAVE | CONST_COMP | 2017-06-05 | AD: ITS | 001 | CLOSED | 1605 | 0 | 1449.0475 | 1449.0475
PJ0005801 | RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | NORTON, DAVE | CONST_COMP | 2017-06-05 | CP: PROJECT CONTINGENCY | 001 | OPEN | 379.12 | 0 | 0 | 0
PJ0005801 | RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | NORTON, DAVE | CONST_COMP | 2017-06-05 | EL: POWER HOOK UP | 001 | CLOSED | 1733.9328 | 0 | 1223.364 | 1223.364
PJ0005801 | RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | NORTON, DAVE | CONST_COMP | 2017-06-05 | IN: RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | 001 | CLOSED | 77.7084 | 0 | 35.322 | 35.322
PJ0005801 | RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | NORTON, DAVE | CONST_COMP | 2017-06-05 | PM: MOVE TWO CUBICLES - BLD 1 RM 107 | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005801 | RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | NORTON, DAVE | CONST_COMP | 2017-06-05 | SM: RELOCATE TWO WORKSTATIONS - BLD 1 FROM RM 107 TO 131 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005801 Total | [7 empty] | 3795.7612 | 0 | 2707.7335 | 2707.7335
PJ0005800 | UPGRADE CLASSROOM TECH-BLD 03 RMS 207,300A,302,303,305,306,307 | BROWN, CARLA | ESTIMATING | 2017-05-26 | CP: PROJECT CONTINGENCY | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005800 | UPGRADE CLASSROOM TECH-BLD 03 RMS 207,300A,302,303,305,306,307 | BROWN, CARLA | ESTIMATING | 2017-05-26 | PM: CLASSROOM TECHNOLOGY UPDATES - BLD 003 RM 111 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005800 | UPGRADE CLASSROOM TECH-BLD 03 RMS 207,300A,302,303,305,306,307 | BROWN, CARLA | ESTIMATING | 2017-05-26 | SM: UPGRADE CLSRM TECH-BLD 03 RMS 207,300A,302,303,305,306,307 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005800 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005799 | INSTALL CARPET IN LOBBY & OFFICE-BLD 03 RMS 100, 100A, & 100B | ULM, AARON | CONST_COMP | 2017-05-26 | AD: FLOOR CONNECTION | 003 | CLOSED | 5326.46 | 0 | 5326.46 | 5326.46
PJ0005799 | INSTALL CARPET IN LOBBY & OFFICE-BLD 03 RMS 100, 100A, & 100B | ULM, AARON | CONST_COMP | 2017-05-26 | AD: FURNITURE INSTALLATION TEAM | 003 | CLOSED | 817.48 | 0 | 817.48 | 817.48
PJ0005799 | INSTALL CARPET IN LOBBY & OFFICE-BLD 03 RMS 100, 100A, & 100B | ULM, AARON | CONST_COMP | 2017-05-26 | CA: REMOVE BASEBOARDS, DISASSEMBLE FLOOR TOUCHING FURNITURE | 003 | CLOSED | 1468.368 | 0 | 949.005 | 949.005
PJ0005799 | INSTALL CARPET IN LOBBY & OFFICE-BLD 03 RMS 100, 100A, & 100B | ULM, AARON | CONST_COMP | 2017-05-26 | CP: PROJECT CONTINGENCY | 003 | OPEN | 761.24 | 0 | 0 | 0
PJ0005799 | INSTALL CARPET IN LOBBY & OFFICE-BLD 03 RMS 100, 100A, & 100B | ULM, AARON | CONST_COMP | 2017-05-26 | PM: INSTALL CARPET- LOBBY & OFFICE - BLD 03 RM 100, 100A, & 100B | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005799 | INSTALL CARPET IN LOBBY & OFFICE-BLD 03 RMS 100, 100A, & 100B | ULM, AARON | CONST_COMP | 2017-05-26 | SM: INSTALL CARPET IN LOBBY & OFFICE-BLD 3 RMS 100, 100A, & 100B | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005799 Total | [7 empty] | 8373.548 | 0 | 7092.945 | 7092.945
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | AD: FIT | 003 | CLOSED | 662.33 | 0 | 662.33 | 662.33
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | AD: JL FASULO DRYWALL | 003 | CLOSED | 5341.44 | 0 | 5341.44 | 5341.44
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | CA: DISASSEMBLE FURNITURE, REMOVE BLINDS, BASEBOARDS, WALL ITEMS | 003 | CLOSED | 978.912 | 0 | 1792.374 | 1792.374
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | CP: PROJECT CONTINGENCY | 003 | OPEN | 687.28 | 0 | 0 | 0
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | PA: REMOVE WALLPAPER IN 405/405A. PAINT AFTER TEXTURE. | 003 | CLOSED | 2779.1616 | 0 | 1533.036 | 1533.036
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | PM: REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005798 | REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | ULM, AARON | CONST_COMP | 2017-05-26 | SM: REMOVE WALLPAPER AND PAINT AREA OFFICE -BLD 3 RM 405 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005798 Total | [7 empty] | 10449.1236 | 0 | 9329.18 | 9329.18
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | AD: GENERATOR | 051 | OPEN | 33170 | 0 | 0 | 0
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | CA: INSTALL CONCRETE PAD & FENCE ENCLOSURE | 051 | ASSIGNED | 14210.7642 | 0 | 139.05 | 139.05
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | CP: PROJECT CONTINGENCY | 051 | OPEN | 10232.64 | 0 | 0 | 0
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | EL: INSTALL UNDERGROUND ELECTRICAL & GENERATOR | 051 | LONG_TERM | 13795.788 | 0 | 1936.104 | 1936.104
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | IN: SR 17/18: INSTALL GENERATOR - UH 51 | 051 | ASSIGNED | 282.576 | 0 | 70.644 | 70.644
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | LA: TRENCHING & BACKFILL FOR UTILITIES & GENERATOR CONCRETE | 051 | OPEN | 3002.112 | 0 | 3633.48 | 3633.48
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | PA: PAINT FENCE ENCLOSURE TO MATCH EXISTING | 051 | OPEN | 1994.3712 | 0 | 0 | 0
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | PL: INSTALL UNDERGROUND GAS & FINAL CONNECTIONS FOR GENERATOR | 051 | PEND_SCHED | 3928.104 | 0 | 1257.516 | 1257.516
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | PM: SR17/18 INSTALL GENERATOR -BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005797 | SR 17/18: INSTALL GENERATOR - UH 51 | ULM, AARON | SCHEDULING | 2017-05-25 | SM: SR 17/18: INSTALL GENERATOR - UH 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005797 Total | [7 empty] | 80616.3554 | 0 | 7036.794 | 7036.794
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | CU: SUPPORT FOR LAUREN SOUTHERN EVENT - 5/25 | 033 | CLOSED | 0 | 0 | 180.9948 | 180.9948
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | EL: SUPPORT FOR LAUREN SOUTHERN EVENT - MAY 25 | 033 | CLOSED | 0 | 0 | 338.03 | 338.03
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | LA: SUPPORT FOR LAUREN SOUTHERN EVENT - 5/25 | 033 | CLOSED | 0 | 0 | 66.72 | 66.72
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | MC: SUPPORT FOR LAUREN SOUTHERN EVENT - MAY 25 | 033 | CLOSED | 0 | 0 | 80 | 80
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | PA: REMOVE GRAFFITI AT FISHER SCIENCE - 5/26 | 033 | CLOSED | 0 | 0 | 108.34 | 108.34
PJ0005796 | SUPPORT FOR LAUREN SOUTHERN - MAY 25TH, 2017 (MAINT) | POPHAM, DONALD J. | CLOSED | 2017-05-24 | PL: SET UP FENCING FOR SOUTHERN EVENT - 5/25 | 033 | CLOSED | 0 | 0 | 107.48 | 107.48
PJ0005796 Total | [7 empty] | 0 | 0 | 881.5648 | 881.5648
PJ0005795 | SR 17/18: RESERVOIRS INSPECTION AND REPAIR | SINE, MARK | ESTIMATING | 2017-05-18 | AD: AQUATIC INSPECTIONS MUNICIPAL DIVING SERVICES | GENERAL | OPEN | 18725 | 0 | 17922.5 | 17922.5
PJ0005795 | SR 17/18: RESERVOIRS INSPECTION AND REPAIR | SINE, MARK | ESTIMATING | 2017-05-18 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 1523.5 | 0 | 0 | 0
PJ0005795 | SR 17/18: RESERVOIRS INSPECTION AND REPAIR | SINE, MARK | ESTIMATING | 2017-05-18 | ES: SUPPORT FOR TANK INSPECTION | GENERAL | CLOSED | 288.9216 | 0 | 196.992 | 196.992
PJ0005795 | SR 17/18: RESERVOIRS INSPECTION AND REPAIR | SINE, MARK | ESTIMATING | 2017-05-18 | IN: SR 17/18 RESERVOIRS INSPECTION AND REPAIR | GENERAL | OPEN | 310.8336 | 0 | 0 | 0
PJ0005795 | SR 17/18: RESERVOIRS INSPECTION AND REPAIR | SINE, MARK | ESTIMATING | 2017-05-18 | PL: SHOP SUPPORT FOR TANK INSPECTIONS | GENERAL | COMPLETE | 1134.9888 | 0 | 381.8259 | 381.8259
PJ0005795 | SR 17/18: RESERVOIRS INSPECTION AND REPAIR | SINE, MARK | ESTIMATING | 2017-05-18 | SM: SR 17/18: RESERVOIRS INSPECTION AND REPAIR | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005795 Total | [7 empty] | 21983.244 | 0 | 18501.3179 | 18501.3179
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | AD: GOT YOU COVER'D RENTAL SPRING COMMENCEMENT - 6/17 | 061 | CLOSED | 0 | 0 | 211.85 | 211.85
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | AD: MATERIALS PURCHASE FOR SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 618.28 | 618.28
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | CA: SUPPORT FOR SPRING COMMENCEMENT - 6/14 - 6/20 | 061 | CLOSED | 0 | 0 | 9062.23 | 9062.23
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | CBS: SUPPORT FOR SPRING COMMENCEMENT - 6/17 & 6/18 | 061 | CLOSED | 0 | 0 | 560.0775 | 560.0775
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | CPE: SUPPORT FOR SPRING COMMENCEMENT - 6/17-6/18 | 061 | CLOSED | 0 | 0 | 612.6 | 612.6
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | CU: SUPPORT FOR COMMENCEMENT | 061 | CLOSED | 0 | 0 | 9060.4318 | 9060.4318
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | EL: SUPPORT FOR SPRING COMMENCEMENT - 6/17 & 6/18 | 061 | CLOSED | 0 | 0 | 1128.6 | 1128.6
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | LA: SUPPORT FOR SPRING COMMENCEMENT - | 061 | CLOSED | 0 | 0 | 11426.6418 | 11426.6418
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | MC: SUPPORT FOR SPRING COMMENCEMENT - 6/7 & 6/18 | 061 | CLOSED | 0 | 0 | 2541.8 | 2541.8
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | PA: SUPPORT FOR 2017 SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 464.31 | 464.31
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | PCV: COMMENCEMENT SUPPORT | 061 | CLOSED | 0 | 0 | 1007.535 | 1007.535
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | PERMIT: SUPPORT FOR SPRING COMMENCEMENT - 6/18-6/18 | 061 | CLOSED | 0 | 0 | 176.61 | 176.61
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | PL: SUPPORT FOR SPRING COMMENCEMENT - 6/17 & 6/18 | 061 | CLOSED | 0 | 0 | 5490.111 | 5490.111
PJ0005794 | SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CONST_COMP | 2017-05-17 | SM: SUPPORT FOR 2017 SPRING COMMENCEMENT (MAINT) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005794 Total | [7 empty] | 0 | 0 | 42361.0771 | 42361.0771
PJ0005792 | REPLACE CARPET, PAINT - BLD 20 RM 100 | NORTON, DAVE | SCOPE_DEV | 2017-02-21 | CP: PROJECT CONTINGENCY | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005792 | REPLACE CARPET, PAINT - BLD 20 RM 100 | NORTON, DAVE | SCOPE_DEV | 2017-02-21 | PM: REPLACE CARPET, PAINT & ADD COOL WATER LINES - BLD 20 RM 100 | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005792 | REPLACE CARPET, PAINT - BLD 20 RM 100 | NORTON, DAVE | SCOPE_DEV | 2017-02-21 | SM: REPLACE CARPET, PAINT & ADD COOL WATER LINES - BLD 20 RM 100 | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005792 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | AD: FLOOR CONNECTION - INSTALL YELLOW STRIPES | 192 | CLOSED | 1349.7729 | 0 | 684.8 | 684.8
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | AD: ITS/CT | 192 | CLOSED | 2675 | 0 | 1645.66 | 1645.66
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | AD: STATE FIRE MARSHAL | 192 | CLOSED | 267.5 | 0 | 385.4889 | 385.4889
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | CA: INSTALL PROJECTOR SCREEN | 192 | CLOSED | 244.728 | 0 | 887.46 | 887.46
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | CP: PROJECT CONTINGENCY | 192 | OPEN | 2161.19 | 0 | 0 | 0
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | CU: | 192 | CLOSED | 5605.2211 | 0 | 133.632 | 133.632
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | EL:BROWN 192-130 SURFACE MOUNT ELECTRICAL OUTLET | 192 | CLOSED | 2300.8992 | 0 | 1275.792 | 1275.792
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | IN: RENOVATE QL+ LAB - BLD 192 RM 130 | 192 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | PA: PATCH & PAINT | 192 | CLOSED | 8885.928 | 0 | 5803.512 | 5803.512
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | PM: RENOVATE QL+ LAB - BLD 192 RM 130 | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0005790 | RENOVATE QL+ LAB - BLD 192 RM 130 | BROWN, CARLA | CONST_COMP | 2017-04-24 | SM: RENOVATE QL+ LAB - BLD 192 RM 130 | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005790 Total | [7 empty] | 23772.8152 | 0 | 10992.9549 | 10992.9549
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | AD: CAL POLY PROJECT COORDINATION FEE | P-R01 | OPEN | 2327.5 | 0 | 2327.5 | 2327.5
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | AD: ENGELKIRK AND SABOL | P-R01 | OPEN | 500 | 0 | 500 | 500
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | AD: STATE FIRE MARSHAL | P-R01 | OPEN | 214 | 0 | 120.054 | 120.054
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | AD: WILDAN | P-R01 | OPEN | 1500 | 0 | 1500 | 1500
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | CP: PROJECT CONTINGENCY | P-R01 | OPEN | 598.49 | 0 | 0 | 0
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | EL: | P-R01 | OPEN | 716.4394 | 0 | 0 | 0
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | IN: TI: VERIZON CELL SITE MODIFICATIONS - R-1 PARKING LOT (MAINT | P-R01 | ASSIGNED | 588.7 | 0 | 235.48 | 235.48
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | PM: TI: VERIZON CELL SITE MODIFICATIONS - R-1 PARKING LOT | P-R01 | OPEN | 0 | 0 | 0 | 0
PJ0005789 | TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2017-05-01 | SM: TI: VERIZON CELL SITE MODIFICATIONS R01 PARKING LOT | P-R01 | OPEN | 0 | 0 | 0 | 0
PJ0005789 Total | [7 empty] | 6445.1294 | 0 | 4683.034 | 4683.034
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: BKM | 001 | OPEN | 43075.7711 | 0 | 8835.7711 | 8835.7711
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: BOWEN | 001 | OPEN | 14445 | 0 | 14445 | 14445
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: DEFINITELY DIFFERENT DESIGNS GLASS - ETCHED SIGN | 001 | OPEN | 2140 | 387.3079 | 387.3079 | 774.6158
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: FLOOR CONNECTION | 001 | OPEN | 2851.55 | 0 | 2851.55 | 2851.55
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: ITS | 001 | OPEN | 1444.5 | 0 | 1438.8825 | 1438.8825
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: MORRO BAY CABINETS | 001 | OPEN | 8537.53 | 0 | 8130.93 | 8130.93
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: RICK MCKENNA | 001 | OPEN | 6534.49 | 192.6 | 6341.89 | 6534.49
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: SANTA MARIA ACOUSTICS | 001 | OPEN | 1284 | 0 | 1012.22 | 1012.22
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD: THE SIGN PLACE | 001 | OPEN | 7735.5971 | 4378.3758 | 3357.2213 | 7735.5971
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | AD:STATE FIRE MARSHAL | 001 | OPEN | 278.2 | 0 | 365.8865 | 365.8865
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | CA: CARPENTRY, DRYWALL, SIGNAGE, MISC- BLDG 1-4TH FLOOR | 001 | ASSIGNED | 18213.3162 | 0 | 13945.5808 | 13945.5808
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | CP: PROJECT CONTINGENCY | 001 | OPEN | 1398.41 | 0 | 0 | 0
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | CU: | 001 | OPEN | 368.412 | 0 | 0 | 0
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | EH&S: | 001 | OPEN | 128.736 | 0 | 0 | 0
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | EL: ELECTRICAL FOR RMS 402 AND 408- BLDG 1- 4TH FL | 001 | CLOSED | 9864.018 | 0 | 8486.04 | 8486.04
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | ES: INSTALL HVAC CAP | 001 | CLOSED | 131.328 | 0 | 0 | 0
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | IN: 4TH FL CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | 001 | ASSIGNED | 353.22 | 0 | 0 | 0
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | MO: REMOVE ITEMS TO SURPLUS | 001 | CLOSED | 368.676 | 0 | 72 | 72
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | PA: PAINT WALLS IN RM 408 AND 402; CORRIDOR PAINT- TRIM AND ACC | 001 | ASSIGNED | 6647.904 | 0 | 9905.658 | 9905.658
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | PL: RELOCATE KITCHEN- ADMIN- 4TH FLOOR | 001 | COMPLETE | 7316.208 | 0 | 11286.2204 | 11286.2204
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | PM: REMODEL FOURTH FLOOR - BLD 001 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005788 | 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMODEL - BLD 001 | NORTON, DAVE | IN_CONSTR | 2017-04-28 | SM: 4TH FLR CORRIDOR SIGNAGE/BRANDING & KITCHEN REMDL - BLD 001 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005788 Total | [7 empty] | 133116.8664 | 4958.2837 | 90862.1584 | 95820.4421
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | AD: JOC 16.040.5787 NEWTON | 051 | OPEN | 24217.6524 | 1020.0524 | 23197.6 | 24217.6524
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | AD: MCKENNA | 051 | CLOSED | 1355.69 | 0 | 1355.69 | 1355.69
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | CA: BLDG 51: ROOF / FLASHING INSPECTION FOR AARON ULM | 051 | CLOSED | 489.456 | 0 | 166.86 | 166.86
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | CP: PROJECT CONTINGENCY | 051 | OPEN | 1333.55 | 0 | 0 | 0
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | IN: ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | 051 | CLOSED | 310.8336 | 0 | 176.61 | 176.61
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | PA: BLDG 51: PAINT NEW EXTERIOR STUCCO: AARON ULM | 051 | CLOSED | 1874.3712 | 0 | 930.264 | 930.264
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | PM: ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0005787 | ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | ULM, AARON | CONST_COMP | 2017-04-28 | SM: ASSESS SOURCE OF WATER INTRUSION & REPAIR AS NEEDED - UH 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005787 Total | [7 empty] | 29581.5532 | 1020.0524 | 25827.024 | 26847.0764
PJ0005784 | SPRING STAMPEDE SUPPORT 6/3/17- STATE FACILITIES | POPHAM, DONALD J. | CONST_COMP | 2017-04-27 | AD: MATERIALS PURCHASE FOR STAMPEDE CONCERT | 163 | CLOSED | 0 | 0 | 258.492 | 258.492
PJ0005784 | SPRING STAMPEDE SUPPORT 6/3/17- STATE FACILITIES | POPHAM, DONALD J. | CONST_COMP | 2017-04-27 | CP: PROJECT CONTINGENCY | 163 | OPEN | 0 | 0 | 0 | 0
PJ0005784 | SPRING STAMPEDE SUPPORT 6/3/17- STATE FACILITIES | POPHAM, DONALD J. | CONST_COMP | 2017-04-27 | EL: GROUND GENERATOR FOR STAMPEDE - JUNE 1 | 163 | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005784 | SPRING STAMPEDE SUPPORT 6/3/17- STATE FACILITIES | POPHAM, DONALD J. | CONST_COMP | 2017-04-27 | MC: MOVE 5 STACKS OF ADA MATS TO SPRTS COMPLX BY JUNE 2 | 163 | CLOSED | 0 | 0 | 204 | 204
PJ0005784 | SPRING STAMPEDE SUPPORT 6/3/17- STATE FACILITIES | POPHAM, DONALD J. | CONST_COMP | 2017-04-27 | SM: SPRING STAMPEDE SUPPORT 6/3/17- STATE FACILITIES | 163 | OPEN | 0 | 0 | 0 | 0
PJ0005784 Total | [7 empty] | 0 | 0 | 526.92 | 526.92
PJ0005783 | SUPPORT FOR EVENING OF GREEN & GOLD 5/4/17 - BLD 43 RM 100 | POPHAM, DONALD J. | CLOSED | 2017-04-27 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005783 | SUPPORT FOR EVENING OF GREEN & GOLD 5/4/17 - BLD 43 RM 100 | POPHAM, DONALD J. | CLOSED | 2017-04-27 | EL: SUPPORT FOR EVENING OF GREEN & GOLD - 5/4 | 043 | CLOSED | 0 | 0 | 1393.116 | 1393.116
PJ0005783 | SUPPORT FOR EVENING OF GREEN & GOLD 5/4/17 - BLD 43 RM 100 | POPHAM, DONALD J. | CLOSED | 2017-04-27 | MC: MOVE ALL CARPET TILES TO REC CENTER LOADING DOCK | 043 | CLOSED | 0 | 0 | 799.0182 | 799.0182
PJ0005783 Total | [7 empty] | 0 | 0 | 2192.1342 | 2192.1342
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | AD: RF KOERBER | 996B | CLOSED | 1797.6 | 0 | 1797.6 | 1797.6
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | AD: STATE FIRE MARSHAL | 996B | CLOSED | 321 | 0 | 114.3402 | 114.3402
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | CP: PROJECT CONTINGENCY | 996B | OPEN | 351.46 | 0 | 0 | 0
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | IN: ADD DOOR TO KITCHEN AREA (984 CHORRO) -BLD 996B RM 203 | 996B | CLOSED | 77.7084 | 0 | 70.644 | 70.644
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | LO: INSTALL LOCK HARDWARE | 996B | CLOSED | 441.0492 | 0 | 280.524 | 280.524
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | PA: PAINT INSTALLED DOOR IN CONFERENCE ROOM | 996B | CLOSED | 877.1856 | 0 | 469.02 | 469.02
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | PM: DOOR INSTALL FOR DT OFFICE 984 CHORRO ST - | 996B | CLOSED | 0 | 0 | 0 | 0
PJ0005782 | ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | MACDONALD, WENDY | CONST_COMP | 2017-04-21 | SM: ADD DOOR TO KITCHEN AREA (984 CHORRO) - BLD 996B RM 203 | 996B | OPEN | 0 | 0 | 0 | 0
PJ0005782 Total | [7 empty] | 3866.0032 | 0 | 2732.1282 | 2732.1282
PJ0005781 | SUPPORT FOR CEP - ARTHRITIS WALK ON O'NEILL LAWN (MAY 12-13) | POPHAM, DONALD J. | CLOSED | 2017-04-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005781 | SUPPORT FOR CEP - ARTHRITIS WALK ON O'NEILL LAWN (MAY 12-13) | POPHAM, DONALD J. | CLOSED | 2017-04-25 | LA: ARTHRITIS WALK SUPPORT (O'NEILL LAWN) MAY 13 | GENERAL | CLOSED | 0 | 0 | 40.032 | 40.032
PJ0005781 | SUPPORT FOR CEP - ARTHRITIS WALK ON O'NEILL LAWN (MAY 12-13) | POPHAM, DONALD J. | CLOSED | 2017-04-25 | SUPPLY RENTAL: ARTHRITIS WALKWATHON | GENERAL | CLOSED | 0 | 0 | 47 | 47
PJ0005781 Total | [7 empty] | 0 | 0 | 87.032 | 87.032
PJ0005779 | INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103 | MACDONALD, WENDY | CONST_COMP | 2017-03-08 | AD: AIRTEK | 024 | CLOSED | 6420 | 0 | 6420 | 6420
PJ0005779 | INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103 | MACDONALD, WENDY | CONST_COMP | 2017-03-08 | CP: PROJECT CONTINGENCY | 024 | OPEN | 866.97 | 0 | 0 | 0
PJ0005779 | INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103 | MACDONALD, WENDY | CONST_COMP | 2017-03-08 | IN: INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103(N/L) | 024 | CLOSED | 141.288 | 0 | 0 | 0
PJ0005779 | INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103 | MACDONALD, WENDY | CONST_COMP | 2017-03-08 | PM: INSPECT DUCTING - BLD 24 RM 103 | 024 | CLOSED | 0 | 0 | 0 | 0
PJ0005779 | INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103 | MACDONALD, WENDY | CONST_COMP | 2017-03-08 | SM: INSPECT DUCTING IN TEACHING KITCHEN - BLD 24 RM 103 | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005779 Total | [7 empty] | 7428.258 | 0 | 6420 | 6420
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | AD: FPCP MANAGEMENT/DESIGN | 041A | OPEN | 1680 | 0 | 0 | 0
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | AD: STATE FIRE MARSHAL | 041A | OPEN | 283.55 | 0 | 0 | 0
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | CP: PROJECT CONTINGENCY | 041A | OPEN | 2639.27 | 0 | 0 | 0
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | CPE: DUNN-REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | 041A | ASSIGNED | 17744.364 | 0 | 8043.654 | 8043.654
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | EL: DUNN- REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | 041A | OPEN | 8081.7984 | 0 | 0 | 0
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | IN: REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | 041A | OPEN | 282.576 | 0 | 0 | 0
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | PM: REMOVE EXISTING A/C, INSTALL NEW HVAC & CARPET - BLD 41A-121 | 041A | OPEN | 0 | 0 | 0 | 0
PJ0005778 | REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | DUNN, TRAVIS | IN_CONSTR | 2017-04-12 | SM: REMOVE EXISTING A/C, INSTALL NEW HVAC - BLD 41A RM 121 | 041A | OPEN | 0 | 0 | 0 | 0
PJ0005778 Total | [7 empty] | 30711.5584 | 0 | 8043.654 | 8043.654
PJ0005777 | CENG ADVISING CENTER REMODEL - BLD 40 LOBBY, 110, 111, 114, 115 | NORTON, DAVE | ESTIMATING | 2017-04-05 | CP: PROJECT CONTINGENCY | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005777 | CENG ADVISING CENTER REMODEL - BLD 40 LOBBY, 110, 111, 114, 115 | NORTON, DAVE | ESTIMATING | 2017-04-05 | PM: CENG ADVISING CENTER WINDOW | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005777 | CENG ADVISING CENTER REMODEL - BLD 40 LOBBY, 110, 111, 114, 115 | NORTON, DAVE | ESTIMATING | 2017-04-05 | SM: CENG ADVISING CTR REMODEL - BLD 40 LOBBY, 110, 111, 114, 115 | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005777 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | AD: (50/50 SPLIT) TRANE | 018A | CLOSED | 42150.51 | 0 | 41154.0725 | 41154.0725
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | AD: (SR) BOB'S CRANE | 018A | CLOSED | 1070 | 0 | 1391 | 1391
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | CA: (SR) BUILD RAMP TO MOVE CHILLER AT DPTC - BLDG 18A | 018A | CLOSED | 522.48 | 0 | 349.347 | 349.347
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | CA: (SR) ELECTRICAL TAGS FOR NEW CHILLER AT DPTC | 018A | CLOSED | 231.24 | 0 | 111.24 | 111.24
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | CP: PROJECT CONTINGENCY | 018A | OPEN | 5880.51 | 0 | 0 | 0
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | CPE: (SR) INSTALL CHILLER AT DPTC | 018A | CLOSED | 5739.84 | 0 | 6786.228 | 6786.228
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | EL: (SPLIT) MATERIALS (ONLY!) FOR NEW CHILLER AT DPTC | 018A | CLOSED | 13980 | 0 | 20415.948 | 20415.948
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | EL: (SR) LABOR (ONLY!) FOR NEW CHILLER AT DPTC | 018A | CLOSED | 3401.7984 | 0 | 5117.2934 | 5117.2934
PJ0005776 | SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | SINE, MARK | CONST_COMP | 2017-03-28 | SM: SR 16/17: REPLACE CHILLER AT DPTC - BLD 18A | 018A | OPEN | 0 | 0 | 0 | 0
PJ0005776 Total | [7 empty] | 72976.3784 | 0 | 75325.1289 | 75325.1289
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: (RL002) THE SIGN PLACE | 038 | CLOSED | 5887.5252 | 0 | 5887.5252 | 5887.5252
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: A-TOWN AUDIO-VIDEO | 038 | CLOSED | 21137.3685 | 0 | 21130.1567 | 21130.1567
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: ALAN'S DRAPERIES | 038 | CLOSED | 21116.45 | 0 | 21116.45 | 21116.45
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: BKM FURNITURE | 038 | CLOSED | 19153 | 0 | 19129.888 | 19129.888
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: HERTZ FURNITURE | 038 | CLOSED | 56909.02 | 0 | 51066.0175 | 51066.0175
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: ITS | 038 | CLOSED | 11282.1014 | 0 | 10242.7034 | 10242.7034
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: JOC 16.040.5775.00 NEWTON | 038 | CLOSED | 346468.3112 | 0 | 346468.3112 | 346468.3112
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: JOC 16.040.5775.01 NEWTON | 038 | CLOSED | 6535.5921 | 0 | 6535.5921 | 6535.5921
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: MCKENNA ENVIRONMENTAL | 038 | CLOSED | 4847.1 | 0 | 4151.6 | 4151.6
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | AD: STATE FIRE MARSHAL | 038 | OPEN | 278.2 | 0 | 57.1701 | 57.1701
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | CA: (RL002) PURCHASE & INSTALL CORK BOARDS IN OFFICES - BLDG 38 | 038 | CLOSED | 789.456 | 0 | 713.04 | 713.04
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | CA: INSTALL CORKBORDS | 038 | CLOSED | 611.82 | 0 | 122.376 | 122.376
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | CP: PROJECT CONTINGENCY | 038 | OPEN | 13201.77 | 0 | 0 | 0
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | CU:BLDG 38-2ND FLOOR ROOM CLEAN AND WAX FLOORS | 038 | CLOSED | 736.824 | 0 | 1344.66 | 1344.66
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | EL: TRADE SUPPORT- BLDG 38 2ND FLOOR CLASSROOMS | 038 | CLOSED | 1417.416 | 0 | 1646.994 | 1646.994
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | ES: RELOCATE THERMOSTAT- BLDG 39-204 | 038 | CLOSED | 656.64 | 0 | 912.912 | 912.912
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | IN: SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | 038 | CLOSED | 466.2504 | 0 | 459.186 | 459.186
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | MO: BLDG 38 MOVE OUT OLD TAB ARM CHAIRS; MOVE IN NEW COMBO DESKS | 038 | CLOSED | 4719.388 | 0 | 1500 | 1500
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | PM: CLASSROOM REFRESH - BLD 38 | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0005775 | SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | NORTON, DAVE | CONST_COMP | 2017-03-21 | SM: SP 17/18, SR 17/18: SSF - CLASSROOM REFRESH - BLD 38 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005775 Total | [7 empty] | 516214.2328 | 0 | 492484.5822 | 492484.5822
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 10073.02 | 0 | 0 | 0
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | EO: REMOVE SHRUBS FOR PAINTING OF AG ERHART/ENGLISH - BLD 10&22 | GENERAL | OPEN | 0 | 0 | 488.034 | 488.034
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | LA: SUPPORT PAINTING OF AG ERHART AND ENGLISH BLDGS (010/022) | GENERAL | COMPLETE | 2401.92 | 0 | 4233.5521 | 4233.5521
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | PA: PAINT EXTERIOR OF AG ERHART & ENGLISH BLDG (010/022) | GENERAL | CLOSED | 98328.3791 | 0 | 67445.0778 | 67445.0778
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | PA: PAINT NORTH SIDE OF BLDG 047 | GENERAL | ASSIGNED | 0 | 0 | 13688.6267 | 13688.6267
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | PCV PA: ASSIST WITH EXTERIOR PAINTING ON BLDG 10 & 22 (PROJECT) | GENERAL | CLOSED | 0 | 0 | 6902.742 | 6902.742
PJ0005771 | SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | POLVI, STEVEN | IN_CONSTR | 2017-03-17 | SM: SR 17/18: CLEAN AND PAINT BLDGS 10 AND 22 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005771 Total | [7 empty] | 110803.3191 | 0 | 92758.0326 | 92758.0326
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | AD: AQUA CENTS | 061 | CLOSED | 0 | 0 | 16041.975 | 16041.975
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | CA: REPAIR HANDRAILS AT SOUTHWEST SIDE OF STADIUM | 061 | CLOSED | 0 | 0 | 441.548 | 441.548
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | CU: SUPPORT FOR RODEO | 061 | CLOSED | 0 | 0 | 2689.393 | 2689.393
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | EL: SUPPORT FOR RODEO CONCERT | 061 | CLOSED | 0 | 0 | 3308.4 | 3308.4
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | LA: (MAINT) PRE-RODEO TURFGRASS WORK | 061 | CLOSED | 0 | 0 | 609.36 | 609.36
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | LA: SUPPORT FOR RODEO | 061 | CLOSED | 0 | 0 | 2066.76 | 2066.76
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | LO: SUPORT FOR RODEO | 061 | CLOSED | 0 | 0 | 225.096 | 225.096
PJ0005770 | SUPPORT FOR 2017 RODEO AT SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2017-03-15 | MC: MOVE ADA MATS TO STADIUM - 4/3 | 061 | CLOSED | 0 | 0 | 138 | 138
PJ0005770 Total | [7 empty] | 0 | 0 | 25520.532 | 25520.532
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: 4LEAF | 113A | CLOSED | 3080.2625 | 0 | 3080.2625 | 3080.2625
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: DEEP BLUE | 113A | CLOSED | 1326.8 | 0 | 1326.8 | 1326.8
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: DESIGN SERVICES | 113A | CLOSED | 1070 | 0 | 1070 | 1070
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: FLOOR CONNECTION | 113A | CLOSED | 10749.22 | 0 | 10749.22 | 10749.22
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: JOC 16.041.5768 MAINO | 113A | CLOSED | 774646.83 | 0 | 774646.83 | 774646.83
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: MCKENNA ENVIRONMENTAL | 113A | CLOSED | 17061.15 | 0 | 12092.07 | 12092.07
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: MIYAMOTO INTERNATIONAL (STRUCTURAL ENGINEERS) | 113A | CLOSED | 2041.025 | 0 | 2041.025 | 2041.025
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | AD: STATE FIRE MARSHAL FEES | 113A | CLOSED | 1284 | 0 | 730.5104 | 730.5104
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | CA:SIERRA MADRE TR ZERO RESTROOM REMODEL SUMMER 2017 | 113A | CLOSED | 1157.73 | 0 | 828.42 | 828.42
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | CP: PROJECT CONTINGENCY | 113A | OPEN | 89330.31 | 0 | 0 | 0
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | EL:SIERRA MADRE TOWER ZERO RESTROOM REMODEL PANEL RELOCATION | 113A | CLOSED | 103893.1486 | 0 | 104201.694 | 104201.694
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | ES:SIERRA MADRE TWR ZERO RESTROOM REMODEL SUMMER 2017 | 113A | CLOSED | 722.304 | 0 | 98.496 | 98.496
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | IN: SIERRA MADRE TOWER ZERO RESTROOM REMODEL - BLD 113A | 113A | CLOSED | 2472.54 | 0 | 1412.88 | 1412.88
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | LO:SIERRA MADRE TWR ZERO RESTROOM REMODEL SUMMER 2017 | 113A | CLOSED | 3648.3936 | 0 | 4254.471 | 4254.471
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | PA:SIERRA MADRE TWR ZERO RESTROOM REMODEL SUMMER 2017 | 113A | CLOSED | 5525.928 | 0 | 2517.816 | 2517.816
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | PL:SIERRA MADRE TOWER ZERO RESTROOM REMODEL | 113A | CLOSED | 33765.576 | 0 | 35832.516 | 35832.516
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | PM: SIERRA MADRE TOWER ZERO RESTROOM REMODEL - BLD 113A | 113A | CLOSED | 0 | 0 | 0 | 0
PJ0005768 | SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | ULM, AARON | CONST_COMP | 2017-03-02 | SM: SIERRA MADRE TOWER 0 RESTROOM RENOVATION - BLD 113A | 113A | OPEN | 0 | 0 | 0 | 0
PJ0005768 Total | [7 empty] | 1051775.2177 | 0 | 954883.0109 | 954883.0109
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | AD: COASTAL DEMO | 052 | CLOSED | 1070 | 0 | 401.25 | 401.25
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | AD: STATE FIRE MARSHAL | 052 | CLOSED | 283.55 | 0 | 130.6791 | 130.6791
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | CA:DUNN- PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 3296.736 | 0 | 4097.7142 | 4097.7142
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | CP: PROJECT CONTINGENCY | 052 | OPEN | 4833.42 | 0 | 0 | 0
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | CPE: DUNN- PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 19689.216 | 0 | 13821.474 | 13821.474
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | CU:DUNN- PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 267.936 | 0 | 73.68 | 73.68
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | EL:DUNN- PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 22087.08 | 0 | 23420.898 | 23420.898
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | ES: PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 - DUNN | 052 | CLOSED | 2587.1424 | 0 | 1254.2562 | 1254.2562
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | IN: PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | LA:DUNN- PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 648.4224 | 0 | 788.616 | 788.616
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | PA: DUNN- PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 1209.5808 | 0 | 371.448 | 371.448
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | PM: PURCHASE & INSTALL DUCTLESS AC UNITS - BLD 52 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005767 | INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | DUNN, TRAVIS | CONST_COMP | 2017-03-06 | SM: INSTALL DUCTLESS A/C UNITS IN OFFICES - BLD 52 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005767 Total | [7 empty] | 56114.3716 | 0 | 44501.3035 | 44501.3035
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | AD: A-TOWN | 038 | CLOSED | 5991.7539 | 0 | 5991.7539 | 5991.7539
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | AD: ITS - BROWN 38/135 INSTALL PROJECTOR MOUNT AND PULL DOWN SCR | 038 | CLOSED | 656.017 | 0 | 656.017 | 656.017
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | AD: STATE FIRE MARSHAL(NO CHARGES) | 038 | CLOSED | 267.5 | 0 | 0 | 0
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | CA: BROWN 38/135 INSTALL PROJECTOR MOUNT AND PULL DOWN SCREEN | 038 | CLOSED | 4492.008 | 0 | 2116.584 | 2116.584
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | CP: PROJECT CONTINGENCY | 038 | OPEN | 1023.15 | 0 | 0 | 0
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | EL: BROWN 38/135 INSTALL PROJECTOR MOUNT AND PULL DOWN SCREEN | 038 | CLOSED | 6881.7984 | 0 | 4204.488 | 4204.488
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | IN: AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | 038 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | PM: AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0005765 | AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | BROWN, CARLA | CONST_COMP | 2017-02-22 | SM: AUDIO VISUAL UPGRADES IN CLASSROOM - BLD 38 RM 135 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005765 Total | [7 empty] | 19594.8033 | 0 | 13145.4529 | 13145.4529
PJ0005764 | SR 17/18: RESPOND TO MAIN WATER LINE LEAK - POLY-P HILL - 3/8/17 | ULM, AARON | CLOSED | 2017-03-10 | AD: G.F. GARCIA | GENERAL | CLOSED | 0 | 0 | 2127.3633 | 2127.3633
PJ0005764 | SR 17/18: RESPOND TO MAIN WATER LINE LEAK - POLY-P HILL - 3/8/17 | ULM, AARON | CLOSED | 2017-03-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005764 | SR 17/18: RESPOND TO MAIN WATER LINE LEAK - POLY-P HILL - 3/8/17 | ULM, AARON | CLOSED | 2017-03-10 | EL: MAIN WATER LEAK ON POLY-P HILL - 3/8/17 | GENERAL | CLOSED | 0 | 0 | 773.136 | 773.136
PJ0005764 | SR 17/18: RESPOND TO MAIN WATER LINE LEAK - POLY-P HILL - 3/8/17 | ULM, AARON | CLOSED | 2017-03-10 | EO: MAIN WATER LEAK ON POLY-P HILL - 3/8/17 (USE WO0803032) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005764 | SR 17/18: RESPOND TO MAIN WATER LINE LEAK - POLY-P HILL - 3/8/17 | ULM, AARON | CLOSED | 2017-03-10 | PL: MAIN WATER LEAK ON POLY-P HILL - 3/8/17 (USE WO0803031) | GENERAL | CLOSED | 0 | 0 | 2369.352 | 2369.352
PJ0005764 Total | [7 empty] | 0 | 0 | 5269.8513 | 5269.8513
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: BKM 23P | 047 | CLOSED | 7378.1743 | 0 | 12151.3373 | 12151.3373
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: BKM 24 (SEE WO0796304) | 047 | CLOSED | 4751.6774 | 0 | 0 | 0
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: HOME DEPOT REFRIDGERATOR | 047 | CLOSED | 589.4523 | 0 | 475.7541 | 475.7541
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: STAPLES HUTCH | 047 | CLOSED | 1910.6883 | 0 | 1910.6883 | 1910.6883
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: STATE FIRE MARSHAL FEES | 047 | CLOSED | 0 | 0 | 114.3402 | 114.3402
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | CA: PJ5763 RENOVATE PSY/CD OFFICE & MAILROOM | 047 | CLOSED | 1460.442 | 0 | 1372.56 | 1372.56
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | CP: PROJECT CONTINGENCY | 047 | OPEN | 129.57 | 0 | 0 | 0
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | IN: RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | 047 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | PA: PAINT MAIL ROOMS IN F.O.N. - BLDG. 47 | 047 | CLOSED | 495.264 | 0 | 544.8 | 544.8
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | PM: RENOVATE PSY/CD MAILROOM - BLD 47 RM 23P | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0005763 | RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | SM: RENOVATE PSY/CD BACK OFFICE & MAILROOM -BLD 47 RM 23P | 047 | OPEN | 0 | 0 | 0 | 0
PJ0005763 Total | [7 empty] | 16785.9123 | 0 | 16640.1239 | 16640.1239
PJ0005762 | OUTDOOR MEETING/STUDY AREA & PROJECT/ACTIVITY SPACE - BLD 20 | DUNN, TRAVIS | DESIGN | 2017-03-03 | AD: RRM DESIGN GROUP | 020 | OPEN | 24567.2 | 24567.2 | 0 | 24567.2
PJ0005762 | OUTDOOR MEETING/STUDY AREA & PROJECT/ACTIVITY SPACE - BLD 20 | DUNN, TRAVIS | DESIGN | 2017-03-03 | CP: PROJECT CONTINGENCY | 020 | OPEN | 2456.72 | 0 | 0 | 0
PJ0005762 | OUTDOOR MEETING/STUDY AREA & PROJECT/ACTIVITY SPACE - BLD 20 | DUNN, TRAVIS | DESIGN | 2017-03-03 | PM: OUTDOOR MEETING/STUDY AREA & PROJECT/ACTIVITY SPACE - BLD 20 | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005762 | OUTDOOR MEETING/STUDY AREA & PROJECT/ACTIVITY SPACE - BLD 20 | DUNN, TRAVIS | DESIGN | 2017-03-03 | SM: OUTDOOR MEETING/STUDY AREA & PROJECT/ACTIVITY SPACE - BLD 20 | 020 | OPEN | 0 | 0 | 0 | 0
PJ0005762 Total | [7 empty] | 27023.92 | 24567.2 | 0 | 24567.2
PJ0005761 | REMOVE BUILT-INS & INSTALL 4 WORKSTATIONS - BLD 36 RM 101 | BROWN, CARLA | HOLD | 2017-03-06 | CP: PROJECT CONTINGENCY | 036 | OPEN | 0 | 0 | 0 | 0
PJ0005761 | REMOVE BUILT-INS & INSTALL 4 WORKSTATIONS - BLD 36 RM 101 | BROWN, CARLA | HOLD | 2017-03-06 | PM: ROOM RENOVATION - BLD 36 RM 101 | 036 | OPEN | 0 | 0 | 0 | 0
PJ0005761 | REMOVE BUILT-INS & INSTALL 4 WORKSTATIONS - BLD 36 RM 101 | BROWN, CARLA | HOLD | 2017-03-06 | SM: REMOVE BUILT-INS & INSTALL 4 WORKSTATIONS - BLD 36 RM 101 | 036 | OPEN | 0 | 0 | 0 | 0
PJ0005761 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: BKM FURNITURE | 070 | CLOSED | 13907.4213 | 0 | 13542.7546 | 13542.7546
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: FLOOR CONNECTION | 070 | CLOSED | 3258.15 | 0 | 3258.15 | 3258.15
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: ITS | 070 | CLOSED | 2140 | 0 | 990.0924 | 990.0924
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | AD: STATE FIRE MARSHAL FEES | 070 | CLOSED | 283.55 | 0 | 264.7929 | 264.7929
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | CA: PJ5760 CREATE OFFICE SPACE BLG. 70 RM. 108A - DUNN | 070 | CLOSED | 5026.656 | 0 | 5381.424 | 5381.424
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | CP: PROJECT CONTINGENCY | 070 | OPEN | 297.96 | 0 | 0 | 0
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | CU: PJ5760 CREATE OFFICE SPACE BLG. 70 RM. 108A - DUNN | 070 | CLOSED | 307.4566 | 0 | 244.076 | 244.076
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | EL: PJ5760 CREATE OFFICE SPACE BLG. 70 RM. 108A - DUNN | 070 | CLOSED | 5412.8291 | 0 | 3148.752 | 3148.752
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | ES: PJ5760 CREATE OFFICE SPACE BLG. 70 RM. 108A - DUNN | 070 | CLOSED | 8467.3536 | 0 | 9367.176 | 9367.176
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | IN: CREATE TEMPORARY OFFICES - BLD 70 RM 108A | 070 | CLOSED | 706.44 | 0 | 353.22 | 353.22
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | PA: PJ5760 CREATE OFFICE SPACE - DUNN | 070 | CLOSED | 802.896 | 0 | 123.816 | 123.816
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | PL: PJ5760 CREATE OFFICE SPACE BLG. 70 RM. 108A - DUNN | 070 | CLOSED | 1847.712 | 0 | 232.9712 | 232.9712
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | PM: CREATE TEMPORARY OFFICES - BLD 70 RM 108A | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0005760 | CREATE TEMPORARY OFFICES - BLD 70 RM 108A | DUNN, TRAVIS | CONST_COMP | 2017-03-03 | SM: CREATE TEMPORARY OFFICES - BLD 70 RM 108A | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005760 Total | [7 empty] | 42458.4245 | 0 | 36907.2251 | 36907.2251
PJ0005758 | REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | ULM, AARON | CONST_COMP | 2017-01-13 | AD: JOC MAINO | 113 | CLOSED | 46415.0913 | 0 | 46415.0913 | 46415.0913
PJ0005758 | REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | ULM, AARON | CONST_COMP | 2017-01-13 | AD: STATE FIRE MARSHAL | 113 | CLOSED | 228.6804 | 0 | 186.0302 | 186.0302
PJ0005758 | REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | ULM, AARON | CONST_COMP | 2017-01-13 | CP: PROJECT CONTINGENCY | 113 | OPEN | 4730.78 | 0 | 0 | 0
PJ0005758 | REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | ULM, AARON | CONST_COMP | 2017-01-13 | IN: REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | 113 | CLOSED | 423.864 | 0 | 141.288 | 141.288
PJ0005758 | REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | ULM, AARON | CONST_COMP | 2017-01-13 | PM: REPAIR/POUR CONCRETE - BLDG 113 | 113 | CLOSED | 0 | 0 | 0 | 0
PJ0005758 | REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | ULM, AARON | CONST_COMP | 2017-01-13 | SM: REPAIR/POUR CONCRETE SLABS & WALKWAYS - BLDG 113 | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005758 Total | [7 empty] | 51798.4157 | 0 | 46742.4095 | 46742.4095
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | CA: INSTALL SIGNAGE FOR I-FIELD IMPROVEMENTS PROJECT | GENERAL | CLOSED | 0 | 0 | 376.155 | 376.155
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 52000 | 0 | 0 | 0
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | EL: MARK UTILITIES FOR I-FIELD IMPROVEMENT PROJECT JUN 12-16, 20 | GENERAL | LONG_TERM | 0 | 0 | 3578.532 | 3578.532
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | LA: PLAN REVIEW FOR I-FIELD IMPROVMENTS | GENERAL | OPEN | 0 | 0 | 307.8152 | 307.8152
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | LA: TREE TRANSPLANT FOR I-FIELD IMPROVMENTS PROJECT | GENERAL | OPEN | 0 | 0 | 1028.808 | 1028.808
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | PL: I-FIELD PROJECT SUPPORT | GENERAL | WORKING | 0 | 0 | 1499.364 | 1499.364
PJ0005757 | MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | PRINCI, COLIN | IN_CONSTR | 2017-02-28 | SM: MJ: IN-HOUSE SUPPORT FOR I-FIELD IMPROVEMENTS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005757 Total | [7 empty] | 52000 | 0 | 6790.6742 | 6790.6742
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | CA: INSTALL SIGNAGE FOR BASEBALL CLUBHOUSE - SPORTS COMPLEX | 160 | CLOSED | 0 | 0 | 646.227 | 646.227
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | CP: PROJECT CONTINGENCY | 160 | OPEN | 5000 | 0 | 0 | 0
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | EL: LOCATE UTILITIES FOR SPORTS COMPLEX PROJECT | 160 | LONG_TERM | 0 | 0 | 20402.091 | 20402.091
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | IN: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | 160 | ASSIGNED | 0 | 0 | 459.186 | 459.186
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | LA: LOCATE UTILITIES FOR SPORTS COMPLEX PROJECT | 160 | OPEN | 0 | 0 | 3916.421 | 3916.421
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | PL: LOCATE UTILITIES FOR SPORTS COMPLEX PROJECT | 160 | LONG_TERM | 0 | 0 | 6216.1225 | 6216.1225
PJ0005756 | MJ: IN-HOUSE SUPPORT FOR SPORTS COMPLEX CLUBHOUSE & BLEACHERS | CREEL, AUSTIN | IN_CONSTR | 2017-02-28 | SM: MJ: IN-HOUSE SUPPORT FOR SPORTS CPLX CLUBHOUSE & BLEACHERS | 160 | OPEN | 0 | 0 | 0 | 0
PJ0005756 Total | [7 empty] | 5000 | 0 | 31640.0475 | 31640.0475
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: B&B TECHNICAL SERVICES | 058 | CLOSED | 258.9507 | 0 | 258.9507 | 258.9507
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: BKM OFFICE ENVIRONMENTS | 058 | CLOSED | 46365.4861 | 0 | 46623.9125 | 46623.9125
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: FLOOR CONNECTION | 058 | CLOSED | 4927.35 | 0 | 4927.35 | 4927.35
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: ITS BLDG 58 RMS 109A, 108A DREAM CENTER | 058 | CLOSED | 8694.0282 | 0 | 8519.5112 | 8519.5112
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: J.L. FASULO DRYWALL | 058 | CLOSED | 5569.2858 | 0 | 5583.26 | 5583.26
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: MEATHEAD MOVERS | 058 | CLOSED | 4952.3024 | 0 | 6044.9222 | 6044.9222
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: MTI ELECTRICAL | 058 | CLOSED | 5350 | 0 | 5602.52 | 5602.52
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: QUAGLINO ROOFING | 058 | CLOSED | 2140 | 0 | 508.25 | 508.25
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: SIGN PLACE | 058 | CLOSED | 350.3929 | 0 | 350.3929 | 350.3929
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | AD: STATE FIRE MARSHAL | 058 | CLOSED | 428 | 0 | 158.8094 | 158.8094
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | CA:BLDG 58, RM 108A, 109A CABINET DETACH, NEW DOOR | 058 | CLOSED | 5845.26 | 0 | 4744.755 | 4744.755
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | CP: PROJECT CONTINGENCY | 058 | OPEN | 0 | 0 | 0 | 0
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | CPE:BLDG 58 ROOM 109A-SUPPLY AND INSTALL NEW HVAC UNIT | 058 | CLOSED | 10573.824 | 0 | 7122.654 | 7122.654
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | CU: | 058 | CLOSED | 368.412 | 0 | 297.288 | 297.288
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | EL:BLDG 58, RMS 109A 108A DREAM CENTER | 058 | CLOSED | 5692.248 | 0 | 7362.954 | 7362.954
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | IN: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | 058 | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | LA: REMOVE BEE SWARM FROM CAVITY IN WALL - BLDG 58 RM. 109A | 058 | CLOSED | 400.32 | 0 | 195.828 | 195.828
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | LO: BLDG 58, RMS 109A, 108A DREAM CENTER | 058 | CLOSED | 1496.1312 | 0 | 1235.46 | 1235.46
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | MO:BLDG 58, RMS 109A, 108A DREAM CENTER | 058 | CLOSED | 804.384 | 0 | 195 | 195
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | PA: PJ5755 SP 16/17: DREAM CENTER | 058 | CLOSED | 3748.7424 | 0 | 2173.2 | 2173.2
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | PL:BLDG. 58 ROOM 109A-REMOVE SINK AND CAP-OFF | 058 | CLOSED | 515.6208 | 0 | 228.936 | 228.936
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | PM: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 RM 108 | 058 | CLOSED | 0 | 0 | 0 | 0
PJ0005755 | SP 16/17: DREAM CENTER - CREATE OFFICE SPACE - BLD 58 108A & 109 | BROWN, CARLA | CONST_COMP | 2017-02-23 | SM: SP 16/17: DREAM CTR- CREATE OFFICE SPACE - BLD 58 108A & 109 | 058 | OPEN | 0 | 0 | 0 | 0
PJ0005755 Total | [7 empty] | 108692.6705 | 0 | 102310.5639 | 102310.5639
PJ0005754 | SR 17/18: REMOVE FALLEN TREE & REPAIR STORM DAMAGE - BLD 3 | FLEDDERMAN, JUDE | CLOSED | 2017-02-20 | AD: BOBS CRANE | 003 | CLOSED | 0 | 0 | 642 | 642
PJ0005754 | SR 17/18: REMOVE FALLEN TREE & REPAIR STORM DAMAGE - BLD 3 | FLEDDERMAN, JUDE | CLOSED | 2017-02-20 | AD: GREENVALE TREE SERVICE | 003 | CLOSED | 0 | 0 | 1310.75 | 1310.75
PJ0005754 | SR 17/18: REMOVE FALLEN TREE & REPAIR STORM DAMAGE - BLD 3 | FLEDDERMAN, JUDE | CLOSED | 2017-02-20 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005754 | SR 17/18: REMOVE FALLEN TREE & REPAIR STORM DAMAGE - BLD 3 | FLEDDERMAN, JUDE | CLOSED | 2017-02-20 | EO: SUPPORT FOR FALLEN TREE/STORM DAMAGE CLEAN-UP AT BUSINESS 03 | 003 | CLOSED | 0 | 0 | 128.43 | 128.43
PJ0005754 | SR 17/18: REMOVE FALLEN TREE & REPAIR STORM DAMAGE - BLD 3 | FLEDDERMAN, JUDE | CLOSED | 2017-02-20 | LA: SUPPORT FOR FALLEN TREE/STORM DAMAGE CLEAN-UP AT BUSINESS 03 | 003 | CLOSED | 0 | 0 | 1206.288 | 1206.288
PJ0005754 | SR 17/18: REMOVE FALLEN TREE & REPAIR STORM DAMAGE - BLD 3 | FLEDDERMAN, JUDE | CLOSED | 2017-02-20 | PL: RESPOND TO FALLEN TREE NEAR BUSINESS BUILDING | 003 | CLOSED | 0 | 0 | 212.832 | 212.832
PJ0005754 Total | [7 empty] | 0 | 0 | 3500.3 | 3500.3
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: ARCADIS CM SERVICES (BIDDING) | RESIDENCE | OPEN | 107000 | 10523.45 | 77815.75 | 88339.2
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: BOB'S CRANE | RESIDENCE | OPEN | 1926 | 0 | 1926 | 1926
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: BRANDOW JOHNSON | RESIDENCE | OPEN | 9844 | 7383 | 2461 | 9844
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: CANNON | RESIDENCE | OPEN | 280313.25 | 54321.1822 | 218528.8178 | 272850
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: EARTH SYSTEMS PACIFIC | RESIDENCE | OPEN | 415492.77 | 63259.4593 | 352233.3107 | 415492.77
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: FENCE FACTORY | RESIDENCE | CLOSED | 5649.6 | 156.327 | 5493.273 | 5649.6
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: FUGRO | RESIDENCE | OPEN | 16050 | 5237.65 | 10812.35 | 16050
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: GARCIA AND SONS | RESIDENCE | CLOSED | 25112.2366 | 0 | 25112.2366 | 25112.2366
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: GREENVALE TREE SERVICE | RESIDENCE | CLOSED | 13241.25 | 0 | 13241.25 | 13241.25
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: HERC | RESIDENCE | OPEN | 37450 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: JOC 16.038.031 & 16.041.5753 MAINO | RESIDENCE | CLOSED | 893420.9388 | 0 | 893420.9388 | 893420.9388
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: MAINO | RESIDENCE | CLOSED | 8346 | 0 | 8346 | 8346
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: PRINTING AND SHIPPING | RESIDENCE | OPEN | 500 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: SLO COUNTY AIR POLLUTION CONTROL DISTRICT | RESIDENCE | OPEN | 205.4186 | 0 | 205.4186 | 205.4186
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: SPECIALTY CONSTRUCTION | RESIDENCE | OPEN | 1070000 | 0 | 883045.5019 | 883045.5019
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 535 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | AD: SWCA | RESIDENCE | OPEN | 21400 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | CA: CREATE AND INSTALL SIGNAGE TO CLOSE ACCESS TO POLY P | RESIDENCE | CLOSED | 417.15 | 0 | 417.15 | 417.15
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | CA: DELINEATE SLIDING HILL SIDE AND BOARD UP WINDOW - FREMONT | RESIDENCE | CLOSED | 5654.0358 | 0 | 5654.238 | 5654.238
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 123318.99 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | CU: MONITOR MUD SLIDE ON EAST SIDE OF FREMONT | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | EL: LOCATE/CHECK FOR UTILITIES IN LANDSLIDE AREA BEHIND FREMONT | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | EO: MAIN WATER LEAK ON POLY-P HILL - 3/8/17 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | EO: SUPPORT FOR FREMONT LANDSLIDE | RESIDENCE | OPEN | 256.86 | 0 | 256.86 | 256.86
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | ES: MONITOR MUD SLIDE ON EAST SIDE OF FREMONT | RESIDENCE | CLOSED | 196.992 | 0 | 196.992 | 196.992
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | LA: SUPPORT FOR FREMONT LANDSLIDE | RESIDENCE | ASSIGNED | 3852.492 | 0 | 3852.5243 | 3852.5243
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | LO: CORE CHANGE TO ORANGE CONTRUCTION CORE / FREMONT 109 - 122 | RESIDENCE | CLOSED | 60.924 | 0 | 60.924 | 60.924
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | LO: KEYS AND CORES FOR OVERFLOW ROOMS AT SOUTH MTN. RES HALLS | RESIDENCE | CLOSED | 152.31 | 0 | 152.31 | 152.31
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | LO: KEYS AND CORES FOR OVERFLOW ROOMS AT YOSEMITE | RESIDENCE | CLOSED | 456.93 | 0 | 456.93 | 456.93
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | MO: MOVING SUPPORT FOR LANDSLIDE AT FREMONT DORM | RESIDENCE | CLOSED | 330.1326 | 0 | 330 | 330
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | PCV ES: MONITOR LANDSLIDE BEHIND FREMONT | RESIDENCE | CLOSED | 98.496 | 0 | 98.496 | 98.496
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | PCV PL: ASSIST WITH TESTING WATER MAIN PRESSURE FROM RESERVOIR | RESIDENCE | OPEN | 515.904 | 0 | 515.904 | 515.904
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | PL: FREMONT LANDSLIDE SUPPORT | RESIDENCE | CLOSED | 24978.4711 | 0 | 27305.8018 | 27305.8018
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | PL: MAIN WATER LEAK ON POLY-P HILL | RESIDENCE | CLOSED | 0 | 0 | 35.472 | 35.472
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | PM: SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | RE: DUMPSTER RELOCATION AT FREMONT DORM | RESIDENCE | OPEN | 174.432 | 0 | 174.432 | 174.432
PJ0005753 | SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | ULM, AARON | PUNCH_LIST | 2017-02-20 | SM: SR 17/18: LANDSLIDE REMEDIATION BEHIND FREMONT HALL - 109 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005753 Total | [7 empty] | 3066950.5835 | 140881.0685 | 2532149.8814 | 2673030.9499
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | CA: SUPPORT FOR 2017 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 570.12 | 570.12
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | CA: UPD BOARD AND STANCHION REQUEST | GENERAL | CLOSED | 0 | 0 | 672.075 | 672.075
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | CPE: SUPPORT FOR OPEN HOUSE - SATURDAY APRIL 8 | GENERAL | CLOSED | 0 | 0 | 481.52 | 481.52
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | CU: SUPPORT FOR 2017 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 2621.3177 | 2621.3177
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | EL: SUPPORT FOR 2017 OPEN HOUSE - APRIL 7 & 8 | GENERAL | CLOSED | 0 | 0 | 1589.2375 | 1589.2375
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | ES: SUPPORT FOR 2017 OPEN HOUSE- APRIL 8 | GENERAL | CLOSED | 0 | 0 | 240.76 | 240.76
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | LA: SUPPORT FOR 2017 OPEN HOUSE - APRIL 7 & 8 | GENERAL | CLOSED | 0 | 0 | 4545.618 | 4545.618
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | MC: 2017 OPEN HOUSE SUPPORT | GENERAL | CLOSED | 0 | 0 | 208.24 | 208.24
PJ0005751 | SUPPORT FOR 2017 OPEN HOUSE (MAINT) - PROJECT | POPHAM, DONALD J. | CLOSED | 2017-02-09 | PL: SUPPORT FOR 2017 OPEN HOUSE - APIRL 7 & 8 | GENERAL | CLOSED | 0 | 0 | 8583.3888 | 8583.3888
PJ0005751 Total | [7 empty] | 0 | 0 | 19512.277 | 19512.277
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | AD: ASAP | 014 | OPEN | 150.0033 | 0 | 80.5603 | 80.5603
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | AD: GOSS ENGINEERING | 014 | OPEN | 26964 | 10785.6 | 16178.4 | 26964
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | AD: STATE FIRE MARSHAL | 014 | OPEN | 535 | 0 | 0 | 0
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | CP: PROJECT CONTINGENCY | 014 | OPEN | 3616.23 | 0 | 0 | 0
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | CPE: | 014 | OPEN | 72.2304 | 0 | 0 | 0
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | EH&S: | 014 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | EL: PROVIDE SUPPORT FOR AHU 1 REPAIRS - BLDG. 15 | 014 | CLOSED | 425.2248 | 0 | 322.14 | 322.14
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | ES: REMOVE AND REPLACE AIR HANDLERS 1 & 2 - BLDG. 14 | 014 | CLOSED | 9390.6086 | 0 | 8745.2918 | 8745.2918
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | IN: SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | 014 | ASSIGNED | 70.644 | 0 | 70.644 | 70.644
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | LO: | 014 | OPEN | 134.0328 | 0 | 0 | 0
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | PM: SR 17/18: AHU - 1& 2 SPECIAL REPAIR - BLD 14 | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005750 | SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | KOLEGRAFF, KENNETH | ESTIMATING | 2017-02-10 | SM: SR 17/18: REMOVE & REPLACE AIR HANDLERS 1 & 2 - BLD 14 | 014 | OPEN | 0 | 0 | 0 | 0
PJ0005750 Total | [7 empty] | 41428.7787 | 10785.6 | 25397.0361 | 36182.6361
PJ0005749 | INSTALLATION OF CONE CALORIMETER - BLD 13 RM 126 | DUNN, TRAVIS | ESTIMATING | 2017-02-01 | AD: STATE FIRE MARSHALL FEES | 013 | OPEN | 0 | 114.3402 | 0 | 114.3402
PJ0005749 | INSTALLATION OF CONE CALORIMETER - BLD 13 RM 126 | DUNN, TRAVIS | ESTIMATING | 2017-02-01 | CP: PROJECT CONTINGENCY | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005749 | INSTALLATION OF CONE CALORIMETER - BLD 13 RM 126 | DUNN, TRAVIS | ESTIMATING | 2017-02-01 | PM: INSTALLATION OF CONE CALORIMETER IN BUILDING 13 ROOM 126 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005749 | INSTALLATION OF CONE CALORIMETER - BLD 13 RM 126 | DUNN, TRAVIS | ESTIMATING | 2017-02-01 | SM: INSTALLATION OF CONE CALORIMETER - BLD 13 RM 126 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005749 Total | [7 empty] | 0 | 114.3402 | 0 | 114.3402
PJ0005748 | INSTALL DOUBLE WIDE DOOR & ELECTRICAL - BLD 21 RM 9B | DUNN, TRAVIS | SCOPE_DEV | 2017-01-26 | CP: PROJECT CONTINGENCY | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005748 | INSTALL DOUBLE WIDE DOOR & ELECTRICAL - BLD 21 RM 9B | DUNN, TRAVIS | SCOPE_DEV | 2017-01-26 | PM: INSTALL DOUBLE WIDE DOOR - BLD 21 RM 9B | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005748 | INSTALL DOUBLE WIDE DOOR & ELECTRICAL - BLD 21 RM 9B | DUNN, TRAVIS | SCOPE_DEV | 2017-01-26 | SM: INSTALL DOUBLE WIDE DOOR & ELECTRICAL - BLD 21 RM 9B | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005748 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | AD: THE SIGN PLACE | GENERAL | OPEN | 5418.2767 | 481.9815 | 4936.2952 | 5418.2767
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | CA: DUNN-SR16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | GENERAL | ASSIGNED | 4247.28 | 0 | 4160.616 | 4160.616
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 835.67 | 0 | 0 | 0
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | IN: SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | GENERAL | ASSIGNED | 1130.304 | 0 | 176.61 | 176.61
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | LO: DUNN-SR16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | GENERAL | ASSIGNED | 988.0656 | 0 | 955.434 | 955.434
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | PA: DUNN-SR16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | GENERAL | OPEN | 1874.3712 | 0 | 0 | 0
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | PM: SR16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005747 | SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | DUNN, TRAVIS | IN_CONSTR | 2017-01-27 | SM: SR 16/17: INSTALL ALL GENDER RESTROOM SIGNS - CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005747 Total | [7 empty] | 14493.9675 | 481.9815 | 10228.9552 | 10710.9367
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | CA: SUPPORT EVENT AT SPANOS THEATRE - JAN 31, 2017 | 044 | CLOSED | 0 | 0 | 470.91 | 470.91
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | EL: SUPPORT FOR EVENT AT SPANOS THEATRE - JANUARY 31, 2017 | 044 | CLOSED | 0 | 0 | 1237.295 | 1237.295
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | LA: SUPPORT FOR EVENT AT SPANOS THEATRE - 1/31 | 044 | CLOSED | 0 | 0 | 375.2972 | 375.2972
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | LO: 6 BARRICADE LOCKS CHECKED OUT | 044 | CLOSED | 0 | 0 | 60 | 60
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | MC: SUPPORT FOR EVENT AT SPANOS THEATRE - JAN 31, 2017 | 044 | CLOSED | 0 | 0 | 170 | 170
PJ0005746 | SUPPORT FOR POLITICAL SPEAKER - 44 SPANOS THEATRE (WED FEB 1ST) | POPHAM, DONALD J. | CLOSED | 2017-01-27 | PL: SUPPORT FOR EVENT AT SPANOS THEATRE - JAN 31 | 044 | CLOSED | 0 | 0 | 427.26 | 427.26
PJ0005746 Total | [7 empty] | 0 | 0 | 2740.7622 | 2740.7622
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | AD: HPS MECHANICAL | U-UDOR | OPEN | 32790.15 | 0 | 32790.15 | 32790.15
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | AD: MAINO (EMERGENCY WORK) | U-UDOR | OPEN | 64902.99 | 0 | 64902.99 | 64902.99
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | CP: PROJECT CONTINGENCY | U-UDOR | OPEN | 678.99 | 0 | 0 | 0
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | CPE: REPAIR UTILIDOR LEAK NEAR BUILDING 15 | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | CPE: REPAIR UTILIDOR LEAK NEAR BUILDING 26M | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | CPE: UTILIDOR LEAK NEAR THE EOC ON NORTH PERIMETER | U-UDOR | OPEN | 3549.3787 | 0 | 1751.466 | 1751.466
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | ES: | U-UDOR | OPEN | 722.304 | 0 | 0 | 0
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | PL: ATL UTILITODR LEAK | U-UDOR | CLOSED | 4401.36 | 0 | 4649.58 | 4649.58
PJ0005745 | SR 16/17: UTILIDOR LEAK REPAIRS | SINE, MARK | IN_CONSTR | 2017-01-20 | SM: SR 16/17: UTILIDOR LEAK REPAIRS | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005745 Total | [7 empty] | 107045.1727 | 0 | 104094.186 | 104094.186
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: BOWEN | 001 | OPEN | 3210 | 0 | 3210 | 3210
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: COASTAL PAINTING | 001 | OPEN | 6152.5 | 0 | 6152.5 | 6152.5
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: DEFINITELY DIFFERENT DESIGNS GLASS ETCHED SIGN | 001 | OPEN | 3987.8258 | 1991.6124 | 1993.9129 | 3985.5253
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: RICK MCKENNA | 001 | OPEN | 1605 | 362.73 | 1097.82 | 1460.55
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: SANTA MARIA ACOUSTICS | 001 | OPEN | 4904.88 | 0 | 4904.88 | 4904.88
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: SIGN PLACE | 001 | OPEN | 9951 | 6696.6913 | 2570.3647 | 9267.056
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | AD: STATE FIRE MARSHAL | 001 | OPEN | 278.2 | 0 | 125.7785 | 125.7785
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | CA: DRYWALL & CARPENTRY | 001 | ASSIGNED | 4247.28 | 0 | 880.632 | 880.632
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | CP: PROJECT CONTINGENCY | 001 | OPEN | 1824.77 | 0 | 0 | 0
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | EL: NEW LIGHTING | 001 | CLOSED | 9052.248 | 0 | 5234.004 | 5234.004
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | IN: 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | 001 | ASSIGNED | 310.8336 | 0 | 70.644 | 70.644
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | LO: BLDG 1-3RD FLOOR- ADJUST CLOSERS AND LOCKS | 001 | CLOSED | 304.62 | 0 | 410.772 | 410.772
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | PL: INSTALL NEW HYDRATION STATION | 001 | COMPLETE | 3423.42 | 0 | 3509.052 | 3509.052
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | PM: 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005743 | 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | NORTON, DAVE | IN_CONSTR | 2017-01-12 | SM: 3RD FLR CORRIDOR SIGNAGE/REBRANDING - BLDG 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005743 Total | [7 empty] | 49252.5774 | 9051.0337 | 30160.3601 | 39211.3938
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | AD: ISES (CORP ADMIN BLDG) | GENERAL | OPEN | 0 | 0 | 1015.43 | 1015.43
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | AD: ISES (HEALTH CENTER) | GENERAL | OPEN | 0 | 0 | 2427.83 | 2427.83
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | AD: ISES (PERFORMING ARTS CENTER) | GENERAL | OPEN | 6944.3 | 0 | 6944.3 | 6944.3
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | AD: ISES (STATE FACILITIES) | GENERAL | OPEN | 0 | 0 | 210570.65 | 210570.65
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | AD: ISES (UNIVERSITY HOUSE) | GENERAL | OPEN | 0 | 0 | 495.41 | 495.41
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | CA: SUPPORT FACILTIY CONDITION ASSESSMENTS (STATE, 15, 27, 51) | GENERAL | CLOSED | 0 | 0 | 166.86 | 166.86
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | EL: SUPPORT FACILTIY CONDITION ASSESSMENTS (STATE, 15, 27, 51) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | ES: SUPPORT FACILTIY CONDITION ASSESSMENTS (STATE, 15, 27, 51) | GENERAL | CLOSED | 0 | 0 | 6254.496 | 6254.496
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | ES: SUPPORT PAC FACILITY ASSESSMENT - BLDG. 06 | GENERAL | CLOSED | 1272.272 | 0 | 295.488 | 295.488
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | LO: SUPPORT FACILTIY CONDITION ASSESSMENTS (STATE, 15, 27, 51) | GENERAL | CLOSED | 0 | 0 | 304.62 | 304.62
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | PCV ES: SUPPORT FACILITY CONDITION ASSESSMENT(STATE, 15, 27, 51) | GENERAL | CLOSED | 0 | 0 | 577.824 | 577.824
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | PL: SUPPORT FACILTIY CONDITION ASSESSMENTS (STATE, 15, 27, 51) | GENERAL | CLOSED | 0 | 0 | 1534.872 | 1534.872
PJ0005742 | FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2017-01-18 | SM: FACILITY CONDITION ASSESSMENTS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005742 Total | [7 empty] | 8216.572 | 0 | 230587.78 | 230587.78
PJ0005741 | STATE FIRE MARSHAL REPORT - DOOR CORRECTIONS - BLD 19 | DUNN, TRAVIS | ESTIMATING | 2017-01-09 | CP: PROJECT CONTINGENCY | 019 | OPEN | 0 | 0 | 0 | 0
PJ0005741 | STATE FIRE MARSHAL REPORT - DOOR CORRECTIONS - BLD 19 | DUNN, TRAVIS | ESTIMATING | 2017-01-09 | PM: STATE FIRE MARSHAL REPORT - DOOR CORRECTIONS - BD 19 | 019 | OPEN | 0 | 0 | 0 | 0
PJ0005741 | STATE FIRE MARSHAL REPORT - DOOR CORRECTIONS - BLD 19 | DUNN, TRAVIS | ESTIMATING | 2017-01-09 | SM: STATE FIRE MARSHAL REPORT - DOOR CORRECTIONS - BLD 19 | 019 | OPEN | 0 | 0 | 0 | 0
PJ0005741 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005739 | INSTALL KEY CARD SYSTEM - BLDG 24 RMS106/107 | BROWN, CARLA | HOLD | 2016-09-19 | CP: PROJECT CONTINGENCY | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005739 | INSTALL KEY CARD SYSTEM - BLDG 24 RMS106/107 | BROWN, CARLA | HOLD | 2016-09-19 | PM: INSTALL KEY CARD SYSTEM - BLDG 24 RMS106/107 | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005739 | INSTALL KEY CARD SYSTEM - BLDG 24 RMS106/107 | BROWN, CARLA | HOLD | 2016-09-19 | SM: INSTALL KEY CARD SYSTEM - BLDG 24 RMS106/107 | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005739 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | AD: SFM (NO CHARGES) | 026 | CLOSED | 535 | 0 | 0 | 0
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | CP: PROJECT CONTINGENCY | 026 | OPEN | 849.14 | 0 | 0 | 0
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | EL: BLDG 26 COMPRESSOR MOTOR REPLACEMENT - KOLEGRAFF | 026 | CLOSED | 4417.416 | 0 | 3020.682 | 3020.682
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | ES: BLDG 26 COMPRESSOR MOTOR REPLACEMENT - KOLEGRAFF | 026 | CLOSED | 3397.4256 | 0 | 2005.968 | 2005.968
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | IN: REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | 026 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | PM: REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005738 | REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-25 | SM: REPLACE FAILING DEPT. AIR COMPRESSOR - BLD 26 RM 121 | 026 | OPEN | 0 | 0 | 0 | 0
PJ0005738 Total | [7 empty] | 9269.6256 | 0 | 5097.294 | 5097.294
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | AD: ITS | 001 | OPEN | 1070 | 0 | 0 | 0
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | AD: JOC 16.040 NEWTON | 001 | OPEN | 124358.61 | 35669.1241 | 79258.0779 | 114927.202
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | AD: MCKENNA | 001 | OPEN | 9569.01 | 0 | 9550.82 | 9550.82
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | AD: SFM | 001 | OPEN | 535 | 0 | 0 | 0
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | CP: PROJECT CONTINGENCY | 001 | OPEN | 15793.47 | 0 | 0 | 0
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | CU: | 001 | OPEN | 368.412 | 0 | 0 | 0
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | EH&S: | 001 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | EL: PROVIDE SUPPORT/REMOVE & REPLACE LIGHTS 125A - KOLEGRAFF | 001 | CLOSED | 2017.416 | 0 | 707.1636 | 707.1636
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | ES: PROVIDE SUPPORT AND SAFE OFF - KOLEGRAFF | 001 | ASSIGNED | 17778.432 | 0 | 5013.798 | 5013.798
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | IN: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | 001 | ASSIGNED | 70.644 | 0 | 70.644 | 70.644
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | LO: | 001 | ASSIGNED | 134.0328 | 0 | 91.386 | 91.386
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | PA: PAINT WALLS & DOOR CASINGS ROOM 125A - KOLEGRAFF | 001 | CLOSED | 1961.976 | 0 | 1245.168 | 1245.168
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | PM: REPLACE FAILED HVAC STATIC DAMPER ACTUATORS - ADM 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005735 | DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS - ADM 01 | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-06 | SM: DM 16/17 SP 17/18: REPLACE FAILED HVAC DAMPER ACTUATORS-BLD1 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005735 Total | [7 empty] | 173727.8076 | 35669.1241 | 95937.0575 | 131606.1816
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | AD: PMSM | 033 | OPEN | 14819.5 | 1257.25 | 13562.25 | 14819.5
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | AD: STATE FIRE MARSHAL FEES | 033 | OPEN | 535 | 0 | 0 | 0
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | CP: PROJECT CONTINGENCY | 033 | OPEN | 1562.48 | 0 | 0 | 0
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | IN: DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | 033 | ASSIGNED | 141.288 | 0 | 35.322 | 35.322
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | PL: | 033 | OPEN | 128.976 | 0 | 0 | 0
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | PM: DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | 033 | OPEN | 0 | 0 | 0 | 0
PJ0005734 | DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | DILLON, JEFFREY | ESTIMATING | 2017-01-06 | SM: DM 16/17: CONVERT RESTROOMS TO ADA COMPLIANCE - BLD 33 | 033 | OPEN | 0 | 0 | 0 | 0
PJ0005734 Total | [7 empty] | 17187.244 | 1257.25 | 13597.572 | 14854.822
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | CA: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMP | GENERAL | ASSIGNED | 73934.5086 | 0 | 31288.7531 | 31288.7531
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 7848.16 | 0 | 0 | 0
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | EL: | GENERAL | OPEN | 1303.062 | 0 | 0 | 0
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | EO: | GENERAL | OPEN | 9041.9857 | 0 | 0 | 0
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | LA: SUPPORT CONCRETE REPLACEMENT WORK | GENERAL | OPEN | 1761.408 | 0 | 6293.4893 | 6293.4893
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | PL: SUPPORT SIDEWALKS/CURBS/GUTTERS/ADA RAMPS PROJECT | GENERAL | COMPLETE | 755.904 | 0 | 96.732 | 96.732
PJ0005732 | DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | POLVI, STEVEN | IN_CONSTR | 2017-01-06 | SM: DM 16/17: REPAIR SIDEWALKS/CURBS/GUTTERS/ADA RAMPS - CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005732 Total | [7 empty] | 94645.0283 | 0 | 37678.9743 | 37678.9743
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | AD: FPCP MANAGEMENT/DESIGN | GENERAL | OPEN | 2800 | 0 | 0 | 0
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | AD: OMNI TOSA | GENERAL | OPEN | 23400.9 | 20190.9 | 3210 | 23400.9
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 2381.9 | 0 | 0 | 0
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | LA: | GENERAL | OPEN | 160.128 | 0 | 0 | 0
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | PL: | GENERAL | OPEN | 257.952 | 0 | 0 | 0
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | PM: DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005730 | DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | KUENTZEL, DOUGLAS A. | ESTIMATING | 2017-01-06 | SM: DM 16/17: LANDSCAPING IMPROVEMENTS W/ SIDEWALK - 116/117 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005730 Total | [7 empty] | 29000.88 | 20190.9 | 3210 | 23400.9
PJ0005729 | DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | POLVI, STEVEN | IN_CONSTR | 2017-01-05 | AD: ASAP REPROGRAPHICS | GENERAL | OPEN | 0 | 0 | 73.3485 | 73.3485
PJ0005729 | DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | POLVI, STEVEN | IN_CONSTR | 2017-01-05 | AD: POWER ENGINEERING SYSTEMS (PES) | GENERAL | OPEN | 11556 | 0 | 11556 | 11556
PJ0005729 | DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | POLVI, STEVEN | IN_CONSTR | 2017-01-05 | AD: R.K. POWER ENGINEERING, INC. | GENERAL | OPEN | 10700 | 0 | 2996 | 2996
PJ0005729 | DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | POLVI, STEVEN | IN_CONSTR | 2017-01-05 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 20915.02 | 0 | 0 | 0
PJ0005729 | DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | POLVI, STEVEN | IN_CONSTR | 2017-01-05 | EL:PERFORM MAINT OF UTILITY POLES (FEEDER Z) | GENERAL | OPEN | 196310.0657 | 0 | 42480.042 | 42480.042
PJ0005729 | DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | POLVI, STEVEN | IN_CONSTR | 2017-01-05 | SM: DM 16/17: FEEDER Z ELECTRICAL DISTRIBUTION UPGRADE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005729 Total | [7 empty] | 239481.0857 | 0 | 57105.3905 | 57105.3905
PJ0005728 | SR 17/18: DESIGN & SCOPE: SCADA REPLACEMENT - GENERAL | POLVI, STEVEN | SCOPE_DEV | 2017-01-05 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005728 | SR 17/18: DESIGN & SCOPE: SCADA REPLACEMENT - GENERAL | POLVI, STEVEN | SCOPE_DEV | 2017-01-05 | SM: SR 17/18: DESIGN & SCOPE: SCADA REPLACEMENT - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005728 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | AD: ALAN'S DRAPERIES | 034 | OPEN | 12829.3 | 0 | 12829.3 | 12829.3
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | AD: FLOOR CONNECTION | 034 | OPEN | 2471.7 | 0 | 1883.2 | 1883.2
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | AD: JOC 16.040.5726 NEWTON | 034 | OPEN | 36557.8661 | 614.0195 | 35943.8466 | 36557.8661
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | AD: STATE FIRE MARSHAL | 034 | OPEN | 278.2 | 0 | 0 | 0
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | CA: BLDG 34-252: INSTALL WALL PANELS | 034 | CLOSED | 244.728 | 0 | 580.0967 | 580.0967
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | CP: PROJECT CONTINGENCY | 034 | OPEN | 0.16 | 0 | 0 | 0
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | EL: | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | ES: | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | IN: SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | 034 | ASSIGNED | 233.1252 | 0 | 70.644 | 70.644
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | MO:MOVE FURNITURE FOR PAINTING- BLDG 34-252 | 034 | CLOSED | 1014.1942 | 0 | 990 | 990
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | PA: PAINT WALLS AND CEILING | 034 | CLOSED | 13296.4271 | 0 | 12267.4704 | 12267.4704
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | PM: SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005726 | SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | NORTON, DAVE | CONST_COMP | 2017-01-05 | SM: SR 17/18: REPAIR CEILING - BLD 34 RMS 227-228; 252-262 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005726 Total | [7 empty] | 66925.7005 | 614.0195 | 64564.5577 | 65178.5772
PJ0005724 | SR 17/18: FALL PROTECTION PHASES 3-6 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005724 | SR 17/18: FALL PROTECTION PHASES 3-6 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | PM: SR 17/18: FALL PROTECTION PHASES 3-6 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005724 | SR 17/18: FALL PROTECTION PHASES 3-6 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | SM: SR 17/18: FALL PROTECTION PHASES 3-6 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005724 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005723 | SR 17/18: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | SCOPE_DEV | 2017-01-05 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005723 | SR 17/18: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | SCOPE_DEV | 2017-01-05 | SM: SR 17/18: ARC FLASH STUDY - 20% OF CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005723 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005722 | SR 17/18: EMERGENCY REPAIRS - CAMPUS WIDE | FLEDDERMAN, JUDE | SCOPE_DEV | 2017-01-05 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005722 | SR 17/18: EMERGENCY REPAIRS - CAMPUS WIDE | FLEDDERMAN, JUDE | SCOPE_DEV | 2017-01-05 | PM: SR 17/18: EMERGENCY REPAIRS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005722 | SR 17/18: EMERGENCY REPAIRS - CAMPUS WIDE | FLEDDERMAN, JUDE | SCOPE_DEV | 2017-01-05 | SM: SR 17/18: EMERGENCY REPAIRS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005722 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005721 | SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2017-01-05 | AD: JOC 16.038.023 MAINO | STREETS | CLOSED | 190038.7945 | 0 | 190038.7945 | 190038.7945
PJ0005721 | SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2017-01-05 | CP: PROJECT CONTINGENCY | STREETS | OPEN | 9523.13 | 0 | 0 | 0
PJ0005721 | SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2017-01-05 | IN: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | STREETS | CLOSED | 423.864 | 0 | 70.644 | 70.644
PJ0005721 | SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2017-01-05 | PM: SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | STREETS | CLOSED | 0 | 0 | 0 | 0
PJ0005721 | SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2017-01-05 | SM: SR 17/18: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | STREETS | OPEN | 0 | 0 | 0 | 0
PJ0005721 Total | [7 empty] | 199985.7885 | 0 | 190109.4385 | 190109.4385
PJ0005717 | CHILDREN'S CENTER IMPROVEMENTS - BLD 133 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | CP: PROJECT CONTINGENCY | 133 | OPEN | 0 | 0 | 0 | 0
PJ0005717 | CHILDREN'S CENTER IMPROVEMENTS - BLD 133 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | PM: M&R ASI 17/18: CHILDREN'S CENTER IMPROVEMENTS - BLD 133 | 133 | OPEN | 0 | 0 | 0 | 0
PJ0005717 | CHILDREN'S CENTER IMPROVEMENTS - BLD 133 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | SM: CHILDREN'S CENTER IMPROVEMENTS - BLD 133 | 133 | OPEN | 0 | 0 | 0 | 0
PJ0005717 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005716 | M&R ASI 17/18: ENERGY MANAGEMENT SOFTWARE - REC 43 & UU 65 | ELLIOT, DENNIS K | SCOPE_DEV | 2017-01-05 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005716 | M&R ASI 17/18: ENERGY MANAGEMENT SOFTWARE - REC 43 & UU 65 | ELLIOT, DENNIS K | SCOPE_DEV | 2017-01-05 | SM: M&R ASI 17/18: ENERGY MANAGEMENT SOFTWARE - REC 43 & UU 65 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005716 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005714 | M&R ASI 17/18: EXERCISE FLOORING - TRACK EXERCISE ROOM - REC 43 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | CP: PROJECT CONTINGENCY | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005714 | M&R ASI 17/18: EXERCISE FLOORING - TRACK EXERCISE ROOM - REC 43 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | PM: M&R ASI 17/18: EXERCISE FLOORING - TRACK EXERCISE RM - REC43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005714 | M&R ASI 17/18: EXERCISE FLOORING - TRACK EXERCISE ROOM - REC 43 | DUNN, TRAVIS | ESTIMATING | 2017-01-05 | SM: M&R ASI 17/18: EXERC. FLOORING - TRACK EXERC. RM - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005714 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005713 | M&R ASI 17/18: FACILITY CONDITION ASSESSMENT - REC 43 | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-01-05 | CP: PROJECT CONTINGENCY | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005713 | M&R ASI 17/18: FACILITY CONDITION ASSESSMENT - REC 43 | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-01-05 | PM: M&R ASI 17/18: FACILITY CONDITION ASSESSMENT - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005713 | M&R ASI 17/18: FACILITY CONDITION ASSESSMENT - REC 43 | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2017-01-05 | SM: M&R ASI 17/18: FACILITY CONDITION ASSESSMENT - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005713 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | AD: ITS | 043 | OPEN | 4393.42 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | AD: JOC NEWTON | 043 | OPEN | 17658.2956 | 17320.5501 | 337.7455 | 17658.2956
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | AD: LOBBY TRAFFIC SYSTEMS | 043 | OPEN | 179201.3102 | 179201.3102 | 0 | 179201.3102
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | AD: STATE FIRE MARSHAL | 043 | OPEN | 850.65 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | CP: PROJECT CONTINGENCY | 043 | OPEN | 20599.01 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | EL: DUNN - TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | OPEN | 1373.9328 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | ES: DUNN - TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | OPEN | 577.8432 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | IN: M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | ASSIGNED | 1130.304 | 0 | 70.644 | 70.644
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | LO: DUNN - TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | OPEN | 268.0656 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | MO: DUNN - TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | OPEN | 536.256 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | PM: M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005712 | M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | DUNN, TRAVIS | SCHEDULING | 2017-01-05 | SM: M&R ASI 17/18: TURNSTILES- FRONT ENTRANCE - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005712 Total | [7 empty] | 226589.0874 | 196521.8603 | 408.3895 | 196930.2498
PJ0005711 | M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | NORTON, DAVE | CONST_COMP | 2017-01-05 | AD: MCWIL SPORT SURFACES, INC | 043 | CLOSED | 60776 | 0 | 60776 | 60776
PJ0005711 | M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | NORTON, DAVE | CONST_COMP | 2017-01-05 | CP: PROJECT CONTINGENCY | 043 | OPEN | 6162.25 | 0 | 0 | 0
PJ0005711 | M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | NORTON, DAVE | CONST_COMP | 2017-01-05 | EL:REC CENTER- PROVIDE CONTRACTOR SUPPORT JUNE 19-JULY 5 | 043 | CLOSED | 257.712 | 0 | 542.016 | 542.016
PJ0005711 | M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | NORTON, DAVE | CONST_COMP | 2017-01-05 | IN: M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | 043 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005711 | M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | NORTON, DAVE | CONST_COMP | 2017-01-05 | PM: M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005711 | M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | NORTON, DAVE | CONST_COMP | 2017-01-05 | SM: M&R ASI 17/18: REFINISH ALL WOOD FLOORS - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005711 Total | [7 empty] | 67337.25 | 0 | 61388.66 | 61388.66
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | AD: SMITH ELECTRIC | 065 | OPEN | 664868.04 | 36137.7413 | 628730.2987 | 664868.04
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | AD: STATE FIRE MARSHAL FEES | 065 | OPEN | 535 | 0 | 0 | 0
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | AD: THOMA ELECTRIC | 065 | OPEN | 3531 | 0 | 3531 | 3531
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | CP: PROJECT CONTINGENCY | 065 | OPEN | 62935.29 | 0 | 0 | 0
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | EL:SUPPORT FOR LIGHT REPLACEMENT AT UU- J DILLON | 065 | LONG_TERM | 6652.248 | 0 | 1944.342 | 1944.342
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | IN: M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | 065 | OPEN | 423.864 | 0 | 0 | 0
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | PA: POSSIBLE TOUCH-UP AFTER LIGHT REPLACEMENT AT UU- J DILLON | 065 | CLOSED | 3623.952 | 0 | 2447.484 | 2447.484
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | PM: M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005707 | M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | DILLON, JEFFREY | PUNCH_LIST | 2017-01-05 | SM: M&R ASI 17/18: LIGHTING UPGRADE - UU 65 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005707 Total | [7 empty] | 742569.394 | 36137.7413 | 636653.1247 | 672790.866
PJ0005705 | M&R PARK 17/18: MISC. WORK TO INCL TREE TRIMMING - CAMPUS WIDE | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-05 | AD: GREENVALE TREE CO. | GEN-PARK | OPEN | 8999.9947 | 2006.2393 | 7623.75 | 9629.9893
PJ0005705 | M&R PARK 17/18: MISC. WORK TO INCL TREE TRIMMING - CAMPUS WIDE | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-05 | CP: PROJECT CONTINGENCY | GEN-PARK | OPEN | 0 | 0 | 0 | 0
PJ0005705 | M&R PARK 17/18: MISC. WORK TO INCL TREE TRIMMING - CAMPUS WIDE | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-05 | LA: | GEN-PARK | OPEN | 999.1987 | 0 | 0 | 0
PJ0005705 | M&R PARK 17/18: MISC. WORK TO INCL TREE TRIMMING - CAMPUS WIDE | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-05 | SM: M&R PARK 17/18: MISC. WRK TO INCL TREE TRIMMING- CAMPUS WIDE | GEN-PARK | OPEN | 0 | 0 | 0 | 0
PJ0005705 Total | [7 empty] | 9999.1934 | 2006.2393 | 7623.75 | 9629.9893
PJ0005700 | M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | DUNN, TRAVIS | PUNCH_LIST | 2017-01-04 | AD: GOLDEN STATE | GEN-PARK | OPEN | 13000.5 | 0 | 0 | 0
PJ0005700 | M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | DUNN, TRAVIS | PUNCH_LIST | 2017-01-04 | AD: JOC 16.038.022 MAINO | GEN-PARK | OPEN | 147256.6528 | 0 | 147256.6528 | 147256.6528
PJ0005700 | M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | DUNN, TRAVIS | PUNCH_LIST | 2017-01-04 | CP: PROJECT CONTINGENCY | GEN-PARK | OPEN | 16039.84 | 0 | 0 | 0
PJ0005700 | M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | DUNN, TRAVIS | PUNCH_LIST | 2017-01-04 | IN: M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | GEN-PARK | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005700 | M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | DUNN, TRAVIS | PUNCH_LIST | 2017-01-04 | PM: M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOT | GEN-PARK | OPEN | 0 | 0 | 0 | 0
PJ0005700 | M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | DUNN, TRAVIS | PUNCH_LIST | 2017-01-04 | SM: M&R PARK 17/18: RESEAL AND RESTRIPE PARKING LOTS | GEN-PARK | OPEN | 0 | 0 | 0 | 0
PJ0005700 Total | [7 empty] | 176438.2808 | 0 | 147362.6188 | 147362.6188
PJ0005699 | M&R PARK 17/18: TREE REPLANT AND IRRIGATION RENO - H12 | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-04 | CP: PROJECT CONTINGENCY | P-H12 | OPEN | 0 | 0 | 0 | 0
PJ0005699 | M&R PARK 17/18: TREE REPLANT AND IRRIGATION RENO - H12 | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-04 | PM: M&R PARK 17/18: TREE REPLANT AND IRRIGATION RENO - H12 | P-H12 | OPEN | 0 | 0 | 0 | 0
PJ0005699 | M&R PARK 17/18: TREE REPLANT AND IRRIGATION RENO - H12 | LOOSLEY, SCOTT L. | SCOPE_DEV | 2017-01-04 | SM: M&R PARK 17/18: TREE REPLANT AND IRRIGATION RENO - H12 | P-H12 | OPEN | 0 | 0 | 0 | 0
PJ0005699 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005694 | M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VILLAGE DR. 271 | DUNN, TRAVIS | CONST_COMP | 2017-01-04 | AD: JOC 16.038.024 MAINO | 271 | CLOSED | 38386.3891 | 0 | 38386.3891 | 38386.3891
PJ0005694 | M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VILLAGE DR. 271 | DUNN, TRAVIS | CONST_COMP | 2017-01-04 | CP: PROJECT CONTINGENCY | 271 | OPEN | 3852.77 | 0 | 0 | 0
PJ0005694 | M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VILLAGE DR. 271 | DUNN, TRAVIS | CONST_COMP | 2017-01-04 | IN: M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VDP 271 | 271 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005694 | M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VILLAGE DR. 271 | DUNN, TRAVIS | CONST_COMP | 2017-01-04 | PM: M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VDP 271 | 271 | CLOSED | 0 | 0 | 0 | 0
PJ0005694 | M&R PARK 17/18: PARKING STRUCTURE MAINTENANCE - VILLAGE DR. 271 | DUNN, TRAVIS | CONST_COMP | 2017-01-04 | SM: M&R PARK 17/18: PARKING STRUC. MAINTENANCE - VILLAGE DR. 271 | 271 | OPEN | 0 | 0 | 0 | 0
PJ0005694 Total | [7 empty] | 42380.4471 | 0 | 38492.3551 | 38492.3551
PJ0005689 | M&R HOUS 17/18: INSTALL 1000 MATTRESSES - RES | LAMPMAN, COLLEEN | CLOSED | 2017-01-03 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005689 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | AD: ASAP REPROGRAPHICS | S. MTN. | CLOSED | 0 | 0 | 15.4936 | 15.4936
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | AD: GOSS ENGINEERING | S. MTN. | CLOSED | 11449 | 0 | 11449 | 11449
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | AD: STATE FIRE MARSHAL | S. MTN. | CLOSED | 214 | 0 | 0 | 0
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | CA: SUPPORT FOR ENGINEERING WALK THROUGH(NO COSTS) | S. MTN. | CLOSED | 305.91 | 0 | 0 | 0
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | CP: PROJECT CONTINGENCY | S. MTN. | OPEN | 1261.15 | 0 | 0 | 0
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | IN: M&R HOUS 17/18: REPLACE FIRE ALARM SYSTEM - RED BRICK | S. MTN. | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | PM: M&R HOUS 17/18: REPLACE FIRE ALARM SYSTEM - RED BRICK | S. MTN. | CLOSED | 0 | 0 | 0 | 0
PJ0005686 | M&R HOUS 17/18: REPLACE FIRE ALARM SYS- S. MTN. (DSGN ONLY) | KOLEGRAFF, KENNETH | DESGN_COMP | 2017-01-03 | SM: M&R HOUS 17/18: REPLACE FIRE ALARM SYS-RED BRICK(DSGN ONLY) | S. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005686 Total | [7 empty] | 13300.704 | 0 | 11535.1376 | 11535.1376
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: HPS MECHANICAL | RESIDENCE | CLOSED | 3306.3 | 0 | 3306.3 | 3306.3
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: ITS | RESIDENCE | CLOSED | 1284 | 0 | 615.25 | 615.25
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: J.L. FASULO DRYWALL | RESIDENCE | CLOSED | 10208.87 | 0 | 10208.87 | 10208.87
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 2889 | 0 | 2829.08 | 2829.08
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: MEC, INC. | RESIDENCE | CLOSED | 8934.5 | 0 | 8934.5 | 8934.5
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: SANTA MARIA ACOUSTICAL | RESIDENCE | CLOSED | 13965.64 | 0 | 13965.64 | 13965.64
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | AD: SMITH ELECTRIC | RESIDENCE | CLOSED | 18615.86 | 0 | 18615.86 | 18615.86
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 2622.48 | 0 | 0 | 0
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | EL: SUPPORT & 2ND FLOOR LIGHTING REPALCEMENT - KOLEGRAFF | RESIDENCE | CLOSED | 11810.5632 | 0 | 11332.803 | 11332.803
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | ES: SUPPORT FOR HHW GASKET REPLACEMENT - KOLEGRAFF | RESIDENCE | CLOSED | 722.304 | 0 | 2003.1432 | 2003.1432
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | IN: M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | RESIDENCE | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | PA: PAINT STAIRWAY CEILINGS AND TOUCH UP - KOLEGRAFF | RESIDENCE | CLOSED | 3323.952 | 0 | 0 | 0
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | PM: M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005685 | M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | KOLEGRAFF, KENNETH | CONST_COMP | 2017-01-03 | SM: M&R HOUS 17/18: REPLACE UTILIDOR PIPING GASKETS - SO MT | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005685 Total | [7 empty] | 77895.4012 | 0 | 71988.0562 | 71988.0562
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | AD: JOC 16.038.020 MAINO | RESIDENCE | CLOSED | 227210.5838 | 0 | 227210.5731 | 227210.5731
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 9957.42 | 0 | 3969.7 | 3969.7
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | AD: STATE FIRE MARSHAL FEES (N/C) | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | AD: THE SIGN PLACE | RESIDENCE | CLOSED | 13941.3189 | 0 | 13941.3189 | 13941.3189
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | CA: PJ5684 - LASSEN/DIABLO DORM DOOR REPLACEMENT- DUNN | RESIDENCE | CLOSED | 2867.28 | 0 | 933.582 | 933.582
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 22683.03 | 0 | 0 | 0
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | IN: REPLACE ENTRY & RESTROOM DOORS - NO MT | RESIDENCE | CLOSED | 565.152 | 0 | 423.864 | 423.864
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | LO: PJ5684 - LASSEN/DIABLO DORM DOOR REPLACEMENT- DUNN | RESIDENCE | CLOSED | 51871.02 | 0 | 45800.484 | 45800.484
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | PA: PJ5684 - LASSEN/DIABLO DORM DOOR REPLACEMENT- DUNN | RESIDENCE | CLOSED | 1144.7904 | 0 | 185.724 | 185.724
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | PM: M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005684 | M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | DUNN, TRAVIS | CONST_COMP | 2017-01-03 | SM: M&R HOUS 17/18: REPLACE ENTRY & RESTROOM DOORS - NO MT | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005684 Total | [7 empty] | 330240.5951 | 0 | 292465.246 | 292465.246
PJ0005683 | M&R HOUS 17/18: RE-ROOF&TIE-OFF INSTALL-BLDGS 114A,114B,113,113F | BROWN, CARLA | SCOPE_DEV | 2017-01-03 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005683 | M&R HOUS 17/18: RE-ROOF&TIE-OFF INSTALL-BLDGS 114A,114B,113,113F | BROWN, CARLA | SCOPE_DEV | 2017-01-03 | PM: M&R HOUS 17/18: INSTALL TIE-OFFS AT ROOFS - ALL RES | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005683 | M&R HOUS 17/18: RE-ROOF&TIE-OFF INSTALL-BLDGS 114A,114B,113,113F | BROWN, CARLA | SCOPE_DEV | 2017-01-03 | SM: M&R HOUS 17/18: RE-ROOF&TIE-OFF INSTL-BLD 114A,114B,113,113F | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005683 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | AD: 4 LEAF | GENERAL | OPEN | 0 | 6803.74 | 32301.26 | 39105
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | AD: SPECIALTY CONSTRUCTION (FUNDED BY AG OPS) | GENERAL | OPEN | 0 | 855.144 | 0 | 855.144
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | EL: TEMP POWER FOR CONSTRUCTION TRAILER AT NEW EQUINE PAVILION | GENERAL | LONG_TERM | 0 | 0 | 14425.281 | 14425.281
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | ES: | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | LO: TRILOGY LOCKS AT FOALING BARN LOUNGE - EQUESTRIAN PAVILION | GENERAL | ASSIGNED | 0 | 0 | 3693.612 | 3693.612
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | PL: FIRE HYDRANT FLOW TESTING FOR OPPENHEIMER EQUESTRIAN CTR. | GENERAL | COMPLETE | 0 | 0 | 1024.844 | 1024.844
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | PL: LOCATE UTILITIES FOR EQUINE PAVILION PROJECT | GENERAL | ASSIGNED | 0 | 0 | 7814.867 | 7814.867
PJ0005682 | SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | CREEL, AUSTIN | IN_CONSTR | 2017-01-03 | SM: SUPPORT OPPENHEIMER EQUINE PAVILION & AG EVENTS CTR | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005682 Total | [7 empty] | 0 | 7658.884 | 59259.864 | 66918.748
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: ASAP PRINTING | 052 | CLOSED | 0 | 0 | 138.3938 | 138.3938
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: COASTAL DEMO | 052 | CLOSED | 642 | 0 | 642 | 642
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: FLOOR CONNECTION | 052 | CLOSED | 4475.81 | 0 | 4475.81 | 4475.81
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: ITS | 052 | CLOSED | 6741 | 0 | 6717.2781 | 6717.2781
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: JOC 16.042.5681 R.F. KOERBER | 052 | CLOSED | 130686.1513 | 0 | 130686.1513 | 130686.1513
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 3322.35 | 0 | 3321.28 | 3321.28
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: SALAS OBRIEN | 052 | CLOSED | 7383 | 0 | 7383 | 7383
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | AD: STATE FIRE MARSHAL | 052 | OPEN | 1070 | 0 | 484.5816 | 484.5816
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | CA: | 052 | CLOSED | 61.182 | 0 | 0 | 0
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | CP: PROJECT CONTINGENCY | 052 | OPEN | 8654.28 | 0 | 0 | 0
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | CPE: SUPPORT AND INSTALLATION OF MECHANICAL - D11 KOLEGRAFF | 052 | CLOSED | 29435.2166 | 0 | 10009.446 | 10009.446
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | CU: FINAL CLEANING - KOLEGRAFF | 052 | CLOSED | 368.412 | 0 | 316.8663 | 316.8663
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | EL:SAFE OFF FOR DEMO AND ELECTRICAL INSTALLATION - D11 KOLEGRAFF | 052 | CLOSED | 28702.1351 | 0 | 27379.6766 | 27379.6766
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | IN: RENOVATION ROOMS - BLD 52 RMS D11A & D12 | 052 | CLOSED | 353.22 | 0 | 282.576 | 282.576
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | LO: INSTALLATION OF ORANGE CORES AND NEW HARDWARE - D11KOLEGRAFF | 052 | CLOSED | 2956.164 | 0 | 2959.779 | 2959.779
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | PA: FINAL PAINT - BLDG 52 D11 & D12 - KOLEGRAFF | 052 | CLOSED | 6647.904 | 0 | 2235.636 | 2235.636
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | PL: SAFE OFF PLUMBING FOR DEMOLITION - D11 KOLEGRAFF | 052 | CLOSED | 2837.472 | 0 | 3899.31 | 3899.31
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | PM: RENOVATION ROOMS - BLD 52 RMS D11A & D12 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005681 | RENOVATION ROOMS - BLD 52 RMS D11A & D12 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-29 | SM: RENOVATION ROOMS - BLD 52 RMS D11A & D12 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005681 Total | [7 empty] | 234336.297 | 0 | 200931.7847 | 200931.7847
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | AD: MCKENNA | RESIDENCE | OPEN | 5163.82 | 1573.97 | 3589.85 | 5163.82
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | AD: PRINTING | RESIDENCE | OPEN | 0 | 0 | 74.365 | 74.365
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | AD: R.F. KOERBER | RESIDENCE | OPEN | 278156.0123 | 0 | 278156.0016 | 278156.0016
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | CA: CONTRACTOR SUPPORT- ROOF REPAIR | RESIDENCE | ASSIGNED | 5679.492 | 0 | 4130.766 | 4130.766
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 10355.19 | 0 | 0 | 0
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | EL: ELECTRICAL SUPPORT | RESIDENCE | CLOSED | 708.708 | 0 | 2775.978 | 2775.978
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | IN: M&R HOUS 17/18: CSD KITCHEN REMODEL -YOSEMITE & SIERRA MADRE | RESIDENCE | ASSIGNED | 466.2504 | 0 | 459.186 | 459.186
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | LO: CHANGE LOCKS | RESIDENCE | ASSIGNED | 3218.778 | 0 | 2567.148 | 2567.148
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | PA: | RESIDENCE | OPEN | 615.264 | 0 | 0 | 0
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | PL: CSD REMODELS FOR YOSEMITE AND SIERRA MADRE | RESIDENCE | ASSIGNED | 709.368 | 0 | 1425.364 | 1425.364
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | PM: M&R HOUS 17/18: CSD KITCHEN REMODEL - YO & SM | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005680 | M&R HOUS 17/18: CSD KITCHEN REMODEL - YOSEMITE & SIERRA MADRE | NORTON, DAVE | PUNCH_LIST | 2017-01-03 | SM: M&R HOUS 17/18: CSD KITCHEN REMDL - YOSEMITE & SIERRA MADRE | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005680 Total | [7 empty] | 305072.8827 | 1573.97 | 293178.6586 | 294752.6286
PJ0005679 | M&R HOUS 17/18: RENOVATE RESTROOMS - NO MT RES | ULM, AARON | DESIGN | 2017-01-03 | AD: FPCP MANAGEMENT/DESIGN | N. MTN. | OPEN | 1120 | 0 | 700 | 700
PJ0005679 | M&R HOUS 17/18: RENOVATE RESTROOMS - NO MT RES | ULM, AARON | DESIGN | 2017-01-03 | CP: PROJECT CONTINGENCY | N. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005679 | M&R HOUS 17/18: RENOVATE RESTROOMS - NO MT RES | ULM, AARON | DESIGN | 2017-01-03 | PM: M&R HOUS 17/18: RENOVATE RESTROOMS-NO MT RES | N. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005679 | M&R HOUS 17/18: RENOVATE RESTROOMS - NO MT RES | ULM, AARON | DESIGN | 2017-01-03 | SM: M&R HOUS 17/18: RENOVATE RESTROOMS - NO MT RES | N. MTN. | OPEN | 0 | 0 | 0 | 0
PJ0005679 Total | [7 empty] | 1120 | 0 | 700 | 700
PJ0005678 | M&R HOUS 17/18: REPLACE RESTROOM FLOORING - CV 170 | LAMPMAN, COLLEEN | TO_CANCEL | 2017-01-03 | AD: FLOOR CONNECTION (NO OVERHEAD) | 170 | COMPLETE | 0 | 53338.92 | 6105 | 59443.92
PJ0005678 | M&R HOUS 17/18: REPLACE RESTROOM FLOORING - CV 170 | LAMPMAN, COLLEEN | TO_CANCEL | 2017-01-03 | CP: PROJECT CONTINGENCY | 170 | OPEN | 0 | 0 | 0 | 0
PJ0005678 Total | [7 empty] | 0 | 53338.92 | 6105 | 59443.92
PJ0005677 | M&R HOUS 17/18: REPLACE STAIRWAY LOCKS - SM 113 | POLVI, STEVEN | CONST_COMP | 2017-01-03 | CP: PROJECT CONTINGENCY | 113 | OPEN | 2965.47 | 0 | 0 | 0
PJ0005677 | M&R HOUS 17/18: REPLACE STAIRWAY LOCKS - SM 113 | POLVI, STEVEN | CONST_COMP | 2017-01-03 | LO: REPLACE OLD STAIRWAY LOCKSETS | 113 | CLOSED | 23524.74 | 0 | 20706.4934 | 20706.4934
PJ0005677 | M&R HOUS 17/18: REPLACE STAIRWAY LOCKS - SM 113 | POLVI, STEVEN | CONST_COMP | 2017-01-03 | SM: M&R HOUS 17/18: REPLACE STAIRWAY LOCKS - SM 113 | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005677 Total | [7 empty] | 26490.21 | 0 | 20706.4934 | 20706.4934
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | AD: JOC 16-041.5676 MAINO | RESIDENCE | CLOSED | 60327.5844 | 0 | 60327.5844 | 60327.5844
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 2821.49 | 0 | 0 | 0
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | EL: UTILITIES TO MAINO NEW IRRIGATION MAINLINE MUIR&SEQUOIA HALL | RESIDENCE | CLOSED | 2333.9328 | 0 | 0 | 0
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | IN: M&R HOUS 17/18: IRRIGATION RENOVATE/UPGRADE - SO MT RES | RESIDENCE | CLOSED | 2825.76 | 0 | 141.288 | 141.288
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | LA: COLLEEN LAMPMAN IRRIGATION LINES | RESIDENCE | CLOSED | 22706.5603 | 0 | 0 | 0
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | PL: UTILITIES TO MAINO NEW IRRIGATION MAINLINE MUIR&SEQUOIA HALL | RESIDENCE | CLOSED | 2618.736 | 0 | 1002.792 | 1002.792
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | PM: M&R HOUS 17/18: IRRIGATION RENOVATE/UPGRADE - SO MT RES | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005676 | M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | MACDONALD, WENDY | CONST_COMP | 2017-01-03 | SM: M&R HOUS 17/18: IRRIGATION RENOVATION/UPGRADE - SO MT RES | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005676 Total | [7 empty] | 93634.0635 | 0 | 61471.6644 | 61471.6644
PJ0005673 | M&R HOUS 17/18: INSTALL LOW FLOW TOILETS - SO MT. | GONZALES, ALBERT | CONST_COMP | 2016-12-30 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 4762.73 | 0 | 0 | 0
PJ0005673 | M&R HOUS 17/18: INSTALL LOW FLOW TOILETS - SO MT. | GONZALES, ALBERT | CONST_COMP | 2016-12-30 | IN: M&R HOUS 17/18: INSTALL LOW FLOW TOILETS - SO MT. | RESIDENCE | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005673 | M&R HOUS 17/18: INSTALL LOW FLOW TOILETS - SO MT. | GONZALES, ALBERT | CONST_COMP | 2016-12-30 | PL: LOW FLOW TOILET REPLACEMENTS | RESIDENCE | CLOSED | 51937.8929 | 0 | 35362.602 | 35362.602
PJ0005673 | M&R HOUS 17/18: INSTALL LOW FLOW TOILETS - SO MT. | GONZALES, ALBERT | CONST_COMP | 2016-12-30 | SM: M&R HOUS 17/18: INSTALL LOW FLOW TOILETS - SO MT. | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005673 Total | [7 empty] | 56983.1989 | 0 | 35503.89 | 35503.89
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | AD: GF GARCIA & SONS | 101 | OPEN | 12374.55 | 12374.55 | 0 | 12374.55
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | AD: ITS DATA | 101 | OPEN | 0 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | AD: STATE FIRE MARSHAL | 101 | OPEN | 1070 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | CA: | 101 | OPEN | 61.182 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | CP: PROJECT CONTINGENCY | 101 | OPEN | 7615.2 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | EH&S: | 101 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | EL: DEMO & REPLACE N. MOUNTAIN TRANSFORMER - KOLEGRAFF | 101 | LONG_TERM | 59444.4683 | 0 | 450.996 | 450.996
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | ES: | 101 | OPEN | 1083.456 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | IN:M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | 101 | ASSIGNED | 211.932 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | LA: | 101 | OPEN | 1480.704 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | PL:PROVIDE SUPPORT AND MARK UTILITIES - KOLEGRAFF | 101 | ASSIGNED | 354.684 | 0 | 64.488 | 64.488
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | PM: M&R HOUS 17/18: REPLACE TRANSFORMER AND DISTRIBUTION SYSTEM | 101 | OPEN | 0 | 0 | 0 | 0
PJ0005670 | M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS - DIABLO | KOLEGRAFF, KENNETH | SCHEDULING | 2016-12-30 | SM: M&R HOUS 17/18: REPLACE TRANSFORMER/DISTRIBUTION SYS- DIABLO | 101 | OPEN | 0 | 0 | 0 | 0
PJ0005670 Total | [7 empty] | 83766.9811 | 12374.55 | 515.484 | 12890.034
PJ0005669 | M&R HOUS 17/18: INSTALL PLUG-IN CHARGER STATION (SEE 5930) | ULM, AARON | TO_CANCEL | 2016-12-30 | PM: M&R HOUS 17/18: INSTALL PLUG-IN CHARGER STATION - PCV | 171 | CLOSED | 0 | 0 | 0 | 0
PJ0005669 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | AD: NCE | RESIDENCE | OPEN | 14743.53 | 9362.2325 | 5381.2975 | 14743.53
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | AD: PRINTING & SHIPPING SERVICES | RESIDENCE | OPEN | 267.5 | 0 | 0 | 0
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 1704.21 | 0 | 0 | 0
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | EL: PULL TEST ON WIRES FOR FUTURE CART CHARGING STATION | RESIDENCE | CLOSED | 1253.9328 | 0 | 1445.22 | 1445.22
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | IN: M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | RESIDENCE | ASSIGNED | 777.084 | 0 | 70.644 | 70.644
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | PM: M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - RES | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005668 | M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | ULM, AARON | DESIGN | 2016-12-30 | SM: M&R HOUS 17/18: LANDSCAPE FOR CART TURNAROUND AREA - SO. MTN | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005668 Total | [7 empty] | 18746.2568 | 9362.2325 | 6897.1615 | 16259.394
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | AD: DIVISION OF STATE ARCHITECT | RESIDENCE | OPEN | 228.6804 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | AD: FPCP MANAGEMENT/DESIGN | RESIDENCE | OPEN | 1680 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | AD: STATE FIRE MARSHAL | RESIDENCE | OPEN | 267.5 | 0 | 63.5259 | 63.5259
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | CA: RELOCATE TRASH ENCLOSURES @ SIERRA MADRE PER PLANS | RESIDENCE | ASSIGNED | 48193.1682 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 5180.34 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | IN: M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | RESIDENCE | OPEN | 423.864 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | LA: | RESIDENCE | OPEN | 3185.9712 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | PM: M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005666 | M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | ULM, AARON | ESTIMATING | 2016-12-30 | SM: M&R HOUS 17/18: SFM: RELOCATE TRASH ENCLOSURE - YO/SM | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005666 Total | [7 empty] | 59159.5238 | 0 | 63.5259 | 63.5259
PJ0005661 | MJ: IN-HOUSE SUPPORT FOR STUDENT HOUSING P3 - DRUMM RESERVOIR | SODERIN, ERIC | SCOPE_DEV | 2016-12-30 | CP: PROJECT CONTINGENCY | 209 | OPEN | 0 | 0 | 0 | 0
PJ0005661 | MJ: IN-HOUSE SUPPORT FOR STUDENT HOUSING P3 - DRUMM RESERVOIR | SODERIN, ERIC | SCOPE_DEV | 2016-12-30 | EL: LOCATE UTILITIES FOR POSSIBLE STUDENT HOUSING AT DRUMM RES. | 209 | CLOSED | 0 | 0 | 161.07 | 161.07
PJ0005661 | MJ: IN-HOUSE SUPPORT FOR STUDENT HOUSING P3 - DRUMM RESERVOIR | SODERIN, ERIC | SCOPE_DEV | 2016-12-30 | LA: LOCATE UTILITIES FOR POSSIBLE STUDENT HOUSING AT DRUMM RES. | 209 | COMPLETE | 0 | 0 | 60.048 | 60.048
PJ0005661 | MJ: IN-HOUSE SUPPORT FOR STUDENT HOUSING P3 - DRUMM RESERVOIR | SODERIN, ERIC | SCOPE_DEV | 2016-12-30 | PL: LOCATE UTILITIES FOR POSSIBLE STUDENT HOUSING AT DRUMM RES. | 209 | PEND_SCHED | 0 | 0 | 141.888 | 141.888
PJ0005661 | MJ: IN-HOUSE SUPPORT FOR STUDENT HOUSING P3 - DRUMM RESERVOIR | SODERIN, ERIC | SCOPE_DEV | 2016-12-30 | SM: SUPPORT STUDENT HOUSING P3 - DRUMM RESERVOIR (MAJ CAP) | 209 | OPEN | 0 | 0 | 0 | 0
PJ0005661 Total | [7 empty] | 0 | 0 | 363.006 | 363.006
PJ0005659 | SURVEY POOL DECK - BLDG 171 | BRENNAN, MICHAEL | CLOSED | 2016-12-19 | AD: NORTH COAST ENGINEERING | 171 | CLOSED | 0 | 0 | 4102.38 | 4102.38
PJ0005659 | SURVEY POOL DECK - BLDG 171 | BRENNAN, MICHAEL | CLOSED | 2016-12-19 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 0 | 0 | 0 | 0
PJ0005659 | SURVEY POOL DECK - BLDG 171 | BRENNAN, MICHAEL | CLOSED | 2016-12-19 | PM: SURVEY POOL DECK - BLDG 171 | 171 | CLOSED | 0 | 0 | 0 | 0
PJ0005659 Total | [7 empty] | 0 | 0 | 4102.38 | 4102.38
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | AD: MORRO BAY CABINETS (FUNDED BY AFD) | 001 | CLOSED | 8993.14 | 0 | 8731.2 | 8731.2
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | AD: STATE FIRE MARSHAL | 001 | OPEN | 278.2 | 92.1698 | 186.0302 | 278.2
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | AD: THE SIGN PLACE - RM SIGNS, ART WORK | 001 | CLOSED | 16117.4849 | 0 | 16117.4849 | 16117.4849
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | AD:ITS | 001 | OPEN | 802.5 | 132.8405 | 669.6595 | 802.5
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | CA: INSTALL SIGNS, DISPLAY BOARDS, ARTWORK, CLOSET DOOR | 001 | CLOSED | 8758.2 | 0 | 1899.483 | 1899.483
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | CP: PROJECT CONTINGENCY | 001 | OPEN | 1735.24 | 0 | 0 | 0
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | EL: INSTALL MAG HOLD OPEN DEVICES & POWER TO DISPLAY MONITOR | 001 | CLOSED | 3146.124 | 0 | 3390.174 | 3390.174
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | IN: CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | 001 | CLOSED | 155.4168 | 0 | 70.644 | 70.644
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | PA: PAINT AS NEED 2ND FLOOR ADMIN | 001 | CLOSED | 3323.952 | 0 | 928.62 | 928.62
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | PM: CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005658 | CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | NORTON, DAVE | CONST_COMP | 2016-12-06 | SM: CORRIDOR BEAUTIFICATION - BLD 01 2ND FLR | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005658 Total | [7 empty] | 43310.2577 | 225.0103 | 31993.2956 | 32218.3059
PJ0005655 | SR 16/17: DUCT REPAIR - MOTT 42 ROOF | KOLEGRAFF, KENNETH | CLOSED | 2016-12-12 | AD: JOC 16.038.018 MAINO | 042 | CLOSED | 37634.8425 | 0 | 37604.2512 | 37604.2512
PJ0005655 | SR 16/17: DUCT REPAIR - MOTT 42 ROOF | KOLEGRAFF, KENNETH | CLOSED | 2016-12-12 | AD: STATE FIRE MARSHAL FEES | 042 | CLOSED | 0 | 0 | 148.6444 | 148.6444
PJ0005655 | SR 16/17: DUCT REPAIR - MOTT 42 ROOF | KOLEGRAFF, KENNETH | CLOSED | 2016-12-12 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 3987.91 | 0 | 0 | 0
PJ0005655 | SR 16/17: DUCT REPAIR - MOTT 42 ROOF | KOLEGRAFF, KENNETH | CLOSED | 2016-12-12 | IN: SR 16/17: DUCT REPAIR - MOTT 42 ROOF | 042 | CLOSED | 70.644 | 0 | 105.966 | 105.966
PJ0005655 | SR 16/17: DUCT REPAIR - MOTT 42 ROOF | KOLEGRAFF, KENNETH | CLOSED | 2016-12-12 | PM: SR 16/17: DUCT REPAIR - MOTT 42 ROOF | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005655 Total | [7 empty] | 41693.3965 | 0 | 37858.8616 | 37858.8616
PJ0005651 | LIBRARY SHELF REMOVAL - BLDG 35 RM 417 | KOLEGRAFF, KENNETH | CLOSED | 2016-11-29 | AD: COASTAL DEMO | 035 | CLOSED | 5243 | 0 | 5243 | 5243
PJ0005651 | LIBRARY SHELF REMOVAL - BLDG 35 RM 417 | KOLEGRAFF, KENNETH | CLOSED | 2016-11-29 | AD: FLOOR CONNECTION | 035 | CLOSED | 1070 | 0 | 1059.3 | 1059.3
PJ0005651 | LIBRARY SHELF REMOVAL - BLDG 35 RM 417 | KOLEGRAFF, KENNETH | CLOSED | 2016-11-29 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 681.37 | 0 | 0 | 0
PJ0005651 | LIBRARY SHELF REMOVAL - BLDG 35 RM 417 | KOLEGRAFF, KENNETH | CLOSED | 2016-11-29 | PM: LIBRARY SHELF REMOVAL - BLDG 35 RM 417 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005651 Total | [7 empty] | 6994.37 | 0 | 6302.3 | 6302.3
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | CA: SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES (12/17) | 043 | CLOSED | 0 | 0 | 5909.16 | 5909.16
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | CU: SUPPORT FOR FALL COMMENCEMENT | 043 | CLOSED | 0 | 0 | 735.5498 | 735.5498
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | EL: ELECTRICAL SUPPORT FOR FALL COMMENCEMENT (12/17) | 043 | CLOSED | 0 | 0 | 691.135 | 691.135
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | ES: SUPPORT FOR 2016 SPRING COMMENCEMENT - 12/17 | 043 | CLOSED | 0 | 0 | 842.66 | 842.66
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | LA: SUPPORT FOR FALL COMMENCEMENT - 12/17 | 043 | CLOSED | 0 | 0 | 438.065 | 438.065
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | LO: CALLBACK FOR COMMENCEMENT - 12/17 | 043 | CLOSED | 0 | 0 | 178.625 | 178.625
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | MC: SUPPORT FOR 2016 FALL COMMENCEMENT | 043 | CLOSED | 0 | 0 | 150 | 150
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | PA: SUPPORT FOR DON | 043 | CLOSED | 0 | 0 | 515.9 | 515.9
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | PERMIT: 2016 FALL COMMENCEMENT - 12/17 | 043 | CLOSED | 0 | 0 | 470.96 | 470.96
PJ0005650 | SUPPORT FOR 2016 FALL COMMENCEMENT CEREMONIES - 12/17 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-12-02 | PL: SUPPORT FOR DON | 043 | CLOSED | 0 | 0 | 502.52 | 502.52
PJ0005650 Total | [7 empty] | 0 | 0 | 10434.5748 | 10434.5748
PJ0005649 | SR 16/17: EGRESS LIGHTING REPLACEMENT - SPANOS 61 | POLVI, STEVEN | CLOSED | 2016-12-01 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 1740.25 | 0 | 0 | 0
PJ0005649 | SR 16/17: EGRESS LIGHTING REPLACEMENT - SPANOS 61 | POLVI, STEVEN | CLOSED | 2016-12-01 | EL: INSTALL REPLACMENT EGRESS LIGHT FIXURES | 061 | CLOSED | 18091.752 | 0 | 19832.016 | 19832.016
PJ0005649 Total | [7 empty] | 19832.002 | 0 | 19832.016 | 19832.016
PJ0005648 | DESIGN & INSTALL TRASH ROOF STRUCTURES - RES HALLS | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2016-10-31 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005648 | DESIGN & INSTALL TRASH ROOF STRUCTURES - RES HALLS | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2016-10-31 | PM: DESIGN & INSTALL ROOF STRUCTURES - RES HALLS | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005648 | DESIGN & INSTALL TRASH ROOF STRUCTURES - RES HALLS | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2016-10-31 | SM: DESIGN & INSTALL TRASH ROOF STRUCTURES - RES HALLS | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005648 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005647 | TENANT IMPROVEMENT/STRAWBERRY CENTER - TECHPARK 83 RMS 104A&105A | HOGAN, MIKE | CONST_COMP | 2016-11-30 | AD: CAL POLY FAC BUILDING PERMIT FEES | 083 | CLOSED | 1158.1 | 0 | 1158.1 | 1158.1
PJ0005647 | TENANT IMPROVEMENT/STRAWBERRY CENTER - TECHPARK 83 RMS 104A&105A | HOGAN, MIKE | CONST_COMP | 2016-11-30 | AD: CAL POLY FACILITIES PLAN REVIEW | 083 | CLOSED | 1028.83 | 0 | 1028.83 | 1028.83
PJ0005647 | TENANT IMPROVEMENT/STRAWBERRY CENTER - TECHPARK 83 RMS 104A&105A | HOGAN, MIKE | CONST_COMP | 2016-11-30 | AD: STATE FIRE MARSHAL FEES | 083 | CLOSED | 914.85 | 0 | 1214.3644 | 1214.3644
PJ0005647 | TENANT IMPROVEMENT/STRAWBERRY CENTER - TECHPARK 83 RMS 104A&105A | HOGAN, MIKE | CONST_COMP | 2016-11-30 | CP: PROJECT CONTINGENCY | 083 | OPEN | 307.95 | 0 | 0 | 0
PJ0005647 | TENANT IMPROVEMENT/STRAWBERRY CENTER - TECHPARK 83 RMS 104A&105A | HOGAN, MIKE | CONST_COMP | 2016-11-30 | IN: (MAINT) TENANT IMPROVEMENT FOR STRAWBERRY CENTER | 083 | CLOSED | 0 | 0 | 706.44 | 706.44
PJ0005647 | TENANT IMPROVEMENT/STRAWBERRY CENTER - TECHPARK 83 RMS 104A&105A | HOGAN, MIKE | CONST_COMP | 2016-11-30 | SM: TENANT IMPROVEMENT/STRAWBERRY CTR- TECHPARK 83 RMS 104A&105A | 083 | OPEN | 0 | 0 | 0 | 0
PJ0005647 Total | [7 empty] | 3409.73 | 0 | 4107.7344 | 4107.7344
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | AD: DAHL | 011 | CLOSED | 4167.65 | 0 | 4167.65 | 4167.65
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | AD: ITS | 011 | CLOSED | 821.76 | 0 | 822.295 | 822.295
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | AD: STATE FIRE MARSHAL | 011 | CLOSED | 642 | 0 | 245.8432 | 245.8432
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | CA: PJ5645 INSTALL MASS SPECTROMETER - BLD 11 RM 306 | 011 | CLOSED | 561.456 | 0 | 183.564 | 183.564
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | CP: PROJECT CONTINGENCY | 011 | OPEN | 1284.55 | 0 | 0 | 0
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | EL: PJ5645 INSTALL MASS SPECTROMETER - BLD 11 RM 306 | 011 | CLOSED | 6101.7984 | 0 | 4434.33 | 4434.33
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | IN: INSTALL MASS SPECTROMETER - BLD 11 RM 306 | 011 | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | MO: PJ5645 INSTALL MASS SPECTROMETER - BLD 11 RM 306 | 011 | CLOSED | 268.128 | 0 | 156 | 156
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | PM: CONNECT VENT FROM UPLC DEVICE TO FUME HOOD-BLD 11 RM 306 | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0005645 | INSTALL MASS SPECTROMETER - BLD 11 RM 306 | DUNN, TRAVIS | CONST_COMP | 2016-11-02 | SM: INSTALL MASS SPECTROMETER - BLD 11 RM 306 | 011 | OPEN | 0 | 0 | 0 | 0
PJ0005645 Total | [7 empty] | 14129.9184 | 0 | 10150.9702 | 10150.9702
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | CA: SUPPORT FOR FOOTBALL PLAYOFF GAME (11.26) | 061 | CLOSED | 0 | 0 | 244.752 | 244.752
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | CPE: FOOTBALL SUPPORT FOR PLAYOFF GAME (11/26) | 061 | CLOSED | 328.32 | 0 | 361.14 | 361.14
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | CU: FOOTBALL PLAYOFF GAME SUPPORT - 11/26 | 061 | CLOSED | 0 | 0 | 2428.5566 | 2428.5566
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | EL: SUPPORT FOR FOOTBALL PLAYOFF GAME (NOV. 26) | 061 | CLOSED | 0 | 0 | 956.772 | 956.772
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | LA: FOOTBALL PLAYOFF GAME SUPPORT (11/26) | 061 | CLOSED | 0 | 0 | 4423.068 | 4423.068
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | PL: SUPPORT FOR FOOTBALL PLAYOFF GAME (11/26) | 061 | CLOSED | 0 | 0 | 615.0403 | 615.0403
PJ0005644 | 2016: SUPPORT FOR FOOTBALL PLAYOFF GAMES | POPHAM, DONALD J. | CLOSED | 2016-11-18 | SUPPLY RENTAL: FOOTBALL PLAYOFF GAME RENTAL | 061 | CLOSED | 0 | 0 | 143 | 143
PJ0005644 Total | [7 empty] | 328.32 | 0 | 9172.329 | 9172.329
PJ0005643 | M&R ASI 17/18: FEASIBILITY STUDY TO CONVERT GREEN ROOF- REC 43 | DILLON, JEFFREY | DESIGN | 2016-11-08 | AD: CANNON CORP. | 043 | OPEN | 58529 | 5351.6371 | 53177.3629 | 58529
PJ0005643 | M&R ASI 17/18: FEASIBILITY STUDY TO CONVERT GREEN ROOF- REC 43 | DILLON, JEFFREY | DESIGN | 2016-11-08 | AD: STATE FIRE MARSHAL | 043 | OPEN | 214 | 0 | 0 | 0
PJ0005643 | M&R ASI 17/18: FEASIBILITY STUDY TO CONVERT GREEN ROOF- REC 43 | DILLON, JEFFREY | DESIGN | 2016-11-08 | CP: PROJECT CONTINGENCY | 043 | OPEN | 5874.3 | 0 | 0 | 0
PJ0005643 | M&R ASI 17/18: FEASIBILITY STUDY TO CONVERT GREEN ROOF- REC 43 | DILLON, JEFFREY | DESIGN | 2016-11-08 | PM: FEASIBILITY STUDY TO CONVERT GREEN ROOF SPACE - REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005643 | M&R ASI 17/18: FEASIBILITY STUDY TO CONVERT GREEN ROOF- REC 43 | DILLON, JEFFREY | DESIGN | 2016-11-08 | SM: M&R ASI 17/18: FEASIBILITY STUDY TO CNV GREEN ROOF- REC 43 | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005643 Total | [7 empty] | 64617.3 | 5351.6371 | 53177.3629 | 58529
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | AD: FLOOR CONNECTION | 003 | CLOSED | 2140 | 0 | 2629.9744 | 2629.9744
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | AD: NEWTON LVPW | 003 | CLOSED | 4665.2 | 0 | 4665.2 | 4665.2
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | AD: SANTA MARIA ACOUSTIC | 003 | CLOSED | 395.9 | 0 | 395.9 | 395.9
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 160.5 | 0 | 148.6444 | 148.6444
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | CA: PJ#5641 - BLDG. 003, ROOM 107A - HANG PHOTOS & TRIM DOOR | 003 | CLOSED | 111.24 | 0 | 410.298 | 410.298
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | CP: PROJECT CONTINGENCY | 003 | OPEN | 474.86 | 0 | 0 | 0
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | IN: CARPET AND FILL IN DOOR - BLD 03 RMS 106 & 107 | 003 | CLOSED | 155.4168 | 0 | 70.644 | 70.644
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | PA: PJ#5641 BLDG. 003, ROOMS 106 & 107 - PRIME AND PAINT OFFICES | 003 | CLOSED | 2873.952 | 0 | 650.034 | 650.034
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | PM: CARPET AND FILL IN DOOR - BLD 03 RMS 106 & 107 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005641 | CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | MARCHESE, JASON (WILL) | CONST_COMP | 2016-11-04 | SM: CARPET AND IN-FILL DOOR BETWEEN ROOMS - BLD 03 RMS 106 & 107 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005641 Total | [7 empty] | 10977.0688 | 0 | 8970.6948 | 8970.6948
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | AD: CAME SECURITY | 013 | OPEN | 29532 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | AD: ITS - DATA FOR DOR ACCESS CONTROLLER IN 3 ROOMS | 013 | OPEN | 1286.7178 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | AD: STATE FIRE MARSHAL | 013 | OPEN | 267.5 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | CP: PROJECT CONTINGENCY | 013 | OPEN | 2840.27 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | EL: CB INSTALL POLYCARD CAME SECURITY - AC OUTLET AND CONDUIT IN | 013 | OPEN | 9836.6304 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | IN: ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | 013 | OPEN | 353.22 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | LO: CB INSTALL POLYCARD CAME SECURITY | 013 | OPEN | 2907.246 | 0 | 1607.16 | 1607.16
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | PA: CB INSTALL POLYCARD CAME SECURITY-REPAIR/PAINT IF DAMAGED | 013 | OPEN | 1345.7784 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | PM: ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005640 | ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | BROWN, CARLA | SCHEDULING | 2016-10-19 | SM: ADD POLY CARD DOOR LOCKS -BLD 13 RMS 124, 126 & 192 RM 102 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005640 Total | [7 empty] | 48369.3626 | 0 | 1607.16 | 1607.16
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | AD: JOC 16.039.006 NEWTON | RESIDENCE | CLOSED | 139630.72 | 0 | 138392.1736 | 138392.1736
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 0 | 0 | 171.5103 | 171.5103
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 15330.6 | 0 | 0 | 0
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | EL: INSTALLATION OF ELECTRICAL SYSTEM FOR SIERRA MADRE RE-PIPE | RESIDENCE | CLOSED | 10043.5968 | 0 | 7944.552 | 7944.552
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | ES: SUPPORT AND INSTALL CONTROLS FOR SIERRA/YO-REPIPE | RESIDENCE | CLOSED | 22835.2166 | 0 | 29792.2671 | 29792.2671
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | IN: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | RESIDENCE | CLOSED | 282.576 | 0 | 459.186 | 459.186
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | LO: INSTALLATION OF ORANGE CORES SIERRA MADRE/YO MECH. RMS | RESIDENCE | CLOSED | 910.164 | 0 | 152.31 | 152.31
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | PL: Support during HHW Re-fill - Kolegraff | RESIDENCE | CLOSED | 70.9368 | 0 | 2520.732 | 2520.732
PJ0005638 | MJ: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | KOLEGRAFF, KENNETH | CLOSED | 2016-11-08 | PM: REPIPE WORK SIERRA MADRE AND YOSEMITE (SEE PJ4501) | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005638 Total | [7 empty] | 189103.8102 | 0 | 179432.731 | 179432.731
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: A-TOWN TV | 042 | OPEN | 5233.2951 | 0 | 5233.2951 | 5233.2951
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: BKM | 042 | OPEN | 8986.4271 | 0 | 8986.4271 | 8986.4271
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: CREDIT CARD PURCHASE - TO BE INSTALLED BY JOC | 042 | OPEN | 0 | 665.5935 | 1191.1882 | 1856.7817
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: FLOOR CONNECTION | 042 | OPEN | 20009 | 9.63 | 20003.65 | 20013.28
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: HENRY SCHEIN-CABINETS | 042 | OPEN | 21976.3448 | 0 | 21976.3448 | 21976.3448
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: ITS/CT | 042 | OPEN | 4577.7275 | 0 | 4791.7275 | 4791.7275
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: JOC 16.041.5637 MAINO | 042 | OPEN | 164609.977 | 0 | 164609.977 | 164609.977
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: MCKENNA | 042 | OPEN | 2206.34 | 4.28 | 2202.06 | 2206.34
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: P-CARD PURCHASE SHELVING INSTALLED BY PM | 042 | OPEN | 900.5655 | 0 | 900.5655 | 900.5655
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: SIGN PLACE | 042 | OPEN | 3882.1098 | 2024.6968 | 1857.413 | 3882.1098
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | AD: STATE FIRE MARSHAL | 042 | OPEN | 267.5 | 0 | 114.3402 | 114.3402
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | CP: PROJECT CONTINGENCY | 042 | OPEN | 2735.32 | 0 | 0 | 0
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | CPE: ICE MACHINES, MOTT TRAINING | 042 | COMPLETE | 722.304 | 0 | 426.816 | 426.816
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | CU:FINAL CLEANING, 42-125, J. DILLON PM | 042 | OPEN | 221.0472 | 0 | 0 | 0
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | EL:REMODEL TRAINING ROOM | 042 | CLOSED | 22073.9051 | 0 | 18497.619 | 18497.619
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | IN: REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | 042 | ASSIGNED | 847.728 | 0 | 317.898 | 317.898
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | LO:MOTT TRAINING ROOM | 042 | ASSIGNED | 2269.1148 | 0 | 592.416 | 592.416
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | MO:MOTT TRAING ROOM | 042 | OPEN | 335.16 | 0 | 0 | 0
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | PA:MOTT TRAINING ROOM | 042 | CLOSED | 2642.964 | 0 | 1777.608 | 1777.608
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | PL:MOTT TRAINING ROOM REMODEL | 042 | COMPLETE | 11456.208 | 0 | 13545.7091 | 13545.7091
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | PM: REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005637 | REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | DILLON, JEFFREY | PUNCH_LIST | 2016-11-03 | SM: REMODEL ATHLETIC TRAINING ROOM - BLD 42 RM 125D | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005637 Total | [7 empty] | 275953.0379 | 2704.2003 | 267025.0545 | 269729.2548
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | AD: WCR | GENERAL | CLOSED | 29835.88 | 0 | 26637.222 | 26637.222
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 3396.96 | 0 | 0 | 0
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | PL: REFURBISH HEAT EXCHANGER AT ADMIN - 01 RM 126A | 001 | CLOSED | 290.196 | 0 | 290.196 | 290.196
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | PL: REFURBISH HEAT EXCHANGER AT ENGINEERING IV - 192 RM. 111 | 192 | CLOSED | 935.076 | 0 | 596.568 | 596.568
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | PL: REFURBISH HEAT EXCHANGER AT FOOD PROCESSING - 024 RM. 104D | 024 | CLOSED | 257.952 | 0 | 257.952 | 257.952
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | PL: REFURBISH HEAT EXCHANGER AT MOTT - 042 RM. 116 | 042 | CLOSED | 322.44 | 0 | 322.44 | 322.44
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | PL: REFURBISH HEAT EXCHANGER ON NEW SIDE OF HEALTH CENTER 27-181 | 027 | CLOSED | 877.0368 | 0 | 877.08 | 877.08
PJ0005636 | SR 16/17: REFURBISH HEAT EXCHANGERS - BLDS. 01, 24, 27, 42, 192 | SINE, MARK | CLOSED | 2016-11-04 | PL: REFURBISH HEAT EXCHANGER ON OLD SIDE OF HEALTH CENTER 27-171 | 027 | CLOSED | 1450.98 | 0 | 209.604 | 209.604
PJ0005636 Total | [7 empty] | 37366.5208 | 0 | 29191.062 | 29191.062
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: ALAN'S DRAPERIES | 010 | CLOSED | 3434.7 | 0 | 5788.7 | 5788.7
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: BKM FURNITURE | 010 | CLOSED | 34476.6733 | 0 | 33914.8484 | 33914.8484
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: BOWEN ENG & ENVIRONMENTAL - ABATEMENT | 010 | CLOSED | 10646.5 | 0 | 10646.5 | 10646.5
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: EC WEST FURNITURE | 010 | CLOSED | 31528.8233 | 0 | 31528.8233 | 31528.8233
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: FIT FURNITURE INSTALLATION TEAM | 010 | CLOSED | 802.5 | 0 | 530.72 | 530.72
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: FLOOR CONNECTION | 010 | CLOSED | 18022.01 | 0 | 17754.51 | 17754.51
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: ITS | 010 | CLOSED | 0 | 0 | 6082.6825 | 6082.6825
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: MCKENNA ENVIRONMENTAL | 010 | CLOSED | 2535.9 | 0 | 2289.8 | 2289.8
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | AD: STATE FIRE MARSHAL (NO CHARGES) | 010 | CLOSED | 278.2 | 0 | 0 | 0
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | CA: DEMO WALL AT BLDG 10-210 | 010 | CLOSED | 2197.824 | 0 | 2604.2974 | 2604.2974
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | CP: PROJECT CONTINGENCY | 010 | OPEN | 11879.96 | 0 | 0 | 0
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | EL: INSTALL LIGHTS AT OFFICES, REMOVE OUTLET IN 210 | 010 | CLOSED | 19469.664 | 0 | 20715.858 | 20715.858
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | IN: PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | 010 | CLOSED | 233.1252 | 0 | 105.966 | 105.966
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | LO: CHANGE LOCK TO CONSTRUCTION CORE - AG ERHART ROOM 210 | 010 | CLOSED | 121.848 | 0 | 30.462 | 30.462
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | MO: MOVE FURNITURE- BLDG 10- 210 | 010 | CLOSED | 2064.5856 | 0 | 618 | 618
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | PA: PAINT WALLS IN BLDG 10-210 AND 206 | 010 | CLOSED | 5366.916 | 0 | 6121.992 | 6121.992
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | PM: PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0005635 | PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | NORTON, DAVE | CONST_COMP | 2016-08-04 | SM: PAINT & CARPET LOBBY & OFFICE - BLDG 10 RM 210 | 010 | OPEN | 0 | 0 | 0 | 0
PJ0005635 Total | [7 empty] | 143059.2294 | 0 | 138733.1596 | 138733.1596
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | AD: STATE FIRE MARSHAL FEES | 080 | CLOSED | 160.5 | 0 | 111.7187 | 111.7187
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | CA: PJ5634 - BLDG. 80, ROOM 109 - ADD PARTITION WALL & DOORWAY | 080 | CLOSED | 3172.008 | 0 | 3096.138 | 3096.138
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | CP: PROJECT CONTINGENCY | 080 | CLOSED | 833.36 | 0 | 0 | 0
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | EL: PJ5634 - BLDG. 80, ROOM 109 - ADD PARTITION WALL & DOORWAY | 080 | CLOSED | 2077.416 | 0 | 3098.502 | 3098.502
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | IN: ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | 080 | CLOSED | 621.6672 | 0 | 282.576 | 282.576
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | PA: PJ5634 - BLDG. 80, ROOM 109ADD PARTITION WALL & DOORWAY | 080 | CLOSED | 2299.1616 | 0 | 1857.24 | 1857.24
PJ0005634 | ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | MARCHESE, JASON (WILL) | CLOSED | 2016-10-13 | PM: ADD A PARTITION WALL AND DOORWAY - BLD 80 RM 109 | 080 | CLOSED | 0 | 0 | 0 | 0
PJ0005634 Total | [7 empty] | 9164.1128 | 0 | 8446.1747 | 8446.1747
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | AD: BKM OFFICE FURNISHINGS | 038 | CLOSED | 1267.3508 | 0 | 1267.3508 | 1267.3508
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | AD: STATE FIRE MARSHAL FEES | 038 | CLOSED | 214 | 0 | 152.4536 | 152.4536
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | CA:REMOVE PORTION OF CEILING, INSTALL PROJECTOR PLATE, SPEAKERS | 038 | CLOSED | 2437.824 | 0 | 1889.982 | 1889.982
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | CP: PROJECT CONTINGENCY | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | EL:BLDG 38, 127 INSTALL NEW OUTLET AND PATHWAY FOR LOW VOLTAGE | 038 | CLOSED | 4934.832 | 0 | 6311.724 | 6311.724
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | IN: CLASSROOM A/V UPGRADE - BLD 38 RM 127 | 038 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | PA:PAINT SCREEN BOARD. BLDG. 38, ROOM 127 | 038 | CLOSED | 215.724 | 0 | 61.908 | 61.908
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | PM: CLASSROOM A/V UPGRADE - BLD 38 RM 127 | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0005633 | CLASSROOM A/V UPGRADE - BLD 38 RM 127 | MOLLAN, CHERYL L. | CONST_COMP | 2016-10-25 | SM: CLASSROOM A/V UPGRADE - BLD 38 RM 127 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005633 Total | [7 empty] | 9211.0188 | 0 | 9754.0624 | 9754.0624
PJ0005632 | DESIGN OFFICE SPACE - BLD 38 RM 152 | DILLON, JEFFREY | TO_CANCEL | 2016-10-18 | AD: RRM DESIGN | 038 | CLOSED | 16617.1 | 0 | 11230.506 | 11230.506
PJ0005632 | DESIGN OFFICE SPACE - BLD 38 RM 152 | DILLON, JEFFREY | TO_CANCEL | 2016-10-18 | AD: STATE FIRE MARSHAL | 038 | CLOSED | 0 | 0 | 171.5103 | 171.5103
PJ0005632 | DESIGN OFFICE SPACE - BLD 38 RM 152 | DILLON, JEFFREY | TO_CANCEL | 2016-10-18 | CP: PROJECT CONTINGENCY | 038 | OPEN | 1661.71 | 0 | 0 | 0
PJ0005632 | DESIGN OFFICE SPACE - BLD 38 RM 152 | DILLON, JEFFREY | TO_CANCEL | 2016-10-18 | PM: REMODEL OFFICE SPACE - BLD 38 RM 152 | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0005632 | DESIGN OFFICE SPACE - BLD 38 RM 152 | DILLON, JEFFREY | TO_CANCEL | 2016-10-18 | SM: DESIGN OFFICE SPACE - BLD 38 RM 152 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005632 Total | [7 empty] | 18278.81 | 0 | 11402.0163 | 11402.0163
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: ALAN'S DRAPERIES | 042 | OPEN | 363.8 | 0 | 363.8 | 363.8
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: BKM FURNITURE | 042 | OPEN | 48277.7473 | 0 | 48277.7473 | 48277.7473
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: FLOOR CONNECTION | 042 | OPEN | 14445 | 0 | 15215.4 | 15215.4
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: GOSS ENGINEERING | 042 | OPEN | 4173 | 0 | 4173 | 4173
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: ITS | 042 | OPEN | 2140 | 0 | 2033.214 | 2033.214
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: JOC 16.040.5631 NEWTON CONSTRUCTION | 042 | OPEN | 51916.7103 | 0 | 51916.7103 | 51916.7103
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: MCKENNA ENVIRONMENTAL | 042 | OPEN | 4815 | 246.1 | 1968.8 | 2214.9
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: MIDPOINT OFFICE | 042 | OPEN | 14980 | 0 | 12957.9033 | 12957.9033
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: STATE FIRE MARSHAL FEES | 042 | OPEN | 920.2 | 825.8046 | 158.8094 | 984.614
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: THE SIGN PLACE | 042 | OPEN | 517.0775 | 0 | 517.0775 | 517.0775
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: TRI COUNTY FURNITURE | 042 | OPEN | 919.0765 | 0 | 919.0765 | 919.0765
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | CA: CONTRACTOR ASSIST AND CALLBACK FOR CEILING LEAK- BLDG 42-205 | 042 | CLOSED | 1835.46 | 0 | 1557.84 | 1557.84
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | CP: PROJECT CONTINGENCY | 042 | OPEN | 6722.03 | 0 | 0 | 0
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | CU: ROOM CLEAN UP | 042 | OPEN | 736.824 | 0 | 88.752 | 88.752
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | EL: ELECTRICAL WORK- BLDG 42-205 | 042 | CLOSED | 19271.2643 | 0 | 15509.616 | 15509.616
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | IN: ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | 042 | ASSIGNED | 466.2504 | 0 | 388.542 | 388.542
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | MO: FURNITURE MOVE | 042 | CLOSED | 1106.028 | 0 | 420 | 420
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | PA: PAINT WALLS 205 | 042 | CLOSED | 3023.952 | 0 | 1819.356 | 1819.356
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | PL: CALL BACK FOR CEILING LEAK AT MOTT GYM | 042 | OPEN | 283.7472 | 0 | 238.248 | 238.248
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | PM: ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005631 | ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | NORTON, DAVE | CONST_COMP | 2016-09-27 | SM: ATHLETICS COMPUTER LAB - BLDG 42 RM 205 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005631 Total | [7 empty] | 176913.1675 | 1071.9046 | 158523.8923 | 159595.7969
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | AD: (RL002) AIR POLLUTION CONTROL DISTRICT | 038 | CLOSED | 479.3172 | 0 | 479.3172 | 479.3172
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | AD: COASTAL JANITORIAL | 038 | CLOSED | 0 | 0 | 4440.5 | 4440.5
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | CA: (RL002) SUPPORT PAINTING OF MATH BLDG 038 | 038 | CLOSED | 5895.72 | 0 | 7565.31 | 7565.31
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | CP: PROJECT CONTINGENCY | 038 | OPEN | 7595.51 | 0 | 0 | 0
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | EL: SUPPORT PAINTING OF MATH BLDG 038 | 038 | CLOSED | 515.424 | 0 | 4600.104 | 4600.104
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | ES: SUPPORT PAINTING OF MATH BLDG 038 | 038 | CLOSED | 13736.832 | 0 | 20107.3484 | 20107.3484
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | LA: SUPPORT PAINTING OF MATH BLDG 038 | 038 | CLOSED | 1601.28 | 0 | 2111.454 | 2111.454
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | MO: SUPPORT PAINTING OF MATH BLDG 038 | 038 | CLOSED | 536.256 | 0 | 120 | 120
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | PA: PAINT THE MATH BUILDING 038 EXT NOV11 2016 | 038 | CLOSED | 58202.448 | 0 | 57360.2337 | 57360.2337
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | PL: (RL002) SUPPORT PAINTING OF MATH BLDG 038 | 038 | CLOSED | 257.952 | 0 | 386.928 | 386.928
PJ0005630 | DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | POLVI, STEVEN | CONST_COMP | 2016-10-26 | SM: DM 16/17: EXTERIOR RESTORATION & PAINTING - BLD 038 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005630 Total | [7 empty] | 88820.7392 | 0 | 97171.1953 | 97171.1953
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: ASAP REPROGRAPHICS | 019 | CLOSED | 0 | 0 | 176.6142 | 176.6142
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: ENGLEKIRK | 019 | CLOSED | 0 | 0 | 1448.78 | 1448.78
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: HILTI | 019 | CLOSED | 588.5 | 0 | 588.5 | 588.5
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: JMPE ELECTRICAL | 019 | CLOSED | 30441.5 | 0 | 31169.1 | 31169.1
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: JOC 16.041.5629.00 MAINO | 019 | CLOSED | 234535.975 | 0 | 211702.4853 | 211702.4853
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: MCKENNA | 019 | CLOSED | 3143.66 | 0 | 2525.2 | 2525.2
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: OBSESSION ENTERTAINMENT | 019 | CLOSED | 5934.4768 | 0 | 5934.4768 | 5934.4768
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: SIGN PLACE | 019 | CLOSED | 298.9473 | 0 | 298.9473 | 298.9473
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | AD: STATE FIRE MARSHAL FEES | 019 | OPEN | 1070 | 0 | 898.3827 | 898.3827
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | CA: | 019 | CLOSED | 61.182 | 0 | 0 | 0
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | CP: PROJECT CONTINGENCY | 019 | OPEN | 26258.09 | 0 | 0 | 0
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | EL: SUPPORT FOR SWITCHGEAR REPLACEMENT DES/CONST - KOLEGRAFF | 019 | CLOSED | 75294.3263 | 0 | 75697.494 | 75697.494
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | IN: REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | 019 | CLOSED | 423.864 | 0 | 211.932 | 211.932
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | LA: ALTERNATE DINING LOCATION SUPPORT 8/16/17 | 019 | CLOSED | 240.192 | 0 | 51.372 | 51.372
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | LO: LOCKS FOR ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | 019 | CLOSED | 6140.328 | 0 | 4547.933 | 4547.933
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | PA: PAINT BLD19 | 019 | CLOSED | 8228.892 | 0 | 1021.716 | 1021.716
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | PL: SWTCHGEAR SUPPORT | 019 | CLOSED | 2160.6096 | 0 | 870.66 | 870.66
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | PM: REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | 019 | CLOSED | 0 | 0 | 0 | 0
PJ0005629 | REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-10-27 | SM: REPLACE ELECTRICAL SWITCH GEAR - BLD 19 RM 18 | 019 | OPEN | 0 | 0 | 0 | 0
PJ0005629 Total | [7 empty] | 394820.543 | 0 | 337143.5933 | 337143.5933
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | AD: BKM OFFICE | 046 | CLOSED | 129639.0707 | 0 | 129639.0707 | 129639.0707
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | AD: STATE FIRE MARSHAL | 046 | CLOSED | 278.2 | 0 | 297.2888 | 297.2888
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | CP: PROJECT CONTINGENCY | 046 | OPEN | 12610.98 | 0 | 0 | 0
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | CU: CLEAN CARPETS- BLDG 46-100 | 046 | CLOSED | 1657.854 | 0 | 1142.7158 | 1142.7158
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | EL: NEW ELEC FOR REMODEL- BLDG 46-100 | 046 | CLOSED | 6761.7984 | 0 | 6582.336 | 6582.336
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | IN: RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | 046 | CLOSED | 310.8336 | 0 | 176.61 | 176.61
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | PA: PAINT TOUCH UP | 046 | CLOSED | 1290.528 | 0 | 518.844 | 518.844
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | PM: RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | 046 | CLOSED | 0 | 0 | 0 | 0
PJ0005626 | RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | NORTON, DAVE | CONST_COMP | 2016-10-14 | SM: RECONFIGURE CUBES AND FURNITURE - BLDG 46 RM 100 | 046 | OPEN | 0 | 0 | 0 | 0
PJ0005626 Total | [7 empty] | 152549.2647 | 0 | 138356.8653 | 138356.8653
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: BKM FURNISHINGS | 033 | CLOSED | 28701.4767 | 0 | 28701.4767 | 28701.4767
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: FPCP FEES FOR ARCHITECTURAL DRAWINGS | 033 | CLOSED | 1605 | 0 | 1500 | 1500
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: GOSS ENGINEERING | 033 | CLOSED | 2675 | 0 | 2675 | 2675
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: ITS | 033 | CLOSED | 1879.99 | 0 | 1879.99 | 1879.99
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: JOC 16.042.5625 R.F. KOERBER | 033 | CLOSED | 85543.7394 | 0 | 85543.7394 | 85543.7394
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: MCKENNA ENVIRONMENTAL | 033 | CLOSED | 2986.4021 | 0 | 2986.37 | 2986.37
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | AD: STATE FIRE MARSHAL FEES | 033 | CLOSED | 588.5 | 0 | 114.3402 | 114.3402
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | CA:REMOVE WALL SOUND PANELS. UNATTACH FURNITURE | 033 | CLOSED | 333.72 | 0 | 245.016 | 245.016
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | CP: PROJECT CONTINGENCY | 033 | OPEN | 513.75 | 0 | 0 | 0
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | EL:OFFICE REMODEL | 033 | CLOSED | 14150.3173 | 0 | 12534.138 | 12534.138
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | IN: SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | 033 | CLOSED | 466.2504 | 0 | 176.61 | 176.61
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | LO: NEW HARDWARE ON 4 DOORS IN BUILDING 33 ROOMS 290 AND 209A | 033 | CLOSED | 3081.4248 | 0 | 2671.7057 | 2671.7057
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | MO:MOVE DESKS TO ROOM NEXT DOOR | 033 | CLOSED | 663.6168 | 0 | 174 | 174
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | PA: OFFICE REMODEL | 033 | CLOSED | 3323.952 | 0 | 2377.482 | 2377.482
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | PM: SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0005625 | SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | DILLON, JEFFREY | CONST_COMP | 2016-10-14 | SM: SET UP OFFICE TO ACCOMMODATE TWO NEW PEOPLE - BLD 33 RM 290 | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0005625 Total | [7 empty] | 146513.1395 | 0 | 141579.868 | 141579.868
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | AD: BKM FURNITURE | 052 | CLOSED | 6989.4433 | 0 | 6975.7366 | 6975.7366
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 102.9019 | 102.9019
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | CA: ASSIST WITH FURNITURE INSTALLATION | 052 | CLOSED | 549.456 | 0 | 55.62 | 55.62
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 907.35 | 0 | 0 | 0
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | CU: PJ5624 - CLEAN/SHAMPOO CARPETS - DUNN | 052 | CLOSED | 207.3648 | 0 | 331.956 | 331.956
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | EL: PJ5624 - BLDG. 52 E11 DISCONNECT FURNITURE - DUNN | 052 | CLOSED | 193.284 | 0 | 96.642 | 96.642
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | IN: ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | 052 | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | LO: PJ5624: ENCLOSE NEW OFFICE SPACE - BLD 52 RME11 | 052 | CLOSED | 1317.0492 | 0 | 1406.814 | 1406.814
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | PA: PATCH AND PAINT ENTIRE ROOM - DUNN | 052 | CLOSED | 1481.976 | 0 | 247.632 | 247.632
PJ0005624 | ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | DUNN, TRAVIS | CLOSED | 2016-10-04 | PM: ENCLOSE NEW OFFICE SPACE - BLD 52 RM E11 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005624 Total | [7 empty] | 11928.4993 | 0 | 9287.9465 | 9287.9465
PJ0005623 | DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | PROJECT UNASSIGNED | HOLD | 2016-10-11 | AD: STATE FIRE MARSHAL | 208 | CLOSED | 0 | 0 | 65.3342 | 65.3342
PJ0005623 | DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | PROJECT UNASSIGNED | HOLD | 2016-10-11 | AD: SWCA ENVIRONMENTAL CONSULTANTS | 208 | OPEN | 12643.12 | 0 | 4168.1315 | 4168.1315
PJ0005623 | DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | PROJECT UNASSIGNED | HOLD | 2016-10-11 | CP: PROJECT CONTINGENCY | 208 | OPEN | 1278.44 | 0 | 0 | 0
PJ0005623 | DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | PROJECT UNASSIGNED | HOLD | 2016-10-11 | IN: REPLACE/INSTALL CELLULAR POLE/VERIZON & AT&T - RADIO HILL | 208 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005623 | DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | PROJECT UNASSIGNED | HOLD | 2016-10-11 | PM: REPLACE/INSTALL CELLULAR POLE/VERIZON & AT&T - RADIO HILL | 208 | CLOSED | 0 | 0 | 0 | 0
PJ0005623 | DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | PROJECT UNASSIGNED | HOLD | 2016-10-11 | SM: DESIGN ONLY- CELLULAR TOWER/VERIZON & AT&T - RADIO HILL | 208 | OPEN | 0 | 0 | 0 | 0
PJ0005623 Total | [7 empty] | 14062.848 | 0 | 4339.4317 | 4339.4317
PJ0005622 | REPLACE CARPET - BLD 05 RMS 201 & 224 | MOLLAN, CHERYL L. | CLOSED | 2016-10-10 | AD: FLOOR CONNECTION | 005 | CLOSED | 9467.7131 | 0 | 9928.53 | 9928.53
PJ0005622 | REPLACE CARPET - BLD 05 RMS 201 & 224 | MOLLAN, CHERYL L. | CLOSED | 2016-10-10 | CA:REMOVE CARPET AND COVE- DISASSEMBLE CONFERENCE TABLE | 005 | CLOSED | 1706.004 | 0 | 1244.628 | 1244.628
PJ0005622 | REPLACE CARPET - BLD 05 RMS 201 & 224 | MOLLAN, CHERYL L. | CLOSED | 2016-10-10 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 1344.95 | 0 | 0 | 0
PJ0005622 | REPLACE CARPET - BLD 05 RMS 201 & 224 | MOLLAN, CHERYL L. | CLOSED | 2016-10-10 | IN: REPLACE CARPET - BLD 05 RMS 201 & 224 | 005 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005622 | REPLACE CARPET - BLD 05 RMS 201 & 224 | MOLLAN, CHERYL L. | CLOSED | 2016-10-10 | MO:BLDG 5, ROOMS 201A AND 224 MOVE FURNITURE | 005 | CLOSED | 670.32 | 0 | 115.188 | 115.188
PJ0005622 | REPLACE CARPET - BLD 05 RMS 201 & 224 | MOLLAN, CHERYL L. | CLOSED | 2016-10-10 | PM: REPLACE CARPET - BLD 05 RMS 201 & 224 | 005 | CLOSED | 0 | 0 | 0 | 0
PJ0005622 Total | [7 empty] | 13259.6311 | 0 | 11358.99 | 11358.99
PJ0005621 | M&R UU 17/18: CONCEPTUAL DESIGN: MUSTANG LANES, CIAO, RED RADISH | JUDD, PERRY | CONST_COMP | 2016-09-27 | AD: OMNI DESIGN GROUP | 065 | CLOSED | 96193 | 0 | 92778.6942 | 92778.6942
PJ0005621 | M&R UU 17/18: CONCEPTUAL DESIGN: MUSTANG LANES, CIAO, RED RADISH | JUDD, PERRY | CONST_COMP | 2016-09-27 | CP: PROJECT CONTINGENCY | 065 | OPEN | 1019.91 | 0 | 0 | 0
PJ0005621 | M&R UU 17/18: CONCEPTUAL DESIGN: MUSTANG LANES, CIAO, RED RADISH | JUDD, PERRY | CONST_COMP | 2016-09-27 | SM: M&R UU 17/18: CONCEPTUAL DESG: MUSTANG LNS, CIAO, RED RADISH | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005621 Total | [7 empty] | 97212.91 | 0 | 92778.6942 | 92778.6942
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | AD: FPCP MANAGEMENT/DESIGN | 013 | OPEN | 5600 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | AD: FURNITURE - 20 TABLES RM 118 | 013 | OPEN | 11120 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | AD: ITS | 013 | OPEN | 9627.52 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | AD: STATE FIRE MARSHAL | 013 | OPEN | 750 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | CA: CB SWAP 117 & 118 - REMOVE DISPLAY CASES, REINSTALL | 013 | OPEN | 15706.38 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | CP: PROJECT CONTINGENCY | 013 | OPEN | 5923.49 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | CU: CB SWAP 117 & 118 CLEAN CLASSROOMS AFTER WORK COMPLETED | 013 | OPEN | 1178.9184 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | EL: CB SWAP 117 & 118 ELECTRICAL WORK TO SWAP PC LAB | 013 | OPEN | 8036.6304 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | IN: MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | 013 | ASSIGNED | 777.084 | 0 | 105.966 | 105.966
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | LO: CB SWAP 117 & 118 INSTALL NEW DOOR LOCKS | 013 | OPEN | 2410.164 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | MO: CB SWAP 117 & 118 MOVE FURNITURE | 013 | OPEN | 1474.704 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | PA: CB SWAP 117 & 118 PAINT WALLS | 013 | OPEN | 6647.904 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | PM: MODIFY DOORS TO INCREASE CAPACITY FM 49 TO 80 IN RM 13-118 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005620 | MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | BROWN, CARLA | SCHEDULING | 2016-09-27 | SM: MODIFY DOORS TO INCREASE CAP (SWAP W/117)- BLD 13 RM 118 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0005620 Total | [7 empty] | 69252.7948 | 0 | 105.966 | 105.966
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | AD: GF GARCIA & SONS | P-A01 | OPEN | 5296.5 | 0 | 5296.5 | 5296.5
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | AD: ITS | P-A01 | OPEN | 535 | 0 | 0 | 0
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | AD: STATE FIRE MARSHAL | P-A01 | OPEN | 267.5 | 0 | 0 | 0
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | AD: WALLACE GROUP | P-A01 | OPEN | 134794.32 | 43157.4442 | 91636.8758 | 134794.32
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | CP: PROJECT CONTINGENCY | P-A01 | OPEN | 7029.5 | 0 | 0 | 0
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | CPE: MARK UNDERGROUND UTILITIES FOR NEW A-1 LOT | P-A01 | OPEN | 131.328 | 0 | 0 | 0
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | EL:DILLON-MARK UTILITIES FOR A-1 PARKING LOT | P-A01 | CLOSED | 708.708 | 0 | 193.284 | 193.284
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | LA:DILLON- MARK UTILITIES FOR A-1 PARKING LOT | P-A01 | OPEN | 440.352 | 0 | 100.08 | 100.08
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | PL: MARK UNDERGROUND UTILITIES FOR NEW A-1 LOT | P-A01 | ASSIGNED | 628.758 | 0 | 235.392 | 235.392
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | PM: REDESIGN ADMIN PARKING LOT A-1 | P-A01 | OPEN | 0 | 0 | 0 | 0
PJ0005618 | REDESIGN ADMIN PARKING LOT A-1 | DILLON, JEFFREY | DESIGN | 2016-09-10 | SM: REDESIGN ADMIN PARKING LOT A-1 | P-A01 | OPEN | 0 | 0 | 0 | 0
PJ0005618 Total | [7 empty] | 149831.966 | 43157.4442 | 97462.1318 | 140619.576
PJ0005617 | REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | DUNN, TRAVIS | CLOSED | 2016-06-29 | AD: FASULO DRYWALL | 065 | CLOSED | 848.51 | 0 | 848.51 | 848.51
PJ0005617 | REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | DUNN, TRAVIS | CLOSED | 2016-06-29 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 356.36 | 0 | 0 | 0
PJ0005617 | REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | DUNN, TRAVIS | CLOSED | 2016-06-29 | EL: PJ5617 - REMOVE/REPLACE LIGHT FIXTURE - DUNN | 065 | CLOSED | 1493.9328 | 0 | 681.432 | 681.432
PJ0005617 | REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | DUNN, TRAVIS | CLOSED | 2016-06-29 | IN: REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | 065 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005617 | REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | DUNN, TRAVIS | CLOSED | 2016-06-29 | PA: PJ5617 - PAINT NEW DRYWALL - DUNN | 065 | CLOSED | 1149.5808 | 0 | 278.586 | 278.586
PJ0005617 | REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | DUNN, TRAVIS | CLOSED | 2016-06-29 | PM: REPAIR DAMAGE FROM OLD LEAK - BLD 65 RM 101 | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0005617 Total | [7 empty] | 3919.0276 | 0 | 1879.172 | 1879.172
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: A-TOWN AUDIO VIDEO | 192 | CLOSED | 31941.8968 | 0 | 31941.8861 | 31941.8861
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: BKM | 192 | CLOSED | 102243.0903 | 0 | 102243.0903 | 102243.0903
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: FLOOR CONNECTION | 192 | CLOSED | 16579.65 | 0 | 16579.65 | 16579.65
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: ITS | 192 | CLOSED | 374.5 | 0 | 370.7336 | 370.7336
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | AD: STATE FIRE MARSHAL | 192 | CLOSED | 214 | 0 | 134.5204 | 134.5204
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | CA:REMOVE WHITEBOARDS IN ROOM 322, ENGINEERING IV | 192 | CLOSED | 365.91 | 0 | 895.188 | 895.188
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | CP: PROJECT CONTINGENCY | 192 | OPEN | 6748.38 | 0 | 0 | 0
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | EL:BLDG. 192, ENG IV, ROOMS 321, 322 CONNECT "THREAD" TO ELECTRI | 192 | CLOSED | 4034.832 | 0 | 4127.838 | 4127.838
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | IN: REMODEL - BLD 192 RMS 321 & 322 | 192 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | LO:BLDG 192, RM 321, 322 CHANGE CORES TO CONSTRUCTION FROM 6.19 | 192 | CLOSED | 121.848 | 0 | 60.924 | 60.924
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | MO:BLDG. 192, ROOMS 321, 322- MOVE FURNITURE | 192 | CLOSED | 670.32 | 0 | 96 | 96
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | PA:BDG 192, ROOM 321, 322 PAINT ROOMS | 192 | CLOSED | 3143.952 | 0 | 3630.582 | 3630.582
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | PL:REMOVE SINK AND LEAVE IN ROOM BLDG. 192, RM 321 | 192 | CLOSED | 1009.368 | 0 | 1021.43 | 1021.43
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | PM: REMODEL - BLD 192 RMS 321 & 322 | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0005616 | REMODEL - BLD 192 RMS 321 & 322 | NORTON, DAVE | CONST_COMP | 2016-09-27 | SM: REMODEL - BLD 192 RMS 321 & 322 | 192 | OPEN | 0 | 0 | 0 | 0
PJ0005616 Total | [7 empty] | 167589.0351 | 0 | 161207.8084 | 161207.8084
PJ0005614 | INSTALL PANIC BUTTON - BLD 43 - RM 107 | DUNN, TRAVIS | CLOSED | 2016-09-23 | AD: CAME SECURITY | 043 | CLOSED | 2006.25 | 0 | 2006.25 | 2006.25
PJ0005614 | INSTALL PANIC BUTTON - BLD 43 - RM 107 | DUNN, TRAVIS | CLOSED | 2016-09-23 | ANTS: PANIC BUTTON TESTING - REC CENTER ROOM 107 | 043 | CLOSED | 135.552 | 0 | 67.776 | 67.776
PJ0005614 | INSTALL PANIC BUTTON - BLD 43 - RM 107 | DUNN, TRAVIS | CLOSED | 2016-09-23 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 79.2 | 0 | 0 | 0
PJ0005614 | INSTALL PANIC BUTTON - BLD 43 - RM 107 | DUNN, TRAVIS | CLOSED | 2016-09-23 | IN: INSTALL PANIC BUTTON - BLD 43 - RM 107 | 043 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005614 | INSTALL PANIC BUTTON - BLD 43 - RM 107 | DUNN, TRAVIS | CLOSED | 2016-09-23 | PM: INSTALL PANIC BUTTON - BLD 43 - RM 107 | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005614 Total | [7 empty] | 2362.29 | 0 | 2179.992 | 2179.992
PJ0005612 | INSTALL 7 CEILING FANS - BLD 25 RM 208 | DUNN, TRAVIS | CONST_COMP | 2016-09-09 | CP: PROJECT CONTINGENCY | 025 | OPEN | 1295.83 | 0 | 0 | 0
PJ0005612 | INSTALL 7 CEILING FANS - BLD 25 RM 208 | DUNN, TRAVIS | CONST_COMP | 2016-09-09 | EL: PJ5612 - INSTALL 7 CEILING FANS BLD 25 SUITE 208 - DUNN | 025 | CLOSED | 12269.664 | 0 | 13167.912 | 13167.912
PJ0005612 | INSTALL 7 CEILING FANS - BLD 25 RM 208 | DUNN, TRAVIS | CONST_COMP | 2016-09-09 | IN: INSTALL 7 CEILING FANS - BLD 25 RM 208 | 025 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005612 | INSTALL 7 CEILING FANS - BLD 25 RM 208 | DUNN, TRAVIS | CONST_COMP | 2016-09-09 | PM: EVALUATE INSTALLING CEILING FANS - BLD 25 RM 208 | 025 | CLOSED | 0 | 0 | 0 | 0
PJ0005612 | INSTALL 7 CEILING FANS - BLD 25 RM 208 | DUNN, TRAVIS | CONST_COMP | 2016-09-09 | SM: INSTALL 7 CEILING FANS - BLD 25 RM 208 | 025 | OPEN | 0 | 0 | 0 | 0
PJ0005612 Total | [7 empty] | 13706.782 | 0 | 13273.878 | 13273.878
PJ0005609 | CHANGE EXTERIOR SIGNAGE - BLD 11 NORTHEAST CORNER | KUENTZEL, DOUGLAS A. | APPR_PEND | 2016-08-31 | CP: PROJECT CONTINGENCY | 011 | OPEN | 0 | 0 | 0 | 0
PJ0005609 | CHANGE EXTERIOR SIGNAGE - BLD 11 NORTHEAST CORNER | KUENTZEL, DOUGLAS A. | APPR_PEND | 2016-08-31 | PM: CHANGE EXTERIOR SIGNAGE - BLD 11 NORTHEAST CORNER | 011 | OPEN | 0 | 0 | 0 | 0
PJ0005609 | CHANGE EXTERIOR SIGNAGE - BLD 11 NORTHEAST CORNER | KUENTZEL, DOUGLAS A. | APPR_PEND | 2016-08-31 | SM: CHANGE EXTERIOR SIGNAGE - BLD 11 NORTHEAST CORNER | 011 | OPEN | 0 | 0 | 0 | 0
PJ0005609 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | AD: GOSS | 113 | OPEN | 19955.5 | 11973.3 | 7982.2 | 19955.5
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | CP: PROJECT CONTINGENCY | 113 | OPEN | 2131.87 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | CPE: | 113 | OPEN | 361.152 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | EH&S: | 113 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | EL: | 113 | OPEN | 354.354 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | ES: | 113 | OPEN | 361.152 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | IN: DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | 113 | ASSIGNED | 77.7084 | 0 | 35.322 | 35.322
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | LO: | 113 | OPEN | 67.0164 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | PL: | 113 | OPEN | 70.9368 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | PM: INSTALL COGENERATION SYSTEM - RES 113 SIERRA MADRE | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005608 | DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | KOLEGRAFF, KENNETH | DESIGN | 2016-08-22 | SM: DESIGN COGENERATION SYSTEM - RES 113 SIERRA MADRE | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005608 Total | [7 empty] | 23450.4944 | 11973.3 | 8017.522 | 19990.822
PJ0005607 | SR 16/17: ELEVATOR SEISMIC RETROFIT - ARCH 05 | FLEDDERMAN, JUDE | CLOSED | 2016-09-02 | AD: REPUBLIC ELEVATOR | 005 | CLOSED | 21271.6 | 0 | 21271.6 | 21271.6
PJ0005607 | SR 16/17: ELEVATOR SEISMIC RETROFIT - ARCH 05 | FLEDDERMAN, JUDE | CLOSED | 2016-09-02 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 2127.16 | 0 | 0 | 0
PJ0005607 Total | [7 empty] | 23398.76 | 0 | 21271.6 | 21271.6
PJ0005606 | SR 16/17: REPLACE BOILER TUBES - BLD 40 | SINE, MARK | CLOSED | 2016-08-31 | AD: RF MACDONALD | 040 | CLOSED | 0 | 0 | 11891.98 | 11891.98
PJ0005606 | SR 16/17: REPLACE BOILER TUBES - BLD 40 | SINE, MARK | CLOSED | 2016-08-31 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0005606 Total | [7 empty] | 0 | 0 | 11891.98 | 11891.98
PJ0005605 | SR 16/17: TENT FOR TERMITES & REPLACE FLOORING CHEDA | POLVI, STEVEN | CLOSED | 2016-08-31 | AD: FLOOR CONNECTION | 121A | CLOSED | 15996.5 | 0 | 15996.5 | 15996.5
PJ0005605 | SR 16/17: TENT FOR TERMITES & REPLACE FLOORING CHEDA | POLVI, STEVEN | CLOSED | 2016-08-31 | AD: O'CONNER PEST CONTROL | 121A | CLOSED | 6420 | 0 | 3916.2 | 3916.2
PJ0005605 | SR 16/17: TENT FOR TERMITES & REPLACE FLOORING CHEDA | POLVI, STEVEN | CLOSED | 2016-08-31 | CA: SUPPORT FLOORING INSTALLATION AT MCCLOUD RES. | 121A | CLOSED | 2557.824 | 0 | 584.01 | 584.01
PJ0005605 | SR 16/17: TENT FOR TERMITES & REPLACE FLOORING CHEDA | POLVI, STEVEN | CLOSED | 2016-08-31 | CP: PROJECT CONTINGENCY | 121A | CLOSED | 2677.52 | 0 | 0 | 0
PJ0005605 | SR 16/17: TENT FOR TERMITES & REPLACE FLOORING CHEDA | POLVI, STEVEN | CLOSED | 2016-08-31 | PL: DISCONNNECT/RECONNECT PROPANE - CHEDA STUDENT RES(BLDG 121) | 121A | CLOSED | 589.4203 | 0 | 199.92 | 199.92
PJ0005605 Total | [7 empty] | 28241.2643 | 0 | 20696.63 | 20696.63
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | CP: PROJECT CONTINGENCY | 024 | OPEN | 329.69 | 0 | 0 | 0
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | CPE: SUPPORT TO DETERMINE BLDG 24 POWER DISTRIBUTION - KOLEGRAFF | 024 | ASSIGNED | 1589.0688 | 0 | 469.482 | 469.482
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | EH&S: | 024 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | EL: SUPPORT TO DETERMINE BLDG 24 POWER DISTRIBUTION - KOLEGRAFF | 024 | CLOSED | 1559.1576 | 0 | 531.54 | 531.54
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | IN: INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | 024 | CLOSED | 77.7084 | 0 | 70.644 | 70.644
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | PM: INSTALL GENERATOR CIRCUIT BREAKER CONNECTION-BLD 24 | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005604 | INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-25 | SM: INSTALL GENERATOR CIRCUIT BREAKER CONNECTION - BLD 24 | 024 | OPEN | 0 | 0 | 0 | 0
PJ0005604 Total | [7 empty] | 3626.4296 | 0 | 1071.666 | 1071.666
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | CU: SUPPORT FOR EVENING WITH THE PRESIDENT - SEPT 18 - N/L | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | CU: SUPPORT FOR WOW | GENERAL | CLOSED | 0 | 0 | 731.496 | 731.496
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | EL: ELECTRICAL SUPPORT FOR EVENING WITH PRESIDENT - 9/17 | 003 | CLOSED | 0 | 0 | 386.568 | 386.568
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | EL: SUPPORT FOR WOW ACTIVITIES | GENERAL | CLOSED | 0 | 0 | 769.392 | 769.392
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | LA: LANDSCAPE SERVICES SUPPORT FOR WOW | GENERAL | CLOSED | 0 | 0 | 1318.8282 | 1318.8282
PJ0005603 | 2016 SUPPORT FOR WOW (PROJECT) | POPHAM, DONALD J. | CLOSED | 2016-08-29 | LA: SUPPORT FOR EVENING WITH THE PRESIDENT (9/18) | 003 | CLOSED | 0 | 0 | 48.09 | 48.09
PJ0005603 Total | [7 empty] | 0 | 0 | 3254.3742 | 3254.3742
PJ0005601 | PANIC BUTTON ALARM SYSTEM - BLDG 124 | PROJECT UNASSIGNED | HOLD | 2016-08-08 | CP: PROJECT CONTINGENCY | 124 | OPEN | 0 | 0 | 0 | 0
PJ0005601 | PANIC BUTTON ALARM SYSTEM - BLDG 124 | PROJECT UNASSIGNED | HOLD | 2016-08-08 | PM: PANIC BUTTON ALARM SYSTEM - BLDG 124 | 124 | OPEN | 0 | 0 | 0 | 0
PJ0005601 | PANIC BUTTON ALARM SYSTEM - BLDG 124 | PROJECT UNASSIGNED | HOLD | 2016-08-08 | SM: PANIC BUTTON ALARM SYSTEM - BLDG 124 | 124 | OPEN | 0 | 0 | 0 | 0
PJ0005601 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: ASAP PRINTING | 052 | CLOSED | 0 | 0 | 161.463 | 161.463
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: COASTAL DEMO | 052 | CLOSED | 0 | 0 | 1483.2875 | 1483.2875
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: FLOOR CONNECTION | 052 | CLOSED | 8466.91 | 0 | 8466.91 | 8466.91
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: ITS | 052 | CLOSED | 11744.6303 | 0 | 11744.6303 | 11744.6303
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: JOC 16.042.5599 R.F. KOERBER | 052 | CLOSED | 174067.7498 | 0 | 174067.7498 | 174067.7498
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 1973.08 | 0 | 1973.08 | 1973.08
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: SALAS OBRIEN | 052 | CLOSED | 16558.25 | 0 | 16558.25 | 16558.25
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 1070 | 0 | 475.3154 | 475.3154
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | CA: | 052 | CLOSED | 61.182 | 0 | 0 | 0
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | CP: PROJECT CONTINGENCY | 052 | OPEN | 3375.37 | 0 | 0 | 0
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | CU: FINAL CLEANGING AFTER CONST. COMPLETE - KOLEGRAFF | 052 | CLOSED | 368.412 | 0 | 110.52 | 110.52
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | EL: SAFE OFF FOR DEMO AND INSTALL ELECTRICAL SYSTEM - KOLEGRAFF | 052 | CLOSED | 28702.1351 | 0 | 27810.81 | 27810.81
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | IN: ADDITION OF WALLS AND DOORS - BLD 52 RM 12, 12A, 12B | 052 | CLOSED | 353.22 | 0 | 317.898 | 317.898
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | LO: ORANGE CORE INSTALL AND HARDWARE INSTALLATION - D11 KOLEGRAF | 052 | CLOSED | 2096.1312 | 0 | 1962.87 | 1962.87
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | PA: FULL PAINT - BLDG 52 E-12 - KOLEGRAFF | 052 | CLOSED | 6647.904 | 0 | 5202.156 | 5202.156
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | PL: SAFE OFF PLUBMING FOR DEMOLITION - KOLEGRAFF | 052 | CLOSED | 2837.472 | 0 | 4630.23 | 4630.23
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | PM: ADDITION OF WALLS AND DOORS - BLD 52 RM 12, 12A, 12B | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005599 | RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | KOLEGRAFF, KENNETH | CONST_COMP | 2016-08-16 | SM: RENOVATE ROOM E12 - BLD 52 RM 12, 12A, 12B | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005599 Total | [7 empty] | 258322.4464 | 0 | 254965.17 | 254965.17
PJ0005598 | SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | POPHAM, DONALD J. | CONST_COMP | 2016-08-22 | AD: (RL002 FUNDING) A-TOWN AV | 061 | OPEN | 7179.6963 | 0 | 5481.7063 | 5481.7063
PJ0005598 | SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | POPHAM, DONALD J. | CONST_COMP | 2016-08-22 | AD: A-TOWN AUDIO VIDEO | 061 | CLOSED | 14429.806 | 0 | 14429.806 | 14429.806
PJ0005598 | SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | POPHAM, DONALD J. | CONST_COMP | 2016-08-22 | AD: LIFT RENTAL | 061 | CLOSED | 1070 | 0 | 754.8422 | 754.8422
PJ0005598 | SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | POPHAM, DONALD J. | CONST_COMP | 2016-08-22 | CA: SUPPORT AUDIO CONTRACTOR - SPANOS SOUND SYSTEM REPAIRS | 061 | CLOSED | 2158.056 | 0 | 3917.022 | 3917.022
PJ0005598 | SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | POPHAM, DONALD J. | CONST_COMP | 2016-08-22 | CP: PROJECT CONTINGENCY | 061 | OPEN | 1328.7 | 0 | 0 | 0
PJ0005598 | SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | POPHAM, DONALD J. | CONST_COMP | 2016-08-22 | SM: SR 16/17: REPAIR SOUND SYSTEM - BLD 61 SPANOS STADIUM | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005598 Total | [7 empty] | 26166.2583 | 0 | 24583.3765 | 24583.3765
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | AD: FURNITURE INSTALLATION TEAM | 001 | CLOSED | 1960.5931 | 0 | 1960.5931 | 1960.5931
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | AD: SANTA MARIA ACOUSTICAL | 001 | CLOSED | 4307.82 | 0 | 4307.82 | 4307.82
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 321 | 0 | 760.2671 | 760.2671
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | CA: PJ5597 REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM | 001 | CLOSED | 6107.1 | 0 | 4538.013 | 4538.013
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | CP: PROJECT CONTINGENCY | 001 | OPEN | 1496.6 | 0 | 0 | 0
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | EL: PJ5597 REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM | 001 | CLOSED | 283.4832 | 0 | 395.88 | 395.88
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | IN: REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | 001 | CLOSED | 310.8336 | 0 | 176.61 | 176.61
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | LO: PJ5597 REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM | 001 | CLOSED | 1351.5738 | 0 | 748.98 | 748.98
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | MO: PJ5597 REMOVE FURNITURE PIECES IN ENTRY | 001 | CLOSED | 67.032 | 0 | 24 | 24
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | PA: PJ5597 REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM | 001 | CLOSED | 832.896 | 0 | 1114.344 | 1114.344
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | PM: REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005597 | REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | DUNN, TRAVIS | CONST_COMP | 2016-08-10 | SM: REARRANGING FURNITURE & REMOVE TEMP WALL - BLD 01 RM 312 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005597 Total | [7 empty] | 17038.9317 | 0 | 14026.5072 | 14026.5072
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: ASAP REPROGRAPHICS | 052 | CLOSED | 0 | 0 | 23.2404 | 23.2404
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: BKM | 052 | CLOSED | 5269.75 | 0 | 5433.139 | 5433.139
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: DAHL INSULATION | 052 | CLOSED | 535 | 0 | 535 | 535
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: FASULO DRYWALL | 052 | CLOSED | 1605 | 0 | 2089.71 | 2089.71
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: FERGUSON (PARTS INSTALLED BY HPS) | 052 | CLOSED | 2977.9598 | 0 | 3249.3332 | 3249.3332
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: FLOOR CONNECTION | 052 | CLOSED | 1736.61 | 0 | 1736.61 | 1736.61
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: GOSS | 052 | CLOSED | 1605 | 0 | 1605 | 1605
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: HPS MECHANICAL | 052 | CLOSED | 535 | 0 | 535 | 535
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: MAINO LVPW | 052 | CLOSED | 2247 | 0 | 2247 | 2247
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 535 | 0 | 111.7187 | 111.7187
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | CA: DEMO DRYWALL IN E5 - KOLEGRAFF | 052 | CLOSED | 1957.824 | 0 | 2405.9879 | 2405.9879
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | CA: SIGNAGE "NOT AN EXIT" 70-214 | 052 | CLOSED | 0 | 0 | 18 | 18
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 601.96 | 0 | 0 | 0
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | EH&S: LAB CHARGES FOR STORAGE CLOSET RENO AT BLD 52 RM E05 | 052 | CLOSED | 0 | 0 | 246 | 246
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | EL: INSTALLATION OF ELECTRICAL RECEPTACLE - KOLEGRAFF | 052 | CLOSED | 2317.416 | 0 | 1214.67 | 1214.67
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | ES: SUPPORT FOR HEATING INSTALLATION - KOLEGRAFF | 052 | CLOSED | 2355.6864 | 0 | 65.664 | 65.664
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | IN: RENOVATE STORAGE CLOSET - BLD 52 RM E05 | 052 | CLOSED | 148.3524 | 0 | 211.932 | 211.932
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | LO: SUPPORT/INSTALLATION OF NEW HARDWARE - KOLEGRAFF | 052 | CLOSED | 970.0656 | 0 | 954.24 | 954.24
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | MO: RELOCATE STORAGE ITEMS TO BLDG 80 - KOLEGRAFF | 052 | CLOSED | 221.2056 | 0 | 102 | 102
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | PA: PAINT ROOM E5 AND T/U IN E4 - KOLEGRAFF | 052 | CLOSED | 1961.976 | 0 | 932.892 | 932.892
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | PL: DEMO EXISTING FLOOR DRAIN IN E5 - KOLEGRAFF | 052 | CLOSED | 1304.052 | 0 | 386.928 | 386.928
PJ0005596 | RENOVATE STORAGE CLOSET - BLD 52 RM E05 | KOLEGRAFF, KENNETH | CLOSED | 2016-08-03 | PM: UPGRADE TO MULTI USE SPACE - BLD 52 RM E05 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005596 Total | [7 empty] | 28884.8578 | 0 | 24104.0652 | 24104.0652
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | AD: ASAP PRINTING | 003 | CLOSED | 0 | 0 | 55.7684 | 55.7684
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | AD: GOSS ENGINEERING | 003 | CLOSED | 9416 | 0 | 9416 | 9416
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | AD: JOC 16.040.5593 NEWTON | 003 | CLOSED | 84160.2401 | 0 | 83892.9541 | 83892.9541
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | AD: SIEMENS | 003 | CLOSED | 19992.95 | 0 | 19992.95 | 19992.95
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 1498 | 0 | 142.9306 | 142.9306
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | CA: | 003 | CLOSED | 61.182 | 0 | 0 | 0
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | CP: PROJECT CONTINGENCY | 003 | OPEN | 11904.16 | 0 | 0 | 0
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | ES: support for cooling coil installation bldg. 3 - Kolegraff | 003 | CLOSED | 1155.6864 | 0 | 2501.796 | 2501.796
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | IN: REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | 003 | CLOSED | 593.4096 | 0 | 141.288 | 141.288
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | LO: INSTALLATION OF ORANGE CORES 03-110 - KOLEGRAFF | 003 | CLOSED | 134.0328 | 0 | 30.462 | 30.462
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | PA: PAINT PLASTER CEILING PATCHES IN BREEZWAY 03-110 - KOLEGRAFF | 003 | CLOSED | 1961.976 | 0 | 1182.624 | 1182.624
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | PL: PROVIDE SUPPORT FOR DRAINING BLDG 3 CHILLED WATER - KOLEGRAF | 003 | CLOSED | 128.976 | 0 | 322.44 | 322.44
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | PM: REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005593 | REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-26 | SM: REPLACE A/C FOR CURRENT AIR-FLOW SYSTEMS - BLD 03 RM 111 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005593 Total | [7 empty] | 131006.6129 | 0 | 117679.2131 | 117679.2131
PJ0005591 | SR 16/17: REPAIR WATER MAIN BREAK - TENAYA | FLEDDERMAN, JUDE | CLOSED | 2016-07-25 | AD: MAINO | 110 | CLOSED | 0 | 0 | 15325.61 | 15325.61
PJ0005591 | SR 16/17: REPAIR WATER MAIN BREAK - TENAYA | FLEDDERMAN, JUDE | CLOSED | 2016-07-25 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 0 | 0 | 0 | 0
PJ0005591 | SR 16/17: REPAIR WATER MAIN BREAK - TENAYA | FLEDDERMAN, JUDE | CLOSED | 2016-07-25 | PL: REPAIR WATER MAIN BREAK AT TENAYA | 110 | CLOSED | 0 | 0 | 2639.166 | 2639.166
PJ0005591 Total | [7 empty] | 0 | 0 | 17964.776 | 17964.776
PJ0005589 | 16/17: SUPPORT FOR SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | CP: PROJECT CONTINGENCY | 161 | OPEN | 0 | 0 | 0 | 0
PJ0005589 | 16/17: SUPPORT FOR SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | CU: SOFTBALL SUPPORT - 2017/2-17 | 161 | CLOSED | 0 | 0 | 450.1297 | 450.1297
PJ0005589 | 16/17: SUPPORT FOR SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | LA: 16/17 SUPPORT SOFTBALL PRACTICES (SEASON WO) | 161 | CLOSED | 0 | 0 | 294.912 | 294.912
PJ0005589 | 16/17: SUPPORT FOR SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | SM: 16/17: SUPPORT FOR SOFTBALL - JANSSEN FIELD 161 | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0005589 Total | [7 empty] | 0 | 0 | 745.0417 | 745.0417
PJ0005588 | 16/17: SUPPORT FOR BASEBALL (PROJECT) - BAGGETT STADIUM 160 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | CP: PROJECT CONTINGENCY | 160 | OPEN | 0 | 0 | 0 | 0
PJ0005588 | 16/17: SUPPORT FOR BASEBALL (PROJECT) - BAGGETT STADIUM 160 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | CU: BASEBALL GAMES SUPPORT | 160 | CLOSED | 0 | 0 | 1949.8314 | 1949.8314
PJ0005588 | 16/17: SUPPORT FOR BASEBALL (PROJECT) - BAGGETT STADIUM 160 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | EL: INSTALL SPIDER BOX AT BAGGETT CONCOURSE- 4/21 | 160 | CLOSED | 0 | 0 | 257.712 | 257.712
PJ0005588 | 16/17: SUPPORT FOR BASEBALL (PROJECT) - BAGGETT STADIUM 160 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | LA: 16/17 BASEBALL PRACTICES SUPPORT (SEASON WO) | 160 | CLOSED | 0 | 0 | 894.9062 | 894.9062
PJ0005588 | 16/17: SUPPORT FOR BASEBALL (PROJECT) - BAGGETT STADIUM 160 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | SM: 16/17: SUPPORT FOR BASEBALL (PROJECT) - BAGGETT STADIUM 160 | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0005588 Total | [7 empty] | 0 | 0 | 3102.4496 | 3102.4496
PJ0005587 | 16/17: SUPPORT FOR WM. SOCCER (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005587 | 16/17: SUPPORT FOR WM. SOCCER (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | CU: 16/17 SUPPORT FOR WM. SOCCER GAMES | 061 | CLOSED | 0 | 0 | 4626.1793 | 4626.1793
PJ0005587 | 16/17: SUPPORT FOR WM. SOCCER (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | LA: 16/17 SUPPORT WM. SOCCER PRACTICES (SEASON WO) | 061 | CLOSED | 0 | 0 | 360.288 | 360.288
PJ0005587 | 16/17: SUPPORT FOR WM. SOCCER (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | LA: 16/17 SUPPORT WOMEN'S SOCCER GAMES | 061 | CLOSED | 0 | 0 | 1999.368 | 1999.368
PJ0005587 | 16/17: SUPPORT FOR WM. SOCCER (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-22 | SM: 16/17: SUPPORT FOR WM. SOCCER (PROJECT) - SPANOS STADIUM 61 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005587 Total | [7 empty] | 0 | 0 | 6985.8353 | 6985.8353
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CA: 16/17 SUPPORT FOR MEN'S SOCCER V. UCSB - 10/15 | 061 | CLOSED | 0 | 0 | 539.586 | 539.586
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CPE: 16/17 SUPPORT MEN'S SOCCER V. UCSB - 10/15 | 061 | CLOSED | 0 | 0 | 325.026 | 325.026
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CU: 16/17 M. SOCCER GAME SUPPORT | 061 | CLOSED | 0 | 0 | 9301.9697 | 9301.9697
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | EL: 16/17 SUPPORT FOR MEN'S SOCCER V. UCSB - OCT. 15 | 061 | CLOSED | 0 | 0 | 248.052 | 248.052
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | LA: 16/17 SUPPORT FOR M. SOCCER GAMES (SEASON WO) | 061 | CLOSED | 0 | 0 | 3612.996 | 3612.996
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | LA: 16/17 SUPPORT MEN'S SOCCER PRACTICES (SEASON WO) | 061 | CLOSED | 0 | 0 | 1220.976 | 1220.976
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | PL: 16/17 SUPPORT FOR MEN'S SOCCER V. UCSB - 10/15 | 061 | CLOSED | 0 | 0 | 541.728 | 541.728
PJ0005586 | 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | SM: 16/17: SUPPORT FOR MEN'S SOCCER (PROJECT) SPANOS STADIUM 61 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005586 Total | [7 empty] | 0 | 0 | 15790.3337 | 15790.3337
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | AD: PORT-A-COOL RENTAL FOR FOOTBALL - N/L | 061 | CLOSED | 0 | 0 | 1508.0366 | 1508.0366
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | AD: REPUBLIC ELEVATOR | 061 | CLOSED | 0 | 0 | 1172.72 | 1172.72
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CA: 16/17 FOOTBALL GAME SUPPORT | 061 | CLOSED | 0 | 0 | 2605.854 | 2605.854
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CPE: 16/17 FOOTBALL GAME SUPPORT | 061 | CLOSED | 0 | 0 | 1805.7 | 1805.7
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CU: 16/17 FOOTBALL GAMES SUPPORT | 061 | CLOSED | 0 | 0 | 17205.9266 | 17205.9266
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | CU: POWERWASH THE SOUTH BLEACHER PADS | 061 | CLOSED | 0 | 0 | 81.264 | 81.264
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | EL: 16/17 FOOTBALL GAME SUPPORT | 061 | CLOSED | 0 | 0 | 5342.1 | 5342.1
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | LA: 16/17 FOOTBALL GAME SUPPORT | 061 | CLOSED | 0 | 0 | 36393.6761 | 36393.6761
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | LA: 16/17 SUPPORT FOR FOOTBALL PRACTICES/SCRIMMAGES | 061 | CLOSED | 0 | 0 | 4134.468 | 4134.468
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | PL: 16/17 FOOTBALL GAME SUPPORT | 061 | CLOSED | 0 | 0 | 2466.9534 | 2466.9534
PJ0005585 | 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | POPHAM, DONALD J. | CONST_COMP | 2016-07-20 | SM: 16/17: SUPPORT FOR FOOTBALL (PROJECT) - SPANOS STADIUM 61 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005585 Total | [7 empty] | 0 | 0 | 72716.6988 | 72716.6988
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | AD: JOC 16.041.5584.00 MAINO | 113 | CLOSED | 0 | 0 | 16680.6366 | 16680.6366
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | AD: STATE FIRE MARSHAL FEES | 113 | CLOSED | 572.45 | 0 | 1090.2016 | 1090.2016
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | CP: PROJECT CONTINGENCY | 113 | OPEN | 2414.76 | 0 | 0 | 0
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | EL: INSTALLATION OF LIGHTING CONTROLS - KOLEGRAFF | 113 | CLOSED | 3227.8656 | 0 | 4031.046 | 4031.046
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | IN: INSTALL STORAGE CLOSET PARTN - RES 113 (SIERRA MADRE HALL ) | 113 | CLOSED | 211.932 | 0 | 247.254 | 247.254
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | LO: SUPPORT AND INSTALLATION OF NEW HARDWARE - KOLEGRAFF | 113 | CLOSED | 1182.5574 | 0 | 1371.366 | 1371.366
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | PA: PAINT NEW WALLS 410 & 510 - KOLEGRAFF | 113 | CLOSED | 2642.964 | 0 | 619.08 | 619.08
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | PM: INSTALL STORAGE CLOSET PARTITIONS-RES 113 (SM HALL ) | 113 | CLOSED | 0 | 0 | 0 | 0
PJ0005584 | INSTALL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4 & 5 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-07-07 | SM: INSTL STORAGE CLOSET PARTITIONS - SIERRA MADRE 113 TWRS 4&5 | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005584 Total | [7 empty] | 10252.529 | 0 | 24039.5842 | 24039.5842
PJ0005583 | REMOVE NON-STRUCTURAL CORE AT SHELL HOUSE - ARCH VILLAGE 95C | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2016-07-17 | CP: PROJECT CONTINGENCY | 095C | OPEN | 0 | 0 | 0 | 0
PJ0005583 | REMOVE NON-STRUCTURAL CORE AT SHELL HOUSE - ARCH VILLAGE 95C | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2016-07-17 | PM: REMOVE NON-STRUCTURAL CORE AT SHELL HOUSE - ARCH VILLAGE 95C | 095C | OPEN | 0 | 0 | 0 | 0
PJ0005583 | REMOVE NON-STRUCTURAL CORE AT SHELL HOUSE - ARCH VILLAGE 95C | KUENTZEL, DOUGLAS A. | SCOPE_DEV | 2016-07-17 | SM: REMOVE NON-STRUCTURAL CORE AT SHELL HOUSE - ARCH VILLAGE 95C | 095C | OPEN | 0 | 0 | 0 | 0
PJ0005583 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | AD: BOWEN ENGINEERING & ENVIRONMENTAL | 150 | CLOSED | 14091.9 | 0 | 14091.9 | 14091.9
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | AD: JL FASULO | 150 | CLOSED | 7633.38 | 0 | 7633.38 | 7633.38
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | AD: MILLENNIUM ENVIRONMENTAL | 150 | CLOSED | 2140 | 0 | 5543.5095 | 5543.5095
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | AD: WATERLINE TILE | 150 | CLOSED | 9844 | 0 | 9844 | 9844
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | CA: SUPPORT MOLD REMOVAL - POULTRY BLDG 150 RM 106B | 150 | CLOSED | 2224.8 | 0 | 1475.484 | 1475.484
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | CP: PROJECT CONTINGENCY | 150 | CLOSED | 3981.8 | 0 | 0 | 0
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | EH&S: | 150 | CLOSED | 643.68 | 0 | 0 | 0
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | EL: SUPPORT MOLD REMOVAL WORK - POULTRY 150 | 150 | CLOSED | 644.28 | 0 | 64.428 | 64.428
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | ES: REINSTALL REGISTER IN DUCT IN SHOWER IN MEN'S LOCKER ROOM | 150 | CLOSED | 65.664 | 0 | 196.992 | 196.992
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | IN: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY BLDG 150-106B | 150 | CLOSED | 353.22 | 0 | 70.644 | 70.644
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | PA: PAINT WALLS - POULTRY BLDG 150 - RM 106B | 150 | CLOSED | 1609.608 | 0 | 1269.114 | 1269.114
PJ0005582 | SR 16/17: WATER DAMAGE IN MEN'S LOCKER ROOM - POULTRY 150-106B | POLVI, STEVEN | CLOSED | 2016-07-14 | PL: REPAIR PLUMBING IN SHOWER AT POULTRY BLDG. 150 RM. 106B | 150 | CLOSED | 1289.76 | 0 | 467.928 | 467.928
PJ0005582 Total | [7 empty] | 44522.092 | 0 | 40657.3795 | 40657.3795
PJ0005581 | REMOVE CEILING PANELS & REPLACE DOORS - BLD 34 RM 134 | NORTON, DAVE | SCOPE_DEV | 2016-07-12 | AD: MCKENNA | 034 | OPEN | 793.94 | 302.81 | 491.13 | 793.94
PJ0005581 | REMOVE CEILING PANELS & REPLACE DOORS - BLD 34 RM 134 | NORTON, DAVE | SCOPE_DEV | 2016-07-12 | CP: PROJECT CONTINGENCY | 034 | OPEN | 79.39 | 0 | 0 | 0
PJ0005581 | REMOVE CEILING PANELS & REPLACE DOORS - BLD 34 RM 134 | NORTON, DAVE | SCOPE_DEV | 2016-07-12 | PM: REMOVE CEILING PANELS & REPLACE DOORS - BLD 34 RM 134 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005581 | REMOVE CEILING PANELS & REPLACE DOORS - BLD 34 RM 134 | NORTON, DAVE | SCOPE_DEV | 2016-07-12 | SM: REMOVE CEILING PANELS & REPLACE DOORS - BLD 34 RM 134 | 034 | OPEN | 0 | 0 | 0 | 0
PJ0005581 Total | [7 empty] | 873.33 | 302.81 | 491.13 | 793.94
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | AD: (DESIGN) STATE FIRE MARSHAL FEES | 051 | OPEN | 481.5 | 0 | 232.4896 | 232.4896
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | AD: EARTH SYSTEMS | 051 | OPEN | 4896.32 | 4896.32 | 0 | 4896.32
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | AD: GREEN AND CLEAN | 051 | OPEN | 273920 | 208864 | 65056 | 273920
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | AD: LIGHT FIXTURES | 051 | PEND_MATL | 33897.6 | 0 | 0 | 0
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | AD: RRM CONSTRUCTION MGMT | 051 | OPEN | 6634 | 6634 | 0 | 6634
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | AD: RRM DESIGN | 051 | OPEN | 35909.2 | 0 | 35909.2 | 35909.2
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | CA: (CONSTR) | 051 | OPEN | 1044.96 | 0 | 0 | 0
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | CP: PROJECT CONTINGENCY | 051 | OPEN | 10756.07 | 0 | 0 | 0
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | EL: CB UH LANDSCAPE - REMOVE LIGHTING, LAYDOWN CONDUIT, INSTALL | 051 | OPEN | 12692.544 | 0 | 4073.922 | 4073.922
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | IN: (CONSTR) 16/17: UNIVERSITY HOUSE LANDSCAPE DESIGN & CONSTR | 051 | ASSIGNED | 353.22 | 0 | 211.932 | 211.932
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | IN: (DESIGN) 16/17: UNIVERSITY HOUSE LANDSCAPE DESIGN - BLD 51 | 051 | ASSIGNED | 282.576 | 0 | 70.644 | 70.644
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | LA: CB LANDSCAPE SUPPORT DURING CONSTRUCTION WORK | 051 | OPEN | 1921.536 | 0 | 2280.5852 | 2280.5852
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | PA: CB UNIVERSITY HOUSE LANDSCAPE | 051 | OPEN | 3923.952 | 0 | 0 | 0
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | PL: PRESIDENTS HOUSE LANDSCAPE SUPPORT (CONSTR) | 051 | LONG_TERM | 1134.9888 | 0 | 2552.6966 | 2552.6966
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | PM: 16/17: UNIVERSITY HOUSE LANDSCAPE DESIGN - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005580 | 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | BROWN, CARLA | IN_CONSTR | 2016-07-08 | SM: 16/17: UNIVERSITY HOUSE EXTERIOR IMPROVEMENTS - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005580 Total | [7 empty] | 387848.4668 | 220394.32 | 110387.4695 | 330781.7895
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | AD: ITS | 003 | CLOSED | 425.3785 | 0 | 425.3785 | 425.3785
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | AD: JL FASULO DRYWALL | 003 | CLOSED | 2213.83 | 0 | 2213.83 | 2213.83
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | AD: RISE VISION USA | 003 | CLOSED | 44533.079 | 0 | 42312.615 | 42312.615
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 0 | 0 | 106.1761 | 106.1761
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | CA: INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | 003 | CLOSED | 1975.914 | 0 | 2370.351 | 2370.351
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 4971.9 | 0 | 0 | 0
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | EL: SHUTOFF POWER TO ROOM | 003 | CLOSED | 474.354 | 0 | 364.02 | 364.02
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | IN: INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | 003 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | MO: REMOVE TWO DISPLAYS FROM ROOM | 003 | CLOSED | 73.7352 | 0 | 108 | 108
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | PA: PRIME AND PAINT NEW DRYWALL TEXTURE 302 | 003 | CLOSED | 1329.5808 | 0 | 484.872 | 484.872
PJ0005579 | INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | DUNN, TRAVIS | CLOSED | 2016-07-07 | PM: INSTALL DISPLAYS AND TICKERS - BLD 03 RM 302 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005579 Total | [7 empty] | 56280.3475 | 0 | 48561.8526 | 48561.8526
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CP: PROJECT CONTINGENCY | 044 | OPEN | 0 | 0 | 0 | 0
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE EVENT SUPPORT - 9/17 | 044 | CLOSED | 0 | 0 | 55.26 | 55.26
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE EVENT SUPPORT - 9/24 | 044 | CLOSED | 0 | 0 | 37.65 | 37.65
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE EVENT SUPPORT - COMMENCEMENT | 044 | CLOSED | 0 | 0 | 36.84 | 36.84
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT - MILO EVENT - 1/31 | 044 | CLOSED | 0 | 0 | 18.42 | 18.42
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (AFRICAN GUITAR SUMMIT) | 044 | CLOSED | 0 | 0 | 55.26 | 55.26
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (AHS CHORAL SHOW)3/25 | 044 | CLOSED | 0 | 0 | 57.186 | 57.186
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (BIRDS) - 5/11 | 044 | CLOSED | 0 | 0 | 201.5104 | 201.5104
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (BLUE SOLIEL) - 4/19 | 044 | CLOSED | 0 | 0 | 202.2 | 202.2
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (CORE DANCE) | 044 | CLOSED | 0 | 0 | 56.3321 | 56.3321
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (COSI) - 11/12 | 044 | CLOSED | 0 | 0 | 214.746 | 214.746
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT (MYSTICAL ART OF TIBET)-4/14 | 044 | CLOSED | 0 | 0 | 40.44 | 40.44
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT - 10/20 | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT - 12/9 | 044 | CLOSED | 0 | 0 | 55.26 | 55.26
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT - DANCE RECITAL | 044 | CLOSED | 0 | 0 | 110.52 | 110.52
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT - ENCORE | 044 | CLOSED | 0 | 0 | 55.26 | 55.26
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT(CITY BALLET SLO)-4/1 | 044 | CLOSED | 0 | 0 | 75.1052 | 75.1052
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT(IN THE MOOD) - 3/26 | 044 | CLOSED | 0 | 0 | 76.248 | 76.248
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT(PIRATES OF PENZANCE)-4/8 | 044 | CLOSED | 0 | 0 | 75.5161 | 75.5161
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE SUPPORT- STUDENT DANCE | 044 | CLOSED | 0 | 0 | 110.52 | 110.52
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SPANOS THEATRE THEATRE SUPPORT- ARAB ENSEMBLE | 044 | CLOSED | 0 | 0 | 74.6751 | 74.6751
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR JAZZ REACH PERFORMANCE. - 2/4/2017 | 044 | CLOSED | 0 | 0 | 58.0399 | 58.0399
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR RYAN ADAMS DANCE PERF. | 044 | CLOSED | 0 | 0 | 115.056 | 115.056
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATER (A CHRISTMAS CAROL) | 044 | CLOSED | 0 | 0 | 119.3198 | 119.3198
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATER EVENT (ORCHESIS)-1/28 | 044 | CLOSED | 0 | 0 | 128.52 | 128.52
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE (SLO DAYS) | 044 | CLOSED | 0 | 0 | 42.024 | 42.024
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE (WILLY WONKA)-7/16 | 044 | CLOSED | 0 | 0 | 180.252 | 180.252
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE - REVIVE | 044 | CLOSED | 0 | 0 | 56.865 | 56.865
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE EVENT - 1/16/2017 | 044 | CLOSED | 0 | 0 | 40.44 | 40.44
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE EVENT - JAN 21, 2017 | 044 | CLOSED | 0 | 0 | 112.6778 | 112.6778
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE(HAWAIIAN MUSIC)-3/15 | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT FOR SPANOS THEATRE- -INFUSION | 044 | CLOSED | 0 | 0 | 56.6339 | 56.6339
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | CU: SUPPORT SPANOS THEATRE - SPELLING BEE PERF. | 044 | CLOSED | 0 | 0 | 137.7161 | 137.7161
PJ0005578 | 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | POPHAM, DONALD J. | CONST_COMP | 2016-07-13 | SM: 16/17: SPANOS THEATRE EVENT SUPPORT - BLD 44 | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0005578 Total | [7 empty] | 0 | 0 | 2803.8536 | 2803.8536
PJ0005577 | INSTALL PANIC BUTTONS - BLDS. 31,106, 113, 114, 170, 171 | PROJECT UNASSIGNED | HOLD | 2016-02-17 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005577 | INSTALL PANIC BUTTONS - BLDS. 31,106, 113, 114, 170, 171 | PROJECT UNASSIGNED | HOLD | 2016-02-17 | PM: INSTALL PANIC BUTTONS - BLDS. 31,106, 113, 114, 170, 171 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005577 | INSTALL PANIC BUTTONS - BLDS. 31,106, 113, 114, 170, 171 | PROJECT UNASSIGNED | HOLD | 2016-02-17 | SM: INSTALL PANIC BUTTONS - BLDS. 31,106, 113, 114, 170, 171 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005577 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005576 | INSTALL 4 ELECTRONIC SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | DUNN, TRAVIS | CLOSED | 2016-07-01 | AD: MAINO LVPW | 043 | CLOSED | 9941.37 | 0 | 9941.37 | 9941.37
PJ0005576 | INSTALL 4 ELECTRONIC SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | DUNN, TRAVIS | CLOSED | 2016-07-01 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 813.96 | 0 | 0 | 0
PJ0005576 | INSTALL 4 ELECTRONIC SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | DUNN, TRAVIS | CLOSED | 2016-07-01 | EL: ELECTRICAL CONNECTION REC. CENTER SCOREBOARDS | 043 | CLOSED | 1428.708 | 0 | 1371.456 | 1371.456
PJ0005576 | INSTALL 4 ELECTRONIC SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | DUNN, TRAVIS | CLOSED | 2016-07-01 | IN: INSTALL 4 ELECT SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | 043 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005576 | INSTALL 4 ELECTRONIC SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | DUNN, TRAVIS | CLOSED | 2016-07-01 | PA: 4 ELECTRONIC SCOREBOARDS | 043 | CLOSED | 1481.976 | 0 | 220.104 | 220.104
PJ0005576 | INSTALL 4 ELECTRONIC SCOREBOARDS - BLD 43 RM 100 (B4 9-16-16) | DUNN, TRAVIS | CLOSED | 2016-07-01 | PM: INSTALL 4 ELECTRONIC SCOREBOARDS-BLD 43 RM 100 (B4 9-16-16) | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005576 Total | [7 empty] | 13807.302 | 0 | 11638.896 | 11638.896
PJ0005575 | PRESIDENT'S OFFICE PANIC BUTTONS - BLD 01 RM 407 | PROJECT UNASSIGNED | HOLD | 2016-07-13 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005575 | PRESIDENT'S OFFICE PANIC BUTTONS - BLD 01 RM 407 | PROJECT UNASSIGNED | HOLD | 2016-07-13 | PM: PRESIDENT'S OFFICE PANIC BUTTONS - BLD 01 RM 407 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005575 | PRESIDENT'S OFFICE PANIC BUTTONS - BLD 01 RM 407 | PROJECT UNASSIGNED | HOLD | 2016-07-13 | SM: PRESIDENT'S OFFICE PANIC BUTTONS - BLD 01 RM 407 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005575 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | AD: COASTAL JANITORIAL | 051 | OPEN | 0 | 0 | 502.9 | 502.9
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | AD: IDLER'S | 051 | OPEN | 0 | 0 | 2278.2333 | 2278.2333
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | AD: MAINO (WATER LINE REPAIR) | 051 | OPEN | 0 | 0 | 13216.64 | 13216.64
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | AD: QUAGLINO | 051 | OPEN | 0 | 0 | 572.45 | 572.45
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | AD: RAYNE WATER CONDITIONING AT PRESIDENT'S RESIDENCE | 051 | PEND_SCHED | 0 | 0 | 643.391 | 643.391
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | AD: RUFFONI'S APPLIANCE | 051 | OPEN | 0 | 0 | 324.99 | 324.99
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | CA: ASSIST PLUMBERS WITH WATER LEAKS IN BASEMENT OF BLD. 051 | 051 | CLOSED | 0 | 0 | 182.157 | 182.157
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | CP: PROJECT CONTINGENCY | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | EL: INSPECT EXTERIOR LIGHTS AND REPLACE AS NEEDED - BLDG 51 | 051 | CLOSED | 0 | 0 | 566.304 | 566.304
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | PL: CONNECT NEW WASHER/DRIER AT PRESIDENT'S RESIDENCE | 051 | CLOSED | 0 | 0 | 193.464 | 193.464
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | PL: INSTALL NEW WATERLINE AT PRESIDENT'S RESIDENCE - 051 | 051 | CLOSED | 0 | 0 | 64.488 | 64.488
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | PL: INVESTIGATE WATER LEAKS IN BASEMENT OF PRESIDENT'S RESIDENCE | 051 | CLOSED | 0 | 0 | 146.436 | 146.436
PJ0005574 | 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | POPHAM, DONALD J. | CONST_COMP | 2016-07-14 | SM: 16/17: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLD 51 | 051 | OPEN | 0 | 0 | 0 | 0
PJ0005574 Total | [7 empty] | 0 | 0 | 18691.4533 | 18691.4533
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: ASAP REPROGRAPHICS | 035 | CLOSED | 0 | 0 | 249.2458 | 249.2458
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: FLOOR CONNECTION | 035 | CLOSED | 14407.55 | 0 | 14403.27 | 14403.27
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: GOSS ENGINEERING | 035 | CLOSED | 7896.6 | 0 | 7896.6 | 7896.6
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: ITS | 035 | CLOSED | 2163.647 | 0 | 2163.647 | 2163.647
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: JOC 16-039.011 NEWTON | 035 | CLOSED | 67633.5337 | 0 | 67633.5337 | 67633.5337
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: MCKENNA ENVIRONMENTAL | 035 | CLOSED | 1070 | 0 | 749 | 749
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: QUARESMA DRYWALL | 035 | CLOSED | 535 | 0 | 535 | 535
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: SIMPLEX GRINNEL | 035 | CLOSED | 11089.9294 | 0 | 11089.9401 | 11089.9401
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 1070 | 0 | 1026.4403 | 1026.4403
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | CA: Installation of 3 door stops room 209C, 209D, 209E | 035 | CLOSED | 305.91 | 0 | 222.48 | 222.48
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | CP: PROJECT CONTINGENCY | 035 | OPEN | 661.53 | 0 | 0 | 0
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | CPE: MODIFY DUCT WORK FOR 209 REMODEL - KOLEGRAFF | 035 | CLOSED | 18662.0352 | 0 | 8713.74 | 8713.74
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | CU: FULL CLEANING AFTER FURNITURE REMOVAL | 035 | CLOSED | 1105.236 | 0 | 705.1474 | 705.1474
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | EL: INSTALLATION OF ELECTRICAL SYSTEMS PER PLAN - KOLEGRAFF | 035 | CLOSED | 14008.4004 | 0 | 14363.598 | 14363.598
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | IN: RENOVATE ROOM 209 - BLD 35 RM 209 | 035 | CLOSED | 310.8336 | 0 | 494.508 | 494.508
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | LO: SUPPORT AND HARDWARE INSTALLATION - KOLEGRAFF | 035 | CLOSED | 3670.164 | 0 | 1889 | 1889
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | MO: SUPPORT FOR RELOCATING - KOLEGRAFF | 035 | CLOSED | 351.918 | 0 | 204 | 204
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | PA: PAINT WALLS, NEW DUCT, DOOR FRAMES 35 - 209 - KOLEGRAFF | 035 | CLOSED | 8447.904 | 0 | 4974.432 | 4974.432
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | PM: RENOVATE ROOM 209 - BLD 35 RM 209 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005573 | RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | KOLEGRAFF, KENNETH | CONST_COMP | 2016-06-21 | SM: RENOVATE CTLT ROOM 209 - BLD 35 RM 209 | 035 | OPEN | 0 | 0 | 0 | 0
PJ0005573 Total | [7 empty] | 153390.1913 | 0 | 137313.5823 | 137313.5823
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | CP: PROJECT CONTINGENCY | 061 | OPEN | 0 | 0 | 0 | 0
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | CU: FOOTBALL TAILGATING SUPPORT (SEASON) | 061 | CLOSED | 0 | 0 | 1395.3222 | 1395.3222
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | EL: INSTALL POWER FOR MUSTANG BBQ - O'NEILL LAWN (SEASON) | 003 | CLOSED | 0 | 0 | 1589.496 | 1589.496
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | EL: SUPPLY POWER FOR SPIDER BOX AT 186 TAILGATING | 186 | CLOSED | 0 | 0 | 677.352 | 677.352
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | LA: LANDSCAPE/IRRIGATION REPAIR - MUSTANG BBQ (O'NEILL LAWN) | 003 | CLOSED | 0 | 0 | 360.288 | 360.288
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | LA: SUPPORT FOR TAILGATING AND MUSTANG BBQ - 10/21 | 061 | CLOSED | 0 | 0 | 525.678 | 525.678
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | LINERS FOR BASKETBALL TENT AT MOTT GYM | 061 | CLOSED | 0 | 0 | 113.647 | 113.647
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | LS: INSTALL LOCK HASPS ON REFRIG. DOORS- SPANOS STADIUM | 061D | CLOSED | 0 | 0 | 301.234 | 301.234
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | MC: MOVE FLOOR TILES FROM MOOT GYM - BLDG. 80 | 061 | CLOSED | 0 | 0 | 96 | 96
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | MC: PLEASE DELIVER 5 PALLETS OF ADA MATS MOTT GYM (11/10) | 042 | CLOSED | 0 | 0 | 36 | 36
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | PERMIT: FOOTBALL TAILGATING PERMIT | 061 | CLOSED | 0 | 0 | 388.542 | 388.542
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | RE: 16/17 FOOTBALL BBQ SUPPORT | 061 | CLOSED | 0 | 0 | 1775.112 | 1775.112
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | RE: PLAYOFF GAME TAILGATE SUPPORT (11/26) | 061 | CLOSED | 0 | 0 | 287.856 | 287.856
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | RENTAL: BASEBALL ALUMNI RECEPTION - 4.21 | 061 | CLOSED | 0 | 0 | 45 | 45
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | SM: 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | SUPPLY RENTAL: END OF CAMP BBQ - 8/20/2016 | 061 | CLOSED | 0 | 0 | 47 | 47
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | SUPPLY RENTAL: FOOTBALL BBQ | 061 | CLOSED | 0 | 0 | 52 | 52
PJ0005569 | 16/17 SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CONST_COMP | 2016-06-29 | SUPPLY RENTAL: MUSTANG BBQ - 9/10, 9/24, 10/22, 11/5,11/19 | 061 | CLOSED | 0 | 0 | 445 | 445
PJ0005569 Total | [7 empty] | 0 | 0 | 8135.5272 | 8135.5272
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | AD: BOB'S CRANE | GENERAL | CLOSED | 0 | 0 | 963 | 963
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | AD: HPS MECHANICAL | GENERAL | CLOSED | 0 | 0 | 5989.86 | 5989.86
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | CA: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | GENERAL | CLOSED | 0 | 0 | 1637.244 | 1637.244
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | CPE: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | GENERAL | CLOSED | 0 | 0 | 6734.934 | 6734.934
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | EL: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | GENERAL | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005568 | SR 16/17: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | FLEDDERMAN, JUDE | CLOSED | 2016-06-29 | PL: UTILIDOR LEAK BY BLDGS. 14, 21, 26,187 | GENERAL | CLOSED | 0 | 0 | 35.472 | 35.472
PJ0005568 Total | [7 empty] | 0 | 0 | 15424.938 | 15424.938
PJ0005567 | REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-06-28 | CP: PROJECT CONTINGENCY | 036 | OPEN | 522.94 | 0 | 0 | 0
PJ0005567 | REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-06-28 | EL: ASSESS CONDUIT FOR CONNECTIVITY | 036 | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005567 | REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-06-28 | EL: CONNECT SECURITY GATE POWER TO BACK-UP GENERATOR | 036 | CLOSED | 4377.12 | 0 | 3384.018 | 3384.018
PJ0005567 | REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-06-28 | IN: REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | 036 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005567 | REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-06-28 | PM: REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | 036 | CLOSED | 0 | 0 | 0 | 0
PJ0005567 | REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-06-28 | SM: REWIRE SECURITY GATE TO BACK-UP GENERATOR - BLD 36 | 036 | OPEN | 0 | 0 | 0 | 0
PJ0005567 Total | [7 empty] | 5041.348 | 0 | 3519.09 | 3519.09
PJ0005563 | DM 16/17, SP 16/17: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | AD: JOC 16.038.004 MAINO | GENERAL | CLOSED | 230133.0855 | 0 | 230133.0855 | 230133.0855
PJ0005563 | DM 16/17, SP 16/17: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 23027.44 | 0 | 0 | 0
PJ0005563 | DM 16/17, SP 16/17: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | IN: SP 16/17: ANNUAL ROAD MAINTENANCE - CAMPUS WIDE | GENERAL | CLOSED | 141.288 | 0 | 176.61 | 176.61
PJ0005563 Total | [7 empty] | 253301.8135 | 0 | 230309.6955 | 230309.6955
PJ0005562 | SP 16/17: ANNUAL ROAD RESTRIPING - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | AD: JOC 16.036.005 MAINO | GENERAL | CLOSED | 45411.228 | 0 | 50850.2413 | 50850.2413
PJ0005562 | SP 16/17: ANNUAL ROAD RESTRIPING - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 4555.25 | 0 | 0 | 0
PJ0005562 | SP 16/17: ANNUAL ROAD RESTRIPING - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | IN: SP 16/17: ANNUAL ROAD RESTRIPING - CAMPUS WIDE | GENERAL | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005562 | SP 16/17: ANNUAL ROAD RESTRIPING - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2016-06-15 | PM: SP 16/17: ANNUAL ROAD RESTRIPING - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005562 Total | [7 empty] | 50107.766 | 0 | 50920.8853 | 50920.8853
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | AD: ENGLEKIRK PEER REVIEW | GENERAL | OPEN | 535 | 0 | 535 | 535
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | AD: STATE FIRE MARSHAL FEES | GENERAL | OPEN | 567.1 | 0 | 330.7691 | 330.7691
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 284.39 | 0 | 0 | 0
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | EL: PJ5561 INSTALL SOLAR TREE - UU PLAZA/MUSTANG WAY - DUNN | GENERAL | CLOSED | 128.856 | 0 | 128.856 | 128.856
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | IN: INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | GENERAL | ASSIGNED | 282.576 | 0 | 70.644 | 70.644
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | LA: PJ5561 - MARK IRRIGATION AT PROPOSED INSTALLATION SITE -DUNN | GENERAL | OPEN | 412.2816 | 0 | 120.096 | 120.096
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | PL:PJ5561 INSTALL SOLAR TREE - UU PLAZA | GENERAL | ASSIGNED | 2334.9888 | 0 | 1438.104 | 1438.104
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | PM: INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005561 | INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | DUNN, TRAVIS | DESIGN | 2016-05-20 | SM: INSTALL SOLAR TREE - UU PLAZA / MUSTANG WAY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005561 Total | [7 empty] | 4545.1924 | 0 | 2623.4691 | 2623.4691
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | AD: ITS | 026 | CLOSED | 5350 | 0 | 684.8 | 684.8
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | AD: ITS (FOR OH ONLY CHARGES) | 026 | CLOSED | 0 | 0 | 171.2 | 171.2
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | AD: JOC 16.038.002 MAINO | 026 | CLOSED | 69815.36 | 0 | 54312.7078 | 54312.7078
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | AD: MCKENNA | 026 | CLOSED | 4248.6704 | 0 | 2610.8 | 2610.8
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | AD: MEATHEAD MOVERS | 026 | CLOSED | 4177.9969 | 0 | 4177.9969 | 4177.9969
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | CA: SUPPORT FOR SEWER LINE REPLACEMENT - BLDG 26 | 026 | CLOSED | 978.912 | 0 | 27.81 | 27.81
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 2690.2 | 0 | 0 | 0
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | EL: SUPPORT 26 SEWER REPLACEMENT - BRENNAN | 026 | CLOSED | 921.3204 | 0 | 2757.672 | 2757.672
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | IN: SR 15/16: REPLACE SEWER LINE - BLDG 26 | 026 | CLOSED | 2486.6688 | 0 | 529.83 | 529.83
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | LO: BLDG 26 RM 210A-INSTALL TEMP LOCK-BRENNAN | 026 | CLOSED | 536.1312 | 0 | 556.848 | 556.848
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | MO: MOVE SIT/STAND TABLE FROM BLDG 26 TO 35 - BRENNAN | 026 | CLOSED | 589.8816 | 0 | 36 | 36
PJ0005560 | SR 15/16: REPLACE SEWER LINE - BLDG 26 | BRENNAN, MICHAEL | CLOSED | 2016-05-24 | PL: BLDG 26 REPLACE SEWER - BRENNAN | 026 | CLOSED | 27342.48 | 0 | 10736.688 | 10736.688
PJ0005560 Total | [7 empty] | 119137.6213 | 0 | 76602.3527 | 76602.3527
PJ0005558 | CARPET IN GRAD LOUNGE - BLD 03 RM 308 | MARCHESE, JASON (WILL) | CLOSED | 2016-05-17 | AD: FLOOR CONNECTION | 003 | CLOSED | 5350 | 0 | 5225.88 | 5225.88
PJ0005558 | CARPET IN GRAD LOUNGE - BLD 03 RM 308 | MARCHESE, JASON (WILL) | CLOSED | 2016-05-17 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 267.5 | 0 | 208.6821 | 208.6821
PJ0005558 | CARPET IN GRAD LOUNGE - BLD 03 RM 308 | MARCHESE, JASON (WILL) | CLOSED | 2016-05-17 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 620.63 | 0 | 0 | 0
PJ0005558 | CARPET IN GRAD LOUNGE - BLD 03 RM 308 | MARCHESE, JASON (WILL) | CLOSED | 2016-05-17 | IN: CARPET IN GRAD LOUNGE - BLD 03 RM 308 | 003 | CLOSED | 314.3658 | 0 | 105.966 | 105.966
PJ0005558 Total | [7 empty] | 6552.4958 | 0 | 5540.5281 | 5540.5281
PJ0005557 | EVALUATE STRUCTURAL CONDITION CHUMASH AUDITORIUM - UU65 RM 205 | DILLON, JEFFREY | ESTIMATING | 2016-05-11 | AD: ENGLEKIRK & SABOL | 065 | OPEN | 51895 | 0 | 51895 | 51895
PJ0005557 | EVALUATE STRUCTURAL CONDITION CHUMASH AUDITORIUM - UU65 RM 205 | DILLON, JEFFREY | ESTIMATING | 2016-05-11 | AD: STATE FIRE MARSHAL | 065 | OPEN | 535 | 0 | 0 | 0
PJ0005557 | EVALUATE STRUCTURAL CONDITION CHUMASH AUDITORIUM - UU65 RM 205 | DILLON, JEFFREY | ESTIMATING | 2016-05-11 | CP: PROJECT CONTINGENCY | 065 | OPEN | 5243 | 0 | 0 | 0
PJ0005557 | EVALUATE STRUCTURAL CONDITION CHUMASH AUDITORIUM - UU65 RM 205 | DILLON, JEFFREY | ESTIMATING | 2016-05-11 | PM: EVALUATE CONDITION CHUMASH AUDITORIUM - UU65 RM 205 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005557 | EVALUATE STRUCTURAL CONDITION CHUMASH AUDITORIUM - UU65 RM 205 | DILLON, JEFFREY | ESTIMATING | 2016-05-11 | SM: EVALUATE STRUCTURAL COND. CHUMASH AUDITORIUM - UU65 RM 205 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005557 Total | [7 empty] | 57673 | 0 | 51895 | 51895
PJ0005555 | INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | LAMPMAN, GREG | CLOSED | 2016-03-09 | AD: JOC 16.038.015 MAINO | 170B | CLOSED | 9544.3144 | 0 | 9544.3144 | 9544.3144
PJ0005555 | INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | LAMPMAN, GREG | CLOSED | 2016-03-09 | AD: STATE FIRE MARSHAL | 170B | CLOSED | 0 | 0 | 106.1761 | 106.1761
PJ0005555 | INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | LAMPMAN, GREG | CLOSED | 2016-03-09 | CP: PROJECT CONTINGENCY | 170B | CLOSED | 1026.71 | 0 | 0 | 0
PJ0005555 | INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | LAMPMAN, GREG | CLOSED | 2016-03-09 | IN: INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | 170B | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005555 | INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | LAMPMAN, GREG | CLOSED | 2016-03-09 | LA: | 170B | CLOSED | 440.256 | 0 | 100.08 | 100.08
PJ0005555 | INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | LAMPMAN, GREG | CLOSED | 2016-03-09 | PM: INSTALL PAVERS TO EXTEND BBQ PATIO - 170B CERRO CABRILLO | 170B | CLOSED | 0 | 0 | 0 | 0
PJ0005555 Total | [7 empty] | 11293.8564 | 0 | 9891.8585 | 9891.8585
PJ0005554 | RETROFIT FENCE ACCESS UNDER ALL STAIRWELLS - 170 CERRO VISTA | LAMPMAN, GREG | CLOSED | 2016-03-09 | AD: JOC 16.038.014 MAINO | 170 | CLOSED | 26090.1631 | 0 | 26090.1631 | 26090.1631
PJ0005554 | RETROFIT FENCE ACCESS UNDER ALL STAIRWELLS - 170 CERRO VISTA | LAMPMAN, GREG | CLOSED | 2016-03-09 | AD: STATE FIRE MARSHAL FEES | 170 | CLOSED | 0 | 0 | 106.1761 | 106.1761
PJ0005554 | RETROFIT FENCE ACCESS UNDER ALL STAIRWELLS - 170 CERRO VISTA | LAMPMAN, GREG | CLOSED | 2016-03-09 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 2735.78 | 0 | 0 | 0
PJ0005554 | RETROFIT FENCE ACCESS UNDER ALL STAIRWELLS - 170 CERRO VISTA | LAMPMAN, GREG | CLOSED | 2016-03-09 | IN: RETROFIT FENCE ACCESS UNDER STAIRWELL - 170 CERRO VISTA | 170 | CLOSED | 423.864 | 0 | 247.254 | 247.254
PJ0005554 | RETROFIT FENCE ACCESS UNDER ALL STAIRWELLS - 170 CERRO VISTA | LAMPMAN, GREG | CLOSED | 2016-03-09 | LO: PROVIDE 13 PAD LOCKS | 170 | CLOSED | 843.696 | 0 | 392.04 | 392.04
PJ0005554 | RETROFIT FENCE ACCESS UNDER ALL STAIRWELLS - 170 CERRO VISTA | LAMPMAN, GREG | CLOSED | 2016-03-09 | PM: RETROFIT FENCE ACCESS UNDER STAIRWELL - 170 CERRO VISTA | 170 | CLOSED | 0 | 0 | 0 | 0
PJ0005554 Total | [7 empty] | 30093.5031 | 0 | 26835.6332 | 26835.6332
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | AD: BKM FURNITURE | 001 | OPEN | 3210 | 0 | 2926.3216 | 2926.3216
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | AD: DRYWALL HYDRATION STATION | 001 | OPEN | 1070 | 0 | 0 | 0
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | AD: STATE FIRE MARSHAL | 001 | OPEN | 278.2 | 0 | 475.7862 | 475.7862
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | AD: THE SIGN PLACE | 001 | OPEN | 17101.1894 | 519.1533 | 15786.0631 | 16305.2164
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | CA: HANDYMAN WORK | 001 | CLOSED | 6418.2 | 0 | 4996.506 | 4996.506
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | CP: PROJECT CONTINGENCY | 001 | OPEN | 656.13 | 0 | 0 | 0
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | CU: | 001 | OPEN | 368.412 | 0 | 0 | 0
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | EH&S: | 001 | OPEN | 128.736 | 0 | 0 | 0
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | EL: VARIOUS ELECTRICAL | 001 | OPEN | 3146.124 | 0 | 2101.95 | 2101.95
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | IN: INTERIOR SIGNAGE - ADMIN 01 | 001 | ASSIGNED | 282.576 | 0 | 70.644 | 70.644
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | PA: ACCENT PAINT AT WALLS | 001 | CLOSED | 7409.88 | 0 | 588.126 | 588.126
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | PL: INSTALL NEW HYDRATION STATION | 001 | COMPLETE | 3213.42 | 0 | 2966.502 | 2966.502
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | PM: INTERIOR SIGNAGE - ADMIN 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005550 | INTERIOR SIGNAGE - ADMIN 01 | NORTON, DAVE | IN_CONSTR | 2016-05-05 | SM: INTERIOR SIGNAGE - ADMIN 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005550 Total | [7 empty] | 43282.8674 | 519.1533 | 29911.8989 | 30431.0522
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: BKM | GENERAL | CLOSED | 306651.6103 | 0 | 300340.4828 | 300340.4828
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: CAME SECURITY | GENERAL | CLOSED | 0 | 0 | 206.51 | 206.51
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: FLOOR CONNECTION | GENERAL | CLOSED | 90515.3018 | 0 | 90515.3125 | 90515.3125
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: ITS | GENERAL | CLOSED | 4942.33 | 0 | 4943.079 | 4943.079
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: JOC 16.039.002 NEWTON | GENERAL | CLOSED | 188407.8149 | 0 | 189137.9294 | 189137.9294
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: MCKENNA ENVIRONMENTAL | GENERAL | CLOSED | 10286.98 | 0 | 9769.1 | 9769.1
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: MEATHEAD MOVERS | GENERAL | CLOSED | 941.6 | 0 | 941.6 | 941.6
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: NEWTON LVPW | GENERAL | CLOSED | 642 | 0 | 642 | 642
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: P-CARD PURCHASE (BULLETIN BOARDS) | GENERAL | CLOSED | 516.275 | 0 | 554.7094 | 554.7094
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: STATE FIRE MARSHAL FEES | GENERAL | CLOSED | 278.2 | 0 | 643.177 | 643.177
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | AD: THE SIGN PLACE | GENERAL | CLOSED | 13438.6543 | 0 | 13438.6436 | 13438.6436
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | CA: CONTRACTOR SUPPORTM FOR JESPERSEN & HERON OFFICE RENOVATIONS | GENERAL | CLOSED | 7918.2 | 0 | 10053.89 | 10053.89
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 3246.21 | 0 | 0 | 0
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | CU: CLEAN ROOMS | GENERAL | CLOSED | 736.824 | 0 | 370.7443 | 370.7443
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | EL: CONTRACTOR SUPPORT | GENERAL | CLOSED | 1417.416 | 0 | 3115.11 | 3115.11
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | IN: SP 15/16: OFFICE RENOVS JESPERSEN & HERON - BLDGS 116 & 117 | GENERAL | CLOSED | 918.372 | 0 | 671.118 | 671.118
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | LO: LOCK CHANGE - JESPERSON HALL | GENERAL | CLOSED | 3173.115 | 0 | 1623.662 | 1623.662
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | MO: MOVE FURNITURE BLD#116,117 | GENERAL | CLOSED | 9438.4408 | 0 | 2241.096 | 2241.096
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | PA: PAINT TOUCH UP AND ACCENT PAINT - HERON & JESPERSON | GENERAL | CLOSED | 11496.4271 | 0 | 15964.95 | 15964.95
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | PM: SP 15/16: OFFICE RENOVATIONS JESPERSEN&HERON-BLDGS 116 & 117 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005549 | SP 16/17: OFFICE RENOVATIONS JESPERSEN & HERON - BLDGS 116 & 117 | NORTON, DAVE | CONST_COMP | 2016-05-04 | SM: SP 16/17: OFF. RENOVATIONS JESPERSEN & HERON - BLDS 116&117 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005549 Total | [7 empty] | 654965.7711 | 0 | 645173.114 | 645173.114
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | AD: FLOOR CONNECTION | 197 | CLOSED | 12460.15 | 0 | 12460.15 | 12460.15
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | AD: STATE FIRE MARSHAL | 197 | CLOSED | 214 | 0 | 495.4742 | 495.4742
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | CP: PROJECT CONTINGENCY | 197 | OPEN | 1111.82 | 0 | 0 | 0
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | IN: REMOVE CARPET - BLD 197 RM 104 | 197 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | LO: INSTALL ORANGE CORE | 197 | CLOSED | 182.772 | 0 | 60.924 | 60.924
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | MO: BLDG. 197, ROOM 104- MOVE FURNITURE TO HALLWAY | 197 | CLOSED | 201.096 | 0 | 162 | 162
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | PM: REMOVE CARPET - BLD 197 RM 104 | 197 | CLOSED | 0 | 0 | 0 | 0
PJ0005547 | REMOVE CARPET - BLD 197 RM 104 | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-04-13 | SM: REMOVE CARPET - BLD 197 RM 104 | 197 | OPEN | 0 | 0 | 0 | 0
PJ0005547 Total | [7 empty] | 14240.482 | 0 | 13249.1922 | 13249.1922
PJ0005546 | INSTALL WEB CAM FOR DEMO & CONSTRUCTION OF NEW BUILDING 112 | MCNALLY, CURTIS J. | CLOSED | 2016-04-01 | AD: ITS | 112 | CLOSED | 535 | 0 | 85.6 | 85.6
PJ0005546 | INSTALL WEB CAM FOR DEMO & CONSTRUCTION OF NEW BUILDING 112 | MCNALLY, CURTIS J. | CLOSED | 2016-04-01 | AD: STATE FIRE MARSHAL FEES | 112 | CLOSED | 0 | 0 | 115.4637 | 115.4637
PJ0005546 | INSTALL WEB CAM FOR DEMO & CONSTRUCTION OF NEW BUILDING 112 | MCNALLY, CURTIS J. | CLOSED | 2016-04-01 | AD: WESCO ELECTRIC | 112 | CLOSED | 4280 | 0 | 1828.8654 | 1828.8654
PJ0005546 | INSTALL WEB CAM FOR DEMO & CONSTRUCTION OF NEW BUILDING 112 | MCNALLY, CURTIS J. | CLOSED | 2016-04-01 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 495.63 | 0 | 0 | 0
PJ0005546 | INSTALL WEB CAM FOR DEMO & CONSTRUCTION OF NEW BUILDING 112 | MCNALLY, CURTIS J. | CLOSED | 2016-04-01 | IN: INSTALL WEB CAM FOR DEMO + CONSTRUCTION OF NEW BUILDING 112 | 112 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005546 Total | [7 empty] | 5451.918 | 0 | 2171.2171 | 2171.2171
PJ0005544 | SUPPORT: EVENING OF GREEN & GOLD - MAY 6, 2016 | POPHAM, DONALD J. | CLOSED | 2016-04-25 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005544 | SUPPORT: EVENING OF GREEN & GOLD - MAY 6, 2016 | POPHAM, DONALD J. | CLOSED | 2016-04-25 | CU: SUPPORT FOR E.G.G. (5/7/2016) | 043 | CLOSED | 0 | 0 | 149.952 | 149.952
PJ0005544 | SUPPORT: EVENING OF GREEN & GOLD - MAY 6, 2016 | POPHAM, DONALD J. | CLOSED | 2016-04-25 | EL: SUPPORT FOR EVENING OF GREEN & GOLD - MAY 6 | 043 | CLOSED | 0 | 0 | 1549.164 | 1549.164
PJ0005544 | SUPPORT: EVENING OF GREEN & GOLD - MAY 6, 2016 | POPHAM, DONALD J. | CLOSED | 2016-04-25 | MC: MOVE THE EVENT CARPETING FROM BLDG 81 TO REC CTR | 043 | CLOSED | 0 | 0 | 66 | 66
PJ0005544 Total | [7 empty] | 0 | 0 | 1765.116 | 1765.116
PJ0005542 | INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP ROAD | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-03-23 | AD: GARCIA AND SONS | 083 | CLOSED | 18045.55 | 0 | 18045.55 | 18045.55
PJ0005542 | INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP ROAD | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-03-23 | CP: PROJECT CONTINGENCY | 083 | OPEN | 1825.13 | 0 | 0 | 0
PJ0005542 | INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP ROAD | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-03-23 | IN: INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP RD | 083 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005542 | INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP ROAD | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-03-23 | PM: INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP RD | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0005542 | INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP ROAD | KUENTZEL, DOUGLAS A. | CONST_COMP | 2016-03-23 | SM: INSTALL ASPHALT CURB BY TECHNOLOGY PARK (83) - MT BISHOP RD | 083 | OPEN | 0 | 0 | 0 | 0
PJ0005542 Total | [7 empty] | 20011.968 | 0 | 18116.194 | 18116.194
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | AD: ITS ACTIVATE PORTS BLDG. 38, ROOM 144 | 038 | CLOSED | 321 | 0 | 297.6205 | 297.6205
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | AD: STATE FIRE MARSHAL FEES | 038 | CLOSED | 0 | 0 | 125.1365 | 125.1365
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | CA:BLDG. 38 RM 144 REMOVE WHITEBOARD- INSTALL BRACKET | 038 | CLOSED | 334.728 | 0 | 30.594 | 30.594
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 619.57 | 0 | 0 | 0
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | EL:BLDG. 38, RM 144 INSTALL NEW ELECTRICAL AND IT PATHWAY | 038 | CLOSED | 4046.124 | 0 | 4657.542 | 4657.542
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | IN: CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | 038 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | PA:BLDG 38, RM 144 PAINT ACCENT WALL | 038 | CLOSED | 1421.976 | 0 | 496.386 | 496.386
PJ0005541 | CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | MOLLAN, CHERYL L. | CLOSED | 2016-03-25 | PM: CONFERENCE ROOM UPGRADE - BLD 38 RM 144 | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0005541 Total | [7 empty] | 6814.042 | 0 | 5677.923 | 5677.923
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | AD: MAINO | 038 | CLOSED | 2140 | 0 | 2140 | 2140
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | AD: STATE FIRE MARSHALL FEES | 038 | CLOSED | 0 | 0 | 57.1701 | 57.1701
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | CA:CHILD CENTER GATE REPLACE | 038 | CLOSED | 1208.7888 | 0 | 266.184 | 266.184
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | CP: PROJECT CONTINGENCY | 038 | OPEN | 591.79 | 0 | 0 | 0
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | IN: REPLACE ENTRANCE GATE - BLD 38 RM 125 | 038 | CLOSED | 141.288 | 0 | 0 | 0
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | LO:NEW PUSHBAR AND KEYPAD LOCK | 038 | CLOSED | 2320.9723 | 0 | 2226.494 | 2226.494
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | PM: REPLACE ENTRANCE GATE - BLD 38 RM 125 | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0005540 | REPLACE ENTRANCE GATE - BLD 38 RM 125 | DILLON, JEFFREY | CONST_COMP | 2016-03-17 | SM: REPLACE ENTRANCE GATE - BLD 38 RM 125 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0005540 Total | [7 empty] | 6402.8391 | 0 | 4689.8481 | 4689.8481
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (DEPT) BKM FURNITURE | 042 | CLOSED | 81979.1735 | 0 | 73833.2849 | 73833.2849
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (DEPT) FPCP CONTRACT OVERSIGHT FEE - FLOORING | 042 | CLOSED | 535 | 0 | 535 | 535
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (DEPT) FPCP DESIGN FEE | 042 | CLOSED | 535 | 0 | 535 | 535
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (DEPT) ITS | 042 | CLOSED | 5992 | 0 | 6877.746 | 6877.746
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (DEPT) MCKENNA | 042 | CLOSED | 3745 | 0 | 3006.7 | 3006.7
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (SPLIT 38/62) JOC 16.039.010 NEWTON | 042 | CLOSED | 41112.9524 | 0 | 40535.987 | 40535.987
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (SPLIT FUNDING) GOSS ENGINEERING | 042 | CLOSED | 2033 | 0 | 2033 | 2033
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | AD: (SPLIT FUNDING) STATE FIRE MARSHAL FEES | 042 | CLOSED | 278.2 | 0 | 262.7171 | 262.7171
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | CP: (DEPT) PROJECT CONTINGENCY | 042 | CLOSED | 14607.54 | 0 | 0 | 0
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | CP: (SPLIT FUNDING) PROJECT CONTINGENCY | 042 | OPEN | 281.38 | 0 | 0 | 0
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | EL: (DEPT) ELECTRICAL FOR REMODEL | 042 | CLOSED | 7655.7312 | 0 | 9261.33 | 9261.33
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | IN: (SPLIT 13/87)) SR 16/17: FURN INSTALL - MOTT 42 RM 201 | 042 | CLOSED | 529.83 | 0 | 105.966 | 105.966
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | MO: (DEPT) MOVE OLD FURNITURE OUT | 042 | CLOSED | 589.8816 | 0 | 108 | 108
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | PA: (DEPT) PAINT WALL WHERE WIRE MOLDING WAS REMOVED. 42-201 | 042 | CLOSED | 1481.976 | 0 | 742.896 | 742.896
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | PM: SR 16/17: OFFICE FURNITURE INSTALL - MOTT 42 RM 201 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005539 | SR 16/17: OFFICE FURNITURE INSTALL & HVAC UPGADE- MOTT 42 RM 201 | NORTON, DAVE | CONST_COMP | 2016-04-05 | SM: SR 16/17: OFF. FURNITURE INSTL & HVAC UPGADE- MOTT 42 RM 201 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005539 Total | [7 empty] | 161356.6647 | 0 | 137837.627 | 137837.627
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | AD: GREENVALE TREE SERVICE | 114 | CLOSED | 0 | 0 | 0 | 0
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | AD: MAINO - LVPW | 114 | CLOSED | 0 | 0 | 18382.6 | 18382.6
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | ANTS: ALARMS PROGRAMMING FOR YOSEMITE FIRE PROTECTION PROJECT | 114 | CLOSED | 0 | 0 | 203.328 | 203.328
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | CP: PROJECT CONTINGENCY | 114 | OPEN | 10000 | 0 | 0 | 0
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | EL: LOCATE UTILITIES & DISCONNECT CIRCUITS - YOS FIRE PROTECTION | 114 | CLOSED | 0 | 0 | 4095.324 | 4095.324
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | EL: SUPPORT FOR YOSEMITE FIRE PROTECTION PHASE I | 114 | CLOSED | 0 | 0 | 770.928 | 770.928
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | ES: MARK HYDRONIC PIPING FOR YOSEMITE FIRE PROTECTION PROJECT | 114 | CLOSED | 0 | 0 | 561.414 | 561.414
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | ES: SUPPORT FOR YOSEMITE FIRE SPRINKLER INSTALLATION | 114 | CLOSED | 0 | 0 | 525.312 | 525.312
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | LA: LOCATE UTILITIES FOR YOSEMITE FIRE PROTECTION BEFORE 5/1/17 | 114 | CLOSED | 0 | 0 | 790.632 | 790.632
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | LA: SUPPORT FOR YOSEMITE FIRE PROTECTION PROJECT | 114 | CLOSED | 0 | 0 | 380.304 | 380.304
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | LO: CHANGE LOCKS TO ORANGE CORES FOR YOS FIRE PROTECTION PROJECT | 114 | CLOSED | 0 | 0 | 852.936 | 852.936
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | LO: ORANGE CORES FOR YOSEMITE FIRE PROTECTIOIN PROJECT - TWR 0-5 | 114 | CLOSED | 0 | 0 | 609.24 | 609.24
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | PA: SUPPORT FOR YOSEMITE FIRE PROTECTION PHASE I | 114 | CLOSED | 0 | 0 | 105.648 | 105.648
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | PL: LOCATE UTILITIES FOR YOSEMITE FIRE PROTECTION BEFORE 5/1/17 | 114 | CLOSED | 0 | 0 | 12672.7212 | 12672.7212
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | PL: SUPPORT FOR YOSEMITE FIRE PROTECTION PHASE I | 114 | CLOSED | 0 | 0 | 5120.5356 | 5120.5356
PJ0005538 | MJ: IN-HOUSE SUPPORT: YOSEMITE FIRE PROTECTION | PRINCI, COLIN | CONST_COMP | 2016-03-29 | SM: MJ: FACILITIES SUPPORT FOR YOSEMITE FIRE PROTECTION | 114 | OPEN | 0 | 0 | 0 | 0
PJ0005538 Total | [7 empty] | 10000 | 0 | 45070.9228 | 45070.9228
PJ0005536 | KECK LAB FURNITURE REPLACEMENT - BLD 07 RM 2 | POPHAM, DONALD J. | CONST_COMP | 2016-03-21 | AD: TRI COUNTIES OFFICE FURNITURE | 007 | CLOSED | 64607.1885 | 0 | 66122.9933 | 66122.9933
PJ0005536 | KECK LAB FURNITURE REPLACEMENT - BLD 07 RM 2 | POPHAM, DONALD J. | CONST_COMP | 2016-03-21 | CP: PROJECT CONTINGENCY | 007 | OPEN | 6058.82 | 0 | 0 | 0
PJ0005536 | KECK LAB FURNITURE REPLACEMENT - BLD 07 RM 2 | POPHAM, DONALD J. | CONST_COMP | 2016-03-21 | SM: KECK LAB FURNITURE REPLACEMENT - BLD 07 RM 2 | 007 | OPEN | 0 | 0 | 0 | 0
PJ0005536 Total | [7 empty] | 70666.0085 | 0 | 66122.9933 | 66122.9933
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | AD: (DEPT FUNDING) A-TOWN | 042 | CLOSED | 5322.394 | 0 | 5322.394 | 5322.394
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | AD: (DEPT FUNDING) GRAND PERFORMANCE | 042 | CLOSED | 5739.4693 | 0 | 5739.3516 | 5739.3516
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | AD: (DEPT FUNDING) MTI - WIRELESS CONTROLS & THEATRE LIGHTING | 042 | CLOSED | 39135.25 | 0 | 39135.25 | 39135.25
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | AD: JMPE | 042 | CLOSED | 8346 | 0 | 8346 | 8346
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | AD: MORELAND THOMPSON - GYM LIGHTING | 042 | CLOSED | 126507.598 | 0 | 126507.598 | 126507.598
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | AD: STATE FIRE MARSHAL FEES | 042 | CLOSED | 535 | 0 | 0 | 0
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | CP: (DEPT FUNDING) PROJECT CONTINGENCY | 042 | CLOSED | 21.37 | 0 | 0 | 0
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | CP: PROJECT CONTINGENCY | 042 | OPEN | 1352.99 | 0 | 0 | 0
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | EL:MOTT GYM LIGHTING-SUPPORT- J. DILLON | 042 | CLOSED | 3893.0904 | 0 | 3952.511 | 3952.511
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | IN: SR 16/17: LED RETROFIT - MOTT GYM 42 | 042 | CLOSED | 423.864 | 0 | 388.542 | 388.542
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | LO:MOTT GYM LIGHTING REPLACE- J. DILLON | 042 | CLOSED | 134.0328 | 0 | 30.462 | 30.462
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | PA:MOTT GYM LIGHTING REPLACE- J. DILLON | 042 | CLOSED | 1389.5808 | 0 | 183.816 | 183.816
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | PM: SR 16/17: LED RETROFIT - MOTT GYM 42 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005535 | SR 16/17: LED RETROFIT - MOTT GYM 42 | DILLON, JEFFREY | CONST_COMP | 2016-03-18 | SM: SR 16/17: LED RETROFIT - MOTT GYM 42 | 042 | OPEN | 0 | 0 | 0 | 0
PJ0005535 Total | [7 empty] | 192800.6393 | 0 | 189605.9246 | 189605.9246
PJ0005531 | CLEAN EXTERIOR & INTERIOR WINDOWS - BLD 03 | CANTU, MONICA M. | CLOSED | 2016-03-11 | AD: COASTAL JANITORIAL | 003 | CLOSED | 22652.97 | 0 | 22652.97 | 22652.97
PJ0005531 | CLEAN EXTERIOR & INTERIOR WINDOWS - BLD 03 | CANTU, MONICA M. | CLOSED | 2016-03-11 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 2412.67 | 0 | 0 | 0
PJ0005531 | CLEAN EXTERIOR & INTERIOR WINDOWS - BLD 03 | CANTU, MONICA M. | CLOSED | 2016-03-11 | CU: INTERIOR WINDOWS ON ALL FLOORS OF BUSINESS BLD - 03 | 003 | CLOSED | 1473.648 | 0 | 1363.2881 | 1363.2881
PJ0005531 Total | [7 empty] | 26539.288 | 0 | 24016.2581 | 24016.2581
PJ0005530 | ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF (BY 4/14/2016) | BRENNAN, MICHAEL | CLOSED | 2016-02-26 | AD: RRM DESIGN GROUP | 034 | CLOSED | 642 | 0 | 642 | 642
PJ0005530 | ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF (BY 4/14/2016) | BRENNAN, MICHAEL | CLOSED | 2016-02-26 | CA: INSTALL RAPPELLING ANCHORS, DEXTER | 034 | CLOSED | 735.018 | 0 | 2695.752 | 2695.752
PJ0005530 | ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF (BY 4/14/2016) | BRENNAN, MICHAEL | CLOSED | 2016-02-26 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0.15 | 0 | 0 | 0
PJ0005530 | ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF (BY 4/14/2016) | BRENNAN, MICHAEL | CLOSED | 2016-02-26 | IN: ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF (BY 4/14/2016) | 034 | CLOSED | 70.644 | 0 | 105.966 | 105.966
PJ0005530 | ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF (BY 4/14/2016) | BRENNAN, MICHAEL | CLOSED | 2016-02-26 | PM: ANCHOR POINT/FALL ARREST SYSTEM - BLD 34 ROOF | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0005530 Total | [7 empty] | 1447.812 | 0 | 3443.718 | 3443.718
PJ0005529 | SR 15/16: DEMO EXTERIOR SUN SHADES - HC 27 | MARCHESE, JASON (WILL) | CLOSED | 2016-03-01 | AD: COASTAL JANITORIAL | 027 | CLOSED | 1047.3588 | 0 | 615.25 | 615.25
PJ0005529 | SR 15/16: DEMO EXTERIOR SUN SHADES - HC 27 | MARCHESE, JASON (WILL) | CLOSED | 2016-03-01 | AD: JOC 16.037.002 MAINO | 027 | CLOSED | 77140.3767 | 0 | 77140.3767 | 77140.3767
PJ0005529 | SR 15/16: DEMO EXTERIOR SUN SHADES - HC 27 | MARCHESE, JASON (WILL) | CLOSED | 2016-03-01 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 6443.32 | 0 | 0 | 0
PJ0005529 | SR 15/16: DEMO EXTERIOR SUN SHADES - HC 27 | MARCHESE, JASON (WILL) | CLOSED | 2016-03-01 | IN: SR 15/16: DEMO EXTERIOR SUN SHADES - HC 27 | 027 | CLOSED | 621.6672 | 0 | 565.152 | 565.152
PJ0005529 | SR 15/16: DEMO EXTERIOR SUN SHADES - HC 27 | MARCHESE, JASON (WILL) | CLOSED | 2016-03-01 | LA: REPAIR LANDSCAPING AROUND CONSTRUCTION AREA | 027 | CLOSED | 320.256 | 0 | 80.064 | 80.064
PJ0005529 Total | [7 empty] | 85572.9787 | 0 | 78400.8427 | 78400.8427
PJ0005528 | PURCHASE AND INSTALL DONOR BENCH - POLY CANYON ROAD | POPHAM, DONALD J. | CLOSED | 2016-02-29 | AD: QUIKRETE BENCH PURCHASE (NO OVERHEAD) | GENERAL | CLOSED | 1358.8 | 0 | 1358.8 | 1358.8
PJ0005528 | PURCHASE AND INSTALL DONOR BENCH - POLY CANYON ROAD | POPHAM, DONALD J. | CLOSED | 2016-02-29 | CA: INSTALL PLAQUE FOR BENCH BY 3/9 | GENERAL | CLOSED | 124.0326 | 0 | 139.05 | 139.05
PJ0005528 | PURCHASE AND INSTALL DONOR BENCH - POLY CANYON ROAD | POPHAM, DONALD J. | CLOSED | 2016-02-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 81.61 | 0 | 0 | 0
PJ0005528 | PURCHASE AND INSTALL DONOR BENCH - POLY CANYON ROAD | POPHAM, DONALD J. | CLOSED | 2016-02-29 | IN: PURCHASE AND INSTALL DONOR BENCH - POLY CANYON ROAD | GENERAL | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005528 | PURCHASE AND INSTALL DONOR BENCH - POLY CANYON ROAD | POPHAM, DONALD J. | CLOSED | 2016-02-29 | LA: CLEAR AREA AND INSTALL BECH - POLY CYN ROD. | GENERAL | CLOSED | 356.2848 | 0 | 865.332 | 865.332
PJ0005528 Total | [7 empty] | 1991.3714 | 0 | 2433.826 | 2433.826
PJ0005527 | MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2016-02-18 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 535 | 0 | 55.2227 | 55.2227
PJ0005527 | MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2016-02-18 | CA:MOVE PROJECTOR LOCATION BUSINESS BLDG 3, ROOM 113 | 003 | CLOSED | 1580.094 | 0 | 513.504 | 513.504
PJ0005527 | MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2016-02-18 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 535.58 | 0 | 0 | 0
PJ0005527 | MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2016-02-18 | EL:RELOCATE ELECTRICAL OUTLET FOR NEW LOCATION OF PROJECTOR | 003 | CLOSED | 1150.4496 | 0 | 407.688 | 407.688
PJ0005527 | MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2016-02-18 | IN: MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | 003 | CLOSED | 70.644 | 0 | 105.966 | 105.966
PJ0005527 | MOVE PROJECTOR MOUNT LOCATION IN CEILING - BLD 3 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2016-02-18 | PA:PAINT METAL POLE HANGING FROM CEILING, BLDG 3, ROOM 113 | 003 | CLOSED | 1601.976 | 0 | 123.816 | 123.816
PJ0005527 Total | [7 empty] | 5473.7436 | 0 | 1206.1967 | 1206.1967
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | CA:MAJ CAP PROJECT SUPPORT | 060 | CLOSED | 0 | 0 | 0 | 0
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | CP: PROJECT CONTINGENCY | 060 | OPEN | 0 | 0 | 0 | 0
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | CPE:MAJ CAP PROJECT SUPPORT | 060 | OPEN | 0 | 0 | 328.32 | 328.32
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | EL: MAJ CAP PROJECT SUPPORT | 060 | LONG_TERM | 0 | 0 | 3938.298 | 3938.298
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | ES:MAJ CAP PROJECT SUPPORT | 060 | CLOSED | 0 | 0 | 1443.996 | 1443.996
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | LO: CHANGE LOCK CORES TO CONSTRUCTION SETS | 060 | PEND_SCHED | 121.848 | 0 | 60.924 | 60.924
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | MO: RELOCATE ITEMS IN ELECTRICAL ROOM 10 TO BASEMENT OFFICE | 060 | CLOSED | 0 | 0 | 84 | 84
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | PA: REPAINT OFFICE - CRANDALL 103 | 060 | CLOSED | 0 | 0 | 742.896 | 742.896
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | PL:MAJ CAP PROJECT SUPPORT | 060 | OPEN | 0 | 0 | 5964.8003 | 5964.8003
PJ0005526 | MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | MCNALLY, CURTIS J. | IN_CONSTR | 2016-02-29 | SM: MJ: SUPPORT FOR CRANDALL GYM STRUCTURAL RETROFIT | 060 | OPEN | 0 | 0 | 0 | 0
PJ0005526 Total | [7 empty] | 121.848 | 0 | 12563.2343 | 12563.2343
PJ0005525 | SR 15/16: ENG WEST STORM DRAIN REPAIR - BLD 21 | GONZALES, ALBERT | CLOSED | 2016-02-23 | AD: MAINO | 021 | CLOSED | 17958.88 | 0 | 17958.88 | 17958.88
PJ0005525 | SR 15/16: ENG WEST STORM DRAIN REPAIR - BLD 21 | GONZALES, ALBERT | CLOSED | 2016-02-23 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 2121.75 | 0 | 0 | 0
PJ0005525 | SR 15/16: ENG WEST STORM DRAIN REPAIR - BLD 21 | GONZALES, ALBERT | CLOSED | 2016-02-23 | PL: ENG WEST STORM DRAIN REPAIR - BLD 21 | 021 | CLOSED | 3257.472 | 0 | 490.116 | 490.116
PJ0005525 Total | [7 empty] | 23338.102 | 0 | 18448.996 | 18448.996
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: AVIARY MGMT PROFESSIONALS | 035 | CLOSED | 0 | 0 | 459.351 | 459.351
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: BKM FURNITURE | 035 | CLOSED | 239495.9386 | 0 | 239495.9279 | 239495.9279
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: COASTAL DEMO | 035 | CLOSED | 2140 | 0 | 2086.5 | 2086.5
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: COASTAL ROLL-OFF | 035 | CLOSED | 400 | 0 | 375.1099 | 375.1099
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: FLOOR CONNECTION | 035 | CLOSED | 65707.6621 | 0 | 65707.6621 | 65707.6621
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: JL FASULO | 035 | CLOSED | 3272.06 | 0 | 3591.99 | 3591.99
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: JOC 16.037.013 MAINO | 035 | CLOSED | 50667.389 | 0 | 49597.389 | 49597.389
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: KI FURNITURE | 035 | CLOSED | 102101.4223 | 0 | 101705.6828 | 101705.6828
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: MCKENNA ENVIRONMENTAL | 035 | CLOSED | 535 | 0 | 535 | 535
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: REPUBLIC ELEVATOR | 035 | CLOSED | 1318.24 | 0 | 988.68 | 988.68
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 572.45 | 0 | 612.3503 | 612.3503
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | AD: THOMA ELECTRIC | 035 | CLOSED | 898.8 | 0 | 898.8 | 898.8
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | CA: SUPPORT AND WALL FURRING | 035 | CLOSED | 10465.7358 | 0 | 8929.554 | 8929.554
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 10259.57 | 0 | 0 | 0
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | CU: CLEAN RM. 111, 1ST FL. HALL, AND STOREFRONTS - LIBRARY | 035 | CLOSED | 334.92 | 0 | 388.368 | 388.368
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | EL: SUPPORT & MISC. RELOCATIONS AND ADDITIONS | 035 | CLOSED | 5275.153 | 0 | 4556.616 | 4556.616
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | IN: SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | 035 | CLOSED | 353.22 | 0 | 317.898 | 317.898
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | LO: Provide Material for Elevator Switching | 035 | CLOSED | 661.1118 | 0 | 834.342 | 834.342
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | MO: Furniture Salvage and Moving for Carpet Replacement | 035 | CLOSED | 447.4386 | 0 | 72 | 72
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | PA: PAINT T/U'S, ACCENT WALLS, ETC. 111, 114 &B, 3RD FLOOR | 035 | CLOSED | 2307.1081 | 0 | 3018.402 | 3018.402
PJ0005523 | SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-17 | PM: SP 15/16: SSF - EXPAND 24 HOUR SPACE - BLD 35 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005523 Total | [7 empty] | 497213.2193 | 0 | 484171.623 | 484171.623
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | AD: CAL POLY BUILDING PERMIT FEES | RESIDENCE | CLOSED | 500 | 0 | 500 | 500
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | AD: CAL POLY FAC PLAN REVIEW FEES | RESIDENCE | CLOSED | 500 | 0 | 500 | 500
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | AD: ENGLEKIRK & SABOL PEER REIVEW | RESIDENCE | CLOSED | 500 | 0 | 500 | 500
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | AD: ON-TRAC | RESIDENCE | CLOSED | 0 | 0 | 30.5485 | 30.5485
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 502.9 | 0 | 207.8154 | 207.8154
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 154.3 | 0 | 0 | 0
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | EL:PROVIDE CONTRACTOR SUPPORT FOR AT&T AT KLAMMATH PARKING LOT | RESIDENCE | CLOSED | 951.1212 | 0 | 64.428 | 64.428
PJ0005521 | AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | MOLLAN, CHERYL L. | CLOSED | 2016-02-23 | IN: AT&T CELL SITE - KLAMATH & CERRO VISTA CIRCLE | RESIDENCE | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005521 Total | [7 empty] | 3249.6092 | 0 | 1908.7579 | 1908.7579
PJ0005520 | MJ: IN-HOUSE SUPPORT TO INSTALL SYNTHETIC TURF AT I-FIELD F-04 | PRINCI, COLIN | DESIGN | 2016-02-16 | CP: PROJECT CONTINGENCY | F-04 | OPEN | 0 | 0 | 0 | 0
PJ0005520 | MJ: IN-HOUSE SUPPORT TO INSTALL SYNTHETIC TURF AT I-FIELD F-04 | PRINCI, COLIN | DESIGN | 2016-02-16 | SM: MJ: IN-HOUSE SUPPORT TO INSTL SYNTHETIC TURF AT I-FIELD F-04 | F-04 | OPEN | 0 | 0 | 0 | 0
PJ0005520 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005519 | SR15/16: REPAIR LEAK UNDER STAGE - BLD 44 RM 107 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-11 | AD: HPS MECHANICAL | 044 | CLOSED | 12840 | 0 | 10682.88 | 10682.88
PJ0005519 | SR15/16: REPAIR LEAK UNDER STAGE - BLD 44 RM 107 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-11 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 1710.02 | 0 | 0 | 0
PJ0005519 | SR15/16: REPAIR LEAK UNDER STAGE - BLD 44 RM 107 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-11 | CPE: Isolate Grand Avenue Run Out & Fill system once complete | 044 | CLOSED | 866.7648 | 0 | 164.16 | 164.16
PJ0005519 | SR15/16: REPAIR LEAK UNDER STAGE - BLD 44 RM 107 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-11 | ES: SUPPORT FOR UTILIDOR GASKET REPLACEMENT | 044 | CLOSED | 1155.6864 | 0 | 443.232 | 443.232
PJ0005519 | SR15/16: REPAIR LEAK UNDER STAGE - BLD 44 RM 107 | KOLEGRAFF, KENNETH | CLOSED | 2016-02-11 | IN: SR15/16: REPAIR LEAK UNDER STAGE - BLD 44 RM 107 | 044 | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005519 Total | [7 empty] | 16784.4032 | 0 | 11466.882 | 11466.882
PJ0005518 | CAMERA INSTALL FOR PCV AND CERRO VISTA ELEVATORS | PROJECT UNASSIGNED | HOLD | 2016-02-08 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005518 | CAMERA INSTALL FOR PCV AND CERRO VISTA ELEVATORS | PROJECT UNASSIGNED | HOLD | 2016-02-08 | PM: CAMERA INSTALL FOR PCV AND CERRO VISTA ELEVATORS | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005518 | CAMERA INSTALL FOR PCV AND CERRO VISTA ELEVATORS | PROJECT UNASSIGNED | HOLD | 2016-02-08 | SM: CAMERA INSTALL FOR PCV AND CERRO VISTA ELEVATORS | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005518 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | AD: ITS DATA | 021 | CLOSED | 535 | 0 | 529.9924 | 529.9924
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | AD: JL FASULO | 021 | CLOSED | 2620.43 | 0 | 2620.43 | 2620.43
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | AD: MAINO LVPW | 021 | CLOSED | 3745 | 0 | 3745 | 3745
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | AD: PARC ENVIRONMENTAL | 021 | CLOSED | 3324.49 | 0 | 3324.49 | 3324.49
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | AD: STATE FIRE MARSHAL FEES | 021 | CLOSED | 160.5 | 0 | 212.3415 | 212.3415
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | CP: PROJECT CONTINGENCY | 021 | OPEN | 1624.59 | 0 | 0 | 0
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | EL:REMOVE SURFACE MOUNT CONDUITS AND RECPTCLS | 021 | CLOSED | 2317.416 | 0 | 1464.504 | 1464.504
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | IN: ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | 021 | CLOSED | 155.4168 | 0 | 70.644 | 70.644
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | LO: INSTALL NEW HARDWARE IN NEW PAIR OF DOORS | 021 | CLOSED | 1302.0984 | 0 | 606.588 | 606.588
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | MO:REMOVE CAB., 21-120A | 021 | CLOSED | 67.032 | 0 | 18 | 18
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | PA:REPAINT BOTH SIDES OF WALL AFTER NEW DOORS INSTALL | 021 | CLOSED | 1754.3712 | 0 | 742.896 | 742.896
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | PM: ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0005517 | ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | DILLON, JEFFREY | CONST_COMP | 2016-02-04 | SM: ADD DOOR BETWEEN ROOMS - BLD 21 RMS 120A , 120B | 021 | OPEN | 0 | 0 | 0 | 0
PJ0005517 Total | [7 empty] | 17606.3444 | 0 | 13334.8859 | 13334.8859
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | AD: BKM | 043A | CLOSED | 4812.6674 | 0 | 4812.6674 | 4812.6674
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | AD: STATE FIRE MARSHAL | 043A | CLOSED | 0 | 0 | 171.5103 | 171.5103
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | CA:UNFASTEN CABS; ATTACH NEW CABS; SIGNAGE | 043A | CLOSED | 1349.64 | 0 | 1247.409 | 1247.409
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | CP: PROJECT CONTINGENCY | 043A | CLOSED | 997.15 | 0 | 0 | 0
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | IN: REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | 043A | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | LO:REMOVE LEVER SET, INSTALL COVER PLATES | 043A | CLOSED | 121.0164 | 0 | 128.53 | 128.53
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | PA:REPAINT ENTIRE ROOM | 043A | CLOSED | 3323.952 | 0 | 742.896 | 742.896
PJ0005513 | REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | DILLON, JEFFREY | CLOSED | 2016-02-11 | PM: REMODEL KINESIOLOGY DEPT OFFICES - BLD 43A RMS 361,451-454 | 043A | CLOSED | 0 | 0 | 0 | 0
PJ0005513 Total | [7 empty] | 10745.7138 | 0 | 7208.9787 | 7208.9787
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | CA: SUPPORT 2016 OPEN HOUSE BOARD/STANCHIONS (APR. 15 &16) | GENERAL | CLOSED | 741.6 | 0 | 370.8 | 370.8
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | CA: SUPPORT FOR 2016 OPEN HOUSE (APR. 14 - 16) | GENERAL | CLOSED | 927 | 0 | 2118.28 | 2118.28
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | CP: SUPPORT FOR OPEN HOUSE - SAT APRIL 16 | GENERAL | CLOSED | 0 | 0 | 481.52 | 481.52
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | CU: SUPPORT FOR OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 3272.712 | 3272.712
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | EL: MATERIALS FOR SPIDER BOX AT NORTH POLY VUE. (N/L) | GENERAL | CLOSED | 0 | 0 | 631.008 | 631.008
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | EL: SUPPORT FOR 2016 OPEN HOUSE (APR 15 & 16) | GENERAL | CLOSED | 0 | 0 | 3177.05 | 3177.05
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | ES: SUPPORT FOR OPEN HOUSE 2016 | GENERAL | CLOSED | 0 | 0 | 481.52 | 481.52
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | LA: OPEN HOUSE SUPPORT 2016 | GENERAL | CLOSED | 0 | 0 | 3226.2735 | 3226.2735
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | MC: SUPPORT FOR 2016 OPEN HOUSE EVENTS (4/15) | GENERAL | CLOSED | 0 | 0 | 30 | 30
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | PERMIT: OPEN HOUSE SHOWCASE - APRIL 16, 2016 | GENERAL | CLOSED | 0 | 0 | 176.61 | 176.61
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | PL: SUPPORT FOR 2016 OPEN HOUSE (APRIL16, 2016) | GENERAL | CLOSED | 0 | 0 | 506.96 | 506.96
PJ0005512 | SUPPORT FOR 2016 OPEN HOUSE (MAINT) | POPHAM, DONALD J. | CLOSED | 2016-02-05 | RE: SUPPORT FOR OPEN HOUSE - 2016 | GENERAL | CLOSED | 0 | 0 | 392.52 | 392.52
PJ0005512 Total | [7 empty] | 1668.6 | 0 | 14865.2535 | 14865.2535
PJ0005511 | PAINT AND CARPET - BLDG. 53 RMS 205, 210E | DUNN, TRAVIS | CLOSED | 2016-01-29 | AD: FLOOR CONNECTION | 053 | CLOSED | 2273.75 | 0 | 2273.75 | 2273.75
PJ0005511 | PAINT AND CARPET - BLDG. 53 RMS 205, 210E | DUNN, TRAVIS | CLOSED | 2016-01-29 | CA: DEMO CARPET AND BASEBOARD | 053 | CLOSED | 1756.368 | 0 | 1040.196 | 1040.196
PJ0005511 | PAINT AND CARPET - BLDG. 53 RMS 205, 210E | DUNN, TRAVIS | CLOSED | 2016-01-29 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 848.04 | 0 | 0 | 0
PJ0005511 | PAINT AND CARPET - BLDG. 53 RMS 205, 210E | DUNN, TRAVIS | CLOSED | 2016-01-29 | IN: PAINT AND CARPET - BLDG. 53 RMS 205, 210E | 053 | CLOSED | 282.576 | 0 | 105.966 | 105.966
PJ0005511 | PAINT AND CARPET - BLDG. 53 RMS 205, 210E | DUNN, TRAVIS | CLOSED | 2016-01-29 | MO: MOVE RM. 205 INTO 210E | 053 | CLOSED | 589.8816 | 0 | 45 | 45
PJ0005511 | PAINT AND CARPET - BLDG. 53 RMS 205, 210E | DUNN, TRAVIS | CLOSED | 2016-01-29 | PA: PAINT ROOM 205, 210E, AND HALLWAY BULLETIN BOARD WALL | 053 | CLOSED | 2963.952 | 0 | 1114.344 | 1114.344
PJ0005511 Total | [7 empty] | 8714.5676 | 0 | 4579.256 | 4579.256
PJ0005510 | MOLD MITIGATION ACTION PLAN SUPPORT - PCV 171B RMS A/B/C/D | FLEDDERMAN, JUDE | CLOSED | 2016-02-03 | AD: CRITERION ENVIRONMENTAL | 171B | CLOSED | 0 | 0 | 5504.08 | 5504.08
PJ0005510 | MOLD MITIGATION ACTION PLAN SUPPORT - PCV 171B RMS A/B/C/D | FLEDDERMAN, JUDE | CLOSED | 2016-02-03 | AD: FLOOR CONNECTION | 171B | CLOSED | 0 | 0 | 693.36 | 693.36
PJ0005510 | MOLD MITIGATION ACTION PLAN SUPPORT - PCV 171B RMS A/B/C/D | FLEDDERMAN, JUDE | CLOSED | 2016-02-03 | CP: PROJECT CONTINGENCY | 171B | CLOSED | 0 | 0 | 0 | 0
PJ0005510 | MOLD MITIGATION ACTION PLAN SUPPORT - PCV 171B RMS A/B/C/D | FLEDDERMAN, JUDE | CLOSED | 2016-02-03 | PCV CA: MOLD REMEDIATION IN 171B ROOM 106 | 171B | CLOSED | 0 | 0 | 7917.2635 | 7917.2635
PJ0005510 Total | [7 empty] | 0 | 0 | 14114.7035 | 14114.7035
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: A-TOWN AUDIO VIDEO | 022 | CLOSED | 7490.7276 | 0 | 7621.396 | 7621.396
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: BKM FURNITURE | 022 | CLOSED | 95533.7088 | 0 | 88105.8651 | 88105.8651
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: COASTAL JANITORIAL | 022 | CLOSED | 635.58 | 0 | 635.58 | 635.58
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: COMP VIEW - A/V EQUIP | 022 | CLOSED | 2568 | 0 | 2405.5633 | 2405.5633
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: FLOOR CONNECTION | 022 | CLOSED | 14749.95 | 0 | 14749.95 | 14749.95
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: ITS REMOVE AND REPLACE WI-FI | 022 | CLOSED | 6420 | 0 | 1286.675 | 1286.675
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: JOC 15.036.024 STAPLES | 022 | CLOSED | 243174.4167 | 0 | 243173.7533 | 243173.7533
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: MCKENNA | 022 | CLOSED | 5486.96 | 0 | 5203.41 | 5203.41
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | AD: MEATHEAD MOVERS | 022 | CLOSED | 0 | 0 | 1478.74 | 1478.74
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | CA: INSTALL CHAIR RAIL & WHITEBOARDS & ROOM SIGNS & CLOCKS | 022 | CLOSED | 38874.5682 | 0 | 43729.446 | 43729.446
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | CP: PROJECT CONTINGENCY | 022 | OPEN | 6168.88 | 0 | 0 | 0
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | CU: ROOM CLEAN | 022 | CLOSED | 964.5696 | 0 | 1893.3622 | 1893.3622
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | EL: ELECTRICAL SUPPORT | 022 | CLOSED | 3134.832 | 0 | 1311.18 | 1311.18
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | IN:SP 15/16: RFRSH CLSSRMS- BLD 22 RMS 210-212; 218-220, 311-315 | 022 | CLOSED | 607.5384 | 0 | 353.22 | 353.22
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | LO: INSTALL ORANGE CORES | 022 | CLOSED | 201.0492 | 0 | 304.62 | 304.62
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | MO: MOVE TABLES AND CHAIRS | 022 | CLOSED | 1876.896 | 0 | 456 | 456
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | PM: SP 15/16: REFRESH CLSSRMS-BLD 22 RM 210-212; 218-220,311-315 | 022 | CLOSED | 0 | 0 | 0 | 0
PJ0005509 | SP 15/16: SSF- REFRESH CLASSRMS-BLD 22 210-212; 218-220, 311-315 | NORTON, DAVE | CONST_COMP | 2016-02-01 | SM: SP 15/16: SSF- REFRESH CLSRMS-BLD 22 210-212;218-220,311-315 | 022 | OPEN | 0 | 0 | 0 | 0
PJ0005509 Total | [7 empty] | 427887.6765 | 0 | 412708.7609 | 412708.7609
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | AD: FLOOR CONNECTION | 002 | CLOSED | 4590.3 | 0 | 4590.3 | 4590.3
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | AD: ITS DATA LINES | 002 | CLOSED | 1070 | 0 | 949.625 | 949.625
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | AD: STATE FIRE MARSHAL FEES | 002 | CLOSED | 278.2 | 0 | 398.6927 | 398.6927
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | AD: TRICOUNTY OFFICE FURNITURE | 002 | CLOSED | 21549.6609 | 0 | 21549.6609 | 21549.6609
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | CA: INSTALL DOOR | 002 | CLOSED | 3386.004 | 0 | 2672.109 | 2672.109
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | CP: PROJECT CONTINGENCY | 002 | OPEN | 3289.43 | 0 | 0 | 0
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | EL: HOOK UP NEW WORKSTATIONS | 002 | CLOSED | 403.4832 | 0 | 385.896 | 385.896
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | ES: FURNISH SHEET METAL COVERS | 002 | CLOSED | 2344.608 | 0 | 1473.81 | 1473.81
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | IN: FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | 002 | CLOSED | 310.8336 | 0 | 105.966 | 105.966
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | LO: PROVIDE LOCKSET TO NEW ENTRY DOOR | 002 | CLOSED | 134.0328 | 0 | 194.964 | 194.964
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | MO: MOVE FURNIITURE | 002 | CLOSED | 737.352 | 0 | 192 | 192
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | PA: PAINT ACCENT WALLS AND TOUCH UP | 002 | CLOSED | 3203.952 | 0 | 1242.432 | 1242.432
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | PM: FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0005508 | FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | NORTON, DAVE | CONST_COMP | 2016-01-29 | SM: FURNITURE REMODEL OF SOE OFFICE SUITE - BLD 02 RM 120 | 002 | OPEN | 0 | 0 | 0 | 0
PJ0005508 Total | [7 empty] | 41297.8565 | 0 | 33755.4556 | 33755.4556
PJ0005507 | INSTALL CHARGING STATIONS FOR 2 ELECTRIC CARTS - BLD 80 | DUNN, TRAVIS | CLOSED | 2016-02-01 | CA: FORM, POUR, AND FINISH MONUMENT | 080 | CLOSED | 3123.6462 | 0 | 1741.2134 | 1741.2134
PJ0005507 | INSTALL CHARGING STATIONS FOR 2 ELECTRIC CARTS - BLD 80 | DUNN, TRAVIS | CLOSED | 2016-02-01 | CP: PROJECT CONTINGENCY | 080 | CLOSED | 824.99 | 0 | 0 | 0
PJ0005507 | INSTALL CHARGING STATIONS FOR 2 ELECTRIC CARTS - BLD 80 | DUNN, TRAVIS | CLOSED | 2016-02-01 | EL: RUN POWER TO GOLF CART CHARGING STATION | 080 | CLOSED | 4574.2811 | 0 | 4177.26 | 4177.26
PJ0005507 | INSTALL CHARGING STATIONS FOR 2 ELECTRIC CARTS - BLD 80 | DUNN, TRAVIS | CLOSED | 2016-02-01 | IN: INSTALL CHARGING STATIONS FOR 2 ELECTRIC CARTS - BLD 80 | 080 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005507 | INSTALL CHARGING STATIONS FOR 2 ELECTRIC CARTS - BLD 80 | DUNN, TRAVIS | CLOSED | 2016-02-01 | LA: TRENCH FOR NEW ELECTRICAL SERVICE TO GOLF CART CHARGING | 080 | CLOSED | 1959.9667 | 0 | 385.974 | 385.974
PJ0005507 Total | [7 empty] | 10624.172 | 0 | 6445.7354 | 6445.7354
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: ASAP REPROGRAPHICS | 001 | CLOSED | 0 | 0 | 292.8055 | 292.8055
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: CAME SECURITY | 001 | CLOSED | 5644.25 | 0 | 7195.75 | 7195.75
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: FLOOR CONNECTION | 001 | CLOSED | 4066 | 0 | 4039.25 | 4039.25
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: ITS | 001 | CLOSED | 3745 | 0 | 4535.9975 | 4535.9975
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: JOC 16.038.016 MAINO | 001 | CLOSED | 195222.5486 | 0 | 195156.6473 | 195156.6473
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: MCKENNA | 001 | CLOSED | 7088.75 | 0 | 7079.12 | 7079.12
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: RRM DESIGN AND ENGLEKIRK & SABOL | 001 | CLOSED | 31173.38 | 0 | 30125.8393 | 30125.8393
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 1070 | 0 | 1700.1658 | 1700.1658
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | AD: TRI COUNTY OFFICE FURNITURE | 001 | CLOSED | 32100 | 0 | 31302.5825 | 31302.5825
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | ANTS: ALARM PROGRAMMING | 001 | CLOSED | 203.328 | 0 | 135.552 | 135.552
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | CA: CONTRACTOR ASSIST | 001 | CLOSED | 1223.64 | 0 | 195.564 | 195.564
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | CP: PROJECT CONTINGENCY | 001 | OPEN | 12692.45 | 0 | 0 | 0
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | CU: CLEAN UP | 001 | CLOSED | 184.206 | 0 | 0 | 0
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | EL: TENANT IMPROVEMENTS | 001 | CLOSED | 12813.8483 | 0 | 14343.36 | 14343.36
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | ES: CONTRACTOR ASSIST | 001 | CLOSED | 1322.304 | 0 | 2481.714 | 2481.714
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | IN: UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | 001 | CLOSED | 1059.66 | 0 | 844.62 | 844.62
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | LO: NEW LOCKSET | 001 | CLOSED | 1235.082 | 0 | 947.96 | 947.96
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | MO: | 001 | CLOSED | 335.16 | 0 | 0 | 0
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | PA: PAINT CASHIER'S OFFICE | 001 | CLOSED | 3325.86 | 0 | 2233.2 | 2233.2
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | PM: UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005506 | UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | NORTON, DAVE | CONST_COMP | 2016-01-06 | SM: UNIVERSITY CASHIERS OFFICE REMODEL - BLD 01 RM 131E | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005506 Total | [7 empty] | 314505.4669 | 0 | 302610.1279 | 302610.1279
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: DESIGN PLANS & SPECS | 001 | CLOSED | 1000 | 0 | 1000 | 1000
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: FLOOR CONNECTION | 001 | CLOSED | 1802.95 | 0 | 1802.95 | 1802.95
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: JL FASULO | 001 | CLOSED | 1414.54 | 0 | 1414.54 | 1414.54
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: KI FURNITURE | 001 | CLOSED | 695.5 | 0 | 747.6625 | 747.6625
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: MCKENNA ENVIRONMENTAL | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: MORRO BAY CABINETS | 001 | CLOSED | 5350 | 0 | 5350 | 5350
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 278.2 | 0 | 75.2638 | 75.2638
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | CA: DEMO WALL AND CABINETS | 001 | CLOSED | 2775.6462 | 0 | 4081.872 | 4081.872
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1483.31 | 0 | 0 | 0
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | EL: NEW ELECTRICAL FOR KITCHEN | 001 | CLOSED | 3480.9857 | 0 | 1427.094 | 1427.094
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | ES: TRADE SUPPORT | 001 | CLOSED | 365.0918 | 0 | 794.532 | 794.532
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | IN: KITCHEN REMODEL - BLD 01 RM 129 | 001 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | MO: MOVE CABINETS & REF | 001 | CLOSED | 167.58 | 0 | 54 | 54
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | PA; PAINT WALLS OF NEW KITCHEN | 001 | CLOSED | 2022.2806 | 0 | 807.048 | 807.048
PJ0005505 | KITCHEN REMODEL - BLD 01 RM 129 | NORTON, DAVE | CLOSED | 2016-01-06 | PL: NEW KITCHEN PLUMBING | 001 | CLOSED | 3783.3893 | 0 | 3493.524 | 3493.524
PJ0005505 Total | [7 empty] | 24902.0496 | 0 | 21225.0963 | 21225.0963
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD: APCD APPLICATION FEE | 040 | CLOSED | 0 | 0 | 235.4 | 235.4
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD: ASAP REPROGRAPHICS | 040 | CLOSED | 0 | 0 | 703.4929 | 703.4929
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD: ENGLEKIRK | 040 | CLOSED | 0 | 0 | 1107.45 | 1107.45
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD: GOSS ENGINEERING | 040 | CLOSED | 22146.86 | 0 | 22146.86 | 22146.86
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD: MCKENNA | 040 | CLOSED | 7226.78 | 0 | 573.52 | 573.52
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD: STATE FIRE MARSHAL | 040 | CLOSED | 1605 | 0 | 266.7938 | 266.7938
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | AD:SLO COUNTY AIR POLLUTION CONTROL DISTRICT | 040 | CLOSED | 2172.1 | 0 | 2172.1 | 2172.1
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | CP: PROJECT CONTINGENCY | 040 | OPEN | 1032.89 | 0 | 0 | 0
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | IN: SP 15/16: PONY BOILER ADDITION | 040 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | PM: SP 15/16: PONY BOILER ADDITION | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0005504 | SP 15/16: DESIGN PONY BOILER ADDITION | KOLEGRAFF, KENNETH | DESGN_COMP | 2016-01-20 | SM: SP 15/16: DESIGN PONY BOILER ADDITION | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005504 Total | [7 empty] | 34324.918 | 0 | 27276.2607 | 27276.2607
PJ0005503 | SR 15/16: SCADA ETHERNET SWITCH REPLACEMENT | POLVI, STEVEN | CONST_COMP | 2016-01-20 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 8818.98 | 0 | 0 | 0
PJ0005503 | SR 15/16: SCADA ETHERNET SWITCH REPLACEMENT | POLVI, STEVEN | CONST_COMP | 2016-01-20 | EL: SCADA ETHERNET SWITCH REPLACEMENT PROJECT | GENERAL | CLOSED | 77493.1085 | 0 | 85625.97 | 85625.97
PJ0005503 | SR 15/16: SCADA ETHERNET SWITCH REPLACEMENT | POLVI, STEVEN | CONST_COMP | 2016-01-20 | SM: SR 15/16: SCADA ETHERNET SWITCH REPLACEMENT | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005503 Total | [7 empty] | 86312.0885 | 0 | 85625.97 | 85625.97
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | AD: FLOOR CONNECITON | 001 | CLOSED | 17136.05 | 0 | 16964.85 | 16964.85
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | CA: DIS-ASSEMBLE AND RE-ASSEMBLE FURNITURE | 001 | CLOSED | 1218.912 | 0 | 150.318 | 150.318
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | CP: PROJECT CONTINGENCY | 001 | OPEN | 1861.39 | 0 | 0 | 0
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | IN: INSTALL CARPET - BLD 01 RM 218 | 001 | CLOSED | 155.4168 | 0 | 70.644 | 70.644
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | MO: MOVE FURNITURE FOR CARPET INSTALLATION | 001 | CLOSED | 221.2056 | 0 | 228 | 228
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | PM: INSTALL CARPET - BLD 01 RM 218 | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005502 | INSTALL CARPET - BLD 01 RM 218 | NORTON, DAVE | CONST_COMP | 2016-01-08 | SM: INSTALL CARPET - BLD 01 RM 218 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005502 Total | [7 empty] | 20592.9744 | 0 | 17413.812 | 17413.812
PJ0005501 | INSTALL "PANIC" SECURITY BUTTONS - BLD 03 | PROJECT UNASSIGNED | HOLD | 2016-01-11 | CP: PROJECT CONTINGENCY | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005501 | INSTALL "PANIC" SECURITY BUTTONS - BLD 03 | PROJECT UNASSIGNED | HOLD | 2016-01-11 | PM: INSTALL "PANIC" SECURITY BUTTONS - BLD 03 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005501 | INSTALL "PANIC" SECURITY BUTTONS - BLD 03 | PROJECT UNASSIGNED | HOLD | 2016-01-11 | SM: INSTALL "PANIC" SECURITY BUTTONS - BLD 03 | 003 | OPEN | 0 | 0 | 0 | 0
PJ0005501 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: (SR) HERTZ FURNITURE | 021 | CLOSED | 27634.89 | 0 | 27634.89 | 27634.89
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: (SR) JL FASULO DRYWALL | 021 | CLOSED | 17615.3458 | 0 | 17615.3458 | 17615.3458
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: (SR) JOC 16.037.010 MAINO | 021 | CLOSED | 17983.597 | 0 | 17983.597 | 17983.597
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: BKM FURNITURE | 021 | CLOSED | 2190.8571 | 0 | 2047.53 | 2047.53
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: CED GREENTECH | 021 | CLOSED | 5324.3307 | 0 | 5324.3307 | 5324.3307
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: FLOOR CONNECTION | 021 | CLOSED | 9749.84 | 0 | 9749.84 | 9749.84
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: ITS | 021 | CLOSED | 7440.1915 | 0 | 9735.502 | 9735.502
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: JOC 16.037.010 MAINO | 021 | CLOSED | 76360.55 | 0 | 51866.7841 | 51866.7841
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: MCKENNA ENVIRONMENTAL | 021 | CLOSED | 128.4 | 0 | 128.4 | 128.4
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | AD: STATE FIRE MARSHAL FEES | 021 | CLOSED | 642 | 0 | 75.2638 | 75.2638
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | CA:BLD 21, R 133 204,205,235,236,237,238-REPLACE BOARDS-BRACKETS | 021 | CLOSED | 57110.3124 | 0 | 34073.2794 | 34073.2794
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | CP: (SR) CONTINGENCY | 021 | CLOSED | 114.28 | 0 | 0 | 0
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 5302.17 | 0 | 0 | 0
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | CU:BLD 21, RMS 133, 204,205,235,236,237,238- CONTRACTOR SUPPORT | 021 | CLOSED | 1222.458 | 0 | 1937.957 | 1937.957
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | EL:BLD 21, RMS 133, 204,205,235,236,237,238- CONTRACTOR SUPPORT | 021 | CLOSED | 2546.124 | 0 | 5958.12 | 5958.12
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | ES:BLDG 21, RMS 204,205,235,236,237,238- SMART ROOM UPGRADES | 021 | CLOSED | 9067.3536 | 0 | 5501.765 | 5501.765
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | IN: SMART CLASSROOM UPGRADE - BLD 21 RM 204 | 021 | CLOSED | 706.44 | 0 | 423.864 | 423.864
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | LO:INSTALL NEW LEVER LOCKSETS IN BLD 21, | 021 | CLOSED | 5138.2296 | 0 | 5879.748 | 5879.748
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | MO:MOVE CHAIRS TO ESURPLUS- BLDG 21, ROOM 205, 235,237,238 | 021 | CLOSED | 402.192 | 0 | 969 | 969
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | PA: (SR) PAINT ROOMS, BLDG 21, RMS 204,205,235,236,237,238,133 | 021 | CLOSED | 7651.8786 | 0 | 7639.8 | 7639.8
PJ0005497 | SMART CLASSROOM UPGRADE - BLD 21 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2015-11-23 | PM: SMART CLASSROOM UPGRADE - BLD 21 RM 204 | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0005497 Total | [7 empty] | 254331.4403 | 0 | 204545.0169 | 204545.0169
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: ASAP PRINTING & ONTRAC | 161 | OPEN | 107 | 0 | 108.2947 | 108.2947
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: EARTH SYSTEMS PACIFIC | 161 | OPEN | 2199.92 | 1001.52 | 1198.4 | 2199.92
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: ENGLEKIRK & SABOL | 161 | OPEN | 4055.3 | 0 | 3833.81 | 3833.81
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: MAINO | 161 | OPEN | 319123.8085 | 106298.187 | 212825.6215 | 319123.8085
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: RRM DESIGN | 161 | OPEN | 58336.4 | 7462.5652 | 50688.7248 | 58151.29
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: STATE FIRE MARSHAL FEES | 161 | OPEN | 1872.5 | 0 | 562.4027 | 562.4027
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | AD: WILDAN - CODE CHECK | 161 | OPEN | 1605 | 0 | 1605 | 1605
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | CP: PROJECT CONTINGENCY | 161 | OPEN | 25083.74 | 0 | 0 | 0
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | EH&S: | 161 | OPEN | 283.2192 | 0 | 0 | 0
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | EL:J. DILLON PM. ELEC FOR BATTING CAGE | 161 | LONG_TERM | 55693.1195 | 0 | 55145.103 | 55145.103
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | IN: INSTALL COVERED BATTING CAGE BOB JANSSEN FIELD - 161 | 161 | ASSIGNED | 1356.3648 | 0 | 353.22 | 353.22
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | LA:J. DILLON PM.- IRRIGATION WORK AT SOFTBALL BATTING CAGE | 161 | OPEN | 480.384 | 0 | 452.5625 | 452.5625
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | PA:SOFTBALL BATTING CAGE PAINTING J DILLON | 161 | ASSIGNED | 4958.3232 | 0 | 3861.138 | 3861.138
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | PL: | 161 | ASSIGNED | 600.3833 | 0 | 1631.8183 | 1631.8183
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | PM: INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | 161 | OPEN | 0 | 0 | 0 | 0
PJ0005495 | INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | DILLON, JEFFREY | IN_CONSTR | 2016-01-04 | SM: INSTALL COVERED BATTING CAGE AT BOB JANSSEN FIELD - 161 | 161 | OPEN | 0 | 0 | 0 | 0
PJ0005495 Total | [7 empty] | 475755.4625 | 114762.2722 | 332266.0955 | 447028.3677
PJ0005494 | ASBESTOS ABATEMENT & FLOORING - BLD 35 2ND FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: FLOOR CONNECTION | 035 | CLOSED | 36902.8876 | 0 | 36902.8662 | 36902.8662
PJ0005494 | ASBESTOS ABATEMENT & FLOORING - BLD 35 2ND FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 572.45 | 0 | 75.2638 | 75.2638
PJ0005494 | ASBESTOS ABATEMENT & FLOORING - BLD 35 2ND FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 3788.1 | 0 | 0 | 0
PJ0005494 | ASBESTOS ABATEMENT & FLOORING - BLD 35 2ND FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN: ASBESTOS ABATEMENT & FLOORING - BLD 35 2ND FLR | 035 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005494 | ASBESTOS ABATEMENT & FLOORING - BLD 35 2ND FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | PA: Patch & Paint Room 208 Prior to new furniture installation | 035 | CLOSED | 1049.036 | 0 | 278.586 | 278.586
PJ0005494 Total | [7 empty] | 42383.1176 | 0 | 37327.36 | 37327.36
PJ0005493 | REMOVE 3M SECURITY GATE & INSTALL WALK-OFF CARPET - BLD 35-101A | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: FLOOR CONNECTION | 035 | CLOSED | 9052.4033 | 0 | 9052.4033 | 9052.4033
PJ0005493 | REMOVE 3M SECURITY GATE & INSTALL WALK-OFF CARPET - BLD 35-101A | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CA: REMOVE AND RELOCATE SECURITY GATES | 035 | CLOSED | 1110.5922 | 0 | 830.034 | 830.034
PJ0005493 | REMOVE 3M SECURITY GATE & INSTALL WALK-OFF CARPET - BLD 35-101A | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1639.26 | 0 | 0 | 0
PJ0005493 | REMOVE 3M SECURITY GATE & INSTALL WALK-OFF CARPET - BLD 35-101A | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | EL: DISCONNECT POWER TO SECURITY GATES (N/L) | 035 | CLOSED | 1494.1673 | 0 | 0 | 0
PJ0005493 | REMOVE 3M SECURITY GATE & INSTALL WALK-OFF CARPET - BLD 35-101A | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN: REMOVE 3M SECURITY GATE & INST WALK-OFF CARPET - BLD 35-101A | 035 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005493 Total | [7 empty] | 13437.7108 | 0 | 10023.7253 | 10023.7253
PJ0005492 | INSTALL PLUG MOLD AND GALLERY RAIL - BLD 35 RM 111 AND 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CA: GALLERY RAIL INSTALLATION | 035 | CLOSED | 1414.0686 | 0 | 703.662 | 703.662
PJ0005492 | INSTALL PLUG MOLD AND GALLERY RAIL - BLD 35 RM 111 AND 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1106.52 | 0 | 0 | 0
PJ0005492 | INSTALL PLUG MOLD AND GALLERY RAIL - BLD 35 RM 111 AND 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | EL: PLUG MOLD INSTALLATION | 035 | CLOSED | 9361.9714 | 0 | 6035.052 | 6035.052
PJ0005492 | INSTALL PLUG MOLD AND GALLERY RAIL - BLD 35 RM 111 AND 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN: INST PLUG MOLD AND GALLERY RAIL - BLD 35 RM 111 & 3RD FLOOR | 035 | CLOSED | 211.932 | 0 | 211.932 | 211.932
PJ0005492 Total | [7 empty] | 12094.492 | 0 | 6950.646 | 6950.646
PJ0005490 | SECURITY CAMERAS & EMERGENCY PULLS & CARD SWIPE - BLD 35 1ST FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: CAME SECURITY | 035 | CLOSED | 4761.5 | 0 | 4333.5 | 4333.5
PJ0005490 | SECURITY CAMERAS & EMERGENCY PULLS & CARD SWIPE - BLD 35 1ST FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: SOV SECURITY | 035 | CLOSED | 12427.6006 | 0 | 13369.2006 | 13369.2006
PJ0005490 | SECURITY CAMERAS & EMERGENCY PULLS & CARD SWIPE - BLD 35 1ST FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | ANTS: Support for new panic pull station installation | 035 | CLOSED | 298.2144 | 0 | 135.552 | 135.552
PJ0005490 | SECURITY CAMERAS & EMERGENCY PULLS & CARD SWIPE - BLD 35 1ST FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1773.75 | 0 | 0 | 0
PJ0005490 | SECURITY CAMERAS & EMERGENCY PULLS & CARD SWIPE - BLD 35 1ST FLR | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN:SECURITY CAMERAS & EMGRCY PULLS & CARD SWIPE - BLD 35 1ST FLR | 035 | CLOSED | 211.932 | 0 | 70.644 | 70.644
PJ0005490 Total | [7 empty] | 19472.997 | 0 | 17908.8966 | 17908.8966
PJ0005488 | CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: BKM FURNITURE | 035 | CLOSED | 34918.8508 | 0 | 33879.3351 | 33879.3351
PJ0005488 | CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 572.45 | 0 | 148.1736 | 148.1736
PJ0005488 | CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: VALLEY GLASS & MIRROR | 035 | CLOSED | 0 | 0 | 953.37 | 953.37
PJ0005488 | CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 3739.99 | 0 | 0 | 0
PJ0005488 | CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | EL: SUPPORT & (E) POWER DEMO & PLUG MOLD WORK 111 & 114 | 035 | CLOSED | 813.4092 | 0 | 2289.18 | 2289.18
PJ0005488 | CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN: CONSTRUCT 7 GLASS STUDY ROOMS - BLD 35 RM 111 | 035 | CLOSED | 211.932 | 0 | 141.288 | 141.288
PJ0005488 Total | [7 empty] | 40256.632 | 0 | 37411.3467 | 37411.3467
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: JOC 16.037.021 MAINO | 035 | CLOSED | 23453.5975 | 0 | 23310.6134 | 23310.6134
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 0 | 0 | 55.2227 | 55.2227
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 3019.8 | 0 | 0 | 0
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | EL: EXTEND ELECTRICAL RECEPTACLES & INSTALL PLUG MOLD | 035 | CLOSED | 3254.2811 | 0 | 2456.136 | 2456.136
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN: SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | 035 | CLOSED | 211.932 | 0 | 141.288 | 141.288
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | LO: INSTALLATION OF ORANGE CORES ROOMS 111E & F | 035 | CLOSED | 67.6256 | 0 | 30.462 | 30.462
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | MO: RELOCATE FURNITURE IN ROOMS 111E & F | 035 | CLOSED | 745.731 | 0 | 102 | 102
PJ0005487 | SOUNDPROOF & PAINT TWO OFFICES - BLD 35 RMS 111F, 111E | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | PA: PAINT WALLS 111E & F AFTER DRYWALL | 035 | CLOSED | 2322.2806 | 0 | 495.264 | 495.264
PJ0005487 Total | [7 empty] | 33075.2478 | 0 | 26590.9861 | 26590.9861
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: BKM FURNITURE | 035 | CLOSED | 13229.48 | 0 | 13229.1162 | 13229.1162
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: CAME SECURITY | 035 | CLOSED | 0 | 0 | 347.75 | 347.75
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: COASTAL DEMO | 035 | CLOSED | 5243 | 0 | 5243 | 5243
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: FLOOR CONNECTION | 035 | CLOSED | 23240.4 | 0 | 23240.4 | 23240.4
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: ITS | 035 | CLOSED | 3058.809 | 0 | 3572.409 | 3572.409
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | AD: STATE FIRE MARSHAL | 035 | CLOSED | 572.45 | 0 | 0 | 0
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CA: Anchor Roll Tower on room 409 | 035 | CLOSED | 1523.64 | 0 | 111.24 | 111.24
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1932.95 | 0 | 0 | 0
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | EL: DEMO & RECONNECT POWER FOR FURNITURE RM 409 | 035 | CLOSED | 2971.77 | 0 | 1669.884 | 1669.884
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | IN: REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | 035 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | MO: FURNITURE RELOCATION FOR CARPET REPLACEMENT | 035 | CLOSED | 553.014 | 0 | 495 | 495
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | PA: BLDG 35 RM409 PATCH & PAINT AFTER FURNITURE RELOCATION 35 | 035 | CLOSED | 2302.47 | 0 | 1403.694 | 1403.694
PJ0005485 | REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | KOLEGRAFF, KENNETH | CLOSED | 2015-12-18 | PM: REMOVE SHELVING & MODULAR WALL - BLD 35 RM 409 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005485 Total | [7 empty] | 54769.271 | 0 | 49418.4592 | 49418.4592
PJ0005484 | REPLACE PLEXI-GLASS WEST SIDE SPANOS - BLD 61 | DUNN, TRAVIS | CLOSED | 2016-01-04 | AD: RICK TEXEIRA WELDING | 061 | CLOSED | 42136.6 | 0 | 42136.6 | 42136.6
PJ0005484 | REPLACE PLEXI-GLASS WEST SIDE SPANOS - BLD 61 | DUNN, TRAVIS | CLOSED | 2016-01-04 | AD: THE SIGN SHOP | 061 | CLOSED | 1694.773 | 0 | 1694.773 | 1694.773
PJ0005484 | REPLACE PLEXI-GLASS WEST SIDE SPANOS - BLD 61 | DUNN, TRAVIS | CLOSED | 2016-01-04 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 4348.68 | 0 | 0 | 0
PJ0005484 | REPLACE PLEXI-GLASS WEST SIDE SPANOS - BLD 61 | DUNN, TRAVIS | CLOSED | 2016-01-04 | IN: REPLACE PLEXI-GLASS WEST SIDE SPANOS - BLD 61 | 061 | CLOSED | 1130.304 | 0 | 176.61 | 176.61
PJ0005484 | REPLACE PLEXI-GLASS WEST SIDE SPANOS - BLD 61 | DUNN, TRAVIS | CLOSED | 2016-01-04 | MO: ASSIST CONTRACTOR WITH HANDRAIL INSTALLATION(CXL) | 061 | CLOSED | 147.4704 | 0 | 0 | 0
PJ0005484 Total | [7 empty] | 49457.8274 | 0 | 44007.983 | 44007.983
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | CA: SPRING COMMENCEMENT SUPPORT - JUNE 11 & 12 | 061 | CLOSED | 3708 | 0 | 11858.415 | 11858.415
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | CPE: 2016 SPRING COMMENCEMENT SUPPORT 6/11 & 6/12 | GENERAL | CLOSED | 0 | 0 | 832.565 | 832.565
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | CU: 2016 SPRING COMMENCEMENT SUPPORT | GENERAL | CLOSED | 0 | 0 | 7523.0773 | 7523.0773
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | EL: SUPPORT FOR SPRING COMMENCEMENT - JUNE 11 & 12 | 061 | CLOSED | 0 | 0 | 1174.96 | 1174.96
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | ES: SUPPORT FOR 2016 SPRING COMMENCEMENT - 6/11 & 6/12 | GENERAL | CLOSED | 0 | 0 | 1037.76 | 1037.76
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | HC: FRONT OFFICE SUPPORT FOR COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 567.255 | 567.255
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | LA: SPRING COMMENCEMENT SUPPORT - JUNE 11 & 12 | 061 | CLOSED | 0 | 0 | 13209.1496 | 13209.1496
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | LS: SUPPORT FOR COMMENCEMENT - 6/11 & 6/12 | 061D | CLOSED | 0 | 0 | 0 | 0
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | MC: 2016 SPRING COMMENCEMENT SUPPORT | GENERAL | CLOSED | 0 | 0 | 1016.37 | 1016.37
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | PA: 2016 COMMENCEMENT SUPPORT - 6/11& 6/12 | GENERAL | CLOSED | 0 | 0 | 92.43 | 92.43
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | PERMIT: 2016 SPRING COMMENCEMENT - JUNE 11 & 12 | 061 | CLOSED | 0 | 0 | 117.74 | 117.74
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | PL: COMMENCEMENT SUPPORT - 6/11 & 6/12 | GENERAL | CLOSED | 0 | 0 | 3350.8 | 3350.8
PJ0005483 | 2016 SPRING COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2016-01-06 | RC: SUPPORT FOR SPRING COMMENCEMENT - 6/11& 12 | 061 | CLOSED | 0 | 0 | 224.75 | 224.75
PJ0005483 Total | [7 empty] | 3708 | 0 | 41005.2719 | 41005.2719
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | AD: ITS - DATA | 001 | CLOSED | 3103 | 0 | 2736.311 | 2736.311
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 278.2 | 0 | 203.2037 | 203.2037
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | AD: TRI COUNTY OFFICE FURNITURE | 001 | CLOSED | 25618.7853 | 0 | 24920.7922 | 24920.7922
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | CA: INSTALL BASEBOARD | 001 | CLOSED | 278.1 | 0 | 184.65 | 184.65
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | CU: CLEAN CARPET | 001 | CLOSED | 186.2155 | 0 | 448.1933 | 448.1933
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | EL: DISCONNECT AND SUPPLY POWER | 001 | CLOSED | 1914.1673 | 0 | 257.712 | 257.712
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | ES: HVAC SHUT DOWN | 001 | CLOSED | 196.992 | 0 | 167.628 | 167.628
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | IN: EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | 001 | CLOSED | 157.5361 | 0 | 105.966 | 105.966
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | MO: MOVE EXISTING FURNITURE | 001 | CLOSED | 373.0331 | 0 | 156 | 156
PJ0005482 | EXPAND OFFICE WORKSPACE/STATIONS - BLD 01 RM 131 | NORTON, DAVE | CLOSED | 2015-12-16 | PA: PAINT WALLS | 001 | CLOSED | 1738.0721 | 0 | 278.586 | 278.586
PJ0005482 Total | [7 empty] | 33844.1014 | 0 | 29459.0422 | 29459.0422
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | AD: ITS CHARGES | 180 | CLOSED | 6166.1425 | 0 | 6166.1425 | 6166.1425
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | AD: PROJECT COORDINATION FEES | 180 | CLOSED | 535 | 0 | 535 | 535
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | AD: SANTA MARIA ACOUSTICAL | 180 | CLOSED | 404.46 | 0 | 404.46 | 404.46
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | AD: STATE FIRE MARSHAL FEES | 180 | CLOSED | 283.55 | 0 | 0 | 0
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 1149.94 | 0 | 0 | 0
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | EL: CONNECT FURNITURE TO POWER (PLANS ATTACHED IN DOCUMENTS) | 180 | CLOSED | 3794.2811 | 0 | 3205.578 | 3205.578
PJ0005480 | CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | DUNN, TRAVIS | CLOSED | 2015-12-22 | IN: CONNECT FURNITURE TO POWER/DATA - BLD 180 RM 110 | 180 | CLOSED | 314.3658 | 0 | 70.644 | 70.644
PJ0005480 Total | [7 empty] | 12647.7394 | 0 | 10381.8245 | 10381.8245
PJ0005478 | REMOVE CARPET IN DEAN'S OFFICES & UPGRADE FLOORING BLD 05 RM 212 | DUNN, TRAVIS | ESTIMATING | 2015-12-08 | CP: PROJECT CONTINGENCY | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005478 | REMOVE CARPET IN DEAN'S OFFICES & UPGRADE FLOORING BLD 05 RM 212 | DUNN, TRAVIS | ESTIMATING | 2015-12-08 | PM: REMOVE CARPET IN DEANS OFFICE & UPGRADE FLOORNG BLD 5 RM 212 | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005478 | REMOVE CARPET IN DEAN'S OFFICES & UPGRADE FLOORING BLD 05 RM 212 | DUNN, TRAVIS | ESTIMATING | 2015-12-08 | SM: REMOVE CPT IN DEAN'S OFFICES & UPGRADE FLOORING BLD 5 RM 212 | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005478 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005477 | PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | DUNN, TRAVIS | IN_CONSTR | 2015-12-08 | CP: PROJECT CONTINGENCY | 005 | OPEN | 193.44 | 0 | 0 | 0
PJ0005477 | PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | DUNN, TRAVIS | IN_CONSTR | 2015-12-08 | PA: PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | 005 | CLOSED | 1934.3712 | 0 | 1272.84 | 1272.84
PJ0005477 | PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | DUNN, TRAVIS | IN_CONSTR | 2015-12-08 | PM: PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005477 | PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | DUNN, TRAVIS | IN_CONSTR | 2015-12-08 | SM: PAINT DUCTWORK AND UPGRADE FLOORING - BLD 5 RM 105 | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005477 Total | [7 empty] | 2127.8112 | 0 | 1272.84 | 1272.84
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | AD: FPCP PLAN REVIEW & PROJECT COORDINATION FEES | 005 | OPEN | 2000 | 0 | 2000 | 2000
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | AD: JOC 16.040.5476 NEWTON | 005 | OPEN | 164248.8841 | 33390.7945 | 130858.0682 | 164248.8627
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | AD: STATE FIRE MARSHAL | 005 | OPEN | 267.5 | 0 | 0 | 0
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | CP: PROJECT CONTINGENCY | 005 | OPEN | 597.68 | 0 | 0 | 0
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | EL: CLEAR ELEC POWER TO WALL OUTLET | 005 | COMPLETE | 566.568 | 0 | 2161.71 | 2161.71
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | IN: REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | 005 | ASSIGNED | 423.864 | 0 | 282.576 | 282.576
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | LA: CAP WATER SUPPLY FOR PATIO DEMO AT BLDG. 5 | 005 | OPEN | 780.384 | 0 | 241.3512 | 241.3512
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | PL: CAP WATER & GAS SERVICE | 005 | ASSIGNED | 377.952 | 0 | 1022.16 | 1022.16
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | PM: REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005476 | REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | KUENTZEL, DOUGLAS A. | IN_CONSTR | 2015-12-08 | SM: REMOVE EXISTING PAVING AND RE-GRADE PATIO AREA BEHIND 05-105 | 005 | OPEN | 0 | 0 | 0 | 0
PJ0005476 Total | [7 empty] | 169262.8321 | 33390.7945 | 136565.8654 | 169956.6599
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | AD: BOB'S CRANE | U-UDOR | CLOSED | 2140 | 0 | 2648.25 | 2648.25
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | AD: DAHL AIR CONDITIONING | U-UDOR | CLOSED | 0 | 0 | 588.5 | 588.5
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | AD: HPS MECHANICAL | U-UDOR | CLOSED | 17444.745 | 0 | 10652.92 | 10652.92
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | CA: CLEAN UP EDGES & RE-CAULK UTILIDOR LIDS NEAR DEXTER LAWN SE | U-UDOR | CLOSED | 1934.88 | 0 | 1316.448 | 1316.448
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 2728.86 | 0 | 0 | 0
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | CPE: SUPPORT FOR UTILIDOOR LEAK DISCOVERED 12/16/15 | U-UDOR | CLOSED | 3939.84 | 0 | 393.984 | 393.984
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | LA: REPLACE PAVERS FOLLOWING UTILIDOR REPAIR - DEXTER LAWN SE | U-UDOR | CLOSED | 0 | 0 | 1499.964 | 1499.964
PJ0005475 | SR 15/16: REPAIR UTILIDOR HOT WATER LEAK - S.E. DEXTER LAWN | SINE, MARK | CLOSED | 2015-12-16 | PL: HELP WITH DRAIN DOWN OF UTILIDOR LEAK | U-UDOR | CLOSED | 515.904 | 0 | 396.612 | 396.612
PJ0005475 Total | [7 empty] | 28704.229 | 0 | 17496.678 | 17496.678
PJ0005473 | INSTALL DIGITAL SIGNAGE - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | MARCHESE, JASON (WILL) | CLOSED | 2015-12-01 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 160.5 | 0 | 125.1365 | 125.1365
PJ0005473 | INSTALL DIGITAL SIGNAGE - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | MARCHESE, JASON (WILL) | CLOSED | 2015-12-01 | CA: PJ 5473 INSTALL DIGITAL SIGNAGE - BLDG. 003, 4TH FLOOR LOBBY | 003 | CLOSED | 2867.28 | 0 | 310.596 | 310.596
PJ0005473 | INSTALL DIGITAL SIGNAGE - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | MARCHESE, JASON (WILL) | CLOSED | 2015-12-01 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 782.11 | 0 | 0 | 0
PJ0005473 | INSTALL DIGITAL SIGNAGE - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | MARCHESE, JASON (WILL) | CLOSED | 2015-12-01 | EL: PJ5473 INSTALL DIGITAL DISPLAY BLDG. 003, 4TH FLOOR LOBBY | 003 | CLOSED | 3686.124 | 0 | 2746.608 | 2746.608
PJ0005473 | INSTALL DIGITAL SIGNAGE - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | MARCHESE, JASON (WILL) | CLOSED | 2015-12-01 | IN: INSTALL DIGITAL SIGN - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | 003 | CLOSED | 155.4168 | 0 | 211.932 | 211.932
PJ0005473 | INSTALL DIGITAL SIGNAGE - BLDG 03 - 4TH FL. VESTIBULE & HALLWAY | MARCHESE, JASON (WILL) | CLOSED | 2015-12-01 | PM: INSTALL DIGITAL SIGNAGE-BLDG 03 - 4TH FL VESTIBULE & HALLWAY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005473 Total | [7 empty] | 7651.4308 | 0 | 3394.2725 | 3394.2725
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: BKM FURNITURE | 052 | CLOSED | 36292.7843 | 0 | 37884.7196 | 37884.7196
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: CLASSROOM TECHNOLOGIES(DIRECT BILLED TO DEPT, NO OH) | 052 | CLOSED | 38520 | 0 | 0 | 0
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: COASTAL JANITORIAL | 052 | CLOSED | 2247 | 0 | 1150.25 | 1150.25
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: FLOOR CONNECTION | 052 | CLOSED | 11502.5 | 0 | 12700.9 | 12700.9
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: ITS | 052 | CLOSED | 3085.1845 | 0 | 3085.1845 | 3085.1845
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: JOC 15.036.025 STAPLES | 052 | CLOSED | 18544.1486 | 0 | 14180.6886 | 14180.6886
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 321 | 0 | 75.2638 | 75.2638
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | CA: BLDG 52 E3 NEW WORK ORDER | 052 | CLOSED | 12831.9462 | 0 | 13321.317 | 13321.317
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 10438.53 | 0 | 0 | 0
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | EL:DEMO FIXTURES, PROJECT SUPPORT BLDG 52-E3 | 052 | CLOSED | 7285.2816 | 0 | 6817.14 | 6817.14
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | IN: CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | 052 | CLOSED | 565.152 | 0 | 282.576 | 282.576
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | LO: INSTALL ORANGE CORES BLDG 52 | 052 | CLOSED | 243.696 | 0 | 60.924 | 60.924
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | MO:BLDG 52-E3 MOVE CABINETS FROM ROOM | 052 | CLOSED | 268.128 | 0 | 225 | 225
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | PA:BLDG 52-E3 PATCH PAINT WALLS, PAINT CEILING | 052 | CLOSED | 6647.904 | 0 | 4382.652 | 4382.652
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | PCV CA: ASSIST WITH CLASSROOM CONVERSION 52-E03 | 052 | CLOSED | 0 | 0 | 1284.948 | 1284.948
PJ0005472 | CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | BRENNAN, MICHAEL | CLOSED | 2015-12-01 | PM: CONVERT LAB TO CLASSROOM - BLD 52 RM E03 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005472 Total | [7 empty] | 148793.2552 | 0 | 95451.5635 | 95451.5635
PJ0005470 | FIRST FLOOR HVAC UPGRADES DESIGN - BLDG 26 1ST FLOOR | DILLON, JEFFREY | CLOSED | 2015-12-01 | AD: GOSS ENGINEERING | 026 | CLOSED | 14445 | 0 | 14445 | 14445
PJ0005470 | FIRST FLOOR HVAC UPGRADES DESIGN - BLDG 26 1ST FLOOR | DILLON, JEFFREY | CLOSED | 2015-12-01 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 1502.58 | 0 | 0 | 0
PJ0005470 | FIRST FLOOR HVAC UPGRADES DESIGN - BLDG 26 1ST FLOOR | DILLON, JEFFREY | CLOSED | 2015-12-01 | PM: FIRST FLOOR HVAC UPGRADES DESIGN - BLDG 26 1ST FLOOR | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005470 Total | [7 empty] | 15947.58 | 0 | 14445 | 14445
PJ0005468 | INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | DUNN, TRAVIS | CLOSED | 2015-11-13 | AD: ITS | 041 | CLOSED | 564.1575 | 0 | 564.1575 | 564.1575
PJ0005468 | INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | DUNN, TRAVIS | CLOSED | 2015-11-13 | AD: STATE FIRE MARSHAL FEES | 041 | CLOSED | 0 | 0 | 125.1365 | 125.1365
PJ0005468 | INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | DUNN, TRAVIS | CLOSED | 2015-11-13 | CP: PROJECT CONTINGENCY | 041 | CLOSED | 143.08 | 0 | 0 | 0
PJ0005468 | INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | DUNN, TRAVIS | CLOSED | 2015-11-13 | EL: CONNECT ELECTRICAL TO DOOR ACCESS CONTROLS | 041 | CLOSED | 725.2248 | 0 | 362.13 | 362.13
PJ0005468 | INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | DUNN, TRAVIS | CLOSED | 2015-11-13 | IN: INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | 041 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005468 | INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | DUNN, TRAVIS | CLOSED | 2015-11-13 | PM: INSTALL ID CARD READER LOCKS - BLD 41 RMS 203A, 209 | 041 | CLOSED | 0 | 0 | 0 | 0
PJ0005468 Total | [7 empty] | 1573.7503 | 0 | 1122.068 | 1122.068
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | AD: CAL POLY FACILITIES BLDG PERMIT FEES | GENERAL | OPEN | 2600.7 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | AD: CAL POLY FACILITIES PLAN REVIEW FEES | GENERAL | OPEN | 2314.62 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | AD: SEISMIC PEER REVIEW | GENERAL | OPEN | 1313 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | AD: STIATE FIRE MARSHAL FEES | GENERAL | OPEN | 1070 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 825.04 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | EH&S: | GENERAL | OPEN | 553.104 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | EL: | GENERAL | OPEN | 257.712 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | IN: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | GENERAL | ASSIGNED | 141.288 | 0 | 70.644 | 70.644
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | PM: EVALUATE VERIZON MICRO CELL SITES - GENERAL CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005467 | TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL CAMPUS | PROJECT UNASSIGNED | HOLD | 2015-12-07 | SM: TI: EVALUATE VERIZON MICRO CELL SITES & LEASES - GENERAL | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005467 Total | [7 empty] | 9075.464 | 0 | 70.644 | 70.644
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | AD: FLOOR CONNECTION | 038 | CLOSED | 10833.75 | 0 | 10833.75 | 10833.75
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | CA: REMOVE BASEBOARD | 038 | CLOSED | 1528.368 | 0 | 465.069 | 465.069
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 2055.59 | 0 | 0 | 0
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | EL: REMOVE FLOOR MOUNTED POWER PEDESTALS (N/L) | 038 | CLOSED | 386.568 | 0 | 0 | 0
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | IN: REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | 038 | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | MO: MOVE FURNITURE | 038 | CLOSED | 804.384 | 0 | 36 | 36
PJ0005466 | REPLACE CARPET AND PAINT ROOM - BLD 38 RM 135 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-01 | PA: BLDG 38 RM 135 REPAIR CRACKS AND PAINT WALLS | 038 | CLOSED | 6392.64 | 0 | 1244.364 | 1244.364
PJ0005466 Total | [7 empty] | 22283.876 | 0 | 12720.471 | 12720.471
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | CA: 2015 FALL COMMENCEMENT SUPPORT | 043 | CLOSED | 3708 | 0 | 3063.465 | 3063.465
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | CU: 2015 COMMENCEMENT SUPPORT - 12/12/2015 | 043 | CLOSED | 0 | 0 | 330.59 | 330.59
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | EL: ELECTRICAL SUPPORT - FALL COMMENCEMENT 2015 | 043 | CLOSED | 0 | 0 | 722.14 | 722.14
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | ES: 2015 FALL COMMENCEMENT SUPPORT (DEC./12/2015) | 043 | CLOSED | 0 | 0 | 361.14 | 361.14
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | LA: SUPPORT FOR 2015 COMMENCEMENT - 12/12 | 043 | CLOSED | 0 | 0 | 1164.508 | 1164.508
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | LO: EMERGENCY DOORS STICKING - REC CENTER RM 100 (12/12) | 043 | CLOSED | 0 | 0 | 187.58 | 187.58
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | MC: 2015 FALL COMMENCEMENT SUPPORT - 12/12/2015 | 043 | CLOSED | 0 | 0 | 312.2175 | 312.2175
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | PA: PAINT STAGE / 2015 COMMENCEMENT SUPPORT - 12/12/2015 | 043 | CLOSED | 0 | 0 | 283.745 | 283.745
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | PERMIT: BUILDING PERMIT FOR 2015 FALL COMMENCEMENT-9/12 | 043 | CLOSED | 0 | 0 | 147.175 | 147.175
PJ0005465 | 2015: FALL COMMENCEMENT SUPPORT. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-11-20 | PL: 2015 FALL COMMENCEMENT SUPPORT - 12/12/2015 | 043 | CLOSED | 0 | 0 | 472.96 | 472.96
PJ0005465 Total | [7 empty] | 3708 | 0 | 7045.5205 | 7045.5205
PJ0005464 | M&R ASI 15/16: INSTALL HOT H2O SUPPLY/RETURN ISOLATION VALVES | DUNN, TRAVIS | CLOSED | 2015-11-12 | AD: JOC 15.036.021 STAPLES | 043 | CLOSED | 17858.4926 | 0 | 17858.4926 | 17858.4926
PJ0005464 | M&R ASI 15/16: INSTALL HOT H2O SUPPLY/RETURN ISOLATION VALVES | DUNN, TRAVIS | CLOSED | 2015-11-12 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 1805.05 | 0 | 0 | 0
PJ0005464 | M&R ASI 15/16: INSTALL HOT H2O SUPPLY/RETURN ISOLATION VALVES | DUNN, TRAVIS | CLOSED | 2015-11-12 | EL: DISABLE FIRE ALARM FOR WELDING WORK | 043 | CLOSED | 128.856 | 0 | 64.428 | 64.428
PJ0005464 | M&R ASI 15/16: INSTALL HOT H2O SUPPLY/RETURN ISOLATION VALVES | DUNN, TRAVIS | CLOSED | 2015-11-12 | ES: SUPPORT INSTALLATION OF ISOLATION VALVES | 043 | CLOSED | 850.8403 | 0 | 955.41 | 955.41
PJ0005464 | M&R ASI 15/16: INSTALL HOT H2O SUPPLY/RETURN ISOLATION VALVES | DUNN, TRAVIS | CLOSED | 2015-11-12 | IN: M&R UU 16/17: INST HOT H2O SUPPLY/RETURN ISOLATION VALVES | 043 | CLOSED | 628.7316 | 0 | 282.576 | 282.576
PJ0005464 Total | [7 empty] | 21271.9705 | 0 | 19160.9066 | 19160.9066
PJ0005463 | DESIGN SLACKLINE POLES - NO. MT. & FREMONT | MARCHESE, JASON (WILL) | CLOSED | 2015-11-20 | AD: RRM DESIGN GROUP | RESIDENCE | CLOSED | 2033 | 0 | 1765.5 | 1765.5
PJ0005463 | DESIGN SLACKLINE POLES - NO. MT. & FREMONT | MARCHESE, JASON (WILL) | CLOSED | 2015-11-20 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 267.5 | 0 | 254.0715 | 254.0715
PJ0005463 | DESIGN SLACKLINE POLES - NO. MT. & FREMONT | MARCHESE, JASON (WILL) | CLOSED | 2015-11-20 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 195.58 | 0 | 0 | 0
PJ0005463 | DESIGN SLACKLINE POLES - NO. MT. & FREMONT | MARCHESE, JASON (WILL) | CLOSED | 2015-11-20 | IN: INSTALL SLACKLINE POLES - NO. MT. & FREMONT | RESIDENCE | CLOSED | 310.8336 | 0 | 70.644 | 70.644
PJ0005463 | DESIGN SLACKLINE POLES - NO. MT. & FREMONT | MARCHESE, JASON (WILL) | CLOSED | 2015-11-20 | PM: INSTALL SLACKLINE POLES - NO. MT. & FREMONT | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005463 Total | [7 empty] | 2806.9136 | 0 | 2090.2155 | 2090.2155
PJ0005462 | INSTALL CARPETING - BLD 38 RM 101 & 101A | MOLLAN, CHERYL L. | CLOSED | 2015-11-17 | AD: FLOOR CONNECTION | 038 | CLOSED | 1891.76 | 0 | 1891.76 | 1891.76
PJ0005462 | INSTALL CARPETING - BLD 38 RM 101 & 101A | MOLLAN, CHERYL L. | CLOSED | 2015-11-17 | CA:TRIM UNDERSIDE OF DOOR IN HALLWAY BLDG 38 ROOM 101 | 038 | CLOSED | 491.5416 | 0 | 207.5604 | 207.5604
PJ0005462 | INSTALL CARPETING - BLD 38 RM 101 & 101A | MOLLAN, CHERYL L. | CLOSED | 2015-11-17 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 346.96 | 0 | 0 | 0
PJ0005462 | INSTALL CARPETING - BLD 38 RM 101 & 101A | MOLLAN, CHERYL L. | CLOSED | 2015-11-17 | IN: INSTALL CARPETING - BLD 38 RM 101 & 101A | 038 | CLOSED | 70.644 | 0 | 141.288 | 141.288
PJ0005462 | INSTALL CARPETING - BLD 38 RM 101 & 101A | MOLLAN, CHERYL L. | CLOSED | 2015-11-17 | MO:MOVE FILE CABINETS AND SMALL FURNITURE TO HALLWAY FOR CARPET | 038 | CLOSED | 402.192 | 0 | 36 | 36
PJ0005462 | INSTALL CARPETING - BLD 38 RM 101 & 101A | MOLLAN, CHERYL L. | CLOSED | 2015-11-17 | PA:PAINT BASEBOARDS IN BLDG 38, ROOM 101 AND 101A N/L | 038 | CLOSED | 615.264 | 0 | 0 | 0
PJ0005462 Total | [7 empty] | 3818.3616 | 0 | 2276.6084 | 2276.6084
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: (RL002-SR) THE SIGN PLACE | 052 | CLOSED | 3702.8634 | 0 | 3702.8634 | 3702.8634
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: COASTAL DEMO | 052 | CLOSED | 1123.5 | 0 | 1123.5 | 1123.5
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: COASTAL JANITORIAL | 052 | CLOSED | 749 | 0 | 749 | 749
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: FISCHER SCIENTIFIC | 052 | CLOSED | 62836.8093 | 0 | 62836.8093 | 62836.8093
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: GRAINGER (FUME HOODS INSTALLED BY CONTRACTOR) | 052 | CLOSED | 20776.9711 | 0 | 20776.9711 | 20776.9711
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: ITS | 052 | CLOSED | 3929.468 | 0 | 3929.468 | 3929.468
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: JOC 16.037.009 MAINO | 052 | CLOSED | 296166.584 | 0 | 296248.8563 | 296248.8563
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 3727.88 | 0 | 3727.88 | 3727.88
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 186.2442 | 0 | 186.2442 | 186.2442
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | CA: REPAIR CEILING TILES - 52 D13,15 & 20 - BRENNAN | 052 | CLOSED | 587.556 | 0 | 587.556 | 587.556
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | CP: (RL002-SR) PROJECT CONTINGENCY | 052 | CLOSED | 127.54 | 0 | 0 | 0
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | CP: PROJECT CONTINGENCY | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | CPE: DISCONNECT DUCT ON FUME HOOD - BLDG. 52 RM D21 | 052 | CLOSED | 144.4608 | 0 | 144.456 | 144.456
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | EL: 52 DWING - ELECTRICAL MODS AND PJ SUPPORT - BRENNAN | 052 | CLOSED | 11573.622 | 0 | 11573.6311 | 11573.6311
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | ES: 52 D21 - DISCONNECT FLOOR HOOD - BRENNAN | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | IN: (RL002-SR) RENOVATE D-WING ROOMS - BLD 52 RMS D13, D15, D20- | 052 | CLOSED | 70.644 | 0 | 141.288 | 141.288
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | IN: RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | 052 | CLOSED | 211.932 | 0 | 211.932 | 211.932
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | LO: 52 DWING CORES - BRENNAN | 052 | CLOSED | 275.904 | 0 | 275.888 | 275.888
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | MO: MOVE STUFF BLDG 52- | 052 | CLOSED | 264.1061 | 0 | 264 | 264
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | PA: BLDG 52 DWING - SUPPORT, MATERIALS - BRENNAN PAINT TOUCH UP | 052 | CLOSED | 2706.6 | 0 | 2706.6 | 2706.6
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | PL: 52 DWING - REMOVE AND REPLACE FIXTURES - BRENNAN | 052 | CLOSED | 54001.158 | 0 | 54072.1068 | 54072.1068
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | PM: RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005459 | RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | NORTON, DAVE | CONST_COMP | 2015-11-17 | SM: RENOVATE D-WING ROOMS - BLD 52 RMS D13,D15,D20-D24 | 052 | OPEN | 0 | 0 | 0 | 0
PJ0005459 Total | [7 empty] | 463162.8429 | 0 | 463259.0502 | 463259.0502
PJ0005457 | INSTALL COMMERCIAL REFRIGERATOR IN CATERING KITCHEN - BLD 51A | NORTON, DAVE | CLOSED | 2015-11-18 | AD: PROJECT COORDINATION AND DESIGN | 051A | CLOSED | 535 | 0 | 535 | 535
PJ0005457 | INSTALL COMMERCIAL REFRIGERATOR IN CATERING KITCHEN - BLD 51A | NORTON, DAVE | CLOSED | 2015-11-18 | CA: MODIFY CABINETS | 051A | CLOSED | 2965.4496 | 0 | 1915.896 | 1915.896
PJ0005457 | INSTALL COMMERCIAL REFRIGERATOR IN CATERING KITCHEN - BLD 51A | NORTON, DAVE | CLOSED | 2015-11-18 | CP: PROJECT CONTINGENCY | 051A | CLOSED | 509.74 | 0 | 0 | 0
PJ0005457 | INSTALL COMMERCIAL REFRIGERATOR IN CATERING KITCHEN - BLD 51A | NORTON, DAVE | CLOSED | 2015-11-18 | EL: INSTALL OUTLET FOR WINE REF | 051A | CLOSED | 1447.4627 | 0 | 515.424 | 515.424
PJ0005457 | INSTALL COMMERCIAL REFRIGERATOR IN CATERING KITCHEN - BLD 51A | NORTON, DAVE | CLOSED | 2015-11-18 | IN: INSTALL COMMERCIAL REFRIG IN CATERING KITCHEN - BLD 51A | 051A | CLOSED | 157.5361 | 0 | 70.644 | 70.644
PJ0005457 Total | [7 empty] | 5615.1884 | 0 | 3036.964 | 3036.964
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | AD: JOC 16.039.001 NEWTON | 003 | CLOSED | 58487.2165 | 0 | 58433.449 | 58433.449
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | AD: ONE SOURCE BLINDS | 003 | CLOSED | 1070 | 0 | 577.8 | 577.8
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 6318.97 | 0 | 0 | 0
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | CU: STEAM CLEAN CARPETS | 003 | CLOSED | 776.4925 | 0 | 698.548 | 698.548
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | EL: PROJECT SUPPORT FOR LIGHTING UPGRADE | 003 | CLOSED | 1555.4558 | 0 | 1028.094 | 1028.094
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | IN: IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | 003 | CLOSED | 314.3658 | 0 | 176.61 | 176.61
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | PA: PRIME AND PAINT - BLDG. 003, ROOM 114 | 003 | CLOSED | 4285.5863 | 0 | 4013.916 | 4013.916
PJ0005456 | IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | MARCHESE, JASON (WILL) | CLOSED | 2015-11-13 | PM: IMPROVE LIGHTING REPLACE WHITEBOARDS - BLD 3 RM 114 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005456 Total | [7 empty] | 72808.0869 | 0 | 64928.417 | 64928.417
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | AD: BKM OFFICE FURNISHINGS | 014 | CLOSED | 121688.1682 | 0 | 120773.2647 | 120773.2647
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | AD: FLOOR CONNECTION | 014 | CLOSED | 10587.65 | 0 | 10587.65 | 10587.65
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | AD: ITS-DATA | 014 | CLOSED | 14016.6041 | 0 | 13909.6041 | 13909.6041
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | AD: MAINO LVPW | 014 | CLOSED | 2152.84 | 0 | 2152.84 | 2152.84
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | AD: STATE FIRE MARSHAL FEES | 014 | CLOSED | 214 | 0 | 98.7824 | 98.7824
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | AD: TRI COUNTY OFFICE FURN - REMOVAL | 014 | CLOSED | 4076.7 | 0 | 4413.75 | 4413.75
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 14633.85 | 0 | 0 | 0
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | EL:POWER AND LIGHTING | 014 | CLOSED | 13420.1136 | 0 | 10339.7604 | 10339.7604
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | IN: FURNITURE REDESIGN - BLDG 14 RM 112 | 014 | CLOSED | 388.542 | 0 | 141.288 | 141.288
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | MO:MOVE FURNITURE | 014 | CLOSED | 335.16 | 0 | 180 | 180
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | PA: BLDG 14 RM 112 WALL PAINT | 014 | CLOSED | 3443.952 | 0 | 742.896 | 742.896
PJ0005455 | FURNITURE REDESIGN - BLDG 14 RM 112 | DILLON, JEFFREY | CLOSED | 2015-11-09 | PM: FURNITURE REDESIGN - BLDG 14 RM 112 | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0005455 Total | [7 empty] | 184957.5799 | 0 | 163339.8356 | 163339.8356
PJ0005452 | SR 15/16: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | KOLEGRAFF, KENNETH | CLOSED | 2015-11-10 | AD: G.F. GARCIA & SON | GENERAL | CLOSED | 25930.2409 | 0 | 25930.2409 | 25930.2409
PJ0005452 | SR 15/16: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | KOLEGRAFF, KENNETH | CLOSED | 2015-11-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 24069.76 | 0 | 0 | 0
PJ0005452 | SR 15/16: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | KOLEGRAFF, KENNETH | CLOSED | 2015-11-10 | CPE: Emergency Repair Support for Hot Water Leak at Sierra Madre | GENERAL | CLOSED | 0 | 0 | 3031.344 | 3031.344
PJ0005452 | SR 15/16: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | KOLEGRAFF, KENNETH | CLOSED | 2015-11-10 | EL: Emergency Repair Support for Hot Water Leak at Sierra Madre | GENERAL | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005452 | SR 15/16: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | KOLEGRAFF, KENNETH | CLOSED | 2015-11-10 | IN: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | GENERAL | CLOSED | 0 | 0 | 247.254 | 247.254
PJ0005452 | SR 15/16: REPAIR HYDRONIC LINE - SIERRA MADRE, YOSEMITE, VG | KOLEGRAFF, KENNETH | CLOSED | 2015-11-10 | PL: Emergency Repair Support for Hot Water Leak at Sierra Madre | GENERAL | CLOSED | 0 | 0 | 99.96 | 99.96
PJ0005452 Total | [7 empty] | 50000.0009 | 0 | 29373.2269 | 29373.2269
PJ0005451 | SR 15/16: REPAIR CAPACITOR BANK AT SUBSTATION | POLVI, STEVEN | CLOSED | 2015-11-10 | CP: PROJECT CONTINGENCY | 075 | CLOSED | 1415.09 | 0 | 0 | 0
PJ0005451 | SR 15/16: REPAIR CAPACITOR BANK AT SUBSTATION | POLVI, STEVEN | CLOSED | 2015-11-10 | EL: REPAIR CAPACITOR BANK AT MUSTANG SUBSTATION | 075 | CLOSED | 14151.2509 | 0 | 13535.544 | 13535.544
PJ0005451 Total | [7 empty] | 15566.3409 | 0 | 13535.544 | 13535.544
PJ0005449 | SR 15/16: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | KOLEGRAFF, KENNETH | CLOSED | 2015-11-09 | AD: GARCIA AND SONS | P-C07 | CLOSED | 0 | 0 | 8802.89 | 8802.89
PJ0005449 | SR 15/16: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | KOLEGRAFF, KENNETH | CLOSED | 2015-11-09 | CP: PROJECT CONTINGENCY | P-C07 | CLOSED | 0 | 0 | 0 | 0
PJ0005449 | SR 15/16: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | KOLEGRAFF, KENNETH | CLOSED | 2015-11-09 | EL: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | P-C07 | CLOSED | 0 | 0 | 96.642 | 96.642
PJ0005449 | SR 15/16: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | KOLEGRAFF, KENNETH | CLOSED | 2015-11-09 | IN: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | P-C07 | CLOSED | 0 | 0 | 141.288 | 141.288
PJ0005449 | SR 15/16: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | KOLEGRAFF, KENNETH | CLOSED | 2015-11-09 | LA: SUPPORT EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | P-C07 | CLOSED | 0 | 0 | 0 | 0
PJ0005449 | SR 15/16: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | KOLEGRAFF, KENNETH | CLOSED | 2015-11-09 | PL: EMERGENCY REPAIRS FOR GAS LINE LEAK C7 PARKING LOT | P-C07 | CLOSED | 0 | 0 | 2011.26 | 2011.26
PJ0005449 Total | [7 empty] | 0 | 0 | 11052.08 | 11052.08
PJ0005447 | TINT WINDOWS - BLD 03 RMS 400 & 401 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-30 | AD: ATD WINDOW TINTING | 003 | CLOSED | 2675 | 0 | 2378.61 | 2378.61
PJ0005447 | TINT WINDOWS - BLD 03 RMS 400 & 401 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-30 | AD: STATE FIRE MARSHAL | 003 | CLOSED | 160.5 | 0 | 0 | 0
PJ0005447 | TINT WINDOWS - BLD 03 RMS 400 & 401 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-30 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 298.19 | 0 | 0 | 0
PJ0005447 | TINT WINDOWS - BLD 03 RMS 400 & 401 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-30 | IN: TINT WINDOWS - BLD 03 RM 401 | 003 | CLOSED | 78.4148 | 0 | 70.644 | 70.644
PJ0005447 | TINT WINDOWS - BLD 03 RMS 400 & 401 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-30 | LO: PROVIDE HOLIDAY ACCESS TO CONTRACTOR | 003 | CLOSED | 67.6256 | 0 | 30.462 | 30.462
PJ0005447 Total | [7 empty] | 3279.7305 | 0 | 2479.716 | 2479.716
PJ0005446 | SR 15/16: BOILER #3 EMERGENCY REPAIR WORK | FLEDDERMAN, JUDE | CLOSED | 2015-11-04 | AD: K&W HYDROBLAST | 040 | CLOSED | 16236.287 | 0 | 16236.287 | 16236.287
PJ0005446 | SR 15/16: BOILER #3 EMERGENCY REPAIR WORK | FLEDDERMAN, JUDE | CLOSED | 2015-11-04 | AD: RF MCDONALD | 040 | CLOSED | 36341.48 | 0 | 38302.9291 | 38302.9291
PJ0005446 | SR 15/16: BOILER #3 EMERGENCY REPAIR WORK | FLEDDERMAN, JUDE | CLOSED | 2015-11-04 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 5257.78 | 0 | 0 | 0
PJ0005446 Total | [7 empty] | 57835.547 | 0 | 54539.2161 | 54539.2161
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: ATD WINDOW TINTING | 003 | CLOSED | 5082.5 | 0 | 4701.58 | 4701.58
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: BKM FURNITURE | 003 | CLOSED | 132738.957 | 0 | 128678.9704 | 128678.9704
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: COASTAL DEMO | 003 | CLOSED | 481.5 | 0 | 481.5 | 481.5
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: FLOOR CONNECTION | 003 | CLOSED | 32169.55 | 0 | 32169.55 | 32169.55
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: ITS | 003 | CLOSED | 0 | 0 | 1182.35 | 1182.35
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: MTI | 003 | CLOSED | 7513.54 | 0 | 7513.54 | 7513.54
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: NEWTON LVPW | 003 | CLOSED | 2118.6 | 0 | 2118.6 | 2118.6
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: ONE SOURCE BLINDS | 003 | CLOSED | 3745 | 0 | 3108.564 | 3108.564
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: PROCARD PURCHASE - GRAINGER | 003 | CLOSED | 0 | 0 | 414.09 | 414.09
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: QUARESMA DRYWALL | 003 | CLOSED | 5931.01 | 0 | 5931.01 | 5931.01
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: SANTA MARIA ACOUSTIC | 003 | CLOSED | 17284.78 | 0 | 17284.78 | 17284.78
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 374.5 | 0 | 85.7605 | 85.7605
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | AD: THE SIGN PLACE | 003 | CLOSED | 1070 | 0 | 1158.7565 | 1158.7565
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | CA: PROJECT DEMO AND FINISH FOR OFFICE REMODEL - BLD 03 RM 302A | 003 | CLOSED | 6961.8846 | 0 | 4056.867 | 4056.867
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 15340.28 | 0 | 0 | 0
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | CU: | 003 | CLOSED | 644.721 | 0 | 912.396 | 912.396
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | EL: LIGHTING UPGRADE FOR REMODEL OFFICE - BLD 03 RM 302A | 003 | CLOSED | 58403.6458 | 0 | 63732.934 | 63732.934
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | ES: STUDENT SUCCESS LOUNGE REMODEL | 003 | CLOSED | 7302.7046 | 0 | 4545.87 | 4545.87
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | IN: REMODEL OFFICE - BLD 03 RM 302A | 003 | CLOSED | 628.7316 | 0 | 388.542 | 388.542
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | LO: PROVIDE ROOM ACCESS TO CONTRACTORS | 003 | CLOSED | 135.8605 | 0 | 91.386 | 91.386
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | MO: MOVING SERVICES FOR OFFICE REMODEL - BLD 03 RM 302A | 003 | CLOSED | 698.8086 | 0 | 698.58 | 698.58
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | PA: REMOVE WALL PAPER & PAINT FOR OFFICE REMODEL - BLD 3 RM 302A | 003 | CLOSED | 4733.5972 | 0 | 5145.81 | 5145.81
PJ0005445 | REMODEL OFFICE - BLD 03 RM 300 & 302A | MARCHESE, JASON (WILL) | CLOSED | 2015-10-28 | PM: REMODEL OFFICE - BLD 03 RM 302A | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005445 Total | [7 empty] | 303360.1709 | 0 | 284401.4364 | 284401.4364
PJ0005443 | DESIGN FOR INSTALLATION OF 2015 SOLAR DECATHLON HOUSE | MACDONALD, WENDY | DESGN_COMP | 2015-10-21 | AD: JOC 16.038.011 MAINO | GENERAL | CLOSED | 14302.1657 | 0 | 14302.1657 | 14302.1657
PJ0005443 | DESIGN FOR INSTALLATION OF 2015 SOLAR DECATHLON HOUSE | MACDONALD, WENDY | DESGN_COMP | 2015-10-21 | AD: PMSM ARCHITECTS | GENERAL | CLOSED | 47962.75 | 0 | 39531.15 | 39531.15
PJ0005443 | DESIGN FOR INSTALLATION OF 2015 SOLAR DECATHLON HOUSE | MACDONALD, WENDY | DESGN_COMP | 2015-10-21 | AD: STATE FIRE MARSHAL FEES | GENERAL | CLOSED | 0 | 0 | 262.7171 | 262.7171
PJ0005443 | DESIGN FOR INSTALLATION OF 2015 SOLAR DECATHLON HOUSE | MACDONALD, WENDY | DESGN_COMP | 2015-10-21 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 6335.82 | 0 | 0 | 0
PJ0005443 | DESIGN FOR INSTALLATION OF 2015 SOLAR DECATHLON HOUSE | MACDONALD, WENDY | DESGN_COMP | 2015-10-21 | IN: PERMANENT INSTALLATION OF SOLAR HOUSE | GENERAL | CLOSED | 706.44 | 0 | 70.644 | 70.644
PJ0005443 | DESIGN FOR INSTALLATION OF 2015 SOLAR DECATHLON HOUSE | MACDONALD, WENDY | DESGN_COMP | 2015-10-21 | PM: PERMANENT INSTALLATION OF SOLAR DECATHALON HOUSE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005443 Total | [7 empty] | 69307.1757 | 0 | 54166.6768 | 54166.6768
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | AD: BKM FURNITURE | 025 | CLOSED | 13995.386 | 0 | 14009.3709 | 14009.3709
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | AD: FLOOR CONNECTION | 025 | CLOSED | 3616.6 | 0 | 3616.6 | 3616.6
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | CA: PREPARE BOLTED FOR REMOVAL BY MOVERS. | 025 | CLOSED | 333.72 | 0 | 723.09 | 723.09
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | CP: PROJECT CONTINGENCY | 025 | CLOSED | 1527.92 | 0 | 0 | 0
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | CU: STRIP FLOOR WAX FOR CARPET TILES | 025 | CLOSED | 267.936 | 0 | 532.056 | 532.056
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | IN: STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | 025 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | MO: MOVE CABINETS TO SURPLUS | 025 | CLOSED | 201.096 | 0 | 18 | 18
PJ0005442 | STATISTICS DEPARTMENT OFFICE SUITE REMODEL - BLD 25 107D | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-20 | PA: PAINT ROOM | 025 | CLOSED | 6752.64 | 0 | 2451.6 | 2451.6
PJ0005442 Total | [7 empty] | 26836.586 | 0 | 21456.6829 | 21456.6829
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: ATD WINDOW TINTING | 003 | CLOSED | 1919.58 | 0 | 1919.58 | 1919.58
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: BKM FURNITURE | 003 | CLOSED | 26735.4908 | 0 | 26735.4908 | 26735.4908
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: ONE SOURCE BLINDS | 003 | CLOSED | 2253.42 | 0 | 2253.42 | 2253.42
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: QUARESMA DRYWALL | 003 | CLOSED | 6264.85 | 0 | 6259.5 | 6259.5
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: SANTA MARIA ACOUSTICAL | 003 | CLOSED | 5350 | 0 | 5328.6 | 5328.6
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 374.5 | 0 | 55.2227 | 55.2227
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: THE SIGN PLACE | 003 | CLOSED | 1070 | 0 | 1280.8435 | 1280.8435
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | CA: MASTERS PROGRAMS REMODEL | 003 | CLOSED | 3747.1878 | 0 | 1843.878 | 1843.878
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1646.32 | 0 | 0 | 0
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | CU: | 003 | CLOSED | 283.0074 | 0 | 315.9874 | 315.9874
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | EL: INSTALL NEW LED LIGHTS / PROVIDE POWER FOR INT. FURNITURE | 003 | CLOSED | 12277.3954 | 0 | 8768.232 | 8768.232
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | IN: REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLD 3 RM 408 & 409 | 003 | CLOSED | 315.0722 | 0 | 141.288 | 141.288
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | MO: MOVE FURNITURE IN MASTERS PROGRAMS OFFICES 408 & 409 | 003 | CLOSED | 298.2924 | 0 | 36 | 36
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | PA: REMOVE WALL PAPER AND PAINT - BLDG 003 RM 408 & 409 | 003 | CLOSED | 3055.5251 | 0 | 2789.196 | 2789.196
PJ0005440 | REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | PM: REMOVE WALLPAPER, PAINT, NEW FURNITURE - BLDG 3 RM 408 & 409 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005440 Total | [7 empty] | 65590.6411 | 0 | 57727.2384 | 57727.2384
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: ATD WINDOW TINTING | 003 | CLOSED | 1605 | 0 | 1279.72 | 1279.72
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | AD: QUARESMA DRYWALL | 003 | CLOSED | 5350 | 0 | 5243 | 5243
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | CA: FURNITURE, COVE BASE, BLINDS | 003 | CLOSED | 3687.1878 | 0 | 1823.847 | 1823.847
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1794.76 | 0 | 0 | 0
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | CU: CLEAN-UP FOLLOWING OFFICE REMODEL - BLDG 03 RMS 402 & 404 | 003 | CLOSED | 298.0788 | 0 | 310.6051 | 310.6051
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | IN: REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | 003 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | LO: PROVIDE ACCESS KEY FOR CONTRACTOR | 003 | CLOSED | 135.8605 | 0 | 0 | 0
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | MO: MOVE FURNITURE IN OFFICES BLDG. 003, ROOMS 402 & 404 | 003 | CLOSED | 298.2924 | 0 | 225 | 225
PJ0005439 | REMOVE WALLPAPER & PAINT OFFICES - BLD 03 RMS 402 & 404 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-07 | PA: REMOVE WALLPAPER & PAINT - BLDG 03 RMS 402 & 404 | 003 | CLOSED | 4733.5972 | 0 | 1957.308 | 1957.308
PJ0005439 Total | [7 empty] | 18217.1425 | 0 | 10980.7681 | 10980.7681
PJ0005438 | INSTALL PANIC PENDANTS - BLD 27 ((11-11-15)) | MOLLAN, CHERYL L. | CLOSED | 2015-10-26 | AD: PROJECT COORDINATION FEES (COORDINATE WITH CAME SECURITY) | 027 | CLOSED | 214 | 0 | 214 | 214
PJ0005438 | INSTALL PANIC PENDANTS - BLD 27 ((11-11-15)) | MOLLAN, CHERYL L. | CLOSED | 2015-10-26 | ANTS:STARTUP OF PANIC PENDANTS TO COMMUNICATE WITH UPD | 027 | CLOSED | 271.104 | 0 | 101.664 | 101.664
PJ0005438 | INSTALL PANIC PENDANTS - BLD 27 ((11-11-15)) | MOLLAN, CHERYL L. | CLOSED | 2015-10-26 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 66.7 | 0 | 0 | 0
PJ0005438 | INSTALL PANIC PENDANTS - BLD 27 ((11-11-15)) | MOLLAN, CHERYL L. | CLOSED | 2015-10-26 | IN: INSTALL PANIC PENDANTS - BLD 27 ((11-11-15)) | 027 | CLOSED | 70.644 | 0 | 105.966 | 105.966
PJ0005438 Total | [7 empty] | 622.448 | 0 | 421.63 | 421.63
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: A-TOWN A/V | 045 | CLOSED | 7843.2177 | 0 | 9118.2297 | 9118.2297
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: CONSTRUCTED SOLUTIONS | 045 | CLOSED | 37450 | 0 | 37739.97 | 37739.97
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: EQUIPMENT PURCHASED | 045 | CLOSED | 0 | 0 | 17781.8913 | 17781.8913
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: FLOOR CONNECTION | 045 | CLOSED | 9838.65 | 0 | 9838.65 | 9838.65
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: ITS-DATA | 045 | CLOSED | 642 | 0 | 1050.312 | 1050.312
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: JOC 16.037.007 MAINO | 045 | CLOSED | 158614.4888 | 0 | 158614.4888 | 158614.4888
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: MAINO LVPW | 045 | CLOSED | 2953.2 | 0 | 2953.2 | 2953.2
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | AD: STATE FIRE MARSHAL FEES | 045 | CLOSED | 0 | 0 | 155.6315 | 155.6315
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | CA: SUPPORT FOR ROOM RENOVATION AT BLDG. 45 RM. 216 | 045 | CLOSED | 0 | 0 | 4415.502 | 4415.502
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 9374.71 | 0 | 0 | 0
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | CU: CLEAN FLOOR | 045 | CLOSED | 745.5319 | 0 | 950.808 | 950.808
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | EL: ELECTRICAL SUPPORT | 045 | CLOSED | 717.0836 | 0 | 289.926 | 289.926
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | IN: RENOVATE ROOM - BLD 45 RM 216 | 045 | CLOSED | 392.7806 | 0 | 176.61 | 176.61
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | LO: LOCK CHANGE | 045 | CLOSED | 121.848 | 0 | 60.924 | 60.924
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | PA: PAINT ACOUSTIC CEILING | 045 | CLOSED | 2438.16 | 0 | 1457.112 | 1457.112
PJ0005437 | RENOVATE BAND ROOM - BLD 45 RM 216 | NORTON, DAVE | CLOSED | 2015-10-08 | PM: RENOVATE BAND ROOM - BLD 45 RM 216 | 045 | CLOSED | 0 | 0 | 0 | 0
PJ0005437 Total | [7 empty] | 231131.6707 | 0 | 244603.2553 | 244603.2553
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (COSAM) ASAP REPROGRAPHICS & SHIPPING | 228 | OPEN | 535 | 0 | 348.6381 | 348.6381
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (COSAM) CONTRACT OVERSIGHT FEES | 228 | OPEN | 36950.62 | 0 | 3815 | 3815
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) CALIFORNIA REGIONAL WATER QUALITY CONTROL | 228 | OPEN | 214 | 0 | 214 | 214
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) CANNON- CONSTRUCTION ENGINEERING | 228 | OPEN | 12500 | 11161 | 1339 | 12500
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) EARTH SYSTEMS- CONSTRUCTION INSPECTION | 228 | OPEN | 13940 | 13940 | 0 | 13940
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) ENGLEKIRK & SABOL | 228 | OPEN | 2500 | 0 | 2500 | 2500
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) LVPW PORT SAN LUIS OBISPO | 228 | OPEN | 4943 | 4943 | 0 | 4943
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) SHORELINE ENGINEERING - DESIGN | 228 | OPEN | 45000 | 0 | 45000 | 45000
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) SHORELINE ENGINEERING - REDESIGN PLANS | 228 | OPEN | 6000 | 0 | 6000 | 6000
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) STATE FIRE MARSHAL REVIEW FEES | 228 | OPEN | 1500 | 0 | 0 | 0
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (NSF- NO OH) WILLDAN PLAN REVIEW | 228 | OPEN | 1500 | 0 | 1500 | 1500
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | AD: (SPLIT-NO OH) MAINO | 228 | OPEN | 439769 | 439769 | 0 | 439769
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | CP: (COSAM) PROJECT CONTINGENCY | 228 | OPEN | 6322.39 | 0 | 0 | 0
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | IN: (SPLIT) RECONSTRUCT BOAT LANDING -CP PIER | 228 | ASSIGNED | 628.7316 | 0 | 70.644 | 70.644
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | PM: RECONSTRUCT BOAT LANDING - CP PIER 228 | 228 | OPEN | 0 | 0 | 0 | 0
PJ0005435 | RECONSTRUCT BOAT LANDING - CP PIER 228 | ULM, AARON | IN_CONSTR | 2015-10-29 | SM: RECONSTRUCT BOAT LANDING - CP PIER 228 | 228 | OPEN | 0 | 0 | 0 | 0
PJ0005435 Total | [7 empty] | 572302.7416 | 469813 | 60787.2821 | 530600.2821
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | AD: ASAP REPROGRAPHICS | U-ELEC | OPEN | 0 | 0 | 37.1825 | 37.1825
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | AD: POWER ENGINEERING SERVICES | U-ELEC | OPEN | 26102.65 | 6525.93 | 19576.72 | 26102.65
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | AD: STATE FIRE MARSHAL | U-ELEC | OPEN | 1070 | 0 | 0 | 0
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | CP: PROJECT CONTINGENCY | U-ELEC | OPEN | 2862.28 | 0 | 0 | 0
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | EH&S: | U-ELEC | OPEN | 70.8048 | 0 | 0 | 0
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | EL: | U-ELEC | OPEN | 708.708 | 0 | 0 | 0
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | IN: SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | U-ELEC | ASSIGNED | 70.644 | 0 | 70.644 | 70.644
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | PA: | U-ELEC | OPEN | 600 | 0 | 0 | 0
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | PM: SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | U-ELEC | OPEN | 0 | 0 | 0 | 0
PJ0005434 | SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | KOLEGRAFF, KENNETH | ESTIMATING | 2015-10-23 | SM: SR 16/17: ELECTRICAL OVERHEAD DISTRIBUTION IMPROVEMENTS | U-ELEC | OPEN | 0 | 0 | 0 | 0
PJ0005434 Total | [7 empty] | 31485.0868 | 6525.93 | 19684.5465 | 26210.4765
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | AD: JOC 15.036.020 STAPLES | 026 | CLOSED | 25018.3869 | 0 | 25017.4667 | 25017.4667
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | AD: MCKENNA | 026 | CLOSED | 2651.46 | 0 | 2651.46 | 2651.46
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | AD: STATE FIRE MARSHAL | 026 | CLOSED | 0 | 0 | 75.221 | 75.221
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | CPE: REPIPE DUCT SEGMENTS FOR DOOR INSTALL AT 26-110A/116A | 026 | CLOSED | 0 | 0 | 521.364 | 521.364
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | EL: ELECTRICAL CLEARANCE FOR DOOR INSTALLATION | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | ES: REPIPE DUCT SEGMENTS | 026 | CLOSED | 1013.1955 | 0 | 498.936 | 498.936
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | IN: INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | 026 | CLOSED | 423.864 | 0 | 317.898 | 317.898
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | MO: MOVE STORAGE RACKS | 026 | CLOSED | 33.516 | 0 | 87 | 87
PJ0005433 | INSTALL DOUBLE WIDE DOOR BETWEEN 26-110A & 26-116A | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-19 | PL: REMOVE UNUSED GAS PIPE | 026 | CLOSED | 255.7342 | 0 | 177.36 | 177.36
PJ0005433 Total | [7 empty] | 29396.1566 | 0 | 29346.7057 | 29346.7057
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | AD: CAI FALL PROTECTION A&E | 114F | CLOSED | 14124 | 0 | 9523 | 9523
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | AD: JOC 16.037.005 MAINO | 114F | CLOSED | 205652.1917 | 0 | 205652.1917 | 205652.1917
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | AD: STATE FIRE MARSHAL FEES | 114F | OPEN | 1070 | 0 | 210.8542 | 210.8542
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | CP: PROJECT CONTINGENCY | 114F | OPEN | 22155.26 | 0 | 0 | 0
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | IN: M&R HOUS 16/17: REPLACE ROOF - YO 114F T5 | 114F | CLOSED | 706.44 | 0 | 353.22 | 353.22
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | PM: M&R HOUS 16/17: REPLACE ROOF - YOSEMITE 114F T5 | 114F | OPEN | 0 | 0 | 0 | 0
PJ0005432 | M&R HOUS 16/17: REPLACE ROOF & DSGN FALL PROTECTION- YOS 114F T5 | KOLEGRAFF, KENNETH | CONST_COMP | 2015-10-23 | SM: M&R HOUS 16/17: REPL ROOF & DSGN FALL PROTECTION-YOS 114F T5 | 114F | OPEN | 0 | 0 | 0 | 0
PJ0005432 Total | [7 empty] | 243707.8917 | 0 | 215739.2659 | 215739.2659
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | AD: CAL POLY FPCP ARCHITECTURAL DESIGN SERVICES | 113F | CLOSED | 1070 | 0 | 1070 | 1070
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | AD: CENTRAL COAST SPECIALTY (INSTALLED BY JOC) | 113F | CLOSED | 37949.69 | 0 | 37949.69 | 37949.69
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | AD: FLOOR CONNECTION | 113F | CLOSED | 10700 | 0 | 8517.2 | 8517.2
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | AD: JOC 15.035.019 MAINO | 113F | CLOSED | 713261.3259 | 0 | 684029.9959 | 684029.9959
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | AD: MCKENNA ENVIRONMENTAL | 113F | CLOSED | 17061.15 | 0 | 9593.62 | 9593.62
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | AD: STATE FIRE MARSHAL | 113F | CLOSED | 1284 | 0 | 1434.5383 | 1434.5383
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | ANTS:COORDINATE WITH FIRE ALARM TESTING AT END OF PROJECT SM T5 | 113F | CLOSED | 271.104 | 0 | 101.664 | 101.664
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | CA:PROVIDE CONTRACTOR SUPPORT FOR SIERRA MADRE T5 RESTROOM | 113F | CLOSED | 1430.1012 | 0 | 472.77 | 472.77
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | CP: PROJECT CONTINGENCY | 113F | CLOSED | 49242 | 0 | 0 | 0
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | EH&S:PROJECT SUPPORT SM 113, T5 RESTROOMS | 113F | CLOSED | 561.84 | 0 | 0 | 0
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | EL:REWIRE PANELS AND RESTROOMS SM T5 AND CONTRACTOR SUPPORT | 113F | CLOSED | 75149.0278 | 0 | 67711.215 | 67711.215
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | ES:PROVIDE CONTRACTOR SUPPORT FOR SIERRA MADRE T5 RESTROOMS | 113F | CLOSED | 1387.4803 | 0 | 1070.316 | 1070.316
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | IN: M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | 113F | CLOSED | 1766.1 | 0 | 1730.778 | 1730.778
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | LO:REMOVE AND REINSTALL DOOR CLOSERS- SM 113, T5 RESTROOMS | 113F | CLOSED | 1940.8216 | 0 | 1391.162 | 1391.162
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | PA:PAINT NEW WALLS SIERRA MADRE 113, T5 RESTROOMS | 113F | CLOSED | 8268.96 | 0 | 3626.94 | 3626.94
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | PL:SUPPLY RESTROOM FIXTURES AND CONTRACT SUPPORT SM T5 | 113F | CLOSED | 37768.3382 | 0 | 23316.7635 | 23316.7635
PJ0005431 | M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | MOLLAN, CHERYL L. | CLOSED | 2015-10-23 | PM: M&R HOUS 16/17: REMODEL RESTROOM & SHOWERS - SM 113 T-5 | 113F | CLOSED | 0 | 0 | 0 | 0
PJ0005431 Total | [7 empty] | 959111.939 | 0 | 842016.6527 | 842016.6527
PJ0005430 | M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | LAMPMAN, GREG | CLOSED | 2015-10-23 | AD: JOC 16.037.020 MAINO | RESIDENCE | CLOSED | 100984.0534 | 0 | 100984.0534 | 100984.0534
PJ0005430 | M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | LAMPMAN, GREG | CLOSED | 2015-10-23 | CA: SUPPORT FOR CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | RESIDENCE | CLOSED | 18201.4962 | 0 | 13959.396 | 13959.396
PJ0005430 | M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | LAMPMAN, GREG | CLOSED | 2015-10-23 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 12034.04 | 0 | 0 | 0
PJ0005430 | M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | LAMPMAN, GREG | CLOSED | 2015-10-23 | IN: M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | RESIDENCE | CLOSED | 211.932 | 0 | 211.932 | 211.932
PJ0005430 | M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | LAMPMAN, GREG | CLOSED | 2015-10-23 | PM: M&R HOUS 16/17: CENTRALIZED TRASH ENCLOSURES - NO MT HALLS | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005430 Total | [7 empty] | 131431.5216 | 0 | 115155.3814 | 115155.3814
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | AD: HPS MECHANICAL | RESIDENCE | CLOSED | 18190 | 0 | 17954.6 | 17954.6
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | AD: ITS | RESIDENCE | CLOSED | 535 | 0 | 535 | 535
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 1171.65 | 0 | 1157.74 | 1157.74
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | AD: PARC ENVIRONMENTAL | RESIDENCE | CLOSED | 8774 | 0 | 8700.17 | 8700.17
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | AD: SANTA MARIA ACOUSTICAL | RESIDENCE | CLOSED | 13375 | 0 | 13116.06 | 13116.06
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 4959.9 | 0 | 0 | 0
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | EL: PROVIDE SUPPORT AND REPLACE LIGHTING | RESIDENCE | CLOSED | 7161.7438 | 0 | 5019.222 | 5019.222
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | ES: Provide Support for U-Dor Gasket Replacement | RESIDENCE | CLOSED | 1435.2499 | 0 | 229.824 | 229.824
PJ0005429 | M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | KOLEGRAFF, KENNETH | CLOSED | 2015-10-23 | IN: M&R HOUS 16/17: REPLACE UTILIDOR GASKETS - SO MT HALLS | RESIDENCE | CLOSED | 392.7806 | 0 | 282.576 | 282.576
PJ0005429 Total | [7 empty] | 55995.3243 | 0 | 46995.192 | 46995.192
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 278.2 | 0 | 99.7882 | 99.7882
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | CA: FRAME WALL & HANG DOOR | RESIDENCE | CLOSED | 3347.28 | 0 | 2157.882 | 2157.882
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 2111.3 | 0 | 0 | 0
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | EL: INSTALL POWER TO WATER HEATER | RESIDENCE | CLOSED | 7469.664 | 0 | 3072.768 | 3072.768
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | IN: M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | RESIDENCE | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | LO: INSTALL LOCKSET | RESIDENCE | CLOSED | 674.0328 | 0 | 472.31 | 472.31
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | PA: SM CSD APT.PAINT WALL AT CLOSET | RESIDENCE | CLOSED | 1661.976 | 0 | 866.712 | 866.712
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | PL: INSTALL WATER HEATER | RESIDENCE | CLOSED | 6732.4608 | 0 | 3090.044 | 3090.044
PJ0005428 | M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | NORTON, DAVE | CLOSED | 2015-10-23 | PM: M&R HOUS 16/17: REMODEL CSD KITCHEN - YOSEMITE/SIERRA MADRE | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005428 Total | [7 empty] | 22416.2016 | 0 | 9865.4702 | 9865.4702
PJ0005427 | M&R HOUS 16/17: INSTALL LOW FLOW TOILETS - SO MOUNTAIN | GONZALES, ALBERT | CLOSED | 2015-10-23 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 6107.13 | 0 | 0 | 0
PJ0005427 | M&R HOUS 16/17: INSTALL LOW FLOW TOILETS - SO MOUNTAIN | GONZALES, ALBERT | CLOSED | 2015-10-23 | IN: M&R HOUS 16/17: INSTALL LOW FLOW TOILETS - SO MOUNTAIN | RESIDENCE | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005427 | M&R HOUS 16/17: INSTALL LOW FLOW TOILETS - SO MOUNTAIN | GONZALES, ALBERT | CLOSED | 2015-10-23 | PA: | RESIDENCE | CLOSED | 1269.5808 | 0 | 835.758 | 835.758
PJ0005427 | M&R HOUS 16/17: INSTALL LOW FLOW TOILETS - SO MOUNTAIN | GONZALES, ALBERT | CLOSED | 2015-10-23 | PL: PURCHASE, REMOVE, AND REPLACE FIXTURES | RESIDENCE | CLOSED | 59137.8929 | 0 | 32360.7109 | 32360.7109
PJ0005427 Total | [7 empty] | 66797.1797 | 0 | 33337.7569 | 33337.7569
PJ0005419 | M&R HOUS 16/17: ASSESS FACILITY CONDITION - RES | JUDD, PERRY | CONST_COMP | 2015-10-22 | AD: ISES | RESIDENCE | CLOSED | 26671.0126 | 0 | 19640.278 | 19640.278
PJ0005419 | M&R HOUS 16/17: ASSESS FACILITY CONDITION - RES | JUDD, PERRY | CONST_COMP | 2015-10-22 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 2877.23 | 0 | 0 | 0
PJ0005419 | M&R HOUS 16/17: ASSESS FACILITY CONDITION - RES | JUDD, PERRY | CONST_COMP | 2015-10-22 | ES: ASSIST WITH FACILITIES CONDITION ASSESSMENT AT RES. HAL | RESIDENCE | CLOSED | 2101.248 | 0 | 0 | 0
PJ0005419 | M&R HOUS 16/17: ASSESS FACILITY CONDITION - RES | JUDD, PERRY | CONST_COMP | 2015-10-22 | SM: M&R HOUS 16/17: ASSESS FACILITY CONDITION - RES | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005419 Total | [7 empty] | 31649.4906 | 0 | 19640.278 | 19640.278
PJ0005417 | M&R ASI 16/17: FACILITY CONDITION ASSESSMENT - BLD 65 | JUDD, PERRY | CONST_COMP | 2015-10-22 | AD: ISES | 065 | CLOSED | 8117.8974 | 0 | 8117.8867 | 8117.8867
PJ0005417 | M&R ASI 16/17: FACILITY CONDITION ASSESSMENT - BLD 65 | JUDD, PERRY | CONST_COMP | 2015-10-22 | CP: PROJECT CONTINGENCY | 065 | OPEN | 916.85 | 0 | 0 | 0
PJ0005417 | M&R ASI 16/17: FACILITY CONDITION ASSESSMENT - BLD 65 | JUDD, PERRY | CONST_COMP | 2015-10-22 | ES: ASSIST WITH FACILITIES ASSESSMENT AT UU | 065 | CLOSED | 1050.624 | 0 | 0 | 0
PJ0005417 | M&R ASI 16/17: FACILITY CONDITION ASSESSMENT - BLD 65 | JUDD, PERRY | CONST_COMP | 2015-10-22 | SM: M&R ASI 16/17: FACILITY CONDITION ASSESSMENT - BLD 65 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005417 Total | [7 empty] | 10085.3714 | 0 | 8117.8867 | 8117.8867
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | AD: DAHL AC | 065 | CLOSED | 5296.5 | 0 | 5296.5 | 5296.5
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | AD: GOSS ENGINEERING | 065 | CLOSED | 7811 | 0 | 7811 | 7811
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | AD: JOC 16.040.5416 NEWTON | 065 | CLOSED | 33734.4571 | 0 | 33734.4571 | 33734.4571
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | AD: MCKENNA ENVIRONMENTAL | 065 | OPEN | 1491.58 | 350.96 | 1140.62 | 1491.58
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | AD: STATE FIRE MARSHAL | 065 | OPEN | 695.5 | 471.0354 | 273.1496 | 744.185
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | CP: PROJECT CONTINGENCY | 065 | OPEN | 10.63 | 0 | 0 | 0
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | EL:SUPPORT AT UU CRAFT CENTER, J DILLON PM | 065 | CLOSED | 244.8264 | 0 | 128.856 | 128.856
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | ES:SUPPORT FOR NEW FAN AT UU CRAFT CENTER, J. DILLON PM | 065 | CLOSED | 65.664 | 0 | 65.664 | 65.664
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | IN: M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | 065 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | PA:TOUCH UP AT SURFBAORD ROOM UU, J. DILLON PM | 065 | CLOSED | 323.532 | 0 | 323.532 | 323.532
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | PM: M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0005416 | M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | DILLON, JEFFREY | CONST_COMP | 2015-10-22 | SM: M&R ASI 16/17: VENT SURFBOARD SHAPING ROOM - BLD 65 RM 111 | 065 | OPEN | 0 | 0 | 0 | 0
PJ0005416 Total | [7 empty] | 49956.2655 | 821.9954 | 48950.3887 | 49772.3841
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | AD: JOC 15.035.024 MAINO | 043 | CLOSED | 51820.5922 | 0 | 51820.5922 | 51820.5922
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | AD: MAINO LVPW | 043 | CLOSED | 4552.85 | 0 | 4552.85 | 4552.85
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 5797.53 | 0 | 0 | 0
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | CPE: SUPPORT FOR U-DOR ZONE 5 ISOLATION VALVE INSTALL | 043 | CLOSED | 1534.5677 | 0 | 2406.552 | 2406.552
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | ES: SUPPORT FOR U-DOR ZONE 5 ISOLATION VALVE INSTALL | 043 | CLOSED | 1242.3629 | 0 | 853.632 | 853.632
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | IN: M&R UU 16/17: UTILIDOR QUARTERING VALVES - REC 43 | 043 | CLOSED | 353.22 | 0 | 317.898 | 317.898
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | LA: TREE TRIMMING REQUIRED FOR U-DOR LID REMOVAL | 043 | CLOSED | 222.5779 | 0 | 394.308 | 394.308
PJ0005414 | M&R ASI 16/17: UTILIDOR QUARTERING VALVES - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-10-22 | PL: SUPPORT FOR U-DOR ZONE 5 ISOLATION VALVE INSTALL | 043 | CLOSED | 860.9148 | 0 | 638.496 | 638.496
PJ0005414 Total | [7 empty] | 66384.6155 | 0 | 60984.3282 | 60984.3282
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: COASTAL JANITORIAL | 043 | CLOSED | 1058.23 | 0 | 1058.23 | 1058.23
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: FLOOR CONNECTION | 043 | CLOSED | 444498.972 | 0 | 444498.972 | 444498.972
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: MID-SATE CONTAINERS | 043 | CLOSED | 4198.4125 | 0 | 4198.4125 | 4198.4125
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: QUINN LIFT | 043 | CLOSED | 1404.6746 | 0 | 1404.6746 | 1404.6746
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: ROQ ASSOCIATES | 043 | CLOSED | 1605 | 0 | 1605 | 1605
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: STATE FIRE MARSHAL FEES | 043 | CLOSED | 130.4758 | 0 | 130.4865 | 130.4865
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CA: FILL VOIDS FOR FLOOR LEVELING | 043 | CLOSED | 3184.4856 | 0 | 3437.535 | 3437.535
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | EL: TEMP POWER AND ELECT CLEARANCE FOR FLOORING REPLACEMENT | 043 | CLOSED | 3250.6519 | 0 | 3250.662 | 3250.662
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | IN: M&R UU 16/17: REPLACE EXERCISE FLOOR - REC 43 | 043 | CLOSED | 211.932 | 0 | 211.932 | 211.932
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | MO: MOVE EXCERCISE EQUIPMENT TO STORAGE CONTAINERS | 043 | CLOSED | 2314.2318 | 0 | 2314.224 | 2314.224
PJ0005413 | M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | PM: M&R ASI 16/17: REPLACE EXERCISE FLOOR - REC 43 | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005413 Total | [7 empty] | 461857.0662 | 0 | 462110.1286 | 462110.1286
PJ0005412 | M&R ASI 16/17: REGROUT LOCKER ROOMS - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: VISALIA CERAMIC TILE | 043 | CLOSED | 59907.16 | 0 | 59907.16 | 59907.16
PJ0005412 | M&R ASI 16/17: REGROUT LOCKER ROOMS - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 5990.72 | 0 | 0 | 0
PJ0005412 Total | [7 empty] | 65897.88 | 0 | 59907.16 | 59907.16
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: STATE FIRE MARSHAL FEES | 043 | CLOSED | 139.1 | 0 | 55.2227 | 55.2227
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CA: INSTALL DOORS AND VCT | 043 | CLOSED | 7247.28 | 0 | 5046.183 | 5046.183
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CA:OPEN WALL FOR INSPECTION | 043 | CLOSED | 444.96 | 0 | 257.007 | 257.007
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 1411.6 | 0 | 0 | 0
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | IN: M&R UU 16/17: CONCERT STORAGE - REC 43 | 043 | CLOSED | 282.576 | 0 | 105.966 | 105.966
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | LO: INSTALL ADAMS RITE LOSKSET ON NEW ROLLING DOORS | 043 | CLOSED | 822.0984 | 0 | 538.668 | 538.668
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | PA: BLDG 43 RM 189 PAINT ROOM | 043 | CLOSED | 3323.952 | 0 | 836.88 | 836.88
PJ0005411 | M&R ASI 16/17: CONCERT STORAGE - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | PL: CAP UNUSED WATER SUPPLY AND DRAINS | 043 | CLOSED | 1031.2416 | 0 | 461.136 | 461.136
PJ0005411 Total | [7 empty] | 14702.808 | 0 | 7301.0627 | 7301.0627
PJ0005410 | M&R ASI 16/17: REPLACE CARPET - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: FLOOR CONNECTION | 043 | CLOSED | 30527.1 | 0 | 30527.1 | 30527.1
PJ0005410 | M&R ASI 16/17: REPLACE CARPET - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | AD: STATE FIRE MARSHAL FEES | 043 | CLOSED | 139.1 | 0 | 75.2638 | 75.2638
PJ0005410 | M&R ASI 16/17: REPLACE CARPET - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 3094.88 | 0 | 0 | 0
PJ0005410 | M&R ASI 16/17: REPLACE CARPET - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-10-22 | IN: M&R UU 16/17: REPLACE CARPET - REC 43 | 043 | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005410 Total | [7 empty] | 34043.656 | 0 | 30743.6518 | 30743.6518
PJ0005407 | M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | DUNN, TRAVIS | CONST_COMP | 2015-10-22 | CP: PROJECT CONTINGENCY | 163 | OPEN | 3477.8 | 0 | 0 | 0
PJ0005407 | M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | DUNN, TRAVIS | CONST_COMP | 2015-10-22 | EL: PJ5407 M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX | 163 | CLOSED | 33614.8043 | 0 | 37650.5235 | 37650.5235
PJ0005407 | M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | DUNN, TRAVIS | CONST_COMP | 2015-10-22 | IN: M&R UU 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | 163 | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0005407 | M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | DUNN, TRAVIS | CONST_COMP | 2015-10-22 | LA: SUPPORT ELECTRICIANS AS NEEDED | 163 | CLOSED | 880.704 | 0 | 120.096 | 120.096
PJ0005407 | M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | DUNN, TRAVIS | CONST_COMP | 2015-10-22 | PM: M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0005407 | M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | DUNN, TRAVIS | CONST_COMP | 2015-10-22 | SM: M&R ASI 16/17: UPGRADE LIGHTS - LOWER SPORTS COMPLEX 163 | 163 | OPEN | 0 | 0 | 0 | 0
PJ0005407 Total | [7 empty] | 38255.8843 | 0 | 37841.2635 | 37841.2635
PJ0005406 | M&R PARK 16/17: TREE TRIMMING & OTHER MISC WORK - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2015-10-22 | AD: GREENVALE TREE COMPANY | GEN-PARK | CLOSED | 8999.9947 | 0 | 10418.59 | 10418.59
PJ0005406 | M&R PARK 16/17: TREE TRIMMING & OTHER MISC WORK - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2015-10-22 | CP: PROJECT CONTINGENCY | GEN-PARK | OPEN | 0 | 0 | 0 | 0
PJ0005406 | M&R PARK 16/17: TREE TRIMMING & OTHER MISC WORK - CAMPUS WIDE | LOOSLEY, SCOTT L. | CONST_COMP | 2015-10-22 | SM: M&R PARK 16/17: TREE TRIMMING & OTHER MISC WRK - CAMPUS WIDE | GEN-PARK | OPEN | 0 | 0 | 0 | 0
PJ0005406 Total | [7 empty] | 8999.9947 | 0 | 10418.59 | 10418.59
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | AD: (GRAND STRUCTURE) JOC 16.037.006 MAINO | 130 | CLOSED | 79212.6671 | 0 | 79212.6671 | 79212.6671
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | AD: (LOT C-2B) JOC 16.037.006 MAINO | P-C02 | CLOSED | 23237.4254 | 0 | 23237.4254 | 23237.4254
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | AD: (LOT C-3) JOC 16.037.006 MAINO | P-C03 | CLOSED | 20284.4073 | 0 | 20284.4073 | 20284.4073
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | AD: (LOT H-12) JOC 16.037.006 MAINO | P-H12 | CLOSED | 80767.7409 | 0 | 80767.7409 | 80767.7409
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | AD: (LOT H-4F) JOC 16.037.006 MAINO | P-H04 | CLOSED | 31590.5516 | 0 | 31590.5516 | 31590.5516
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | AD: JOC MAINO (G-2 SLURRY AND STRIPE) | GEN-PARK | CLOSED | 26038.1718 | 0 | 26038.1718 | 26038.1718
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 164.53 | 0 | 0 | 0
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | IN: M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | GEN-PARK | CLOSED | 353.22 | 0 | 141.288 | 141.288
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | PA: PAINT COLUMNS (130 - GRAND STRUCTURE) | 130 | CLOSED | 7927.5424 | 0 | 7926.816 | 7926.816
PJ0005399 | M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | NORTON, DAVE | CLOSED | 2015-10-20 | PM: M&R PARK 16/17: MAINTANENCE, RESEAL AND RESTRIPE PROJECTS | GEN-PARK | CLOSED | 0 | 0 | 0 | 0
PJ0005399 Total | [7 empty] | 269576.2565 | 0 | 269199.0681 | 269199.0681
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: BKM FURNISHINGS | 052 | CLOSED | 13064.7 | 0 | 11295.2624 | 11295.2624
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: FLOOR CONNECTION | 052 | CLOSED | 15515 | 0 | 12706.25 | 12706.25
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: ITS DATA | 052 | CLOSED | 12345.1678 | 0 | 5960.1461 | 5960.1461
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: JOC 15.035.038 MAINO | 052 | CLOSED | 231846.9901 | 0 | 231846.5942 | 231846.5942
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: JOC 16.038.003 MAINO | 052 | CLOSED | 34294.4523 | 0 | 34294.4523 | 34294.4523
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 9423.49 | 0 | 9367.85 | 9367.85
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 535 | 0 | 98.7824 | 98.7824
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | CA: ASSIST WITH CORE DRILLING IN EMBASSY ENGLISH | 052 | CLOSED | 398.1 | 0 | 222.48 | 222.48
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | EL:UNDERFLOOR DEMO AND SUPPORT | 052 | CLOSED | 6269.664 | 0 | 3722.598 | 3722.598
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | ES:BLDG ISOLATION AND DEMO EQUIPMENT | 052 | CLOSED | 4067.0592 | 0 | 952.128 | 952.128
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | IN: RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | 052 | CLOSED | 310.8336 | 0 | 1342.236 | 1342.236
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | LO:NEW LOCKS AT 8 DOORS FOR EMBASSY ENGLISH PROJECT - BLDG 52 | 052 | CLOSED | 6172.2624 | 0 | 5635.644 | 5635.644
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | PA:PAINT ALL WALLS IN 6 ROOMS, 1 CEILING | 052 | CLOSED | 7847.904 | 0 | 2346.33 | 2346.33
PJ0005397 | RENOVATE OFFICES FOR EMBASSY ENGLISH - BLD 52 RMS D25-D27 | DILLON, JEFFREY | CLOSED | 2015-10-19 | PL:DEMO UNDERFLOOR | 052 | CLOSED | 7122.8304 | 0 | 11594.5273 | 11594.5273
PJ0005397 Total | [7 empty] | 349213.4538 | 0 | 331385.2807 | 331385.2807
PJ0005396 | EVALUATE ADDING ADDITIONAL HVAC: BLDG 8A RM 033L | LAMPMAN, GREG | CLOSED | 2015-10-19 | AD: COASTAL DEMO | 008A | CLOSED | 599.2 | 0 | 599.2 | 599.2
PJ0005396 | EVALUATE ADDING ADDITIONAL HVAC: BLDG 8A RM 033L | LAMPMAN, GREG | CLOSED | 2015-10-19 | AD: STATE FIRE MARSHAL FEES | 008A | CLOSED | 0 | 0 | 115.4637 | 115.4637
PJ0005396 | EVALUATE ADDING ADDITIONAL HVAC: BLDG 8A RM 033L | LAMPMAN, GREG | CLOSED | 2015-10-19 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 556.35 | 0 | 0 | 0
PJ0005396 | EVALUATE ADDING ADDITIONAL HVAC: BLDG 8A RM 033L | LAMPMAN, GREG | CLOSED | 2015-10-19 | CPE: INSTALL HVAC DUCT WORK | 008A | CLOSED | 3966.912 | 0 | 1669.098 | 1669.098
PJ0005396 | EVALUATE ADDING ADDITIONAL HVAC: BLDG 8A RM 033L | LAMPMAN, GREG | CLOSED | 2015-10-19 | IN: EVALUATE ADDING ADDITIONAL HVAC: BLDG 8A RM 033L | 008A | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005396 Total | [7 empty] | 5263.75 | 0 | 2454.4057 | 2454.4057
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | AD: RRM DESIGN GROUP | 070 | CLOSED | 20544 | 0 | 19474 | 19474
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | AD: STATE FIRE MARSHAL FEES | 070 | CLOSED | 0 | 0 | 833.9687 | 833.9687
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | CP: PROJECT CONTINGENCY | 070 | OPEN | 2268.53 | 0 | 0 | 0
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | EL:SUPPORT FOR DESIGN | 070 | CLOSED | 708.708 | 0 | 0 | 0
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | ES:SUPPORT FOR DESIGN | 070 | CLOSED | 722.304 | 0 | 32.832 | 32.832
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | PL:SUPPORT FOR DESIGN | 070 | CLOSED | 709.368 | 0 | 35.472 | 35.472
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | PM: SP 15/16: DESIGN FOR 1ST FLOOR REMODEL - BLD 70 | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005395 | SP 15/16: DESIGN FOR BLD 70 REMODEL | PRINCI, COLIN | SCOPE_DEV | 2015-10-09 | SM: SP 15/16: DESIGN FOR BLD 70 REMODEL | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005395 Total | [7 empty] | 24952.91 | 0 | 20376.2727 | 20376.2727
PJ0005394 | NEW CARPET & FURNITURE - BLDG 38-143 & 144 | HICKS, MICHAEL | CLOSED | 2015-09-24 | AD: COASTAL JANITORIAL(POSTED TO PJ#5318 IN ERROR-SEE TASK NOTE) | 038 | CLOSED | 567.1214 | 0 | 0 | 0
PJ0005394 | NEW CARPET & FURNITURE - BLDG 38-143 & 144 | HICKS, MICHAEL | CLOSED | 2015-09-24 | AD: FLOOR CONNECTION | 038 | CLOSED | 2724.22 | 0 | 2727.1732 | 2727.1732
PJ0005394 | NEW CARPET & FURNITURE - BLDG 38-143 & 144 | HICKS, MICHAEL | CLOSED | 2015-09-24 | CA: DISASSEMBLE FURNITURE INSTALL MONITOR MOUNT | 038 | CLOSED | 615.018 | 0 | 947.202 | 947.202
PJ0005394 | NEW CARPET & FURNITURE - BLDG 38-143 & 144 | HICKS, MICHAEL | CLOSED | 2015-09-24 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 413.02 | 0 | 0 | 0
PJ0005394 | NEW CARPET & FURNITURE - BLDG 38-143 & 144 | HICKS, MICHAEL | CLOSED | 2015-09-24 | IN: NEW CARPET & FURNITURE - BLDG 38-143 & 144 | 038 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005394 | NEW CARPET & FURNITURE - BLDG 38-143 & 144 | HICKS, MICHAEL | CLOSED | 2015-09-24 | MO:MOVE OUT AND BACK IN FURNITURE TO RECARPET | 038 | CLOSED | 493.0331 | 0 | 107.046 | 107.046
PJ0005394 Total | [7 empty] | 4953.7005 | 0 | 3922.7092 | 3922.7092
PJ0005392 | 15/16: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0005392 | 15/16: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | CU: BASEBALL GAME CLEAN UP SUPPORT | 160 | CLOSED | 0 | 0 | 1034.628 | 1034.628
PJ0005392 | 15/16: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | LA: BASEBALL GAME SUPPORT - 2015/2016 | 160 | CLOSED | 0 | 0 | 13210.1359 | 13210.1359
PJ0005392 | 15/16: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | LA: PRACTICE SUPPORT FOR BASEBALL (15/16) | 160 | CLOSED | 0 | 0 | 488.256 | 488.256
PJ0005392 Total | [7 empty] | 0 | 0 | 14733.0199 | 14733.0199
PJ0005391 | 15/16 SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0005391 | 15/16 SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | CU: SUPPORT FOR SOFTBALL | 161 | CLOSED | 0 | 0 | 249.9835 | 249.9835
PJ0005391 | 15/16 SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | LA: PRACTICE SUPPORT FOR SOFTBALL TEAM (15/16) | 161 | CLOSED | 0 | 0 | 40.032 | 40.032
PJ0005391 | 15/16 SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2015-10-13 | LA: SUPPORT FOR SOFTBALL GAMES - 2015/2016 | 161 | CLOSED | 0 | 0 | 8153.7871 | 8153.7871
PJ0005391 Total | [7 empty] | 0 | 0 | 8443.8026 | 8443.8026
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE EVENT SUPPORT (TRANSCEND) - 1/28 | 044 | CLOSED | 0 | 0 | 97.284 | 97.284
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE EVENT SUPPORT - 1/23/2016 | 044 | CLOSED | 0 | 0 | 126.9533 | 126.9533
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE STUDENT ATHLETICS - 9/19 | 044 | CLOSED | 0 | 0 | 38.6685 | 38.6685
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - CRUCIBLE - 4/16 | 044 | CLOSED | 0 | 0 | 38.46 | 38.46
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT (11/22) | 044 | CLOSED | 0 | 0 | 44.292 | 44.292
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - 11/12 | 044 | CLOSED | 0 | 0 | 29.97 | 29.97
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - 11/17 | 044 | CLOSED | 0 | 0 | 18.42 | 18.42
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - 11/17 (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - CAMPBELL BROS. 4/17 | 044 | CLOSED | 0 | 0 | 42.024 | 42.024
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - COMP. SCIENCE & DANCE- 5/31 | 044 | CLOSED | 0 | 0 | 36.84 | 36.84
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - CREOLE CARNIVAL | 044 | CLOSED | 0 | 0 | 57.204 | 57.204
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - LITTLE PRINCE (11/14) | 044 | CLOSED | 0 | 0 | 42.36 | 42.36
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - LITTLE PRINCE PERFORMANCES | 044 | CLOSED | 0 | 0 | 72.006 | 72.006
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - OPEN HOUSE CENG | 044 | CLOSED | 0 | 0 | 38.136 | 38.136
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - SCOTT VERNON 4/19 | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT - SPRING DANCE CONCERT - 5/26 | 044 | CLOSED | 0 | 0 | 87.0372 | 87.0372
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SPANOS THEATRE SUPPORT(DORE DANCE)-6/25 | 044 | CLOSED | 0 | 0 | 160.9874 | 160.9874
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT CPA - LAS CAFETERAS - 10/25 | 044 | CLOSED | 0 | 0 | 37.7025 | 37.7025
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR CONGRESSIONAL DEBATE - 2/4 | 044 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR FOUR HEARTS EVENT - 10/14 | 044 | CLOSED | 0 | 0 | 38.565 | 38.565
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR GUEST SPEAKER EVENT - 10/12 | 044 | CLOSED | 0 | 0 | 87.18 | 87.18
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR LA GUITARRA PERFORMANCE - 9/27 | 044 | CLOSED | 0 | 0 | 92.1 | 92.1
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR SPANOS THEATRE (BLACK COMEDY)-5/14 | 044 | CLOSED | 0 | 0 | 177.444 | 177.444
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR SPANOS THEATRE (CRUCIBLE)- 3/3 | 044 | CLOSED | 0 | 0 | 176.5757 | 176.5757
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR SPANOS THEATRE - INFUSION DANCE (6/4) | 044 | CLOSED | 0 | 0 | 103.1743 | 103.1743
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR SPANOS THEATRE EVENT (RHYTHMS) | 044 | CLOSED | 0 | 0 | 122.184 | 122.184
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR SPANOS THEATRE EVENT (STUD. DANCE)-5/25 | 044 | CLOSED | 0 | 0 | 103.356 | 103.356
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR SPANOS THEATRE EVENT - PHILIPINO CULT. NIGHT | 044 | CLOSED | 0 | 0 | 80.484 | 80.484
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT FOR STUDIO @ DANCE RECITAL - 12/13 | 044 | CLOSED | 0 | 0 | 76.44 | 76.44
PJ0005387 | 15/16: SPANOS THEATRE EVENT SUPPORT (PROJECT) | POPHAM, DONALD J. | CLOSED | 2015-10-05 | CU: SUPPORT SPANOS THEATRE EVENT - CP TALENT SHOW - 10/25 | 044 | CLOSED | 0 | 0 | 42.36 | 42.36
PJ0005387 Total | [7 empty] | 0 | 0 | 2215.5679 | 2215.5679
PJ0005386 | INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | AD: JOC 16.037.014 MAINO | 133 | CLOSED | 11331.9848 | 0 | 11331.9848 | 11331.9848
PJ0005386 | INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | AD: MORELAND THOMPSON | 133 | CLOSED | 909.5 | 0 | 909.5 | 909.5
PJ0005386 | INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 868.59 | 0 | 0 | 0
PJ0005386 | INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | IN: INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | 133 | CLOSED | 314.3658 | 0 | 247.254 | 247.254
PJ0005386 | INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | LO: INSTALL DOOR HARDWARE ON SHED | 133 | CLOSED | 706.9723 | 0 | 331.456 | 331.456
PJ0005386 | INSTALL READING SHED (GARDEN LIBRARY) - ASI CC 133 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | PA: BLDG 133 PAINT SHED | 133 | CLOSED | 4555.5251 | 0 | 2313.324 | 2313.324
PJ0005386 Total | [7 empty] | 18686.938 | 0 | 15133.5188 | 15133.5188
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | AD: JOC 16.038.017 MAINO | 133L | CLOSED | 87267.7876 | 0 | 87267.7876 | 87267.7876
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | AD: RRM DESIGN GROUP | 133L | CLOSED | 7062 | 0 | 6588.9209 | 6588.9209
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | AD: STATE FIRE MARSHAL FEES | 133L | CLOSED | 160.5 | 0 | 50.7929 | 50.7929
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | CP: PROJECT CONTINGENCY | 133L | OPEN | 4430.91 | 0 | 0 | 0
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | EL: MARK EL UTILITIES - PJ5385_ASI 133, YARD #5 | 133L | CLOSED | 283.4832 | 0 | 0 | 0
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | IN: RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | 133L | CLOSED | 621.6672 | 0 | 671.118 | 671.118
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | PL: MARK UTILITIES_PJ5385_ASI 133 YARD #5 | 133L | CLOSED | 283.7472 | 0 | 5397.8672 | 5397.8672
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | PM: RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | 133L | CLOSED | 0 | 0 | 0 | 0
PJ0005385 | RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | MARCHESE, JASON (WILL) | CONST_COMP | 2015-10-05 | SM: RECONFIGURE OUTSIDE YARD # 5 - ASI CHILDREN'S CENTER 133 | 133L | OPEN | 0 | 0 | 0 | 0
PJ0005385 Total | [7 empty] | 100110.0952 | 0 | 99976.4866 | 99976.4866
PJ0005384 | CUSTOM CABINETRY - ASI CHILDREN'S CENTER 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | AD: JOC 15.035.029 MAINO | 133 | CLOSED | 73776.7247 | 0 | 73776.7247 | 73776.7247
PJ0005384 | CUSTOM CABINETRY - ASI CHILDREN'S CENTER 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 6433.35 | 0 | 0 | 0
PJ0005384 | CUSTOM CABINETRY - ASI CHILDREN'S CENTER 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | EL: MODIFY RECEPTACLES IN ASI 133 CLASSROOM #4 | 133 | CLOSED | 377.712 | 0 | 198.2674 | 198.2674
PJ0005384 | CUSTOM CABINETRY - ASI CHILDREN'S CENTER 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | IN: CUSTOM CABINETRY - ASI CC 133 RMS 2 & 5 | 133 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005384 | CUSTOM CABINETRY - ASI CHILDREN'S CENTER 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | PL: INSTALL ISOLATION VALVES AT CHILDREN'S CENTER | 133 | CLOSED | 496.5576 | 0 | 689.112 | 689.112
PJ0005384 Total | [7 empty] | 81398.7101 | 0 | 74805.3921 | 74805.3921
PJ0005383 | REPLACE EXTERIOR DOORS/WINDOWS - ASI CC 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | AD: JOC 16.037.019 MAINO | 133 | CLOSED | 27932.7673 | 0 | 27932.7673 | 27932.7673
PJ0005383 | REPLACE EXTERIOR DOORS/WINDOWS - ASI CC 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | AD: STATE FIRE MARSHAL FEES | 133 | CLOSED | 267.5 | 0 | 158.7666 | 158.7666
PJ0005383 | REPLACE EXTERIOR DOORS/WINDOWS - ASI CC 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 3081.29 | 0 | 0 | 0
PJ0005383 | REPLACE EXTERIOR DOORS/WINDOWS - ASI CC 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | IN: REPLACE EXTERIOR DOORS/WINDOWS - ASI CC 133 RMS 2 & 5 | 133 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005383 | REPLACE EXTERIOR DOORS/WINDOWS - ASI CC 133 RMS 4 & 5 | MARCHESE, JASON (WILL) | CLOSED | 2015-10-05 | PA: PAINT CLASSROOMS 4 & 5 AT ASI 133 | 133 | CLOSED | 4027.1254 | 0 | 1631.688 | 1631.688
PJ0005383 Total | [7 empty] | 35623.0485 | 0 | 29864.5099 | 29864.5099
PJ0005381 | M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | DUNN, TRAVIS | IN_CONSTR | 2015-10-02 | AD: QUAGLINO ROOFING | 006 | OPEN | 2514.5 | 0 | 2514.5 | 2514.5
PJ0005381 | M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | DUNN, TRAVIS | IN_CONSTR | 2015-10-02 | CA: | 006 | OPEN | 111.24 | 0 | 0 | 0
PJ0005381 | M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | DUNN, TRAVIS | IN_CONSTR | 2015-10-02 | CP: PROJECT CONTINGENCY | 006 | OPEN | 154.34 | 0 | 0 | 0
PJ0005381 | M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | DUNN, TRAVIS | IN_CONSTR | 2015-10-02 | IN: M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | 006 | ASSIGNED | 141.288 | 0 | 70.644 | 70.644
PJ0005381 | M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | DUNN, TRAVIS | IN_CONSTR | 2015-10-02 | PM: M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005381 | M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | DUNN, TRAVIS | IN_CONSTR | 2015-10-02 | SM: M&R PAC 16/17: ASSESS / REPLACE / RELINE GUTTERS - PAC 06 | 006 | OPEN | 0 | 0 | 0 | 0
PJ0005381 Total | [7 empty] | 2921.368 | 0 | 2585.144 | 2585.144
PJ0005380 | M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | BRENNAN, MICHAEL | CLOSED | 2015-10-02 | AD: COAST PAINTING | 006 | CLOSED | 3745 | 0 | 3745 | 3745
PJ0005380 | M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | BRENNAN, MICHAEL | CLOSED | 2015-10-02 | AD: JOC 15.035.026 MAINO | 006 | CLOSED | 8182.4933 | 0 | 8182.4933 | 8182.4933
PJ0005380 | M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | BRENNAN, MICHAEL | CLOSED | 2015-10-02 | AD: STATE FIRE MARSHAL | 006 | CLOSED | 0 | 0 | 55.2227 | 55.2227
PJ0005380 | M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | BRENNAN, MICHAEL | CLOSED | 2015-10-02 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1213.94 | 0 | 0 | 0
PJ0005380 | M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | BRENNAN, MICHAEL | CLOSED | 2015-10-02 | IN: M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | 006 | CLOSED | 211.932 | 0 | 58.87 | 58.87
PJ0005380 | M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | BRENNAN, MICHAEL | CLOSED | 2015-10-02 | PM: M&R PAC 16/17: REFURBISH MAIN ENTRY DOORS | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005380 Total | [7 empty] | 13353.3653 | 0 | 12041.586 | 12041.586
PJ0005378 | M&R PAC 16/17: INSTALL URINAL DIVIDERS DOWNSTAIRS | LAMPMAN, GREG | CLOSED | 2015-10-02 | CA: REMOVE AND REPLACE 10 URINAL SCREENS | 006 | CLOSED | 4980.6282 | 0 | 4343.7 | 4343.7
PJ0005378 | M&R PAC 16/17: INSTALL URINAL DIVIDERS DOWNSTAIRS | LAMPMAN, GREG | CLOSED | 2015-10-02 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 512.24 | 0 | 0 | 0
PJ0005378 | M&R PAC 16/17: INSTALL URINAL DIVIDERS DOWNSTAIRS | LAMPMAN, GREG | CLOSED | 2015-10-02 | IN: M&R PAC 16/17: INSTALL URINAL DIVIDERS DOWNSTAIRS | 006 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005378 Total | [7 empty] | 5634.1562 | 0 | 4484.988 | 4484.988
PJ0005375 | MODIFY OFFICE DESK BLDG 01-209G | NORTON, DAVE | CLOSED | 2015-09-25 | AD: BKM | 001 | CLOSED | 1027.2 | 0 | 1026.9111 | 1026.9111
PJ0005375 | MODIFY OFFICE DESK BLDG 01-209G | NORTON, DAVE | CLOSED | 2015-09-25 | AD: DA CRAGHEAD | 001 | CLOSED | 642 | 0 | 595.99 | 595.99
PJ0005375 | MODIFY OFFICE DESK BLDG 01-209G | NORTON, DAVE | CLOSED | 2015-09-25 | AD: ECWEST | 001 | CLOSED | 2340.6785 | 0 | 2340.6785 | 2340.6785
PJ0005375 | MODIFY OFFICE DESK BLDG 01-209G | NORTON, DAVE | CLOSED | 2015-09-25 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 415.11 | 0 | 0 | 0
PJ0005375 | MODIFY OFFICE DESK BLDG 01-209G | NORTON, DAVE | CLOSED | 2015-09-25 | IN: MODIFY OFFICE DESK BLDG 01-209G | 001 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005375 Total | [7 empty] | 4566.2765 | 0 | 4034.2236 | 4034.2236
PJ0005374 | MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | NORTON, DAVE | CLOSED | 2015-09-22 | AD: CAME SECURITY | 001 | CLOSED | 3317 | 0 | 3317 | 3317
PJ0005374 | MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | NORTON, DAVE | CLOSED | 2015-09-22 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 0 | 0 | 127.009 | 127.009
PJ0005374 | MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | NORTON, DAVE | CLOSED | 2015-09-22 | ANTS: CONNECT ALARM PANEL TO UPD | 001 | CLOSED | 301.6032 | 0 | 169.44 | 169.44
PJ0005374 | MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | NORTON, DAVE | CLOSED | 2015-09-22 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 228.21 | 0 | 0 | 0
PJ0005374 | MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | NORTON, DAVE | CLOSED | 2015-09-22 | EL:ADD OUTLET FOR ALARM PANEL | 001 | CLOSED | 658.2197 | 0 | 684.762 | 684.762
PJ0005374 | MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | NORTON, DAVE | CLOSED | 2015-09-22 | IN: MOVE ALARM PANEL FROM 4TH FLR TO 3RD FLR - ADMIN BLDG | 001 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005374 Total | [7 empty] | 4646.3209 | 0 | 4439.499 | 4439.499
PJ0005373 | BLD 180 RM 630, 631, 633-REPLACE WINDOWED DOORS WITH SOLID DOORS | HICKS, MICHAEL | CLOSED | 2015-08-27 | AD: ADT WINDOW TINTING | 180 | CLOSED | 476.15 | 0 | 422.65 | 422.65
PJ0005373 | BLD 180 RM 630, 631, 633-REPLACE WINDOWED DOORS WITH SOLID DOORS | HICKS, MICHAEL | CLOSED | 2015-08-27 | CA: REPLACE EXISTING FRENCH DOORS WITH SOLID DOORS | 180 | CLOSED | 1230.5922 | 0 | 816.222 | 816.222
PJ0005373 | BLD 180 RM 630, 631, 633-REPLACE WINDOWED DOORS WITH SOLID DOORS | HICKS, MICHAEL | CLOSED | 2015-08-27 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 224.56 | 0 | 0 | 0
PJ0005373 | BLD 180 RM 630, 631, 633-REPLACE WINDOWED DOORS WITH SOLID DOORS | HICKS, MICHAEL | CLOSED | 2015-08-27 | IN: BLD180 RM 630, 631, 633-REPLACE WINDOWED DOORS W SOLID DOORS | 180 | CLOSED | 70.644 | 0 | 141.288 | 141.288
PJ0005373 | BLD 180 RM 630, 631, 633-REPLACE WINDOWED DOORS WITH SOLID DOORS | HICKS, MICHAEL | CLOSED | 2015-08-27 | LO: SWAP DOOR HARDWARE AND ADD SECURE DOUBLE DEADBOLT | 180 | CLOSED | 1245.3354 | 0 | 1186.176 | 1186.176
PJ0005373 Total | [7 empty] | 3247.2816 | 0 | 2566.336 | 2566.336
PJ0005371 | REVIEW AND MODIFY WALL FINISH IN ROOM 05-105 | MARCHESE, JASON (WILL) | CLOSED | 2015-09-03 | AD: FASULO LVPW | 005 | CLOSED | 3745 | 0 | 3141.52 | 3141.52
PJ0005371 | REVIEW AND MODIFY WALL FINISH IN ROOM 05-105 | MARCHESE, JASON (WILL) | CLOSED | 2015-09-03 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 691.83 | 0 | 0 | 0
PJ0005371 | REVIEW AND MODIFY WALL FINISH IN ROOM 05-105 | MARCHESE, JASON (WILL) | CLOSED | 2015-09-03 | EL: RE-ENERGIZE CIRCUITS & INSTALL COVERS ON OUTLETS & SWITCHS | 005 | CLOSED | 1747.4627 | 0 | 1495.086 | 1495.086
PJ0005371 | REVIEW AND MODIFY WALL FINISH IN ROOM 05-105 | MARCHESE, JASON (WILL) | CLOSED | 2015-09-03 | IN: REVIEW AND MODIFY WALL FINISH IN ROOM 05-105 | 005 | CLOSED | 141.288 | 0 | 211.932 | 211.932
PJ0005371 | REVIEW AND MODIFY WALL FINISH IN ROOM 05-105 | MARCHESE, JASON (WILL) | CLOSED | 2015-09-03 | LO: CHANGE CORES BACK TO ORIGINALS | 005 | CLOSED | 0 | 0 | 30.462 | 30.462
PJ0005371 Total | [7 empty] | 6325.5807 | 0 | 4879 | 4879
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: ASAP REPROGRAPHICS & SHIPPING | 027 | CLOSED | 0 | 0 | 108.3803 | 108.3803
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: GRAINGER- PROCARD PURCHASE¿ TO BE INSTALLED BY CONTRACTOR | 027 | CLOSED | 318.539 | 0 | 318.539 | 318.539
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: MCKENNA | 027 | CLOSED | 11459.7 | 0 | 11232.86 | 11232.86
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: MEC INC | 027 | CLOSED | 2105.76 | 0 | 2105.76 | 2105.76
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: QUARESMA DRYWALL | 027 | CLOSED | 3424 | 0 | 3424 | 3424
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: STATE FIRE MARSHAL | 027 | CLOSED | 3578.5829 | 0 | 5185.0595 | 5185.0595
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: TYCO SIMPLEX GRINNELL | 027 | CLOSED | 287592.1711 | 0 | 287591.711 | 287591.711
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | AD: VORTEX | 027 | CLOSED | 765.264 | 0 | 765.264 | 765.264
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | ANTS: ALARMS PROGRAMING FOR HEALTH CENTER SIMPLEX UPGRADE | 027 | CLOSED | 271.104 | 0 | 440.544 | 440.544
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | CA: | 027 | CLOSED | 61.182 | 0 | 0 | 0
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | CP: PROJECT CONTINGENCY | 027 | OPEN | 7654.23 | 0 | 0 | 0
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | EL:SUPPORT FOR FIRE ALARM DESIGN BLDG 27 - KOLEGRAFF | 027 | CLOSED | 1891.77 | 0 | 2756.424 | 2756.424
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | IN:M&R H/C 16/17, SR 16/17: REPL SIMPLEX FIRE ALARM - HEALTH CTR | 027 | CLOSED | 289.6404 | 0 | 141.288 | 141.288
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | LO: INSTALLATION OF ORANGE CORES - KOLEGRAFF | 027 | CLOSED | 335.082 | 0 | 30.462 | 30.462
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | PA: PATCH AND PAINT WHERE FIRE ALARM REPLACMENT SEE MAP | 027 | CLOSED | 5285.928 | 0 | 1516.746 | 1516.746
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | PM: M&R H/C 16/17, SR 16/17: REPLACE SIMPLEX FIRE ALARM-HLTH CTR | 027 | CLOSED | 0 | 0 | 0 | 0
PJ0005369 | M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FIRE ALARM - HEALTH CTR | KOLEGRAFF, KENNETH | CONST_COMP | 2015-09-01 | SM: M&R H/C 16/17, DM 15/16: REPLACE SIMPLEX FALARM - HEALTH CTR | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005369 Total | [7 empty] | 325032.9534 | 0 | 315617.0378 | 315617.0378
PJ0005368 | SR 16/17: CO2 SYSTEM - ANDERSON POOL 42A | KUENTZEL, DOUGLAS A. | ESTIMATING | 2015-09-01 | CP: PROJECT CONTINGENCY | 042A | OPEN | 0 | 0 | 0 | 0
PJ0005368 | SR 16/17: CO2 SYSTEM - ANDERSON POOL 42A | KUENTZEL, DOUGLAS A. | ESTIMATING | 2015-09-01 | PM: SR 16/17: CO2 SYSTEM - ANDERSON POOL 42A | 042A | OPEN | 0 | 0 | 0 | 0
PJ0005368 | SR 16/17: CO2 SYSTEM - ANDERSON POOL 42A | KUENTZEL, DOUGLAS A. | ESTIMATING | 2015-09-01 | SM: SR 16/17: CO2 SYSTEM - ANDERSON POOL 42A | 042A | OPEN | 0 | 0 | 0 | 0
PJ0005368 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005367 | SR 16/17: EARTHQUAKE VALVE INSTALLATIONS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2015-09-01 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 5093.31 | 0 | 0 | 0
PJ0005367 | SR 16/17: EARTHQUAKE VALVE INSTALLATIONS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2015-09-01 | PL: PJ5367 EARTHQUAKE VALVES | GENERAL | OPEN | 50932.9265 | 0 | 1384.428 | 1384.428
PJ0005367 | SR 16/17: EARTHQUAKE VALVE INSTALLATIONS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2015-09-01 | PM: SR 16/17: EARTHQUAKE VALVE INSTALLATIONS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005367 | SR 16/17: EARTHQUAKE VALVE INSTALLATIONS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2015-09-01 | SM: SR 16/17: EARTHQUAKE VALVE INSTALLATIONS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005367 Total | [7 empty] | 56026.2365 | 0 | 1384.428 | 1384.428
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | AD: BOBS CRANE | GENERAL | CLOSED | 0 | 0 | 963 | 963
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | AD: DIGITAL ENERGY | GENERAL | CLOSED | 5243 | 0 | 5243 | 5243
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 667 | 0 | 0 | 0
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | IN: SR 16/17: WATER VALVE REPLACEMENTS - CAMPUS | GENERAL | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | LA: CLEAN-UP FOLLOWING WATER VALVE REPLACEMENTS - CAMPUS WIDE | GENERAL | CLOSED | 1601.28 | 0 | 140.112 | 140.112
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | PL: CAMPUS WATER SYSTEM UPGRADE STUDY | GENERAL | CLOSED | 17151.5016 | 0 | 15576.048 | 15576.048
PJ0005365 | DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | KOLEGRAFF, KENNETH | CLOSED | 2015-09-01 | PM: DM 16/17: ENGINEERING FOR WATER VALVE UPGRADES - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005365 Total | [7 empty] | 24874.7136 | 0 | 22098.77 | 22098.77
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | AD: JOC 16-039.008.00 NEWTON | 070 | OPEN | 69484.088 | 0 | 69484.088 | 69484.088
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | AD: NEWTON LVPW | 070 | OPEN | 1843.61 | 0 | 1843.61 | 1843.61
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | AD: NORTH COAST ENGINEERING | 070 | OPEN | 3521.37 | 0 | 3521.37 | 3521.37
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | CA: INSTALL RAIN GUTTER | 070 | LONG_TERM | 3064.8 | 0 | 0 | 0
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | CP: PROJECT CONTINGENCY | 070 | OPEN | 1446.18 | 0 | 0 | 0
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | ES: REMOVE SPACE HEATER | 070 | CLOSED | 393.984 | 0 | 0 | 0
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | IN: DM 16/17: PAVE CORP YARD IN FRONT OF EL SHOP (REPLACES 573 | 070 | ASSIGNED | 282.576 | 0 | 247.254 | 247.254
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | PL: CONNECT WATER SUPLY TO INDOOR DRINKING FOUNTAIN | 070 | COMPLETE | 257.952 | 0 | 373.296 | 373.296
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | PM: DM 16/17: PAVE CORPORATION YARD BY BLD 70 | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005364 | DM 16/17: PAVE CORP YARD IN FRONT OF ELECT. SHOP (REPLACES 5733) | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2015-09-01 | SM: DM 16/17: PAVE CORP YARD IN FRT OF ELEC SHOP (REPLACES 5733) | 070 | OPEN | 0 | 0 | 0 | 0
PJ0005364 Total | [7 empty] | 80294.56 | 0 | 75469.618 | 75469.618
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | AD: JOC 16.038.019 MAINO | GENERAL | CLOSED | 85912.3009 | 0 | 85912.3009 | 85912.3009
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | AD: STATE FIRE MARSHAL FEES(NO CHARGES) | GENERAL | CLOSED | 535 | 0 | 0 | 0
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | CA: PJ5363 SR 16/17: FALL PROTECTION PHASE 2 OF 6 - DUNN | GENERAL | CLOSED | 222.48 | 0 | 131.916 | 131.916
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 6160.9 | 0 | 0 | 0
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | IN: SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | GENERAL | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | LO: PJ5363 SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - DUNN | GENERAL | CLOSED | 60.924 | 0 | 54.462 | 54.462
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | PM: SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005363 | SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-09-01 | SM: SR 16/17: FALL PROTECTION, PHASE 2 OF 6 - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005363 Total | [7 empty] | 93174.1809 | 0 | 86169.3229 | 86169.3229
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | AD: CENTRAL COAST SPECIALTY | 033 | CLOSED | 1437 | 0 | 1537.59 | 1537.59
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | AD: JOC 16.037.025 MAINO | 033 | CLOSED | 16232.0926 | 0 | 16232.0926 | 16232.0926
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | AD: PMSM ARCHITECTS | 033 | CLOSED | 12438.75 | 0 | 11589.5766 | 11589.5766
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 5083.19 | 0 | 0 | 0
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | IN: SR 16/17: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | 033 | CLOSED | 423.864 | 0 | 176.61 | 176.61
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | PL: DEMO 2 TOILETS AND INSTALL (1) NEW ADA TOILET | 033 | CLOSED | 5984.9664 | 0 | 1400.204 | 1400.204
PJ0005362 | FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | LAMPMAN, GREG | CLOSED | 2015-09-01 | PM: FP 15/16: RETROFIT WOMEN'S RESTROOM TO ADA - BLD 33 RM 234 | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0005362 Total | [7 empty] | 41599.863 | 0 | 30936.0732 | 30936.0732
PJ0005361 | SR 16/17: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE II | LOOSLEY, SCOTT L. | CLOSED | 2015-09-01 | AD: IMPERIAL SPRINKLER | GENERAL | CLOSED | 0 | 0 | 25835.6529 | 25835.6529
PJ0005361 | SR 16/17: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE II | LOOSLEY, SCOTT L. | CLOSED | 2015-09-01 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 50000 | 0 | 0 | 0
PJ0005361 | SR 16/17: LANDSCAPE IRRIGATION CONTROL UPGRADE PHASE II | LOOSLEY, SCOTT L. | CLOSED | 2015-09-01 | LA: CALSENSE IRRIGATION CONTROL UPGRADE PHASE II | GENERAL | CLOSED | 0 | 0 | 4143.312 | 4143.312
PJ0005361 Total | [7 empty] | 50000 | 0 | 29978.9649 | 29978.9649
PJ0005360 | SR 16/17: REPLACE PURLINS IN SMALL SHED ROOF- BLD 18 | LAMPMAN, GREG | CLOSED | 2015-09-01 | AD: JOC 15.035.025 MAINO | 018 | CLOSED | 71981.789 | 0 | 71981.789 | 71981.789
PJ0005360 | SR 16/17: REPLACE PURLINS IN SMALL SHED ROOF- BLD 18 | LAMPMAN, GREG | CLOSED | 2015-09-01 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 8137.16 | 0 | 0 | 0
PJ0005360 | SR 16/17: REPLACE PURLINS IN SMALL SHED ROOF- BLD 18 | LAMPMAN, GREG | CLOSED | 2015-09-01 | EL: INSTALL SAVED LIGHT FIXTURES | 018 | CLOSED | 9180.0248 | 0 | 5114.556 | 5114.556
PJ0005360 | SR 16/17: REPLACE PURLINS IN SMALL SHED ROOF- BLD 18 | LAMPMAN, GREG | CLOSED | 2015-09-01 | IN: SR 16/17: REPLACE PURLINS SMALL SHED ROOF- BLD 18 | 018 | CLOSED | 211.932 | 0 | 317.898 | 317.898
PJ0005360 Total | [7 empty] | 89510.9058 | 0 | 77414.243 | 77414.243
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | AD: BOWEN ENVIRONMENTAL | 020 | CLOSED | 4815 | 0 | 3745 | 3745
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | AD: MCKENNA ENVIRONMENTAL | 020 | CLOSED | 3745 | 0 | 2184.94 | 2184.94
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 829.12 | 0 | 0 | 0
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | EH&S: (N/L) | 020 | CLOSED | 143.5406 | 0 | 0 | 0
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | IN: SR 15/16: LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | 020 | CLOSED | 157.5361 | 0 | 105.966 | 105.966
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | LA: PROVIDE WATER ACCESS AT BLDG. 20 ROOM 107A | 020 | CLOSED | 44.4355 | 0 | 40.032 | 40.032
PJ0005359 | LEAD CLEAN-UP - BLDG 20 - RM 107/107A & COURTYARD | MARCHESE, JASON (WILL) | CLOSED | 2015-08-31 | LO: RE-CORE DOORS FOR LEAD CLEAN-UP PROJECT - BLD 20 RM 107&107A | 020 | CLOSED | 60.924 | 0 | 60.924 | 60.924
PJ0005359 Total | [7 empty] | 9795.5563 | 0 | 6136.862 | 6136.862
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | AD: POWER ENGINEERING SERVICE | GENERAL | OPEN | 92084.2 | 1043.25 | 91040.95 | 92084.2
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 9723.84 | 0 | 0 | 0
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | EL: ARC FLASH ASSESSMENT (CORP ADMIN, BLDG 15) | GENERAL | OPEN | 132.7217 | 0 | 0 | 0
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | EL: ARC FLASH ASSESSMENT (DINING, BLDG 19) | GENERAL | OPEN | 389.1451 | 0 | 0 | 0
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | EL: ARC FLASH ASSESSMENT (STATE BLDGS, ZONE4) | GENERAL | OPEN | 4133.0562 | 0 | 0 | 0
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | EL: ARC FLASH ASSESSMENT (UU, BLDG 65) | GENERAL | OPEN | 499.317 | 0 | 0 | 0
PJ0005358 | SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | POLVI, STEVEN | PUNCH_LIST | 2015-08-27 | SM: SR 16/17: ARC FLASH STUDY 20% OF CAMPUS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005358 Total | [7 empty] | 106962.28 | 1043.25 | 91040.95 | 92084.2
PJ0005355 | SR 16/17: ELECTRICAL ASSESSMENT - BLDG 01 | POLVI, STEVEN | SCOPE_DEV | 2015-08-25 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005355 | SR 16/17: ELECTRICAL ASSESSMENT - BLDG 01 | POLVI, STEVEN | SCOPE_DEV | 2015-08-25 | PM: SR 16/17: ELECTRICAL ASSESSMENT - BLDG 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005355 | SR 16/17: ELECTRICAL ASSESSMENT - BLDG 01 | POLVI, STEVEN | SCOPE_DEV | 2015-08-25 | SM: SR 16/17: ELECTRICAL ASSESSMENT - BLDG 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005355 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005354 | SR 16/17: RECYCLING PROGRAM IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-08-25 | AD: ASAP REPROGRAPHICS | GENERAL | CLOSED | 0 | 0 | 296.4542 | 296.4542
PJ0005354 | SR 16/17: RECYCLING PROGRAM IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-08-25 | AD: EQUIPMENT | GENERAL | CLOSED | 61792.5 | 0 | 7580.6709 | 7580.6709
PJ0005354 | SR 16/17: RECYCLING PROGRAM IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-08-25 | AD: GUERILLA GARDENING | GENERAL | CLOSED | 5617.5 | 0 | 5617.5 | 5617.5
PJ0005354 | SR 16/17: RECYCLING PROGRAM IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-08-25 | AD: MARKETING/OUTREACH/PROGRAMS | GENERAL | CLOSED | 21935 | 0 | 7495.8422 | 7495.8422
PJ0005354 | SR 16/17: RECYCLING PROGRAM IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-08-25 | AD: WASTE CONNECTIONS-SLO GARBAGE | GENERAL | CLOSED | 0 | 0 | 38297.8466 | 38297.8466
PJ0005354 | SR 16/17: RECYCLING PROGRAM IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-08-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005354 Total | [7 empty] | 89345 | 0 | 59288.3139 | 59288.3139
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | CA: ASSIST PLUMBERS WITH FIXTURE RETROFITS | GENERAL | CLOSED | 4847.28 | 0 | 1273.8571 | 1273.8571
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 8373.15 | 0 | 0 | 0
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | CU: CLEAN TAPE RESIDUE FROM TOWEL & SOAP DISPENSERS - SCI NORTH | GENERAL | CLOSED | 1639.68 | 0 | 0 | 0
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | EH&S: | GENERAL | CLOSED | 347.472 | 0 | 0 | 0
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | IN: SR 16/17: LOW FLOW PLUMBING RETROFITS | GENERAL | CLOSED | 565.152 | 0 | 70.644 | 70.644
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | PL: REPLACE FIXTURES IN LIBRARY, SCIENCE NORTH, AND FISHER | GENERAL | CLOSED | 94369.2689 | 0 | 88546.7666 | 88546.7666
PJ0005353 | SR 16/17: LOW FLOW PLUMBING RETROFITS | GONZALES, ALBERT | CONST_COMP | 2015-08-25 | SM: SR 16/17: LOW FLOW PLUMBING RETROFITS | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005353 Total | [7 empty] | 110142.0029 | 0 | 89891.2676 | 89891.2676
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | AD: JOC 16.037.024 MAINO | 046 | CLOSED | 69470.4669 | 0 | 71615.0144 | 71615.0144
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | AD: PMSM | 046 | CLOSED | 11609.5 | 0 | 11268.5552 | 11268.5552
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 7797.07 | 0 | 0 | 0
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | EL: BLDG. 46-100- GREG LAMPMAN- CONTRACTOR SUPPORT | 046 | CLOSED | 1537.416 | 0 | 788.034 | 788.034
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | IN: FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | 046 | CLOSED | 494.508 | 0 | 600.474 | 600.474
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | LO: BLDG. 46-100- GREG LAMPMAN- INSTALL LOCKS | 046 | CLOSED | 1150.0656 | 0 | 657.884 | 657.884
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | PA: BLDG. 46-100- GREG LAMPMAN- PAINT NEW RESTROOM | 046 | CLOSED | 1961.976 | 0 | 858.354 | 858.354
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | PL: BLDG. 46-100- GREG LAMPMAN- CONTRACTOR SUPPORT | 046 | CLOSED | 644.88 | 0 | 212.832 | 212.832
PJ0005352 | FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | LAMPMAN, GREG | CLOSED | 2015-08-25 | PM: FP 15/16: DESIGN & DEVELOP ADA RESTROOM - BLD 46A NATATORIUM | 046 | CLOSED | 0 | 0 | 0 | 0
PJ0005352 Total | [7 empty] | 94665.8825 | 0 | 86001.1476 | 86001.1476
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: A-TOWN AUDIO VIDEO | 117T | CLOSED | 4504.6037 | 0 | 4504.6037 | 4504.6037
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: FLOOR CONNECTION | 117T | CLOSED | 25644.69 | 0 | 25644.69 | 25644.69
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: JOC 15.035.015 MAINO | 117T | CLOSED | 57815.845 | 0 | 51484.8904 | 51484.8904
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: JOC 16.038.010 MAINO | 117T | CLOSED | 9408.7133 | 0 | 9511.6901 | 9511.6901
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: MAINO LVPW | 117T | CLOSED | 2894.35 | 0 | 2894.35 | 2894.35
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: QUAGLINO ROOFING | 117T | CLOSED | 5162.75 | 0 | 5162.75 | 5162.75
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: SHORELINE | 117T | CLOSED | 2235.23 | 0 | 2235.23 | 2235.23
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: STATE FIRE MARSHAL FEES | 117T | CLOSED | 1070 | 0 | 1875.1857 | 1875.1857
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: THOMA ELECTRIC | 117T | CLOSED | 2081.15 | 0 | 2081.15 | 2081.15
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: TRI COUNTY OFFICE FURNITURE | 117T | CLOSED | 1712 | 0 | 1712 | 1712
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | AD: WAREHOUSE PARTS TO BE INSTALLED BY JOC | 117T | CLOSED | 240 | 0 | 200.0867 | 200.0867
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | ANTS: ALARMS TESTING FOR NEW PANEL AT MODULAR 117T | 117T | CLOSED | 203.328 | 0 | 237.216 | 237.216
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | CP: PROJECT CONTINGENCY | 117T | CLOSED | 333.08 | 0 | 0 | 0
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | EL: DEMO, MOVE LIGHT FIXTURES AND NEW ELECTRICAL | 117T | CLOSED | 6401.8576 | 0 | 12923.3779 | 12923.3779
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | IN: FR5351, REFRESH AND MODIFICATION OF TRAILER: BLDG 117T | 117T | CLOSED | 706.44 | 0 | 918.372 | 918.372
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | LO: MOVE AND INSTALL LOCKS AS PER PLANS | 117T | CLOSED | 2350.7214 | 0 | 2030.432 | 2030.432
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | PA: PAINT AND PATCH AS NEEDED THE ENTIRE INSIDE | 117T | CLOSED | 7911.6692 | 0 | 7298.532 | 7298.532
PJ0005351 | REFRESH AND MODIFY TRAILER: BLDG 117T | LAMPMAN, GREG | CLOSED | 2015-08-10 | PL: INSTALL NEW URINAL AND MOVE SINK | 117T | CLOSED | 5881.3716 | 0 | 6419.16 | 6419.16
PJ0005351 Total | [7 empty] | 136557.7998 | 0 | 137133.7165 | 137133.7165
PJ0005350 | CUT UP & DISPOSE OF RETIRED SOCCER GOALS: BLDG 163 | HICKS, MICHAEL | CLOSED | 2015-08-12 | CA:CUT UP & DISPOSE OF OLD SOCCER/LACROSSE GOALS | 163 | CLOSED | 1038.5922 | 0 | 1317.756 | 1317.756
PJ0005350 | CUT UP & DISPOSE OF RETIRED SOCCER GOALS: BLDG 163 | HICKS, MICHAEL | CLOSED | 2015-08-12 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 131.87 | 0 | 0 | 0
PJ0005350 | CUT UP & DISPOSE OF RETIRED SOCCER GOALS: BLDG 163 | HICKS, MICHAEL | CLOSED | 2015-08-12 | EH&S: CUT UP & DISPOSE OF RETIRED SOCCER GOALS: BLDG 163 | 163 | CLOSED | 128.736 | 0 | 0 | 0
PJ0005350 | CUT UP & DISPOSE OF RETIRED SOCCER GOALS: BLDG 163 | HICKS, MICHAEL | CLOSED | 2015-08-12 | IN: CUT UP & DISPOSE OF RETIRED SOCCER GOALS: BLDG 163, | 163 | CLOSED | 157.5361 | 0 | 141.288 | 141.288
PJ0005350 Total | [7 empty] | 1456.7343 | 0 | 1459.044 | 1459.044
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: BKM OFFICE FURNITURE | 001 | CLOSED | 54695.2756 | 0 | 56965.1522 | 56965.1522
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: BOWEN ENVIRONMENTAL | 001 | CLOSED | 8255.05 | 0 | 8255.05 | 8255.05
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: CAME SECURITY | 001 | CLOSED | 2407.5 | 0 | 2059.75 | 2059.75
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: FLOOR CONNECTION | 001 | CLOSED | 8784.7 | 0 | 8784.7 | 8784.7
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: JL FASULO | 001 | CLOSED | 6420 | 0 | 5584.33 | 5584.33
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: PRIOR INDUSTRIES | 001 | CLOSED | 4423.5298 | 0 | 4423.5298 | 4423.5298
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: RICK MCKENNA | 001 | CLOSED | 3424 | 0 | 2969.25 | 2969.25
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: SANTA MARIA ACOUSTICAL | 001 | CLOSED | 2675 | 0 | 1619.98 | 1619.98
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | AD: STATE FIRE MARSHAL | 001 | CLOSED | 802.5 | 0 | 1968.5432 | 1968.5432
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | CA: INSTALL TV & FURNITURE | 001 | CLOSED | 619.0506 | 0 | 542.502 | 542.502
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 574.34 | 0 | 0 | 0
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | EL: NEW ELECTRICAL FOR KITCHEN | 001 | CLOSED | 4067.6903 | 0 | 4999.824 | 4999.824
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | ES: SHUT DOWN HVAC (N/L) | 001 | CLOSED | 511.5226 | 0 | 0 | 0
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | IN: REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | 001 | CLOSED | 565.152 | 0 | 317.898 | 317.898
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | ITS: RELOCATE DATA LINE | 001 | CLOSED | 535 | 0 | 452.396 | 452.396
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | LO: REMOVE LOCKS | 001 | CLOSED | 135.8605 | 0 | 121.848 | 121.848
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | PA: PAINT WALLS | 001 | CLOSED | 3655.5251 | 0 | 3111.48 | 3111.48
PJ0005349 | REMODEL - OFFICE OF THE VICE PRESIDENT: BLDG 01 RM 116 | NORTON, DAVE | CLOSED | 2015-08-10 | PL: INSTALL SINK | 001 | CLOSED | 4644.3041 | 0 | 4812.096 | 4812.096
PJ0005349 Total | [7 empty] | 107196.0005 | 0 | 106988.3292 | 106988.3292
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | AD: ENGLEKIRK & SABOL | 043A | OPEN | 1774.06 | 1774.06 | 0 | 1774.06
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | AD: GOSS ENGINEERING | 043A | OPEN | 39927.05 | 13920.7 | 24401.35 | 38322.05
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | AD: KBZ ARCHITECTS - ROOF DESIGN | 043A | OPEN | 28890 | 20865 | 0 | 20865
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | AD: PURCHASE AHU UNIT DMG CORP (CONTRACTOR TO INSTALL) | 043A | OPEN | 68854.5 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | AD: STATE FIRE MARSHAL FEES | 043A | OPEN | 267.5 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | AD: WILDAN | 043A | OPEN | 1605 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | CP: PROJECT CONTINGENCY | 043A | OPEN | 12492.57 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | CPE: | 043A | OPEN | 577.8432 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | EL: | 043A | OPEN | 566.9664 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | ES: | 043A | OPEN | 577.8432 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | IN: SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | 043A | ASSIGNED | 1398.7512 | 0 | 70.644 | 70.644
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | PM: SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | 043A | OPEN | 0 | 0 | 0 | 0
PJ0005345 | SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | ULM, AARON | DESIGN | 2015-08-21 | SM: SR 16/17: REPLACE DX ROOFTOP AIR HANDLER - BLD 43A | 043A | OPEN | 0 | 0 | 0 | 0
PJ0005345 Total | [7 empty] | 156932.084 | 36559.76 | 24471.994 | 61031.754
PJ0005343 | INSTALL CARPETING - BLD 40 RMS 110, 113 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-07-28 | AD: FLOOR CONNECTION | 040 | CLOSED | 11170.8 | 0 | 8115.95 | 8115.95
PJ0005343 | INSTALL CARPETING - BLD 40 RMS 110, 113 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-07-28 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 1191.62 | 0 | 0 | 0
PJ0005343 | INSTALL CARPETING - BLD 40 RMS 110, 113 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-07-28 | CU: FLOOR PREP FOR CARPET | 040 | CLOSED | 745.5319 | 0 | 304.392 | 304.392
PJ0005343 Total | [7 empty] | 13107.9519 | 0 | 8420.342 | 8420.342
PJ0005341 | SR 16/17: ENERGY METERING REPAIRS/UPGRADES - (DESIGN ONLY) | ELLIOT, DENNIS K | DESGN_COMP | 2015-08-17 | AD: DIGITAL ENERGY | GENERAL | CLOSED | 72760 | 0 | 56025.2 | 56025.2
PJ0005341 | SR 16/17: ENERGY METERING REPAIRS/UPGRADES - (DESIGN ONLY) | ELLIOT, DENNIS K | DESGN_COMP | 2015-08-17 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 7276 | 0 | 0 | 0
PJ0005341 | SR 16/17: ENERGY METERING REPAIRS/UPGRADES - (DESIGN ONLY) | ELLIOT, DENNIS K | DESGN_COMP | 2015-08-17 | SM: SR 16/17: ENERGY METERING REPAIRS/UPGRADES - (DESIGN ONLY) | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005341 Total | [7 empty] | 80036 | 0 | 56025.2 | 56025.2
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | AD: ARC ALTERNATIVES | GENERAL | OPEN | 30511.05 | 10464.6 | 20046.45 | 30511.05
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | AD: CHINOOK WINDS | GENERAL | OPEN | 21400 | 88.81 | 21311.19 | 21400
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | AD: ECOSHIFT | GENERAL | OPEN | 28312.2 | 2321.9 | 25990.3 | 28312.2
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | AD: HARTMAN ENGINEERING | GENERAL | OPEN | 155891.51 | 139861.6902 | 16029.8198 | 155891.51
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | AD: INTEGRAL GROUP | GENERAL | OPEN | 10571.6 | 0 | 10571.6 | 10571.6
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 15468.03 | 0 | 0 | 0
PJ0005340 | SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | ELLIOT, DENNIS K | IN_CONSTR | 2015-08-17 | SM: SR 16/17: DEVELOP RENEWABLE ENERGY RFP - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005340 Total | [7 empty] | 262154.39 | 152737.0002 | 93949.3598 | 246686.36
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: ASAP REPROGRAPHICS | 042 | CLOSED | 0 | 0 | 24.9631 | 24.9631
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: DAHL INSULATION | 042 | CLOSED | 0 | 0 | 535 | 535
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: HPS MECHANICAL | 042 | CLOSED | 2942.5 | 0 | 2942.5 | 2942.5
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: ITS | 042 | CLOSED | 3959 | 0 | 1979.5 | 1979.5
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: JL FASULO DRYWALL | 042 | CLOSED | 4661.99 | 0 | 4661.99 | 4661.99
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: JOC 15.036.028 STAPLES | 042 | CLOSED | 246535.49 | 0 | 242005.1207 | 242005.1207
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: MCKENNA | 042 | CLOSED | 5590.75 | 0 | 5590.75 | 5590.75
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: STATE FIRE MARSHAL FEES | 042 | CLOSED | 572.45 | 0 | 130.4865 | 130.4865
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | AD: THOMA | 042 | CLOSED | 3745 | 0 | 3745 | 3745
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 19746.83 | 0 | 0 | 0
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | CU: Final Cleaning Mott Gym Lobby & Corridor | 042 | CLOSED | 736.824 | 0 | 764.226 | 764.226
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | ES: PROJECT SUPPORT - MOTT GYM VIC GASKET REPAIR | 042 | CLOSED | 866.7648 | 0 | 1993.032 | 1993.032
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | IN: SR 16/17: UPDATE HVAC, CEILING HAZMAT, VALVE LEAKS - MOTT 42 | 042 | CLOSED | 423.864 | 0 | 353.22 | 353.22
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | LO: Support & Installation of Orange Cores | 042 | CLOSED | 67.0164 | 0 | 304.62 | 304.62
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | PA:BLDG 42 PAINT ALL WALLS 1ST FLOOR LOBBY AND CORRIDOR | 042 | CLOSED | 5966.916 | 0 | 3409.2 | 3409.2
PJ0005339 | SR 16/17: UPDATE HVAC, CEILING HAZMAT, LEAKING VALVES - MOTT 42 | KOLEGRAFF, KENNETH | CLOSED | 2015-08-17 | PL: Support for Existing Plumbing in Ceiling During Demolition | 042 | CLOSED | 70.9368 | 0 | 9201.24 | 9201.24
PJ0005339 Total | [7 empty] | 295886.332 | 0 | 277640.8483 | 277640.8483
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | AD: JOC 16.037.026 MAINO | 035 | CLOSED | 98366.491 | 0 | 98366.491 | 98366.491
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | AD: PMSM | 035 | CLOSED | 10914 | 0 | 10145.0766 | 10145.0766
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 11260.3 | 0 | 0 | 0
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | EL: SUPPORT FOR ELECTRIAL WORK ONLY | 035 | CLOSED | 1537.416 | 0 | 7971.468 | 7971.468
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | IN: SR 16/17: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | 035 | CLOSED | 989.016 | 0 | 671.118 | 671.118
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | LO: INSTALL NEW LOCKS AS PER PLANS | 035 | CLOSED | 2300.1312 | 0 | 1840.95 | 1840.95
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | PA: PAINT AS NEEDED WALLS AND CEILINGS 9/13 | 035 | CLOSED | 2642.964 | 0 | 2790.348 | 2790.348
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | PL: DEMO EXISTING FIXTURES AND INSTALL NEW. | 035 | CLOSED | 19630.5329 | 0 | 27957.9015 | 27957.9015
PJ0005338 | FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | LAMPMAN, GREG | CLOSED | 2015-08-17 | PM: FP 15/16: REMODEL RESTROOMS ADA - KEN 35 RMS 115 & 116 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005338 Total | [7 empty] | 147640.8511 | 0 | 149743.3531 | 149743.3531
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | AD: JOC 16.037.016 MAINO | STREETS | CLOSED | 236870.6294 | 0 | 236870.6294 | 236870.6294
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | AD: NORTH COAST ENGINEERING | STREETS | CLOSED | 0 | 0 | 2504.228 | 2504.228
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 4381.7 | 0 | 0 | 0
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | IN: SR 16/17:DESIGN/CONSTRUCT NEW INTERSECTION -VLG DR & TRUCKEE | STREETS | CLOSED | 565.152 | 0 | 529.83 | 529.83
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | LA: PROVIDE CONTRACTOR SUPPORT AT TRUCKEE AND VILLAGE WAY | STREETS | CLOSED | 2801.28 | 0 | 2593.7446 | 2593.7446
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | PL: SUPPOR FOR NEW INTERSECTION AT VILLAGE DR & TRUCKEE | STREETS | CLOSED | 644.88 | 0 | 1909.74 | 1909.74
PJ0005337 | SR 15/16:DESIGN/CONSTRUCT NEW INTERSECTION -VILLAGE DR & TRUCKEE | LAMPMAN, GREG | CLOSED | 2015-08-17 | PM: SR 16/17:DESIGN/CONSTRUCT NEW INTERSECTION-VILLAGE &TRUCKEE | STREETS | CLOSED | 0 | 0 | 0 | 0
PJ0005337 Total | [7 empty] | 245263.6414 | 0 | 244408.172 | 244408.172
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: ASAP | GENERAL | OPEN | 214 | 0 | 55.7684 | 55.7684
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: BOB'S CRANE | GENERAL | OPEN | 1284 | 0 | 0 | 0
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: CANNON | GENERAL | OPEN | 8051.75 | 453.9475 | 7597.8025 | 8051.75
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: DIGITAL ENERGY | GENERAL | OPEN | 52194.6 | 26444.4615 | 25750.1385 | 52194.6
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: EARTH SYSTEMS PACIFIC | GENERAL | OPEN | 9523 | 4280 | 5243 | 9523
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: G.F. GARCIA AND SONS | GENERAL | OPEN | 4815 | 0 | 4815 | 4815
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: GARCIA AND SONS | GENERAL | OPEN | 11770 | 0 | 5164.355 | 5164.355
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | AD: STATE FIRE MARSHAL FEES | GENERAL | OPEN | 0 | 0 | 637.3776 | 637.3776
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | CA: CAULK AND REGROUT UTILIDOR LIDS | GENERAL | CLOSED | 1523.64 | 0 | 2267.862 | 2267.862
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 8321.15 | 0 | 0 | 0
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | CPE: MARK UTILITIES FOR POTHOLING | GENERAL | OPEN | 288.9216 | 0 | 131.328 | 131.328
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | EH&S: SR 16/17: REPLACE WATERLINES & HYDRANTS | GENERAL | OPEN | 70.8048 | 0 | 0 | 0
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | EL: MARK UTILITIES FOR POTHOLING | GENERAL | CLOSED | 283.4832 | 0 | 0 | 0
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | ES: MARK UTILITIES FOR POTHOLING | GENERAL | CLOSED | 144.4608 | 0 | 0 | 0
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | IN: SR 16/17: REPLACE WATERLINES & HYDRANTS | GENERAL | ASSIGNED | 211.932 | 0 | 70.644 | 70.644
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | LA: MARK UTILITIES AND PROVIDE SUPPORT | GENERAL | COMPLETE | 264.2112 | 0 | 551.4155 | 551.4155
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | PL: REPLACE PRV AT VISTA GRANDE WATER MAIN | GENERAL | OPEN | 241213.4818 | 0 | 118962.8959 | 118962.8959
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | PM: DM 16/17: WATER LINE AND VALVE UPGRADES | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005335 | DM 16/17: WATER LINE AND VALVE UPGRADES | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-08-17 | SM: DM 16/17: WATER LINE AND VALVE UPGRADES | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005335 Total | [7 empty] | 340174.4354 | 31178.409 | 171247.5874 | 202425.9964
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | AD: JOC 15.036.013 STAPLES | 003 | CLOSED | 20921.2178 | 0 | 20921.2178 | 20921.2178
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | AD: MEATHEAD MOVERS | 003 | CLOSED | 410.88 | 0 | 410.88 | 410.88
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | CA: RE-INSTALL BULLETIN BOARD | 003 | CLOSED | 143.4996 | 0 | 183.564 | 183.564
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1700.57 | 0 | 0 | 0
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | EL: INSTALL AND LABEL OUTLET COVERS - BLDG. 03 RMS. 408 & 409 | 003 | CLOSED | 134.856 | 0 | 132.936 | 132.936
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | ES: REMOVE/REINSTALL HEATERS -BLDG. 03, RMS. 402-409 ON 11/30/15 | 003 | CLOSED | 8228.5901 | 0 | 10929.024 | 10929.024
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | IN: SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | 003 | CLOSED | 628.7316 | 0 | 459.186 | 459.186
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | MO: MOVE/REMOVE FURNITURE BLDG. 03, RMS. 402-409 on 11/30/2015 | 003 | CLOSED | 134.064 | 0 | 107.046 | 107.046
PJ0005332 | SR 15/16: MOLD REMEDIATION IN OFFICES - BLD 3 RMS 402-409 | DUNN, TRAVIS | CLOSED | 2015-08-12 | PA: PRIME AND PAINT 003/402-409 STARTING ON 12/11/15 | 003 | CLOSED | 2804.5439 | 0 | 1827.176 | 1827.176
PJ0005332 Total | [7 empty] | 35106.953 | 0 | 34971.0298 | 34971.0298
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | AD: COURTS & GREENS LVPW | 042 | CLOSED | 4012.5 | 0 | 2996 | 2996
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 921.8 | 0 | 0 | 0
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | EH&S: HAZARDOUS WASTE DISPOSAL COSTS | 042 | CLOSED | 0 | 0 | 171.2 | 171.2
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | EH&S: SAMPLING FOR WRESTLING LIGHT REMOVAL PROJECT | 042 | CLOSED | 263.5406 | 0 | 257.472 | 257.472
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | EL: (NL) - SEE PJ#5265 WO0754742 | 042 | CLOSED | 5501.8576 | 0 | 0 | 0
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | IN: SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | 042 | CLOSED | 314.3658 | 0 | 176.61 | 176.61
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | LO: ACCESS TO MOTT GYM | 042 | CLOSED | 135.8605 | 0 | 30.462 | 30.462
PJ0005331 | SR 15/16: REMOVE WRESTLING LIGHT & COMPONENTS: BLDG 42-102 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-11 | MO: MOVE CONSTRUCTION DEBRIS | 042 | CLOSED | 100.548 | 0 | 25.353 | 25.353
PJ0005331 Total | [7 empty] | 11250.4725 | 0 | 3657.097 | 3657.097
PJ0005330 | INSTALL BIRD NETTING ABOVE WALL - BLD 34 RM 128G | DUNN, TRAVIS | CLOSED | 2015-07-22 | AD: AVIARY MANAGEMENT PROFESSIONALS | 034 | CLOSED | 5752.9192 | 0 | 5752.9192 | 5752.9192
PJ0005330 | INSTALL BIRD NETTING ABOVE WALL - BLD 34 RM 128G | DUNN, TRAVIS | CLOSED | 2015-07-22 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 430.71 | 0 | 0 | 0
PJ0005330 | INSTALL BIRD NETTING ABOVE WALL - BLD 34 RM 128G | DUNN, TRAVIS | CLOSED | 2015-07-22 | IN: INSTALL BIRD NETTING ABOVE WALL - BLD 34 RM 128G | 034 | CLOSED | 155.4168 | 0 | 105.966 | 105.966
PJ0005330 | INSTALL BIRD NETTING ABOVE WALL - BLD 34 RM 128G | DUNN, TRAVIS | CLOSED | 2015-07-22 | LA: TRIM TREE | 034 | CLOSED | 160.128 | 0 | 40.032 | 40.032
PJ0005330 Total | [7 empty] | 6499.174 | 0 | 5898.9172 | 5898.9172
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: ASAP REPROGRAPHICS | 001 | OPEN | 0 | 0 | 187.7208 | 187.7208
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: CAME SECURITY | 001 | OPEN | 2969.25 | 0 | 2969.25 | 2969.25
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: ENGLEKIRK & SABOL | 001 | OPEN | 1605 | 0 | 1123.5 | 1123.5
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: FLOOR CONNECTION | 001 | OPEN | 1712 | 0 | 2156.05 | 2156.05
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: ITS | 001 | OPEN | 2033 | 0 | 1974.257 | 1974.257
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: JOC 16.037.008 MAINO | 001 | OPEN | 198640.3105 | 0 | 198760.632 | 198760.632
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: MCKENNA | 001 | OPEN | 6099 | 0 | 6097.93 | 6097.93
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: PMSM ARCHITECTS | 001 | OPEN | 23513.25 | 0 | 22753.55 | 22753.55
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | AD: STATE FIRE MARSHAL FEES | 001 | OPEN | 1605 | 0 | 498.5344 | 498.5344
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | ANTS: ALARMS PROGRAMMING FOR REGRISTRAR'S OFFICE | 001 | OPEN | 135.552 | 0 | 0 | 0
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | CA: CARPENTER SUPPORT FOR PROJECT | 001 | CLOSED | 2687.28 | 0 | 0 | 0
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | CP: PROJECT CONTINGENCY | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | EL: ELECTRICAL SUPPORT AND SAFE OFF WORK | 001 | CLOSED | 2567.8656 | 0 | 3880.512 | 3880.512
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | ES: ASSIST JOC CONTRACTOR | 001 | CLOSED | 1443.456 | 0 | 1019.658 | 1019.658
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | IN: REMODEL FRONT DESK: BLDG 01 RM 221 | 001 | CLOSED | 1130.304 | 0 | 635.796 | 635.796
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | LO: ORANGE CORE | 001 | ASSIGNED | 134.0328 | 0 | 304.62 | 304.62
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | PA: BLDG 1 RM 221 PAINT WALLS | 001 | CLOSED | 2522.964 | 0 | 1551.972 | 1551.972
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | PM: REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005329 | REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | NORTON, DAVE | CONST_COMP | 2015-07-14 | SM: REMODEL FRONT DESK AT REGISTRAR'S OFFICE: BLDG 01 RM 221 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0005329 Total | [7 empty] | 248798.2649 | 0 | 243913.9822 | 243913.9822
PJ0005328 | INSTALL WINDOWS IN DOORS - BLD 11 RM 204, 205, 207, 208 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-03 | AD: STATE FIRE MARSHAL FEES | 011 | CLOSED | 1337.5 | 0 | 945.0668 | 945.0668
PJ0005328 | INSTALL WINDOWS IN DOORS - BLD 11 RM 204, 205, 207, 208 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-03 | CA: REPLACE RATED DOORS | 011 | CLOSED | 10328.7654 | 0 | 9140.415 | 9140.415
PJ0005328 | INSTALL WINDOWS IN DOORS - BLD 11 RM 204, 205, 207, 208 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-03 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 1345.76 | 0 | 0 | 0
PJ0005328 | INSTALL WINDOWS IN DOORS - BLD 11 RM 204, 205, 207, 208 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-03 | IN: INSTALL WINDOWS IN DOORS - BLD 11 RM 204, 205, 207, 208, | 011 | CLOSED | 314.3658 | 0 | 176.61 | 176.61
PJ0005328 | INSTALL WINDOWS IN DOORS - BLD 11 RM 204, 205, 207, 208 | MARCHESE, JASON (WILL) | CLOSED | 2015-08-03 | LO: EXCHANGE DOOR HARDWARE | 011 | CLOSED | 1476.1682 | 0 | 1005.3 | 1005.3
PJ0005328 Total | [7 empty] | 14802.5594 | 0 | 11267.3918 | 11267.3918
PJ0005326 | SR 15/16: REPLACE HOT WATER VALVES AT HEALTH CENTER | KOLEGRAFF, KENNETH | CLOSED | 2015-08-10 | AD: GARCIA & SONS | 027 | CLOSED | 6420 | 0 | 6420 | 6420
PJ0005326 | SR 15/16: REPLACE HOT WATER VALVES AT HEALTH CENTER | KOLEGRAFF, KENNETH | CLOSED | 2015-08-10 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 2265.36 | 0 | 0 | 0
PJ0005326 | SR 15/16: REPLACE HOT WATER VALVES AT HEALTH CENTER | KOLEGRAFF, KENNETH | CLOSED | 2015-08-10 | EL: Support and Mark Utilities | 027 | CLOSED | 71.5151 | 0 | 0 | 0
PJ0005326 | SR 15/16: REPLACE HOT WATER VALVES AT HEALTH CENTER | KOLEGRAFF, KENNETH | CLOSED | 2015-08-10 | IN: SR 15/16: REPL. HOT WATER VALVES AT HEALTH CENTER | 027 | CLOSED | 353.22 | 0 | 141.288 | 141.288
PJ0005326 | SR 15/16: REPLACE HOT WATER VALVES AT HEALTH CENTER | KOLEGRAFF, KENNETH | CLOSED | 2015-08-10 | PL: MARK UTIILTIES AND PROVIDE SUPPORT | 027 | CLOSED | 1435.5029 | 0 | 13.392 | 13.392
PJ0005326 Total | [7 empty] | 10545.598 | 0 | 6574.68 | 6574.68
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: CAL POLY FACILITIES BUILDING PERMIT FEES | GENERAL | CLOSED | 3293.57 | 0 | 3293.57 | 3293.57
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: CAL POLY FACILITIES PLAN REVIEW FEES | GENERAL | CLOSED | 1326.28 | 0 | 1326.28 | 1326.28
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: EARTH SYSTEMS | GENERAL | CLOSED | 1540.8 | 0 | 971.56 | 971.56
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: ENGLEKIRK & SABOL | GENERAL | CLOSED | 2140 | 0 | 2140 | 2140
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: GARCIA AND SONS | GENERAL | CLOSED | 2675 | 0 | 2675 | 2675
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: ITS | GENERAL | CLOSED | 2675 | 0 | 2040.1048 | 2040.1048
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: PLCS PLUS (SCADA) | GENERAL | CLOSED | 1203.75 | 0 | 1203.75 | 1203.75
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: SHIPPING AND PRINTING SERVICES | GENERAL | CLOSED | 199.234 | 0 | 254.2534 | 254.2534
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: STATE FIRE MARSHAL | GENERAL | CLOSED | 2140 | 0 | 1988.2526 | 1988.2526
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | AD: WILDAN, PLAN REVIEW | GENERAL | CLOSED | 1605 | 0 | 1605 | 1605
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | CA: DETACH BIKE RACKS | GENERAL | CLOSED | 111.24 | 0 | 194.67 | 194.67
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | CA:SHAKE SMART CORING AND PLASTIC TAGS FOR ELECTRICAL PANELS | GENERAL | CLOSED | 444.96 | 0 | 748.632 | 748.632
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 3224.01 | 0 | 0 | 0
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | EL:UNDERGROUND AND EQUIP FOR SHAKE SMART | GENERAL | CLOSED | 37403.7203 | 0 | 30451.368 | 30451.368
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | IN: (MAINT) CONSTRUCT NEW JUICE KIOSK NEAR NW CORNER - BLD 43A | GENERAL | CLOSED | 0 | 0 | 1589.49 | 1589.49
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | LA:REPAIR / REPLACE LANDSCAPE AND IRRIGATION AT 43A | GENERAL | CLOSED | 4057.6896 | 0 | 1209.4832 | 1209.4832
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | PL:SHAKE SMART OBSERVATION | GENERAL | CLOSED | 2837.472 | 0 | 1157.352 | 1157.352
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | PM: CONSTRUCT NEW JUICE KIOSK NEAR NW CORNER OF 43A | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005324 | TI: CONSTRUCT JUICE KIOSK NEAR NW CORNER (SHAKESMART) - BLD 43A | DILLON, JEFFREY | CONST_COMP | 2015-07-31 | SM: TI: CONSTRUCT JUICE KIOSK NEAR NW COR. (SHAKESMART)- BLD 43A | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005324 Total | [7 empty] | 66877.7259 | 0 | 52848.766 | 52848.766
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | AD: J.L. FASULO DRYWALL | 043 | CLOSED | 1073.21 | 0 | 1073.21 | 1073.21
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | AD: KNECHTS HEATING AND AIR | 043 | CLOSED | 1070 | 0 | 471.87 | 471.87
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | AD: STATE FIRE MARSHAL | 043 | CLOSED | 160.5 | 0 | 417.3 | 417.3
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | AD: TOMARK SPORTS (BSN SPORTS) | 043 | CLOSED | 29960 | 0 | 29275.2 | 29275.2
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | CA: DEMO WALL PADDING, REPLACE DRYWALL | 043 | CLOSED | 8018.2476 | 0 | 5163.6001 | 5163.6001
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 1949.14 | 0 | 0 | 0
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | EL: REPLACE RECEPTACLES AND TRIMS | 043 | CLOSED | 573.4092 | 0 | 225.498 | 225.498
PJ0005321 | REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-28 | IN: REMOVE WALL MATS AND REPAIR WALL - REC 43 RM 192 | 043 | CLOSED | 314.3658 | 0 | 211.932 | 211.932
PJ0005321 Total | [7 empty] | 43118.8726 | 0 | 36838.6101 | 36838.6101
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | AD: ITS | 074D | OPEN | 4280 | 0 | 0 | 0
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | AD: JOC 16.041 MAINO | 074D | OPEN | 77057.3982 | 0 | 62776.9642 | 62776.9642
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | AD: STATE FIRE MARSHAL | 074D | OPEN | 695.5 | 0 | 558.9894 | 558.9894
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | CP: PROJECT CONTINGENCY | 074D | OPEN | 9249.36 | 0 | 0 | 0
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | CPE:J. DILLON PM, EOC REMODEL BLDG. 74D | 074D | COMPLETE | 16914.432 | 0 | 9078.849 | 9078.849
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | CU:J. DILLON PM- EOC REMODEL, BLDG. 74D | 074D | OPEN | 294.7296 | 0 | 0 | 0
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | EL:J. DILLON PM- EOC REMODEL , BLDG 74 | 074D | CLOSED | 11069.664 | 0 | 11335.482 | 11335.482
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | IN: UPGRADE/RENOVATE EOC GARAGE - BLD 74D | 074D | CLOSED | 423.864 | 0 | 282.576 | 282.576
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | LO:J DILLON PM- EOC REMODEL, BLDG. 74D | 074D | CLOSED | 2190.0984 | 0 | 2015.616 | 2015.616
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | PA:J DILLON PM EOC REMODEL BLDG. 74D | 074D | CLOSED | 3323.952 | 0 | 2757.372 | 2757.372
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | PM: UPGRADE/RENOVATE EOC GARAGE - BLD 74D | 074D | OPEN | 0 | 0 | 0 | 0
PJ0005319 | UPGRADE/RENOVATE EOC GARAGE - BLD 74D | DILLON, JEFFREY | CONST_COMP | 2015-07-20 | SM: UPGRADE/RENOVATE EOC GARAGE - BLD 74D | 074D | OPEN | 0 | 0 | 0 | 0
PJ0005319 Total | [7 empty] | 125498.9982 | 0 | 88805.8486 | 88805.8486
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | AD: BOWEN ENGINEERING & ENVIRONMENTAL | 065 | CLOSED | 3251.8156 | 0 | 3251.73 | 3251.73
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | AD: COASTAL JANITORIAL(POSTED IN ERROR-SB PJ#5394-SEE TASK NOTE) | 065 | CLOSED | 0 | 0 | 90.95 | 90.95
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | AD: FIT (REMOVE, REPLACE FURNITURE) | 065 | CLOSED | 4421.24 | 0 | 4421.24 | 4421.24
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | AD: FLOOR CONNECTION | 065 | CLOSED | 19372.35 | 0 | 19372.35 | 19372.35
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 0 | 0 | 324.5631 | 324.5631
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 471.79 | 0 | 0 | 0
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | IN: REPLACE/ADD CARPET TILED HIGH TRAFFIC AREAS - UU 65 RM 217 | 065 | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0005318 | REPLACE/ADD CARPET TILES IN HIGH TRAFFIC AREAS - UU 65 RM 217 | HICKS, MICHAEL | CLOSED | 2015-07-22 | PA: REPAINT UU BLDG 65 ROOM 217 | 065 | CLOSED | 2924.5439 | 0 | 1604.312 | 1604.312
PJ0005318 Total | [7 empty] | 30724.3155 | 0 | 29206.4331 | 29206.4331
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | AD: GOSS ENGINEERING | 035 | CLOSED | 25680 | 0 | 25680 | 25680
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | AD: ITS | 035 | CLOSED | 342.4 | 0 | 342.4 | 342.4
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 0 | 0 | 187.8385 | 187.8385
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 3489.18 | 0 | 0 | 0
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | IN: REMODEL INNOVATION SANDBOX - BLD 35 RM 114C | 035 | CLOSED | 296.7048 | 0 | 141.288 | 141.288
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | LO: INISTALLATION OF PANIC HARDWARE IN SF DOOR 35 - 111C | 035 | CLOSED | 3804.1968 | 0 | 3197.388 | 3197.388
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | MO: RELOCATE EXISTING FURNITURE FROM 35 - 111C | 035 | CLOSED | 737.352 | 0 | 309 | 309
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | PA: MISC. PATCH & PAINT IN 35 - 111C AFTER ROOM IS CLEARED | 035 | CLOSED | 1961.976 | 0 | 495.264 | 495.264
PJ0005317 | DESIGN FOR INNOVATION SANDBOX - BLD 35 RM 111C | KOLEGRAFF, KENNETH | CLOSED | 2015-07-23 | PM: REMODEL INNOVATION SANDBOX - BLD 35 RM 111C | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005317 Total | [7 empty] | 36311.8096 | 0 | 30353.1785 | 30353.1785
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | CU: SUPPORT FOR FOOTBALL TAILGATING | 061 | CLOSED | 0 | 0 | 635.2781 | 635.2781
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | EL: CALLBACK FOR M. SOCCER BBQ - 8/28 | 061 | CLOSED | 0 | 0 | 215.304 | 215.304
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | EL:CALLBACK ON10/12 - POWER FOR BOUNCE HOUSE MUSTANG PLAZA | 061 | CLOSED | 0 | 0 | 215.304 | 215.304
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | LA: CLEAN UP SUPPORT FOR MUSTANG CORRAL BBQS (SEASON) | 003 | CLOSED | 0 | 0 | 120.096 | 120.096
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | LA: REPAIR BROKEN VALVE BOX FROM VENDOR - 11/21 | 061 | CLOSED | 0 | 0 | 120.096 | 120.096
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | MC: PICK UP ADA MATS BEHIND MOTT GYM (3/14) | 042 | CLOSED | 0 | 0 | 84 | 84
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | PERMIT: BASEBALL TAILGATING AT PARKING LOT H-14 | P-H14 | CLOSED | 0 | 0 | 247.254 | 247.254
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | RE: DELIVER ONE DUMSPTER TO O'NEILL LAWN - 8/22 | 003 | CLOSED | 0 | 0 | 65.412 | 65.412
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | RE: SUPPORT FOR MUSTANG BBQ EVENTS - O'NEILL LAWN | 061 | CLOSED | 0 | 0 | 1799.1 | 1799.1
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | SUPPLY RENTAL: MEN'S SOCCER PIZZA DINNER - 8/14 | 061 | CLOSED | 0 | 0 | 41 | 41
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | SUPPLY RENTAL: MUSTANG BBQ | 061 | CLOSED | 0 | 0 | 42.3334 | 42.3334
PJ0005313 | 15/16: SUPPORT FOR ATHLETICS ADVANCEMENT EVENTS | POPHAM, DONALD J. | CLOSED | 2015-07-22 | SUPPLY RENTAL: MUSTANG SOCCER CORRAL (SEASON RENTAL) | 061 | CLOSED | 0 | 0 | 615 | 615
PJ0005313 Total | [7 empty] | 0 | 0 | 4200.1775 | 4200.1775
PJ0005312 | 15/16: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-22 | CP: PROJECT CONTINGENCY | 061D | CLOSED | 0 | 0 | 0 | 0
PJ0005312 | 15/16: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-22 | CU: SUPPORT FOR WMS. SPRING SOCCER GAMES | 061D | CLOSED | 0 | 0 | 228.9588 | 228.9588
PJ0005312 | 15/16: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-22 | CU; SUPPORT FOR W. SOCCER GAMES | 061D | CLOSED | 0 | 0 | 5482.6755 | 5482.6755
PJ0005312 | 15/16: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-22 | LA: SUPPORT FOR W. SOCCER PRACTICES (SEASON WO) | 061D | CLOSED | 0 | 0 | 1292.292 | 1292.292
PJ0005312 | 15/16: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-22 | LA: SUPPORT FOR WM'S SOCCER SPRING GAMES | 061D | CLOSED | 0 | 0 | 620.808 | 620.808
PJ0005312 | 15/16: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-22 | LA: WMS SOCCER GAME SUPPORT - 2015/16 SEASON (SEASON WO) | 061D | CLOSED | 0 | 0 | 1372.65 | 1372.65
PJ0005312 Total | [7 empty] | 0 | 0 | 8997.3843 | 8997.3843
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: ASAP REPROGRAPHICS | 026 | CLOSED | 0 | 0 | 62.4024 | 62.4024
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: BKM FURNITURE | 026 | CLOSED | 198093.1981 | 0 | 197189.9041 | 197189.9041
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: CLASSROOM TECHNOLOGIES A/V EQUIP | 026 | CLOSED | 26750 | 0 | 2823.5588 | 2823.5588
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: COMP VIEW (PURCHASED FROM ITS) | 026 | CLOSED | 0 | 0 | 16880.3735 | 16880.3735
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: GOSS ENGINEERING | 026 | CLOSED | 9811.9 | 0 | 9811.9 | 9811.9
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: ITS | 026 | CLOSED | 43478.38 | 0 | 42750.4162 | 42750.4162
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: MEATHEAD MOVERS | 026 | CLOSED | 1159.88 | 0 | 1159.88 | 1159.88
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: STATE FIRE MARSHAL FEES | 026 | CLOSED | 1070 | 0 | 370.434 | 370.434
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | AD: THE SIGN PLACE | 026 | CLOSED | 0 | 0 | 1232.0087 | 1232.0087
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | CA: TRADE SUPPORT FOR FURNISHINGS | 026 | CLOSED | 2752.167 | 0 | 1990.5564 | 1990.5564
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 4665.72 | 0 | 0 | 0
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | CU: FINAL CLEAN UP AFTER CONSTRUCTION | 026 | CLOSED | 736.824 | 0 | 1187.226 | 1187.226
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | EL:TRADE SUPPORT FOR NEW POWER AND LIGHTING | 026 | CLOSED | 7746.5291 | 0 | 4210.14 | 4210.14
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | ES:TRADE SUPPORT IN INSTALL OF CONTROLS FOR NEW UNITS | 026 | CLOSED | 11235.072 | 0 | 6603.354 | 6603.354
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | IN: OFFICE RENOVATIONS - BLD 26 RMS 109 & 110 | 026 | CLOSED | 918.372 | 0 | 1200.948 | 1200.948
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | LO:ORANGE CORES AND POSSIBLE LOCK CHANGE | 026 | CLOSED | 2540.328 | 0 | 2394.34 | 2394.34
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | MO:MOVE FURNISHINGS FROM HERON TO 26 | 026 | CLOSED | 904.932 | 0 | 117 | 117
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | PA: PURCHASE MATERIALS FOR PAINTING | 026 | CLOSED | 1080 | 0 | 1060.14 | 1060.14
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | PL:DEMO ALL SUPPLY AND WASTE LINES CENTER 110 ROOMS | 026 | CLOSED | 3878.3868 | 0 | 3064.8096 | 3064.8096
PJ0005311 | FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | DILLON, JEFFREY | CLOSED | 2015-07-21 | PM: FURNITURE AND TECHNOLOGY UPGRADES - BLD 26 RMS 109 & 110 | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005311 Total | [7 empty] | 316821.689 | 0 | 294109.3917 | 294109.3917
PJ0005310 | SUPPORT EVENT IN LOADING DOCK AREA OF PAC SEPT 19, 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-01 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005310 | SUPPORT EVENT IN LOADING DOCK AREA OF PAC SEPT 19, 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-01 | CU: POWERWASH LOADING DOCK AND ASPHALT AREA | 006 | CLOSED | 0 | 0 | 110.52 | 110.52
PJ0005310 Total | [7 empty] | 0 | 0 | 110.52 | 110.52
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | AD: OTIS ELEVATOR STANDBY SUPPORT - M. SOCCER V. UCSB 10/17 | 061 | CLOSED | 0 | 0 | 1623.7143 | 1623.7143
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CA: ADDRESS LOOSE BLEACHERS FROM SOCCER GAMES | 061 | CLOSED | 667.44 | 0 | 1091.172 | 1091.172
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CA: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 17 | 061 | CLOSED | 222.48 | 0 | 244.752 | 244.752
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CPE: SUPPPORT FOR MEN'S SOCCER V. UCSB - OCT 17 | 061 | CLOSED | 0 | 0 | 361.14 | 361.14
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CU: SUPPORT FOR M. SOCCER SUPPORT SPRING GAMES | 061 | CLOSED | 0 | 0 | 711.408 | 711.408
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CU: SUPPORT FOR MEN'S SOCCER HOME GAMES - 2015/2016 | 061 | CLOSED | 0 | 0 | 7389.7131 | 7389.7131
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | EL: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 17 | 061 | CLOSED | 0 | 0 | 283.488 | 283.488
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | LA: MEN'S SOCCER GAME SUPPORT - 2015/16 SEASON (SEASON WO) | 061 | CLOSED | 0 | 0 | 3463.74 | 3463.74
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | LA: SUPPORT FOR MEN'S SOCCER PRACTICES -2015/16 SEASON | 061 | CLOSED | 0 | 0 | 1129.05 | 1129.05
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | LA: SUPPORT FOR MEN'S SOCCER SPRING GAMES (2016) | 061 | CLOSED | 0 | 0 | 908.736 | 908.736
PJ0005309 | 15/16: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2015-07-14 | PL: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 17 | 061 | CLOSED | 0 | 0 | 272.394 | 272.394
PJ0005309 Total | [7 empty] | 889.92 | 0 | 17479.3074 | 17479.3074
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | AD: OTIS ELEVATOR STANDBY SUPPROT FOR 15/16 FOOTBALL SEASON | 061 | CLOSED | 0 | 0 | 10283.5346 | 10283.5346
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CA: ADDRESS LOOSE BLEACHERS/SEATS AT SPANOS STADIUM | 061 | CLOSED | 444.96 | 0 | 1188.42 | 1188.42
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CA: SUPPORT FOR FALL 2015 FOOTBALL GAMES (SEASON WO) | 061 | CLOSED | 0 | 0 | 1209.99 | 1209.99
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CPE: SUPPORT FOR FOOTBALL GAMES-2015/16 SESAON (WO FOR SEASON) | 061 | CLOSED | 0 | 0 | 2275.182 | 2275.182
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CU: FOOTBALL SPRING GAME SUPPORT - 4/30 - N/L | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | CU: SUPPORT FOR FOOTBALL GAMES | 061 | CLOSED | 0 | 0 | 11184.2288 | 11184.2288
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | EL: FOOTBALL GAME SUPPORT FALL 2015 SEASON (WO FOR SEASON) | 061 | CLOSED | 0 | 0 | 5088.306 | 5088.306
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | LA: FOOTBALL GAME SUPPORT - 2015/2016 | 061 | CLOSED | 0 | 0 | 36987.096 | 36987.096
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | LA: SUPPORT FOR FOOTBALL PRACTICES - 2015/2016 | 061 | CLOSED | 0 | 0 | 2455.308 | 2455.308
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | LA: SUPPORT FOR FOOTBALL SPRING GAMES - 2016 | 061 | CLOSED | 0 | 0 | 565.5257 | 565.5257
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | PL: SUPPORT FOR FALL 2015 FOOTBALL GAMES (SEASON WO) | 061 | CLOSED | 0 | 0 | 1099.632 | 1099.632
PJ0005308 | 15/16: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2015-07-14 | RE: SUPPORT FOR 15/16 FOOTBALL GAMES | 061 | CLOSED | 0 | 0 | 95.952 | 95.952
PJ0005308 Total | [7 empty] | 444.96 | 0 | 72433.1751 | 72433.1751
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | AD: EXTERIOR COLLECTION STATIONS (TBD) | GENERAL | CLOSED | 3511.9968 | 0 | 3511.9968 | 3511.9968
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | AD: GUERILLA GARDENING CLUB | GENERAL | CLOSED | 5350 | 0 | 5350 | 5350
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | AD: MARKETING MATERIAL | GENERAL | CLOSED | 746.0147 | 0 | 746.0147 | 746.0147
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | AD: MAX-R ZERO WASTE STATIONS | GENERAL | CLOSED | 29453.676 | 0 | 29453.676 | 29453.676
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | AD: PRINT MATERIALS FOR HOUSING MOVE-OUT | GENERAL | CLOSED | 1088.297 | 0 | 1088.3 | 1088.3
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | CA: INSTALL BACKBOARDS ON 9 ZERO WASTE STATIONS AT LIBRARY (N/L) | GENERAL | CLOSED | 2.52 | 0 | 2.52 | 2.52
PJ0005306 | SR 14/15: RECYCLING/COMPOSTING IMPROVEMENTS | VEIUM, ERIC | CLOSED | 2015-07-08 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005306 Total | [7 empty] | 40152.5045 | 0 | 40152.5075 | 40152.5075
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | AD: COASTAL JANITORIAL | 051 | CLOSED | 0 | 0 | 1017.035 | 1017.035
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | AD: COULTON'S APPLIANCE | 051 | CLOSED | 0 | 0 | 267.5 | 267.5
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | AD: RAYNE WATER CONDITIONING | 051 | CLOSED | 588.5 | 0 | 496.502 | 496.502
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | CA: (PJ) STAIN FENCE-PAINT DECK | 051 | CLOSED | 556.2 | 0 | 0 | 0
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | CA: DINING ROOM DOOR RAMP PURCHASE AND INSTALL | 051 | CLOSED | 586.86 | 0 | 471 | 471
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | CA: REPAIR DAMAGE TO STORAGE SHED FROM FALLEN TREE LIMB | 051 | CLOSED | 667.44 | 0 | 1039.62 | 1039.62
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | CA: WOODEN GATE DOES NOT OPEN | 051 | CLOSED | 222.48 | 0 | 55.62 | 55.62
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 943.7 | 0 | 0 | 0
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | EL: (PJ) U-HOUSE, RECONNECT ELECTRICAL & INSTALL NEW LIGHTS | 051 | CLOSED | 5101.63 | 0 | 5233.164 | 5233.164
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | EL: ELECTRIC GATE REPAIR | 051 | CLOSED | 0 | 0 | 307.248 | 307.248
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | IN: (PJ) STAIN FENCE-PAINT DECK | 051 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | IN: (PJ) U-HOUSE, RECONNECT ELECTRICAL & INSTALL NEW LIGHTS | 051 | CLOSED | 219.7028 | 0 | 70.644 | 70.644
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | PA: (PJ) STAIN FENCE-PAINT DECK | 051 | CLOSED | 3355.5251 | 0 | 1717.752 | 1717.752
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | PA: TOUCH-UP WHERE TREE LIMB HIT THE OUT-BUILDING | 051 | CLOSED | 0 | 0 | 123.816 | 123.816
PJ0005305 | 15/16: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2015-07-08 | PL: TOILET IN UPSTAIRS GUEST BATH WON'T STOP RUNNING | 051 | CLOSED | 108.732 | 0 | 110.7 | 110.7
PJ0005305 Total | [7 empty] | 12492.0579 | 0 | 11016.567 | 11016.567
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | AD: BOWEN ENGINEERING | 065 | CLOSED | 2343.3 | 0 | 2343.3 | 2343.3
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | AD: FASULO DRYWALL | 065 | CLOSED | 671.96 | 0 | 671.96 | 671.96
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | AD: MCKENNA ENVIRONMENTAL | 065 | CLOSED | 2701.75 | 0 | 1782.62 | 1782.62
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 0 | 0 | 347.3755 | 347.3755
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1136.19 | 0 | 0 | 0
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | IN: INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | 065 | CLOSED | 282.576 | 0 | 105.966 | 105.966
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | PL: ALTER PLUMBING FOR NEW FLOOR SINK | 065 | CLOSED | 5364.949 | 0 | 5639.856 | 5639.856
PJ0005304 | INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | DUNN, TRAVIS | CLOSED | 2015-07-01 | PM: INSTALL FLOOR SINK IN CUSTODIAL CLOSET - BLD 65 RM 215 | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0005304 Total | [7 empty] | 12500.725 | 0 | 10891.0775 | 10891.0775
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | CA: SET UP ADA RAMP AT REC CENTER - 7/10 | 043 | CLOSED | 1334.88 | 0 | 1434.06 | 1434.06
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | CU: SUPPORT FOR SOAR | 011 | CLOSED | 0 | 0 | 138.114 | 138.114
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | EL: INSTALL SPIDER BOX AT DEXTER LAWN ON 7/14 (SOAR) | 034 | CLOSED | 0 | 0 | 257.712 | 257.712
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | EL: INSTALL SPIDER BOX AT REC CENTER - 7/30 | 043 | CLOSED | 0 | 0 | 32.214 | 32.214
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | EL:SPIDER BOX FOR REC CENTER MAIN GYM SOAR ORIENTATION 43-100 | 043 | CLOSED | 0 | 0 | 96.642 | 96.642
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | LA: SUPPORT FOR SOAR 2015 | 011 | CLOSED | 0 | 0 | 40.032 | 40.032
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | MC: DELIVER ADA RAMP STAGING TO REC CENTER 7/10/2015 (AM) | 043 | CLOSED | 0 | 0 | 107.046 | 107.046
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | MC: MOVE ONE SET OF ADA RAMPS TO REC CENTER LOADING DOCK (7/30) | 043 | CLOSED | 0 | 0 | 118.314 | 118.314
PJ0005303 | SUPPORT FOR SOAR 2015 | POPHAM, DONALD J. | CLOSED | 2015-07-07 | RE: SUPPORT FOR SOAR (JULY 15- AUG 11) | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0005303 Total | [7 empty] | 1334.88 | 0 | 2224.134 | 2224.134
PJ0005302 | INSTALL PANIC BUTTONS FOR 3 CUBICLES - BLD 14 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2015-05-07 | AD: CAME SECURITY | 014 | CLOSED | 2354 | 0 | 2006.25 | 2006.25
PJ0005302 | INSTALL PANIC BUTTONS FOR 3 CUBICLES - BLD 14 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2015-05-07 | ANTS:COORDINATE FOR CONNECTION OF NEW PANIC DEVICES WITH UPD | 014 | CLOSED | 135.552 | 0 | 101.664 | 101.664
PJ0005302 | INSTALL PANIC BUTTONS FOR 3 CUBICLES - BLD 14 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2015-05-07 | CA:CONTRACTOR SUPPORT FOR DRILLING INTO WALL- BLDG 14, 115 | 014 | CLOSED | 111.24 | 0 | 129.816 | 129.816
PJ0005302 | INSTALL PANIC BUTTONS FOR 3 CUBICLES - BLD 14 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2015-05-07 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 267.14 | 0 | 0 | 0
PJ0005302 | INSTALL PANIC BUTTONS FOR 3 CUBICLES - BLD 14 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2015-05-07 | IN: INSTALL PANIC BUTTONS FOR 3 CUBICLES - BLD 14 RM 115 | 014 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005302 Total | [7 empty] | 2938.576 | 0 | 2308.374 | 2308.374
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | AD: JL FASULO DRYWALL | 003 | CLOSED | 5344.65 | 0 | 4645.94 | 4645.94
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 0 | 0 | 381.0056 | 381.0056
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | CA: PREP ROOM FOR SOUNDBOARD INSTALL | 003 | CLOSED | 1106.5596 | 0 | 857.982 | 857.982
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1000.38 | 0 | 0 | 0
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | EL: EXTEND ELECTRICAL BOXES | 003 | CLOSED | 1770.4928 | 0 | 669.996 | 669.996
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | IN: INSTALL SOUND BRD IN OFFICE OF ASSOC DEAN - BLDG 03 RM 447 | 003 | CLOSED | 157.5361 | 0 | 141.288 | 141.288
PJ0005300 | INSTALL SOUND BOARD IN OFFICE OF ASSOCIATE DEAN - BLDG 03 RM 447 | MARCHESE, JASON (WILL) | CLOSED | 2015-07-01 | PA: PAINT WALLS | 003 | CLOSED | 1480.0172 | 0 | 650.034 | 650.034
PJ0005300 Total | [7 empty] | 10859.6358 | 0 | 7346.2456 | 7346.2456
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | AD: CAL POLY FACILITIES PLAN REVIEW FEES | 035 | CLOSED | 631 | 0 | 631 | 631
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | AD: CAL POLY FACILITY BLDG PERMIT FEE | 035 | CLOSED | 709 | 0 | 709 | 709
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | AD: STATE FIRE MARSHAL REVIEW AND INSPECTION FEES | 035 | CLOSED | 283.55 | 0 | 0 | 0
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 748.02 | 0 | 0 | 0
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | EL: BRING POWER FROM EXISTING PANEL TO NEW PANEL IN CABINET | 035 | CLOSED | 4147.4627 | 0 | 5240.7 | 5240.7
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | IN: TRADE SUPPORT FOR JULIAN'S KIOSK - BLD 35 RM 216 (MAINT) | 035 | CLOSED | 0 | 0 | 264.915 | 264.915
PJ0005298 | TI: PROVIDE TRADE SUPPORT FOR NEW JULIAN'S KIOSK - BLD 35 RM 216 | DUNN, TRAVIS | CLOSED | 2015-06-29 | PL: INSTALL P-TRAP PRIMER | 035 | CLOSED | 1711.6946 | 0 | 2236.752 | 2236.752
PJ0005298 Total | [7 empty] | 8230.7273 | 0 | 9082.367 | 9082.367
PJ0005296 | SIGNAGE UPDATE ON BUILDING (HEALTH CENTER) - NAME CHANGE | MOLLAN, CHERYL L. | CLOSED | 2015-06-05 | AD: THE SIGN PLACE | 027 | CLOSED | 4981.5776 | 0 | 4981.5776 | 4981.5776
PJ0005296 | SIGNAGE UPDATE ON BUILDING (HEALTH CENTER) - NAME CHANGE | MOLLAN, CHERYL L. | CLOSED | 2015-06-05 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 198.39 | 0 | 0 | 0
PJ0005296 | SIGNAGE UPDATE ON BUILDING (HEALTH CENTER) - NAME CHANGE | MOLLAN, CHERYL L. | CLOSED | 2015-06-05 | EL:RELOCATE OR REMOVE ELECTRICAL BOX AT EXT HC SIGN POST | 027 | CLOSED | 188.856 | 0 | 131.484 | 131.484
PJ0005296 | SIGNAGE UPDATE ON BUILDING (HEALTH CENTER) - NAME CHANGE | MOLLAN, CHERYL L. | CLOSED | 2015-06-05 | IN: SIGNAGE UPDATE ON BUILDING (HEALTH CENTER) - NAME CHANGE | 027 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005296 | SIGNAGE UPDATE ON BUILDING (HEALTH CENTER) - NAME CHANGE | MOLLAN, CHERYL L. | CLOSED | 2015-06-05 | PA:PATCH AND PAINT AT 3 EXT LOCATIONS AT HC TO REPAIR FOR SIGNAG | 027 | CLOSED | 1006.4718 | 0 | 123.816 | 123.816
PJ0005296 Total | [7 empty] | 6516.5834 | 0 | 5342.8436 | 5342.8436
PJ0005295 | M&R ASI 17/18: SAFETY RAILS ON ROOF TOP AIR HANDLERS - REC CTR. | DUNN, TRAVIS | CONST_COMP | 2015-05-28 | AD: JOC 16.041.5295 MAINO | 043 | CLOSED | 134836.05 | 0 | 134836.05 | 134836.05
PJ0005295 | M&R ASI 17/18: SAFETY RAILS ON ROOF TOP AIR HANDLERS - REC CTR. | DUNN, TRAVIS | CONST_COMP | 2015-05-28 | CP: PROJECT CONTINGENCY | 043 | OPEN | 13518.93 | 0 | 0 | 0
PJ0005295 | M&R ASI 17/18: SAFETY RAILS ON ROOF TOP AIR HANDLERS - REC CTR. | DUNN, TRAVIS | CONST_COMP | 2015-05-28 | IN: INSTALL SAFETY RAILS ON ROOF TOP AIR HANDLERS | 043 | CLOSED | 353.22 | 0 | 141.288 | 141.288
PJ0005295 | M&R ASI 17/18: SAFETY RAILS ON ROOF TOP AIR HANDLERS - REC CTR. | DUNN, TRAVIS | CONST_COMP | 2015-05-28 | PM: INSTALL SAFETY RAILS ON ROOF TOP AIR HANDLERS | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005295 | M&R ASI 17/18: SAFETY RAILS ON ROOF TOP AIR HANDLERS - REC CTR. | DUNN, TRAVIS | CONST_COMP | 2015-05-28 | SM: M&R ASI 17/18: SFTY RAILS ON ROOF TOP AIR HANDLERS - REC CTR | 043 | OPEN | 0 | 0 | 0 | 0
PJ0005295 Total | [7 empty] | 148708.2 | 0 | 134977.338 | 134977.338
PJ0005292 | INSTALL VIDEO EQUIPMENT FOR FOOTBALL REPLAY: BLDG. 61 - SPANOS | BRENNAN, MICHAEL | CLOSED | 2015-06-24 | AD: JOC 15.036.012 STAPLES | 061 | CLOSED | 23156.1482 | 0 | 23156.1482 | 23156.1482
PJ0005292 | INSTALL VIDEO EQUIPMENT FOR FOOTBALL REPLAY: BLDG. 61 - SPANOS | BRENNAN, MICHAEL | CLOSED | 2015-06-24 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 2810.9 | 0 | 0 | 0
PJ0005292 | INSTALL VIDEO EQUIPMENT FOR FOOTBALL REPLAY: BLDG. 61 - SPANOS | BRENNAN, MICHAEL | CLOSED | 2015-06-24 | EL: INSTALL PULG AT SOUTH BLEACHER FOR CAMERA | 061 | CLOSED | 4667.6903 | 0 | 3492.6 | 3492.6
PJ0005292 | INSTALL VIDEO EQUIPMENT FOR FOOTBALL REPLAY: BLDG. 61 - SPANOS | BRENNAN, MICHAEL | CLOSED | 2015-06-24 | IN: INSTALL VIDEO EQPMT FOR FOOTBALL REPLAY: BLDG. 61 - SPANOS | 061 | CLOSED | 282.576 | 0 | 211.932 | 211.932
PJ0005292 Total | [7 empty] | 30917.3145 | 0 | 26860.6802 | 26860.6802
PJ0005291 | MJ: IN-HOUSE SUPPORT FOR CULINARY SUPPORT CENTER - BLD 82 | MCNALLY, CURTIS J. | CLOSED | 2015-06-23 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 0 | 0 | 0 | 0
PJ0005291 | MJ: IN-HOUSE SUPPORT FOR CULINARY SUPPORT CENTER - BLD 82 | MCNALLY, CURTIS J. | CLOSED | 2015-06-23 | EL: LOCATE UTILITIES FOR CULINARY SUPPORT CENTER - BLDG 82 | 082 | CLOSED | 0 | 0 | 70.872 | 70.872
PJ0005291 | MJ: IN-HOUSE SUPPORT FOR CULINARY SUPPORT CENTER - BLD 82 | MCNALLY, CURTIS J. | CLOSED | 2015-06-23 | PL: LOCATE UTILITIES FOR CULINARY SUPPORT CENTER - BLDG 82 | 082 | CLOSED | 0 | 0 | 128.976 | 128.976
PJ0005291 Total | [7 empty] | 0 | 0 | 199.848 | 199.848
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON APRIL 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 1390.09 | 1390.09
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON AUGUST 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 1888.76 | 1888.76
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON DECEMBER 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 879.11 | 879.11
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON FEBRUARY 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 1364.25 | 1364.25
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON JANUARY 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 1926.43 | 1926.43
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON JULY 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 1785.41 | 1785.41
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON JULY 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 2926.85 | 2926.85
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON JUNE 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 1733.99 | 1733.99
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON JUNE 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 2426.72 | 2426.72
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON MARCH 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 3688.23 | 3688.23
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON MAY 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 773.48 | 773.48
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON NOVEMBER 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 4098.02 | 4098.02
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON OCTOBER 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 7453.44 | 7453.44
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON OCTOBER 2016 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 167.76 | 167.76
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: OVERHEAD ON SEPTEMBER 2015 BILLING FOR IN-HOUSE WORK | GENERAL | CLOSED | 0 | 0 | 2996.25 | 2996.25
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK DURING AUGUST 2016 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK DURING SEPT. 2016 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN APRIL 2017 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN DECEMBER 2016 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN FEBRUARY 2017 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN JANUARY 2017 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN JUNE 2017 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN MARCH 2017 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN MAY 2017 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | AD: THERE WAS NO IN-HOUSE WORK IN NOVEMBER 2016 BILLING PERIOD | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 | IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | FLEDDERMAN, JUDE | CLOSED | 2015-06-19 | CP: IN-HOUSE OVERHEAD ON OPPENHEIMER PROJECTS | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005290 Total | [7 empty] | 0 | 0 | 35498.79 | 35498.79
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | CA: PAC MAINTENANCE WALK-THROUGH 10/09/15 | 006 | CLOSED | 5932.8 | 0 | 4539.4492 | 4539.4492
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | CA: PAC MAINTENANCE WALK-THROUGH 4/14/15 - PRIORITY 1 ITEMS | 006 | CLOSED | 3708 | 0 | 4559.26 | 4559.26
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | CU: PAC MAINTENANCE WALK-THROUGH 4/14/15 - PRIORITY 1 ITEMS | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | EL: PAC MAINTENANCE WALK-THROUGH 4/14/15 - PRIORITY 1 ITEMS | 006 | CLOSED | 0 | 0 | 423.1809 | 423.1809
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | PA: PAC MAINTENANCE WALK-THROUGH 4/14/15 - PRIORITY 1 ITEMS | 006 | CLOSED | 0 | 0 | 3888.395 | 3888.395
PJ0005287 | PAC QUARTERLY MAINTENANCE WALK-THROUGH 04/14/15 | POLVI, STEVEN | CLOSED | 2015-06-09 | PL: PAC MAINTENANCE WALK-THROUGH 4/14/15 - PRIORITY 1 ITEMS | 006 | CLOSED | 0 | 0 | 53.74 | 53.74
PJ0005287 Total | [7 empty] | 9640.8 | 0 | 13464.0251 | 13464.0251
PJ0005286 | SR 14/15: NEW RELAY FOR TRANSFORMER AT MUSTANG SUBSTATION | POLVI, STEVEN | CLOSED | 2015-06-12 | AD: RK POWER ENGINEERING | 075 | CLOSED | 15536.4 | 0 | 14766 | 14766
PJ0005286 | SR 14/15: NEW RELAY FOR TRANSFORMER AT MUSTANG SUBSTATION | POLVI, STEVEN | CLOSED | 2015-06-12 | CP: PROJECT CONTINGENCY | 075 | CLOSED | 0 | 0 | 0 | 0
PJ0005286 | SR 14/15: NEW RELAY FOR TRANSFORMER AT MUSTANG SUBSTATION | POLVI, STEVEN | CLOSED | 2015-06-12 | EL: SUPPORT FOR NEW RELAY INSTALLATION AT MUSTANG SUBSTATION | 075 | CLOSED | 515.424 | 0 | 128.856 | 128.856
PJ0005286 Total | [7 empty] | 16051.824 | 0 | 14894.856 | 14894.856
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | AD: COASTAL DEMO | 010 | CLOSED | 981.725 | 0 | 2522.525 | 2522.525
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | AD: JOC 15.036.008 STAPLES | 010 | CLOSED | 40907.4375 | 0 | 38927.884 | 38927.884
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | AD: MAINO LVPW | 010 | CLOSED | 1415.61 | 0 | 1415.61 | 1415.61
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | CA: INFILL CONCRETE FLOOR SLAB | 010 | CLOSED | 979.92 | 0 | 1906.8 | 1906.8
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 3193.75 | 0 | 0 | 0
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | CU: STRIP AND WAX FLOOR, RM 104 | 010 | CLOSED | 200.952 | 0 | 497.31 | 497.31
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | EL: DISCONNECT CIRCUITS SERVING SLAND CABINET | 010 | CLOSED | 953.136 | 0 | 1459.29 | 1459.29
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | IN: SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | 010 | CLOSED | 706.44 | 0 | 105.966 | 105.966
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | LA: SUPPORT PLUMBERS - REMOVE EXCESS DIRT FROM 10-104 | 010 | CLOSED | 160.128 | 0 | 160.128 | 160.128
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | LO: INSTALL CONTRACTOR ORANGE CORE @10-104 | 010 | CLOSED | 182.772 | 0 | 60.924 | 60.924
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | MO: MOVE CABINETS | 010 | CLOSED | 536.256 | 0 | 33.804 | 33.804
PJ0005285 | SR 14/15: MOLD REMEDIATION BLD 10 RM 104 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-06-02 | PL: DISCONNECT AND REPIPE COUNTER SINK SUPPLY AND WASTE OF THE I | 010 | CLOSED | 6105.8638 | 0 | 7005.3497 | 7005.3497
PJ0005285 Total | [7 empty] | 56323.9903 | 0 | 54095.5907 | 54095.5907
PJ0005281 | SR 15/16 CAMPUS ROAD STRIPING | NORTON, DAVE | CLOSED | 2015-05-28 | AD: JOC 14.034.023 MAINO | STREETS | CLOSED | 41325.1227 | 0 | 41325.1227 | 41325.1227
PJ0005281 | SR 15/16 CAMPUS ROAD STRIPING | NORTON, DAVE | CLOSED | 2015-05-28 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 4153.71 | 0 | 0 | 0
PJ0005281 | SR 15/16 CAMPUS ROAD STRIPING | NORTON, DAVE | CLOSED | 2015-05-28 | IN: SR 15/16 CAMPUS ROAD STRIPING | STREETS | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005281 Total | [7 empty] | 45690.7647 | 0 | 41501.7327 | 41501.7327
PJ0005280 | SUPPORT FOR SLO SOCCER TOURNAMENT -TURF FIELDS- (AUG 8 &9 2015) | POPHAM, DONALD J. | CLOSED | 2015-05-22 | CP: PROJECT CONTINGENCY | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0005280 | SUPPORT FOR SLO SOCCER TOURNAMENT -TURF FIELDS- (AUG 8 &9 2015) | POPHAM, DONALD J. | CLOSED | 2015-05-22 | CU: SUPPORT FOR SOCCER TOURNAMENT - 8/7-8/9 | 160F | CLOSED | 0 | 0 | 55.26 | 55.26
PJ0005280 | SUPPORT FOR SLO SOCCER TOURNAMENT -TURF FIELDS- (AUG 8 &9 2015) | POPHAM, DONALD J. | CLOSED | 2015-05-22 | SUPPLY RENTAL: SLO SOCCER TOURNAMENT - 8/7/2015 | 160F | CLOSED | 0 | 0 | 42 | 42
PJ0005280 Total | [7 empty] | 0 | 0 | 97.26 | 97.26
PJ0005279 | CLEAN WINDOWS & WALL BY MARQUEE - MOTT 42 | CANTU, MONICA M. | CLOSED | 2015-05-29 | AD: COASTAL JANITORIAL | 042 | CLOSED | 454.75 | 0 | 454.75 | 454.75
PJ0005279 | CLEAN WINDOWS & WALL BY MARQUEE - MOTT 42 | CANTU, MONICA M. | CLOSED | 2015-05-29 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 45.48 | 0 | 0 | 0
PJ0005279 Total | [7 empty] | 500.23 | 0 | 454.75 | 454.75
PJ0005278 | INSTALL CAMES ALARM PANIC BUTTON TO OFFICE ADMIN 01 RM. 410 | NORTON, DAVE | CLOSED | 2015-02-07 | AD: CAME SECURITY | 001 | CLOSED | 1978.9115 | 0 | 1979.5 | 1979.5
PJ0005278 | INSTALL CAMES ALARM PANIC BUTTON TO OFFICE ADMIN 01 RM. 410 | NORTON, DAVE | CLOSED | 2015-02-07 | ANTS: SECURITY HOOK-UP | 001 | CLOSED | 226.3718 | 0 | 67.776 | 67.776
PJ0005278 | INSTALL CAMES ALARM PANIC BUTTON TO OFFICE ADMIN 01 RM. 410 | NORTON, DAVE | CLOSED | 2015-02-07 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005278 | INSTALL CAMES ALARM PANIC BUTTON TO OFFICE ADMIN 01 RM. 410 | NORTON, DAVE | CLOSED | 2015-02-07 | EL: ELECTRICAL SUPPORT | 001 | CLOSED | 658.2197 | 0 | 225.498 | 225.498
PJ0005278 | INSTALL CAMES ALARM PANIC BUTTON TO OFFICE ADMIN 01 RM. 410 | NORTON, DAVE | CLOSED | 2015-02-07 | IN: INSTALL CAMES ALARM PANIC BUTTON TO OFFICE ADMIN | 001 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005278 Total | [7 empty] | 2934.147 | 0 | 2343.418 | 2343.418
PJ0005277 | UPGRADE WHITEBOARDS - BLDG 45- RM 130 | NORTON, DAVE | CLOSED | 2015-05-14 | CA: PURCHASE & INSTALL WHITEBOARDS | 045 | CLOSED | 5306.5596 | 0 | 4780.6498 | 4780.6498
PJ0005277 | UPGRADE WHITEBOARDS - BLDG 45- RM 130 | NORTON, DAVE | CLOSED | 2015-05-14 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 579.47 | 0 | 0 | 0
PJ0005277 | UPGRADE WHITEBOARDS - BLDG 45- RM 130 | NORTON, DAVE | CLOSED | 2015-05-14 | IN: UPGRADE WHITEBOARDS - BLDG 45- RM 130 | 045 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005277 | UPGRADE WHITEBOARDS - BLDG 45- RM 130 | NORTON, DAVE | CLOSED | 2015-05-14 | PA: PAINT TOUCH UP- FRONT WALL ONLY BLDG45 130 | 045 | CLOSED | 344.2085 | 0 | 371.448 | 371.448
PJ0005277 Total | [7 empty] | 6371.5261 | 0 | 5222.7418 | 5222.7418
PJ0005276 | INSTALL MIST PUMP - 048 GREENHOUSE 9 | KOLEGRAFF, KENNETH | CLOSED | 2015-05-14 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 2180.66 | 0 | 0 | 0
PJ0005276 | INSTALL MIST PUMP - 048 GREENHOUSE 9 | KOLEGRAFF, KENNETH | CLOSED | 2015-05-14 | EL: INSTALL MOUNTING SYSTEM, POWER AND MIST PUMP | 048 | CLOSED | 5741.8576 | 0 | 3951.27 | 3951.27
PJ0005276 | INSTALL MIST PUMP - 048 GREENHOUSE 9 | KOLEGRAFF, KENNETH | CLOSED | 2015-05-14 | IN: INSTALL MIST PUMP - 048 GREENHOUSE 9 | 048 | CLOSED | 423.864 | 0 | 282.576 | 282.576
PJ0005276 | INSTALL MIST PUMP - 048 GREENHOUSE 9 | KOLEGRAFF, KENNETH | CLOSED | 2015-05-14 | PL: REPLACE EXISTING PIPING, WATER SOFTENER & MIST PUMP | 048 | CLOSED | 15576.2246 | 0 | 15753.0211 | 15753.0211
PJ0005276 Total | [7 empty] | 23922.6062 | 0 | 19986.8671 | 19986.8671
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | AD: JL FASULO DRYWALL | GENERAL | CLOSED | 9107.84 | 0 | 8884.21 | 8884.21
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | AD: JOC 16.039.004 NEWTON | GENERAL | CLOSED | 12050.6717 | 0 | 12050.6717 | 12050.6717
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | AD: RF KOERBER | GENERAL | CLOSED | 909.5 | 0 | 909.5 | 909.5
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | AD: SLO PLASTERING | GENERAL | CLOSED | 5250.49 | 0 | 5250.49 | 5250.49
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | AD: STATE FIRE MARSHAL FEES | GENERAL | CLOSED | 0 | 0 | 338.6764 | 338.6764
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | AD: THE SIGN PLACE | GENERAL | CLOSED | 434.7945 | 0 | 693.6061 | 693.6061
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | CA: TRADE SUPPORT FOR INSTALLATION OF HYDRATION STATIONS | GENERAL | CLOSED | 14779.3434 | 0 | 16302.7062 | 16302.7062
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 432.1 | 0 | 0 | 0
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | EL: TRADE SUPPORT FOR INSTALLATION OF HYDRATION STATIONS | GENERAL | CLOSED | 8168.38 | 0 | 7479.222 | 7479.222
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | ES:ADMIN HYDRATION - SHUTDOWN AHU FOR WORK | GENERAL | CLOSED | 262.656 | 0 | 361.152 | 361.152
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | IN: PJ5275 CAMPUSWIDE INSTALL 25 HYDRATION STATION - ASI FUNDING | GENERAL | CLOSED | 3930.6322 | 0 | 317.898 | 317.898
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | ITS: | GENERAL | CLOSED | 0 | 0 | 240.75 | 240.75
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | PA: TRADE SUPPORT FOR INSTALLATION OF HYDRATION STATIONS | GENERAL | CLOSED | 6398.4196 | 0 | 4447.5911 | 4447.5911
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | PL: INSTALLATION OF HYDRATION STATIONS - CAMPUS WIDE | GENERAL | CLOSED | 88275.173 | 0 | 92723.5831 | 92723.5831
PJ0005275 | CAMPUS WIDE INSTALLATION OF 25 HYDRATION STATIONS - ASI FUNDING | DUNN, TRAVIS | CLOSED | 2015-05-14 | PM: CAMPUS WIDE INSTALLATIONS-25 HYDRATION STATIONS-ASI FUNDING | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005275 Total | [7 empty] | 150000.0003 | 0 | 150000.0566 | 150000.0566
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | CA: SUPPORT FOR 2015 SPRING COMMENCEMENT- JUNE 13 & 14 | 061 | CLOSED | 3708 | 0 | 7624.595 | 7624.595
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | CP: SUPPORT FOR SPRING COMMENCEMENT - JUNE 13 & 14 | 061 | CLOSED | 0 | 0 | 782.47 | 782.47
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | CU: 2015 SPRING COMMENCEMENT SUPPORT - 6/13 & 6/14 | 061 | CLOSED | 0 | 0 | 6626.6 | 6626.6
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | EL: SUPPORT FOR 2015 SPRING COMMENCEMENT-JUNE 13 &14 | 061 | CLOSED | 0 | 0 | 1648.295 | 1648.295
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | ES: SUPPORT FOR 2015 SPRING COMMENCEMENT - JUNE 13 & 14 | 061 | CLOSED | 0 | 0 | 963.04 | 963.04
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | LA: SUPPORT FOR 2015 SPRING COMMENCEMENT - JUNE 13&14 | 061 | CLOSED | 0 | 0 | 15508.8134 | 15508.8134
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | MC: SUPPORT FOR COMMENCEMENT - JUNE 13 & 14 | 061 | CLOSED | 0 | 0 | 1014.12 | 1014.12
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | PA: SUPPORT FOR SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 257.95 | 257.95
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | PERMIT: IME TENT PERMIT-BLDG 41 (6/13/2015)(PENDING PERMIT SIGN) | 061 | CLOSED | 0 | 0 | 206.045 | 206.045
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | PERMIT: TENT/ADA SPEC. EVENTS PERMIT FOR SPRING COMM-6/13&14 | 061 | CLOSED | 0 | 0 | 264.915 | 264.915
PJ0005274 | 2015: SUPPORT FOR SPRING COMMENCEMENT (JUNE 13 &14) | POPHAM, DONALD J. | CLOSED | 2015-05-12 | PL: SUPPORT FOR 2015 SPRING COMMENCEMENT - 6/13 & 14 | 061 | CLOSED | 0 | 0 | 1628.4 | 1628.4
PJ0005274 Total | [7 empty] | 3708 | 0 | 36525.2433 | 36525.2433
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: ASAP REPROGRAPHICS | 026 | CLOSED | 0 | 0 | 402.0097 | 402.0097
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: BKM - FURNISHINGS | 026 | CLOSED | 39516.0951 | 0 | 39516.0951 | 39516.0951
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: FLOOR CONNECTIONS | 026 | CLOSED | 10127.55 | 0 | 10127.55 | 10127.55
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: ITS- DATA | 026 | CLOSED | 7437.57 | 0 | 7437.57 | 7437.57
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: JOC 15.036.022 STAPLES | 026 | CLOSED | 140964.1326 | 0 | 140964.1326 | 140964.1326
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: MCKENNA | 026 | CLOSED | 7414.03 | 0 | 7406.54 | 7406.54
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: RRM DESIGN GROUP | 026 | CLOSED | 12840 | 0 | 10668.97 | 10668.97
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: STATE FIRE MARSHAL FEES | 026 | CLOSED | 535 | 0 | 377.8705 | 377.8705
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | AD: THE SIGN PLACE | 026 | CLOSED | 0 | 0 | 201.7592 | 201.7592
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | CA: PLANE HINGE SIDE OF DOOR | 026 | CLOSED | 2157.54 | 0 | 1984.584 | 1984.584
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | CP: PROJECT CONTINGENCY | 026 | OPEN | 1166.66 | 0 | 0 | 0
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | EL:TRADE SUPPORT | 026 | CLOSED | 2461.3135 | 0 | 161.07 | 161.07
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | ES:TRADE SUPPORT | 026 | CLOSED | 1663.9258 | 0 | 801.096 | 801.096
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | IN: REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | 026 | CLOSED | 282.576 | 0 | 812.406 | 812.406
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | LO:REMOVE E HARDWARE, NEW HARDWARE | 026 | CLOSED | 2595.1476 | 0 | 1112.424 | 1112.424
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | PA: BLDG 26 100-104 REPAINT | 026 | CLOSED | 7124.088 | 0 | 1632.216 | 1632.216
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | PL:DEMO AND CAP OF SINK | 026 | CLOSED | 1344.9888 | 0 | 694.896 | 694.896
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | PM: REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005273 | REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | DILLON, JEFFREY | CONST_COMP | 2015-04-30 | SM: REMODEL BLDG 26, ROOMS 100, 100A, 101, 103A | 026 | OPEN | 0 | 0 | 0 | 0
PJ0005273 Total | [7 empty] | 237630.6174 | 0 | 224301.1891 | 224301.1891
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | AD: R.F. KOERBER | 180 | CLOSED | 909.5 | 0 | 909.5 | 909.5
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | AD: STATE FIRE MARSHAL | 180 | CLOSED | 0 | 0 | 127.009 | 127.009
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | CA:DEMO DRYWALL, BACKING, NEW DRYWALL AND IN-PRO SURFACE | 180 | CLOSED | 1422.5922 | 0 | 523.824 | 523.824
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 530.54 | 0 | 0 | 0
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | EL: HYDRATION STATIONS (2) RELOCATE RECEPTCL. | 180 | CLOSED | 466.7046 | 0 | 842.832 | 842.832
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | IN: INST 2 HYDRATION STN -BLD 180: 1 EA ON 1ST AND 2ND FLRS | 180 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | PA:PAINT BACK WALL OF DF NOOK AT SECOND FLOOR | 180 | CLOSED | 139.293 | 0 | 154.77 | 154.77
PJ0005270 | INSTALL HYDRATION STATION -BLD 180 | DILLON, JEFFREY | CLOSED | 2015-02-26 | PL: 2 HYDRATION STATIONS | 180 | CLOSED | 3757.2763 | 0 | 2981.208 | 2981.208
PJ0005270 Total | [7 empty] | 7367.1941 | 0 | 5680.431 | 5680.431
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | AD: J.L. FASULO DRYWALL | 001 | CLOSED | 1678.83 | 0 | 1678.83 | 1678.83
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | AD: STATE FIRE MARSHAL | 001 | CLOSED | 0 | 0 | 259.6569 | 259.6569
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | CA: INSULATE SPACE BETWEEN PRES OFFICE & KITCHEN | 001 | CLOSED | 8930.8992 | 0 | 8818.5392 | 8818.5392
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 718.95 | 0 | 0 | 0
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 001 | CLOSED | 0 | 0 | 8.4 | 8.4
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | EL: ADD LIGHTS; RELOCATE LIGHT | 001 | CLOSED | 3529.4706 | 0 | 910.62 | 910.62
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | ES: TURN OFF HVAC FOR CONSTRUCTION | 001 | CLOSED | 328.32 | 0 | 32.832 | 32.832
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | IN: MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | 001 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | LO: NEW LATCH SET | 001 | CLOSED | 375.8605 | 0 | 164.028 | 164.028
PJ0005268 | MODIFY DOOR/SPACE BETWEEN KITCHEN AND PRESIDENT'S OFFICE | NORTON, DAVE | CLOSED | 2015-05-05 | PA: PAINT WALLS AT PRES KITCHEN AREA | 001 | CLOSED | 2229.0533 | 0 | 650.034 | 650.034
PJ0005268 Total | [7 empty] | 18105.7494 | 0 | 12664.2281 | 12664.2281
PJ0005267 | DROUGHT CONTINGENCY/RESPONSE - CAMPUS WIDE (MAINT) | LOOSLEY, SCOTT L. | IN_CONSTR | 2015-05-08 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005267 | DROUGHT CONTINGENCY/RESPONSE - CAMPUS WIDE (MAINT) | LOOSLEY, SCOTT L. | IN_CONSTR | 2015-05-08 | LA: REMOVE LAWNS FOR DROUGHT RESPONSE - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 76335.8715 | 76335.8715
PJ0005267 | DROUGHT CONTINGENCY/RESPONSE - CAMPUS WIDE (MAINT) | LOOSLEY, SCOTT L. | IN_CONSTR | 2015-05-08 | SM: DROUGHT CONTINGENCY/RESPONSE - CAMPUS WIDE (MAINT) | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005267 Total | [7 empty] | 0 | 0 | 76335.8715 | 76335.8715
PJ0005266 | ADD ELECTRICAL OUTLETS FOR GOLF CARTS - BLD 46 RM 100 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-20 | AD: MAINO LVPW | 046 | CLOSED | 5350 | 0 | 5260.12 | 5260.12
PJ0005266 | ADD ELECTRICAL OUTLETS FOR GOLF CARTS - BLD 46 RM 100 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-20 | AD: STATE FIRE MARSHAL FEES | 046 | CLOSED | 267.5 | 0 | 0 | 0
PJ0005266 | ADD ELECTRICAL OUTLETS FOR GOLF CARTS - BLD 46 RM 100 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-20 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 1379.25 | 0 | 0 | 0
PJ0005266 | ADD ELECTRICAL OUTLETS FOR GOLF CARTS - BLD 46 RM 100 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-20 | EL: ADD ELECTRICAL OUTLETS FOR GOLF CART CHARGING STATIONS | 046 | CLOSED | 6636.0248 | 0 | 2925.702 | 2925.702
PJ0005266 | ADD ELECTRICAL OUTLETS FOR GOLF CARTS - BLD 46 RM 100 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-20 | IN: ADD ELECTRICAL OUTLETS FOR GOLF CARTS - BLD 46 RM 100 | 046 | CLOSED | 471.9019 | 0 | 141.288 | 141.288
PJ0005266 Total | [7 empty] | 14104.6768 | 0 | 8327.11 | 8327.11
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | AD: COURT & GREENS | 042 | CLOSED | 26750 | 0 | 24075 | 24075
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 3123.56 | 0 | 0 | 0
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | EL: LOCKOUT POWER TO BASKETBALL HOISTS AT MOTT GYM | 042 | CLOSED | 406.7046 | 0 | 4710.732 | 4710.732
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | ES: REBUILD BASKETBALL BACKSTOP | 042 | CLOSED | 4107.7709 | 0 | 3901.536 | 3901.536
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | IN: SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | 042 | CLOSED | 157.5361 | 0 | 70.644 | 70.644
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | PA: PAINT BASKETBALL BACKSTOP | 042 | CLOSED | 335.4906 | 0 | 167.88 | 167.88
PJ0005265 | SR 15/16: REPLACE BASKETBALL BACKBOARD HOIST SYSTEM - MOTT | MARCHESE, JASON (WILL) | CLOSED | 2015-05-04 | PL: SUPPLY 20 3" OD CAPS | 042 | CLOSED | 119.5817 | 0 | 111.54 | 111.54
PJ0005265 Total | [7 empty] | 35000.6439 | 0 | 33037.332 | 33037.332
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: COASTAL DEMO | 042 | CLOSED | 0 | 0 | 909.5 | 909.5
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: FLOOR CONNECTION | 042 | CLOSED | 66800.1 | 0 | 66447 | 66447
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: ITS | 042 | CLOSED | 3210 | 0 | 1342.315 | 1342.315
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: JL FASULO DRYWALL | 042 | CLOSED | 5210.9 | 0 | 5210.9 | 5210.9
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: JOC 15.036.027 STAPLES | 042 | CLOSED | 197882.3225 | 0 | 197882.3332 | 197882.3332
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: MAINO LVPW | 042 | CLOSED | 0 | 0 | 1501.21 | 1501.21
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: MCKENNA | 042 | CLOSED | 5729.85 | 0 | 5729.85 | 5729.85
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | AD: STATE FIRE MARSHAL FEES | 042 | CLOSED | 572.45 | 0 | 333.6902 | 333.6902
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | CA: MOTT GYM 1ST FLOOR REFRESH PROJECT SUPPORT | 042 | CLOSED | 2824.8 | 0 | 3637.752 | 3637.752
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 15309.61 | 0 | 0 | 0
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | EL: Safe off, Construction Power, & Support | 042 | CLOSED | 3434.832 | 0 | 3412.938 | 3412.938
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | IN: MOTT GYM 1ST FLOOR REFRESH, FR5264 | 042 | CLOSED | 353.22 | 0 | 953.694 | 953.694
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | LO: Installation of Orange Cores & Support | 042 | CLOSED | 335.082 | 0 | 0 | 0
PJ0005264 | MOTT GYM 1ST FLOOR REFRESH | KOLEGRAFF, KENNETH | CLOSED | 2015-04-30 | PA: BLDG 42 PART 1 PAINT ALL WALLS 1ST FLOOR LOBBY AND CORRIDOR | 042 | CLOSED | 6566.916 | 0 | 839.124 | 839.124
PJ0005264 Total | [7 empty] | 308230.0825 | 0 | 288200.3064 | 288200.3064
PJ0005263 | FIRE REMEDIATION - ENGINEERING IV - BLD 192 RM 330 | POLVI, STEVEN | CLOSED | 2015-05-01 | AD: SERVICE MASTER | 192 | CLOSED | 0 | 0 | 5599.524 | 5599.524
PJ0005263 | FIRE REMEDIATION - ENGINEERING IV - BLD 192 RM 330 | POLVI, STEVEN | CLOSED | 2015-05-01 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0005263 | FIRE REMEDIATION - ENGINEERING IV - BLD 192 RM 330 | POLVI, STEVEN | CLOSED | 2015-05-01 | EL: FIRE ALARM RESPONSE AT ENGINEERING IV | 192 | CLOSED | 128.856 | 0 | 740.96 | 740.96
PJ0005263 | FIRE REMEDIATION - ENGINEERING IV - BLD 192 RM 330 | POLVI, STEVEN | CLOSED | 2015-05-01 | ES: FIRE ALARM RESPONSE AT ENGINEERING IV | 192 | CLOSED | 131.328 | 0 | 32.832 | 32.832
PJ0005263 Total | [7 empty] | 260.184 | 0 | 6373.316 | 6373.316
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | AD: FLOOR CONNECTION | 042 | CLOSED | 1872.5 | 0 | 1353.55 | 1353.55
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | AD: SANTA MARIA ACOUSTICAL | 042 | CLOSED | 4815 | 0 | 2849.41 | 2849.41
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | AD: STATE FIRE MARSHAL | 042 | CLOSED | 0 | 0 | 190.5135 | 190.5135
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | CA: DEMO DROP CEILING AND CARPET | 042 | CLOSED | 1603.872 | 0 | 1090.1316 | 1090.1316
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 1413.58 | 0 | 0 | 0
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | EH&S: ROOM SURVEY & DEMO OVERSITE (N/L) | 042 | CLOSED | 143.5406 | 0 | 0 | 0
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | EL: DEMO RECESSED FIXTURES & INSTALL NEW FIXTURES | 042 | CLOSED | 3655.4558 | 0 | 3131.502 | 3131.502
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | IN: RENOVATE OFFICE - MOTT 042 RM. 209 | 042 | CLOSED | 157.5361 | 0 | 141.288 | 141.288
PJ0005262 | RENOVATE OFFICE - MOTT 042 RM. 209 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-27 | PA: PAINT OFFICE 209 | 042 | CLOSED | 1815.5078 | 0 | 897.666 | 897.666
PJ0005262 Total | [7 empty] | 15476.9924 | 0 | 9654.0611 | 9654.0611
PJ0005261 | REORGANIZING OFFICE SPACE - BLD 52 RM E07 | DUNN, TRAVIS | CLOSED | 2015-04-14 | CA: UNINSTALL FURNITURE/DRILL ATTACHMENT FOR BKM | 052 | CLOSED | 111.24 | 0 | 305.91 | 305.91
PJ0005261 | REORGANIZING OFFICE SPACE - BLD 52 RM E07 | DUNN, TRAVIS | CLOSED | 2015-04-14 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 168.04 | 0 | 0 | 0
PJ0005261 | REORGANIZING OFFICE SPACE - BLD 52 RM E07 | DUNN, TRAVIS | CLOSED | 2015-04-14 | EL: INSTALL AN OUTLET ON EAST WALL 8/28/15 | 052 | CLOSED | 873.4092 | 0 | 945.144 | 945.144
PJ0005261 | REORGANIZING OFFICE SPACE - BLD 52 RM E07 | DUNN, TRAVIS | CLOSED | 2015-04-14 | IN: REORGANIZING OFFICE SPACE - BLD 52 RM E07 | 052 | CLOSED | 78.4148 | 0 | 105.966 | 105.966
PJ0005261 | REORGANIZING OFFICE SPACE - BLD 52 RM E07 | DUNN, TRAVIS | CLOSED | 2015-04-14 | MO: remove and surplus items in office | 052 | CLOSED | 50.274 | 0 | 22.536 | 22.536
PJ0005261 | REORGANIZING OFFICE SPACE - BLD 52 RM E07 | DUNN, TRAVIS | CLOSED | 2015-04-14 | PA: FILL, PRIME, AND PAINT 8/31/15 | 052 | CLOSED | 550.9812 | 0 | 569.676 | 569.676
PJ0005261 Total | [7 empty] | 1832.3592 | 0 | 1949.232 | 1949.232
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | AD: DA CRAIGHEAD CONSTRUCTION | 130 | OPEN | 81962 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | AD: EARTH SYSTEMS PACIFIC | 130 | OPEN | 4178.6175 | 4178.6175 | 0 | 4178.6175
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | AD: ENGLEKIRK & SABOL | 130 | OPEN | 1230.5 | 0 | 1070 | 1070
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | AD: ITS | 130 | OPEN | 535 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | AD: RRM DESIGN | 130 | OPEN | 20758 | 8507.9338 | 11929.0662 | 20437
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | AD: STATE FIRE MARSHAL FEES | 130 | OPEN | 535 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | CA: REPAIR HEIGHT BAR HIT BY VEHICL - GAPS 130 (UPD # 15-0444) | 130 | CLOSED | 16365.9864 | 0 | 9166.938 | 9166.938
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | CP: PROJECT CONTINGENCY | 130 | OPEN | 12162.55 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | EH&S: | 130 | OPEN | 70.8048 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | EL: LOCATE CONDUIT AT COLUMNS - PAC GARAGE - PJ5259 | 130 | COMPLETE | 3260.8764 | 0 | 1315.872 | 1315.872
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | EO: SUPPORT CARPENTERS FOR HEIGHT LIMIT BAR REPAIR | 130 | CLOSED | 0 | 0 | 102.744 | 102.744
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | ES: RESPOND TO CALL - DAMAGED HEIGHT BAR AT BLG 130(UPD #15-0444 | 130 | CLOSED | 196.992 | 0 | 196.992 | 196.992
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | IN: REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS 130 | 130 | OPEN | 1316.0977 | 0 | 141.288 | 141.288
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | LA: | 130 | OPEN | 220.176 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | PA: PAINT HEIGHT INDICATORS FOR GRAND AVE PARKING STRUCTURE -130 | 130 | OPEN | 3119.148 | 0 | 216.678 | 216.678
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | PM: REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN-GAPS (UPD #15-0444) | 130 | OPEN | 0 | 0 | 0 | 0
PJ0005259 | REPAIR HEIGHT LIMIT BAR & IMPROVE DESIGN - GAPS (UPD #15-0444) | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-04-22 | SM: REPAIR HEIGHT LIMIT BAR & IMPROVE DESG - GAPS (UPD #15-0444) | 130 | OPEN | 0 | 0 | 0 | 0
PJ0005259 Total | [7 empty] | 145911.7488 | 12686.5513 | 24139.5782 | 36826.1295
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | CA: SUPPORT FOR GREEN & GOLD - 5/1 | 042 | CLOSED | 222.48 | 0 | 222.48 | 222.48
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | CU: SUPPORT FOR EVENING OF GREEN & GOLD - 5/1 | 042 | CLOSED | 0 | 0 | 110.52 | 110.52
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | EL: SUPPORT FOR EVENING OF GREEN & GOLD EVENT (5/1) | 042 | CLOSED | 0 | 0 | 1177.05 | 1177.05
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | ES: SUPPORT FOR 2015 EVENING OF GRN & GOLD - MAY 1 | 042 | CLOSED | 0 | 0 | 36.114 | 36.114
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | IN: 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | 042 | CLOSED | 0 | 0 | 211.932 | 211.932
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | LA: BLOW FRONT OF MOTT GYM ON FRIDAY MAY 1. | 042 | CLOSED | 0 | 0 | 548.2981 | 548.2981
PJ0005258 | SUPPORT FOR 2015 EVENING OF GREEN & GOLD EVENT - BLD 42 (5/1/15) | POPHAM, DONALD J. | CLOSED | 2015-04-22 | MC: SUPPORT FOR EVENING OF GRN & GOLD - MAY 1 | 042 | CLOSED | 0 | 0 | 230.994 | 230.994
PJ0005258 Total | [7 empty] | 222.48 | 0 | 2537.3881 | 2537.3881
PJ0005257 | SP 15/16 - ROOF MAINT FOR BLDG 47 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-21 | AD: QUAGLINO ROOFING | 047 | CLOSED | 10700 | 0 | 6597.62 | 6597.62
PJ0005257 | SP 15/16 - ROOF MAINT FOR BLDG 47 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-21 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 1162.5 | 0 | 0 | 0
PJ0005257 | SP 15/16 - ROOF MAINT FOR BLDG 47 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-21 | IN: SP 15/16 - ROOF MAINT FOR BLDG 47 | 047 | CLOSED | 315.0722 | 0 | 141.288 | 141.288
PJ0005257 Total | [7 empty] | 12177.5722 | 0 | 6738.908 | 6738.908
PJ0005256 | SP 15/16 - ROOF MAINT FOR BLDG 27 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-21 | AD: QUAGLINO ROOFING | 027 | CLOSED | 10700 | 0 | 10064.42 | 10064.42
PJ0005256 | SP 15/16 - ROOF MAINT FOR BLDG 27 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-21 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1163.21 | 0 | 0 | 0
PJ0005256 | SP 15/16 - ROOF MAINT FOR BLDG 27 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-21 | IN: SP 15/16 - ROOF MAINT FOR BLDG 27 | 027 | CLOSED | 314.3658 | 0 | 176.61 | 176.61
PJ0005256 Total | [7 empty] | 12177.5758 | 0 | 10241.03 | 10241.03
PJ0005255 | INSTALL NEW CARPET - BLDG 26 -110L | BRENNAN, MICHAEL | CLOSED | 2015-04-01 | AD: FLOOR CONNECTION | 026 | CLOSED | 4679.8911 | 0 | 4679.8911 | 4679.8911
PJ0005255 | INSTALL NEW CARPET - BLDG 26 -110L | BRENNAN, MICHAEL | CLOSED | 2015-04-01 | AD: STATE FIRE MARSHAL | 026 | CLOSED | 160.5 | 0 | 0 | 0
PJ0005255 | INSTALL NEW CARPET - BLDG 26 -110L | BRENNAN, MICHAEL | CLOSED | 2015-04-01 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 600 | 0 | 0 | 0
PJ0005255 | INSTALL NEW CARPET - BLDG 26 -110L | BRENNAN, MICHAEL | CLOSED | 2015-04-01 | EL: CONNECT POWER TO FURNITURE | 026 | CLOSED | 1017.0836 | 0 | 961.92 | 961.92
PJ0005255 | INSTALL NEW CARPET - BLDG 26 -110L | BRENNAN, MICHAEL | CLOSED | 2015-04-01 | IN: INSTALL NEW CARPET - BLDG 26 -110L | 026 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005255 Total | [7 empty] | 6528.1187 | 0 | 5712.4551 | 5712.4551
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 22000 | 0 | 0 | 0
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | CPE: SUPPORT FOR PG&E ENERGY RETROFIT PROJECT | GENERAL | CLOSED | 0 | 0 | 12941.892 | 12941.892
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | CU: RESPOND TO WATER LEAK BLD 001 RMS 413 & 414 (12/21/15) | GENERAL | CLOSED | 0 | 0 | 9.348 | 9.348
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | EL: RESPOND TO WATER LEAK BLD 001 RMS 413 & 414 (12/21/15) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | EL: SUPPORT FOR CAMPUS WIDE UTILITY IMPROVEMENTS | GENERAL | CLOSED | 0 | 0 | 14452.2156 | 14452.2156
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | ES: SUPPORT FOR PG&E ENERGY RETROFIT PROJECT | GENERAL | CLOSED | 0 | 0 | 20633.361 | 20633.361
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | PL: SUPPORT FOR PG&E ENERGY RETROFIT PROJECT | GENERAL | CLOSED | 0 | 0 | 5815.86 | 5815.86
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | SM: MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005253 | MJ: IN-HOUSE SUPPORT FOR PG&E UTILITY UPGRADES - CAMPUS WIDE | JUDD, PERRY | CONST_COMP | 2015-04-15 | USE WO0762511 - CA: RESPOND TO WATER LEAK BLD 001 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005253 Total | [7 empty] | 22000 | 0 | 53852.6766 | 53852.6766
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | AD: FLOOR CONNECTION | 001 | CLOSED | 13375 | 0 | 10229.2 | 10229.2
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | AD: FURNITURE INSTALLATION TEAM | 001 | CLOSED | 5350 | 0 | 3329.1766 | 3329.1766
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 0 | 0 | 203.2037 | 203.2037
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | CA: TRIM DOORS | 001 | CLOSED | 452.538 | 0 | 244.752 | 244.752
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1937.71 | 0 | 0 | 0
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | IN: CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | 001 | CLOSED | 157.5361 | 0 | 141.288 | 141.288
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | MO: MOVE BOXES | 001 | CLOSED | 74.7407 | 0 | 8.451 | 8.451
PJ0005252 | CARPET REPLACEMENT FOR ALL OFFICES - ADMN 01 RM 122 | MARCHESE, JASON (WILL) | CLOSED | 2015-04-14 | PA: REPAIR DRYWALL & TOUCH UP PAINT | 001 | CLOSED | 222.8688 | 0 | 206.36 | 206.36
PJ0005252 Total | [7 empty] | 21570.3936 | 0 | 14362.4313 | 14362.4313
PJ0005251 | SR 14/15: INSTALL WATER METERS AT FIVE BLDGS. FOR LEED-EB CERT | ELLIOT, DENNIS K | CLOSED | 2015-04-09 | AD: FASULO DRYWALL | GENERAL | CLOSED | 1058.23 | 0 | 1058.23 | 1058.23
PJ0005251 | SR 14/15: INSTALL WATER METERS AT FIVE BLDGS. FOR LEED-EB CERT | ELLIOT, DENNIS K | CLOSED | 2015-04-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 130 | 0 | 0 | 0
PJ0005251 | SR 14/15: INSTALL WATER METERS AT FIVE BLDGS. FOR LEED-EB CERT | ELLIOT, DENNIS K | CLOSED | 2015-04-09 | ES: REPAIR BTU METERS IN 5 BLDGS FOR LEED-EB CERT | GENERAL | CLOSED | 3945.7498 | 0 | 3622.812 | 3622.812
PJ0005251 | SR 14/15: INSTALL WATER METERS AT FIVE BLDGS. FOR LEED-EB CERT | ELLIOT, DENNIS K | CLOSED | 2015-04-09 | IN: SR 14/15: INSTL WATER METERS FIVE BLDGS FOR LEED-EB CERT | GENERAL | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0005251 | SR 14/15: INSTALL WATER METERS AT FIVE BLDGS. FOR LEED-EB CERT | ELLIOT, DENNIS K | CLOSED | 2015-04-09 | PL: INSTALL WATER METER FOR LEED-EB CERT - 5 BLDGS. | GENERAL | CLOSED | 42917.5913 | 0 | 27474.2976 | 27474.2976
PJ0005251 Total | [7 empty] | 48334.147 | 0 | 32225.9836 | 32225.9836
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: ASAP REPROGRAPHICS | 042 | CLOSED | 0 | 0 | 102.4846 | 102.4846
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: FACILITIES ARCHITECTURAL DESIGN FEES | 042 | CLOSED | 3210 | 0 | 3210 | 3210
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: FLOOR CONNECTION | 042 | CLOSED | 4552.85 | 0 | 4552.85 | 4552.85
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: HOLMAN LOCKERS | 042 | CLOSED | 38375.55 | 0 | 32758.05 | 32758.05
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: ITS/CT | 042 | CLOSED | 2170.8695 | 0 | 778.425 | 778.425
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: JOC 15.035.032 MAINO | 042 | CLOSED | 63181.2851 | 0 | 63181.2851 | 63181.2851
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: MATERIALS PURCHASE AND INSTALLED BY THE PROJECT MANAGER | 042 | CLOSED | 0 | 0 | 435 | 435
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: SALAS OBRIEN ENGINEERS | 042 | CLOSED | 14418.25 | 0 | 12492.25 | 12492.25
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | AD: STATE FIRE MARSHAL FEES | 042 | CLOSED | 802.5 | 0 | 273.7595 | 273.7595
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | CA: OPEN TOE KICK FOR VENTILATION, RM 113 - MOTT GYM | 042 | CLOSED | 768.0216 | 0 | 694.704 | 694.704
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 12026.89 | 0 | 0 | 0
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | CPE: NEW EXHAUST SYSTEM | 042 | CLOSED | 12457.7933 | 0 | 5878.065 | 5878.065
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | EL:INSTALL NEW PANEL, PULL WIRE, SUPPORT | 042 | CLOSED | 8433.2588 | 0 | 8322.756 | 8322.756
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | IN: REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | 042 | CLOSED | 211.932 | 0 | 741.762 | 741.762
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | LO: NEW HARDWARE ON EXISTING DOUBLE DOORS | 042 | CLOSED | 944.2236 | 0 | 911 | 911
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | MO:UNLOAD LOCKERS AT BLDG 80 | 042 | CLOSED | 268.128 | 0 | 36.621 | 36.621
PJ0005250 | REMODEL MOTT 113 (MEN'S BASKETBALL LOCKER ROOM) | DILLON, JEFFREY | CLOSED | 2015-02-18 | PA: PAINT ALL WALLS AND CEILING | 042 | CLOSED | 5333.5972 | 0 | 1733.424 | 1733.424
PJ0005250 Total | [7 empty] | 167155.1491 | 0 | 136102.4362 | 136102.4362
PJ0005248 | REPAIR WATER DAMAGE - BLDG 053 RM 312 | LAMPMAN, GREG | CLOSED | 2015-04-06 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 053 | CLOSED | 3083.74 | 0 | 3083.74 | 3083.74
PJ0005248 | REPAIR WATER DAMAGE - BLDG 053 RM 312 | LAMPMAN, GREG | CLOSED | 2015-04-06 | AD: MECA CONSULTING | 053 | CLOSED | 569.9676 | 0 | 569.9676 | 569.9676
PJ0005248 | REPAIR WATER DAMAGE - BLDG 053 RM 312 | LAMPMAN, GREG | CLOSED | 2015-04-06 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 0 | 0 | 0 | 0
PJ0005248 | REPAIR WATER DAMAGE - BLDG 053 RM 312 | LAMPMAN, GREG | CLOSED | 2015-04-06 | IN: REPAIR WATER DAMAGE - BLDG 053 RM 312 | 053 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005248 | REPAIR WATER DAMAGE - BLDG 053 RM 312 | LAMPMAN, GREG | CLOSED | 2015-04-06 | PA: PAINTING IN BLDG. 53 ROOM 312, FOLLOWING WATER DAMAGE REPAIR | 053 | CLOSED | 422.2549 | 0 | 309.54 | 309.54
PJ0005248 Total | [7 empty] | 4146.6065 | 0 | 4033.8916 | 4033.8916
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | AD: FLOOR CONNECTION | 035 | CLOSED | 16585 | 0 | 16585 | 16585
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | AD: JOC 15.036.023 STAPLES | 035 | CLOSED | 23017.733 | 0 | 23017.733 | 23017.733
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | AD: MCKENNA | 035 | CLOSED | 6147.15 | 0 | 5232.3 | 5232.3
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 572.45 | 0 | 75.2638 | 75.2638
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | CA: Under Cut Doors and Relocate Lockers | 035 | CLOSED | 2715.6462 | 0 | 1786.08 | 1786.08
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 87.75 | 0 | 0 | 0
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | IN: SR 15/16: REPLACE CARPET - KEN LIB 35 | 035 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005247 | SR 15/16: REPLACE CARPET - KEN LIB 35 | KOLEGRAFF, KENNETH | CLOSED | 2015-04-06 | MO: MOVE & REPLACE FURNITURE ROOM 208 | 035 | CLOSED | 238.9691 | 0 | 90 | 90
PJ0005247 Total | [7 empty] | 49505.9863 | 0 | 46892.3428 | 46892.3428
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: AIR POLLUTION CONTROL DISTRICT | 027 | OPEN | 869.375 | 0 | 869.375 | 869.375
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: ASAP PRINTING | 027 | OPEN | 240.5895 | 0 | 240.5895 | 240.5895
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: COUNTY PERMIT | 027 | OPEN | 2175.31 | 0 | 2175.31 | 2175.31
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: ENGLEKIRK & SABOL | 027 | OPEN | 1284 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: GOSS ENGINEERING | 027 | OPEN | 23326 | 4665.2 | 18660.8 | 23326
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: JOC 16.040.5246 NEWTON | 027 | OPEN | 74297.0015 | 12201.3919 | 62095.6096 | 74297.0015
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: MICHAEL BRAY CONSTRUCTION | 027 | OPEN | 3745 | 0 | 3745 | 3745
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: PADRE ASSOCIATES | 027 | OPEN | 14267.7438 | 445.5159 | 12888.8241 | 13334.34
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: SPECIALTY CONSTRUCTION | 027 | OPEN | 53640.2984 | 0 | 53640.2984 | 53640.2984
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: STATE FIRE MARSHAL FEES | 027 | HOLD | 0 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | AD: STATE FIRE MARSHAL FEES | 027 | OPEN | 2675 | 0 | 4569.7453 | 4569.7453
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | CA: | 027 | CLOSED | 61.182 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | CP: PROJECT CONTINGENCY | 027 | OPEN | 349.23 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | EH&S: | 027 | OPEN | 643.68 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | EL: HEALTH CENTER GENERATOR REPLACEMENT - KOLEGRAFF | 027 | LONG_TERM | 183536.875 | 0 | 12407.826 | 12407.826
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | IN: M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | 027 | ASSIGNED | 282.576 | 0 | 70.644 | 70.644
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | LA: | 027 | OPEN | 1040.352 | 0 | 40.032 | 40.032
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | LO: | 027 | OPEN | 134.0328 | 0 | 152.31 | 152.31
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | MO: | 027 | OPEN | 36.8676 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | PA: | 027 | OPEN | 3323.952 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | PL: DEMO AND CAP GAS LINE SERVICING (E) GENERATOR - KOLEGRAFF | 027 | ASSIGNED | 1418.736 | 0 | 422.4 | 422.4
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | PM: M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005246 | M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-20 | SM: M&R H/C 15/16: REPLACE EMERGENCY GENERATOR BLDG 027 | 027 | OPEN | 0 | 0 | 0 | 0
PJ0005246 Total | [7 empty] | 367347.8016 | 17312.1078 | 171978.7639 | 189290.8717
PJ0005245 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H01 | NORTON, DAVE | CLOSED | 2015-03-24 | AD: JOC 14.033.040 MAINO | P-H01 | CLOSED | 32197.9692 | 0 | 32272.9227 | 32272.9227
PJ0005245 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H01 | NORTON, DAVE | CLOSED | 2015-03-24 | CP: PROJECT CONTINGENCY | P-H01 | CLOSED | 74.95 | 0 | 0 | 0
PJ0005245 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H01 | NORTON, DAVE | CLOSED | 2015-03-24 | IN: M&R PARK 15/16: RESEAL & RESTRIPE - P-H01 | P-H01 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005245 Total | [7 empty] | 32343.5632 | 0 | 32308.2447 | 32308.2447
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: BOWEN ENVIRONMENTAL | 035 | CLOSED | 5350 | 0 | 5301.85 | 5301.85
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: CAME SECURITY | 035 | CLOSED | 1605 | 0 | 1118.15 | 1118.15
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: ENGLEKIRK SABOL | 035 | CLOSED | 1070 | 0 | 535 | 535
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: FLOOR CONNECTION | 035 | CLOSED | 8025 | 0 | 7574.6584 | 7574.6584
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: MCKENNA ENVIRONMENTAL | 035 | CLOSED | 3745 | 0 | 3070.9 | 3070.9
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: MCMURRAY STERN | 035 | CLOSED | 109675 | 0 | 109675 | 109675
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5296.5 | 0 | 4376.3 | 4376.3
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 0 | 0 | 261.9467 | 261.9467
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | ANTS: SUPPORT FOR CAME SECURITY / ADD ZONES | 035 | CLOSED | 496.8346 | 0 | 135.552 | 135.552
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | CA: INSTALL GALLERY RAILING IN ROOM 101D | 035 | CLOSED | 1129.92 | 0 | 420.192 | 420.192
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 11499.14 | 0 | 0 | 0
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | EL: REMOVE AND REINSTALL FIRE ALARMS | 035 | CLOSED | 837.0836 | 0 | 96.642 | 96.642
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | ES: HVAC - ISOLATION, DIFFUSERS, T-STAT AND BALANCE | 035 | CLOSED | 3430.295 | 0 | 1658.7558 | 1658.7558
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | IN: P5244 INSTALL COMPACT SHELVING IN 35-101F | 035 | CLOSED | 314.3658 | 0 | 176.61 | 176.61
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | LO:INSTALL ORANGE CORE FOR CONTRACTOR ACCESS | 035 | CLOSED | 135.8605 | 0 | 91.386 | 91.386
PJ0005244 | INSTALL COMPACT SHELVING IN 35-101F | MARCHESE, JASON (WILL) | CLOSED | 2015-03-16 | PA: REPAIR DRYWALL AND PAINT | 035 | CLOSED | 3355.5251 | 0 | 1609.608 | 1609.608
PJ0005244 Total | [7 empty] | 155965.5246 | 0 | 136102.5509 | 136102.5509
PJ0005243 | REROUTE RECIRC LINE - SIERRA MADRE TOWERS 0 | GONZALES, ALBERT | CLOSED | 2015-03-10 | AD: AMERICAN LEAK DETECTION | 113A | CLOSED | 374.5 | 0 | 374.5 | 374.5
PJ0005243 | REROUTE RECIRC LINE - SIERRA MADRE TOWERS 0 | GONZALES, ALBERT | CLOSED | 2015-03-10 | AD: GARCIA AND SON | 113A | CLOSED | 53500 | 0 | 53211.1 | 53211.1
PJ0005243 | REROUTE RECIRC LINE - SIERRA MADRE TOWERS 0 | GONZALES, ALBERT | CLOSED | 2015-03-10 | AD: MAINO CONSTRUCTION | 113A | CLOSED | 13910 | 0 | 14076.92 | 14076.92
PJ0005243 | REROUTE RECIRC LINE - SIERRA MADRE TOWERS 0 | GONZALES, ALBERT | CLOSED | 2015-03-10 | CP: PROJECT CONTINGENCY | 113A | CLOSED | 6438.14 | 0 | 0 | 0
PJ0005243 | REROUTE RECIRC LINE - SIERRA MADRE TOWERS 0 | GONZALES, ALBERT | CLOSED | 2015-03-10 | EL: SUPPORT FOR DOMESTIC VALVE REPLACEMENTS AT SM TWR 0 & 5 | 113A | CLOSED | 515.424 | 0 | 161.07 | 161.07
PJ0005243 | REROUTE RECIRC LINE - SIERRA MADRE TOWERS 0 | GONZALES, ALBERT | CLOSED | 2015-03-10 | PL: SM TWR 0 AND 5 VALVES | 113A | CLOSED | 5870.3609 | 0 | 14876.7331 | 14876.7331
PJ0005243 Total | [7 empty] | 80608.4249 | 0 | 82700.3231 | 82700.3231
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: BOWEN ENGINEERING | 027 | CLOSED | 6914.875 | 0 | 6914.875 | 6914.875
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: CAME SECURITY | 027 | CLOSED | 187.25 | 0 | 187.25 | 187.25
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: COASTAL DEMO | 027 | CLOSED | 0 | 0 | 1428.45 | 1428.45
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: FASULO DRYWALL | 027 | CLOSED | 6597.62 | 0 | 6597.62 | 6597.62
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: MAINO LVPW | 027 | CLOSED | 1070 | 0 | 602.41 | 602.41
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: MCKENNA ENVIRONMENTAL | 027 | CLOSED | 3539.56 | 0 | 2163.54 | 2163.54
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: STATE FIRE MARSHAL FEES | 027 | CLOSED | 481.5 | 0 | 0 | 0
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | AD: VISALIA CERAMIC TILE | 027 | CLOSED | 8157.68 | 0 | 8157.68 | 8157.68
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | CA:REMOVE DISPENSERS AND REINSTALL- HC ROOM 165 | 027 | CLOSED | 1394.88 | 0 | 2450.259 | 2450.259
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1368.56 | 0 | 0 | 0
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | CPE: DUCTS AND T-STAT FOR ADA RESTROOM PROJECT @ HEALTH CENTER | 027 | CLOSED | 896.64 | 0 | 466.2 | 466.2
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | EL: REINSTALL LIGHT FIXTURE SO DOOR CLOSER DOES NOT HIT FIXTURE | 027 | CLOSED | 3194.2811 | 0 | 2477.526 | 2477.526
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | ES:EXTEND EXISTING REGISTER TO NEW WALL- BLDG 27, ROOM 165 | 027 | CLOSED | 1330.8403 | 0 | 887.7211 | 887.7211
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | IN: RESTROOM ADA UPGRADE BLDG 027 RM. 165 | 027 | CLOSED | 353.22 | 0 | 247.254 | 247.254
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | PA:PAINT NEW WALL AND CEILING- HC ROOM 165 | 027 | CLOSED | 2487.1081 | 0 | 835.758 | 835.758
PJ0005241 | RESTROOM ADA UPGRADE BLDG 027 RM. 165 | MOLLAN, CHERYL L. | CLOSED | 2015-03-11 | PL:REMOVE AND REINSTALL PLUMBING FIXTURES- HC ROOM 165 | 027 | CLOSED | 3800.3609 | 0 | 4726.932 | 4726.932
PJ0005241 Total | [7 empty] | 41774.3754 | 0 | 38143.4751 | 38143.4751
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | AD: JOC 14.034.018.00 MAINO | P-H01 | CLOSED | 272148.6257 | 0 | 272148.6257 | 272148.6257
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | AD: JOC 15.035.009 MAINO | P-H01 | CLOSED | 348424.2605 | 0 | 348424.2605 | 348424.2605
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | AD: JOC 15.035.036 MAINO | P-H01 | CLOSED | 186667.2245 | 0 | 185602.842 | 185602.842
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | AD: M6 CONSULTING | P-H01 | CLOSED | 2675 | 0 | 2675 | 2675
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | AD: STATE FIRE MARSHAL | P-H01 | CLOSED | 157.9962 | 0 | 158.7559 | 158.7559
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | CP: PROJECT CONTINGENCY | P-H01 | CLOSED | 0 | 0 | 0 | 0
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | EL: INSTALL TEMP POWER FOR CONSTRUCTION | P-H01 | CLOSED | 128.85 | 0 | 128.856 | 128.856
PJ0005240 | SUPPORT FOR SOLAR DECATHLON - CORP WHSE PARKING LOT | BRENNAN, MICHAEL | CLOSED | 2015-03-10 | IN: SUPPORT FOR SOLAR DECATHALON - CORP WHSE PARKING LOT | P-H01 | CLOSED | 2331.252 | 0 | 2331.252 | 2331.252
PJ0005240 Total | [7 empty] | 812533.2089 | 0 | 811469.5921 | 811469.5921
PJ0005239 | SR 15/16: REPLACE VFDS -BLDG 11 | KOLEGRAFF, KENNETH | CLOSED | 2015-03-18 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 3985.17 | 0 | 0 | 0
PJ0005239 | SR 15/16: REPLACE VFDS -BLDG 11 | KOLEGRAFF, KENNETH | CLOSED | 2015-03-18 | EL: REPLACEMENT OF SIX VFD'S IN BLDG 11 MECH. ROOMS | 011 | CLOSED | 10769.5478 | 0 | 8683.554 | 8683.554
PJ0005239 | SR 15/16: REPLACE VFDS -BLDG 11 | KOLEGRAFF, KENNETH | CLOSED | 2015-03-18 | ES: VFD REPLACEMENT | 011 | CLOSED | 28384.3853 | 0 | 44340.4946 | 44340.4946
PJ0005239 | SR 15/16: REPLACE VFDS -BLDG 11 | KOLEGRAFF, KENNETH | CLOSED | 2015-03-18 | IN: SR 15/16: REPLACE VFDS -BLDG 11 | 011 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005239 Total | [7 empty] | 43421.6791 | 0 | 53200.6586 | 53200.6586
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | AD: BKM FURNITURE | 033 | CLOSED | 2024.5256 | 0 | 2023.6161 | 2023.6161
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | AD: HERTZ FURNITURE | 033 | CLOSED | 494.9713 | 0 | 494.9713 | 494.9713
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | AD: KI FURNITURE | 033 | CLOSED | 16050 | 0 | 11741.6985 | 11741.6985
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | AD: STATE FIRE MARSHAL | 033 | CLOSED | 0 | 0 | 376.9717 | 376.9717
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | CA: DEMO ISLAND, PATCH FLOOR, INSTALL WHITEBOARDS | 033 | CLOSED | 7913.7474 | 0 | 2569.531 | 2569.531
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 786.71 | 0 | 0 | 0
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | CU: | 033 | CLOSED | 74.6872 | 0 | 161.262 | 161.262
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | EL: DEMO ELECTRICAL IN ISLAND | 033 | CLOSED | 693.4092 | 0 | 439.044 | 439.044
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | IN: SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | 033 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | LO: | 033 | CLOSED | 542.2236 | 0 | 152.31 | 152.31
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | MO: MOVE TABLES AND CHAIRS FROM 180-110 TO 03-104 (N/L) | 033 | CLOSED | 536.256 | 0 | 0 | 0
PJ0005238 | SR 15/16: CLASSROOM UPGRADE - BLD 33 RM 289 | BRENNAN, MICHAEL | CLOSED | 2015-03-18 | PL: DEMO PLUMBING IN ISLAND | 033 | CLOSED | 1448.5313 | 0 | 2511.804 | 2511.804
PJ0005238 Total | [7 empty] | 30879.4273 | 0 | 20612.4966 | 20612.4966
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | AD: J L FASULO_DEMO WALL PAPER, SKIM COAT WALLS | 003 | CLOSED | 3210 | 0 | 3035.59 | 3035.59
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | CA: DISASSEMBLE FURNITURE, DEMO COVE BASE, REMOVE WINDOW BLINDS | 003 | CLOSED | 1513.0722 | 0 | 1219.4186 | 1219.4186
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0.54 | 0 | 0 | 0
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 003 | CLOSED | 0 | 0 | 8.4 | 8.4
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | EH&S: OVERSITE OF WALLPAPER DEMO (N/L) | 003 | CLOSED | 466.4376 | 0 | 0 | 0
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | IN: REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A | 003 | CLOSED | 157.5361 | 0 | 105.966 | 105.966
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | MO: MOVE FURNITURE, BOXES, WINDOW BLINDS | 003 | CLOSED | 298.2924 | 0 | 28.17 | 28.17
PJ0005237 | REMOVE WALLPAPER AND PAINT: BLDG 3 - RMS 408 & 409A (ONLY 409A) | MARCHESE, JASON (WILL) | CLOSED | 2015-03-03 | PA: PAINT OFFICE 409A | 003 | CLOSED | 2420.2982 | 0 | 1482.18 | 1482.18
PJ0005237 Total | [7 empty] | 8066.1766 | 0 | 5879.7246 | 5879.7246
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: ASAP REPROGRAPHICS | 019 | CLOSED | 0 | 0 | 54.9618 | 54.9618
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: FLOOR CONNECTION | 019 | CLOSED | 3584.5 | 0 | 3552.4 | 3552.4
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: ITS | 019 | CLOSED | 963 | 0 | 911.105 | 911.105
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: JOC 15.035.023 MAINO | 019 | CLOSED | 130903.8 | 0 | 129526.7314 | 129526.7314
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: JOC 16.037.027 MAINO | 019 | CLOSED | 11672.2662 | 0 | 11672.2662 | 11672.2662
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: MCKENNA ENVIRONMENTAL | 019 | CLOSED | 4829.98 | 0 | 2501.66 | 2501.66
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: PMSM ARCHITECTS | 019 | CLOSED | 31351 | 0 | 27573.9 | 27573.9
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | AD: STATE FIRE MARSHAL FEES | 019 | CLOSED | 1605 | 0 | 402.2023 | 402.2023
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | CA: | 019 | CLOSED | 633.72 | 0 | 120.564 | 120.564
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 838.63 | 0 | 0 | 0
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | EL: ELECTRICAL SUPPORT | 019 | CLOSED | 1837.6505 | 0 | 1908.276 | 1908.276
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | IN: DESIGN & BUILD NEW WOK STATION AT THE AVENUE - BLDG 19 | 019 | CLOSED | 918.372 | 0 | 1165.626 | 1165.626
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | PA: PAINT WALLS IN AVENUE FOR SALAD BAR RELOCATION/REMODEL | 019 | CLOSED | 2581.056 | 0 | 1547.73 | 1547.73
PJ0005236 | RELOCATE SALAD BAR AT THE AVENUE - BLDG 19 | NORTON, DAVE | CLOSED | 2015-03-05 | PL: TRADE SUPPORT | 019 | CLOSED | 1390.3613 | 0 | 1050.156 | 1050.156
PJ0005236 Total | [7 empty] | 193109.336 | 0 | 181987.5787 | 181987.5787
PJ0005234 | SUPPORT FOR ASI CONCERT - SPORTS COMPLEX (5/30/15) | POPHAM, DONALD J. | CLOSED | 2015-03-02 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0005234 | SUPPORT FOR ASI CONCERT - SPORTS COMPLEX (5/30/15) | POPHAM, DONALD J. | CLOSED | 2015-03-02 | EL: INSTALL GROUND ROD FOR GENERATOR - 5/28 | 163 | CLOSED | 0 | 0 | 96.642 | 96.642
PJ0005234 | SUPPORT FOR ASI CONCERT - SPORTS COMPLEX (5/30/15) | POPHAM, DONALD J. | CLOSED | 2015-03-02 | LA: SUPPORT FOR ASI CONCERT - 5/30 | 163 | CLOSED | 0 | 0 | 182.664 | 182.664
PJ0005234 | SUPPORT FOR ASI CONCERT - SPORTS COMPLEX (5/30/15) | POPHAM, DONALD J. | CLOSED | 2015-03-02 | MC: MOVE ADA MATS FROM BUTLER BUILDING TO 163 | 163 | CLOSED | 0 | 0 | 78.876 | 78.876
PJ0005234 Total | [7 empty] | 0 | 0 | 358.182 | 358.182
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CA: BARRICADE REQUEST - OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CA: PULL OUT WEST BLEACHERS AT 11AM ON FRIDAY APRIL 17 | 042 | CLOSED | 185.4 | 0 | 417.15 | 417.15
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CA: SUPPORT FOR 2015 OPEN HOUSE - APRIL 18 | GENERAL | CLOSED | 1854 | 0 | 1317.455 | 1317.455
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CA:SIGNAGE FOR OPEN HOUSE DUMPSTERS | GENERAL | CLOSED | 185.4 | 0 | 236.9 | 236.9
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CP: OPEN HOUSE 2015 SUPPORT 4/18/2015 | GENERAL | CLOSED | 0 | 0 | 481.52 | 481.52
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | CU: SUPPORT FOR OPEN HOUSE - 4/18 | GENERAL | CLOSED | 0 | 0 | 2754.3326 | 2754.3326
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | EL: OPEN HOUSE SUPPORT - APRIL 17 & 18 | GENERAL | CLOSED | 0 | 0 | 1782.52 | 1782.52
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | EL: POWER REQUEST FOR ROBORODENTIA - 4/17/15 | 042 | CLOSED | 0 | 0 | 740.922 | 740.922
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | ES: OPEN HOUSE ON SITE SUPPORT - 4/18 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | LA: SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 | GENERAL | CLOSED | 0 | 0 | 4818.3597 | 4818.3597
PJ0005233 | SUPPORT FOR 2015 OPEN HOUSE - APRIL 17 & 18 (MAINT) | POPHAM, DONALD J. | CLOSED | 2015-02-27 | PL: SUPPORT FOR 2015 OPEN HOUSE - APRIL 18 | GENERAL | CLOSED | 0 | 0 | 266.04 | 266.04
PJ0005233 Total | [7 empty] | 2224.8 | 0 | 12815.1993 | 12815.1993
PJ0005232 | SR 14/15: REPLACE STAIRS, WALKWAYS, BUTTRESSES - BLD 150F | LAMPMAN, GREG | CLOSED | 2015-03-06 | AD: JOC 14.033.041 MAINO | 150F | CLOSED | 35268.8692 | 0 | 35268.8692 | 35268.8692
PJ0005232 | SR 14/15: REPLACE STAIRS, WALKWAYS, BUTTRESSES - BLD 150F | LAMPMAN, GREG | CLOSED | 2015-03-06 | AD: STATE FIRE MARSHAL | 150F | CLOSED | 0 | 0 | 174.6347 | 174.6347
PJ0005232 | SR 14/15: REPLACE STAIRS, WALKWAYS, BUTTRESSES - BLD 150F | LAMPMAN, GREG | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 150F | CLOSED | 3555.14 | 0 | 0 | 0
PJ0005232 | SR 14/15: REPLACE STAIRS, WALKWAYS, BUTTRESSES - BLD 150F | LAMPMAN, GREG | CLOSED | 2015-03-06 | IN: SR 14/15: REPLACE STAIRS, WALKWAYS, BUTTRESSES - BLD 150F | 150F | CLOSED | 282.576 | 0 | 1059.66 | 1059.66
PJ0005232 Total | [7 empty] | 39106.5852 | 0 | 36503.1639 | 36503.1639
PJ0005231 | SR 14/15: CAMPUS GAS LINE REPAIRS & NEW LIBRARY CHILLED H2O LINE | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | AD: GF GARCIA AND SONS | GENERAL | CLOSED | 35825.74 | 0 | 35825.74 | 35825.74
PJ0005231 | SR 14/15: CAMPUS GAS LINE REPAIRS & NEW LIBRARY CHILLED H2O LINE | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 3857.63 | 0 | 0 | 0
PJ0005231 | SR 14/15: CAMPUS GAS LINE REPAIRS & NEW LIBRARY CHILLED H2O LINE | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | EL: Support & Utility Marking | GENERAL | CLOSED | 358.2197 | 0 | 660.387 | 660.387
PJ0005231 | SR 14/15: CAMPUS GAS LINE REPAIRS & NEW LIBRARY CHILLED H2O LINE | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | IN: SR 14/15: DESIGN & REVIEW PIPES -LIBRARY/CAMPUS WIDE | GENERAL | CLOSED | 211.932 | 0 | 105.966 | 105.966
PJ0005231 | SR 14/15: CAMPUS GAS LINE REPAIRS & NEW LIBRARY CHILLED H2O LINE | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | LA: Support & Utility Marking | GENERAL | CLOSED | 222.5779 | 0 | 207.5478 | 207.5478
PJ0005231 | SR 14/15: CAMPUS GAS LINE REPAIRS & NEW LIBRARY CHILLED H2O LINE | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | PL: Support & Utility Marking | GENERAL | CLOSED | 4794.0562 | 0 | 2413.62 | 2413.62
PJ0005231 Total | [7 empty] | 45270.1558 | 0 | 39213.2608 | 39213.2608
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | AD: JOC 16.037.003 MAINO | 042A | CLOSED | 105476.5233 | 0 | 105476.3521 | 105476.3521
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | AD: STATE FIRE MARSHAL FEES | 042A | CLOSED | 1284 | 0 | 237.5293 | 237.5293
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 7565.63 | 0 | 0 | 0
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | CPE: | 042A | CLOSED | 262.656 | 0 | 98.496 | 98.496
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | CU:CONTRACTOR SUPPORT DURING CONSTRUCTION- 42A ANDERSON POOL | 042A | CLOSED | 515.7768 | 0 | 200.952 | 200.952
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | EL: RELOCATE EXISTING ELECTRICAL TO SCOREBOARD FOR ROOF BLD43A | 042A | CLOSED | 1330.4496 | 0 | 2725.848 | 2725.848
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | IN: SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | 042A | CLOSED | 847.728 | 0 | 706.44 | 706.44
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | PA:PAINT NEW ROOF OF ANDERSON AQUATIC FILTRATION ROOM | 042A | CLOSED | 5054.838 | 0 | 5043.15 | 5043.15
PJ0005229 | SR 15/16: ADD ROOF OVER TANK & CONNECT TO SEWER - BLD 42A | MOLLAN, CHERYL L. | CLOSED | 2015-03-06 | PL:CONFIRM CONNECTION OF DRAINAGE FROM POOL BACKWASH TANK | 042A | CLOSED | 3179.52 | 0 | 7950.328 | 7950.328
PJ0005229 Total | [7 empty] | 125517.1217 | 0 | 122439.0954 | 122439.0954
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | AD: ASAP | U-UDOR | OPEN | 0 | 0 | 54.3025 | 54.3025
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | AD: G.F. GARCIA AND SONS | U-UDOR | OPEN | 47090.4111 | 0 | 47090.4111 | 47090.4111
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | AD: GOSS ENGINEERING | U-UDOR | OPEN | 10058 | 0 | 10058 | 10058
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | CP: PROJECT CONTINGENCY | U-UDOR | OPEN | 10221.56 | 0 | 0 | 0
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | CPE: SUPPORT & MARK UTILITIES | U-UDOR | OPEN | 438.6355 | 0 | 361.152 | 361.152
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | EH&S: | U-UDOR | OPEN | 200.1845 | 0 | 0 | 0
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | EL: SUPPORT & INSTALLATION OF POWER/CONTROLS KOLEGRAFF | U-UDOR | LONG_TERM | 19919.022 | 0 | 18948.888 | 18948.888
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | EO: Excavation for power at building 46 - see Ken Kolegraff | U-UDOR | COMPLETE | 2654.88 | 0 | 1665.288 | 1665.288
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | IN: DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | U-UDOR | ASSIGNED | 353.22 | 0 | 211.932 | 211.932
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | LA: PROVIDE SUPPORT AND TRIM HEDGES | U-UDOR | COMPLETE | 1268.1341 | 0 | 833.658 | 833.658
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | PL: INSTALLATION OF NEW SUMP PUMP SYSTEM - KOLEGRAFF | U-UDOR | ASSIGNED | 70337.2344 | 0 | 53486.6494 | 53486.6494
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | PM: DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005227 | DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-06 | SM: DM 15/16: CONNECT UTILIDOR SUMP PUMPS TO SANITARY SEWER | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005227 Total | [7 empty] | 162541.2816 | 0 | 132710.281 | 132710.281
PJ0005225 | SR 15/16: EVAL CODE UPGRADE STAIR RISERS - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2015-03-06 | AD: PROJECT MANAGEMENT FEES | GENERAL | CLOSED | 0 | 0 | 10000 | 10000
PJ0005225 | SR 15/16: EVAL CODE UPGRADE STAIR RISERS - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005225 | SR 15/16: EVAL CODE UPGRADE STAIR RISERS - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2015-03-06 | PM: SR 15/16: EVAL CODE UPGRADE STAIR RISERS - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005225 Total | [7 empty] | 0 | 0 | 10000 | 10000
PJ0005224 | SR 15/16: EVAL CODE UPGRADE GUARD/HAND RAILS - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2015-03-06 | AD: PROJECT COORDINATION FEES | GENERAL | CLOSED | 0 | 0 | 10000 | 10000
PJ0005224 | SR 15/16: EVAL CODE UPGRADE GUARD/HAND RAILS - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005224 | SR 15/16: EVAL CODE UPGRADE GUARD/HAND RAILS - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2015-03-06 | PM: SR 15/16: EVAL CODE UPGRADE GUARD/HAND RAILS - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005224 Total | [7 empty] | 0 | 0 | 10000 | 10000
PJ0005223 | DM 15/16: CAMPUS ROAD REPAIR | NORTON, DAVE | CLOSED | 2015-03-06 | AD: (SP FUNDING) JOC 14.033.042 MAINO | STREETS | CLOSED | 126176.2832 | 0 | 126175.1811 | 126175.1811
PJ0005223 | DM 15/16: CAMPUS ROAD REPAIR | NORTON, DAVE | CLOSED | 2015-03-06 | AD: (SP FUNDING) JOC 15.035.008 MAINO | STREETS | CLOSED | 34819.8116 | 0 | 34819.8116 | 34819.8116
PJ0005223 | DM 15/16: CAMPUS ROAD REPAIR | NORTON, DAVE | CLOSED | 2015-03-06 | AD: (SR FUNDING) JOC 14.034.007 MAINO | STREETS | CLOSED | 325781.0168 | 0 | 325781.0168 | 325781.0168
PJ0005223 | DM 15/16: CAMPUS ROAD REPAIR | NORTON, DAVE | CLOSED | 2015-03-06 | CP: (SP FUNDING) PROJECT CONTINGENCY | STREETS | CLOSED | 15793.49 | 0 | 0 | 0
PJ0005223 | DM 15/16: CAMPUS ROAD REPAIR | NORTON, DAVE | CLOSED | 2015-03-06 | IN: (SR FUNDING) SR 15/16, SP 15/16: CAMPUS ROAD REPAIR | STREETS | CLOSED | 282.576 | 0 | 247.254 | 247.254
PJ0005223 | DM 15/16: CAMPUS ROAD REPAIR | NORTON, DAVE | CLOSED | 2015-03-06 | LA: (SP FUNDING) TRIM TREES | STREETS | CLOSED | 320.256 | 0 | 200.16 | 200.16
PJ0005223 Total | [7 empty] | 503173.4336 | 0 | 487223.4235 | 487223.4235
PJ0005222 | SR 15/16: REPAIR ROOF LEAKS - LOWER SCALLOPED AREA - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | AD: JOC 14.034.011 MAINO | 042 | CLOSED | 171388.6624 | 0 | 171388.6624 | 171388.6624
PJ0005222 | SR 15/16: REPAIR ROOF LEAKS - LOWER SCALLOPED AREA - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 17497 | 0 | 0 | 0
PJ0005222 | SR 15/16: REPAIR ROOF LEAKS - LOWER SCALLOPED AREA - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | IN: SR 15/16: REPAIR ROOF LEAKS - LOWER SCALLOPED AREA - BLD 42 | 042 | CLOSED | 1130.304 | 0 | 529.83 | 529.83
PJ0005222 Total | [7 empty] | 190015.9664 | 0 | 171918.4924 | 171918.4924
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: KNECHTS PLUMBING | 042 | CLOSED | 15290.3 | 0 | 14436.6861 | 14436.6861
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: QUAGLINO ROOFING | 042 | CLOSED | 5350 | 0 | 1872.5 | 1872.5
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | CA: SUPPORT FOR ROOF REPAIRS - BLD 42 | 042 | CLOSED | 926.5596 | 0 | 222.48 | 222.48
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 152.68 | 0 | 0 | 0
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | ES: SUPPORT / OBSERVATION | 042 | CLOSED | 584.4096 | 0 | 98.496 | 98.496
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | IN: SR 15/16: REPAIR ROOF LEAKS - BLD 42 | 042 | CLOSED | 157.5361 | 0 | 70.644 | 70.644
PJ0005221 | SR 15/16: REPAIR ROOF LEAKS - BLD 42 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | PM: SR 15/16: REPAIR ROOF LEAKS - BLD 42 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005221 Total | [7 empty] | 22461.4853 | 0 | 16700.8061 | 16700.8061
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | AD: ASAP REPROGRAPHICS & SHIPPING | 035 | CLOSED | 0 | 0 | 20.0625 | 20.0625
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 1605 | 0 | 1178.7976 | 1178.7976
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | AD: TYCO SIMPLEX GRINNELL | 035 | CLOSED | 39123.48 | 0 | 39123.48 | 39123.48
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | CP: PROJECT CONTINGENCY | 035 | OPEN | 4149.61 | 0 | 0 | 0
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | EL: SUPPORT FOR FIRE ALARM DESIGN BLDG 35 - KOLEGRAFF | 035 | CLOSED | 354.354 | 0 | 128.856 | 128.856
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | IN: SR 15/16: REPLACE FIRE ALARM - BLD 35 | 035 | CLOSED | 77.7084 | 0 | 70.644 | 70.644
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | PM: SR 15/16: REPLACE FIRE ALARM - BLD 35 | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0005220 | SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | KOLEGRAFF, KENNETH | DESGN_COMP | 2015-03-06 | SM: SR 15/16: DESIGN FOR FIRE ALARM REPLACEMENT - BLD 35 | 035 | OPEN | 0 | 0 | 0 | 0
PJ0005220 Total | [7 empty] | 45310.1524 | 0 | 40521.8401 | 40521.8401
PJ0005219 | SR 15/16: REPLACE PENTHOUSE ROOF - BLD 34 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | AD: JOC 14.034.013 MAINO | 034 | CLOSED | 86991.4601 | 0 | 86991.4601 | 86991.4601
PJ0005219 | SR 15/16: REPLACE PENTHOUSE ROOF - BLD 34 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 9055.34 | 0 | 0 | 0
PJ0005219 | SR 15/16: REPLACE PENTHOUSE ROOF - BLD 34 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | IN: SR 15/16: REPLACE PENTHOUSE ROOF - BLD 34 | 034 | CLOSED | 1130.304 | 0 | 423.864 | 423.864
PJ0005219 | SR 15/16: REPLACE PENTHOUSE ROOF - BLD 34 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | LO: CHANGE ROOF ACCESS LOCK TO ORANGE CORE - DEXTER PENTHSE ROOF | 034 | CLOSED | 54.462 | 0 | 60.924 | 60.924
PJ0005219 Total | [7 empty] | 97231.5661 | 0 | 87476.2481 | 87476.2481
PJ0005218 | SR 15/16: INSTALL CLEAN-OUTS ON SANITARY SEWER LINE - BLDG 20 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: STATE FIRE MARSHAL FEES (NO FEES) | 020 | CLOSED | 267.5 | 0 | 0 | 0
PJ0005218 | SR 15/16: INSTALL CLEAN-OUTS ON SANITARY SEWER LINE - BLDG 20 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 1867.52 | 0 | 0 | 0
PJ0005218 | SR 15/16: INSTALL CLEAN-OUTS ON SANITARY SEWER LINE - BLDG 20 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | IN: INSTALL CLEAN-OUTS ON SANITARY SEWER LINE - BLDG 20 | 020 | CLOSED | 628.7316 | 0 | 141.288 | 141.288
PJ0005218 | SR 15/16: INSTALL CLEAN-OUTS ON SANITARY SEWER LINE - BLDG 20 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | JOC 15.035.021 MAINO | 020 | CLOSED | 13635.8125 | 0 | 10692.831 | 10692.831
PJ0005218 | SR 15/16: INSTALL CLEAN-OUTS ON SANITARY SEWER LINE - BLDG 20 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | PL: INSTALL CLEANOUT AT BLDG. 20 | 020 | CLOSED | 3796.4177 | 0 | 1844.1 | 1844.1
PJ0005218 Total | [7 empty] | 20195.9818 | 0 | 12678.219 | 12678.219
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | AD: COASTAL JANITORIAL | 005 | CLOSED | 963 | 0 | 963 | 963
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | AD: JOC 14.034.012 MAINO | 005 | CLOSED | 358786.6434 | 0 | 358786.6434 | 358786.6434
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | AD: JOC 15.035.004 MAINO | 005 | CLOSED | 8113.5318 | 0 | 8113.5318 | 8113.5318
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 23877.03 | 0 | 0 | 0
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | IN: SR 15/16: RE-ROOF - BLD 5 | 005 | CLOSED | 1130.304 | 0 | 459.186 | 459.186
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | LA: REPAIR DEXTER LAWN SPRINKLER | 005 | CLOSED | 140.064 | 0 | 80.064 | 80.064
PJ0005216 | DM 15/16: RE-ROOF - BLD 5 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-06 | PL: REMOVE AND RE-INSTALL SOLAR PANEL FOR ROOFING PROJECT | 005 | CLOSED | 3064.3697 | 0 | 1560.012 | 1560.012
PJ0005216 Total | [7 empty] | 396074.9429 | 0 | 369962.4372 | 369962.4372
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: ATASCADERO GLASS | 001 | CLOSED | 3541.7 | 0 | 2921.1 | 2921.1
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: JOC 15.035.022. MAINO | 001 | CLOSED | 148693.6735 | 0 | 148693.6735 | 148693.6735
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: JOC 16.038.007 MAINO | 001 | CLOSED | 0 | 0 | 13141.7079 | 13141.7079
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: MCKENNA | 001 | CLOSED | 3798.5 | 0 | 1958.1 | 1958.1
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 267.5 | 0 | 0 | 0
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | CA: SUPPORT FOR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | 001 | CLOSED | 965.007 | 0 | 287.985 | 287.985
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 15449.64 | 0 | 0 | 0
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | ES: PJ5215 - SHUTDOWN HVAC - ADMIN 001 - 9/10/16 -WO0770420 | 001 | CLOSED | 584.4096 | 0 | 164.16 | 164.16
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | IN: SR 15/16: REPAIR LEAKING WALL PANELS, S TOWER WALL - ADM 01 | 001 | CLOSED | 1398.7512 | 0 | 459.186 | 459.186
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | LA: SUPPLY WATER ACCESS | 001 | CLOSED | 89.2714 | 0 | 40.032 | 40.032
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | PA: PAINT WALL PANEL RM 414 AND 401B | 001 | CLOSED | 615.264 | 0 | 185.724 | 185.724
PJ0005215 | SR 15/16: REPAIR LEAKING WALL PANELS, SOUTH TOWER WALL - ADM 01 | MARCHESE, JASON (WILL) | CLOSED | 2015-03-06 | PM: SR 15/16: REPAIR LEAKING WALL PANELS,S. TOWER WALL-ADM 01 | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0005215 Total | [7 empty] | 175403.7167 | 0 | 167851.6684 | 167851.6684
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | AD: BOBS CRANE | U-UDOR | CLOSED | 1070 | 0 | 294.25 | 294.25
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | AD: HPS MECHANICAL | U-UDOR | CLOSED | 48150 | 0 | 47955.367 | 47955.367
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | CA: PREP & CAULK UTILIDOR LID JOINTS AFTER WORK COMPLETION | U-UDOR | CLOSED | 1485.6102 | 0 | 2586.552 | 2586.552
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 5472.45 | 0 | 0 | 0
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | IN: INSTALL VAULT & VALVES - ENGINEERING WEST | U-UDOR | CLOSED | 314.3658 | 0 | 176.61 | 176.61
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | LA: LANDSCAPE REPAIRS AFTER UTILIDOR VALVE REPLACEMENT BLG. 21 | U-UDOR | CLOSED | 1012.9699 | 0 | 308.232 | 308.232
PJ0005214 | SR 15/16: INSTALL UTILIDOR VAULT & VALVES - ENGINEERING WEST | KOLEGRAFF, KENNETH | CLOSED | 2015-03-06 | PL: UTILIDOR VALVE REPLACEMENT SUPPORT | U-UDOR | CLOSED | 286.9716 | 0 | 1066.332 | 1066.332
PJ0005214 Total | [7 empty] | 57792.3675 | 0 | 52387.343 | 52387.343
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | AD: (FUNDED FROM MINOR CAP, PER JOEL) JOC 16.037.015 MAINO | POLY-P | CLOSED | 54364.453 | 0 | 54364.453 | 54364.453
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | AD: (SL001-SR) SIGN PLACE | POLY-P | CLOSED | 530.7521 | 0 | 530.7521 | 530.7521
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | AD: CAL POLY FARM OPS | POLY-P | CLOSED | 1686.2451 | 0 | 1686.2451 | 1686.2451
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | AD: CALIFORNIA CONSERVATION CORP | POLY-P | CLOSED | 116324.2368 | 0 | 116324.2368 | 116324.2368
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | AD: MATERIALS FOR CALIFORNIA CONSERVATION CORP. | POLY-P | CLOSED | 22665.0717 | 0 | 22665.0717 | 22665.0717
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | CA: DUNN - POLY P TRAILHEAD KIOSK | POLY-P | CLOSED | 4877.28 | 0 | 4768.9432 | 4768.9432
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | CP: (SL001-SR) PROJECT CONTINGENCY | POLY-P | CLOSED | 304.98 | 0 | 0 | 0
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | CP: PROJECT CONTINGENCY | POLY-P | OPEN | 0.45 | 0 | 0 | 0
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | EO:DUNN - POLY P TRAILHEAD KIOSK | POLY-P | CLOSED | 1342.3504 | 0 | 1353.708 | 1353.708
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | IN: SR 15/16: IMPROVE POLY P PATH & STRUCTURE | POLY-P | CLOSED | 494.508 | 0 | 494.508 | 494.508
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | MO: MOVE 1 PALLET OF BUILDING MATERIAL FROM DIST SVCS TO R-1 LOT | POLY-P | CLOSED | 16.758 | 0 | 16.902 | 16.902
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | PM: IMPROVE POLY P PATH & STRUCTURE | POLY-P | CLOSED | 0 | 0 | 0 | 0
PJ0005211 | IMPROVE POLY P PATH & STRUCTURE | DUNN, TRAVIS | CONST_COMP | 2015-03-06 | SM: IMPROVE POLY P PATH & STRUCTURE | POLY-P | OPEN | 0 | 0 | 0 | 0
PJ0005211 Total | [7 empty] | 202607.0851 | 0 | 202204.8199 | 202204.8199
PJ0005210 | SR 15/16: INSTALL GAS ISOLATION VALVE AT CENTRAL PLANT - BLD 40 | GONZALES, ALBERT | CLOSED | 2015-03-05 | AD: RICK TIEXIERA WELDING | 040 | CLOSED | 4922 | 0 | 4922 | 4922
PJ0005210 | SR 15/16: INSTALL GAS ISOLATION VALVE AT CENTRAL PLANT - BLD 40 | GONZALES, ALBERT | CLOSED | 2015-03-05 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 1556.61 | 0 | 0 | 0
PJ0005210 | SR 15/16: INSTALL GAS ISOLATION VALVE AT CENTRAL PLANT - BLD 40 | GONZALES, ALBERT | CLOSED | 2015-03-05 | CPE: CONTRACTOR SUPPORT FOR GAS SHUT DOWN | 040 | CLOSED | 3222.7046 | 0 | 590.976 | 590.976
PJ0005210 | SR 15/16: INSTALL GAS ISOLATION VALVE AT CENTRAL PLANT - BLD 40 | GONZALES, ALBERT | CLOSED | 2015-03-05 | IN: SR 15/16: INSTALL GAS ISOLATION VALVE AT CEN PLANT - BLD 40 | 040 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005210 | SR 15/16: INSTALL GAS ISOLATION VALVE AT CENTRAL PLANT - BLD 40 | GONZALES, ALBERT | CLOSED | 2015-03-05 | PA: REPAINT WELD AREA ON GAS SUPPLY PIPING | 040 | CLOSED | 1282.5815 | 0 | 185.724 | 185.724
PJ0005210 | SR 15/16: INSTALL GAS ISOLATION VALVE AT CENTRAL PLANT - BLD 40 | GONZALES, ALBERT | CLOSED | 2015-03-05 | PL: CONTRACTOR ASSIST WITH GAS VALVE INSTALLATION | 040 | CLOSED | 3953.2543 | 0 | 2047.428 | 2047.428
PJ0005210 Total | [7 empty] | 15078.4384 | 0 | 7816.772 | 7816.772
PJ0005209 | HANG BANNERS & PICTURES, REMOVE BLINDS, PAINT BLDG 52 RM E04 | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | CA: HANG BANNER & PICTURES, REPLACE CEILING TILES | 052 | CLOSED | 474.96 | 0 | 144.654 | 144.654
PJ0005209 | HANG BANNERS & PICTURES, REMOVE BLINDS, PAINT BLDG 52 RM E04 | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0005209 | HANG BANNERS & PICTURES, REMOVE BLINDS, PAINT BLDG 52 RM E04 | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | IN: HANG BANNERS & PICTURES, REMOVE BLINDS, PAINT BLDG 52 RM E04 | 052 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005209 | HANG BANNERS & PICTURES, REMOVE BLINDS, PAINT BLDG 52 RM E04 | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | PA: TOUCH UP PAINT ON WINDOW FRAME | 052 | CLOSED | 138.0548 | 0 | 185.724 | 185.724
PJ0005209 Total | [7 empty] | 683.6588 | 0 | 365.7 | 365.7
PJ0005208 | REPAIR MAGNETIC RELEASE SYSTEM ON FIRE DOORS - UNIVERSITY STORE | MOLLAN, CHERYL L. | CLOSED | 2015-02-10 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 0 | 0 | 148.1736 | 148.1736
PJ0005208 | REPAIR MAGNETIC RELEASE SYSTEM ON FIRE DOORS - UNIVERSITY STORE | MOLLAN, CHERYL L. | CLOSED | 2015-02-10 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0005208 | REPAIR MAGNETIC RELEASE SYSTEM ON FIRE DOORS - UNIVERSITY STORE | MOLLAN, CHERYL L. | CLOSED | 2015-02-10 | IN: REPAIR MAGNETIC RELEASE SYSTEM ON FIRE DOORS - U STORE | 065 | CLOSED | 70.644 | 0 | 105.966 | 105.966
PJ0005208 | REPAIR MAGNETIC RELEASE SYSTEM ON FIRE DOORS - UNIVERSITY STORE | MOLLAN, CHERYL L. | CLOSED | 2015-02-10 | LO:REPAIR DOOR HINGES TO RELEASE FIRE DOOR BLDG 65, 0101-C | 065 | CLOSED | 343.1118 | 0 | 157.848 | 157.848
PJ0005208 Total | [7 empty] | 413.7558 | 0 | 411.9876 | 411.9876
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | AD: ASAP REPROGRAPHICS | GENERAL | CLOSED | 0 | 0 | 146.7505 | 146.7505
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | AD: EARTH SYSTEMS PACIFIC | GENERAL | CLOSED | 19789.65 | 0 | 5877.51 | 5877.51
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | AD: NEWTON MIN-17-DM5206 | GENERAL | CLOSED | 898979.76 | 0 | 849680.58 | 849680.58
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | AD: STATE FIRE MARSHAL FEES | GENERAL | CLOSED | 535 | 0 | 204.8622 | 204.8622
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | AD: WALLACE GROUP | GENERAL | CLOSED | 56068 | 0 | 48231.0418 | 48231.0418
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 91629.47 | 0 | 0 | 0
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | EL: MARK UTILITIES AND PROVIDE SUPPORT CAMPUS GENERAL- KOLEGRAFF | GENERAL | CLOSED | 1417.416 | 0 | 1491.39 | 1491.39
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | ES: MARK UTILITES AND PROVIDE SUPPORT - KOLEGRAFF | GENERAL | CLOSED | 1444.608 | 0 | 716.724 | 716.724
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | IN: DM 15/16: INSTALL GAS ISOLATION VALVES - CAMPUS WIDE | GENERAL | CLOSED | 635.796 | 0 | 1130.304 | 1130.304
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | LA: MARK UTILITIES AND PROVIDE SUPPORT & REPAIRS - KOLEGRAFF | GENERAL | CLOSED | 2080.704 | 0 | 1483.4116 | 1483.4116
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | LO: SUPPLY FOUR 2359 LOCKS FOR THE GAS REG STATION | GENERAL | CLOSED | 120 | 0 | 36 | 36
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | PL: GAS LINE REPLACEMENT SUPPORT - KOLEGRAFF | GENERAL | CLOSED | 31761.8609 | 0 | 33185.1498 | 33185.1498
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | PM: DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005206 | DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | KOLEGRAFF, KENNETH | CONST_COMP | 2015-03-02 | SM: DM 16/17: GAS LINE REPLACEMENTS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005206 Total | [7 empty] | 1104462.2649 | 0 | 942183.7238 | 942183.7238
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | AD: AL'S PUMP | GENERAL | CLOSED | 19527.5 | 0 | 19526.002 | 19526.002
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | AD: FLUID RESOURCE MANAGEMENT | GENERAL | CLOSED | 17120 | 0 | 19161.453 | 19161.453
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | AD: WESTERN OILFIELDS SUPPLY | GENERAL | CLOSED | 8881 | 0 | 8869.0267 | 8869.0267
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | CA: Demo Door Barricade & Reinstall (E) Door | GENERAL | CLOSED | 222.48 | 0 | 55.62 | 55.62
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 4991.18 | 0 | 0 | 0
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | CPE: SUPPORT ANDERSON POOL PUMP REPLACEMENT | GENERAL | CLOSED | 2192.521 | 0 | 2104.53 | 2104.53
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | EL: SUPPORT BACK-UP PUMP REPLACEMENT - 42A ANDERSON POOL | GENERAL | CLOSED | 573.4092 | 0 | 0 | 0
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | ES: | GENERAL | CLOSED | 72.887 | 0 | 0 | 0
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | IN: SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | GENERAL | CLOSED | 70.644 | 0 | 141.288 | 141.288
PJ0005205 | SP 15/16: REPLACE BACKUP PUMP ¿ ANDERSON POOL 42A | KOLEGRAFF, KENNETH | CLOSED | 2015-03-02 | PL: SUPPORT BACK-UP PUMP REPLACEMENT - 42A ANDERSON POOL | GENERAL | CLOSED | 2875.5029 | 0 | 3123.42 | 3123.42
PJ0005205 Total | [7 empty] | 56527.1241 | 0 | 52981.3397 | 52981.3397
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | AD: COASTAL DEMO | 040 | OPEN | 1000.0006 | 0 | 0 | 0
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | AD: GOSS ENGINEERING | 040 | OPEN | 23326 | 2503.8 | 10015.2 | 12519
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | AD: STATE FIRE MARSHAL FEES | 040 | OPEN | 2675 | 0 | 260.3631 | 260.3631
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | CP: PROJECT CONTINGENCY | 040 | OPEN | 4177.87 | 0 | 0 | 0
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | CPE: PJ#5204 - SUPPORT PORTABLE GENERATOR CONNECTION PROJECT | 040 | OPEN | 2325.1622 | 0 | 0 | 0
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | EH&S: | 040 | OPEN | 572.8752 | 0 | 0 | 0
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | EL: PJ#5204 - PORTABLE GENERATOR CONNECTION AT CENTRAL PLANT | 040 | LONG_TERM | 20834.5427 | 0 | 9251.154 | 9251.154
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | IN: SP 15/16: INSTALL GENERATOR ¿ CENTRAL PLANT BLDG 40 | 040 | ASSIGNED | 1243.3344 | 0 | 70.644 | 70.644
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | PM: SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005204 | SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | KOLEGRAFF, KENNETH | IN_CONSTR | 2015-03-02 | SM: SP 15/16: GENERATOR QUICK DISCONNECT - CENTRAL PLANT BLDG 40 | 040 | OPEN | 0 | 0 | 0 | 0
PJ0005204 Total | [7 empty] | 56154.7851 | 2503.8 | 19597.3611 | 22101.1611
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | AD: JOC 16.037.023 MAINO | 010 | CLOSED | 149478.5506 | 0 | 149478.5506 | 149478.5506
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | AD: MCKENNA | 010 | CLOSED | 3840.23 | 0 | 3578.08 | 3578.08
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | AD: PMSM | 010 | CLOSED | 11502.5 | 0 | 10733.5766 | 10733.5766
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 4786.13 | 0 | 0 | 0
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | EL: BLDG. 10-145A &146A GREG LAMPMAN- CONTRACTOR SUPPORT | 010 | CLOSED | 1537.416 | 0 | 1507.098 | 1507.098
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | IN: FP 15/16: CREATE ADA RESTROOMS ¿ BLDGS. 10 & 22, SP5203 | 010 | CLOSED | 353.22 | 0 | 353.22 | 353.22
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | LO: BLDG. 10-146A &145A INSTALL NEW LOCK | 010 | CLOSED | 372.4656 | 0 | 1274.04 | 1274.04
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | PA: BLDG. 10-145A & 146A GREG LAMPMAN PAINT RESTROOM | 010 | CLOSED | 4168.7424 | 0 | 1145.298 | 1145.298
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | PL: BLDG. 10-145A & 146A GREG LAMPMAN CONTRACTOR SUPPORT | 010 | CLOSED | 2242.4832 | 0 | 2449.578 | 2449.578
PJ0005203 | FP 15/16: CREATE ADA RESTROOMS ¿ BLDG. 10 | LAMPMAN, GREG | CLOSED | 2015-03-02 | PM: FP 15/16: CREATE ADA RESTROOMS - BLDG. 10 | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0005203 Total | [7 empty] | 178281.7378 | 0 | 170519.4412 | 170519.4412
PJ0005202 | SP 15/16: REPLACE PURLINS, FINAL PHASE, 2 SM SHED ROOFS¿BLD 18 | LAMPMAN, GREG | CLOSED | 2015-03-02 | AD: JOC 14.034.025 MAINO | 018 | CLOSED | 111047.9491 | 0 | 111047.9491 | 111047.9491
PJ0005202 | SP 15/16: REPLACE PURLINS, FINAL PHASE, 2 SM SHED ROOFS¿BLD 18 | LAMPMAN, GREG | CLOSED | 2015-03-02 | AD: JOC 15.035.006 MAINO | 018 | CLOSED | 14978.1168 | 0 | 14978.1168 | 14978.1168
PJ0005202 | SP 15/16: REPLACE PURLINS, FINAL PHASE, 2 SM SHED ROOFS¿BLD 18 | LAMPMAN, GREG | CLOSED | 2015-03-02 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 0 | 0 | 0 | 0
PJ0005202 | SP 15/16: REPLACE PURLINS, FINAL PHASE, 2 SM SHED ROOFS¿BLD 18 | LAMPMAN, GREG | CLOSED | 2015-03-02 | EL: REMOVE LIGHTS AND REPLACE AFTER NEW PURLINS | 018 | CLOSED | 573.4092 | 0 | 3042.438 | 3042.438
PJ0005202 | SP 15/16: REPLACE PURLINS, FINAL PHASE, 2 SM SHED ROOFS¿BLD 18 | LAMPMAN, GREG | CLOSED | 2015-03-02 | IN: SP 15/16: REPL. PURLINS, FINAL PH, 2 SM SHED ROOFS¿BLD 18 | 018 | CLOSED | 282.576 | 0 | 211.932 | 211.932
PJ0005202 Total | [7 empty] | 126882.0511 | 0 | 129280.4359 | 129280.4359
PJ0005201 | SP 15/16: RE-ROOF - BLDG 22 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-02 | AD: JOC 14.034.010 MAINO | 022 | CLOSED | 134644.1562 | 0 | 134644.1562 | 134644.1562
PJ0005201 | SP 15/16: RE-ROOF - BLDG 22 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-02 | CP: PROJECT CONTINGENCY | 022 | CLOSED | 13766.67 | 0 | 0 | 0
PJ0005201 | SP 15/16: RE-ROOF - BLDG 22 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-02 | IN: SP 15/16: RE-ROOF - BLDG 22 | 022 | CLOSED | 1130.304 | 0 | 247.254 | 247.254
PJ0005201 | SP 15/16: RE-ROOF - BLDG 22 | KUENTZEL, DOUGLAS A. | CLOSED | 2015-03-02 | LO: CHANGE ROOF ACCESS LOCK TO ORANGE CORE - BLDG 22 | 022 | CLOSED | 54.462 | 0 | 60.924 | 60.924
PJ0005201 Total | [7 empty] | 149595.5922 | 0 | 134952.3342 | 134952.3342
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | AD: ASAP REPORGRAPHICS | U-UDOR | OPEN | 0 | 0 | 1333.21 | 1333.21
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | AD: DIGITAL ENERGY (NO OVERHEAD) | U-UDOR | OPEN | 0 | 39900 | 5100 | 45000
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | AD: GOSS ENGINEERING (NO OVERHEAD) | U-UDOR | OPEN | 0 | 75230 | 425770 | 501000
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | AD: GREENVALE TREE COMPANY | U-UDOR | OPEN | 0 | 0 | 2850 | 2850
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | AD: STATE FIRE MARSHAL FEES | U-UDOR | OPEN | 0 | 0 | 448.41 | 448.41
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CA: REBID, CONTRACTOR ASSISTANCE FOR UTILIDOR HOT WATER LINE PJ | U-UDOR | CLOSED | 0 | 0 | 150.594 | 150.594
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CA: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | COMPLETE | 0 | 0 | 3289.17 | 3289.17
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CA: TEMP BOILER INSTALLATION AT MOTT/ANDERSON POOL | U-UDOR | ASSIGNED | 0 | 0 | 984.564 | 984.564
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CP: PROJECT CONTINGENCY | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CPE: MJ-65 PREBID WALK UTILITY IDENTIFICATION | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CPE: REBID, CONTRACTOR ASSISTANCE | U-UDOR | OPEN | 0 | 0 | 52469.6742 | 52469.6742
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CPE: SUPPORT UTILIDOR HOT WATER LINE REPLACMENT - PHASE I | U-UDOR | CLOSED | 0 | 0 | 3159.546 | 3159.546
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CPE: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | ASSIGNED | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | CPE: TEMP BOILER INSTALLATION AT MOTT/ANDERSON POOL | U-UDOR | COMPLETE | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EH&S: REBID, CONTRACTOR ASSISTANCE | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: ELECTRICAL SUPPORT AT VIA CARTA FOR UTILIDOR PROJECT | U-UDOR | LONG_TERM | 0 | 0 | 1711.482 | 1711.482
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: LOCATE UTILITIES FOR UTILIDOR HOT WATER LINE REPLACMENT | U-UDOR | CLOSED | 0 | 0 | 70.872 | 70.872
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: MJ-65 PREBID WALK UTILITY IDENTIFICATION | U-UDOR | CLOSED | 0 | 0 | 5593.158 | 5593.158
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: REBID, CONTRACTOR ASSISTANCE | U-UDOR | LONG_TERM | 0 | 0 | 9881.664 | 9881.664
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: REPAIR WORK AT SIERRA MADRE FOR UTILIDOR WATER LINE PROJECT | U-UDOR | CLOSED | 0 | 0 | 10859.31 | 10859.31
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | EL: TEMP BOILER INSTALLATION AT MOTT/ANDERSON POOL | U-UDOR | CLOSED | 0 | 0 | 531.132 | 531.132
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | ES: LOCATE UTILITIES FOR UTILIDOR HOT WATER LINE REPLACMENT | U-UDOR | CLOSED | 0 | 0 | 15823.911 | 15823.911
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | ES: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | OPEN | 0 | 0 | 13861.0624 | 13861.0624
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | ES: TEMP BOILER INSTALLATION AT MOTT/ANDERSON POOL | U-UDOR | CLOSED | 0 | 0 | 14023.524 | 14023.524
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | ITS: MJ-65 PREBID WALK UTILITY IDENTIFICATION | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LA: LOCATE UTILITIES FOR UTILIDOR HOT WATER LINE REPLACMENT | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LA: MJ-65 PREBID WALK UTILITY IDENTIFICATION | U-UDOR | OPEN | 0 | 0 | 2825.7724 | 2825.7724
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LA: REBID, CONTRACTOR ASSISTANCE | U-UDOR | OPEN | 0 | 0 | 9342.7781 | 9342.7781
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LA: REPAIR WORK AT SIERRA MADRE FOR UTILIDOR WATER LINE PROJECT | U-UDOR | COMPLETE | 0 | 0 | 1604.8006 | 1604.8006
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LA: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | OPEN | 0 | 0 | 1709.896 | 1709.896
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LO: REBID, CONTRACTOR ASSISTANCE | U-UDOR | ASSIGNED | 0 | 0 | 578.778 | 578.778
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | LO: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | WORKING | 0 | 0 | 365.544 | 365.544
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | MO: CLEAR WORK AREA FOR UTILIDOR WATER LINE REPLACEMENT- PHASE I | U-UDOR | OPEN | 0 | 0 | 240 | 240
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | MO: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | PL: LOCATE UTILITIES FOR UTILIDOR HOT WATER LINE REPLACMENT | U-UDOR | OPEN | 0 | 0 | 4679.496 | 4679.496
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | PL: MJ-65 PREBID WALK UTILITY IDENTIFICATION | U-UDOR | PEND_SCHED | 0 | 0 | 2498.304 | 2498.304
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | PL: REBID, CONTRACTOR ASSISTANCE | U-UDOR | PEND_SCHED | 0 | 0 | 110163.5913 | 110163.5913
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | PL: SUPPORT UTILIDOR WATER LINE REPLACEMENT - PHASE II 2017 | U-UDOR | ASSIGNED | 0 | 0 | 38131.6208 | 38131.6208
PJ0005200 | MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | SODERIN, ERIC | IN_CONSTR | 2015-02-23 | SM: MJ: SUPPORT FOR UTILIDOR HOT WATER LINE REPLACEMENT | U-UDOR | OPEN | 0 | 0 | 0 | 0
PJ0005200 Total | [7 empty] | 0 | 115130 | 740051.8648 | 855181.8648
PJ0005199 | SP 14/15: IRRIGATION CONTROL RETROFIT (NO OVERHEAD) | HOSTICK, RONALD | CLOSED | 2015-02-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 12784.05 | 0 | 0 | 0
PJ0005199 | SP 14/15: IRRIGATION CONTROL RETROFIT (NO OVERHEAD) | HOSTICK, RONALD | CLOSED | 2015-02-13 | EL: SUPPORT IRRIGATION CONTROLLER INSTALLATIONS | GENERAL | CLOSED | 8321.95 | 0 | 2362.36 | 2362.36
PJ0005199 | SP 14/15: IRRIGATION CONTROL RETROFIT (NO OVERHEAD) | HOSTICK, RONALD | CLOSED | 2015-02-13 | LA: CALSENSE CONTROLLER INSTALLATION | GENERAL | CLOSED | 128137 | 0 | 151986.9761 | 151986.9761
PJ0005199 Total | [7 empty] | 149243 | 0 | 154349.3361 | 154349.3361
PJ0005198 | SP 14/15: LOW FLOW PLUMBING RETROFIT CAMUPS WIDE (STATE) | JUDD, PERRY | CONST_COMP | 2015-02-13 | AD: PACIFIC GAS AND ELECTRIC (NO OVERHEAD) | GENERAL | CLOSED | 133679 | 0 | 162162.94 | 162162.94
PJ0005198 | SP 14/15: LOW FLOW PLUMBING RETROFIT CAMUPS WIDE (STATE) | JUDD, PERRY | CONST_COMP | 2015-02-13 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 13799.97 | 0 | 0 | 0
PJ0005198 | SP 14/15: LOW FLOW PLUMBING RETROFIT CAMUPS WIDE (STATE) | JUDD, PERRY | CONST_COMP | 2015-02-13 | SM: SP 14/15: LOW FLOW PLUMBING RETROFIT CAMUPS WIDE (STATE) | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005198 Total | [7 empty] | 147478.97 | 0 | 162162.94 | 162162.94
PJ0005197 | RE-INSTALL DOOR, REMOVE ORGANIZER, PAINT - BLDG 10 RMS 133 & 134 | BRENNAN, MICHAEL | CLOSED | 2015-02-12 | CA: INSTALL DOOR IN EXIST JAMB | 010 | CLOSED | 915.018 | 0 | 824.604 | 824.604
PJ0005197 | RE-INSTALL DOOR, REMOVE ORGANIZER, PAINT - BLDG 10 RMS 133 & 134 | BRENNAN, MICHAEL | CLOSED | 2015-02-12 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 141.97 | 0 | 0 | 0
PJ0005197 | RE-INSTALL DOOR, REMOVE ORGANIZER, PAINT - BLDG 10 RMS 133 & 134 | BRENNAN, MICHAEL | CLOSED | 2015-02-12 | LO: INSTALL LOCKSET IN NEW DOOR | 010 | CLOSED | 435.8605 | 0 | 703.812 | 703.812
PJ0005197 | RE-INSTALL DOOR, REMOVE ORGANIZER, PAINT - BLDG 10 RMS 133 & 134 | BRENNAN, MICHAEL | CLOSED | 2015-02-12 | PA: TOUCHUP PAINT - BLDG 10 RMS 133 & 134 | 010 | CLOSED | 68.7179 | 0 | 185.724 | 185.724
PJ0005197 Total | [7 empty] | 1561.5664 | 0 | 1714.14 | 1714.14
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | CA: SUPPORT FOR CAMPUS WIDE HYDRATION STATION INSTALLATIONS | GENERAL | CLOSED | 854.016 | 0 | 711.684 | 711.684
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 4612.33 | 0 | 0 | 0
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | EL: PJ5196 - DISCONNECT BLDG 155 DRINKING FOUNTAIN - DUNN | GENERAL | CLOSED | 188.2428 | 0 | 291.096 | 291.096
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | IN: SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | GENERAL | CLOSED | 565.152 | 0 | 353.22 | 353.22
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | PL: CAMPUS WIDE INSTALLATION OF HYDRATION STATION | GENERAL | CLOSED | 44512.416 | 0 | 43868.052 | 43868.052
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | PM: SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005196 | SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | DUNN, TRAVIS | CONST_COMP | 2015-02-19 | SM: SP 14/15: INSTALL HYDRATION STATIONS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005196 Total | [7 empty] | 50732.1568 | 0 | 45224.052 | 45224.052
PJ0005195 | DETERMINE THE STRUCTURAL CAPACITY OF THE GRIDIRON - BLDG 006 PAC | LAMPMAN, GREG | CLOSED | 2015-02-19 | AD: BUEHLER AND BUEHLER | 006 | CLOSED | 1800 | 0 | 1800 | 1800
PJ0005195 | DETERMINE THE STRUCTURAL CAPACITY OF THE GRIDIRON - BLDG 006 PAC | LAMPMAN, GREG | CLOSED | 2015-02-19 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 199.66 | 0 | 0 | 0
PJ0005195 | DETERMINE THE STRUCTURAL CAPACITY OF THE GRIDIRON - BLDG 006 PAC | LAMPMAN, GREG | CLOSED | 2015-02-19 | IN: DETERMINE STRUCTURAL CAPACITY OF THE GRIDIRON - BLDG 006 PAC | 006 | CLOSED | 58.87 | 0 | 58.87 | 58.87
PJ0005195 Total | [7 empty] | 2058.53 | 0 | 1858.87 | 1858.87
PJ0005194 | LEAD CLEANUP OUTSIDE BLDG 004A (PAINT SCRAPED FROM BOAT TRAILER) | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | AD: MCKENNA ENVIRONMENTAL | 004A | CLOSED | 1893.9 | 0 | 1091.4 | 1091.4
PJ0005194 | LEAD CLEANUP OUTSIDE BLDG 004A (PAINT SCRAPED FROM BOAT TRAILER) | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | CP: PROJECT CONTINGENCY | 004A | CLOSED | 323.3 | 0 | 0 | 0
PJ0005194 | LEAD CLEANUP OUTSIDE BLDG 004A (PAINT SCRAPED FROM BOAT TRAILER) | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 004A | CLOSED | 0 | 0 | 25.2 | 25.2
PJ0005194 | LEAD CLEANUP OUTSIDE BLDG 004A (PAINT SCRAPED FROM BOAT TRAILER) | BRENNAN, MICHAEL | CLOSED | 2015-02-11 | EH&S: LEAD CLEAN-UP OUTSIDE BUILDING 04(N/L) | 004A | CLOSED | 1329.888 | 0 | 0 | 0
PJ0005194 Total | [7 empty] | 3547.088 | 0 | 1116.6 | 1116.6
PJ0005193 | INSTALL OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK - BLDG 180 RM 120 | NORTON, DAVE | CLOSED | 2014-11-06 | AD: STATE FIRE MARSHAL | 180 | CLOSED | 278.2 | 0 | 0 | 0
PJ0005193 | INSTALL OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK - BLDG 180 RM 120 | NORTON, DAVE | CLOSED | 2014-11-06 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 249.31 | 0 | 0 | 0
PJ0005193 | INSTALL OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK - BLDG 180 RM 120 | NORTON, DAVE | CLOSED | 2014-11-06 | EL: RE-ROUTE WIRE FOR ELECTRIC STRIKE | 180 | CLOSED | 526.7046 | 0 | 225.498 | 225.498
PJ0005193 | INSTALL OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK - BLDG 180 RM 120 | NORTON, DAVE | CLOSED | 2014-11-06 | IN: OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK- BLDG 180 RM 120 | 180 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005193 | INSTALL OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK - BLDG 180 RM 120 | NORTON, DAVE | CLOSED | 2014-11-06 | LO: OCCUPIED/VACANT DEADBOLT & KEYPAD LOCK - BLDG. 180 RM. 120 | 180 | CLOSED | 1546.9723 | 0 | 1321.8 | 1321.8
PJ0005193 Total | [7 empty] | 2742.4749 | 0 | 1653.264 | 1653.264
PJ0005192 | SR 14/15: INSTALL WATER TANK FENCE AT RESERVOIR #3 - BLDG 206 | POLVI, STEVEN | CLOSED | 2015-02-10 | AD: CENTRAL COAST FENCE | 206 | CLOSED | 17630.39 | 0 | 16150.58 | 16150.58
PJ0005192 | SR 14/15: INSTALL WATER TANK FENCE AT RESERVOIR #3 - BLDG 206 | POLVI, STEVEN | CLOSED | 2015-02-10 | CP: PROJECT CONTINGENCY | 206 | CLOSED | 1859.54 | 0 | 0 | 0
PJ0005192 | SR 14/15: INSTALL WATER TANK FENCE AT RESERVOIR #3 - BLDG 206 | POLVI, STEVEN | CLOSED | 2015-02-10 | EL: LOCATE UTILITIES NEAR NEW FENCE AT WATER TANK | 206 | CLOSED | 286.7046 | 0 | 257.712 | 257.712
PJ0005192 | SR 14/15: INSTALL WATER TANK FENCE AT RESERVOIR #3 - BLDG 206 | POLVI, STEVEN | CLOSED | 2015-02-10 | PL: LOCATE UTILITIES NEAR NEW FENCE AT WATER TAN | 206 | CLOSED | 286.9716 | 0 | 193.464 | 193.464
PJ0005192 Total | [7 empty] | 20063.6062 | 0 | 16601.756 | 16601.756
PJ0005191 | SR 14/15: PURCHASE/INSTALL GENERATOR - BLDG 47 | POLVI, STEVEN | CLOSED | 2015-02-11 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 3163.3 | 0 | 0 | 0
PJ0005191 | SR 14/15: PURCHASE/INSTALL GENERATOR - BLDG 47 | POLVI, STEVEN | CLOSED | 2015-02-11 | EL: PURCHASE AND INSTALL NEW GENERATOR | 047 | CLOSED | 31633.2827 | 0 | 34530.924 | 34530.924
PJ0005191 Total | [7 empty] | 34796.5827 | 0 | 34530.924 | 34530.924
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | AD: COASTAL DEMO | 051 | CLOSED | 3346.425 | 0 | 3346.425 | 3346.425
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | AD: ITS | 051 | CLOSED | 250 | 0 | 198.2 | 198.2
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | CA: BUILD SUMP PIT AT BASEMENT OF PRESIDENTS HOUSE | 051 | CLOSED | 3375.6462 | 0 | 8380.209 | 8380.209
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 1970.38 | 0 | 0 | 0
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | EL: SUMP PIT AT PRESIDENTS HOUSE | 051 | CLOSED | 7301.8576 | 0 | 1812.162 | 1812.162
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | IN: SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | 051 | CLOSED | 282.576 | 0 | 105.966 | 105.966
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | LA: SUMP PIT AT PRES RES PROJECT SUPPORT | 051 | CLOSED | 480.384 | 0 | 1027.44 | 1027.44
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | MO: ASSIST WITH THE REMOVAL OF ITEMS IN THE BASEMENT | 051 | CLOSED | 134.064 | 0 | 67.608 | 67.608
PJ0005190 | SR 15/16: REPLACE SUMP PUMP - UNIVERSITY HOUSE BLDG 051 | GONZALES, ALBERT | CLOSED | 2015-02-10 | PL: SUMP PIT AT PRESIDENTS RESIDENCE | 051 | CLOSED | 14741.3666 | 0 | 10619.3322 | 10619.3322
PJ0005190 Total | [7 empty] | 31882.6994 | 0 | 25557.3422 | 25557.3422
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | AD: FLOOR CONNECTION | 061 | CLOSED | 38750.05 | 0 | 38750.05 | 38750.05
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | AD: STATE FIRE MARSHAL | 061 | CLOSED | 0 | 0 | 148.1736 | 148.1736
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | CA: PREPARE FOR LOCKERS AND PAINT | 061 | CLOSED | 4635.6462 | 0 | 12382.0201 | 12382.0201
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 4134.03 | 0 | 0 | 0
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | EL: REPAIR LIGHTING, REMOVE OUTLETS | 061 | CLOSED | 286.7046 | 0 | 2680.782 | 2680.782
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | IN: RENOVATE SPANOS 012 (LOCKER ROOM) | 061 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | LO: INSTALL NEW HARDWARE AND CLOSER ON NEW DOOR | 061 | CLOSED | 3798.0841 | 0 | 3262.932 | 3262.932
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | PA: REPAINT PAINT SPANOS LOCKER ROOM | 061 | CLOSED | 13422.7194 | 0 | 3392.568 | 3392.568
PJ0005189 | RENOVATE SPANOS STADIUM LOCKER ROOM - BLDG. 61 RM. 12 | BRENNAN, MICHAEL | CLOSED | 2015-01-27 | PL: REMOVE FOUNTAINS & INSTALL HYDRATION STATION | 061 | CLOSED | 5153.2543 | 0 | 2206.044 | 2206.044
PJ0005189 Total | [7 empty] | 70463.0646 | 0 | 62999.1797 | 62999.1797
PJ0005188 | MODIFY LEFT FIELD GATE AT BAGGETT STADIUM | NORTON, DAVE | CLOSED | 2015-01-27 | AD: CENTRAL COAST FENCE | 160 | CLOSED | 3184.32 | 0 | 3184.32 | 3184.32
PJ0005188 | MODIFY LEFT FIELD GATE AT BAGGETT STADIUM | NORTON, DAVE | CLOSED | 2015-01-27 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 325.5 | 0 | 0 | 0
PJ0005188 | MODIFY LEFT FIELD GATE AT BAGGETT STADIUM | NORTON, DAVE | CLOSED | 2015-01-27 | IN: MODIFY LEFT FIELD GATE AT BAGGETT STADIUM | 160 | CLOSED | 70.644 | 0 | 176.61 | 176.61
PJ0005188 Total | [7 empty] | 3580.464 | 0 | 3360.93 | 3360.93
PJ0005185 | INSTALL GAS LINE AND COUNTER TOP SPIGOTS BLDG 033 - 461 | GONZALES, ALBERT | CLOSED | 2015-01-27 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 408.24 | 0 | 0 | 0
PJ0005185 | INSTALL GAS LINE AND COUNTER TOP SPIGOTS BLDG 033 - 461 | GONZALES, ALBERT | CLOSED | 2015-01-27 | IN: INSTALL GAS LINE AND COUNTER TOP SPIGOTS BLDG 033 - 461 | 033 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005185 | INSTALL GAS LINE AND COUNTER TOP SPIGOTS BLDG 033 - 461 | GONZALES, ALBERT | CLOSED | 2015-01-27 | PL: INSTALL GAS LINE AND TURRETS | 033 | CLOSED | 3942.4745 | 0 | 870.54 | 870.54
PJ0005185 Total | [7 empty] | 4492.0025 | 0 | 1011.828 | 1011.828
PJ0005184 | REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | DILLON, JEFFREY | CLOSED | 2015-01-21 | AD: MAINO LVPW | 042 | CLOSED | 4280 | 0 | 4267.16 | 4267.16
PJ0005184 | REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | DILLON, JEFFREY | CLOSED | 2015-01-21 | AD: RRM DESIGN | 042 | CLOSED | 1016.5 | 0 | 1016.5 | 1016.5
PJ0005184 | REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | DILLON, JEFFREY | CLOSED | 2015-01-21 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 740.95 | 0 | 0 | 0
PJ0005184 | REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | DILLON, JEFFREY | CLOSED | 2015-01-21 | EL: DISCONNECT ICE MACHINE AND RECONNECT | 042 | CLOSED | 143.6744 | 0 | 96.642 | 96.642
PJ0005184 | REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | DILLON, JEFFREY | CLOSED | 2015-01-21 | IN: REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | 042 | CLOSED | 141.288 | 0 | 282.576 | 282.576
PJ0005184 | REPLACE THERAPEUTIC WHIRLPOOLS BLDG 042 - 125C | DILLON, JEFFREY | CLOSED | 2015-01-21 | PL: PLUMBING DISCONECTIONS AND CAPPING | 042 | CLOSED | 2579.4461 | 0 | 2505.5226 | 2505.5226
PJ0005184 Total | [7 empty] | 8901.8585 | 0 | 8168.4006 | 8168.4006
PJ0005182 | M&R PARK 15/16: MISC. LOT WORK INCLUDING TREE TRIM - CAMPUS WIDE | HOSTICK, RONALD | CLOSED | 2015-01-29 | AD: GREENVALE TREE SERVICE | GENERAL | CLOSED | 5000.003 | 0 | 2386.1 | 2386.1
PJ0005182 | M&R PARK 15/16: MISC. LOT WORK INCLUDING TREE TRIM - CAMPUS WIDE | HOSTICK, RONALD | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005182 Total | [7 empty] | 5000.003 | 0 | 2386.1 | 2386.1
PJ0005181 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-G | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | P-H04 | CLOSED | 6391.7627 | 0 | 6391.7627 | 6391.7627
PJ0005181 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-G | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 0 | 0 | 0 | 0
PJ0005181 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-G | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-G | P-H04 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005181 Total | [7 empty] | 6462.4067 | 0 | 6427.0847 | 6427.0847
PJ0005180 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-D | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | P-H04 | CLOSED | 11887.6144 | 0 | 11887.6144 | 11887.6144
PJ0005180 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-D | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 0 | 0 | 0 | 0
PJ0005180 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-D | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PARK 15/16: RESEAL & RESTRIPE - P-H04-D | P-H04 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005180 Total | [7 empty] | 11958.2584 | 0 | 11922.9364 | 11922.9364
PJ0005179 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-C | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | P-H02 | CLOSED | 5649.8247 | 0 | 5649.8247 | 5649.8247
PJ0005179 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-C | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | P-H02 | CLOSED | 0 | 0 | 0 | 0
PJ0005179 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-C | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-C | P-H02 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005179 Total | [7 empty] | 5720.4687 | 0 | 5685.1467 | 5685.1467
PJ0005178 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-A | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | P-H02 | CLOSED | 19830.3956 | 0 | 19830.3956 | 19830.3956
PJ0005178 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-A | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | P-H02 | CLOSED | 0 | 0 | 0 | 0
PJ0005178 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-A | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PARK 15/16: RESEAL & RESTRIPE - P-H02-A | P-H02 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005178 Total | [7 empty] | 19901.0396 | 0 | 19865.7176 | 19865.7176
PJ0005177 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H13 | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | P-H13 | CLOSED | 4084.3933 | 0 | 4084.3933 | 4084.3933
PJ0005177 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H13 | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | P-H13 | CLOSED | 0 | 0 | 0 | 0
PJ0005177 | M&R PARK 15/16: RESEAL & RESTRIPE - P-H13 | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PARK 15/16: RESEAL & RESTRIPE - P-H13 | P-H13 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005177 Total | [7 empty] | 4155.0373 | 0 | 4155.0373 | 4155.0373
PJ0005176 | M&R PARK 15/16: SPOT CUT AT TREE ROOTS & PATCH, TRIM TREE- P-H12 | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | P-H12 | CLOSED | 30216.9605 | 0 | 30216.9605 | 30216.9605
PJ0005176 | M&R PARK 15/16: SPOT CUT AT TREE ROOTS & PATCH, TRIM TREE- P-H12 | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | P-H12 | CLOSED | 0 | 0 | 0 | 0
PJ0005176 | M&R PARK 15/16: SPOT CUT AT TREE ROOTS & PATCH, TRIM TREE- P-H12 | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PRK15/16: SPOTCUT AT TREEROOTS & PATCH, TRIM TREE- P-H12 | P-H12 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005176 Total | [7 empty] | 30287.6045 | 0 | 30287.6045 | 30287.6045
PJ0005175 | M&R PARK 15/16: GRAND AVE PARKING STRUCTURE MAINTENANCE | NORTON, DAVE | CLOSED | 2015-01-29 | AD: JOC 14.033.040 MAINO | 130 | CLOSED | 56969.8281 | 0 | 56969.8281 | 56969.8281
PJ0005175 | M&R PARK 15/16: GRAND AVE PARKING STRUCTURE MAINTENANCE | NORTON, DAVE | CLOSED | 2015-01-29 | AD: MAINO (LVPW) SLURRY APPLICATION | 130 | CLOSED | 4491.86 | 0 | 4491.86 | 4491.86
PJ0005175 | M&R PARK 15/16: GRAND AVE PARKING STRUCTURE MAINTENANCE | NORTON, DAVE | CLOSED | 2015-01-29 | AD: MAINO (LVPW) STRIPPING | 130 | CLOSED | 3826.3842 | 0 | 3999.66 | 3999.66
PJ0005175 | M&R PARK 15/16: GRAND AVE PARKING STRUCTURE MAINTENANCE | NORTON, DAVE | CLOSED | 2015-01-29 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 0 | 0 | 0 | 0
PJ0005175 | M&R PARK 15/16: GRAND AVE PARKING STRUCTURE MAINTENANCE | NORTON, DAVE | CLOSED | 2015-01-29 | IN: M&R PARK 15/16: GRAND AVE PARKING STRUCTURE MAINTENANCE | 130 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005175 Total | [7 empty] | 65429.3603 | 0 | 65567.3141 | 65567.3141
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | AD: MORRO BAY CABINETS | 025 | CLOSED | 2022.3 | 0 | 2610.8 | 2610.8
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | AD: STATE FIRE MARSHAL | 025 | CLOSED | 0 | 0 | 148.1736 | 148.1736
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | CA: REMOVE COUNTERS AT EXTEND WALL | 025 | CLOSED | 3704.5002 | 0 | 1603.074 | 1603.074
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | CP: PROJECT CONTINGENCY | 025 | CLOSED | 731.08 | 0 | 0 | 0
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | EL: RELOCATE LIGHTS AND RECIRCUIT SWITCHING | 025 | CLOSED | 933.4092 | 0 | 431.898 | 431.898
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | IN: OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | 025 | CLOSED | 211.932 | 0 | 105.966 | 105.966
PJ0005174 | OFFICE SUITE REMODEL - BLD 25 RMS 208 A-F | NORTON, DAVE | CLOSED | 2015-01-27 | MO: MOVE OLD FURNITURE | 025 | CLOSED | 223.8869 | 0 | 157.752 | 157.752
PJ0005174 Total | [7 empty] | 7827.1083 | 0 | 5057.6636 | 5057.6636
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | AD: (FPCP FUNDING) JOC 16.037.017 MAINO | 150G | CLOSED | 0 | 0 | 31424.5518 | 31424.5518
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | AD: JOC 14.034.008 MAINO | 150G | CLOSED | 69880.18 | 0 | 65367.85 | 65367.85
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | AD: STATE FIRE MARSHAL | 150G | CLOSED | 0 | 0 | 163.21 | 163.21
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | CA: SIGNS FOR ELECTRIC SHOP | 150G | CLOSED | 164.05 | 0 | 483.525 | 483.525
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | CP: PROJECT CONTINGENCY | 150G | CLOSED | 9515.22 | 0 | 0 | 0
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | EL: (FPCP FUNDING) ELECTRICAL FOR POULTRY CAGES - BLDG 150G | 150G | CLOSED | 0 | 0 | 1530.75 | 1530.75
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | EL: INSTALL ELECTRICAL FOR CAGES | 150G | CLOSED | 24899.1211 | 0 | 27987.5618 | 27987.5618
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | IN: (FPCP FUNDING) RENOVATE POULTRY CAGES- BLDG 150G | 150G | CLOSED | 0 | 0 | 529.83 | 529.83
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | PA: PAINTING FOR POULTRY CAGE RENOVATION - BLDG.150G | 150G | CLOSED | 5499.861 | 0 | 3973.6618 | 3973.6618
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | PL: INSTALL NEW GAS LINE TO HEATER & LOCATE UTILITIES | 150G | CLOSED | 737.4 | 0 | 887.25 | 887.25
PJ0005173 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | LAMPMAN, GREG | CLOSED | 2015-01-26 | PM: RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150G | 150G | CLOSED | 0 | 0 | 0 | 0
PJ0005173 Total | [7 empty] | 110695.8321 | 0 | 132348.1904 | 132348.1904
PJ0005171 | MEMORIAL BENCH - COLLEEN RODRIGUEZ - ADMIN 01 | BRENNAN, MICHAEL | CLOSED | 2015-01-22 | AD: QUICKCRETE | GENERAL | CLOSED | 1337.5 | 0 | 1297.482 | 1297.482
PJ0005171 | MEMORIAL BENCH - COLLEEN RODRIGUEZ - ADMIN 01 | BRENNAN, MICHAEL | CLOSED | 2015-01-22 | CA: INSTALL PLAQUE ON MEMORIAL BENCH | GENERAL | CLOSED | 124.0326 | 0 | 27.81 | 27.81
PJ0005171 | MEMORIAL BENCH - COLLEEN RODRIGUEZ - ADMIN 01 | BRENNAN, MICHAEL | CLOSED | 2015-01-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 172.09 | 0 | 0 | 0
PJ0005171 | MEMORIAL BENCH - COLLEEN RODRIGUEZ - ADMIN 01 | BRENNAN, MICHAEL | CLOSED | 2015-01-22 | EO: LOCATE MEMORIAL BENCH | GENERAL | CLOSED | 114.5596 | 0 | 202.824 | 202.824
PJ0005171 | MEMORIAL BENCH - COLLEEN RODRIGUEZ - ADMIN 01 | BRENNAN, MICHAEL | CLOSED | 2015-01-22 | IN: MEMORIAL BENCH - COLLEEN RODRIGUEZ - ADMIN 01 | GENERAL | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005171 Total | [7 empty] | 1818.8262 | 0 | 1598.76 | 1598.76
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | CA: INSPECTION OF ALL AG STUDENT HOUSING | RESIDENCE | CLOSED | 0 | 0 | 231.75 | 231.75
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | EL: INSPECTION OF ALL AG STUDENT HOUSING | RESIDENCE | CLOSED | 0 | 0 | 402.675 | 402.675
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | ES: INSPECTION OF ALL AG STUDENT HOUSING | RESIDENCE | CLOSED | 0 | 0 | 820.8 | 820.8
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | LO: INSPECTION OF ALL AG STUDENT HOUSING | RESIDENCE | CLOSED | 0 | 0 | 177.695 | 177.695
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | PA: INSPECTION OF ALL AG STUDENT HOUSING (N/L) | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005170 | AG STUDENT HOUSING ASSESSMENT - JANUARY 2015 (MAINT) | POLVI, STEVEN | CLOSED | 2015-01-21 | PL: INSPECTION OF ALL AG STUDENT HOUSING | RESIDENCE | CLOSED | 0 | 0 | 214.96 | 214.96
PJ0005170 Total | [7 empty] | 0 | 0 | 1847.88 | 1847.88
PJ0005169 | SR 14/15: BIRD REMEDIATION (INSTALL NETTING) - BLD 5 RM 205 | SHAW, KEVIN | CLOSED | 2015-01-21 | AD: AVIARY MANAGEMENT PROFESSIONALS | 005 | CLOSED | 53580.25 | 0 | 53580.25 | 53580.25
PJ0005169 | SR 14/15: BIRD REMEDIATION (INSTALL NETTING) - BLD 5 RM 205 | SHAW, KEVIN | CLOSED | 2015-01-21 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 556.08 | 0 | 0 | 0
PJ0005169 Total | [7 empty] | 54136.33 | 0 | 53580.25 | 53580.25
PJ0005167 | INSULATE ROOF OF SHOP BLDG 53A RM 9 | DILLON, JEFFREY | CLOSED | 2015-01-13 | CA: INSULATE ROOF OF SHOP BLDG 53A RM 9 | 053A | CLOSED | 6860.223 | 0 | 7449.531 | 7449.531
PJ0005167 | INSULATE ROOF OF SHOP BLDG 53A RM 9 | DILLON, JEFFREY | CLOSED | 2015-01-13 | CP: PROJECT CONTINGENCY | 053A | CLOSED | 701.4 | 0 | 0 | 0
PJ0005167 | INSULATE ROOF OF SHOP BLDG 53A RM 9 | DILLON, JEFFREY | CLOSED | 2015-01-13 | IN: INSULATE ROOF OF SHOP BLDG 53A RM 9 | 053A | CLOSED | 157.5361 | 0 | 105.966 | 105.966
PJ0005167 Total | [7 empty] | 7719.1591 | 0 | 7555.497 | 7555.497
PJ0005164 | CUT & REMOVE STEEL BRACKETS AT MOTT BLDG 042 RM 102 | BRENNAN, MICHAEL | CLOSED | 2015-01-05 | CA: REMOVE BRACKETS AT MOTT GYM | 042 | CLOSED | 1794.2316 | 0 | 1731.252 | 1731.252
PJ0005164 | CUT & REMOVE STEEL BRACKETS AT MOTT BLDG 042 RM 102 | BRENNAN, MICHAEL | CLOSED | 2015-01-05 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 187.17 | 0 | 0 | 0
PJ0005164 | CUT & REMOVE STEEL BRACKETS AT MOTT BLDG 042 RM 102 | BRENNAN, MICHAEL | CLOSED | 2015-01-05 | IN: CUT & REMOVE STEEL BRACKETS AT MOTT BLDG 042 RM 102 | 042 | CLOSED | 78.4148 | 0 | 70.644 | 70.644
PJ0005164 Total | [7 empty] | 2059.8164 | 0 | 1801.896 | 1801.896
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | AD: FPCP PROJECT MANAGEMENT | 035 | CLOSED | 802.5 | 0 | 750 | 750
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | AD: ITS | 035 | CLOSED | 712.3525 | 0 | 712.3525 | 712.3525
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | CA: INSTALL GALLERY RAIL AND (2) WHITE BOARDS | 035 | CLOSED | 3319.2204 | 0 | 2068.974 | 2068.974
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1968.51 | 0 | 0 | 0
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | EL: ORDER AND INSTALLATION OF PLUG MOLD | 035 | CLOSED | 12803.7151 | 0 | 8425.41 | 8425.41
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | IN: REMODEL 3RD FLOOR BLDG 035 | 035 | CLOSED | 353.22 | 0 | 211.932 | 211.932
PJ0005162 | REMODEL 3RD FLOOR BLDG 035 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-19 | PA: PAINT WALLS TO MATCH NEW COLOR SCHEME PER PLAN | 035 | CLOSED | 9467.1943 | 0 | 6866.556 | 6866.556
PJ0005162 Total | [7 empty] | 29426.7123 | 0 | 19035.2245 | 19035.2245
PJ0005160 | SR 14/15: ARCH FLASH STUDY PHASE II - VARIOUS STATE BLDS | POLVI, STEVEN | CLOSED | 2015-01-09 | AD: POWER ENGINEERING | GENERAL | CLOSED | 151351.5 | 0 | 150600.36 | 150600.36
PJ0005160 | SR 14/15: ARCH FLASH STUDY PHASE II - VARIOUS STATE BLDS | POLVI, STEVEN | CLOSED | 2015-01-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 16683.83 | 0 | 0 | 0
PJ0005160 Total | [7 empty] | 168035.33 | 0 | 150600.36 | 150600.36
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | AD: HPS MECHANICAL INC | U-UDOR | CLOSED | 42800 | 0 | 36337.2 | 36337.2
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | CA: PREP & CAULK UTILIDOR LIDS AFTER UTILIDOR WORK COMPLETE | U-UDOR | CLOSED | 1485.6102 | 0 | 2334.546 | 2334.546
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 5270.53 | 0 | 0 | 0
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | CPE: UTILIDOR VALVE REPLACEMENT SUPPORT - BLDG. 033 | U-UDOR | CLOSED | 2922.7046 | 0 | 2456.238 | 2456.238
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | ES: UTILIDOR VALVE REPLACEMENT SUPPORT - ZONE 2 | U-UDOR | CLOSED | 1169.4758 | 0 | 1461.018 | 1461.018
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | IN: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | U-UDOR | CLOSED | 314.3658 | 0 | 388.542 | 388.542
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | LA: LANDSCAPING AFTER UTILIDOR VALVE REPLACEMENT - BLDG 33 (N/L) | U-UDOR | CLOSED | 1012.9699 | 0 | 2.1526 | 2.1526
PJ0005159 | SR 14/15: REPLACE UTILIDOR VALVES & INSTALL VAULT - BLD 33 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-09 | PL: UTILIDOR VALVE REPLACEMENT SUPPORT | U-UDOR | CLOSED | 286.9716 | 0 | 1213.05 | 1213.05
PJ0005159 Total | [7 empty] | 55262.628 | 0 | 44192.7466 | 44192.7466
PJ0005158 | M&R ASI 15/16: MUSTANG LANES LOWFLOW RESTRM FIXTURES -UU 115/116 | PINHEIRO, RICK | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1875.41 | 0 | 0 | 0
PJ0005158 | M&R ASI 15/16: MUSTANG LANES LOWFLOW RESTRM FIXTURES -UU 115/116 | PINHEIRO, RICK | CLOSED | 2015-01-06 | IN: MUSTANG LANES LOW FLOW RESTRM FIXTURES -UU 115/116 | 065 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005158 | M&R ASI 15/16: MUSTANG LANES LOWFLOW RESTRM FIXTURES -UU 115/116 | PINHEIRO, RICK | CLOSED | 2015-01-06 | PL:PURCHASE & INSTALL LOW FLOW TOILETS ¿ MUSTANG LANES | 065 | CLOSED | 16893.9761 | 0 | 10045.236 | 10045.236
PJ0005158 Total | [7 empty] | 19083.7519 | 0 | 10186.524 | 10186.524
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | AD: FLOOR CONNECTION | 065 | CLOSED | 2581.4499 | 0 | 2581.4499 | 2581.4499
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | CA:DEMO WALL, INSTALL NEW DOOR IN E FRAME BLDG 65, RM 208,212 | 065 | CLOSED | 3675.6462 | 0 | 2868.2906 | 2868.2906
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1358.58 | 0 | 0 | 0
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | EL:DISCONNECT EL FOR DEMO, RELOCATE AS NEEDED 65, 208B,212B | 065 | CLOSED | 3827.6903 | 0 | 747.48 | 747.48
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | ES:REPAIR DUCTWORK AND BALANCE SYSTEMB UU, 208A, 212B | 065 | CLOSED | 678.6355 | 0 | 192.288 | 192.288
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | IN: M&R UU 15/16: IT SUITE UPGRADES - REC 65 | 065 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | LO:INSTALL NEW MORTISE LOCK AND RELOCATE EXISTING UU, 212B, 208B | 065 | CLOSED | 1126.9723 | 0 | 610.476 | 610.476
PJ0005157 | M&R ASI 15/16: IT SUITE UPGRADES - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2015-01-06 | PA:VARNISH DOOR - PAINT CONCRETE WALL PATCH 208 | 065 | CLOSED | 1426.4718 | 0 | 1176.252 | 1176.252
PJ0005157 Total | [7 empty] | 14816.734 | 0 | 8282.2025 | 8282.2025
PJ0005156 | M&R ASI 15/16: REFINISH FLOORING CHUMASH - UU 65 | HICKS, MICHAEL | CLOSED | 2015-01-06 | AD: MCWIL SPORTS SURFACES | 065 | CLOSED | 7111.22 | 0 | 7111.648 | 7111.648
PJ0005156 | M&R ASI 15/16: REFINISH FLOORING CHUMASH - UU 65 | HICKS, MICHAEL | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 236.02 | 0 | 0 | 0
PJ0005156 | M&R ASI 15/16: REFINISH FLOORING CHUMASH - UU 65 | HICKS, MICHAEL | CLOSED | 2015-01-06 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 065 | CLOSED | 0 | 0 | 8.4 | 8.4
PJ0005156 | M&R ASI 15/16: REFINISH FLOORING CHUMASH - UU 65 | HICKS, MICHAEL | CLOSED | 2015-01-06 | IN: M&R UU 15/16: REFINISH FLOORING CHUMASH - REC 65 | 065 | CLOSED | 78.4148 | 0 | 70.644 | 70.644
PJ0005156 Total | [7 empty] | 7425.6548 | 0 | 7190.692 | 7190.692
PJ0005155 | M&R ASI 15/16: EPOXY EXTERIOR STAIRS & DECK - UU BLDG. 65 | MARCHESE, JASON (WILL) | CLOSED | 2015-01-06 | AD: JOC 15.036.015 STAPLES | 065 | CLOSED | 69815.36 | 0 | 69717.1982 | 69717.1982
PJ0005155 | M&R ASI 15/16: EPOXY EXTERIOR STAIRS & DECK - UU BLDG. 65 | MARCHESE, JASON (WILL) | CLOSED | 2015-01-06 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 267.5 | 0 | 324.5631 | 324.5631
PJ0005155 | M&R ASI 15/16: EPOXY EXTERIOR STAIRS & DECK - UU BLDG. 65 | MARCHESE, JASON (WILL) | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 7132.15 | 0 | 0 | 0
PJ0005155 | M&R ASI 15/16: EPOXY EXTERIOR STAIRS & DECK - UU BLDG. 65 | MARCHESE, JASON (WILL) | CLOSED | 2015-01-06 | IN: M&R UU 15/16: EPOXY EXTERIOR STAIRS & DECK - UU BLDG. 65 | 065 | CLOSED | 314.3658 | 0 | 353.22 | 353.22
PJ0005155 | M&R ASI 15/16: EPOXY EXTERIOR STAIRS & DECK - UU BLDG. 65 | MARCHESE, JASON (WILL) | CLOSED | 2015-01-06 | PL: PROJECT SUPPORT - DRAIN BACKUP PREVENTION | 065 | CLOSED | 573.9432 | 0 | 221.1 | 221.1
PJ0005155 Total | [7 empty] | 78103.319 | 0 | 70616.0813 | 70616.0813
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | AD: QUINTRON | 065 | CLOSED | 80892 | 0 | 79134.7497 | 79134.7497
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 294.25 | 0 | 0 | 0
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | CA: DRILL HOLES FOR SCREEN & SPEAKER MOUNTING | 065 | CLOSED | 222.48 | 0 | 389.34 | 389.34
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 8819.86 | 0 | 0 | 0
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | EL: ELECTRICAL POWER TO NEW SCREEN & CONTROL WIRING | 065 | CLOSED | 4787.6903 | 0 | 2577.24 | 2577.24
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | IN: M&R UU 15/16: REPLACE CHUMASH MOVIE SCREEN - REC 65 | 065 | CLOSED | 471.9019 | 0 | 70.644 | 70.644
PJ0005154 | M&R ASI 15/16: REPLACE CHUMASH MOVIE SCREEN - UU 65 | DUNN, TRAVIS | CLOSED | 2015-01-06 | PA: PAINTING TOUCH UP ON STAGE WALL | 065 | CLOSED | 2984.5439 | 0 | 801.996 | 801.996
PJ0005154 Total | [7 empty] | 98472.7261 | 0 | 82973.9697 | 82973.9697
PJ0005152 | M&R ASI 15/16: EVALUATE MAIN GYM ROOF CONDITION - REC 43 | LAMPMAN, GREG | CLOSED | 2015-01-06 | AD: T. BROOKS & ASSOCIATES | 043 | CLOSED | 3745 | 0 | 3745 | 3745
PJ0005152 | M&R ASI 15/16: EVALUATE MAIN GYM ROOF CONDITION - REC 43 | LAMPMAN, GREG | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 403.81 | 0 | 0 | 0
PJ0005152 | M&R ASI 15/16: EVALUATE MAIN GYM ROOF CONDITION - REC 43 | LAMPMAN, GREG | CLOSED | 2015-01-06 | IN: M&R UU 15/16: EVALUATE MAIN GYM ROOF CONDITION - REC 43 | 043 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005152 Total | [7 empty] | 4219.454 | 0 | 3815.644 | 3815.644
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | AD: CAME SECURITY | 043 | CLOSED | 1045.925 | 0 | 1045.925 | 1045.925
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | AD: EARTH SYSTEMS PACIFIC | 043 | CLOSED | 3589.208 | 0 | 3538.0085 | 3538.0085
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | AD: ENGLEKIRK & SABOL CONSULTING | 043 | CLOSED | 535 | 0 | 535 | 535
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | AD: JOC 15.036.010 STAPLES | 043 | CLOSED | 113005.2573 | 0 | 113005.2573 | 113005.2573
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | AD: STATE FIRE MARSHAL | 043 | CLOSED | 535 | 0 | 56.4425 | 56.4425
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 10109.52 | 0 | 0 | 0
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | EL: PROVIDE SUPPORT, INSTALL POWER & LIGHTING | 043 | CLOSED | 18203.7151 | 0 | 18124.89 | 18124.89
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | ES: MARK UTILITIES AND PROVIDE SUPPORT (N/L) | 043 | CLOSED | 1096.2048 | 0 | 804 | 804
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | IN: M&R UU 15/16: POOL DECK / INSTALL SHADE - REC 43 | 043 | CLOSED | 1554.168 | 0 | 741.762 | 741.762
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | LA: MARK UTILITIES & PROVIDE SUPPORT | 043 | CLOSED | 1491.1123 | 0 | 1100.574 | 1100.574
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | LO: ISSUE KEYS FOR POOL ACCESS | 043 | CLOSED | 135.8605 | 0 | 30.462 | 30.462
PJ0005150 | M&R ASI 15/16: POOL DECK / INSTALL SHADE - REC 43 | KOLEGRAFF, KENNETH | CLOSED | 2015-01-06 | PL: MARK UTILITIES & PROVIDE SUPPORT | 043 | CLOSED | 1173.9432 | 0 | 1248.348 | 1248.348
PJ0005150 Total | [7 empty] | 152474.9143 | 0 | 140230.6693 | 140230.6693
PJ0005149 | PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO ESTIMATE) | LOOSLEY, SCOTT L. | CLOSED | 2014-12-30 | CA: PAC MAINTENANCE WALK-THROUGH 10/14/14 | 006 | CLOSED | 1854 | 0 | 2043.685 | 2043.685
PJ0005149 | PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO ESTIMATE) | LOOSLEY, SCOTT L. | CLOSED | 2014-12-30 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005149 | PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO ESTIMATE) | LOOSLEY, SCOTT L. | CLOSED | 2014-12-30 | CU: PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO LABOR) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005149 | PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO ESTIMATE) | LOOSLEY, SCOTT L. | CLOSED | 2014-12-30 | LO: PAC MAINTENANCE WALK-THROUGH 10/14/14 | 006 | CLOSED | 0 | 0 | 814.855 | 814.855
PJ0005149 | PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO ESTIMATE) | LOOSLEY, SCOTT L. | CLOSED | 2014-12-30 | PA: PAC MAINTENANCE WALK-THROUGH 10/14/14 | 006 | CLOSED | 0 | 0 | 103.18 | 103.18
PJ0005149 | PAC MAINTENANCE WALK-THROUGH 10/14/14 (NO ESTIMATE) | LOOSLEY, SCOTT L. | CLOSED | 2014-12-30 | PL: PAC MAINTENANCE WALK-THROUGH 10/14/14 | 006 | CLOSED | 0 | 0 | 26.87 | 26.87
PJ0005149 Total | [7 empty] | 1854 | 0 | 2988.59 | 2988.59
PJ0005147 | SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | AD: STATE FIRE MARSHAL | 003 | CLOSED | 428 | 0 | 0 | 0
PJ0005147 | SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | CA: INSTALL NEW BRACKETS FOR AV EQUIPMENT BLDG 3 | 003 | CLOSED | 11074.7754 | 0 | 11643.948 | 11643.948
PJ0005147 | SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0005147 | SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | EL:INSTALL ELECTRICAL AND LOW VOLTAGE FOR AUDIO VIDEO | 003 | CLOSED | 19871.4054 | 0 | 13507.164 | 13507.164
PJ0005147 | SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | IN: SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | 003 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005147 | SMARTROOM UPGRADES - BLDG 03-RMS.112,113,114,201,204,206,209 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | PA:TOUCH UP PAINT FOR SMARTROOM UPGRADES BLDG 3 | 003 | CLOSED | 679.08 | 0 | 2616.708 | 2616.708
PJ0005147 Total | [7 empty] | 32194.5488 | 0 | 27838.464 | 27838.464
PJ0005145 | M&R ASI 15/16: LANDSCAPE IMPROV. CLIMBING WALL - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-12-19 | AD: JOC 15.035.035 MAINO | 043 | CLOSED | 15262.3409 | 0 | 15262.3409 | 15262.3409
PJ0005145 | M&R ASI 15/16: LANDSCAPE IMPROV. CLIMBING WALL - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-12-19 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 1587.3 | 0 | 0 | 0
PJ0005145 | M&R ASI 15/16: LANDSCAPE IMPROV. CLIMBING WALL - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-12-19 | EL: REMOVE / REPLACE POLE LIGHT | 043 | CLOSED | 833.136 | 0 | 450.996 | 450.996
PJ0005145 | M&R ASI 15/16: LANDSCAPE IMPROV. CLIMBING WALL - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-12-19 | IN: M&R UU 15/16: LANDSCAPE IMPROV. CLIMBING WALL - REC 43 | 043 | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0005145 | M&R ASI 15/16: LANDSCAPE IMPROV. CLIMBING WALL - REC 43 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-12-19 | LA: REMOVE / REPLACE LANDSCAPE MATERIALS AND REPLACE. | 043 | CLOSED | 5422.3363 | 0 | 4458.57 | 4458.57
PJ0005145 Total | [7 empty] | 23387.6892 | 0 | 20242.5509 | 20242.5509
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | ANTS:PROVIDE PROJECT SUPPORT | 112 | OPEN | 0 | 0 | 0 | 0
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | CA: GENERAL CONSTRUCTION SUPPORT FOR VG REPLACEMENT PROJECT | 112 | ASSIGNED | 0 | 0 | 500.58 | 500.58
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | CA: RELOCATE CONSTRUCTION SIGN | 112 | CLOSED | 0 | 0 | 639.63 | 639.63
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | CA: REPAIR TEMP FENCE ALONG DEER RD FOR VISTA GRANDE PROJECT | 112 | CLOSED | 0 | 0 | 511.2 | 511.2
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | CP: PROJECT CONTINGENCY | 112 | OPEN | 285320 | 0 | 0 | 0
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | CPE:PROVIDE SUPPORT FOR MJ PROJECT | 112 | OPEN | 0 | 0 | 0 | 0
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | EH&S: PROVIDE PROJECT SUPPORT | 112 | OPEN | 0 | 0 | 0 | 0
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | EL: UTILITY MARK OUT FOR NEW VISTA GRANDE BUILDING - 112 | 112 | LONG_TERM | 0 | 0 | 25232.25 | 25232.25
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | EL:PROCURE EMERGENCY GENERATOR | 112 | WORKING | 0 | 0 | 1175.232 | 1175.232
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | LA:PROVIDE CONTRACTOR SUPPORT | 112 | ASSIGNED | 0 | 0 | 2744.208 | 2744.208
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | LO: INSTALL CONST. CORE FOR DEMO - SUPPORT NEW FACILITY INSTALL | 112 | OPEN | 0 | 0 | 152.31 | 152.31
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | PL: UTILITY MARK OUT FOR NEW VISTA GRANDE BUILDING - 112 | 112 | OPEN | 0 | 0 | 39394.1211 | 39394.1211
PJ0005143 | MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | MCNALLY, CURTIS J. | IN_CONSTR | 2014-12-19 | SM: MJ: SUPPORT FOR NEW VISTA GRANDE BUILDING - BLD 112 | 112 | OPEN | 0 | 0 | 0 | 0
PJ0005143 Total | [7 empty] | 285320 | 0 | 70349.5311 | 70349.5311
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | AD: JOC 15.035.003 MAINO | 042 | CLOSED | 14380.0617 | 0 | 14380.0617 | 14380.0617
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 2677.49 | 0 | 0 | 0
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | EL: MARK UTILITIES AND RUN NEW POWER SOURCE FOR BBALL TENT | 042 | CLOSED | 8879.6993 | 0 | 7772.538 | 7772.538
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | EO: Pot Hole for elect. conduit south basket ball courts | 042 | CLOSED | 228.6054 | 0 | 205.488 | 205.488
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | ES: SUPPORT & MARK UTILITIES (N/L) | 042 | CLOSED | 292.2048 | 0 | 0 | 0
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | IN: INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | 042 | CLOSED | 360.9908 | 0 | 282.576 | 282.576
PJ0005142 | INSTALL PERMANENT POWER SOURCE: SOUTH SIDE MOTT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-11 | PL: Provide Support and Mark Utilities | 042 | CLOSED | 286.9716 | 0 | 70.944 | 70.944
PJ0005142 Total | [7 empty] | 27106.0236 | 0 | 22711.6077 | 22711.6077
PJ0005141 | INSTALL TRACK LIGHTING SYSTEM IN DEXTER 34 ROOM 145 | MOLLAN, CHERYL L. | CLOSED | 2014-12-10 | AD: MORELAND THOMPSON, INC. | 034 | CLOSED | 3921.55 | 0 | 3921.55 | 3921.55
PJ0005141 | INSTALL TRACK LIGHTING SYSTEM IN DEXTER 34 ROOM 145 | MOLLAN, CHERYL L. | CLOSED | 2014-12-10 | AD: SANTA MARIA ACOUSTICAL | 034 | CLOSED | 6024.1 | 0 | 6024.1 | 6024.1
PJ0005141 | INSTALL TRACK LIGHTING SYSTEM IN DEXTER 34 ROOM 145 | MOLLAN, CHERYL L. | CLOSED | 2014-12-10 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 1021.56 | 0 | 0 | 0
PJ0005141 | INSTALL TRACK LIGHTING SYSTEM IN DEXTER 34 ROOM 145 | MOLLAN, CHERYL L. | CLOSED | 2014-12-10 | EL:CONTRACTOR SUPPORT FOR BLDG 34, ROOM 145 FLOOD LIGHT | 034 | CLOSED | 128.856 | 0 | 64.428 | 64.428
PJ0005141 | INSTALL TRACK LIGHTING SYSTEM IN DEXTER 34 ROOM 145 | MOLLAN, CHERYL L. | CLOSED | 2014-12-10 | IN: INSTALL TRACK LIGHTING SYSTEM IN DEXTER 34 ROOM 145 | 034 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005141 Total | [7 empty] | 11237.354 | 0 | 10151.366 | 10151.366
PJ0005140 | BUILD CABINETRY AROUND THE FIRST FLOOR OF 43A | NORTON, DAVE | CLOSED | 2014-12-11 | AD: CONSTRUCTED SOLUTIONS, INC | 043A | CLOSED | 40414.4778 | 0 | 40426.3227 | 40426.3227
PJ0005140 | BUILD CABINETRY AROUND THE FIRST FLOOR OF 43A | NORTON, DAVE | CLOSED | 2014-12-11 | AD: STATE FIRE MARSHAL FEES | 043A | CLOSED | 283.55 | 0 | 666.7919 | 666.7919
PJ0005140 | BUILD CABINETRY AROUND THE FIRST FLOOR OF 43A | NORTON, DAVE | CLOSED | 2014-12-11 | CP: PROJECT CONTINGENCY | 043A | CLOSED | 0 | 0 | 0 | 0
PJ0005140 | BUILD CABINETRY AROUND THE FIRST FLOOR OF 43A | NORTON, DAVE | CLOSED | 2014-12-11 | IN: BUILD CABINETRY AROUND THE FIRST FLOOR OF 43A | 043A | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005140 Total | [7 empty] | 40909.9598 | 0 | 41269.7246 | 41269.7246
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: DEEP BLUE INTEGRATIONS | 006 | CLOSED | 9893.22 | 0 | 1782.8875 | 1782.8875
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: DGS GENERAL SERVICE | 006 | CLOSED | 0 | 0 | 48.15 | 48.15
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: DODGE DATA & ANALYTICS | 006 | CLOSED | 2445.1212 | 0 | 2445.1212 | 2445.1212
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: ONTRAC SHIPPING | 006 | CLOSED | 0 | 0 | 21.293 | 21.293
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: REPUBLIC ELEVATOR | 006 | CLOSED | 171200 | 0 | 158201.64 | 158201.64
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: STATE FIRE MARSHAL FEES | 006 | CLOSED | 1605 | 0 | 894.4665 | 894.4665
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: TELEGRAM TRIBUNE | 006 | CLOSED | 0 | 0 | 660.1686 | 660.1686
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: VDA CONSULTANTS | 006 | CLOSED | 24610 | 0 | 23509.6548 | 23509.6548
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 15707.24 | 0 | 0 | 0
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | EL: INVESTIGATE CONDITIONS AND SUPPORT ELEVATOR MOD PJ | 006 | CLOSED | 5879.3422 | 0 | 4402.788 | 4402.788
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | IN: UPGRADE CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | 006 | CLOSED | 2306.016 | 0 | 423.864 | 423.864
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | PA: PATCH AND PAINT DRYWALL AROUND NEW FLOOR LIGHTS | 006 | CLOSED | 809.036 | 0 | 154.77 | 154.77
PJ0005138 | UPGRADE ELEVATOR CONTROL SYSTEM AT BLDG 006 PASSENGER ELEVATOR | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | PL: cap fire sprinkler | 006 | CLOSED | 802.8756 | 0 | 128.976 | 128.976
PJ0005138 Total | [7 empty] | 235257.851 | 0 | 192673.7796 | 192673.7796
PJ0005137 | M&R HOUS 15/16: FACILITY CONDITION ASSESSMENT - RESIDENCES | NEEL, JOEL | CLOSED | 2014-12-09 | AD: ISES CORPORATION | RESIDENCE | CLOSED | 75506.69 | 0 | 75506.69 | 75506.69
PJ0005137 | M&R HOUS 15/16: FACILITY CONDITION ASSESSMENT - RESIDENCES | NEEL, JOEL | CLOSED | 2014-12-09 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 7813.33 | 0 | 0 | 0
PJ0005137 | M&R HOUS 15/16: FACILITY CONDITION ASSESSMENT - RESIDENCES | NEEL, JOEL | CLOSED | 2014-12-09 | PCVES: ASSIST WITH FACILITIES CONDITION ASSESSMENT - RES. HALLS | RESIDENCE | CLOSED | 2626.56 | 0 | 0 | 0
PJ0005137 Total | [7 empty] | 85946.58 | 0 | 75506.69 | 75506.69
PJ0005136 | M&R HOUS 15/16: DESIGN AIR CONDITIONING SYSTEM REPLACEMENT -S MT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | AD: ASAP REPROGRAPHICS | RESIDENCE | CLOSED | 0 | 0 | 117.3255 | 117.3255
PJ0005136 | M&R HOUS 15/16: DESIGN AIR CONDITIONING SYSTEM REPLACEMENT -S MT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | AD: GOSS ENGINEERING | RESIDENCE | CLOSED | 37439.3 | 0 | 37439.3 | 37439.3
PJ0005136 | M&R HOUS 15/16: DESIGN AIR CONDITIONING SYSTEM REPLACEMENT -S MT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 0 | 0 | 296.3365 | 296.3365
PJ0005136 | M&R HOUS 15/16: DESIGN AIR CONDITIONING SYSTEM REPLACEMENT -S MT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 4044.39 | 0 | 0 | 0
PJ0005136 | M&R HOUS 15/16: DESIGN AIR CONDITIONING SYSTEM REPLACEMENT -S MT | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | IN: M&R HOUS 15/16: DESIGN AIR COND SYSTEM REPLACEMENT -S MT | RESIDENCE | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005136 Total | [7 empty] | 41624.978 | 0 | 37923.606 | 37923.606
PJ0005134 | M&R HOUS 15/16: INSTALL LOW FLOW TOILETS - TRINITY HALL | PINHEIRO, RICK | CLOSED | 2014-12-09 | CP: PROJECT CONTINGENCY | 105 | CLOSED | 3184.09 | 0 | 0 | 0
PJ0005134 | M&R HOUS 15/16: INSTALL LOW FLOW TOILETS - TRINITY HALL | PINHEIRO, RICK | CLOSED | 2014-12-09 | IN: M&R HOUS 15/16: INSTALL LOW FLOW TOILETS - TRINITY HALL | 105 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005134 | M&R HOUS 15/16: INSTALL LOW FLOW TOILETS - TRINITY HALL | PINHEIRO, RICK | CLOSED | 2014-12-09 | PL: INSTALL LOW FLOW TOILETS - TRINITY HALL | 105 | CLOSED | 29717.5913 | 0 | 22207.212 | 22207.212
PJ0005134 Total | [7 empty] | 33216.0471 | 0 | 22348.5 | 22348.5
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | AD: ATASCADERO GLASS | RESIDENCE | CLOSED | 5082.5 | 0 | 4433.01 | 4433.01
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | AD: BENCHMARK WOODWORKS | RESIDENCE | CLOSED | 5350 | 0 | 5141.35 | 5141.35
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | AD: BOWEN ENVIRONMENTAL | RESIDENCE | CLOSED | 5350 | 0 | 5018.3 | 5018.3
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | AD: JL FASULO DRYWALL | RESIDENCE | CLOSED | 5082.5 | 0 | 3738.58 | 3738.58
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 2996 | 0 | 3076.25 | 3076.25
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | AD: STATE FIRE MARSHAL | RESIDENCE | CLOSED | 174.6347 | 0 | 174.6347 | 174.6347
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | CA: REMODEL TRINITY HALL VENDING AREA | RESIDENCE | CLOSED | 12670.0218 | 0 | 7927.4508 | 7927.4508
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 3385.68 | 0 | 0 | 0
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | EL: TRINITY HALL VENDING ELECTRICAL | RESIDENCE | CLOSED | 3647.6903 | 0 | 3206.748 | 3206.748
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | ES: RELOCATE T-STAT - INSPECT AND INSULATE LINE IN SOFFIT | RESIDENCE | CLOSED | 393.984 | 0 | 1020.6 | 1020.6
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | IN: M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | RESIDENCE | CLOSED | 565.152 | 0 | 353.22 | 353.22
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | LO: SFIC LOCK CYLINDERS | RESIDENCE | CLOSED | 451.721 | 0 | 175.386 | 175.386
PJ0005133 | M&R HOUS 15/16: UPGRADE VENDING AREA - TRINITY 105 | MARCHESE, JASON (WILL) | CLOSED | 2014-12-09 | PA: PAINT TRINITY HALL VENDING AREA | RESIDENCE | CLOSED | 1312.5815 | 0 | 1064.832 | 1064.832
PJ0005133 Total | [7 empty] | 46462.4653 | 0 | 35330.3615 | 35330.3615
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | AD: ASAP REPROGRAPHICS | RESIDENCE | CLOSED | 0 | 0 | 186.2121 | 186.2121
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | AD: REA & LUKER | RESIDENCE | CLOSED | 27820 | 0 | 27777.2 | 27777.2
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | AD: STATE FIRE MARSHAL | RESIDENCE | CLOSED | 1605 | 0 | 382.4073 | 382.4073
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 2989.46 | 0 | 0 | 0
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | IN: M&R HOUS 15/16: DSGN CSD KITCHEN REMDL -YOSEMITE 114 &SM 113 | RESIDENCE | CLOSED | 471.9019 | 0 | 141.288 | 141.288
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | PM: M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOS 114 & SM 113 | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005132 | M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOSEMITE 114 &SM 113 | NORTON, DAVE | DESGN_COMP | 2014-12-09 | SM: M&R HOUS 15/16: DESIGN CSD KITCHEN REMODEL -YOS 114 &SM 113 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0005132 Total | [7 empty] | 32886.3619 | 0 | 28487.1074 | 28487.1074
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | AD: JOC 14.034.021 MAINO | 114 | CLOSED | 24169.7271 | 0 | 24169.7271 | 24169.7271
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | AD: STATE FIRE MARSHAL | 114 | CLOSED | 0 | 0 | 156.3163 | 156.3163
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 2527.84 | 0 | 0 | 0
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | EL: TANSFORMER REPLACEMENT | 114 | CLOSED | 50339.74 | 0 | 51014.976 | 51014.976
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | IN: M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | 114 | CLOSED | 282.576 | 0 | 247.254 | 247.254
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | PA: PAINT CURB AT YOSEMITE TOWER 9 ACCESS ROAD/FIRE LANE | 114 | CLOSED | 123.816 | 0 | 61.908 | 61.908
PJ0005131 | M&R HOUS 15/16: REPLACE TRANSFORMER - YOSEMITE 114 | KOLEGRAFF, KENNETH | CLOSED | 2014-12-09 | PL: Mark Underground Utilities in dig area prior to construction | 114 | CLOSED | 128.976 | 0 | 161.22 | 161.22
PJ0005131 Total | [7 empty] | 77572.6751 | 0 | 75811.4014 | 75811.4014
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | AD: HPS MECHANICAL | U-UDOR | CLOSED | 18190 | 0 | 17954.6 | 17954.6
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | AD: MCKENNA ENVIRONMENTAL | U-UDOR | CLOSED | 1845.75 | 0 | 1318.24 | 1318.24
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | AD: PARC ENVIRONMENTAL | U-UDOR | CLOSED | 9637.49 | 0 | 9637.49 | 9637.49
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | AD: SANTA MARIA ACOUSTICAL | U-UDOR | CLOSED | 13054 | 0 | 12474.06 | 12474.06
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | AD: STATE FIRE MARSHAL FEES | U-UDOR | CLOSED | 0 | 0 | 55.2227 | 55.2227
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 5184.18 | 0 | 0 | 0
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | EL: SUPPORT & REPLACEMENT OF EXISTING LIGHTS | U-UDOR | CLOSED | 7161.7438 | 0 | 8787.156 | 8787.156
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | ES: SUPPORT & DUCT DEMOLITION - RED BRICKS | U-UDOR | CLOSED | 1435.2499 | 0 | 2005.26 | 2005.26
PJ0005130 | M&R HOUS 15/16: REPLACE UTILIDOR PIPING GASKETS - TENAYA HALL | KOLEGRAFF, KENNETH | CLOSED | 2014-12-08 | IN: M&R HOUS 15/16: REPL UTILIDOR PIPING GASKETS - TENAYA HALL | U-UDOR | CLOSED | 392.7806 | 0 | 353.22 | 353.22
PJ0005130 Total | [7 empty] | 56901.1943 | 0 | 52585.2487 | 52585.2487
PJ0005129 | M&R HOUS 15/16: REPLACE RESTROOM TILE - CV 170 A-F | LAMPMAN, COLLEEN | CLOSED | 2014-12-08 | AD: FLOOR CONNECTION (NO OVERHEAD) | 170 | CLOSED | 0 | 0 | 95593.01 | 95593.01
PJ0005129 | M&R HOUS 15/16: REPLACE RESTROOM TILE - CV 170 A-F | LAMPMAN, COLLEEN | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 113286.86 | 0 | 0 | 0
PJ0005129 | M&R HOUS 15/16: REPLACE RESTROOM TILE - CV 170 A-F | LAMPMAN, COLLEEN | CLOSED | 2014-12-08 | PCV CA: PULL DOORS IN ALL CV RESTROOMS FOR TILE PROJECT | 170 | CLOSED | 0 | 0 | 2009.664 | 2009.664
PJ0005129 | M&R HOUS 15/16: REPLACE RESTROOM TILE - CV 170 A-F | LAMPMAN, COLLEEN | CLOSED | 2014-12-08 | PCV PL: PULL TOILETS IN ALL CV RESTROOMS FOR TILE PROJECT | 170 | CLOSED | 0 | 0 | 14493.828 | 14493.828
PJ0005129 Total | [7 empty] | 113286.86 | 0 | 112096.502 | 112096.502
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | AD: JOC 14.033.026 MAINO | 113 | CLOSED | 162685.8816 | 0 | 160168.3321 | 160168.3321
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | AD: STATE FIRE MARSHAL FEES | 113 | OPEN | 0 | 0 | 234.3942 | 234.3942
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | CP: PROJECT CONTINGENCY | 113 | OPEN | 16381.45 | 0 | 0 | 0
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | EH&S: | 113 | OPEN | 304.368 | 0 | 0 | 0
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | EL:INSTALL NEW BREAKER FOR POC OF MAU T4 & T5 SIERRA MADRE | 113 | OPEN | 3173.136 | 0 | 1783.23 | 1783.23
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | ES:CONTRACTOR SUPPORT AND BALANCING OF SYSTEM T4&T5, SIERRA MADR | 113 | CLOSED | 2866.56 | 0 | 590.976 | 590.976
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | IN: M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | 113 | CLOSED | 706.44 | 0 | 282.576 | 282.576
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | LO: CLOSURE REMOVAL AND INSTALLATION | 113 | CLOSED | 793.2305 | 0 | 2224.524 | 2224.524
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | PM: M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005128 | M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2014-12-08 | SM: M&R HOUS 15/16: UPGRADE MECH. EXHAUST SYS - SM 113 T4 & T5 | 113 | OPEN | 0 | 0 | 0 | 0
PJ0005128 Total | [7 empty] | 186911.0661 | 0 | 165284.0323 | 165284.0323
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | AD: JOC 14.033.035 MAINO | RESIDENCE | CLOSED | 90162.8973 | 0 | 90162.8973 | 90162.8973
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 3098.72 | 0 | 3098.72 | 3098.72
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 567.1 | 0 | 0 | 0
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | CA: PROVIDE SUPPORT FOR DOOR/FRAME INSTALL | RESIDENCE | CLOSED | 495.018 | 0 | 745.314 | 745.314
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 7020.46 | 0 | 0 | 0
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | EH&S: TESTING SAMPLES FOR COMPLIANCE | RESIDENCE | CLOSED | 812.8752 | 0 | 0 | 0
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | IN: M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | RESIDENCE | CLOSED | 786.2677 | 0 | 494.508 | 494.508
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | LO: LOCKSET AND CLOSURES FOR ROOM DOOR - WHITNEY HALL | RESIDENCE | CLOSED | 42539.6227 | 0 | 24280.938 | 24280.938
PJ0005127 | M&R HOUS 15/16: REPLACE DOORS & JAMBS - NORTH MT | HICKS, MICHAEL | CLOSED | 2014-12-08 | PA: SUPPLY FINISH PAINT MATERIALS TO JOC CONTRACTOR (N/L) | RESIDENCE | CLOSED | 4702.5815 | 0 | 320.052 | 320.052
PJ0005127 Total | [7 empty] | 150185.5424 | 0 | 119102.4293 | 119102.4293
PJ0005126 | M&R HOUS 15/16: DESIGN CENTRALIZED TRASH ENCLOSURES - NORTH MT | LAMPMAN, GREG | CLOSED | 2014-12-08 | AD: FAC PLANNING DESIGN FEES | RESIDENCE | CLOSED | 2000 | 0 | 2000 | 2000
PJ0005126 | M&R HOUS 15/16: DESIGN CENTRALIZED TRASH ENCLOSURES - NORTH MT | LAMPMAN, GREG | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0005126 Total | [7 empty] | 2000 | 0 | 2000 | 2000
PJ0005125 | M&R HOUS 15/16: REPLACE ROOF / REMOVE SOLAR PANELS - RES 110 | LAMPMAN, GREG | CLOSED | 2014-12-08 | AD: JOC 14.033.032 MAINO | 110 | CLOSED | 307036.0078 | 0 | 307036.0078 | 307036.0078
PJ0005125 | M&R HOUS 15/16: REPLACE ROOF / REMOVE SOLAR PANELS - RES 110 | LAMPMAN, GREG | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 16520.06 | 0 | 0 | 0
PJ0005125 | M&R HOUS 15/16: REPLACE ROOF / REMOVE SOLAR PANELS - RES 110 | LAMPMAN, GREG | CLOSED | 2014-12-08 | IN: M&R HOUS 15/16: REPLACE ROOF / REMOVE SOLAR PANELS - RES 110 | 110 | CLOSED | 211.932 | 0 | 388.542 | 388.542
PJ0005125 | M&R HOUS 15/16: REPLACE ROOF / REMOVE SOLAR PANELS - RES 110 | LAMPMAN, GREG | CLOSED | 2014-12-08 | LO: CHANGE ROOF ACCESS LOCK TO CONSTRUCTION CORE - TENAYA 110 | 110 | CLOSED | 60.924 | 0 | 60.924 | 60.924
PJ0005125 Total | [7 empty] | 323828.9238 | 0 | 307485.4738 | 307485.4738
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | AD: FLOOR CONNECTION | 113 | CLOSED | 8731.2 | 0 | 8731.2 | 8731.2
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | AD: JOC 14.034.006 MAINO | 113 | CLOSED | 660029.1469 | 0 | 660029.1469 | 660029.1469
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | AD: MCKENNA ENVIRONMENTAL | 113 | CLOSED | 17013 | 0 | 16987.32 | 16987.32
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | AD: STATE FIRE MARSHAL | 113 | CLOSED | 1070 | 0 | 1044.2451 | 1044.2451
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | ANTS:CONTRACTOR SUPPORT FOR FIRE ALARMS SM T4 | 113 | CLOSED | 406.656 | 0 | 101.664 | 101.664
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | CA:PROVIDE CONTRACTOR SUPPORT AS NEEDED SMT4 | 113 | CLOSED | 333.72 | 0 | 860.7 | 860.7
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 66840.38 | 0 | 0 | 0
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 113 | CLOSED | 0 | 0 | 159 | 159
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | EL:DISCONNECT ELECTRICAL AND FIRE- INSTALL NEW SM T4 RESTROOMS | 113 | CLOSED | 32895.9902 | 0 | 58769.664 | 58769.664
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | IN: M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | 113 | CLOSED | 706.44 | 0 | 1518.846 | 1518.846
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | LO:INSTALL ORANGE CORES ON FLOORS, DOOR CLOSERS AND LOCK SM T4 | 113 | CLOSED | 4314.7399 | 0 | 3676.764 | 3676.764
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | PA:PAINT WALLS ON HALLWAY SIDE- SIERRA MADRE T4 | 113 | CLOSED | 9267.12 | 0 | 3492.522 | 3492.522
PJ0005124 | M&R HOUS 15/16: RESTROOM REMODEL - SIERRA MADRE 113 | MOLLAN, CHERYL L. | CLOSED | 2014-12-08 | PL:PURCHASE PLUMBING FIXTURES- PROVIDE CONTRACTOR SUPPORT SMT4 R | 113 | CLOSED | 29181.4891 | 0 | 30551.2043 | 30551.2043
PJ0005124 Total | [7 empty] | 830789.8822 | 0 | 785922.2763 | 785922.2763
PJ0005122 | M&R HOUS 15/16: ARC FLASH STUDY - UNIVERSITY HOUSING | POLVI, STEVEN | CLOSED | 2014-12-08 | AD: POWER ENGINEERING | RESIDENCE | CLOSED | 52162.5 | 0 | 52913.64 | 52913.64
PJ0005122 | M&R HOUS 15/16: ARC FLASH STUDY - UNIVERSITY HOUSING | POLVI, STEVEN | CLOSED | 2014-12-08 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 5646.44 | 0 | 0 | 0
PJ0005122 Total | [7 empty] | 57808.94 | 0 | 52913.64 | 52913.64
PJ0005118 | REMOVE ONE BUILT-IN WOOD CABINET & MOVE ANOTHER- BLDG 124 RM 120 | BRENNAN, MICHAEL | CLOSED | 2014-10-29 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 124 | CLOSED | 1979.5 | 0 | 1476.6 | 1476.6
PJ0005118 | REMOVE ONE BUILT-IN WOOD CABINET & MOVE ANOTHER- BLDG 124 RM 120 | BRENNAN, MICHAEL | CLOSED | 2014-10-29 | CA: INSTALL COVE BASE - BLDG. 124 ROOM 120 | 124 | CLOSED | 282.48 | 0 | 183.627 | 183.627
PJ0005118 | REMOVE ONE BUILT-IN WOOD CABINET & MOVE ANOTHER- BLDG 124 RM 120 | BRENNAN, MICHAEL | CLOSED | 2014-10-29 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 49.29 | 0 | 0 | 0
PJ0005118 | REMOVE ONE BUILT-IN WOOD CABINET & MOVE ANOTHER- BLDG 124 RM 120 | BRENNAN, MICHAEL | CLOSED | 2014-10-29 | IN: REMOVE 1 BUILT-IN WOOD CABINET &MOVE ANOTHER-BLDG 124 RM 120 | 124 | CLOSED | 78.4148 | 0 | 35.322 | 35.322
PJ0005118 | REMOVE ONE BUILT-IN WOOD CABINET & MOVE ANOTHER- BLDG 124 RM 120 | BRENNAN, MICHAEL | CLOSED | 2014-10-29 | PA: PAINTING IN BUILDING 124 ROOM 120 | 124 | CLOSED | 1222.5815 | 0 | 680.988 | 680.988
PJ0005118 Total | [7 empty] | 3612.2663 | 0 | 2376.537 | 2376.537
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: COASTAL JANITORIAL | 020 | CLOSED | 0 | 0 | 272.85 | 272.85
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: DEEP BLUE INTEGRATION | 020 | CLOSED | 32100 | 0 | 30210.38 | 30210.38
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: FLOOR CONNECTION | 020 | CLOSED | 10876.8175 | 0 | 10876.8175 | 10876.8175
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: J.L. FASULO | 020 | CLOSED | 2074.73 | 0 | 2074.73 | 2074.73
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | AD: MORELAND THOMPSON | 020 | CLOSED | 17191.69 | 0 | 17191.69 | 17191.69
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | CA: DEMO FLOOR AND OTHER ITEMS, INSTALL DRYWALL AND BOARDS | 020 | CLOSED | 5371.2204 | 0 | 9943.488 | 9943.488
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 5718.73 | 0 | 0 | 0
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 020 | CLOSED | 0 | 0 | 8.4 | 8.4
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | EL: BRING POWER CIRCUITS TO ROOM | 020 | CLOSED | 42905.5727 | 0 | 43978.392 | 43978.392
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | IN: RENOVATE LAB IN BUILDING 20, ROOM 127 | 020 | CLOSED | 628.7316 | 0 | 317.898 | 317.898
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | LO: INSTALL ORANGE CORE | 020 | CLOSED | 135.8605 | 0 | 91.386 | 91.386
PJ0005114 | RENOVATE LAB IN BUILDING 20, ROOM 127 | BRENNAN, MICHAEL | CLOSED | 2014-11-25 | PA: PAINTING FOR LAB RENOVATION IN BUILDING 20, ROOM 127 | 020 | CLOSED | 3955.5251 | 0 | 3340.515 | 3340.515
PJ0005114 Total | [7 empty] | 120958.8778 | 0 | 118306.5465 | 118306.5465
PJ0005113 | INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | MOLLAN, CHERYL L. | CLOSED | 2014-11-25 | AD: FLOOR CONNECTION | 038 | CLOSED | 5639.8309 | 0 | 5639.8309 | 5639.8309
PJ0005113 | INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | MOLLAN, CHERYL L. | CLOSED | 2014-11-25 | AD: STATE FIRE MARSHAL FEES | 038 | CLOSED | 428 | 0 | 0 | 0
PJ0005113 | INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | MOLLAN, CHERYL L. | CLOSED | 2014-11-25 | CA:TRIM DOORS AT BLDG 38, ROOM 152 | 038 | CLOSED | 393.72 | 0 | 427.104 | 427.104
PJ0005113 | INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | MOLLAN, CHERYL L. | CLOSED | 2014-11-25 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 280.82 | 0 | 0 | 0
PJ0005113 | INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | MOLLAN, CHERYL L. | CLOSED | 2014-11-25 | IN: INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | 038 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005113 | INSTALL CARPETING IN GRANTS DEVELOPMENT OFFICE 038-152 | MOLLAN, CHERYL L. | CLOSED | 2014-11-25 | MO:CONTRACTOR SUPPORT FOR MOVING BOXES AND FURN 38, 152ROOMS | 038 | CLOSED | 536.256 | 0 | 371.844 | 371.844
PJ0005113 Total | [7 empty] | 7419.9149 | 0 | 6509.4229 | 6509.4229
PJ0005111 | SR 14/15: INSPECTION & TREATMENT OF UTILITY POLES - CAMPUS WIDE | POLVI, STEVEN | CLOSED | 2014-11-25 | AD: OSMOSE UTILITY SERVICES, INC. | U-ELEC | CLOSED | 29532 | 0 | 23087.5719 | 23087.5719
PJ0005111 | SR 14/15: INSPECTION & TREATMENT OF UTILITY POLES - CAMPUS WIDE | POLVI, STEVEN | CLOSED | 2014-11-25 | CP: PROJECT CONTINGENCY | U-ELEC | CLOSED | 3107.83 | 0 | 0 | 0
PJ0005111 | SR 14/15: INSPECTION & TREATMENT OF UTILITY POLES - CAMPUS WIDE | POLVI, STEVEN | CLOSED | 2014-11-25 | EL:SUPPORT INSPECTION OF UTILITY POLES | U-ELEC | CLOSED | 1546.272 | 0 | 8908.062 | 8908.062
PJ0005111 Total | [7 empty] | 34186.102 | 0 | 31995.6339 | 31995.6339
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | AD: JOC 14.033.020 MAINO | 010 | CLOSED | 550400.8845 | 0 | 430522.6748 | 430522.6748
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | AD: MECA | 010 | CLOSED | 7490 | 0 | 8900.3777 | 8900.3777
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | CA: SHOP SUPPORT FOR BUILDING RE-ROOF AND CEILING REPAIR | 010 | CLOSED | 2404.416 | 0 | 5064.018 | 5064.018
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 37269.81 | 0 | 0 | 0
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | CPE: SHUT DOWN/RESTART COOLING UNITS ON ROOF - BLDG. 10 | 010 | CLOSED | 1997.952 | 0 | 17014.209 | 17014.209
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | CU: MOVE FURNITURE FROM HALLWAY; STRIP & WAX FLOOR BLDG 10 RM203 | 010 | CLOSED | 131.184 | 0 | 791.208 | 791.208
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | EL: SHOP SUPPORT FOR BLDG RE-ROOF AND CEILING REPAIRS | 010 | CLOSED | 19264.752 | 0 | 33571.716 | 33571.716
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | ES: SHOP SUPPORT FOR CEILING REPAIRS IN BUILDING 10. | 010 | CLOSED | 1997.952 | 0 | 801.57 | 801.57
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | IN: SR 14/15: REPLACE ROOF - BLD 10 | 010 | CLOSED | 570.0984 | 0 | 706.44 | 706.44
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | LO: CHANGE CORES ON ROOMS 317 & 317A, BLDG. 22 | 010 | CLOSED | 116.088 | 0 | 179.892 | 179.892
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | PA: REPAIR AND PAINT DAMAGED WALLS | 010 | CLOSED | 2199.648 | 0 | 2300.298 | 2300.298
PJ0005110 | SR 14/15: REPLACE ROOF - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-11-18 | PL: REPAIR VENT THRU ROOF PIPE | 010 | CLOSED | 2089.344 | 0 | 883.536 | 883.536
PJ0005110 Total | [7 empty] | 625932.1289 | 0 | 500735.9395 | 500735.9395
PJ0005108 | EXPAND OVERHEAD PAGING SYSTEM - BLDG 27 | DILLON, JEFFREY | CLOSED | 2014-11-19 | AD: GRAND PERFORMANCE | 027 | CLOSED | 2782 | 0 | 2782 | 2782
PJ0005108 | EXPAND OVERHEAD PAGING SYSTEM - BLDG 27 | DILLON, JEFFREY | CLOSED | 2014-11-19 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 521.81 | 0 | 0 | 0
PJ0005108 | EXPAND OVERHEAD PAGING SYSTEM - BLDG 27 | DILLON, JEFFREY | CLOSED | 2014-11-19 | EL:SPEAKER SYSTEM WIRE PULL ABOVE CEILING IN CORRIDOR; COORD. | 027 | CLOSED | 2294.2811 | 0 | 328.584 | 328.584
PJ0005108 | EXPAND OVERHEAD PAGING SYSTEM - BLDG 27 | DILLON, JEFFREY | CLOSED | 2014-11-19 | IN: PJ 5108 EXPAND OVERHEAD PAGING SYSTEM - BLDG 27 | 027 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005108 Total | [7 empty] | 5739.3791 | 0 | 3216.55 | 3216.55
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | CA: COMMENCEMENT SUPPORT - 12/13 | GENERAL | CLOSED | 2819.4 | 0 | 2702.345 | 2702.345
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | CU: SUPPORT FOR 2014 FALL COMMENCEMENT - 12/13 | GENERAL | CLOSED | 0 | 0 | 248.71 | 248.71
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | EL: SUPPORT FOR FALL COMMENCEMENT - 12/13 | GENERAL | CLOSED | 0 | 0 | 1031.24 | 1031.24
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | ES: STAND BY SUPPORT FOR 2014 FALL COMMENCEMENT- 12/13 | GENERAL | CLOSED | 0 | 0 | 599.145 | 599.145
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | LA: LANDSCAPING SUPPORT FOR 2014 FALL COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 227.7 | 227.7
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | MO: DELIVER ITEMS FOR FALL COMMENCEMENT - 12/10 | GENERAL | CLOSED | 0 | 0 | 120.72 | 120.72
PJ0005107 | SUPPORT FOR 2014 FALL COMMENCEMENT: DEC 13, 2014 (MAINT) | POPHAM, DONALD J. | CLOSED | 2014-11-19 | PA: SUPPORT FOR FALL COMMENCEMENT - 12/12/2014 (N/L) | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0005107 Total | [7 empty] | 2819.4 | 0 | 4929.86 | 4929.86
PJ0005104 | CARPET TILE INSTALLATION & PAINT IN 01-222A & 01-222B | NORTON, DAVE | CLOSED | 2014-11-19 | AD: FLOOR CONNECTION | 001 | CLOSED | 2033 | 0 | 1952.75 | 1952.75
PJ0005104 | CARPET TILE INSTALLATION & PAINT IN 01-222A & 01-222B | NORTON, DAVE | CLOSED | 2014-11-19 | CA: REMOVE STANDARDS | 001 | CLOSED | 313.5173 | 0 | 145.488 | 145.488
PJ0005104 | CARPET TILE INSTALLATION & PAINT IN 01-222A & 01-222B | NORTON, DAVE | CLOSED | 2014-11-19 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 389.45 | 0 | 0 | 0
PJ0005104 | CARPET TILE INSTALLATION & PAINT IN 01-222A & 01-222B | NORTON, DAVE | CLOSED | 2014-11-19 | IN: CARPET TILE INSTALLATION & PAINT IN 01-222A & 01-222B | 001 | CLOSED | 71.1022 | 0 | 35.322 | 35.322
PJ0005104 | CARPET TILE INSTALLATION & PAINT IN 01-222A & 01-222B | NORTON, DAVE | CLOSED | 2014-11-19 | PA: PAINT WALLS | 001 | CLOSED | 1032.5094 | 0 | 890.46 | 890.46
PJ0005104 Total | [7 empty] | 3839.5788 | 0 | 3024.02 | 3024.02
PJ0005101 | URGENT - NEW DOOR & KEY PAD - BLDG 052 RM E25 | LAMPMAN, GREG | CLOSED | 2014-11-14 | AD: WLH BUILDERS | 052 | CLOSED | 722.25 | 0 | 722.25 | 722.25
PJ0005101 | URGENT - NEW DOOR & KEY PAD - BLDG 052 RM E25 | LAMPMAN, GREG | CLOSED | 2014-11-14 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 421.03 | 0 | 0 | 0
PJ0005101 | URGENT - NEW DOOR & KEY PAD - BLDG 052 RM E25 | LAMPMAN, GREG | CLOSED | 2014-11-14 | IN: URGENT - NEW DOOR & KEY PAD - BLDG 052 RM E25 | 052 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005101 | URGENT - NEW DOOR & KEY PAD - BLDG 052 RM E25 | LAMPMAN, GREG | CLOSED | 2014-11-14 | LO: INSTALL 2 KEY PAD LOCKS (TRILOGY LOCKS) | 052 | CLOSED | 3346.9723 | 0 | 2118.84 | 2118.84
PJ0005101 Total | [7 empty] | 4631.5403 | 0 | 2911.734 | 2911.734
PJ0005100 | STRUCTURAL ASSESSMENT OF TRUSSES - BLDG. 150G | LAMPMAN, GREG | CLOSED | 2014-11-18 | CP: PROJECT CONTINGENCY | 150G | CLOSED | 0 | 0 | 0 | 0
PJ0005100 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005099 | WIRELESS SECURITY BOX & PANIC BUTTON - BLDG. 074M-M064A RM A100 | LAMPMAN, GREG | CLOSED | 2014-11-14 | AD: CAME SECURITY | 074M-M064A | CLOSED | 1524.75 | 0 | 1524.75 | 1524.75
PJ0005099 | WIRELESS SECURITY BOX & PANIC BUTTON - BLDG. 074M-M064A RM A100 | LAMPMAN, GREG | CLOSED | 2014-11-14 | ANTS: PROGRAM ALARMS FOR MODULAR A AT OLD UPD SITE - RM. 100 | 074M-M064A | CLOSED | 48.048 | 0 | 67.776 | 67.776
PJ0005099 | WIRELESS SECURITY BOX & PANIC BUTTON - BLDG. 074M-M064A RM A100 | LAMPMAN, GREG | CLOSED | 2014-11-14 | CP: PROJECT CONTINGENCY | 074M-M064A | CLOSED | 110.81 | 0 | 0 | 0
PJ0005099 | WIRELESS SECURITY BOX & PANIC BUTTON - BLDG. 074M-M064A RM A100 | LAMPMAN, GREG | CLOSED | 2014-11-14 | IN: INSTALL ELECTRIC CAMES SECURITY BOX- BLDG 074M-M064A RM A100 | 074M-M064A | CLOSED | 64.056 | 0 | 70.644 | 70.644
PJ0005099 Total | [7 empty] | 1747.664 | 0 | 1663.17 | 1663.17
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | AD: FLOOR CONNECTION | 192 | CLOSED | 1871.43 | 0 | 1764.43 | 1764.43
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | AD: J.L. FASULO DRYWALL | 192 | CLOSED | 740.44 | 0 | 744.72 | 744.72
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | AD: STATE FIRE MARSHAL | 192 | CLOSED | 401.25 | 0 | 0 | 0
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | CA: INSTALLING HM WINDOW FRAME AND RATED GLAZING | 192 | CLOSED | 10247.4486 | 0 | 7911.318 | 7911.318
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 2010.87 | 0 | 0 | 0
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | EL: REWIRE LIGHT SWITCH IN OFFICE | 192 | CLOSED | 3404.2811 | 0 | 2401.137 | 2401.137
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | IN: CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | 192 | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | LO: CHANGE FUNCTION PER OCCUPANT REQUEST - RE-KEY | 192 | CLOSED | 195.8605 | 0 | 121.386 | 121.386
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | MO: REMOVE FURNITURE FROM OFFICE AND RETURN AFTER WORK COMPLETED | 192 | CLOSED | 223.8869 | 0 | 45.072 | 45.072
PJ0005098 | CARPET, PAINT AND ADDITIONAL WINDOW - BLDG. 192 RM. 313 | HICKS, MICHAEL | CLOSED | 2014-11-12 | PA:REPAINT INTERIOR OF OFFICE, PAINT CORRIDOR WALL FOR WINDOW | 192 | CLOSED | 2589.0533 | 0 | 1489.158 | 1489.158
PJ0005098 Total | [7 empty] | 21896.4524 | 0 | 14653.831 | 14653.831
PJ0005096 | INSTALL PANIC BUTTONS UNDER DESKS - BLD 01 RM 407A & 415 | MOLLAN, CHERYL L. | CLOSED | 2014-11-05 | AD: CAME SECURITY | 001 | CLOSED | 668.75 | 0 | 668.75 | 668.75
PJ0005096 | INSTALL PANIC BUTTONS UNDER DESKS - BLD 01 RM 407A & 415 | MOLLAN, CHERYL L. | CLOSED | 2014-11-05 | ANTS:PROVIDE INTERFACE SUPPORT FOR NEW PANIC BUTTONS | 001 | CLOSED | 96.096 | 0 | 67.776 | 67.776
PJ0005096 | INSTALL PANIC BUTTONS UNDER DESKS - BLD 01 RM 407A & 415 | MOLLAN, CHERYL L. | CLOSED | 2014-11-05 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 82.89 | 0 | 0 | 0
PJ0005096 | INSTALL PANIC BUTTONS UNDER DESKS - BLD 01 RM 407A & 415 | MOLLAN, CHERYL L. | CLOSED | 2014-11-05 | IN: INSTALL PANIC BUTTONS UNDER DESKS - BLD 01 RM 407A & 415 | 001 | CLOSED | 64.056 | 0 | 70.644 | 70.644
PJ0005096 Total | [7 empty] | 911.792 | 0 | 807.17 | 807.17
PJ0005095 | INSTALL CEILING OUTLETS FOR PROJECTORS IN BLDG. 53 | KOLEGRAFF, KENNETH | CLOSED | 2014-11-04 | AD: JOC 15.036.011 STAPLES | 053 | CLOSED | 16221.2214 | 0 | 16221.2214 | 16221.2214
PJ0005095 | INSTALL CEILING OUTLETS FOR PROJECTORS IN BLDG. 53 | KOLEGRAFF, KENNETH | CLOSED | 2014-11-04 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 2993.23 | 0 | 0 | 0
PJ0005095 | INSTALL CEILING OUTLETS FOR PROJECTORS IN BLDG. 53 | KOLEGRAFF, KENNETH | CLOSED | 2014-11-04 | EL: INSTALL ELECTRICAL RECEPTACLES FOR PROJECTORS | 053 | CLOSED | 11903.7151 | 0 | 11285.097 | 11285.097
PJ0005095 | INSTALL CEILING OUTLETS FOR PROJECTORS IN BLDG. 53 | KOLEGRAFF, KENNETH | CLOSED | 2014-11-04 | IN: INSTALL CEILING OUTLETS FOR PROJECTORS | 053 | CLOSED | 1412.88 | 0 | 247.254 | 247.254
PJ0005095 | INSTALL CEILING OUTLETS FOR PROJECTORS IN BLDG. 53 | KOLEGRAFF, KENNETH | CLOSED | 2014-11-04 | LO: | 053 | CLOSED | 135.8605 | 0 | 121.848 | 121.848
PJ0005095 Total | [7 empty] | 32666.907 | 0 | 27875.4204 | 27875.4204
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | AD: CLARK SECURITY | 008 | CLOSED | 9434.7571 | 0 | 9434.7571 | 9434.7571
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | AD: FLOOR CONNECTION | 008 | CLOSED | 3975.05 | 0 | 3975.05 | 3975.05
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | AD: KI FURNITURE | 008 | CLOSED | 2063.5485 | 0 | 2063.5485 | 2063.5485
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | CP: PROJECT CONTINGENCY | 008 | CLOSED | 114.2 | 0 | 0 | 0
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | EL: INSTALL ELECTRICAL FOR NEW ADA DOOR PUSH PADS BLDG8, 123 | 008 | CLOSED | 1740.6802 | 0 | 2740.074 | 2740.074
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | IN: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | 008 | CLOSED | 192.168 | 0 | 141.288 | 141.288
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | LO: INSTALL NEW ADA DOOR PUSH PADS, BLDG 8, ROOM 123 | 008 | CLOSED | 1741.32 | 0 | 1683.468 | 1683.468
PJ0005094 | SR 14/15: NEW ADA PUSH PADS FOR DOOR OPENING/BLINDS-BLD 8/123 | MOLLAN, CHERYL L. | CLOSED | 2014-09-17 | PA: SR 14/15: NEW ADA PUSH PADS DR OPENING/BLINDS-BLD 8/123 | 008 | CLOSED | 431.448 | 0 | 0 | 0
PJ0005094 Total | [7 empty] | 19693.1718 | 0 | 20038.1856 | 20038.1856
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | AD: JOC 14.033.030 MAINO | STREETS | CLOSED | 185447.05 | 0 | 183820.9924 | 183820.9924
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | AD: JOC 15.035.001 MAINO | STREETS | CLOSED | 15398.4877 | 0 | 15398.4877 | 15398.4877
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 1595.88 | 0 | 0 | 0
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | EL: (N/L) | STREETS | CLOSED | 1630.848 | 0 | 0 | 0
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | IN: SP 14/15: REPAVE ROADWAYS BEHIND S.MTN DORMS | STREETS | CLOSED | 353.22 | 0 | 176.61 | 176.61
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | LA: (N/L) | STREETS | CLOSED | 1669.2547 | 0 | 0 | 0
PJ0005093 |  | NORTON, DAVE | CLOSED | 2014-11-08 | PL: REPAIR WATER LEAK | STREETS | CLOSED | 3888.888 | 0 | 1622.573 | 1622.573
PJ0005093 Total | [7 empty] | 209983.6284 | 0 | 201018.6631 | 201018.6631
PJ0005092 | INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | BRENNAN, MICHAEL | CLOSED | 2014-11-04 | AD: QUICKCRETE | 018 | CLOSED | 1337.5 | 0 | 1297.482 | 1297.482
PJ0005092 | INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | BRENNAN, MICHAEL | CLOSED | 2014-11-04 | CA: INSTALL PLAQUES ON MEMORIAL BENCHES | 018 | CLOSED | 124.0326 | 0 | 27.81 | 27.81
PJ0005092 | INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | BRENNAN, MICHAEL | CLOSED | 2014-11-04 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 172.09 | 0 | 0 | 0
PJ0005092 | INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | BRENNAN, MICHAEL | CLOSED | 2014-11-04 | EO: MOVE MEMORIAL BENCHES INTO PLACE | 018 | CLOSED | 114.5596 | 0 | 91.404 | 91.404
PJ0005092 | INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | BRENNAN, MICHAEL | CLOSED | 2014-11-04 | IN: INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | 018 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005092 | INSTALL MEMORIAL BENCH FOR IVAN A. WOOD BEHIND BLDG 18 | BRENNAN, MICHAEL | CLOSED | 2014-11-04 | MO: CXLD | 018 | CLOSED | 74.7407 | 0 | 0 | 0
PJ0005092 Total | [7 empty] | 1893.5668 | 0 | 1487.34 | 1487.34
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | AD: APC CONTRACTORS | 016A | CLOSED | 0 | 0 | 4739.03 | 4739.03
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | AD: FLOOR CONNECTION | 016A | CLOSED | 0 | 0 | 2487.75 | 2487.75
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | AD: MCKENNA ENVIRONMENTAL | 016A | CLOSED | 0 | 0 | 3472.15 | 3472.15
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | CA: SUPPORT FOR HERDSMAN HALL CEILING LEAK #183 | 016A | CLOSED | 0 | 0 | 2851.6626 | 2851.6626
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | CP: PROJECT CONTINGENCY | 016A | CLOSED | 0 | 0 | 0 | 0
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | EL:REMOVE AND REINSTALL LIGHT IN BATHROOM | 016A | CLOSED | 0 | 0 | 895.7126 | 895.7126
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | ES: REPAIR DUCT WORK AND REINSTALL DEFUSER | 016A | CLOSED | 0 | 0 | 387.16 | 387.16
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | IN: SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD | 016A | CLOSED | 0 | 0 | 80.07 | 80.07
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | LO: CONSTRUCTION CORES FOR HERDSMAN HALL CEILING REPAIRS | 016A | CLOSED | 0 | 0 | 210.622 | 210.622
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | PA: SUPPORT FOR HERDSMAN HALL CEILING LEAK | 016A | CLOSED | 0 | 0 | 2913.783 | 2913.783
PJ0005090 | SR 14/15: REPAIR LEAKING CEILING - HERDSMAN HALL - BLD 16A | POLVI, STEVEN | CLOSED | 2014-10-27 | PL: REPAIR LEAKING PIPE IN CEILING AT HERDSMAN HALL 16A | 016A | CLOSED | 0 | 0 | 1438.848 | 1438.848
PJ0005090 Total | [7 empty] | 0 | 0 | 19476.7882 | 19476.7882
PJ0005088 | CHANGE DEPARTMENT SIGNAGE AT 180-260 | PINHEIRO, RICK | CLOSED | 2014-07-21 | AD: THE SIGN PLACE | 180 | CLOSED | 285.8184 | 0 | 285.8184 | 285.8184
PJ0005088 | CHANGE DEPARTMENT SIGNAGE AT 180-260 | PINHEIRO, RICK | CLOSED | 2014-07-21 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 34.72 | 0 | 0 | 0
PJ0005088 Total | [7 empty] | 320.5384 | 0 | 285.8184 | 285.8184
PJ0005087 | INSTALL SECURITY LOCKING SYSTEMS - BLD 45 RMS 114-120 | NORTON, DAVE | HOLD | 2014-10-30 | CP: PROJECT CONTINGENCY | 045 | OPEN | 0 | 0 | 0 | 0
PJ0005087 | INSTALL SECURITY LOCKING SYSTEMS - BLD 45 RMS 114-120 | NORTON, DAVE | HOLD | 2014-10-30 | PM: INSTALL SECURITY LOCKING SYSTEMS - BLD 45 RMS 114-120 | 045 | OPEN | 0 | 0 | 0 | 0
PJ0005087 | INSTALL SECURITY LOCKING SYSTEMS - BLD 45 RMS 114-120 | NORTON, DAVE | HOLD | 2014-10-30 | SM: INSTALL SECURITY LOCKING SYSTEMS - BLD 45 RMS 114-120 | 045 | OPEN | 0 | 0 | 0 | 0
PJ0005087 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005084 | INSTALL RO SYSTEM AND RELOCATE SOFT-WATER BRINE - BLD 42 RM 115 | GONZALES, ALBERT M. | CLOSED | 2014-10-28 | AD: SILVA CLEAN, INC. (NO COST - DONATED BY SILVA CLEAN) | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0005084 | INSTALL RO SYSTEM AND RELOCATE SOFT-WATER BRINE - BLD 42 RM 115 | GONZALES, ALBERT M. | CLOSED | 2014-10-28 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 189.08 | 0 | 0 | 0
PJ0005084 | INSTALL RO SYSTEM AND RELOCATE SOFT-WATER BRINE - BLD 42 RM 115 | GONZALES, ALBERT M. | CLOSED | 2014-10-28 | EL: | 042 | CLOSED | 360.0012 | 0 | 0 | 0
PJ0005084 | INSTALL RO SYSTEM AND RELOCATE SOFT-WATER BRINE - BLD 42 RM 115 | GONZALES, ALBERT M. | CLOSED | 2014-10-28 | IN: INSTALL RO SYSTEM & RELOCATE SOFT-WATER BRINE -BLD 42 RM 115 | 042 | CLOSED | 128.112 | 0 | 141.288 | 141.288
PJ0005084 | INSTALL RO SYSTEM AND RELOCATE SOFT-WATER BRINE - BLD 42 RM 115 | GONZALES, ALBERT M. | CLOSED | 2014-10-28 | PL: INSTALL RO SYSTEM & RELOCATE SOFT-WATER BRINE - MOTT 42-115 | 042 | CLOSED | 1402.8505 | 0 | 881.442 | 881.442
PJ0005084 Total | [7 empty] | 2080.0437 | 0 | 1022.73 | 1022.73
PJ0005083 | SR 14/15: REPLACE ELEVATOR PIT VALVE & HOSE - BLD 45 | BRENNAN, MICHAEL | CLOSED | 2014-10-28 | AD: OTIS ELEVATOR | 045 | CLOSED | 16404.17 | 0 | 16404.17 | 16404.17
PJ0005083 | SR 14/15: REPLACE ELEVATOR PIT VALVE & HOSE - BLD 45 | BRENNAN, MICHAEL | CLOSED | 2014-10-28 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 1711.03 | 0 | 0 | 0
PJ0005083 | SR 14/15: REPLACE ELEVATOR PIT VALVE & HOSE - BLD 45 | BRENNAN, MICHAEL | CLOSED | 2014-10-28 | IN: SR 14/15: REPLACE ELEVATOR PIT VALVE & HOSE - BLD 45 | 045 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0005083 Total | [7 empty] | 18243.312 | 0 | 16468.226 | 16468.226
PJ0005082 | WINDOW WASHING - BLDG 035 | CANTU, MONICA M. | CLOSED | 2014-10-22 | AD: COASTAL JANITORIAL | 035 | CLOSED | 3607.5799 | 0 | 3922.62 | 3922.62
PJ0005082 | WINDOW WASHING - BLDG 035 | CANTU, MONICA M. | CLOSED | 2014-10-22 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 360.76 | 0 | 0 | 0
PJ0005082 Total | [7 empty] | 3968.3399 | 0 | 3922.62 | 3922.62
PJ0005080 | INSTALL OPERABLE CURTAINS/SHADES TO BLOCK SUNLIGHT IN WINDOW | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-16 | AD: AGGSON'S GLASS | 046 | CLOSED | 4494 | 0 | 4071.0611 | 4071.0611
PJ0005080 | INSTALL OPERABLE CURTAINS/SHADES TO BLOCK SUNLIGHT IN WINDOW | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-16 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 541.96 | 0 | 0 | 0
PJ0005080 | INSTALL OPERABLE CURTAINS/SHADES TO BLOCK SUNLIGHT IN WINDOW | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-16 | IN: INSTALL OPERABLE CURTAINS/SHADES TO BLOCK SUNLIGHT IN WINDOW | 046 | CLOSED | 157.5361 | 0 | 105.966 | 105.966
PJ0005080 Total | [7 empty] | 5193.4961 | 0 | 4177.0271 | 4177.0271
PJ0005078 | INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYSTEM | LAMPMAN, GREG | CLOSED | 2014-10-15 | AD: JOC 16.038.008 MAINO | 017 | CLOSED | 3829.4551 | 0 | 3829.4551 | 3829.4551
PJ0005078 | INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYSTEM | LAMPMAN, GREG | CLOSED | 2014-10-15 | AD: SHORE-TEK | 017 | CLOSED | 7488.288 | 0 | 7453.62 | 7453.62
PJ0005078 | INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYSTEM | LAMPMAN, GREG | CLOSED | 2014-10-15 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 748.2 | 0 | 0 | 0
PJ0005078 | INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYSTEM | LAMPMAN, GREG | CLOSED | 2014-10-15 | IN: INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYS | 017 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005078 | INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYSTEM | LAMPMAN, GREG | CLOSED | 2014-10-15 | PM: INSTALL ENGINEERED DEMAND CONTROLLED VENTILATION (DCV) SYS | 017 | CLOSED | 0 | 0 | 0 | 0
PJ0005078 Total | [7 empty] | 12207.2311 | 0 | 11353.7191 | 11353.7191
PJ0005077 | INSTALL AIR CONDITIONING - BLDG 033 RM 395 | LAMPMAN, GREG | CLOSED | 2014-10-15 | AD: GOSS ENGINEERING | 033 | CLOSED | 8239 | 0 | 7415.1 | 7415.1
PJ0005077 | INSTALL AIR CONDITIONING - BLDG 033 RM 395 | LAMPMAN, GREG | CLOSED | 2014-10-15 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 838.03 | 0 | 0 | 0
PJ0005077 | INSTALL AIR CONDITIONING - BLDG 033 RM 395 | LAMPMAN, GREG | CLOSED | 2014-10-15 | IN: INSTALL AIR CONDITIONING - BLDG 033 RM 395 | 033 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005077 Total | [7 empty] | 9218.318 | 0 | 7485.744 | 7485.744
PJ0005076 | PURCHASE AND INSTALLATION OF BLACK OUT CURTAINS IN 10-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-08 | AD: FLOOR CONNECTION | 010 | CLOSED | 2568 | 0 | 2463.14 | 2463.14
PJ0005076 | PURCHASE AND INSTALLATION OF BLACK OUT CURTAINS IN 10-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-08 | CA: REMOVE WINDOW BLINDS AND INSTALL NEW SHADES | 010 | CLOSED | 1050.5922 | 0 | 590.688 | 590.688
PJ0005076 | PURCHASE AND INSTALLATION OF BLACK OUT CURTAINS IN 10-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-08 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 400.08 | 0 | 0 | 0
PJ0005076 | PURCHASE AND INSTALLATION OF BLACK OUT CURTAINS IN 10-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-08 | IN: PURCHASE AND INSTALLATION OF BLACK OUT CURTAINS IN 10-100 | 010 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0005076 Total | [7 empty] | 4159.9602 | 0 | 3159.794 | 3159.794
PJ0005074 | INSTALL EOC SECURITY ALARM SYSTEM - BLD 74 RM 300A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-06 | AD: CAME SECURITY ALARMS | 074D | CLOSED | 2086.5 | 0 | 2086.5 | 2086.5
PJ0005074 | INSTALL EOC SECURITY ALARM SYSTEM - BLD 74 RM 300A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-06 | ANTS: PROGRAMMING FOR EOC SECURITY ALARM SYSTEM - BLD 74 RM 300A | 074D | CLOSED | 48.048 | 0 | 67.776 | 67.776
PJ0005074 | INSTALL EOC SECURITY ALARM SYSTEM - BLD 74 RM 300A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-06 | CP: PROJECT CONTINGENCY | 074D | CLOSED | 32.49 | 0 | 0 | 0
PJ0005074 | INSTALL EOC SECURITY ALARM SYSTEM - BLD 74 RM 300A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-10-06 | IN: INSTALL EOC SECURITY ALARM SYSTEM - BLD 74 RM 300A | 074D | CLOSED | 128.112 | 0 | 176.61 | 176.61
PJ0005074 Total | [7 empty] | 2295.15 | 0 | 2330.886 | 2330.886
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | AD: FLOOR CONNECTION | 011 | CLOSED | 4049.95 | 0 | 4049.95 | 4049.95
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | AD: ITS | 011 | CLOSED | 971.9345 | 0 | 971.9345 | 971.9345
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | AD: JOC 16.038.006 MAINO | 011 | CLOSED | 18489.8247 | 0 | 18489.8247 | 18489.8247
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | AD: STATE FIRE MARSHAL FEES | 011 | CLOSED | 321 | 0 | 115.4637 | 115.4637
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | CA: BLDG. 11-210 GREG LAMPMAN- INSTALL GLASS MARKER BOARD. | 011 | CLOSED | 2287.092 | 0 | 1198.608 | 1198.608
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 1827.88 | 0 | 0 | 0
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | EL: CONTRACTOR SUPPORT | 011 | CLOSED | 1313.9328 | 0 | 622.038 | 622.038
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | IN: REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | 011 | CLOSED | 211.932 | 0 | 459.186 | 459.186
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | PA: PRIME AND PAINT 11-210 | 011 | CLOSED | 5285.928 | 0 | 1643.928 | 1643.928
PJ0005073 | REMODEL OFFICES, CONFERENCE, BREAK, & LOBBY AREAS - BLDG 11 | LAMPMAN, GREG | CLOSED | 2014-10-20 | PM: REMODEL OFFICES, CONFERENCE, BREAK,&LOBBY AREAS-BLDG 11 | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0005073 Total | [7 empty] | 34759.474 | 0 | 27550.9329 | 27550.9329
PJ0005072 | INSTALL CARPET & PAINT - BLDG 11 ROOMS 204, 205, 207, & 208 | MCNALLY, CURTIS | CLOSED | 2014-10-16 | AD: FLOOR CONNECTION | 011 | CLOSED | 3638 | 0 | 2927.9266 | 2927.9266
PJ0005072 | INSTALL CARPET & PAINT - BLDG 11 ROOMS 204, 205, 207, & 208 | MCNALLY, CURTIS | CLOSED | 2014-10-16 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 648.01 | 0 | 0 | 0
PJ0005072 | INSTALL CARPET & PAINT - BLDG 11 ROOMS 204, 205, 207, & 208 | MCNALLY, CURTIS | CLOSED | 2014-10-16 | IN: INSTALL CARPET & PAINT - BLDG 11 ROOMS 204, 205, 207, & 208 | 011 | CLOSED | 141.288 | 0 | 35.322 | 35.322
PJ0005072 | INSTALL CARPET & PAINT - BLDG 11 ROOMS 204, 205, 207, & 208 | MCNALLY, CURTIS | CLOSED | 2014-10-16 | PA: PAINTING IN ROOMS 204, 205, 207, & 208 - BLDG. 011 | 011 | CLOSED | 2804.5439 | 0 | 1795.332 | 1795.332
PJ0005072 Total | [7 empty] | 7231.8419 | 0 | 4758.5806 | 4758.5806
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | AD: FLOOR CONNECTION | 003 | CLOSED | 1267.95 | 0 | 1267.95 | 1267.95
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | AD: J.L. FASULO DRYWALL | 003 | CLOSED | 5332.88 | 0 | 5332.88 | 5332.88
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | AD: JL. FASULO CARPENTRY | 003 | CLOSED | 1800.81 | 0 | 1800.81 | 1800.81
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | AD: KNECTS HVAC | 003 | CLOSED | 3745 | 0 | 3545.98 | 3545.98
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | AD: MORRO BAY CABINETS | 003 | CLOSED | 6307.65 | 0 | 4542.15 | 4542.15
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 283.55 | 0 | 415.0744 | 415.0744
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | CA: INSTALL WINDOW IN DOOR | 003 | CLOSED | 309.2472 | 0 | 550.776 | 550.776
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 2808.11 | 0 | 0 | 0
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | CU: OFFICE CLEAN | 003 | CLOSED | 111.8633 | 0 | 198.93 | 198.93
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | EL: ELECTRICAL | 003 | CLOSED | 2867.6903 | 0 | 2792.424 | 2792.424
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | IN: EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | 003 | CLOSED | 282.576 | 0 | 282.576 | 282.576
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | LO: INSTALL ORANGE CORE LOCK | 003 | CLOSED | 135.8605 | 0 | 30.462 | 30.462
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | PA: PAINT | 003 | CLOSED | 3355.5251 | 0 | 1217.976 | 1217.976
PJ0005070 | EXPAND LITC SPACE UTILIZING CLOSET BEHIND OFFICES | NORTON, DAVE | CLOSED | 2014-10-14 | PL: REMOVE & REINSTALL SINK & FAUCET | 003 | CLOSED | 2168.5313 | 0 | 906.012 | 906.012
PJ0005070 Total | [7 empty] | 30777.2436 | 0 | 22884.0004 | 22884.0004
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | AD: COASTAL DEMO (BLDG 65) | GENERAL | OPEN | 1155.814 | 0 | 963 | 963
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | AD: REPUBLIC ELEVATOR COMPANY (PO13486L1-10) | GENERAL | OPEN | 359887.7055 | 29326.56 | 326994.14 | 356320.7
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | AD: REPUBLIC ELEVATOR COMPANY (PO13486L11-13) | GENERAL | OPEN | 48588.0045 | 0 | 48588.0045 | 48588.0045
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | AD: VDA CONSULTANTS | GENERAL | OPEN | 5564 | 0 | 5564 | 5564
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | ANTS: | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | EL: PJ5069 SUPPORT - DUNN | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | IN: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | GENERAL | ASSIGNED | 2334.8412 | 0 | 70.644 | 70.644
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | MO: TRANSPORT HAZ MAT BARRELS FROM BDLG 26 TO 70G - KOLEGRAFF | GENERAL | OPEN | 67.032 | 0 | 480 | 480
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | PL: PJ5069 SUPPORT - DUNN | GENERAL | COMPLETE | 1031.808 | 0 | 5245.6944 | 5245.6944
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | PM: SR 14/15: REPAIR SINGLE BOTTOM CYLINDR ELEVATORS-21,26,19,65 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005069 | DM 15/16: REPAIR SINGLE BOTTOM CYLINDER ELEVATORS - 21,26,19,65 | DUNN, TRAVIS | IN_CONSTR | 2014-10-10 | SM: DM 15/16: REPAIR SINGLE BOTTOM CYL. ELEVATORS - 21,26,19,65 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005069 Total | [7 empty] | 418629.2052 | 29326.56 | 387905.4829 | 417232.0429
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | AD: JOC 14.034.003 MAINO | 150E | CLOSED | 43435.59 | 0 | 43435.59 | 43435.59
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | AD: STATE FIRE MARSHAL | 150E | CLOSED | 0 | 0 | 163.21 | 163.21
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | CP: PROJECT CONTINGENCY | 150E | CLOSED | 6502.83 | 0 | 0 | 0
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | EL: (FPCP FUNDING) ELECTRICAL FOR POULTRY CAGES - BLDG 150E | 150E | CLOSED | 0 | 0 | 1094.502 | 1094.502
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | EL: INSTALL ELECTRICAL TO CAGE SYSTEM | 150E | CLOSED | 14858.5578 | 0 | 37071.7175 | 37071.7175
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | IN: (FPCP FUNDING) RENOVATE POULTRY CAGES - BLDG 150E | 150E | CLOSED | 0 | 0 | 353.22 | 353.22
PJ0005066 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150E | LAMPMAN, GREG | CLOSED | 2014-10-09 | PA: PAINTING FOR POULTRY CAGE RENOVATION - BLDG 150E | 150E | CLOSED | 3496.2709 | 0 | 2132.37 | 2132.37
PJ0005066 Total | [7 empty] | 68293.2487 | 0 | 84250.6095 | 84250.6095
PJ0005065 | INSTALL DOOR MAG STRIP READER & CLASS PIN/PAD - BLDG. 192 RM 333 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-09-05 | AD: CAME SECURITY | 192 | CLOSED | 6072.25 | 0 | 6072.25 | 6072.25
PJ0005065 | INSTALL DOOR MAG STRIP READER & CLASS PIN/PAD - BLDG. 192 RM 333 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-09-05 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 750.92 | 0 | 0 | 0
PJ0005065 | INSTALL DOOR MAG STRIP READER & CLASS PIN/PAD - BLDG. 192 RM 333 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-09-05 | IN: DOOR MAG STRIP READER & CLASS PIN/PAD - BLDG. 192 RM 333 | 192 | CLOSED | 128.112 | 0 | 141.288 | 141.288
PJ0005065 | INSTALL DOOR MAG STRIP READER & CLASS PIN/PAD - BLDG. 192 RM 333 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-09-05 | LO: INSTALL ELECTRIC STRIKE | 192 | CLOSED | 882.108 | 0 | 639.18 | 639.18
PJ0005065 Total | [7 empty] | 7833.39 | 0 | 6852.718 | 6852.718
PJ0005063 | INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GONZALES, ALBERT | CLOSED | 2014-10-06 | CA: INSTALL BOLLARDS AT ENGINEERING PLAZA | GENERAL | CLOSED | 8494.6968 | 0 | 5099.1126 | 5099.1126
PJ0005063 | INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GONZALES, ALBERT | CLOSED | 2014-10-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 990.32 | 0 | 0 | 0
PJ0005063 | INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GONZALES, ALBERT | CLOSED | 2014-10-06 | EL: LOCATE UTILITIES AT BONDERSON PLAZA | GENERAL | CLOSED | 143.6744 | 0 | 70.872 | 70.872
PJ0005063 | INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GONZALES, ALBERT | CLOSED | 2014-10-06 | IN: INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GENERAL | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0005063 | INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GONZALES, ALBERT | CLOSED | 2014-10-06 | LO: SUPPLY PADLOCKS FOR BOLLARDS (NO LABOR) | GENERAL | CLOSED | 157.6256 | 0 | 75 | 75
PJ0005063 | INSTALL REMOVABLE BOLLARDS - ENGINEERING PLAZA | GONZALES, ALBERT | CLOSED | 2014-10-06 | PL: LOCATE UTILITIES FOR BOLLARD INSTALL | GENERAL | CLOSED | 143.8082 | 0 | 368.028 | 368.028
PJ0005063 Total | [7 empty] | 10212.7011 | 0 | 5683.6566 | 5683.6566
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: ITS (DEPT FUNDING) | 150F | CLOSED | 0 | 0 | 4143.17 | 4143.17
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: JOC 14.034.004 MAINO | 150F | CLOSED | 192560.63 | 0 | 188852.79 | 188852.79
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: JOC 15.035.005 MAINO | 150F | CLOSED | 11180.01 | 0 | 11180.01 | 11180.01
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: JOC MAINO 14.033.034 | 150F | CLOSED | 43548.36 | 0 | 43548.36 | 43548.36
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: MAINO (LOW-VALUE PUBLIC WORKS) | 150F | CLOSED | 1725 | 0 | 1725 | 1725
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: PMSM ARCHITECTS | 150F | CLOSED | 16500 | 0 | 14400 | 14400
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | AD: STATE FIRE MARSHAL | 150F | CLOSED | 0 | 0 | 163.21 | 163.21
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | CP: PROJECT CONTINGENCY | 150F | CLOSED | 18469.87 | 0 | 0 | 0
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | EL: SAFE OFF POWER AND INSTALL ELECTRICAL TO THE (N) CAGES | 150F | CLOSED | 35386.1821 | 0 | 94897.9969 | 94897.9969
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | IN: (FPCP FUNDING) INSULATION & INSTALL SLAT FLOOR -BLDG 150F | 150F | CLOSED | 0 | 0 | 565.152 | 565.152
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | LO: REPAIR LOCK AND LATCH AS NEEDED | 150F | CLOSED | 101.54 | 0 | 232.31 | 232.31
PJ0005062 | RENOVATE POULTRY CAGES (OPPENHEIMER) - BLDG 150F | LAMPMAN, GREG | CLOSED | 2014-10-07 | PA: PAINTING FOR CAGE RENO AT BLDG 150F | 150F | CLOSED | 16977.7194 | 0 | 8966.1449 | 8966.1449
PJ0005062 Total | [7 empty] | 336449.3115 | 0 | 368674.1438 | 368674.1438
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | AD: BKM (FOUNDATION FUNDING) | GENERAL | CLOSED | 9669.3546 | 0 | 9565.8321 | 9565.8321
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | AD: FLOOR CONNECTION (FOUNDATION FUNDING) | GENERAL | CLOSED | 1744.1 | 0 | 1744.1 | 1744.1
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | AD: PROCARD PURCHASES | GENERAL | CLOSED | 0 | 0 | 280.3186 | 280.3186
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | AD: STATE FIRE MARSHAL FEES | GENERAL | CLOSED | 481.5 | 0 | 412.7632 | 412.7632
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | CA:FABRICATE AND INSTALL NEW LACTATION ROOM SIGNS | GENERAL | CLOSED | 1408.02 | 0 | 2138.6124 | 2138.6124
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 16.33 | 0 | 0 | 0
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | CP: PROJECT CONTINGENCY FOR CO1 (FOUNDATION FUNDING) | GENERAL | CLOSED | 1148.45 | 0 | 0 | 0
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | CU:STEAM CLEAN 4 CHAIRS IN BLDG 70, ROOM 110 | GENERAL | CLOSED | 193.968 | 0 | 189.384 | 189.384
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | EL:REPLACE EXISTING HARSH LIGHTING WITH NEW AMBIENT LIGHTING | GENERAL | CLOSED | 2334.1673 | 0 | 816.402 | 816.402
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | IN: LACTATION ROOM UPGRADE - CAMPUSWIDE (SPLIT FUNDING) | GENERAL | CLOSED | 282.576 | 0 | 105.966 | 105.966
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | LO: SUPPLY AND INSTALL NEW LOCKSETS FOR LACTATION ROOMS | GENERAL | CLOSED | 3813.3354 | 0 | 4075.062 | 4075.062
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | MO:MOVE FURNITURE AS NEEDED FROM VARIOUS ROOMS | GENERAL | CLOSED | 201.096 | 0 | 54 | 54
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | PA:PAINT ROOMS- BLD 33-233A, 14-241B, 3-334 ADD 35-311 | GENERAL | CLOSED | 1042.896 | 0 | 1670.784 | 1670.784
PJ0005060 | LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | MOLLAN, CHERYL L. | CLOSED | 2014-10-01 | PM: LACTATION ROOM UPGRADE - BUILDINGS 03, 14, 33, & 35 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005060 Total | [7 empty] | 22335.7933 | 0 | 21053.2243 | 21053.2243
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 003 | 003 | CLOSED | 0 | 0 | 213.328 | 213.328
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 004 | 004 | CLOSED | 0 | 0 | 267.57 | 267.57
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 005 | 005 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 006 | 006 | CLOSED | 0 | 0 | 134.513 | 134.513
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 007 | 007 | CLOSED | 0 | 0 | 53.69 | 53.69
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 008 | 008 | CLOSED | 0 | 0 | 107.38 | 107.38
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 013 | 013 | CLOSED | 0 | 0 | 53.69 | 53.69
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 018/018B | 018 | CLOSED | 0 | 0 | 104.516 | 104.516
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 019 (N/L) | 019 | CLOSED | 0 | 0 | 0 | 0
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 021 | 021 | CLOSED | 0 | 0 | 107.38 | 107.38
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 026 | 026 | CLOSED | 0 | 0 | 53.69 | 53.69
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 027 | 027 | CLOSED | 0 | 0 | 518.2108 | 518.2108
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 033 | 033 | CLOSED | 0 | 0 | 134.225 | 134.225
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 034 | 034 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 035 | 035 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 038 | 038 | CLOSED | 0 | 0 | 161.07 | 161.07
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 040 | 040 | CLOSED | 0 | 0 | 26.845 | 26.845
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 042 | 042 | CLOSED | 0 | 0 | 160.16 | 160.16
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 043 | 043 | CLOSED | 0 | 0 | 128.856 | 128.856
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 044 | 044 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 045 | 045 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 047 | 047 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 052 | 052 | CLOSED | 0 | 0 | 26.845 | 26.845
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 061 | 061 | CLOSED | 0 | 0 | 236.4798 | 236.4798
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 080 | 080 | CLOSED | 0 | 0 | 80.535 | 80.535
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 106 | 106 | CLOSED | 0 | 0 | 384.1414 | 384.1414
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 108 | 108 | CLOSED | 0 | 0 | 295.583 | 295.583
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 109 | 109 | CLOSED | 0 | 0 | 306.4938 | 306.4938
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 114 | 114 | CLOSED | 0 | 0 | 1607.195 | 1607.195
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 115 | 115 | CLOSED | 0 | 0 | 53.69 | 53.69
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 116 | 116 | CLOSED | 0 | 0 | 53.69 | 53.69
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 117T | 117T | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 124 | 124 | CLOSED | 0 | 0 | 53.69 | 53.69
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 133 | 133 | CLOSED | 0 | 0 | 32.214 | 32.214
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 150 | 150 | CLOSED | 0 | 0 | 214.76 | 214.76
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 154 | 154 | CLOSED | 0 | 0 | 215.048 | 215.048
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 155 | 155 | CLOSED | 0 | 0 | 26.845 | 26.845
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 170A | 170A | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 170C | 170C | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 170D | 170D | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 170G | 170G | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171A | 171A | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171B | 171B | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171C | 171C | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171E | 171E | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171F | 171F | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171G | 171G | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 171I | 171I | CLOSED | 0 | 0 | 28.09 | 28.09
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - BLDG. 192 | 192 | CLOSED | 0 | 0 | 26.845 | 26.845
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - CAMPUS MARKET 024 | 024 | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0005059 | 2014 FIRE ALARM TESTING - SYSTEM REPAIRS - CAMPUS WIDE (MAINT) | POLVI, STEVEN | CLOSED | 2014-09-29 | EL: FIRE ALARMS TESTING - CORRECTIVE ACTIONS - SAFETY WHSE. 074 | 074 | CLOSED | 0 | 0 | 26.845 | 26.845
PJ0005059 Total | [7 empty] | 0 | 0 | 6787.0798 | 6787.0798
PJ0005058 | INSTALL HORSE WALKER - EQUINE CENTER 32 | DILLON, JEFFREY | CLOSED | 2014-09-09 | AD: PROJECT COORDINATION FEE | 032 | CLOSED | 535 | 0 | 535 | 535
PJ0005058 | INSTALL HORSE WALKER - EQUINE CENTER 32 | DILLON, JEFFREY | CLOSED | 2014-09-09 | CP: PROJECT CONTINGENCY | 032 | CLOSED | 394.18 | 0 | 0 | 0
PJ0005058 | INSTALL HORSE WALKER - EQUINE CENTER 32 | DILLON, JEFFREY | CLOSED | 2014-09-09 | EL: ROUGH AND FINISH | 032 | CLOSED | 3194.2811 | 0 | 2171.838 | 2171.838
PJ0005058 | INSTALL HORSE WALKER - EQUINE CENTER 32 | DILLON, JEFFREY | CLOSED | 2014-09-09 | IN: PJ5058 INSTALL HORSE WALKER - EQUINE CENTER 32 | 032 | CLOSED | 211.932 | 0 | 105.966 | 105.966
PJ0005058 Total | [7 empty] | 4335.3931 | 0 | 2812.804 | 2812.804
PJ0005055 | SP 14/15: UPGRADE SIEMENS EMS - CAMPUS WIDE | ELLIOT, DENNIS K | CONST_COMP | 2014-09-23 | AD: SIEMENS INDUSTRY | GENERAL | CLOSED | 0 | 0 | 1014360 | 1014360
PJ0005055 | SP 14/15: UPGRADE SIEMENS EMS - CAMPUS WIDE | ELLIOT, DENNIS K | CONST_COMP | 2014-09-23 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 1115075 | 0 | 0 | 0
PJ0005055 | SP 14/15: UPGRADE SIEMENS EMS - CAMPUS WIDE | ELLIOT, DENNIS K | CONST_COMP | 2014-09-23 | ES: SUPPORT FOR SIEMENS EMS PANEL UPGRADE - CAMPUS WIDE | GENERAL | CLOSED | 0 | 0 | 7767.63 | 7767.63
PJ0005055 | SP 14/15: UPGRADE SIEMENS EMS - CAMPUS WIDE | ELLIOT, DENNIS K | CONST_COMP | 2014-09-23 | ITS: INSTALL ETHERNET PORTS FOR SIEMENS EMS PANEL UPGRADES | GENERAL | CLOSED | 0 | 0 | 68219.1875 | 68219.1875
PJ0005055 | SP 14/15: UPGRADE SIEMENS EMS - CAMPUS WIDE | ELLIOT, DENNIS K | CONST_COMP | 2014-09-23 | SM: SP 14/15: UPGRADE SIEMENS EMS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005055 Total | [7 empty] | 1115075 | 0 | 1090346.8175 | 1090346.8175
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: AL'S SEPTIC | 075 | OPEN | 0 | 0 | 401.25 | 401.25
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: ASAP REPROGRAPHICS | 075 | OPEN | 0 | 0 | 746.95 | 746.95
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: BUILDING POINT PACIFIC | 075 | OPEN | 2000 | 800 | 1200 | 2000
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: CONSTRUCTION (CAL ELECTRO) | 075 | OPEN | 1402636 | 25406.35 | 1241703.5 | 1267109.85
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: DEPT OF GEN. SRVCS. CA CONTRACTS REGISTER | 075 | OPEN | 50 | 0 | 0 | 0
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: DODGE DATA & ANALYTICS | 075 | OPEN | 3250 | 0 | 0 | 0
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: DRAKE FARMS TRUCKING | 075 | OPEN | 0 | 250 | 750 | 1000
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: EARTH SYSTEMS PACIFIC | 075 | OPEN | 1587.4 | 9517.7 | 2319.7 | 11837.4
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: ENGLEKIRK & SABOL | 075 | OPEN | 4387 | 500 | 3887 | 4387
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: ITEC - PURCHASE TRANSFORMERS TO BE INSTALLED BY CONTRACTOR | 075 | OPEN | 25679.6 | 0 | 26292.74 | 26292.74
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: M6 CONSULTING | 075 | OPEN | 4520 | 0 | 4556.4 | 4556.4
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: MCKENNA | 075 | OPEN | 0 | 0 | 400 | 400
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: NORTH COAST ENGINEERING | 075 | OPEN | 13900 | 13116.66 | 783.34 | 13900
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: P2S ENGINEER | 075 | OPEN | 2000 | 0 | 2000 | 2000
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: PG&E | 075 | OPEN | 35000 | 0 | 15000 | 15000
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: POWER ENGINEERING SYSTEMS, INC. | 075 | OPEN | 134100 | 0 | 135100 | 135100
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: REPUBLIC ELEVATOR - POWER OUTAGE STAND-BY ON AUG. 20, 2016 | 075 | OPEN | 0 | 0 | 1156 | 1156
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: TELEGRAM TRIBUNE, SLO COUNTY NEWSPAPERS | 075 | OPEN | 750 | 0 | 0 | 0
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: THE SIGN PLACE | 075 | OPEN | 115.57 | 0 | 115.57 | 115.57
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | AD: TRIMBLE NAVIGATION | 075 | OPEN | 0 | 0 | 6722.33 | 6722.33
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | CP: PROJECT CONTINGENCY | 075 | OPEN | 87512.77 | 0 | 0 | 0
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | CPE: SUPPORT MUSTANG TRANSFORMER POWER OUTAGE - AUG. 20, 2016 | 075 | ASSIGNED | 0 | 0 | 3955.202 | 3955.202
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | EL: SUPPORT FOR NEW TRANSFORMER AT MUSTANG SUBSTATION | 075 | CLOSED | 8546.3263 | 0 | 4742.832 | 4742.832
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | EL: SUPPORT MUSTANG TRANSFORMER POWER OUTAGE - AUG. 20, 2016 | 075 | CLOSED | 7503.1085 | 0 | 22759.512 | 22759.512
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | ES: SUPPORT MUSTANG TRANSFORMER POWER OUTAGE - AUG. 20, 2016 | 075 | CLOSED | 0 | 0 | 4942.737 | 4942.737
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | IN: SP 14/15: NEW TRANSFORMER - BLDG. 75 | 075 | CLOSED | 10248.96 | 0 | 32.028 | 32.028
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | LA: | 075 | CLOSED | 160.128 | 0 | 40.032 | 40.032
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | LO: PROVIDE PADLOCKS FOR MUSTANG SUBSTATION PROJECT | 075 | CLOSED | 0 | 0 | 373.386 | 373.386
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | PL: SUPPORT MUSTANG TRANSFORMER POWER OUTAGE - AUG. 20, 2016 | 075 | CLOSED | 0 | 0 | 1586.184 | 1586.184
PJ0005054 | SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | SODERIN, ERIC | CONST_COMP | 2014-09-23 | SM: SP 14/15: NEW TRANSFORMER AT SUBSTATION - BLG 75 | 075 | OPEN | 0 | 0 | 0 | 0
PJ0005054 Total | [7 empty] | 1743946.8628 | 49590.71 | 1481566.693 | 1531157.403
PJ0005053 | FORKLIFT DAMAGE TO RESTROOM DOOR IN WAREHOUSE - BLDG 82 | POLVI, STEVEN | CLOSED | 2014-09-22 | CA: REPAIR DOOR AND WALL DAMAGED BY FORKLIFT - CORP. WHSE. | 082 | CLOSED | 800.7798 | 0 | 348.228 | 348.228
PJ0005053 | FORKLIFT DAMAGE TO RESTROOM DOOR IN WAREHOUSE - BLDG 82 | POLVI, STEVEN | CLOSED | 2014-09-22 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 138.95 | 0 | 0 | 0
PJ0005053 | FORKLIFT DAMAGE TO RESTROOM DOOR IN WAREHOUSE - BLDG 82 | POLVI, STEVEN | CLOSED | 2014-09-22 | PA: REPAINT WALL DAMAGED BY FORKLIFT - CORP. WHSE. | 082 | CLOSED | 588.3396 | 0 | 148.41 | 148.41
PJ0005053 Total | [7 empty] | 1528.0694 | 0 | 496.638 | 496.638
PJ0005050 | WINDOW TINTING - BLDG. 03 RM. 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-09-15 | AD: ATD WINDOW TINTING | 003 | CLOSED | 1136.34 | 0 | 1136.34 | 1136.34
PJ0005050 | WINDOW TINTING - BLDG. 03 RM. 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-09-15 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 113.63 | 0 | 0 | 0
PJ0005050 Total | [7 empty] | 1249.97 | 0 | 1136.34 | 1136.34
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | AD: JL FASULO | 014 | CLOSED | 2270.54 | 0 | 2270.54 | 2270.54
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | AD: MEATHEAD MOVERS | 014 | CLOSED | 684.8 | 0 | 547.84 | 547.84
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | AD: PARC ENVIRONMENTAL | 014 | CLOSED | 3012.05 | 0 | 3012.05 | 3012.05
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | AD: VISALIA TILE | 014 | CLOSED | 2120.74 | 0 | 2120.74 | 2120.74
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | CA:CAULKING FLR. PEN., WALL DEMO, LEAD ABATEMENT | 014 | CLOSED | 6485.289 | 0 | 5298.5152 | 5298.5152
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 1289.76 | 0 | 0 | 0
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | IN: SR 14/15: DSGN WATER DMG PREVENTION - BLDG 14 RMS 241 & 243 | 014 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | LO:CHANGE LOCK CORE ROOM 240, BLDG. 14 | 014 | CLOSED | 60.924 | 0 | 30.462 | 30.462
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | PA:PAINT TO MATCH, WALLS IN 2 ROOMS | 014 | CLOSED | 1126.4718 | 0 | 257.95 | 257.95
PJ0005049 | SR 14/15: DESIGN WATER DAMAGE PREVENTION - BLDG 14 RMS 241 & 243 | DILLON, JEFFREY | CLOSED | 2014-09-18 | PL:REPLUMB URINAL WALL | 014 | CLOSED | 5195.0839 | 0 | 4629.3907 | 4629.3907
PJ0005049 Total | [7 empty] | 22386.9467 | 0 | 18308.7759 | 18308.7759
PJ0005048 | UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | LAMPMAN, GREG | CLOSED | 2014-09-08 | AD: ELECTRICRAFT | 018A | CLOSED | 3593.06 | 0 | 3593.06 | 3593.06
PJ0005048 | UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | LAMPMAN, GREG | CLOSED | 2014-09-08 | AD: WLH CONSTRUCTION | 018A | CLOSED | 4183.7 | 0 | 4183.7 | 4183.7
PJ0005048 | UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | LAMPMAN, GREG | CLOSED | 2014-09-08 | CP: PROJECT CONTINGENCY | 018A | CLOSED | 1980 | 0 | 0 | 0
PJ0005048 | UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | LAMPMAN, GREG | CLOSED | 2014-09-08 | EL: INSTALL ELECTRICAL FOR SMART ROOM EQUIPMENT | 018A | CLOSED | 2894.2811 | 0 | 1776.312 | 1776.312
PJ0005048 | UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | LAMPMAN, GREG | CLOSED | 2014-09-08 | IN: UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | 018A | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0005048 | UPGRADE CLASSROOM TO SMART ROOM - DPTC - BLDG. 18A RM. 111C | LAMPMAN, GREG | CLOSED | 2014-09-08 | ITS: | 018A | CLOSED | 2930.46 | 0 | 4820 | 4820
PJ0005048 Total | [7 empty] | 15722.7891 | 0 | 14443.716 | 14443.716
PJ0005046 | CLEAN-UP AND MODIFICATIONS FOR MAIL ROOM - BLDG 70 | POLVI, STEVEN | CLOSED | 2014-09-08 | AD: PARC ENVIRONMENTAL | 070 | CLOSED | 18083 | 0 | 10272 | 10272
PJ0005046 | CLEAN-UP AND MODIFICATIONS FOR MAIL ROOM - BLDG 70 | POLVI, STEVEN | CLOSED | 2014-09-08 | CA:REPLACE EXISTING DOORS WITH WALL IN TWO LOCATIONS | 070 | CLOSED | 1506.1235 | 0 | 1979.418 | 1979.418
PJ0005046 | CLEAN-UP AND MODIFICATIONS FOR MAIL ROOM - BLDG 70 | POLVI, STEVEN | CLOSED | 2014-09-08 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 2193.55 | 0 | 0 | 0
PJ0005046 | CLEAN-UP AND MODIFICATIONS FOR MAIL ROOM - BLDG 70 | POLVI, STEVEN | CLOSED | 2014-09-08 | IN: CLEAN-UP AND MODIFICATIONS FOR MAIL ROOM - BLDG 70 | 070 | CLOSED | 142.8449 | 0 | 192.168 | 192.168
PJ0005046 | CLEAN-UP AND MODIFICATIONS FOR MAIL ROOM - BLDG 70 | POLVI, STEVEN | CLOSED | 2014-09-08 | PA: PAINT TWO WALLS | 070 | CLOSED | 1825.6124 | 0 | 1127.916 | 1127.916
PJ0005046 Total | [7 empty] | 23751.1308 | 0 | 13571.502 | 13571.502
PJ0005045 | ESTM: REMOVE MODULAR HOUSE AT ARCH VILLAGE - BLD 95B | BRENNAN, MICHAEL | CLOSED | 2014-09-09 | CP: PROJECT CONTINGENCY | 095B | CLOSED | 0 | 0 | 0 | 0
PJ0005045 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0005044 | DEMOLISH CARPORT-LIKE STRUCTURE BETWEEN BLDGS. 04A & 04R | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | AD: BOWEN ENGINEERING & ENVIRONMENTAL | 004 | CLOSED | 4140.9 | 0 | 4140.9 | 4140.9
PJ0005044 | DEMOLISH CARPORT-LIKE STRUCTURE BETWEEN BLDGS. 04A & 04R | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 414.09 | 0 | 0 | 0
PJ0005044 Total | [7 empty] | 4554.99 | 0 | 4140.9 | 4140.9
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: BOWEN ENVIRONMENTAL | 038 | CLOSED | 3859.49 | 0 | 3859.49 | 3859.49
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: FASULO DRYWALL | 038 | CLOSED | 6253.08 | 0 | 6253.08 | 6253.08
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: FLOOR CONNECTION | 038 | CLOSED | 4699.8252 | 0 | 4699.8252 | 4699.8252
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: KI FURNITURE | 038 | CLOSED | 16518.5209 | 0 | 16595.3469 | 16595.3469
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: MAINO (LVPW) | 038 | CLOSED | 3724.67 | 0 | 3724.67 | 3724.67
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: MCKENNA ENVIRONMENTAL | 038 | CLOSED | 1435.94 | 0 | 1435.94 | 1435.94
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | AD: STATE FIRE MARSHAL | 038 | CLOSED | 428 | 0 | 1396.2109 | 1396.2109
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | CA:DISASSEMBLE OFFICE FURNITURE, BLDG 38, ROOM 154 | 038 | CLOSED | 124.0326 | 0 | 83.43 | 83.43
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 2873.87 | 0 | 0 | 0
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | EL:DISCONNECT EL FOR DEMO, INSTALL NEW FIXTURES BLDG 38, 154 | 038 | CLOSED | 2976.7763 | 0 | 5807.778 | 5807.778
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | IN: REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | 038 | CLOSED | 353.22 | 0 | 317.898 | 317.898
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | LO:SUPPLY AND INSTALL NEW LEVER HANDEL LOCKSET BLDG 38, RM 154 | 038 | CLOSED | 845.4862 | 0 | 674.028 | 674.028
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | MO:MOVE FURNITURE TO ESURPLUS BLDG 38, RM 154 | 038 | CLOSED | 201.096 | 0 | 73.242 | 73.242
PJ0005043 | REMOVE ONE WALL AND ADD ANOTHER - BLDG. 38 RM. 154 | MOLLAN, CHERYL L. | CLOSED | 2014-09-03 | PA:PAINT NEW SOFFIT AND WALL REPAIR, BLDG 38, RM 154 | 038 | CLOSED | 675.8323 | 0 | 1020.15 | 1020.15
PJ0005043 Total | [7 empty] | 44969.8395 | 0 | 45941.089 | 45941.089
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | CA: INSTALL AN ADA RAMP FOR ROLLER RINK BEHIND SIERRA MADRE. | GENERAL | CLOSED | 0 | 0 | 88.584 | 88.584
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | CA:INSTALL THE ADA RAMP AT REC CENTER 9/11 | 043 | CLOSED | 0 | 0 | 899.688 | 899.688
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | CU: SUPPORT FOR WOW RALLY AT SPANOS STADIUM-9/16 | GENERAL | CLOSED | 0 | 0 | 756.717 | 756.717
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | CU: SUPPORT FOR WOW WEEK 2014. | GENERAL | CLOSED | 0 | 0 | 72.984 | 72.984
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | EL: INSTALL ONE SPIDER BOX REC CTR MAIN GYM BEFORE MONDAY 9/15 | GENERAL | CLOSED | 0 | 0 | 217.464 | 217.464
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | EL: INSTALL TWO SPIDER BOXES AT O'NEILL LAWN - BEFORE 9/16 | GENERAL | CLOSED | 0 | 0 | 797.892 | 797.892
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | EL: MOVE SPIDER BOX TO NW CORNER OF DEXTER LAWN-9/15 | GENERAL | CLOSED | 0 | 0 | 101.124 | 101.124
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | LA: EVENT SUPPORT FOR WOW CONCERT - 9/19 | 163F | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | LA: LANDSCAPE SUPPORT FOR WOW EVENTS-9/15-9/20 | GENERAL | CLOSED | 0 | 0 | 175.338 | 175.338
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | LA: SUPPORT FOR WOW SHOWCASE - 9/21 | GENERAL | CLOSED | 0 | 0 | 227.7 | 227.7
PJ0005042 | SUPPORT FOR 2014 WEEK OF WELCOME. (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-09-02 | MC: DELIVER ADA RAMPS TO REC CENTER LOADING DOCK-9/11 | 043 | CLOSED | 0 | 0 | 72.432 | 72.432
PJ0005042 Total | [7 empty] | 0 | 0 | 3643.707 | 3643.707
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | CA: INSTALL CONCRETE PAD FOR NEW SWITCH | 006 | CLOSED | 3554.7294 | 0 | 2206.425 | 2206.425
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 9087.24 | 0 | 0 | 0
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | EL:INSTALL CONDUIT AND SWITCH | 006 | CLOSED | 85673.8576 | 0 | 88428.108 | 88428.108
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | EO: EXCAVATION FOR PAC SWITCH | 006 | CLOSED | 685.8162 | 0 | 3441.924 | 3441.924
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | IN: SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH GEAR - PAC 06 | 006 | CLOSED | 314.3658 | 0 | 141.288 | 141.288
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | LA: REMOVE AND REPLACE LANDSCAPING NEAR PAC SWITCH | 006 | CLOSED | 356.2848 | 0 | 101.2186 | 101.2186
PJ0005041 | SP 14/15: REPLACE 12KV DISTRIBUTION SWITCH - PAC 06 | POLVI, STEVEN | CLOSED | 2014-09-05 | PL: LOCATE UTILITIES IN AREA OF EXCAVATION | 006 | CLOSED | 286.9716 | 0 | 64.488 | 64.488
PJ0005041 Total | [7 empty] | 99959.2654 | 0 | 94383.4516 | 94383.4516
PJ0005039 | CLEAN AND SEAL TILE GROUT IN ALL RESTROOMS - PAC 06 | CANTU, MONICA M. | CLOSED | 2014-07-25 | AD: COASTAL JANITORIAL GROUT CLEANING | 006 | CLOSED | 2778.6723 | 0 | 2876.16 | 2876.16
PJ0005039 | CLEAN AND SEAL TILE GROUT IN ALL RESTROOMS - PAC 06 | CANTU, MONICA M. | CLOSED | 2014-07-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 277.87 | 0 | 0 | 0
PJ0005039 Total | [7 empty] | 3056.5423 | 0 | 2876.16 | 2876.16
PJ0005038 | CARPET REMOVAL AND ABATEMENT - BLDG. 113 - SIERRA MADRE TOWER 5 | BRENNAN, MICHAEL | CLOSED | 2014-08-22 | AD: JOC 13.031.035 MAINO | 113 | CLOSED | 18402.7374 | 0 | 18402.7374 | 18402.7374
PJ0005038 | CARPET REMOVAL AND ABATEMENT - BLDG. 113 - SIERRA MADRE TOWER 5 | BRENNAN, MICHAEL | CLOSED | 2014-08-22 | AD: MCKENNA ENVIRONMENTAL | 113 | CLOSED | 3413.3 | 0 | 3413.3 | 3413.3
PJ0005038 | CARPET REMOVAL AND ABATEMENT - BLDG. 113 - SIERRA MADRE TOWER 5 | BRENNAN, MICHAEL | CLOSED | 2014-08-22 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 2188.73 | 0 | 0 | 0
PJ0005038 | CARPET REMOVAL AND ABATEMENT - BLDG. 113 - SIERRA MADRE TOWER 5 | BRENNAN, MICHAEL | CLOSED | 2014-08-22 | IN: CARPET REMOVAL & ABATEMENT - BLDG 113 - SIERRA MADRE TOWER 5 | 113 | CLOSED | 71.1022 | 0 | 64.056 | 64.056
PJ0005038 Total | [7 empty] | 24075.8696 | 0 | 21880.0934 | 21880.0934
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | AD: DELL (EXTENDED SERVICE WARANTEE & HARD DRIVES FOR SERVER) | GENERAL | OPEN | 4244.7221 | 0 | 5461.3442 | 5461.3442
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | AD: ECOVOX | GENERAL | OPEN | 196247.9082 | 79262.1011 | 112799.3465 | 192061.4476
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | AD: PLC'S PLUS INTERNATIONAL | GENERAL | OPEN | 5350 | 0 | 0 | 0
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | AD: SIEMENS | GENERAL | OPEN | 10700 | 0 | 0 | 0
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | ANTS: | GENERAL | OPEN | 14400 | 0 | 0 | 0
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 18425.07 | 0 | 0 | 0
PJ0005036 | SP14/15: ENERGY INFORMATION SYSTEM | ELLIOT, DENNIS K | IN_CONSTR | 2014-08-29 | SM: SP14/15: ENERGY INFORMATION SYSTEM | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0005036 Total | [7 empty] | 249367.7003 | 79262.1011 | 118260.6907 | 197522.7918
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | AD: BKM | 026 | CLOSED | 1904.9103 | 0 | 1904.9103 | 1904.9103
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | AD: COASTAL JANITORIAL | 026 | CLOSED | 2329.39 | 0 | 2329.39 | 2329.39
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | AD: JOC 16.037.018 MAINO | 026 | CLOSED | 566457.1119 | 0 | 566457.1226 | 566457.1226
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | AD: LANDSBERG (BOXES) | 026 | CLOSED | 77.6499 | 0 | 137.4843 | 137.4843
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | AD: MCKENNA | 026 | CLOSED | 9310.07 | 0 | 5905.33 | 5905.33
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | CA:UNFASTEN CABS AND COUNTERS ROOMS 100K, J, N AND F, BLDG 26 | 026 | CLOSED | 910.527 | 0 | 668.466 | 668.466
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 25577.19 | 0 | 0 | 0
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | IN: INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | 026 | CLOSED | 0 | 0 | 211.932 | 211.932
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | LO: NEW HARDWARE AT EXTERIOR DOOR BLDG. 26 | 026 | CLOSED | 4672.2624 | 0 | 4605.472 | 4605.472
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | MO:MOVE ALL CABS, CASES ETC. FROM ROOMS 110 J, K, N AND F | 026 | CLOSED | 831.1968 | 0 | 304.236 | 304.236
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | PA:PAINT ROOM 110C, BLDG. 26 | 026 | CLOSED | 1538.16 | 0 | 726.543 | 726.543
PJ0005035 | INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | DILLON, JEFFREY | CLOSED | 2014-08-27 | PM: INFRASTRUCTURE IMPROVEMENTS AND HVAC UPGRADES | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005035 Total | [7 empty] | 613608.4683 | 0 | 583250.8862 | 583250.8862
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | AD: KI FURNITURE | 026 | CLOSED | 22755.9468 | 0 | 16885.67 | 16885.67
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | AD: MARCHESE CONSTRUCTION | 026 | CLOSED | 1230.5 | 0 | 1230.5 | 1230.5
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | AD: MORELAND THOMPSON INC | 026 | CLOSED | 765.05 | 0 | 765.05 | 765.05
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | AD: SANTA MARIA ACOUSTICAL | 026 | CLOSED | 5285.8 | 0 | 5285.8 | 5285.8
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | CA: CONVERT ROOM TO 40 SEAT CLASSROOM | 026 | CLOSED | 6890.772 | 0 | 5766.432 | 5766.432
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | EL: GRAPHIC ARTS ROOM 123 CLASSROOM UPGRADE | 026 | CLOSED | 6301.3663 | 0 | 6001.794 | 6001.794
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | ES: INSTALL REGISTERS IN DROP CEILING | 026 | CLOSED | 2175.936 | 0 | 1927.872 | 1927.872
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | IN: INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | 026 | CLOSED | 256.224 | 0 | 170.022 | 170.022
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | LO: CORE CHANGES FOR PROJECT SUPPORT | 026 | CLOSED | 798.2958 | 0 | 1423.692 | 1423.692
PJ0005034 | INCREASE CLASSROOM CAPACITY TO 40 OCCUPANTS - BLDG 26 RM 123 | GONZALES, ALBERT M. | CLOSED | 2014-08-27 | PA: GRAPHIC ARTS 26-123 | 026 | CLOSED | 1207.2728 | 0 | 3092.568 | 3092.568
PJ0005034 Total | [7 empty] | 47667.1638 | 0 | 42549.4 | 42549.4
PJ0005033 | REPLACE EXISTING LAB SINK WITH A LARGER MODEL - BLDG. 11 RM. 106 | LOOSLEY, SCOTT L. | CLOSED | 2014-07-16 | CA: ADA CABINET MODIFICATION FOR NEW SINK INSTALLATION | 011 | CLOSED | 5481.1878 | 0 | 3251.7576 | 3251.7576
PJ0005033 | REPLACE EXISTING LAB SINK WITH A LARGER MODEL - BLDG. 11 RM. 106 | LOOSLEY, SCOTT L. | CLOSED | 2014-07-16 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 115.2 | 0 | 0 | 0
PJ0005033 | REPLACE EXISTING LAB SINK WITH A LARGER MODEL - BLDG. 11 RM. 106 | LOOSLEY, SCOTT L. | CLOSED | 2014-07-16 | EL: MODIFY ELECTRICAL FOR NEW SINK AND COUNTER INSTALLATION | 011 | CLOSED | 346.7046 | 0 | 128.856 | 128.856
PJ0005033 | REPLACE EXISTING LAB SINK WITH A LARGER MODEL - BLDG. 11 RM. 106 | LOOSLEY, SCOTT L. | CLOSED | 2014-07-16 | IN: REPLACE EXISTING LAB SINK WITH LARGER MODEL 11-106 (MAINT) | 011 | CLOSED | 0 | 0 | 147.175 | 147.175
PJ0005033 | REPLACE EXISTING LAB SINK WITH A LARGER MODEL - BLDG. 11 RM. 106 | LOOSLEY, SCOTT L. | CLOSED | 2014-07-16 | PA: STAIN CABINET FOR NEW SINK - BLD. 11 RM. 106 | 011 | CLOSED | 802.896 | 0 | 390.276 | 390.276
PJ0005033 | REPLACE EXISTING LAB SINK WITH A LARGER MODEL - BLDG. 11 RM. 106 | LOOSLEY, SCOTT L. | CLOSED | 2014-07-16 | PL: INSTALL NEW SINK(S) IN MODIFIED CABINET FOR ADA COMPLIANCE | 011 | CLOSED | 3353.2543 | 0 | 5065.32 | 5065.32
PJ0005033 Total | [7 empty] | 10099.2427 | 0 | 8983.3846 | 8983.3846
PJ0005032 | M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 371 | NORTON, DAVE | CLOSED | 2014-08-22 | AD: TIM HAAHS | 371 | CLOSED | 9701.3262 | 0 | 9677.5187 | 9677.5187
PJ0005032 | M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 371 | NORTON, DAVE | CLOSED | 2014-08-22 | CP: PROJECT CONTINGENCY | 371 | CLOSED | 977.2 | 0 | 0 | 0
PJ0005032 | M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 371 | NORTON, DAVE | CLOSED | 2014-08-22 | IN: M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 371 | 371 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005032 Total | [7 empty] | 10749.1702 | 0 | 9748.1627 | 9748.1627
PJ0005030 | UPDATE ADMIN BLDG 4TH FLR HALLWAY DIRECTORY | MOLLAN, CHERYL L. | CLOSED | 2014-08-18 | CA:INSTALL NEW VERBIAGE FOR HALLWAY SIGN, ADMIN 4TH FLOOR | 001 | CLOSED | 1496.7798 | 0 | 1098.372 | 1098.372
PJ0005030 | UPDATE ADMIN BLDG 4TH FLR HALLWAY DIRECTORY | MOLLAN, CHERYL L. | CLOSED | 2014-08-18 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 79.06 | 0 | 0 | 0
PJ0005030 | UPDATE ADMIN BLDG 4TH FLR HALLWAY DIRECTORY | MOLLAN, CHERYL L. | CLOSED | 2014-08-18 | IN: UPDATE ADMIN BLDG 4TH FLR HALLWAY DIRECTORY | 001 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0005030 Total | [7 empty] | 1646.4838 | 0 | 1169.016 | 1169.016
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | AD: ATD WINDOW TINTING | 027 | CLOSED | 434.42 | 0 | 434.42 | 434.42
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | AD: FACILITIES PLANNING IN-HOUSE CONSTRUCTION DOCUMENTS | 027 | CLOSED | 1070 | 0 | 1070 | 1070
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | AD: J.L. FASULO DRYWALL | 027 | CLOSED | 8808.24 | 0 | 8808.24 | 8808.24
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | AD: MACDONALD COMPANY | 027 | CLOSED | 9006.9069 | 0 | 9006.9069 | 9006.9069
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | AD: SANTA MARIA ACOUSTICAL | 027 | CLOSED | 15943 | 0 | 15943 | 15943
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | AD: STATE FIRE MARSHAL | 027 | CLOSED | 0 | 0 | 1182.2216 | 1182.2216
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | CA:INSTALL EXIT SIGN- HEALTH CENTER PHARM OFFICE | 027 | CLOSED | 428.0652 | 0 | 832.434 | 832.434
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | CA:SUPPLY AND INSTALL COVEBASE, TV MOUNTS, FIRE EXTI, TV MOUNT | 027 | CLOSED | 1074.3 | 0 | 1039.854 | 1039.854
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1591.62 | 0 | 0 | 0
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | EL: BLDG 27 INSTALL NEW ELECTRICAL IN NEW PHARMACY LOBBY OFFICES | 027 | CLOSED | 18069.1333 | 0 | 15156.9516 | 15156.9516
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | ES:ADD DUCTWORK TO NEW OFFICES- BLDG 27, PHARMACY LOBBY | 027 | CLOSED | 3632.521 | 0 | 3530.2722 | 3530.2722
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | IN: CONVERT PHARMACY LOBBY TO TWO ADMINISTRATIVE OFFICES 27-173 | 027 | CLOSED | 282.576 | 0 | 423.864 | 423.864
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | LO:DOOR CLOSERS AND HARDWARE FOR NEW HC PHARMACY OFFICES | 027 | CLOSED | 3438.0841 | 0 | 1666.872 | 1666.872
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | PA:PAINT NEW OFFICES AND VARNISH NEW DOORS AT HC PHARMACY | 027 | CLOSED | 2217.24 | 0 | 1018.392 | 1018.392
PJ0005029 | CONVERT PHARMACY LOBBY INTO TWO ADMINISTRATIVE OFFICES 27-173 | MOLLAN, CHERYL L. | CLOSED | 2014-08-13 | PCV CA: REMOVE DOOR AND DELIVER TO PAINT SHOP, BLD 27-173 | 027 | CLOSED | 222.48 | 0 | 203.556 | 203.556
PJ0005029 Total | [7 empty] | 66218.5865 | 0 | 60316.9843 | 60316.9843
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | AD: RAYNE WATER CONDITIONING | 051 | CLOSED | 0 | 0 | 537.568 | 537.568
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | CA: REPAIR BROKEN DOOR HANDLE AND - 051 | 051 | CLOSED | 338.328 | 0 | 306.9 | 306.9
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | CA: REPAIR CHIP ON DINING ROOM TABLE - 051 | 051 | CLOSED | 0 | 0 | 169.164 | 169.164
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | CA: SAFETY ISSUES - BASEMENT STAIRS AT PRESIDENT'S RESIDENCE | 051 | CLOSED | 444.96 | 0 | 407.604 | 407.604
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | EL: INSTALL CHRISTMAS LIGHTS AT PRES. RESIDENCE BEFORE 12/1 | 051 | CLOSED | 0 | 0 | 1472.61 | 1472.61
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | EL: REMOVE CHRISTMAS LIGHTS AT PRESIDENT'S RESIDENCE. | 051 | CLOSED | 0 | 0 | 579.852 | 579.852
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | EL:INSTALL CHRISTMAS LIGHTS AT PRES. RESIDENCE BEFORE 12/1 (N/L) | 051 | CLOSED | 0 | 0 | 51.804 | 51.804
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | LA: HANG ORNAMENTS IN PITTOSPORUM TREE - 051 | 051 | CLOSED | 0 | 0 | 254.334 | 254.334
PJ0005028 | 14/15: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 | NORTON, DAVE | CLOSED | 2014-08-22 | PL: MODIFY SUMP PIT LID IN THE BASEMENT OF PRESIDENT'S RESIDENCE | 051 | CLOSED | 0 | 0 | 354.684 | 354.684
PJ0005028 Total | [7 empty] | 783.288 | 0 | 4134.52 | 4134.52
PJ0005027 | REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | AD: FISHER SCIENTIFIC | 197 | CLOSED | 8208.2589 | 0 | 7452.1006 | 7452.1006
PJ0005027 | REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 1271.29 | 0 | 0 | 0
PJ0005027 | REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | EL: DISCONNECT FUME HOOD 197-209 | 197 | CLOSED | 386.568 | 0 | 235.164 | 235.164
PJ0005027 | REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | ES: DISCONNECT FUME HOOD | 197 | CLOSED | 3033.4118 | 0 | 1336.368 | 1336.368
PJ0005027 | REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | IN: REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | 197 | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005027 | REPLACE FUME HOOD WITH BIO CULTURE HOOD - BLDG 197 RM 209 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-08 | PL: DISCONNECT FUME HOOD TO BE REMOVED | 197 | CLOSED | 377.952 | 0 | 385.572 | 385.572
PJ0005027 Total | [7 empty] | 13418.7687 | 0 | 9550.4926 | 9550.4926
PJ0005026 | REPLACE DOUBLE DOORS TO RESIDENCE CATERING KITCHEN - 51A | POLVI, STEVEN | CLOSED | 2014-08-11 | CA:REPLACE DOUBLE DOORS TO RESIDENCE CATERING KITCHEN - 51A | 051A | CLOSED | 1904.2703 | 0 | 2996.124 | 2996.124
PJ0005026 | REPLACE DOUBLE DOORS TO RESIDENCE CATERING KITCHEN - 51A | POLVI, STEVEN | CLOSED | 2014-08-11 | CP: PROJECT CONTINGENCY | 051A | CLOSED | 434.14 | 0 | 0 | 0
PJ0005026 | REPLACE DOUBLE DOORS TO RESIDENCE CATERING KITCHEN - 51A | POLVI, STEVEN | CLOSED | 2014-08-11 | LO:REPLACE HARDWARE ON DOUBLE DOORS - 51A | 051A | CLOSED | 1140.2958 | 0 | 1360.782 | 1360.782
PJ0005026 | REPLACE DOUBLE DOORS TO RESIDENCE CATERING KITCHEN - 51A | POLVI, STEVEN | CLOSED | 2014-08-11 | PA:PAINT NEW DOUBLE DOORS TO RESIDENCE KITCHEN - 51A | 051A | CLOSED | 1297.2728 | 0 | 771.732 | 771.732
PJ0005026 Total | [7 empty] | 4775.9789 | 0 | 5128.638 | 5128.638
PJ0005025 | REVIEW OPERATION OF MECHANICAL SYSTEM - UU STARBUCKS | BRENNAN, MICHAEL | CLOSED | 2014-08-08 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 228.22 | 0 | 0 | 0
PJ0005025 | REVIEW OPERATION OF MECHANICAL SYSTEM - UU STARBUCKS | BRENNAN, MICHAEL | CLOSED | 2014-08-08 | EL:SUPPORT REVIEW MECH SYS OPS - UU STARBUCKS | 065 | CLOSED | 600.0024 | 0 | 441.144 | 441.144
PJ0005025 | REVIEW OPERATION OF MECHANICAL SYSTEM - UU STARBUCKS | BRENNAN, MICHAEL | CLOSED | 2014-08-08 | IN: REVIEW OPERATION OF MECHANICAL SYSTEM - UU STARBUCKS | 065 | CLOSED | 570.0984 | 0 | 606.15 | 606.15
PJ0005025 Total | [7 empty] | 1398.3208 | 0 | 1047.294 | 1047.294
PJ0005024 | M&R PAC 15/16: 2015 WON FIREGUARD ELEV FIRE DOOR MAINT - PAC | POLVI, STEVEN | CLOSED | 2014-08-15 | AD: WONDOOR CORPORATION | 006 | CLOSED | 1000 | 0 | 810 | 810
PJ0005024 | M&R PAC 15/16: 2015 WON FIREGUARD ELEV FIRE DOOR MAINT - PAC | POLVI, STEVEN | CLOSED | 2014-08-15 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0005024 Total | [7 empty] | 1000 | 0 | 810 | 810
PJ0005023 | WASH 3RD FL WINDOWS & POWERWASH 1ST FL TILES & UPPER WALKWAY -03 | CANTU, MONICA M. | CLOSED | 2014-08-15 | AD: COASTAL JANITORIAL | 003 | CLOSED | 4312.1 | 0 | 4584.95 | 4584.95
PJ0005023 | WASH 3RD FL WINDOWS & POWERWASH 1ST FL TILES & UPPER WALKWAY -03 | CANTU, MONICA M. | CLOSED | 2014-08-15 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 431.21 | 0 | 0 | 0
PJ0005023 Total | [7 empty] | 4743.31 | 0 | 4584.95 | 4584.95
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | AD: FLOOR CONNECTION | 003 | CLOSED | 13615.75 | 0 | 13744.15 | 13744.15
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | AD: J.L. FASULO DRYWALL | 003 | CLOSED | 2889 | 0 | 3657.26 | 3657.26
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | CA: REMOVE CABINETS, WHITEBOARDS, DESK - BLG 3 DEAN'S OFFICE STE | 003 | CLOSED | 1123.7064 | 0 | 738.528 | 738.528
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 2621.57 | 0 | 0 | 0
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | EL: ELECTRICAL | 003 | CLOSED | 2055.5119 | 0 | 790.602 | 790.602
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | IN: REMODEL DEAN'S OFFICE - BUSINESS 03-455 | 003 | CLOSED | 206.9009 | 0 | 70.644 | 70.644
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | MO: MOVE FURNITURE | 003 | CLOSED | 793.152 | 0 | 39.438 | 39.438
PJ0005019 | REMODEL DEAN'S OFFICE - BUSINESS 03-455 | NORTON, DAVE | CLOSED | 2014-08-13 | PA: STRIP WALLCOVER & PAINT WALLS | 003 | CLOSED | 5133.7981 | 0 | 2433.612 | 2433.612
PJ0005019 Total | [7 empty] | 28439.3893 | 0 | 21474.234 | 21474.234
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | AD: API | 077 | CLOSED | 2740.0988 | 0 | 2305.0368 | 2305.0368
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | AD: STATE FIRE MARSHAL | 077 | OPEN | 0 | 0 | 1151.0418 | 1151.0418
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | CP: PROJECT CONTINGENCY | 077 | OPEN | 286.48 | 0 | 0 | 0
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | CPE: | 077 | OPEN | 262.656 | 0 | 0 | 0
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | EL: | 077 | OPEN | 515.424 | 0 | 0 | 0
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | IN: ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | 077 | ASSIGNED | 565.152 | 0 | 141.288 | 141.288
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | LO: INSTALL CORES ON MOBILE OFFICE AT RODEO ARENA | 077 | CLOSED | 121.848 | 0 | 60.924 | 60.924
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | PM: ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | 077 | OPEN | 0 | 0 | 0 | 0
PJ0005018 | ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | KUENTZEL, DOUGLAS A. | HOLD | 2014-08-11 | SM: ASSIST IN INSTALLING DONATED MOBILE OFFICE - RODEO GROUND | 077 | OPEN | 0 | 0 | 0 | 0
PJ0005018 Total | [7 empty] | 4491.6588 | 0 | 3658.2906 | 3658.2906
PJ0005016 | INSTALL MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | POPHAM, DONALD J. | CLOSED | 2014-07-31 | CA: REMOVE SHELVING & INSTALL FRP PANELLING - BLDG. 08A RM. 3B | 008A | CLOSED | 2618.9033 | 0 | 6052.6118 | 6052.6118
PJ0005016 | INSTALL MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | POPHAM, DONALD J. | CLOSED | 2014-07-31 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 180.13 | 0 | 0 | 0
PJ0005016 | INSTALL MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | POPHAM, DONALD J. | CLOSED | 2014-07-31 | IN: INSTALL MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | 008A | CLOSED | 192.168 | 0 | 64.056 | 64.056
PJ0005016 | INSTALL MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | POPHAM, DONALD J. | CLOSED | 2014-07-31 | PA: PAINTING FOR MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | 008A | CLOSED | 615.264 | 0 | 247.632 | 247.632
PJ0005016 | INSTALL MOP SINK AT 008A-3B (CUSTODIAL CLOSET) | POPHAM, DONALD J. | CLOSED | 2014-07-31 | PL: INSTALL MOP SINK AT 008A-3B | 008A | CLOSED | 5069.8234 | 0 | 3752.118 | 3752.118
PJ0005016 Total | [7 empty] | 8676.2886 | 0 | 10116.4178 | 10116.4178
PJ0005015 | SP 14/15: RE-CONNECT ELECTRICAL &HEATING AND REPAIR ROOF 58-109A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-11 | AD: QUAGLINO ROOFING | 058 | CLOSED | 5232.3 | 0 | 5232.3 | 5232.3
PJ0005015 | SP 14/15: RE-CONNECT ELECTRICAL &HEATING AND REPAIR ROOF 58-109A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-11 | AD: THOMA ELECTRIC | 058 | CLOSED | 2033 | 0 | 2033 | 2033
PJ0005015 | SP 14/15: RE-CONNECT ELECTRICAL &HEATING AND REPAIR ROOF 58-109A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-11 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 1424.08 | 0 | 0 | 0
PJ0005015 | SP 14/15: RE-CONNECT ELECTRICAL &HEATING AND REPAIR ROOF 58-109A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-11 | CPE: CONNECT VENTILATION TO ADJACENT SPACE HVAC SYSTEM | 058 | CLOSED | 1863.336 | 0 | 1492.068 | 1492.068
PJ0005015 | SP 14/15: RE-CONNECT ELECTRICAL &HEATING AND REPAIR ROOF 58-109A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-11 | EL: RESTORE ELECTRICAL SERVICE TO EXISTING | 058 | CLOSED | 4855.968 | 0 | 5576.826 | 5576.826
PJ0005015 | SP 14/15: RE-CONNECT ELECTRICAL &HEATING AND REPAIR ROOF 58-109A | KUENTZEL, DOUGLAS A. | CLOSED | 2014-08-11 | IN: SP 14/15: ASSESSMENT TO RE-CONNECT ELECTRICAL AND HEATING | 058 | CLOSED | 256.224 | 0 | 70.644 | 70.644
PJ0005015 Total | [7 empty] | 15664.908 | 0 | 14404.838 | 14404.838
PJ0005014 | INSTALL "ALL GENDER" RESTROOM SIGNS - VARIOUS BLDGS | MOLLAN, CHERYL L. | CLOSED | 2014-08-11 | AD: THE SIGN PLACE | GENERAL | CLOSED | 7402.2386 | 0 | 7402.2065 | 7402.2065
PJ0005014 | INSTALL "ALL GENDER" RESTROOM SIGNS - VARIOUS BLDGS | MOLLAN, CHERYL L. | CLOSED | 2014-08-11 | CA:INSTALL "ALL GENDER" RESTROOM SIGNAGE CAMPUSWIDE | GENERAL | CLOSED | 2081.1192 | 0 | 1928.844 | 1928.844
PJ0005014 | INSTALL "ALL GENDER" RESTROOM SIGNS - VARIOUS BLDGS | MOLLAN, CHERYL L. | CLOSED | 2014-08-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 522.49 | 0 | 0 | 0
PJ0005014 | INSTALL "ALL GENDER" RESTROOM SIGNS - VARIOUS BLDGS | MOLLAN, CHERYL L. | CLOSED | 2014-08-11 | IN: INSTALL "ALL GENDER" RESTROOM SIGNS - VARIOUS BLDGS | GENERAL | CLOSED | 141.288 | 0 | 141.288 | 141.288
PJ0005014 | INSTALL "ALL GENDER" RESTROOM SIGNS - VARIOUS BLDGS | MOLLAN, CHERYL L. | CLOSED | 2014-08-11 | PA: PAINTING FOR "ALL GENDER" RESTROOM PROJECT | GENERAL | CLOSED | 679.08 | 0 | 593.285 | 593.285
PJ0005014 Total | [7 empty] | 10826.2158 | 0 | 10065.6235 | 10065.6235
PJ0005011 | SR 14/15: CHILDREN'S RESTROOM ADA COMPLIANCE - BLD 38 RR 125A | NORTON, DAVE | CLOSED | 2014-08-07 | CA: CARPENTRY | 038 | CLOSED | 2957.0501 | 0 | 3584.5902 | 3584.5902
PJ0005011 | SR 14/15: CHILDREN'S RESTROOM ADA COMPLIANCE - BLD 38 RR 125A | NORTON, DAVE | CLOSED | 2014-08-07 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 735.5 | 0 | 0 | 0
PJ0005011 | SR 14/15: CHILDREN'S RESTROOM ADA COMPLIANCE - BLD 38 RR 125A | NORTON, DAVE | CLOSED | 2014-08-07 | IN: CHILDREN'S RESTROOM ADA COMPLIANCE - BLD 38 RR 125A | 038 | CLOSED | 541.2732 | 0 | 304.722 | 304.722
PJ0005011 | SR 14/15: CHILDREN'S RESTROOM ADA COMPLIANCE - BLD 38 RR 125A | NORTON, DAVE | CLOSED | 2014-08-07 | PL: PLUMBING | 038 | CLOSED | 1989.0706 | 0 | 169.392 | 169.392
PJ0005011 Total | [7 empty] | 6222.8938 | 0 | 4058.7042 | 4058.7042
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: (SR FUNDING) JOC 15.035.010 MAINO | 045 | CLOSED | 87375.0658 | 0 | 87375.0658 | 87375.0658
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: (SR FUNDING) PMSM | 045 | CLOSED | 3103 | 0 | 700.85 | 700.85
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: (SR FUNDING) SPANOS & PAC MOVING COSTS | 045 | CLOSED | 1458.6775 | 0 | 2741.875 | 2741.875
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: ASAP REPROGRAPHICS DIRECT BUY | 045 | CLOSED | 0 | 0 | 657.2796 | 657.2796
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: CLASSROOM TECHNOLOGY | 045 | CLOSED | 5785.49 | 0 | 5786.0785 | 5786.0785
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: CONSTRUCTED SOLUTIONS | 045 | CLOSED | 12352.2833 | 0 | 12221.8717 | 12221.8717
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: ENGLEKIRK AND SABOL | 045 | CLOSED | 1658.5 | 0 | 1658.5 | 1658.5
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: FLOOR CONNECTION | 045 | CLOSED | 8054.96 | 0 | 8054.96 | 8054.96
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: IN-HOUSE PLAN CHECK | 045 | CLOSED | 1500 | 0 | 1500 | 1500
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: JOC 14.033.037 MAINO | 045 | CLOSED | 283624.9 | 0 | 279924.1766 | 279924.1766
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: JOC 15.035.010 MAINO | 045 | CLOSED | 24116.9333 | 0 | 24116.9333 | 24116.9333
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: MAINO (LVPW) | 045 | CLOSED | 3261.4242 | 0 | 3261.4242 | 3261.4242
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: MCKENNA | 045 | CLOSED | 2653.6 | 0 | 2653.6 | 2653.6
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: PMSM ARCHITECTS | 045 | CLOSED | 40660 | 0 | 39959.15 | 39959.15
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | AD: STATE FIRE MARSHAL | 045 | CLOSED | 0 | 0 | 1381.5305 | 1381.5305
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 3550.02 | 0 | 0 | 0
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | CU: ROOM CLEAN | 045 | CLOSED | 502.38 | 0 | 453.882 | 453.882
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 045 | CLOSED | 0 | 0 | 75.6 | 75.6
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | EL: ELECTRICAL SUPPORT | 045 | CLOSED | 717.0836 | 0 | 508.986 | 508.986
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | ES: HVAC SUPPORT 45-218 | 045 | CLOSED | 730.8403 | 0 | 499.098 | 499.098
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | IN: (SR FUNDING) RENOVATE CHOIR ROOM - BLD 45 RM 218 | 045 | CLOSED | 70.644 | 0 | 35.322 | 35.322
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | IN: RENOVATE ROOM - BLD 45 RM 218 | 045 | CLOSED | 576.504 | 0 | 1374.264 | 1374.264
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | IN: RENOVATE ROOM - BLD 45 RM 218 (USE WO0251577) | 045 | CLOSED | 0 | 0 | 70.644 | 70.644
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | LO: INSTALL ORANGE CORE | 045 | CLOSED | 135.8605 | 0 | 60.924 | 60.924
PJ0005010 | SR15/16 RENOVATE CHOIR ROOM - BLD 45 RM 218 | NORTON, DAVE | CLOSED | 2014-07-31 | PA: PAINT ROOM | 045 | CLOSED | 9467.1943 | 0 | 7163.696 | 7163.696
PJ0005010 Total | [7 empty] | 491355.3609 | 0 | 482235.7112 | 482235.7112
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | AD: FLOOR CONNECTION | 114 | CLOSED | 802.5 | 0 | 722.25 | 722.25
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | AD: J.L. FASULO DRYWALL | 114 | CLOSED | 2568 | 0 | 2607.59 | 2607.59
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | CA: CARPENTRY | 114 | CLOSED | 15568.5906 | 0 | 19667.3212 | 19667.3212
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 3553.27 | 0 | 0 | 0
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | EH&S: ASBESTOS SUPPORT | 114 | CLOSED | 1316.4158 | 0 | 917.832 | 917.832
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 114 | CLOSED | 0 | 0 | 254.4 | 254.4
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | EL: ELECTRICAL | 114 | CLOSED | 3493.145 | 0 | 3671.937 | 3671.937
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | ES: INSTALL VENTILLATOR | 114 | CLOSED | 6214.9094 | 0 | 4444.68 | 4444.68
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | IN: DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | 114 | CLOSED | 314.3658 | 0 | 635.796 | 635.796
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | LO: LOCKS - CSD OFFICE - YOSEMITE | 114 | CLOSED | 1778.7374 | 0 | 1127.604 | 1127.604
PJ0005009 | DIVIDE OFFICE INTO TWO OFFICE SPACES - YOSEMITE 114 - L202 | NORTON, DAVE | CLOSED | 2014-04-07 | PA: PAINT | 114 | CLOSED | 3475.5251 | 0 | 2600.136 | 2600.136
PJ0005009 Total | [7 empty] | 39085.4592 | 0 | 36649.5462 | 36649.5462
PJ0005008 | PLAYGROUND ENHANCEMENTS & INSIDE LOFT - PRE-SCHOOL LAB | MOLLAN, CHERYL L. | CLOSED | 2014-07-28 | AD: THE SIGN PLACE | 038 | CLOSED | 3184.32 | 0 | 3184.32 | 3184.32
PJ0005008 | PLAYGROUND ENHANCEMENTS & INSIDE LOFT - PRE-SCHOOL LAB | MOLLAN, CHERYL L. | CLOSED | 2014-07-28 | CA:INSTALL SEISMIC BRACING FOR LOFT, BLDG 38, ROOM 125 | 038 | CLOSED | 1285.1418 | 0 | 733.284 | 733.284
PJ0005008 | PLAYGROUND ENHANCEMENTS & INSIDE LOFT - PRE-SCHOOL LAB | MOLLAN, CHERYL L. | CLOSED | 2014-07-28 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 339.77 | 0 | 0 | 0
PJ0005008 | PLAYGROUND ENHANCEMENTS & INSIDE LOFT - PRE-SCHOOL LAB | MOLLAN, CHERYL L. | CLOSED | 2014-07-28 | IN: PLAYGROUND ENHANCEMENTS & INSIDE LOFT - PRE-SCHOOL LAB | 038 | CLOSED | 211.932 | 0 | 105.966 | 105.966
PJ0005008 Total | [7 empty] | 5021.1638 | 0 | 4023.57 | 4023.57
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | AD: JOC 13.030.046 MAINO | RESIDENCE | CLOSED | 205074.8411 | 0 | 205074.8411 | 205074.8411
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | AD: JOC 13.031.036 MAINO | RESIDENCE | CLOSED | 17695.4995 | 0 | 17695.4995 | 17695.4995
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 0 | 0 | 1553.3404 | 1553.3404
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 18554.37 | 0 | 0 | 0
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | CPE: AIR CONDITIONERS FOR TELECOM SHED UPS | RESIDENCE | CLOSED | 57062.9357 | 0 | 32717.97 | 32717.97
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | LO: INSTALL CORES AT TELECOM SHEDS AT RED BRICK DORMS | RESIDENCE | CLOSED | 1753.7636 | 0 | 3045.438 | 3045.438
PJ0005005 | TELECOM SHEDS FOR ALL 6 RED BRICK DORMS | HICKS, MICHAEL | CLOSED | 2014-07-29 | PA: PRIME DOORS & INTERIOR OF TELECOM SHEDS AT RED BRICK DORMS | RESIDENCE | CLOSED | 10688.9112 | 0 | 2841.924 | 2841.924
PJ0005005 Total | [7 empty] | 310830.3211 | 0 | 262929.013 | 262929.013
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: APC CONTRACTORS | 001 | CLOSED | 3531 | 0 | 3083.74 | 3083.74
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: D.A. CRAGHEAD | 001 | CLOSED | 6339.75 | 0 | 6724.95 | 6724.95
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: EC WEST | 001 | CLOSED | 7921.6166 | 0 | 8839.0453 | 8839.0453
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: FLOOR CONNECTION | 001 | CLOSED | 10486 | 0 | 10314.8 | 10314.8
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: GLASS DESIGNS BY MELISSA | 001 | CLOSED | 5387.236 | 0 | 5387.236 | 5387.236
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: IN-HOUSE DESIGN/PLAN | 001 | CLOSED | 1500 | 0 | 1500 | 1500
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: MACDONALD DOOR | 001 | CLOSED | 5457 | 0 | 5255.7223 | 5255.7223
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: PROJECT MANAGEMENT FEE FOR BKM OVERSIGHT | 001 | CLOSED | 2100 | 0 | 2100 | 2100
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | AD: QUARESMA DRYWALL | 001 | CLOSED | 10165 | 0 | 9886.8 | 9886.8
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | ANTS: PROGRAM ALARMS FOR VP SUITE REMODEL - 01 STE. 209 | 001 | CLOSED | 135.552 | 0 | 101.664 | 101.664
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | CA: REPAIR AND REINSTALL CABINETS - STORAGE RM. IN ADMIN 209 STE | 001 | CLOSED | 621.8532 | 0 | 1214.1 | 1214.1
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 2354.29 | 0 | 0 | 0
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | CU: CLEAN BLINDS FOR VP OFFICE REMODEL - ADMIN. STE. 209 | 001 | CLOSED | 365.0195 | 0 | 280.176 | 280.176
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | EH&S: ENV SUPOORT | 001 | CLOSED | 764.631 | 0 | 566.496 | 566.496
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | EL: ELECTRICAL | 001 | CLOSED | 6661.3663 | 0 | 6741.8422 | 6741.8422
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | ES: HVAC RELOCATION | 001 | CLOSED | 3584.738 | 0 | 2630.7292 | 2630.7292
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | IN: REMODEL VP FOR STUDENT AFFAIRS OFFICE STE ADMIN 209, 209A-F | 001 | CLOSED | 427.8941 | 0 | 131.406 | 131.406
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | LO: LOCKS | 001 | CLOSED | 2316.5916 | 0 | 2002.8 | 2002.8
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | MO: FURNITURE MOVING/SURPLUS | 001 | CLOSED | 721.224 | 0 | 283.692 | 283.692
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | PA: INTERIOR PAINTING | 001 | CLOSED | 3783.013 | 0 | 3221.628 | 3221.628
PJ0005004 | REMODEL VP FOR STUDENT AFFAIRS OFFICE SUITE, ADMIN 209, 209A-F | NORTON, DAVE | CLOSED | 2014-07-18 | RE: SUPPORT FOR VP OFFICE REMODEL | 001 | CLOSED | 0 | 0 | 287.856 | 287.856
PJ0005004 Total | [7 empty] | 74623.7753 | 0 | 70554.6829 | 70554.6829
PJ0005003 | MODIFY EXTERIOR BUILDING SIGNAGE - BLD 11 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-07-28 | AD: THE SIGN PLACE | 011 | CLOSED | 2367.375 | 0 | 2367.375 | 2367.375
PJ0005003 | MODIFY EXTERIOR BUILDING SIGNAGE - BLD 11 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-07-28 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 249.55 | 0 | 0 | 0
PJ0005003 | MODIFY EXTERIOR BUILDING SIGNAGE - BLD 11 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-07-28 | IN: MODIFY EXTERIOR BUILDING SIGNAGE - BLD 11 | 011 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0005003 Total | [7 empty] | 2745.037 | 0 | 2431.431 | 2431.431
PJ0005002 | SP 14/15: CAMPUS WIDE ROAD WORK | NORTON, DAVE | CLOSED | 2014-07-18 | AD: JOC 13.031.028 MAINO | GENERAL | CLOSED | 82926.8083 | 0 | 82926.8083 | 82926.8083
PJ0005002 | SP 14/15: CAMPUS WIDE ROAD WORK | NORTON, DAVE | CLOSED | 2014-07-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 8318.3 | 0 | 0 | 0
PJ0005002 | SP 14/15: CAMPUS WIDE ROAD WORK | NORTON, DAVE | CLOSED | 2014-07-18 | IN: SP 14/15: CAMPUS WIDE ROAD WORK | GENERAL | CLOSED | 256.224 | 0 | 224.196 | 224.196
PJ0005002 Total | [7 empty] | 91501.3323 | 0 | 83151.0043 | 83151.0043
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | AD: CAL POLY BUILDING PERMIT FEES | 208U | CLOSED | 600 | 0 | 600 | 600
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | AD: CAL POLY PLAN REVIEW FEES | 208U | CLOSED | 360 | 0 | 300 | 300
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | AD: ENGLEKIRK AND SABOL | 208U | CLOSED | 500 | 0 | 500 | 500
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | AD: ONTRAC SHIPPING | 208U | CLOSED | 0 | 0 | 44.99 | 44.99
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | AD: PROJECT COORDINATION FEES | 208U | CLOSED | 920 | 0 | 920 | 920
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | CP: PROJECT CONTINGENCY | 208U | CLOSED | 305.42 | 0 | 0 | 0
PJ0004999 | MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2014-07-16 | IN: (MAINT) MODIFY SPRINT CELL ANTENNA & EQUIPMENT - RADIO HILL | 208U | CLOSED | 0 | 0 | 53.38 | 53.38
PJ0004999 Total | [7 empty] | 2685.42 | 0 | 2418.37 | 2418.37
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | AD: ASAP REPROGRAPHICS | 045 | CLOSED | 0 | 0 | 130.5293 | 130.5293
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | AD: ENGLEKIRK AND SABOL | 045 | CLOSED | 535 | 0 | 535 | 535
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | AD: GOSS ENGINEERING | 045 | CLOSED | 3932.25 | 0 | 3167.2 | 3167.2
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | AD: STATE FIRE MARSHAL | 045 | CLOSED | 0 | 0 | 716.1617 | 716.1617
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 593.4 | 0 | 0 | 0
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | EL: INSTALL OUTLETS | 045 | CLOSED | 5349.186 | 0 | 2548.95 | 2548.95
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | IN: INSTALL A CENTRAL VACUUM SYSTEM: BLDG 045 RM. 206 | 045 | CLOSED | 155.4168 | 0 | 105.966 | 105.966
PJ0004998 | INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP - BLDG 045 RM. 206 | NORTON, DAVE | CLOSED | 2014-07-07 | PM: INSTALL CENTRAL VACUUM SYSTEM IN SCENE SHOP-BLDG 45 RM.206 | 045 | CLOSED | 0 | 0 | 0 | 0
PJ0004998 Total | [7 empty] | 10565.2528 | 0 | 7203.807 | 7203.807
PJ0004997 | SUPPORT FOR WOW CONCERT - SEPT. 19, 2014 FROM 3 TO 7 PM) | POPHAM, DONALD J. | CLOSED | 2014-07-14 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0004997 | SUPPORT FOR WOW CONCERT - SEPT. 19, 2014 FROM 3 TO 7 PM) | POPHAM, DONALD J. | CLOSED | 2014-07-14 | CU: SUPPORT FOR WOW CONCERT-9/19 | 163 | CLOSED | 0 | 0 | 103.326 | 103.326
PJ0004997 Total | [7 empty] | 0 | 0 | 103.326 | 103.326
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SPANOS THEATRE EVENT SUPPORT (EOP GRAD. RECEP.) | 044 | CLOSED | 0 | 0 | 42.36 | 42.36
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SPANOS THEATRE SUPPORT - 3/29 CRUCIBLE | 044 | CLOSED | 0 | 0 | 38.91 | 38.91
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SPANOS THEATRE SUPPORT - AHS CHORAL - 5/31 | 044 | CLOSED | 0 | 0 | 119.5797 | 119.5797
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SPANOS THEATRE SUPPORT - RHYTHMS CORE DANCE - 3/21 | 044 | CLOSED | 0 | 0 | 76.704 | 76.704
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SPANOS THEATRE SUPPORT FOR ALTAN - 3/28 | 044 | CLOSED | 0 | 0 | 40.29 | 40.29
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SPANOS THEATRE SUPPORT FOR STUDENT DANCE CONCERT - 5/21 | 044 | CLOSED | 0 | 0 | 37.53 | 37.53
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR "LET'S GET RAD" EVENT 12/13/14 | 044 | CLOSED | 0 | 0 | 114.18 | 114.18
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR BEAUTY & THE BEAST (SPANOS THEATRE) | 044 | CLOSED | 0 | 0 | 191.196 | 191.196
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR COMMENCEMENT 6/13/2015 | 044 | CLOSED | 0 | 0 | 38.358 | 38.358
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR FESTIVAL MOSAIC - 7/26 | 044 | CLOSED | 0 | 0 | 39.852 | 39.852
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR MERRY WIDOW - 4/11 | 044 | CLOSED | 0 | 0 | 74.37 | 74.37
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR REEL ROCK TOUR - 10/2 | 044 | CLOSED | 0 | 0 | 54.738 | 54.738
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SOAR JULY 14-16. | 044 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT (STUDIO @RYAN'S) | 044 | CLOSED | 0 | 0 | 75.405 | 75.405
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT - BLACK COMMEN. | 044 | CLOSED | 0 | 0 | 57.537 | 57.537
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT - THE OTHER SHORE | 044 | CLOSED | 0 | 0 | 40.2 | 40.2
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT - THE OTHER SHORE(3/8) | 044 | CLOSED | 0 | 0 | 147.084 | 147.084
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT- 11/22 | 044 | CLOSED | 0 | 0 | 39.852 | 39.852
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT-5/16 | 044 | CLOSED | 0 | 0 | 65.4375 | 65.4375
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT-LOS PUENTES | 044 | CLOSED | 0 | 0 | 77.82 | 77.82
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT FOR WOW EVENT AT SPANOS THEATRE-9/19 | 044 | CLOSED | 0 | 0 | 58.098 | 58.098
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT MISSOULA CHILDREN'S THEATRE EVENT-SPANOS THEATRE | 044 | CLOSED | 0 | 0 | 58.098 | 58.098
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT ORCHESIS DANCE PERFORMANCE - 1/24 | 044 | CLOSED | 0 | 0 | 107.28 | 107.28
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT SPANOS THEATRE EVENT - 3/11 | 044 | CLOSED | 0 | 0 | 36.84 | 36.84
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT SPANOS THEATRE EVENT - THE BOBS | 044 | CLOSED | 0 | 0 | 88.17 | 88.17
PJ0004996 | 14/15: SUPPORT FOR SPANOS THEATER EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-15 | CU: SUPPORT SPANOS THEATRE EVENT-JUST JAZZ 3/14 | 044 | CLOSED | 0 | 0 | 42.216 | 42.216
PJ0004996 Total | [7 empty] | 0 | 0 | 1860.4932 | 1860.4932
PJ0004995 | SIEMENS O&M SUPPORT WHILE POSITIONS VACANT - (SETC NOTIFICATION) | ELLIOT, DENNIS K | CLOSED | 2014-07-14 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004995 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0004994 | INSTALL A EV CHARGING STATION AT THE PRESIDENT'S RESIDENCE | GONZALES, ALBERT M. | CLOSED | 2014-07-10 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 317.3 | 0 | 0 | 0
PJ0004994 | INSTALL A EV CHARGING STATION AT THE PRESIDENT'S RESIDENCE | GONZALES, ALBERT M. | CLOSED | 2014-07-10 | EL: PRESIDENTS VEHICLE CHARGER | 051 | CLOSED | 1740.679 | 0 | 1537.254 | 1537.254
PJ0004994 | INSTALL A EV CHARGING STATION AT THE PRESIDENT'S RESIDENCE | GONZALES, ALBERT M. | CLOSED | 2014-07-10 | IN: INSTALL A EV CHARGING STATION AT THE PRESIDENT'S RESIDENCE | 051 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004994 Total | [7 empty] | 2314.203 | 0 | 1793.478 | 1793.478
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU. SUPPORT W. BBALL V. HAWAI'I - 1/8 | 042 | CLOSED | 0 | 0 | 227.88 | 227.88
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR W. BASKETBALL V. PEPPERDINE - 11/25 | 042 | CLOSED | 0 | 0 | 587.16 | 587.16
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. CSUN | 042 | CLOSED | 0 | 0 | 494.496 | 494.496
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. DARTMOUTH - 11/28 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. FULLERTON - 2/19 | 042 | CLOSED | 0 | 0 | 92.97 | 92.97
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. LOYOLA-11/21 | 042 | CLOSED | 0 | 0 | 108.315 | 108.315
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. TEXAS A&M -- 11/29 | 042 | CLOSED | 0 | 0 | 306.72 | 306.72
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. UC DAVIS - 1/29 | 042 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. BASKETBALL V. UCSB - 3/7 | 042 | CLOSED | 0 | 0 | 336.384 | 336.384
PJ0004991 | 14/15: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: W. BASKETBALL V. UC IRVINE - 1/31 | 042 | CLOSED | 0 | 0 | 261.36 | 261.36
PJ0004991 Total | [7 empty] | 0 | 0 | 2488.965 | 2488.965
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. CSU FULLERTON - 1/22 | 042 | CLOSED | 0 | 0 | 326.028 | 326.028
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. CSUN - 2/12 | 042 | CLOSED | 0 | 0 | 73.68 | 73.68
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. DELEWARE - 11/21 | 042 | CLOSED | 0 | 0 | 108.315 | 108.315
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. HAWAI'I - 2/5 | 042 | CLOSED | 0 | 0 | 110.52 | 110.52
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. UC DAVIS - 2/28 | 042 | CLOSED | 0 | 0 | 780.048 | 780.048
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. UC IRVINE - 2/26 | 042 | CLOSED | 0 | 0 | 110.52 | 110.52
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BASKETBALL V. UC RIVERSIDE - 1/24 | 042 | CLOSED | 0 | 0 | 471.096 | 471.096
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BBALL V. CSU LONG BEACH - 2/14 | 042 | CLOSED | 0 | 0 | 95.184 | 95.184
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. BBALL V. MENLO COLLEGE. - 12/7 | 042 | CLOSED | 0 | 0 | 185.136 | 185.136
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPROT M. BBALL V. UCSB - 1/10 | 042 | CLOSED | 0 | 0 | 311.9088 | 311.9088
PJ0004990 | 14/15: SUPPORT FOR MEN'S BASKETBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | MO: MOVE ADA MATS FROM BLDG. 81 TO AREA BEHIND MOTT GYM. | 042 | CLOSED | 0 | 0 | 72.432 | 72.432
PJ0004990 Total | [7 empty] | 0 | 0 | 2644.8678 | 2644.8678
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: STATE FIRE MARSHAL FEES - EVENT PERMIT FOR BAGGETT | 160 | CLOSED | 0 | 0 | 87.66 | 87.66
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: BASEBALL SEASON GAME SUPPORT - 2015 | 160 | CLOSED | 0 | 0 | 944.2965 | 944.2965
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. BAKERSFIELD - 2/24 @ 6PM | 160 | CLOSED | 0 | 0 | 380.304 | 380.304
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. CSULB (4/24-4/26) | 160 | CLOSED | 0 | 0 | 1431.612 | 1431.612
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. CSUN (5/1-5/3) | 160 | CLOSED | 0 | 0 | 1436.6937 | 1436.6937
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. FRESNO ST. - 4/14 @ 6PM | 160 | CLOSED | 0 | 0 | 451.692 | 451.692
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. GRAND CYN (2/20-2/22) | 160 | CLOSED | 0 | 0 | 2018.784 | 2018.784
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. HAWAI'I (4/10-4/12) | 160 | CLOSED | 0 | 0 | 1405.932 | 1405.932
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. PEPPERDINE - 4/7/15 @ 6PM | 160 | CLOSED | 0 | 0 | 543.096 | 543.096
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. SACRAMENTO ST. (3/12-3/15) | 160 | CLOSED | 0 | 0 | 2130.228 | 2130.228
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. SAN JOSE ST (5/5 @ 6PM) | 160 | CLOSED | 0 | 0 | 443.016 | 443.016
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. SANTA CLARA - 3/3 @6PM | 160 | CLOSED | 0 | 0 | 563.112 | 563.112
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. UC RIVERSIDE (5/15-5/17) | 160 | CLOSED | 0 | 0 | 1615.626 | 1615.626
PJ0004989 | 14/15: SUPPORT FOR BASEBALL (PROJECT). | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT BASEBALL V. USC/DARTMOUTH (3/20-3/23) | 160 | CLOSED | 0 | 0 | 2163.594 | 2163.594
PJ0004989 Total | [7 empty] | 0 | 0 | 15615.6462 | 15615.6462
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR SOFTBALL HOME GAMES (REGULAR SEASON)-2015 | 161 | CLOSED | 0 | 0 | 303.378 | 303.378
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: GROUND ESPNU TV TRUCK (IF NEEDED) SATURDAY MAY 2 | 161 | CLOSED | 0 | 0 | 70.872 | 70.872
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE- 10/24 | 161 | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE- 11/1 (ALUMNI) | 161 | CLOSED | 0 | 0 | 116.892 | 116.892
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE- 11/7 | 161 | CLOSED | 0 | 0 | 136.374 | 136.374
PJ0004988 | 14/15: SUPPORT FOR WOMEN'S SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR WOMEN'S SOFTBALL SPRING GAMES. | 161 | CLOSED | 0 | 0 | 10549.0074 | 10549.0074
PJ0004988 Total | [7 empty] | 0 | 0 | 11332.3794 | 11332.3794
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: CCI PORTABLE RENTALS FOR TAILGATING EVENT - 10/4 | GENERAL | CLOSED | 0 | 0 | 1154.744 | 1154.744
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: CCI PORTABLE TOILET RENTAL - 11/1 | GENERAL | CLOSED | 0 | 0 | 1243.982 | 1243.982
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: CCI PORTABLES RENTAL FOR TAILGATE-9/20 | GENERAL | CLOSED | 0 | 0 | 1114.084 | 1114.084
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: CCI RENTAL FOR 10/25 FOOTBALL GAME | GENERAL | CLOSED | 0 | 0 | 1153.888 | 1153.888
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: CCI TOILET RENTALS FOR TAILGATE EVENT- 11/15 | GENERAL | CLOSED | 0 | 0 | 1124.1848 | 1124.1848
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOOTBALL V. MONTANA - 10/25 | GENERAL | CLOSED | 0 | 0 | 475.8341 | 475.8341
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR FOOTBALL TAILGATE - 11/15 | GENERAL | CLOSED | 0 | 0 | 162.096 | 162.096
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT TAILGATE EVENT - 11/1 | GENERAL | CLOSED | 0 | 0 | 364.92 | 364.92
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | MC: SUPPORT FOR MUSTANG BBQ & TAILGATE- 10/4 | GENERAL | CLOSED | 0 | 0 | 20.16 | 20.16
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | MC: SUPPORT FOR TAILGATE/BBQ - 11/15 | GENERAL | CLOSED | 0 | 0 | 131.7 | 131.7
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 10/4 | GENERAL | CLOSED | 0 | 0 | 65 | 65
PJ0004987 | 14/15: SUPPORT FOR STAMPEDE CLUB EVENTS | POPHAM, DONALD J. | CLOSED | 2014-07-09 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 11/1/14 | GENERAL | CLOSED | 0 | 0 | 65 | 65
PJ0004987 Total | [7 empty] | 0 | 0 | 7075.5929 | 7075.5929
PJ0004986 | 14/15: SUPPORT FOR MEN'S WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004986 | 14/15: SUPPORT FOR MEN'S WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT WRESTLING V. WYOMING - 1/9 | 042 | CLOSED | 0 | 0 | 227.88 | 227.88
PJ0004986 Total | [7 empty] | 0 | 0 | 227.88 | 227.88
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR VOLLEYBALL - 9/19 | 042 | CLOSED | 0 | 0 | 295.764 | 295.764
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR VOLLEYBALL V. RIVERSIDE - 10/4 | 042 | CLOSED | 0 | 0 | 141.732 | 141.732
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR VOLLEYBALL V.SANTA CLARA - 9/20 | 042 | CLOSED | 0 | 0 | 427.314 | 427.314
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT VOLLEYBALL TOURNAMENT - 9/12 & 13 | 042 | CLOSED | 0 | 0 | 544.569 | 544.569
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT VOLLEYBALL V. CSUF - 11/8 | 042 | CLOSED | 0 | 0 | 234.774 | 234.774
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT VOLLEYBALL V. UCD-10/3 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. VOLLEYBALL V. CSULB - 10/18 | 042 | CLOSED | 0 | 0 | 458.796 | 458.796
PJ0004985 | 14/15: SUPPORT FOR WOMEN'S VOLLEYBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. VOLLEYBALL V. CSUN - 10/17 | 042 | CLOSED | 0 | 0 | 434.604 | 434.604
PJ0004985 Total | [7 empty] | 0 | 0 | 2537.553 | 2537.553
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: REMOVE CHAIR BACKS BEFORE SATURDAY 11/8/14 - SPANOS 061 #185 | 061 | CLOSED | 451.104 | 0 | 691.086 | 691.086
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR W. SOCCER - 9/19 | 061 | CLOSED | 0 | 0 | 370.092 | 370.092
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR W. SOCCER GAMES AT SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 224.835 | 224.835
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER TOURNAMENT- 11/6 & 11/9 | 061 | CLOSED | 0 | 0 | 1048.152 | 1048.152
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. CSUF - 10/11 | 061 | CLOSED | 0 | 0 | 694.08 | 694.08
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. FL. ATLANTIC - 8/31 | 061 | CLOSED | 0 | 0 | 286.926 | 286.926
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. FRESNO ST. - 9/19 | 061 | CLOSED | 0 | 0 | 97.176 | 97.176
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. HAWAI'I - 10/12 | 061 | CLOSED | 0 | 0 | 630.516 | 630.516
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. LAMAR-8/24 | 061 | CLOSED | 0 | 0 | 307.656 | 307.656
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. SFSU - 9/28 | 061 | CLOSED | 0 | 0 | 822.492 | 822.492
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. ST. MARY'S - 9/26 | 061 | CLOSED | 0 | 0 | 325.016 | 325.016
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT W. SOCCER V. UCSB - 10/26 | 061 | CLOSED | 0 | 0 | 1085.022 | 1085.022
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: W.SOCCER V. CSUN - 10/5 | 061 | CLOSED | 0 | 0 | 583.38 | 583.38
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT W SOCCER TELEVISED CHAMPIONSHIP GAMES-11/6&11/8 #184 | 061 | CLOSED | 0 | 0 | 562.68 | 562.68
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR W. SOCCER PLAYOFF GAMES-11/6-11/8 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR W. SOCCER SPRING GAMES & PRACTICES | 061 | CLOSED | 0 | 0 | 680.544 | 680.544
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR W. SOCCER V. LAMAR - 8/24 | 061 | CLOSED | 0 | 0 | 177.534 | 177.534
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR W. SOCCER V. WESTMONT- 8/14 | 061 | CLOSED | 0 | 0 | 194.82 | 194.82
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR WOMEN'S SOCCER PRACTICES-2014/2015 | 061 | CLOSED | 0 | 0 | 623.424 | 623.424
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. CSUN - 10/5 (12:00PM) | 061 | CLOSED | 0 | 0 | 58.446 | 58.446
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. FLORIDA ATL. - 8/3 (12:00PM) | 061 | CLOSED | 0 | 0 | 272.748 | 272.748
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. FRESNO ST. - 9/19 (5:00PM) | 061 | CLOSED | 0 | 0 | 259.841 | 259.841
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. HAWAI'I - 10/12 (12:00PM) | 061 | CLOSED | 0 | 0 | 156.948 | 156.948
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. SAN FRANCISCO - 9/28 (12:00PM) | 061 | CLOSED | 0 | 0 | 116.892 | 116.892
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. ST. MARYS - 9/26 (5:00PM) | 061 | CLOSED | 0 | 0 | 175.884 | 175.884
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. UC DAVIS - 10/10 (7:00PM) | 061 | CLOSED | 0 | 0 | 351.768 | 351.768
PJ0004984 | 14/15: SUPPORT FOR W. SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT W. SOCCER V. UCSB - 10/26 (12:00PM) | 061 | CLOSED | 0 | 0 | 343.0795 | 343.0795
PJ0004984 Total | [7 empty] | 451.104 | 0 | 11141.0376 | 11141.0376
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: REPAIR BLEACHER AFTER SOCCER GAME - 10/2 | 061 | CLOSED | 0 | 0 | 201.498 | 201.498
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: SUPPORT M. SOCCER V. UCSB - 11/2 (5:00PM) | 061 | CLOSED | 0 | 0 | 262.416 | 262.416
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CPE: SUPPORT M. SOCCER V. UCSB - 11/2 | 061 | CLOSED | 0 | 0 | 312.66 | 312.66
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR M. SOCCER - 9/19 | 061 | CLOSED | 0 | 0 | 333.6 | 333.6
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR M. SOCCER GAME - 9/6 | 061 | CLOSED | 0 | 0 | 278.964 | 278.964
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR M. SOCCER V. UCSB - 11/2 | 061 | CLOSED | 0 | 0 | 1826.325 | 1826.325
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR SPRING SOCCER GAMES | 061 | CLOSED | 0 | 0 | 1778.55 | 1778.55
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. DRAKE-9/26 | 061 | CLOSED | 0 | 0 | 375.447 | 375.447
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. GRAND CANTON - 9/11 | 061 | CLOSED | 0 | 0 | 392.94 | 392.94
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. PACIFIC -9/21 | 061 | CLOSED | 0 | 0 | 476.772 | 476.772
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. SAC STATE - 10/30/14 #187 | 061 | CLOSED | 0 | 0 | 851.508 | 851.508
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. SAN FRANCISCO - 9/19 | 061 | CLOSED | 0 | 0 | 596.436 | 596.436
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. UC DAVIS - 10/22 | 061 | CLOSED | 0 | 0 | 714.786 | 714.786
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT M. SOCCER V. UCI - 10/2 | 061 | CLOSED | 0 | 0 | 440.388 | 440.388
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT MEN'S SOCCER GAME - 9/7 | 061 | CLOSED | 0 | 0 | 589.776 | 589.776
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT M. SOCCER V. UCSB - 11/2 | 061 | CLOSED | 0 | 0 | 337.608 | 337.608
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR M. SOCCER GAMES AND PRACTICES | 061 | CLOSED | 0 | 0 | 1739.4 | 1739.4
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR MEN'S SOCCER GREEN & GOLD GAME - 8/16 | 061 | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR MEN'S SOCCER PRACTICES - 2014/2015 | 061 | CLOSED | 0 | 0 | 740.316 | 740.316
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. CSUN - 10/5 | 061 | CLOSED | 0 | 0 | 58.446 | 58.446
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. DRAKE - 9/26 | 061 | CLOSED | 0 | 0 | 186.444 | 186.444
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. GRAND CANYON - 9/11 | 061 | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. N. ILLINOIS - 9/5 | 061 | CLOSED | 0 | 0 | 351.768 | 351.768
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. N. MASS. - 9/7 | 061 | CLOSED | 0 | 0 | 294.5659 | 294.5659
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. PACIFIC - 9/21 | 061 | CLOSED | 0 | 0 | 116.892 | 116.892
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. SAC. STATE - 10/29 | 061 | CLOSED | 0 | 0 | 351.768 | 351.768
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. SAN FRANCISCO - 9/19 | 061 | CLOSED | 0 | 0 | 388.5461 | 388.5461
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. UC DAVIS - 10/22 | 061 | CLOSED | 0 | 0 | 156.948 | 156.948
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. UC IRVINE - 10/2 | 061 | CLOSED | 0 | 0 | 351.768 | 351.768
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT M. SOCCER V. UCSB - 11/2 | 061 | CLOSED | 0 | 0 | 467.568 | 467.568
PJ0004983 | 14/15: SUPPORT FOR MEN'S SOCCER (PROJECT) | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PL: SUPPORT M. SOCCER V. UCSB - 11/2 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004983 Total | [7 empty] | 0 | 0 | 15732.312 | 15732.312
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | 14/15: SUPPORT FOR FOOTBALL (PROJECT) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: CCI PORTABLES FOR FOOTBALL V. PORTLAND-9/20 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: OTIS ELEVATOR STANDBY SUPPORT - 9/20 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 2364.6679 | 2364.6679
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: OTIS ELEVATOR SUPPORT FOR FOOTBALL V. UC DAVIS - 11/15 | 061 | CLOSED | 0 | 0 | 2706.2119 | 2706.2119
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: OTIS SUPPORT FOR 10/25 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 2706.2119 | 2706.2119
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | AD: OTIS SUPPORT FOR 11/1 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: SUPPORT FOR FOOTBALL V. MONTANA - OCT 25 | 061 | CLOSED | 0 | 0 | 467.217 | 467.217
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: SUPPORT FOR FOOTBALL V. MONTANA ST. - NOV 1 | 061 | CLOSED | 281.94 | 0 | 292.002 | 292.002
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: SUPPORT FOR FOOTBALL V. PORTLAND ST. - SEPT 20 | 061 | CLOSED | 0 | 0 | 162.528 | 162.528
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT 4 | 061 | CLOSED | 0 | 0 | 259.884 | 259.884
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CA: SUPPORT FOR FOOTBALL V. UC DAVIS - NOV 15 | 061 | CLOSED | 451.104 | 0 | 386.496 | 386.496
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: SUPPORT FOR FOOTBALL V. MONTANA - OCT 25 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: SUPPORT FOR FOOTBALL V. MONTANA ST. - NOV. 1 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: SUPPORT FOR FOOTBALL V. PORTLAND ST. - SEPT 20 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT 4 | 061 | CLOSED | 0 | 0 | 590.58 | 590.58
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CP: SUPPORT FOR FOOTBALL V. UC DAVIS - NOV. 15 | 061 | CLOSED | 312.18 | 0 | 347.4 | 347.4
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: CLEANUP AFTER FOOTBALL GREEN & GOLD GAME-8/16 | 061 | CLOSED | 0 | 0 | 164.214 | 164.214
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: CUSTODIAL SUPPORT FOR FOOTBALL SPRING GAME | 061 | CLOSED | 0 | 0 | 197.52 | 197.52
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: HOLIDAY UNLOCK FOR FOOTBALL - 9/1 | 061 | CLOSED | 0 | 0 | 293.646 | 293.646
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOOTBALL V. MONTANA - 10/25 | 061 | CLOSED | 0 | 0 | 3428.697 | 3428.697
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOOTBALL V. MONTANA ST. - 11/1 | 061 | CLOSED | 0 | 0 | 3235.2 | 3235.2
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOOTBALL V. SOUTHERN UTAH-10/4 | 061 | CLOSED | 0 | 0 | 2701.383 | 2701.383
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR FOOTBALL V. PORTLAND ST. - 9/20 | 061 | CLOSED | 0 | 0 | 1975.596 | 1975.596
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: SUPPORT FOR FOOTBALL V. UC DAVIS - 11/15 | 061 | CLOSED | 0 | 0 | 2748.294 | 2748.294
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | CU: UNLOCK SUPPORT FOR FOOTBALL MEETINGS - 11/11 | 061 | CLOSED | 0 | 0 | 232.392 | 232.392
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SPEAKER MESH LIGHTS | 061 | CLOSED | 0 | 0 | 264.852 | 264.852
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT FOOTBALL V. MONTANA -OCT 25(TELEVISED) | 061 | CLOSED | 0 | 0 | 1832.028 | 1832.028
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT FOOTBALL V. MONTANA ST. - NOV 1(TELEVISED) | 061 | CLOSED | 0 | 0 | 1244.976 | 1244.976
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT FOOTBALL V. PORTLAND ST.-SEPT 20 | 061 | CLOSED | 0 | 0 | 1709.2579 | 1709.2579
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT FOOTBALL V. SOUTHERN UTAH - OCT 4 | 061 | CLOSED | 0 | 0 | 787.752 | 787.752
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | EL: SUPPORT FOOTBALL V. UC DAVIS - NOV 15 | 061 | CLOSED | 0 | 0 | 987.792 | 987.792
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: LINE FOR FOOTBALL SCRIMMAGE - AUG 16. | 061 | CLOSED | 0 | 0 | 428.604 | 428.604
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL PRACTICES | GENERAL | CLOSED | 0 | 0 | 2514.246 | 2514.246
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL SPRING GAMES/PRACTICES | GENERAL | CLOSED | 0 | 0 | 1382.5029 | 1382.5029
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL V. MONTANA - OCT 25 (PARENTS WEEKEND) | 061 | CLOSED | 0 | 0 | 8023.2905 | 8023.2905
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL V. MONTANA ST. - NOV. 1 | 061 | CLOSED | 0 | 0 | 7792.782 | 7792.782
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL V. PORTLAND ST. - SEPT 20 | 061 | CLOSED | 0 | 0 | 8211.2623 | 8211.2623
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT 4. | 061 | CLOSED | 0 | 0 | 6741.624 | 6741.624
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LA: SUPPORT FOR FOOTBALL V. UC DAVIS - NOV. 15 | 061 | CLOSED | 0 | 0 | 6200.052 | 6200.052
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | LO: REPAIR LOCKS ON SUITE REFRIGERATORS- SUITES 2&3 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | MC: SUPPORT FOR FOOTBALL V. S. UTAH - 10/4 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PERMIT: FOOTBALL TAILGATE. | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PERMIT:MUSTANG BBQ AT O'NEILL LAWN | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PL: SUPPORT FOOTBALL V. MONTANTA ST-NOV 1 (HOMECOMING) | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PL: SUPPORT FOOTBALL V. UC DAVIS - NOV 15 (RIVALRY GAME) | 061 | CLOSED | 0 | 0 | 388.578 | 388.578
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PL: SUPPORT FOR FOOTBALL V. MONTANA - OCT 25 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PL: SUPPORT FOR FOOTBALL V. PORTLAND ST. - SEPT 20 | 061 | CLOSED | 0 | 0 | 646.572 | 646.572
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | PL: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT 4 | 061 | CLOSED | 0 | 0 | 453.87 | 453.87
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | RE: SUPPORT FOOTBALL V. MONTANA - 10/25 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | RE: SUPPORT FOOTBALL V. MONTANA ST. - 11/1 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | RE: SUPPORT FOR FOOTBALL - 9/20 | 061 | CLOSED | 0 | 0 | 423.036 | 423.036
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | RE: SUPPORT FOR FOOTBALL V. S. UTAH - 10/4 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 | 14/15: SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2014-07-09 | RE:SUPPORT FOOTBALL V. UC DAVIS - 11/15 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004982 Total | [7 empty] | 1045.224 | 0 | 76916.6983 | 76916.6983
PJ0004981 | 2014: SUPPORT FOR SOAR EVENT JULY 10 - AUG 12 | POPHAM, DONALD J. | CLOSED | 2014-07-07 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004981 | 2014: SUPPORT FOR SOAR EVENT JULY 10 - AUG 12 | POPHAM, DONALD J. | CLOSED | 2014-07-07 | CU: SUPPORT FOR 2014 SOAR | GENERAL | CLOSED | 0 | 0 | 795.303 | 795.303
PJ0004981 | 2014: SUPPORT FOR SOAR EVENT JULY 10 - AUG 12 | POPHAM, DONALD J. | CLOSED | 2014-07-07 | EL: INSTALL ONE SPIDER BOX AT NW CORNER OF DEXTER LAWN-7/9 | 034 | CLOSED | 0 | 0 | 67.416 | 67.416
PJ0004981 | 2014: SUPPORT FOR SOAR EVENT JULY 10 - AUG 12 | POPHAM, DONALD J. | CLOSED | 2014-07-07 | LA: SUPPORT FOR SOAR 2014 - JULY 10-AUG 11 | GENERAL | CLOSED | 0 | 0 | 1314.1181 | 1314.1181
PJ0004981 | 2014: SUPPORT FOR SOAR EVENT JULY 10 - AUG 12 | POPHAM, DONALD J. | CLOSED | 2014-07-07 | PERMIT: SOAR TENT PERMIT - JULY 11-AUG 15 | GENERAL | CLOSED | 0 | 0 | 106.76 | 106.76
PJ0004981 Total | [7 empty] | 0 | 0 | 2283.5971 | 2283.5971
PJ0004979 | REMOVE SHELVING - KENNEDY LIBRARY BLDG 35 1ST & 2ND FLOOR | GONZALES, ALBERT M. | CLOSED | 2014-07-01 | AD: MARCHESE CONSTRUCTION | 035 | CLOSED | 3193.95 | 0 | 3193.95 | 3193.95
PJ0004979 | REMOVE SHELVING - KENNEDY LIBRARY BLDG 35 1ST & 2ND FLOOR | GONZALES, ALBERT M. | CLOSED | 2014-07-01 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 940.89 | 0 | 0 | 0
PJ0004979 | REMOVE SHELVING - KENNEDY LIBRARY BLDG 35 1ST & 2ND FLOOR | GONZALES, ALBERT M. | CLOSED | 2014-07-01 | IN: REMOVE SHELVING - KENNEDY LIBRARY BLDG 35 1ST & 2ND FLOOR | 035 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004979 | REMOVE SHELVING - KENNEDY LIBRARY BLDG 35 1ST & 2ND FLOOR | GONZALES, ALBERT M. | CLOSED | 2014-07-01 | PA: TOUCH UP PAINT WHERE SHELVING WAS REMOVED | 035 | CLOSED | 7080.1957 | 0 | 8002.02 | 8002.02
PJ0004979 Total | [7 empty] | 11343.1477 | 0 | 11260.026 | 11260.026
PJ0004978 | INSTALL CARPET - BLDG. 124 RM.224 | HICKS, MICHAEL | CLOSED | 2014-05-06 | AD: FLOOR CONNECTION | 124 | CLOSED | 10807 | 0 | 10699.3687 | 10699.3687
PJ0004978 | INSTALL CARPET - BLDG. 124 RM.224 | HICKS, MICHAEL | CLOSED | 2014-05-06 | CA: TRIM 2 DOOR BOTTOMS DUE TO CARPET INSTALL | 124 | CLOSED | 343.5173 | 0 | 327.354 | 327.354
PJ0004978 | INSTALL CARPET - BLDG. 124 RM.224 | HICKS, MICHAEL | CLOSED | 2014-05-06 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 1247.52 | 0 | 0 | 0
PJ0004978 | INSTALL CARPET - BLDG. 124 RM.224 | HICKS, MICHAEL | CLOSED | 2014-05-06 | IN: INSTALL CARPET - BLDG. 124 RM.224 | 124 | CLOSED | 71.1022 | 0 | 64.056 | 64.056
PJ0004978 | INSTALL CARPET - BLDG. 124 RM.224 | HICKS, MICHAEL | CLOSED | 2014-05-06 | MO: MOVE FURNITURE OUT OF RM 224 & 133 FOR CARPET INSTALLATION | 124 | CLOSED | 577.044 | 0 | 101.412 | 101.412
PJ0004978 Total | [7 empty] | 13046.1834 | 0 | 11192.1907 | 11192.1907
PJ0004977 | REPLACE FEED MILL DOOR HIT BY TRUCK - ANC (UPD CASE # 14-1041) | NORTON, DAVE | CLOSED | 2014-06-30 | AD: D.A. GRAGHEAD | 154 | CLOSED | 0 | 0 | 4901.0708 | 4901.0708
PJ0004977 | REPLACE FEED MILL DOOR HIT BY TRUCK - ANC (UPD CASE # 14-1041) | NORTON, DAVE | CLOSED | 2014-06-30 | CP: PROJECT CONTINGENCY (UPD CASE # 14-1041) | 154 | CLOSED | 0 | 0 | 0 | 0
PJ0004977 Total | [7 empty] | 0 | 0 | 4901.0708 | 4901.0708
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | AD: COMP VIEW | 061 | CLOSED | 6883.7701 | 0 | 7317.4732 | 7317.4732
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | AD: DEEP BLUE INTEGRATION | 061 | CLOSED | 9257.9075 | 0 | 9257.9075 | 9257.9075
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | AD: J.L. FASULO DRYWALL | 061 | CLOSED | 313.51 | 0 | 313.51 | 313.51
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 1312.21 | 0 | 0 | 0
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | CU: SUPPORT FOR VIDEO FEED INSTALL AT SPANOS SUITES: BLDG 061 | 061 | CLOSED | 437.8266 | 0 | 164.214 | 164.214
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | IN: INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | 061 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004975 | INSTALL VIDEO FEED AT SPANOS SUITES: BLDG 061 | GONZALES, ALBERT M. | CLOSED | 2014-06-26 | PA: SUPPORT FOR VIDEO FEED INSTALL AT SPANOS SUITES: BLDG 061 | 061 | CLOSED | 354.1698 | 0 | 593.64 | 593.64
PJ0004975 Total | [7 empty] | 18815.618 | 0 | 17902.9687 | 17902.9687
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | AD: MCWIL SPORTS - REPAINT GAME LINES AND LOGOS | 042 | CLOSED | 21239.5 | 0 | 21239.5 | 21239.5
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | AD: MCWIL SPORTS - SAND AND FINISH FLOOR | 042 | CLOSED | 38092 | 0 | 38092 | 38092
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 5937.61 | 0 | 0 | 0
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | CU: CUSTODIAL SUPPORT FOR MOTT GYM FLOOR REFINISHING PROJECT | 042 | CLOSED | 131.184 | 0 | 1198.501 | 1198.501
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | ES: SCHEDULE THE HVAC TO BE OFF JULY 28-AUG 18-MOTT GYM (MAINT) | 042 | CLOSED | 0 | 0 | 78.045 | 78.045
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | IN: REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | 042 | CLOSED | 256.224 | 0 | 224.196 | 224.196
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | LO:CHANGE CORES AT MOTT GYM MAIN GYM TO ORG. CONST-7/28 | 042 | CLOSED | 116.088 | 0 | 58.044 | 58.044
PJ0004974 | SAND, REFINISH, PAINT & ADD NEW GRAPHICS- MOTT GYM FLOOR 042-102 | POPHAM, DONALD J. | CLOSED | 2014-06-25 | MO:CLEAR OUT EQUIPMENT AT MOTT GYM - JULY 24 & 28 | 042 | CLOSED | 129.6 | 0 | 90.54 | 90.54
PJ0004974 Total | [7 empty] | 65902.206 | 0 | 60980.826 | 60980.826
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: ASAP REPROGRAPHICS | 035 | CLOSED | 28.0126 | 0 | 41.6765 | 41.6765
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: BKM | 035 | CLOSED | 110176.0596 | 0 | 110176.0596 | 110176.0596
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: BRANDOW & JOHNSON | 035 | CLOSED | 1872.5 | 0 | 1872.5 | 1872.5
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: COASTAL DEMO | 035 | CLOSED | 5243 | 0 | 5243 | 5243
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: DEEP BLUE INTEGRATION | 035 | CLOSED | 3890.52 | 0 | 1712 | 1712
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: ENGLEKIRK & SABOL | 035 | CLOSED | 535 | 0 | 535 | 535
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: FLOOR CONNECTION | 035 | CLOSED | 22362.3259 | 0 | 22362.3259 | 22362.3259
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: GOSS ENGINEERING | 035 | CLOSED | 7971.5 | 0 | 7971.5 | 7971.5
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: ITS | 035 | CLOSED | 20930.912 | 0 | 20609.912 | 20609.912
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: JOC 15.035.014 MAINO | 035 | CLOSED | 152721.1 | 0 | 152700.6095 | 152700.6095
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: L KERSHNER DESIGN | 035 | CLOSED | 172791.2077 | 0 | 161165.0585 | 161165.0585
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: MAINO LVPW | 035 | CLOSED | 3869.9225 | 0 | 3869.9225 | 3869.9225
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: MATERIALS PURCHASE AND INSTALLED BY THE PROJECT MANAGER | 035 | CLOSED | 0 | 0 | 4.068 | 4.068
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: PURCHASE ELECTRONICS ON PROCARD (PROJECT MANAGER) | 035 | CLOSED | 249.24 | 0 | 493.096 | 493.096
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: SIMPLEX GRINNELL | 035 | CLOSED | 29777.7362 | 0 | 29777.7148 | 29777.7148
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: STATE FIRE MARSHAL | 035 | CLOSED | 834.6 | 0 | 2212.3534 | 2212.3534
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | AD: THOMA | 035 | CLOSED | 535 | 0 | 535 | 535
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | CA: SUPPORT FOR WALL PENETRATIONS | 035 | CLOSED | 3075.6462 | 0 | 385.62 | 385.62
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 9277.07 | 0 | 0 | 0
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | CU: FINAL CONSTRUCTION CLEANING | 035 | CLOSED | 745.5319 | 0 | 184.2 | 184.2
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | EL: SUPPORT AND INSTALLATION OF NEW POWER AND LIGHTING | 035 | CLOSED | 40370.4535 | 0 | 39163.938 | 39163.938
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | ES: MECHANICAL SUPPORT AND COTROLS INSTALLATION | 035 | CLOSED | 22753.1558 | 0 | 51913.104 | 51913.104
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | IN: CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | 035 | CLOSED | 1624.812 | 0 | 2189.964 | 2189.964
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | LA: REPAIR IRRIGATION LINE BEHIND LIBRARY - DAMAGE FROM CTLT PJ | 035 | CLOSED | 208.128 | 0 | 40.032 | 40.032
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | LO: SUPPORT AND INSTALLATION OF NEW HARDWARE | 035 | CLOSED | 6157.3867 | 0 | 6573.064 | 6573.064
PJ0004973 | CTLT OFFICE SPACE CONSTRUCTION PHASE - BLD 35 3RD FLR | KOLEGRAFF, KENNETH | CLOSED | 2014-06-26 | PA: NEW PAINT FOR CTLT OFFICE SPACE | 035 | CLOSED | 14382.7194 | 0 | 7120.416 | 7120.416
PJ0004973 Total | [7 empty] | 632383.5401 | 0 | 628852.1347 | 628852.1347
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: BKM | 074 | CLOSED | 0 | 0 | 85635.7808 | 85635.7808
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: EC WEST | 074 | CLOSED | 0 | 0 | 32044.36 | 32044.36
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: ITS CHARGES FOR DATA LINE INSTALLATION (TRACKING, ONLY) | 074 | CLOSED | 26750 | 0 | 24513.5 | 24513.5
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: JOC 13.031.025 MAINO | 074 | CLOSED | 0 | 0 | 89460.132 | 89460.132
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: JOC 13.031.031 & 13.031.026 MAINO | 074 | CLOSED | 116449.8441 | 0 | 171452.4023 | 171452.4023
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: JOC 14.033.019 MAINO | 074 | CLOSED | 0 | 0 | 4912.8622 | 4912.8622
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: MODULAR SPACE CORPORATION | 074 | CLOSED | 0 | 0 | 549313.2295 | 549313.2295
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: OVERSIGHT OF TRAILER INSTALLATION | 074 | CLOSED | 31481.22 | 0 | 31481.22 | 31481.22
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: STATE FIRE MARSHAL | 074 | CLOSED | 0 | 0 | 635.0236 | 635.0236
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | AD: WAREHOUSE PARTS ISSUED TO PROJECT MANAGER | 074 | CLOSED | 0 | 0 | 100.1129 | 100.1129
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | CA: FABRICATE TAGS FOR ELECTRIC SHOP - MODULARS AT BLDG. 74 SITE | 074 | CLOSED | 0 | 0 | 148.218 | 148.218
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | CP: PROJECT CONTINGENCY | 074 | CLOSED | 25021.81 | 0 | 0 | 0
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | CPE: PROGRAM THERMOSTATS FOR MODULARS AT OLD UPD SITE | 074 | CLOSED | 0 | 0 | 230.928 | 230.928
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | EL:TRAILER POWER FOR BLDG 74 SITE | 074 | CLOSED | 60000 | 0 | 27465.528 | 27465.528
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | IN: SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | 074 | CLOSED | 320.28 | 0 | 1377.204 | 1377.204
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | LA. PROVIDE NEW IRRIGATION SYS. AS NEEDED FOR BLDG 74 MODULAR | 074 | CLOSED | 216.6398 | 0 | 1399.2499 | 1399.2499
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | LO: PROVIDE AND INSTALL CORES | 074 | CLOSED | 4800 | 0 | 4256.358 | 4256.358
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | PA: PAINT SKIRTING & STRIPES ON STAIRS - MODULARS AT OLD UPD | 074 | CLOSED | 0 | 0 | 309.54 | 309.54
PJ0004972 | SP 14/15: MODULAR INSTALLATION NEAR OLD UPD SITE - BLDG 74 | LAMPMAN, GREG | CLOSED | 2014-06-26 | PL: PROVIDE CONNECTION TO THE TRAILER RESTROOMS & SITE WORK | 074 | CLOSED | 10200 | 0 | 2545.4124 | 2545.4124
PJ0004972 Total | [7 empty] | 275239.7939 | 0 | 1027281.0616 | 1027281.0616
PJ0004971 | CREATE DOORWAY INTO PARTS ROOM - BLD 71 RM 01 (MAINT) | POLVI, STEVEN | CLOSED | 2014-06-23 | CA: INSTALL DOOR INTO PARTS ROOM - TRANSPO BLDG. 71 | 071 | CLOSED | 1879.6 | 0 | 2164.56 | 2164.56
PJ0004971 | CREATE DOORWAY INTO PARTS ROOM - BLD 71 RM 01 (MAINT) | POLVI, STEVEN | CLOSED | 2014-06-23 | CP: PROJECT CONTINGENCY | 071 | CLOSED | 0 | 0 | 0 | 0
PJ0004971 | CREATE DOORWAY INTO PARTS ROOM - BLD 71 RM 01 (MAINT) | POLVI, STEVEN | CLOSED | 2014-06-23 | IN: CREATE DOORWAY INTO PARTS ROOM - BLD 71 RM 01 (MAINT) | 071 | CLOSED | 0 | 0 | 58.87 | 58.87
PJ0004971 | CREATE DOORWAY INTO PARTS ROOM - BLD 71 RM 01 (MAINT) | POLVI, STEVEN | CLOSED | 2014-06-23 | LO: INSTALL HARDWARE ON DOOR INTO PARTS ROOM - TRANSPO BLDG. 71 | 071 | CLOSED | 0 | 0 | 692.31 | 692.31
PJ0004971 | CREATE DOORWAY INTO PARTS ROOM - BLD 71 RM 01 (MAINT) | POLVI, STEVEN | CLOSED | 2014-06-23 | PA: PAINT NEW DOOR INTO PARTS ROOM - TRANSPO BLDG. 71 | 071 | CLOSED | 0 | 0 | 438.515 | 438.515
PJ0004971 Total | [7 empty] | 1879.6 | 0 | 3354.255 | 3354.255
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: BKM | 026M-M063 | CLOSED | 0 | 0 | 27232.2383 | 27232.2383
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: ECWEST | 026M-M063 | CLOSED | 8323.209 | 0 | 8323.209 | 8323.209
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: ITS DATA LINE INSTALLATIONS (TRACKING, ONLY) | 026M-M063 | CLOSED | 18190 | 0 | 13139.26 | 13139.26
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: JOC 13.031.024 & 13.031.031 MAINO | 026M-M063 | CLOSED | 87836.4498 | 0 | 34225.7369 | 34225.7369
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: JOC 13.031.032 & 13.031.034 MAINO | 026M-M063 | CLOSED | 0 | 0 | 65831.3969 | 65831.3969
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: MODULAR SPACE CORPORATION | 026M-M063 | CLOSED | 0 | 0 | 131818.864 | 131818.864
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: OVERSIGHT OF TRAILER INSTALLATION | 026M-M063 | CLOSED | 7678.09 | 0 | 7678.09 | 7678.09
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: STATE FIRE MARSHAL | 026M-M063 | CLOSED | 0 | 0 | 846.7017 | 846.7017
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | CA: CREATE TAGS FOR ELECTRICAL PANEL FOR MODULARS AT BLDG. 26 | 026M-M063 | CLOSED | 0 | 0 | 119.712 | 119.712
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | CP: PROJECT CONTINGENCY | 026M-M063 | CLOSED | 5441.79 | 0 | 0 | 0
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | CPE: PROGRAM THERMOSTATS FOR GRAPHIC ARTS MODULAR | 026M-M063 | CLOSED | 0 | 0 | 153.96 | 153.96
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | EL:POWER TO TRAILERS BLDG 46/26 SITE | 026M-M063 | CLOSED | 30000 | 0 | 44895.33 | 44895.33
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | IN: SP 14/15: MODULAR INSTALLATION AT BLDG 26 | 026M-M063 | CLOSED | 320.28 | 0 | 800.7 | 800.7
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | LA: REPAIR SPRINKLER SYSTEM AT BLDG. 26 MODULAR SITE | 026M-M063 | CLOSED | 260.2795 | 0 | 1636.488 | 1636.488
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | LO: PROVIDE CORES AND INSTALL ON NEW MODULAR AT BLDG. 26 | 026M-M063 | CLOSED | 2400 | 0 | 698.61 | 698.61
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | PA: PAINT SKIRTING & STRIPES ON STAIRS - MODULARS NEAR BLDG26 | 026M-M063 | CLOSED | 0 | 0 | 1127.916 | 1127.916
PJ0004969 | SP 14/15: MODULAR INSTALLATION AT BLDG 26 | LAMPMAN, GREG | CLOSED | 2014-06-23 | PL: ASSIST WITH MODULAR INSTALLATION NEAR BLDG. 26 | 026M-M063 | CLOSED | 903.504 | 0 | 228.522 | 228.522
PJ0004969 Total | [7 empty] | 161353.6023 | 0 | 338756.7348 | 338756.7348
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: BKM | GENERAL | CLOSED | 0 | 0 | 85888.8679 | 85888.8679
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: ECWEST | GENERAL | CLOSED | 0 | 0 | 28298.9106 | 28298.9106
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: G.F. GARCIA AND SONS | GENERAL | CLOSED | 0 | 0 | 2625.78 | 2625.78
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: ITS CHARGES FOR DATA LINE INSTALLATION (TRACKING, ONLY) | GENERAL | CLOSED | 31030 | 0 | 23186.02 | 23186.02
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: JOC 13.031.023 MAINO | GENERAL | CLOSED | 0 | 0 | 111089.8824 | 111089.8824
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: JOC 13.031.031 & 13.031.027 MAINO | GENERAL | CLOSED | 189574.8853 | 0 | 164953.9071 | 164953.9071
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: JOC 14.033.033 MAINO | GENERAL | CLOSED | 0 | 0 | 3386.9352 | 3386.9352
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: MODULAR SPACE CORPORATION | GENERAL | CLOSED | 0 | 0 | 453728.7278 | 453728.7278
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: OVERSIGHT OF TRAILER INSTALLATION | GENERAL | CLOSED | 25172.07 | 0 | 25172.07 | 25172.07
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | AD: STATE FIRE MARSHAL | GENERAL | CLOSED | 0 | 0 | 931.3601 | 931.3601
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | CA: FABRICATE TAGS FOR ELECTRIC SHOP - POLY GROVE MODULARS | GENERAL | CLOSED | 0 | 0 | 147.906 | 147.906
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 33079.1 | 0 | 0 | 0
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | CPE: PROGRAM THERMOSTATS FOR POLY GROVE MODULARS | GENERAL | CLOSED | 0 | 0 | 230.928 | 230.928
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | EL: POWER TO TRAILER AT POLY GROVE SITE | GENERAL | CLOSED | 78000 | 0 | 45514.9097 | 45514.9097
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | IN: SP 14/15: MODULAR INSTALLATION AT POLY GROVE | GENERAL | CLOSED | 320.28 | 0 | 1281.12 | 1281.12
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | LA: TRIM TREE AS NEEDED FOR POLY GROVE MODULAR INSTALLATION | GENERAL | CLOSED | 693.9488 | 0 | 77.928 | 77.928
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | LO: PROVIDE CORES AND INSTALL | GENERAL | CLOSED | 6000 | 0 | 3688.386 | 3688.386
PJ0004968 | SP 14/15: MODULAR INSTALLATION AT POLY GROVE | LAMPMAN, GREG | CLOSED | 2014-06-23 | PA: PAINT SKIRTING & STRIPES ON STAIRS - MODULARS AT POLY GROVE | GENERAL | CLOSED | 0 | 0 | 495.264 | 495.264
PJ0004968 Total | [7 empty] | 363870.2841 | 0 | 950698.9028 | 950698.9028
PJ0004966 | REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | NORTON, DAVE | CLOSED | 2014-06-18 | AD: FLOOR CONNECTION | 013 | CLOSED | 709.838 | 0 | 709.838 | 709.838
PJ0004966 | REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | NORTON, DAVE | CLOSED | 2014-06-18 | CA: REMOVE CABINETS | 013 | CLOSED | 376.6718 | 0 | 156.87 | 156.87
PJ0004966 | REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | NORTON, DAVE | CLOSED | 2014-06-18 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 229.64 | 0 | 0 | 0
PJ0004966 | REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | NORTON, DAVE | CLOSED | 2014-06-18 | IN: REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | 013 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004966 | REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | NORTON, DAVE | CLOSED | 2014-06-18 | MO: | 013 | CLOSED | 97.2 | 0 | 108.648 | 108.648
PJ0004966 | REMOVE BUILT-IN CABINETS, CLEAR AND PAINT ROOM 13-201 | NORTON, DAVE | CLOSED | 2014-06-18 | PA: PAINT WALLS | 013 | CLOSED | 912.0428 | 0 | 559.548 | 559.548
PJ0004966 Total | [7 empty] | 2389.4487 | 0 | 1598.96 | 1598.96
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | AD: CAL POLY FACILITIES BUILDING PERMIT FEES | 034 | CLOSED | 600 | 0 | 600 | 600
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | AD: CAL POLY FACILITIES PLAN REVIEW FEES | 034 | CLOSED | 534 | 0 | 534 | 534
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | AD: ENGLEKIRK AND SABOL | 034 | CLOSED | 500 | 0 | 500 | 500
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | AD: STATE FIRE MARSHAL FEES | 034 | CLOSED | 481.5 | 0 | 755.6768 | 755.6768
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 619.44 | 0 | 0 | 0
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | EH&S:CONTRACTOR SUPPORT FOR SUBWAY HVAC UPGRADE | 034 | CLOSED | 394.8 | 0 | 0 | 0
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | IN: HVAC/EXHAUST SYSTEM UPGRADE & EXPRESS WINDOW REPAIR - SUBWAY | 034 | CLOSED | 384.336 | 0 | 413.982 | 413.982
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | MO: MOVE CONCRETE TABLES ON DEXTER PLAZA | 034 | CLOSED | 134.064 | 0 | 16.902 | 16.902
PJ0004964 | TI: HVAC & EXHAUST SYSTEM UPGRADE/EXPRESS WINDOW REPAIR - SUBWAY | MOLLAN, CHERYL L. | CLOSED | 2014-06-16 | PA:PAINT EXTERIOR WALL AND INTERIOR WALL IN ROTC- SUBWAY | 034 | CLOSED | 1247.28 | 0 | 445.74 | 445.74
PJ0004964 Total | [7 empty] | 4895.42 | 0 | 3266.3008 | 3266.3008
PJ0004963 | QUARTERLY MAINTENANCE WALK-THROUGH 1/14/14 & 4/8/14 - PAC 06 | LOOSLEY, SCOTT L. | CLOSED | 2014-06-13 | CA: MULTIPLE REPAIR ITEMS | 006 | CLOSED | 0 | 0 | 1478.265 | 1478.265
PJ0004963 | QUARTERLY MAINTENANCE WALK-THROUGH 1/14/14 & 4/8/14 - PAC 06 | LOOSLEY, SCOTT L. | CLOSED | 2014-06-13 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004963 | QUARTERLY MAINTENANCE WALK-THROUGH 1/14/14 & 4/8/14 - PAC 06 | LOOSLEY, SCOTT L. | CLOSED | 2014-06-13 | LO: PAC MAINTENANCE WALK-THROUGH ITEMS | 006 | CLOSED | 0 | 0 | 406.16 | 406.16
PJ0004963 Total | [7 empty] | 0 | 0 | 1884.425 | 1884.425
PJ0004962 | PRESIDENT'S SUITE: PURCHASE AND INSTALL TELEVISIONS | GONZALES, ALBERT M. | CLOSED | 2014-06-12 | AD: COMPVIEW | 061 | CLOSED | 4014.4367 | 0 | 4116.0867 | 4116.0867
PJ0004962 | PRESIDENT'S SUITE: PURCHASE AND INSTALL TELEVISIONS | GONZALES, ALBERT M. | CLOSED | 2014-06-12 | AD: DEEP BLUE INTEGRATION | 061 | CLOSED | 5564 | 0 | 3708.3525 | 3708.3525
PJ0004962 | PRESIDENT'S SUITE: PURCHASE AND INSTALL TELEVISIONS | GONZALES, ALBERT M. | CLOSED | 2014-06-12 | AD: MORELAND THOMPSON, INC. | 061 | CLOSED | 3424 | 0 | 2065.1 | 2065.1
PJ0004962 | PRESIDENT'S SUITE: PURCHASE AND INSTALL TELEVISIONS | GONZALES, ALBERT M. | CLOSED | 2014-06-12 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004962 | PRESIDENT'S SUITE: PURCHASE AND INSTALL TELEVISIONS | GONZALES, ALBERT M. | CLOSED | 2014-06-12 | IN: PRESIDENT'S SUITE: PURCHASE AND INSTALL TELEVISIONS | 061 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004962 Total | [7 empty] | 13258.6607 | 0 | 10145.7632 | 10145.7632
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | AD: BOB'S CRANE | 018A | CLOSED | 2675 | 0 | 1605 | 1605
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | AD: TRANE U.S., INC. | 018A | CLOSED | 49220 | 0 | 49023.655 | 49023.655
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | CA: FORM & POUR CONCRETE PIPE STAND SUPPORT | 018A | CLOSED | 2255.52 | 0 | 1521.8146 | 1521.8146
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | CP: PROJECT CONTINGENCY | 018A | CLOSED | 8529.61 | 0 | 0 | 0
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | CPE: INSTALL NEW CHILLER | 018A | CLOSED | 22737.7034 | 0 | 10790.784 | 10790.784
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | EL: ELECTRICAL WORK FOR NEW CHILLER | 018A | CLOSED | 7800.6862 | 0 | 9765.108 | 9765.108
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | IN: SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | 018A | CLOSED | 1024.896 | 0 | 64.056 | 64.056
PJ0004960 | SR 14/15: REPLACE CHILLER AT DPTC - BLDG 18A RM 18T | BRENNAN, MICHAEL | CLOSED | 2014-06-12 | PL: SUPPORT CHILLER REPLACEMENT AT DPTC - BLDG. 18A (N/L) | 018A | CLOSED | 381.168 | 0 | 0 | 0
PJ0004960 Total | [7 empty] | 94624.5836 | 0 | 72770.4176 | 72770.4176
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | AD: ASAP REPROGRAPHICS | 065 | CLOSED | 0 | 0 | 32.7634 | 32.7634
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | AD: JOC 13.031.011 MAINO | 065 | CLOSED | 212221.8847 | 0 | 211240.3737 | 211240.3737
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | AD: MCKENNA ENVIRONMENTAL | 065 | CLOSED | 845.3 | 0 | 738.3 | 738.3
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 3920 | 0 | 0 | 0
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | EL: ELECTRICAL SUPPORT FOR SALAD BAR | 065 | CLOSED | 1800.679 | 0 | 904.008 | 904.008
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | IN: CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | 065 | CLOSED | 541.2732 | 0 | 1088.952 | 1088.952
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | LO: INSTALL CONSTRUCTION CORE TO SIDE ENTRY DOOR - CIAO | 065 | CLOSED | 116.088 | 0 | 174.132 | 174.132
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | PA: PAINTING FOR NEW SALAD BAR | 065 | CLOSED | 3242.2916 | 0 | 2484.324 | 2484.324
PJ0004959 | CONSTRUCT NEW SALAD BAR (THE RED RADISH) IN CIAO! RESTAURANT | NORTON, DAVE | CLOSED | 2014-06-10 | PL: PLUMBING SUPPORT FOR SALAD BAR | 065 | CLOSED | 5306.1469 | 0 | 616.452 | 616.452
PJ0004959 Total | [7 empty] | 227993.6634 | 0 | 217279.3051 | 217279.3051
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 256800 | 0 | 254062.6083 | 254062.6083
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: BOWEN ENGINEERING | 052 | CLOSED | 1412.4 | 0 | 1412.4 | 1412.4
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 1834.836 | 1834.836
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: FLOOR CONNECTION | 052 | CLOSED | 69550 | 0 | 32459.1883 | 32459.1883
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: J.L. FASULO DRYWAL | 052 | CLOSED | 2176.38 | 0 | 2176.38 | 2176.38
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 13.030.042 MAINO | 052 | CLOSED | 93814.39 | 0 | 65051.3455 | 65051.3455
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 13.031.044 MAINO | 052 | CLOSED | 0 | 0 | 66633.18 | 66633.18
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 14.033.016 | 052 | CLOSED | 0 | 0 | 48970.9468 | 48970.9468
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 12840 | 0 | 10168.5845 | 10168.5845
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: MEATHEAD MOVERS | 052 | CLOSED | 3745 | 0 | 3044.685 | 3044.685
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 98.63 | 98.63
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 45719.8 | 0 | 0 | 0
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | EL: DISCONNECT AND REMOVE ALL POWER FROM ITEMS TO BE REMOVED | 052 | CLOSED | 9002.7326 | 0 | 3916.86 | 3916.86
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | IN: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | 052 | CLOSED | 512.448 | 0 | 192.168 | 192.168
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | ITS: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | 052 | CLOSED | 0 | 0 | 33076.29 | 33076.29
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | LO:RE KEY ROOMS FOR DEPARTMENT USE | 052 | CLOSED | 2833.7636 | 0 | 1980.33 | 1980.33
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | PA: PAINT ALL WALLS | 052 | CLOSED | 21618.6714 | 0 | 19616.646 | 19616.646
PJ0004957 | SP 14/15: STUDENT AFFAIRS RENO - BLDG. 52 E4,E6-11,E13-19,E22-23 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | PL: DISCONNECT ALL PLUMBING FROM ITEMS TO BE REMOVED | 052 | CLOSED | 36770.2278 | 0 | 27394.2997 | 27394.2997
PJ0004957 Total | [7 empty] | 556795.8135 | 0 | 572089.3781 | 572089.3781
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 35779.3555 | 0 | 34416.7105 | 34416.7105
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 270.924 | 270.924
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: EC WEST | 052 | CLOSED | 4993.9254 | 0 | 4993.9254 | 4993.9254
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: FLOOR CONNECTION | 052 | CLOSED | 9630 | 0 | 5570.2488 | 5570.2488
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 13.030.042 MAINO | 052 | CLOSED | 8726.92 | 0 | 7623.3434 | 7623.3434
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 13.031.044 MAINO | 052 | CLOSED | 0 | 0 | 7808.7209 | 7808.7209
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 14.033.016 MAINO | 052 | CLOSED | 0 | 0 | 5738.8915 | 5738.8915
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 2140 | 0 | 1513.6755 | 1513.6755
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 286.56 | 286.56
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 1344.68 | 0 | 0 | 0
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | EL:ELECTRICAL DISCONNECT ROOM E24 | 052 | CLOSED | 3600.6862 | 0 | 3047.304 | 3047.304
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | IN: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | 052 | CLOSED | 256.224 | 0 | 170.022 | 170.022
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | ITS: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | 052 | CLOSED | 0 | 0 | 3575.8 | 3575.8
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | LO: REKEY FOR FACULTY USE | 052 | CLOSED | 498.2958 | 0 | 1159.374 | 1159.374
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | PA: PAINT ROOM E24 | 052 | CLOSED | 2185.6124 | 0 | 4609.068 | 4609.068
PJ0004956 | SP 14/15: OFFICE RENOVATION FOR ACADEMIC AFFAIRS - BLDG 52 - E24 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | PL: DISCONNECT AND REMOVE ALL PLUMBING | 052 | CLOSED | 4106.1469 | 0 | 1479.846 | 1479.846
PJ0004956 Total | [7 empty] | 73261.8462 | 0 | 82264.414 | 82264.414
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 37450 | 0 | 30209.5026 | 30209.5026
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 773.931 | 773.931
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: EC WEST | 052 | CLOSED | 6658.5672 | 0 | 6658.5672 | 6658.5672
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: FLOOR CONNECTION | 052 | CLOSED | 12305 | 0 | 8964.5884 | 8964.5884
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 13.030.042 MAINO | 052 | CLOSED | 10908.65 | 0 | 12514.4097 | 12514.4097
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 13.031.044 MAINO | 052 | CLOSED | 0 | 0 | 12818.7177 | 12818.7177
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: JOC 14.033.016 MAINO | 052 | CLOSED | 0 | 0 | 9420.9113 | 9420.9113
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 2675 | 0 | 2140 | 2140
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: POWER STRIP PURCHASE | 052 | CLOSED | 0 | 0 | 610.98 | 610.98
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: PURCHASE SURGE PROTECTORS FOR ELECTRONICS EQUIPMENT | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 98.63 | 98.63
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 546.66 | 0 | 0 | 0
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | EL: REPLACE BROKEN LIGHT LENS | 052 | CLOSED | 1800.679 | 0 | 101.124 | 101.124
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | IN: SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 E35 - E43 | 052 | CLOSED | 128.112 | 0 | 134.7 | 134.7
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | ITS: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | 052 | CLOSED | 0 | 0 | 6257.82 | 6257.82
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | LO: KEY LOCKSETS FOR FACULTY USE | 052 | CLOSED | 498.2958 | 0 | 260.088 | 260.088
PJ0004955 | SP 14/15: RENOVATION FOR FACULTY OFFICES - BLDG 52 RMS E35 - E43 | MCNALLY, CURTIS | CLOSED | 2014-06-05 | PA: PAINT ROOMS E35-E43 | 052 | CLOSED | 5187.9041 | 0 | 8169.525 | 8169.525
PJ0004955 Total | [7 empty] | 78158.868 | 0 | 99133.4949 | 99133.4949
PJ0004954 | SR 14/15: DEMO OLD UPD - BLDG 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-06 | AD: JOC 13.031.003 MAINO | 074 | CLOSED | 157905.7743 | 0 | 157905.7743 | 157905.7743
PJ0004954 | SR 14/15: DEMO OLD UPD - BLDG 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-06 | AD: MCKENNA ENVIRONMENTAL | 074 | CLOSED | 9256.5165 | 0 | 6348.31 | 6348.31
PJ0004954 | SR 14/15: DEMO OLD UPD - BLDG 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-06 | CP: PROJECT CONTINGENCY | 074 | CLOSED | 16229.35 | 0 | 0 | 0
PJ0004954 | SR 14/15: DEMO OLD UPD - BLDG 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-06 | CPE: START UP HEATING UNIT AT EOC - BLDG. 74D | 074 | CLOSED | 131.328 | 0 | 164.448 | 164.448
PJ0004954 | SR 14/15: DEMO OLD UPD - BLDG 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-06 | IN: SR 14/15: DEMO OLD UPD - BLDG 74 | 074 | CLOSED | 256.224 | 0 | 240.666 | 240.666
PJ0004954 | SR 14/15: DEMO OLD UPD - BLDG 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-06 | PL: RECONNECT GAS PIPE TO EOC - BLDG. 74D | 074 | CLOSED | 381.168 | 0 | 700.74 | 700.74
PJ0004954 Total | [7 empty] | 184160.3608 | 0 | 165359.9383 | 165359.9383
PJ0004953 | WINDOW WASHING - BLDG. 11 RMS 211B, 211C, 211D, 211E, 212, 212B | CANTU, MONICA M. | CLOSED | 2014-06-04 | AD: COASTAL JANITORIAL - WASH WINDOWS | 011 | CLOSED | 0 | 0 | 298.53 | 298.53
PJ0004953 | WINDOW WASHING - BLDG. 11 RMS 211B, 211C, 211D, 211E, 212, 212B | CANTU, MONICA M. | CLOSED | 2014-06-04 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0004953 Total | [7 empty] | 0 | 0 | 298.53 | 298.53
PJ0004952 | PROVOST'S DESK MODIFICATION - BLDG. 1 RM 305B | MCNALLY, CURTIS | CLOSED | 2014-06-02 | AD: BENCHMARK WOODWORKS | 001 | CLOSED | 2247 | 0 | 1013.29 | 1013.29
PJ0004952 | PROVOST'S DESK MODIFICATION - BLDG. 1 RM 305B | MCNALLY, CURTIS | CLOSED | 2014-06-02 | AD: EC WEST | 001 | CLOSED | 1779.1425 | 0 | 1779.1425 | 1779.1425
PJ0004952 | PROVOST'S DESK MODIFICATION - BLDG. 1 RM 305B | MCNALLY, CURTIS | CLOSED | 2014-06-02 | CP: PROJECT CONTINGENCY PHASE | 001 | CLOSED | 465.85 | 0 | 0 | 0
PJ0004952 | PROVOST'S DESK MODIFICATION - BLDG. 1 RM 305B | MCNALLY, CURTIS | CLOSED | 2014-06-02 | IN: PROVOST'S DESK MODIFICATION - BLDG. 1 RM 305B | 001 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004952 Total | [7 empty] | 4620.1045 | 0 | 2824.4605 | 2824.4605
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | AD: ASAP REPROGRAPHICS | 070 | CLOSED | 0 | 0 | 537.83 | 537.83
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | AD: FLOOR CONNECTION | 070 | CLOSED | 25124 | 0 | 25124 | 25124
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | AD: FURNISHINGS | 070 | CLOSED | 20000 | 0 | 16997.08 | 16997.08
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | AD: JOC 13.031.019 MAINO | 070 | CLOSED | 532883.32 | 0 | 532883.32 | 532883.32
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | AD: ONTRAC SHIPPING | 070 | CLOSED | 0 | 0 | 30.88 | 30.88
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | AD: STATE FIRE MARSHAL FEES | 070 | CLOSED | 0 | 0 | 2486.22 | 2486.22
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | CA: OFFICE EXPANSION SUPPORT | 070 | CLOSED | 2879.6 | 0 | 6935.2325 | 6935.2325
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | EL: PROVIDE PPOC FOR FACILITIES PLANNING OFFICE EXPANSION | 070 | CLOSED | 5870.8 | 0 | 8295.545 | 8295.545
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | ES: PROVIDE CONTRACTOR SUPPORT FOR HYDRONIC PIPING ALT | 070 | CLOSED | 832.48 | 0 | 383.04 | 383.04
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | IN: OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 | 070 | CLOSED | 1281.12 | 0 | 3002.37 | 3002.37
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | ITS: DATA CONNECTIONS FOR OFFICE EXPANSION - BLDG. 70 2ND FLOOR | 070 | CLOSED | 12055.7 | 0 | 15715.64 | 15715.64
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | LO: INSTALL LOCKSETS FOR FPCP OFFICES EXPANSION | 070 | CLOSED | 15541.32 | 0 | 12114.915 | 12114.915
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | MO: MOVE CABINETRY TO BE REUSED. | 070 | CLOSED | 440.1 | 0 | 45.27 | 45.27
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | PA: INTERIOR PAINTING FOR FPCP OFFICES EXPANSION | 070 | CLOSED | 3957.6 | 0 | 9645.035 | 9645.035
PJ0004951 | OFFICE EXPANSION CONSTRUCTION PHASE - BLDG. 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-06-03 | PL: PROVIDE CONTRATOR SUPPORT FOR FPCP OFFICES EXPANSION | 070 | CLOSED | 4241.12 | 0 | 161.22 | 161.22
PJ0004951 Total | [7 empty] | 625107.16 | 0 | 634357.5975 | 634357.5975
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | AD: BELFOR N2014003 | 171E | CLOSED | 62871.8518 | 0 | 62871.8625 | 62871.8625
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | AD: FLOOR CONNECTION | 171E | CLOSED | 1111.73 | 0 | 1111.73 | 1111.73
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | AD: JOC 13.031.009 MAINO | 171E | CLOSED | 37258.4914 | 0 | 36167.6264 | 36167.6264
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | CP: PROJECT CONTINGENCY | 171E | CLOSED | 3009.42 | 0 | 0 | 0
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | IN: CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | 171E | CLOSED | 427.8941 | 0 | 608.532 | 608.532
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | PCV CA: SUPPORT WATER DAMAGE PROJECT CAUSED BY TOILET LEAK (N/L) | 171E | CLOSED | 0 | 0 | 0 | 0
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | PCV CA: TO REPLACE 4" RUBBER BASE IN APPT 311, 211, HALLWAYS | 171E | CLOSED | 1868.2703 | 0 | 155.484 | 155.484
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | PCV EL: SUPPORT FOR WATER DAMAGE PROJECT CAUSED BY TOILET LEAK | 171E | CLOSED | 0 | 0 | 269.664 | 269.664
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | PCV PA: PROVIDE PAINT PRIMER & FINISH PAINT (MAT. ONLY) TO JOC | 171E | CLOSED | 1090.584 | 0 | 1002.816 | 1002.816
PJ0004948 | CLEAN-UP WATER DAMAGE - PCV ESTRELLA 211, 311, BREEZEWAY | HICKS, MICHAEL | CLOSED | 2014-06-03 | PCV PL: REPLACE TOILET TANK AND RESET TOILET IN APT 311 | 171E | CLOSED | 286.584 | 0 | 105.582 | 105.582
PJ0004948 Total | [7 empty] | 107924.8256 | 0 | 102293.2969 | 102293.2969
PJ0004947 | REMOVE CONCRETE BLOCK WALL - BLDG 021 - 135A | HICKS, MICHAEL | CLOSED | 2014-06-02 | AD: APC CONTRACTORS | 021 | CLOSED | 4670.55 | 0 | 4280 | 4280
PJ0004947 | REMOVE CONCRETE BLOCK WALL - BLDG 021 - 135A | HICKS, MICHAEL | CLOSED | 2014-06-02 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 597.81 | 0 | 0 | 0
PJ0004947 | REMOVE CONCRETE BLOCK WALL - BLDG 021 - 135A | HICKS, MICHAEL | CLOSED | 2014-06-02 | IN: REMOVE CONCRETE BLOCK WALL - BLDG 021 - 135A | 021 | CLOSED | 142.8449 | 0 | 64.056 | 64.056
PJ0004947 | REMOVE CONCRETE BLOCK WALL - BLDG 021 - 135A | HICKS, MICHAEL | CLOSED | 2014-06-02 | MO: ASSIST & RECEIVE REMOVED ROLL-UP DOOR (N/L) | 021 | CLOSED | 144.18 | 0 | 0 | 0
PJ0004947 Total | [7 empty] | 5555.3849 | 0 | 4344.056 | 4344.056
PJ0004946 | INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | NORTON, DAVE | CLOSED | 2014-05-13 | AD: MACDONALD DOOR | 081 | CLOSED | 2220.785 | 0 | 2190.2365 | 2190.2365
PJ0004946 | INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | NORTON, DAVE | CLOSED | 2014-05-13 | CA: INSTALL DOOR SIGNAGE | 081 | CLOSED | 310.9266 | 0 | 262.146 | 262.146
PJ0004946 | INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | NORTON, DAVE | CLOSED | 2014-05-13 | CP: PROJECT CONTINGENCY | 081 | CLOSED | 562.72 | 0 | 0 | 0
PJ0004946 | INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | NORTON, DAVE | CLOSED | 2014-05-13 | IN: INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | 081 | CLOSED | 128.112 | 0 | 102.672 | 102.672
PJ0004946 | INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | NORTON, DAVE | CLOSED | 2014-05-13 | LO: NEW LOCKSET & REINSTALL EXISTING | 081 | CLOSED | 1666.0297 | 0 | 919.668 | 919.668
PJ0004946 | INSTALL TWO NEW DOORS: BLDG 081 FRONT OFFICE & RM. 005 | NORTON, DAVE | CLOSED | 2014-05-13 | PA: PAINT TWO NEW DOORS RM 5 | 081 | CLOSED | 1224.8911 | 0 | 597.432 | 597.432
PJ0004946 Total | [7 empty] | 6113.4644 | 0 | 4072.1545 | 4072.1545
PJ0004944 | SR 14/15: RESTRIPE ROADS & PEDESTRIAN CROSSINGS - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2014-05-29 | AD: GOLDEN STATE SEALING & STRIPING | GENERAL | CLOSED | 10575.88 | 0 | 10575.1524 | 10575.1524
PJ0004944 | SR 14/15: RESTRIPE ROADS & PEDESTRIAN CROSSINGS - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2014-05-29 | AD: JOC 13.030.052 MAINO | GENERAL | CLOSED | 44724.5769 | 0 | 44724.5769 | 44724.5769
PJ0004944 | SR 14/15: RESTRIPE ROADS & PEDESTRIAN CROSSINGS - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2014-05-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1057.59 | 0 | 0 | 0
PJ0004944 | SR 14/15: RESTRIPE ROADS & PEDESTRIAN CROSSINGS - CAMPUS WIDE | NORTON, DAVE | CLOSED | 2014-05-29 | IN: RESTRIPE ROADS & PEDESTRIAN CROSSINGS - CAMPUS WIDE | GENERAL | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004944 Total | [7 empty] | 56422.1029 | 0 | 55331.7573 | 55331.7573
PJ0004943 | 2014 CATA FARM SHOW (JUNE 24) - FARM SHOP BLD 9 | POPHAM, DONALD J. | CLOSED | 2014-05-28 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0004943 | 2014 CATA FARM SHOW (JUNE 24) - FARM SHOP BLD 9 | POPHAM, DONALD J. | CLOSED | 2014-05-28 | EL: SUPPLY ELECTRICITY FOR CATA FARM SHOW - JUNE 23 | 009 | CLOSED | 0 | 0 | 471.912 | 471.912
PJ0004943 Total | [7 empty] | 0 | 0 | 471.912 | 471.912
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: BKM OFFICE ENVIRONMENTS | 045 | CLOSED | 5499.693 | 0 | 5499.693 | 5499.693
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: DESIGN FEES FOR STATE FIRE MARSHAL DOCUMENTS | 045 | CLOSED | 300 | 0 | 300 | 300
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: ENGLEKIRK AND SABOL | 045 | CLOSED | 642 | 0 | 535 | 535
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: ITS (FACEPLATE) | 045 | CLOSED | 454.75 | 0 | 53.5 | 53.5
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: JOC 14.033.036 MAINO | 045 | CLOSED | 67884.5343 | 0 | 49041.7166 | 49041.7166
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: STATE FIRE MARSHAL FEES | 045 | CLOSED | 1155.6 | 0 | 577.1687 | 577.1687
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: WALLACE GROUP | 045 | CLOSED | 6955 | 0 | 5788.7 | 5788.7
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | AD: WILLIAM-SCOTTSMAN | 045 | CLOSED | 48150 | 0 | 43076.274 | 43076.274
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | CA: BUILD SHELVES, MISC OTHER ITEMS | 045 | CLOSED | 4771.2204 | 0 | 11762.782 | 11762.782
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 7378.83 | 0 | 0 | 0
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | CPE: MANIPULATE EXISTING A/C UNIT TO ONLY RUN THE FAN | 045 | CLOSED | 628.32 | 0 | 473.364 | 473.364
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | CU: CLEAN VCT FLOOR | 045 | CLOSED | 567.1182 | 0 | 480.4518 | 480.4518
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | EL: ELECTRICAL PLUG RELOCATION | 045 | CLOSED | 8188.5622 | 0 | 3694.506 | 3694.506
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | EO: ROAD CREW (HOLD TILL END OF PROJECT) (N/L) | 045 | CLOSED | 685.8162 | 0 | 0 | 0
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | ES: ASSEMBLE PURCHASED FAN INSIDE TRAILER | 045 | CLOSED | 146.4307 | 0 | 608.772 | 608.772
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | IN: BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | 045 | CLOSED | 1100.6335 | 0 | 459.186 | 459.186
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | LA: PROVIDE SUPPORT AND REPLANTING AROUND NEW TRAILER | 045 | CLOSED | 4826.4192 | 0 | 1871.436 | 1871.436
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | LO: LOCKSET AND ADJUSTMENTS | 045 | CLOSED | 2525.0564 | 0 | 2831.43 | 2831.43
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | MO: ASSIST WITH BAND EQUIPMENT MOVE IN | 045 | CLOSED | 373.0331 | 0 | 101.412 | 101.412
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | PA: PAINTING TOUCH UP ON TRAILER OR INSIDE BUILDING | 045 | CLOSED | 1462.5815 | 0 | 894.384 | 894.384
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | PL: LOCATE UTILITIES ONSITE FOR BAND STORAGE TRAILER BEHIND 45 | 045 | CLOSED | 257.952 | 0 | 225.708 | 225.708
PJ0004942 | BAND STORAGE TRAILER BEHIND DAVIDSON MUSIC CENTER - 045 | DUNN, TRAVIS | CLOSED | 2014-04-23 | PL: PLUMBING SUPPORT FOR UNDERGROUND LOCATING | 045 | CLOSED | 286.9716 | 0 | 515.904 | 515.904
PJ0004942 Total | [7 empty] | 164240.5223 | 0 | 128791.3881 | 128791.3881
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | AD: CHARGEPOINT, INC. | GEN-PARK | CLOSED | 58249.9333 | 0 | 56856.7077 | 56856.7077
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | AD: COASTAL DEMO | GEN-PARK | CLOSED | 4494 | 0 | 865.63 | 865.63
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | AD: GOLDEN STATE SEALING | GEN-PARK | CLOSED | 5136 | 0 | 3023.82 | 3023.82
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | AD: PURCHASE BOLLARD COVERS | GEN-PARK | CLOSED | 542.928 | 0 | 542.928 | 542.928
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | AD: RICK TEIXEIRA WELDING | GEN-PARK | CLOSED | 1605 | 0 | 1605 | 1605
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | CA: FORM & POUR BASES FOR EVC STATIONS H-2 & ENGRAVE NAMEPLATES | GEN-PARK | CLOSED | 5562.247 | 0 | 3771.546 | 3771.546
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 9995.03 | 0 | 0 | 0
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | EL: ELECTRICAL CONDUITS, WIRING, & CONNECTION/INSTALL OF CHARGIN | GEN-PARK | CLOSED | 52162.3387 | 0 | 40679.514 | 40679.514
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | EO: TRENCH & BACKFILL FOR CONDUITS IN H-2 LOT | GEN-PARK | CLOSED | 8445.4846 | 0 | 6982.2 | 6982.2
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | IN: DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS-130 & H-2A | GEN-PARK | CLOSED | 855.1476 | 0 | 671.118 | 671.118
PJ0004941 | DESIGN/INSTALL ELECTRIC VEHICLE CHARGING STATIONS:PKG 130 & H-2A | HICKS, MICHAEL | CLOSED | 2014-04-22 | LA: REMOVAL AND REPLACEMENT OF LANDSCAPING AS NEEDED | GEN-PARK | CLOSED | 2981.4569 | 0 | 500.4 | 500.4
PJ0004941 Total | [7 empty] | 150029.566 | 0 | 115498.8637 | 115498.8637
PJ0004940 | INSTALL STORAGE RACKS AND MOVE BOXES ONTO NEW RACKS | MOLLAN, CHERYL L. | CLOSED | 2014-05-23 | CA:SUPPLY AND INSTALL NEW SHELVING UNITS PER PLAN BLD 21 RM 128A | 021 | CLOSED | 3580.6583 | 0 | 3137.34 | 3137.34
PJ0004940 | INSTALL STORAGE RACKS AND MOVE BOXES ONTO NEW RACKS | MOLLAN, CHERYL L. | CLOSED | 2014-05-23 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 468.86 | 0 | 0 | 0
PJ0004940 | INSTALL STORAGE RACKS AND MOVE BOXES ONTO NEW RACKS | MOLLAN, CHERYL L. | CLOSED | 2014-05-23 | EL:RELOCATE EXISTING LIGHT SWITCH, BLDG 21 RM 128A | 021 | CLOSED | 720.0024 | 0 | 259.68 | 259.68
PJ0004940 | INSTALL STORAGE RACKS AND MOVE BOXES ONTO NEW RACKS | MOLLAN, CHERYL L. | CLOSED | 2014-05-23 | IN: INSTALL STORAGE RACKS AND MOVE BOXES ONTO NEW RACKS | 021 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004940 | INSTALL STORAGE RACKS AND MOVE BOXES ONTO NEW RACKS | MOLLAN, CHERYL L. | CLOSED | 2014-05-23 | MO:MOVE BOXES FROM BLDG 34 ROOM 159B TO BLD 21 ROOM 128A | 021 | CLOSED | 324 | 0 | 126.756 | 126.756
PJ0004940 Total | [7 empty] | 5157.5767 | 0 | 3587.832 | 3587.832
PJ0004939 | REPLACE TWELVE COUNTER SINKS IN LOCKER ROOMS-117D & 118D | NORTON, DAVE | CLOSED | 2014-04-17 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 906.01 | 0 | 0 | 0
PJ0004939 | REPLACE TWELVE COUNTER SINKS IN LOCKER ROOMS-117D & 118D | NORTON, DAVE | CLOSED | 2014-04-17 | IN: REPLACE TWELVE COUNTER SINKS IN LOCKER ROOMS-117D & 118D | 043 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0004939 | REPLACE TWELVE COUNTER SINKS IN LOCKER ROOMS-117D & 118D | NORTON, DAVE | CLOSED | 2014-04-17 | PL: REPLACE SINKS | 043 | CLOSED | 8989.253 | 0 | 5248.152 | 5248.152
PJ0004939 Total | [7 empty] | 9965.907 | 0 | 5318.796 | 5318.796
PJ0004937 | REMOVE ROPES COURSE AND ALL RELATED INFRASTRUCTURE | LAMPMAN, GREG | CLOSED | 2014-04-21 | AD: JOC 13.031.004 MAINO | 125U | CLOSED | 22257.605 | 0 | 22257.605 | 22257.605
PJ0004937 | REMOVE ROPES COURSE AND ALL RELATED INFRASTRUCTURE | LAMPMAN, GREG | CLOSED | 2014-04-21 | CP: PROJECT CONTINGENCY | 125U | CLOSED | 2286.1 | 0 | 0 | 0
PJ0004937 | REMOVE ROPES COURSE AND ALL RELATED INFRASTRUCTURE | LAMPMAN, GREG | CLOSED | 2014-04-21 | IN: REMOVE ROPES COURSE AND ALL RELATED INFRASTRUCTURE | 125U | CLOSED | 64.056 | 0 | 67.35 | 67.35
PJ0004937 Total | [7 empty] | 24607.761 | 0 | 22324.955 | 22324.955
PJ0004931 | REMOVE, CLEAN, AND REINSTALL BASEBOARDS IN THE PAVILION - PAC 06 | LAMPMAN, GREG | CLOSED | 2014-05-20 | AD: WLH BUILDING | 006 | CLOSED | 1498 | 0 | 1498 | 1498
PJ0004931 | REMOVE, CLEAN, AND REINSTALL BASEBOARDS IN THE PAVILION - PAC 06 | LAMPMAN, GREG | CLOSED | 2014-05-20 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 156.21 | 0 | 0 | 0
PJ0004931 | REMOVE, CLEAN, AND REINSTALL BASEBOARDS IN THE PAVILION - PAC 06 | LAMPMAN, GREG | CLOSED | 2014-05-20 | IN:REMOVE, CLEAN, AND REINSTALL BASEBOARDS IN THE PAC 06 | 006 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004931 Total | [7 empty] | 1718.266 | 0 | 1530.028 | 1530.028
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | AD: STATE FIRE MARSHAL | 053A | CLOSED | 0 | 0 | 127.009 | 127.009
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | CA: PROVIDE GENERAL HEAVY MAINT. TO FACILITY | 053A | CLOSED | 18064.3974 | 0 | 13156.3031 | 13156.3031
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | CP: PROJECT CONTINGENCY | 053A | OPEN | 5540.52 | 0 | 0 | 0
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | EL: PROVIDE HEAVY MAINT. TO FACILITY FOR SAFETY REPAIRS | 053A | CLOSED | 21539.0957 | 0 | 22725.324 | 22725.324
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | ES: REPLACE ALL EVAP. COOLERS THAT HAVE REACHED END OF LIFE | 053A | CLOSED | 10676.5901 | 0 | 22836.348 | 22836.348
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | IN:SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | 053A | CLOSED | 1130.304 | 0 | 70.644 | 70.644
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | LO: PROVIDE MAINT. TO ALL DOOR HARDWARE | 053A | CLOSED | 511.1118 | 0 | 60.924 | 60.924
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | PM: SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | 053A | CLOSED | 0 | 0 | 0 | 0
PJ0004930 | SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | DUNN, TRAVIS | CONST_COMP | 2014-05-21 | SM: SR 14/15: GREENHOUSE SAFETY UPDATES, PHASE I - BLD 53A | 053A | OPEN | 0 | 0 | 0 | 0
PJ0004930 Total | [7 empty] | 57462.019 | 0 | 58976.5521 | 58976.5521
PJ0004929 | INSTALL COMPRESSOR - HANGAR SE COMPRESSOR SHED - BLD 004A | NORTON, DAVE | CLOSED | 2014-04-11 | CP: PROJECT CONTINGENCY | 004A | CLOSED | 428.7 | 0 | 0 | 0
PJ0004929 | INSTALL COMPRESSOR - HANGAR SE COMPRESSOR SHED - BLD 004A | NORTON, DAVE | CLOSED | 2014-04-11 | EL:- INSTALL COMPRESSOR | 004A | CLOSED | 2640.679 | 0 | 1808.964 | 1808.964
PJ0004929 | INSTALL COMPRESSOR - HANGAR SE COMPRESSOR SHED - BLD 004A | NORTON, DAVE | CLOSED | 2014-04-11 | IN: INSTALL COMPRESSOR - HANGAR SE COMPRESSOR SHED - BLD 004A | 004A | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004929 | INSTALL COMPRESSOR - HANGAR SE COMPRESSOR SHED - BLD 004A | NORTON, DAVE | CLOSED | 2014-04-11 | PL: INSTALL COMPRESSOR | 004A | CLOSED | 1282.8505 | 0 | 326.46 | 326.46
PJ0004929 Total | [7 empty] | 4416.2855 | 0 | 2199.48 | 2199.48
PJ0004928 | REMOVE FIXED TABLES AND WHEELED CHAIRS FROM RAISED FLOOR 38-121 | NORTON, DAVE | CLOSED | 2014-05-12 | CA: PATCH RAISED FLOOR AFTER REMOVAL OF ELECTRICAL- | 038 | CLOSED | 741.8532 | 0 | 584.178 | 584.178
PJ0004928 | REMOVE FIXED TABLES AND WHEELED CHAIRS FROM RAISED FLOOR 38-121 | NORTON, DAVE | CLOSED | 2014-05-12 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 318.28 | 0 | 0 | 0
PJ0004928 | REMOVE FIXED TABLES AND WHEELED CHAIRS FROM RAISED FLOOR 38-121 | NORTON, DAVE | CLOSED | 2014-05-12 | CU: CLEAN CARPET ON RAISED FLOOR - BLDG. 38 RM. 121 | 038 | CLOSED | 0 | 0 | 1231.605 | 1231.605
PJ0004928 | REMOVE FIXED TABLES AND WHEELED CHAIRS FROM RAISED FLOOR 38-121 | NORTON, DAVE | CLOSED | 2014-05-12 | EL: REMOVE ELECTRICAL ABOVE RAISED FLOOR | 038 | CLOSED | 3000.6838 | 0 | 1647.408 | 1647.408
PJ0004928 | REMOVE FIXED TABLES AND WHEELED CHAIRS FROM RAISED FLOOR 38-121 | NORTON, DAVE | CLOSED | 2014-05-12 | IN:REMOVE FIXED TABLES & WHEELED CHAIRS FROM RAISED FLOOR 38-121 | 038 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004928 | REMOVE FIXED TABLES AND WHEELED CHAIRS FROM RAISED FLOOR 38-121 | NORTON, DAVE | CLOSED | 2014-05-12 | MO: REMOVE STUDENT DESKS, CHAIRS AND INSTRUCTORS DESK | 038 | CLOSED | 721.224 | 0 | 371.214 | 371.214
PJ0004928 Total | [7 empty] | 4910.153 | 0 | 3962.517 | 3962.517
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | CA:INSTALL PLYWOOD FOR ADA MAT - JENSSEN STAD - 5/29 | 160 | CLOSED | 0 | 0 | 84.582 | 84.582
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | CU: SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES-5/30-6/2 | 160 | CLOSED | 0 | 0 | 6638.5599 | 6638.5599
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | EL: SUPPLY POWER FOR REGIONAL BASEBALL GAMES - MAY 29-JUNE 1 | 160 | CLOSED | 0 | 0 | 7337.544 | 7337.544
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | LA: CLAY PURCHASE FOR THE BASEBALL REGIONALS | 160 | CLOSED | 0 | 0 | 1252.8 | 1252.8
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | LA: SUPPORT FOR THE REGIONALS BASEBALL GAMES-MAY29-JUNE30 | 160 | CLOSED | 0 | 0 | 7605.153 | 7605.153
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | MOVE COPIER FROM SPANOS STADIUM TO JENSSEN FIELD PRESS TENT | 160 | CLOSED | 0 | 0 | 48.288 | 48.288
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | PERMIT: EVENT PERMIT FOR THE BASEBALL REGIONAL GAMES-5/29-6/2 | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0004927 | SUPPORT FOR BASEBALL REGIONAL PLAYOFF GAMES: MAY 30-JUNE1 | POPHAM, DONALD J. | CLOSED | 2014-05-19 | PL: CALL BACK WORK ORDER FOR BASEBALL REGIONALS - 5/29-6/2 | 160 | CLOSED | 0 | 0 | 245.136 | 245.136
PJ0004927 Total | [7 empty] | 0 | 0 | 23212.0629 | 23212.0629
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 4173 | 0 | 4173 | 4173
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | AD: STATE FIRE MARSHAL | 035 | CLOSED | 0 | 0 | 148.1736 | 148.1736
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 2035.31 | 0 | 0 | 0
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | EL: 2ND FLOOR LIBRARY SHOWCASE AREA | 035 | CLOSED | 1447.4627 | 0 | 4750.53 | 4750.53
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | ES:INSTALL SUPPLY AIR INTO 4 GLASS STUDY ROOMS | 035 | CLOSED | 2653.8854 | 0 | 4466.16 | 4466.16
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | IN: SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | 035 | CLOSED | 282.576 | 0 | 388.542 | 388.542
PJ0004925 | SECOND FLOOR IMPROVEMENTS - EAST SIDE ABOVE FRONT ENTRANCE | BRENNAN, MICHAEL | CLOSED | 2014-05-13 | PA: PAINT SOFFET - 2ND FLOOR LIBRARY ABOVE FRONT ENTRANCE | 035 | CLOSED | 1252.5815 | 0 | 435.6 | 435.6
PJ0004925 Total | [7 empty] | 11844.8156 | 0 | 14362.0056 | 14362.0056
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | AD: JOC 16.037.004.00 MAINO | 013 | CLOSED | 178213.4862 | 0 | 178213.4862 | 178213.4862
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | AD: JOC 16.037.004.01 MAINO | 013 | CLOSED | 8173.409 | 0 | 8173.409 | 8173.409
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | AD: P-CARD PURCHASE (CONTRACTS) | 013 | CLOSED | 19080.24 | 0 | 19138.899 | 19138.899
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | AD: RRM DESIGN GROUP | 013 | CLOSED | 22358.72 | 0 | 22358.934 | 22358.934
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | CP: PROJECT CONTINGENCY | 013 | OPEN | 0.11 | 0 | 0 | 0
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | EL:ASSESS EXISTING SYSTEM TO VERIFY POC FOR NEW EL OUTLETS LIGHT | 013 | CLOSED | 418.782 | 0 | 96.642 | 96.642
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | EL:INSTALL ELECTRICAL PER PLAN BLDG 13 COURTYARD | 013 | CLOSED | 18097.1609 | 0 | 18419.0535 | 18419.0535
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | IN: BUILDING 13 COURTYARD UPGRADE | 013 | CLOSED | 1130.304 | 0 | 1130.304 | 1130.304
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | LA:PROVIDE CONTRACTOR SUPPORT FOR BLDG 13 COURTYARD | 013 | CLOSED | 420.336 | 0 | 428.4765 | 428.4765
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | MO:MOVE FURNITURE FOR COURTYARD | 013 | CLOSED | 670.32 | 0 | 48 | 48
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | PL:CONTRACTOR SUPPORT- ID DRAINS- BLD 13 COURTYARD | 013 | CLOSED | 257.952 | 0 | 128.976 | 128.976
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | PM: ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0004924 | ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | MOLLAN, CHERYL L. | CONST_COMP | 2014-05-08 | SM: ENGINEERING 13 COURTYARD UPGRADE - BLDG 13 | 013 | OPEN | 0 | 0 | 0 | 0
PJ0004924 Total | [7 empty] | 248820.8201 | 0 | 248136.1802 | 248136.1802
PJ0004921 | SR 13/14: DISTRIBUTION SERVICES SIGNAGE | LAMPMAN, GREG | CLOSED | 2014-05-12 | CA: DISTRIBUTION SERVICES SIGNAGE FOR BUILDINGS 70 AND 82 | 070 | CLOSED | 4049.2376 | 0 | 3623.874 | 3623.874
PJ0004921 | SR 13/14: DISTRIBUTION SERVICES SIGNAGE | LAMPMAN, GREG | CLOSED | 2014-05-12 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 417.73 | 0 | 0 | 0
PJ0004921 | SR 13/14: DISTRIBUTION SERVICES SIGNAGE | LAMPMAN, GREG | CLOSED | 2014-05-12 | IN: SR 13/14: DISTRIBUTION SERVICES SIGNAGE | 070 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004921 Total | [7 empty] | 4595.0796 | 0 | 3687.93 | 3687.93
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | AD: PEAK BICYCLE RACKS | 192 | CLOSED | 5350 | 0 | 5240 | 5240
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | CA: INSTALLATION OF 8 BIKE RACKS AT BLDG 192 | 192 | CLOSED | 1231.751 | 0 | 1040.785 | 1040.785
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 734.82 | 0 | 0 | 0
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | EO: REMOVE METAL RAILING UNDER STAIRS AT EAST END OF BLDG 192 | 192 | CLOSED | 95.4663 | 0 | 342.48 | 342.48
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | IN: DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192 | 192 | CLOSED | 0 | 0 | 58.87 | 58.87
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | LA: PLANNTING UNDER STAIR LANDING - EAST END OF BLDG 192 | 192 | CLOSED | 546.904 | 0 | 101.25 | 101.25
PJ0004920 | DESIGN AND CONSTRUCT NEW BIKE PAD AT E. END ENGR IV - 192(MAINT) | HICKS, MICHAEL | CLOSED | 2014-05-09 | MO:MOVE CONCRETE TABLE AND TRASH/RECYCLE BIN AT EAST END 192 | 192 | CLOSED | 124.2885 | 0 | 28.17 | 28.17
PJ0004920 Total | [7 empty] | 8083.2298 | 0 | 6811.555 | 6811.555
PJ0004919 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 34 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | CA: FIRE SAFETY CORRECTIONS - BLD 34 | 034 | CLOSED | 0 | 0 | 187.96 | 187.96
PJ0004919 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 34 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0004919 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 34 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | EL: FIRE SAFETY CORRECTIONS - BLD 34 | 034 | CLOSED | 0 | 0 | 278.9677 | 278.9677
PJ0004919 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 34 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | IN: FIRE SAFETY CORRECTIONS - BLD 34 | 034 | CLOSED | 0 | 0 | 53.38 | 53.38
PJ0004919 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 34 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | LO: FIRE SAFETY CORRECTIONS - BLD 34 | 034 | CLOSED | 0 | 0 | 169.295 | 169.295
PJ0004919 Total | [7 empty] | 0 | 0 | 689.6027 | 689.6027
PJ0004918 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 05 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | CA: FIRE SAFETY CORRECTIONS - BLD 05 | 005 | CLOSED | 751.84 | 0 | 96.3 | 96.3
PJ0004918 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 05 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | CP: PROJECT CONTINGNECY | 005 | CLOSED | 0 | 0 | 0 | 0
PJ0004918 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 05 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | EL: FIRE SAFETY CORRECTIONS - BLD 05 | 005 | CLOSED | 0 | 0 | 215.4359 | 215.4359
PJ0004918 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 05 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | ES: FIRE SAFETY CORRECTIONS - BLD 05 | 005 | CLOSED | 0 | 0 | 208.12 | 208.12
PJ0004918 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES - BLD 05 (MAINT) | POLVI, STEVEN | CLOSED | 2014-05-07 | LO: FIRE SAFETY CORRECTIONS - BLD 05 | 005 | CLOSED | 0 | 0 | 266.035 | 266.035
PJ0004918 Total | [7 empty] | 751.84 | 0 | 785.8909 | 785.8909
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | AD: COASTAL DEMO | 002 | CLOSED | 321 | 0 | 479.36 | 479.36
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | AD: JOC 15.036.002.00 STAPLES | 002 | CLOSED | 14490.796 | 0 | 14490.796 | 14490.796
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | AD: MCKENNA | 002 | CLOSED | 4445.85 | 0 | 2509.15 | 2509.15
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | CA: DEMO PLASTER ON PIPE CHASE | 002 | CLOSED | 222.48 | 0 | 269.172 | 269.172
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 1639.88 | 0 | 0 | 0
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | CU: WAX FLOOR - 002-019 | 002 | CLOSED | 66.984 | 0 | 74.2941 | 74.2941
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | EL: WALL RE-CONSTRUCTION | 002 | CLOSED | 635.424 | 0 | 904.35 | 904.35
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | EO: ASSIST WITH DRAINAGE INSTALL OUTSIDE BLDG. 02 RM. 19 | 002 | CLOSED | 0 | 0 | 138.456 | 138.456
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | IN: SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | 002 | CLOSED | 565.152 | 0 | 282.576 | 282.576
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | LA: DEVELOP DRAINAGE SWAILS OUTSIDE BLDG 02 RM 19 | 002 | CLOSED | 3314.5699 | 0 | 1807.235 | 1807.235
PJ0004916 | SR 14/15: REPAIR/REMEDIATE WATER DAMAGE - BLD 02 RM 19 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-05-07 | PL: DI & PIPE TO STORM DRAIN OUTSIDE BLDG. 02 RM. 19 | 002 | CLOSED | 7919.04 | 0 | 5296.7933 | 5296.7933
PJ0004916 Total | [7 empty] | 33621.1759 | 0 | 26252.1824 | 26252.1824
PJ0004914 | SR 14/15: REPAIR ROOF LEAK & REPAIR/ADD GUTTER - OH PLANT SHOP | NORTON, DAVE | CLOSED | 2014-05-06 | AD: QUAGLINO ROOFING | 048 | CLOSED | 2840.85 | 0 | 2840.85 | 2840.85
PJ0004914 | SR 14/15: REPAIR ROOF LEAK & REPAIR/ADD GUTTER - OH PLANT SHOP | NORTON, DAVE | CLOSED | 2014-05-06 | CA: ROOF & CEILING REPAIRS - POLY PLANT SHOP OFFICE- BLDG. 48 | 048 | CLOSED | 3109.8299 | 0 | 6913.5474 | 6913.5474
PJ0004914 | SR 14/15: REPAIR ROOF LEAK & REPAIR/ADD GUTTER - OH PLANT SHOP | NORTON, DAVE | CLOSED | 2014-05-06 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 763.65 | 0 | 0 | 0
PJ0004914 | SR 14/15: REPAIR ROOF LEAK & REPAIR/ADD GUTTER - OH PLANT SHOP | NORTON, DAVE | CLOSED | 2014-05-06 | IN: REPAIR ROOF LEAK & REPAIR/ADD GUTTER - OH PLANT SHOP | 048 | CLOSED | 192.168 | 0 | 134.7 | 134.7
PJ0004914 | SR 14/15: REPAIR ROOF LEAK & REPAIR/ADD GUTTER - OH PLANT SHOP | NORTON, DAVE | CLOSED | 2014-05-06 | PA: PAINTING AFTER REPAIRS AT POLY PLANT SHOP OFFICE - BLDG. 48 | 048 | CLOSED | 1321.4426 | 0 | 1484.1 | 1484.1
PJ0004914 Total | [7 empty] | 8227.9405 | 0 | 11373.1974 | 11373.1974
PJ0004913 | STOREFRONT INSTALLATION - SIERRA MADRE & YOSEMITE MAIN LOUNGES | MCNALLY, CURTIS | CLOSED | 2014-04-30 | AD: JOC 14.033.029 MAINO | RESIDENCE | CLOSED | 38725.7075 | 0 | 38429.7027 | 38429.7027
PJ0004913 | STOREFRONT INSTALLATION - SIERRA MADRE & YOSEMITE MAIN LOUNGES | MCNALLY, CURTIS | CLOSED | 2014-04-30 | AD: STATE FIRE MARSHAL | RESIDENCE | CLOSED | 0 | 0 | 614.8755 | 614.8755
PJ0004913 | STOREFRONT INSTALLATION - SIERRA MADRE & YOSEMITE MAIN LOUNGES | MCNALLY, CURTIS | CLOSED | 2014-04-30 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 10.64 | 0 | 0 | 0
PJ0004913 | STOREFRONT INSTALLATION - SIERRA MADRE & YOSEMITE MAIN LOUNGES | MCNALLY, CURTIS | CLOSED | 2014-04-30 | IN: STOREFRONT INSTALL - SIERRA MADRE & YOSEMITE MAIN LOUNGE | RESIDENCE | CLOSED | 565.152 | 0 | 105.966 | 105.966
PJ0004913 | STOREFRONT INSTALLATION - SIERRA MADRE & YOSEMITE MAIN LOUNGES | MCNALLY, CURTIS | CLOSED | 2014-04-30 | LO:INSTALL PANIC HARDWARE AT 2 LOCATIONS | RESIDENCE | CLOSED | 5167.392 | 0 | 7742.466 | 7742.466
PJ0004913 Total | [7 empty] | 44468.8915 | 0 | 46893.0102 | 46893.0102
PJ0004911 | 2014 ANNUAL WON FIREGUARD FIRE DOOR MAINT - 6 ELEVATOR DRS - PAC | GRIFFIN, PATRICK E. | CLOSED | 2014-05-02 | AD: WON DOOR | 006 | CLOSED | 810 | 0 | 810 | 810
PJ0004911 | 2014 ANNUAL WON FIREGUARD FIRE DOOR MAINT - 6 ELEVATOR DRS - PAC | GRIFFIN, PATRICK E. | CLOSED | 2014-05-02 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 86.67 | 0 | 0 | 0
PJ0004911 Total | [7 empty] | 896.67 | 0 | 810 | 810
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | AD: APC CONTRACTORS | 002 | CLOSED | 4066 | 0 | 4001.8 | 4001.8
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | AD: J.L. FASULO DRYWALL | 002 | CLOSED | 4285.35 | 0 | 2836.57 | 2836.57
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | AD: MCKENNA ENVIRONMENTAL | 002 | CLOSED | 1260.46 | 0 | 413.02 | 413.02
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | AD: SANTA MARIA ACOUSTICAL | 002 | CLOSED | 850.65 | 0 | 850.65 | 850.65
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | CA: WALL REMOVAL BETWEEN ROOMS 13A & 14 IN BUILDING 02 | 002 | CLOSED | 615.678 | 0 | 288.48 | 288.48
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 81.44 | 0 | 0 | 0
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 002 | CLOSED | 60 | 0 | 25.2 | 25.2
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | IN: REMOVE WALL BETWEEN 02-13A AND 02-14. | 002 | CLOSED | 256.224 | 0 | 160.14 | 160.14
PJ0004910 | REMOVE WALL BETWEEN 02-13A AND 02-14. | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | PA: PAINT ROOM EDUCATION ROOM 14 AND PATCHES | 002 | CLOSED | 882.5094 | 0 | 796.368 | 796.368
PJ0004910 Total | [7 empty] | 12358.3114 | 0 | 9372.228 | 9372.228
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | AD: FLOOR CONNECTION | 005 | CLOSED | 665.754 | 0 | 591.71 | 591.71
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | AD: JOC 15.036.018 STAPLES | 005 | CLOSED | 11905.4299 | 0 | 11905.4299 | 11905.4299
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | AD: MCKENNA ENVIRONMENTAL | 005 | CLOSED | 3694.71 | 0 | 3033.45 | 3033.45
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | AD: STATE FIRE MARSHAL FEES | 005 | CLOSED | 0 | 0 | 301.9968 | 301.9968
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 1919.23 | 0 | 0 | 0
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | CU:WAX NEWLY ABATED CONCRETE FLOOR ARCH BLD 5, RM 302, 302A | 005 | CLOSED | 1790.7289 | 0 | 279.9504 | 279.9504
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | EH&S:TESTS FOR HAZARDOUS MATERIAL BLDG 5 RM 302, 302A | 005 | CLOSED | 188.736 | 0 | 0 | 0
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | IN: REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | 005 | CLOSED | 141.288 | 0 | 105.966 | 105.966
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | MO: MOVE LAB DESKS OUT OF ARCH BLD 5 ROOM 302, 302A FOR ABATEMEN | 005 | CLOSED | 804.384 | 0 | 48 | 48
PJ0004909 | REMOVE WATER DAMAGED CARPET - BLDG. 5 RM. 302 | MOLLAN, CHERYL L. | CLOSED | 2014-03-04 | PM: REMOVE WATER DAMAGED CARPET-BLDG. 5 RM. 302 | 005 | CLOSED | 0 | 0 | 0 | 0
PJ0004909 Total | [7 empty] | 21110.2608 | 0 | 16266.5031 | 16266.5031
PJ0004906 | 3 MAIL SORTING CABINETS FOR NEW DISTRIBUTION SVCS LOCATION | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-03 | AD: MORRO BAY CABINETS | 082 | CLOSED | 6621.588 | 0 | 6621.588 | 6621.588
PJ0004906 | 3 MAIL SORTING CABINETS FOR NEW DISTRIBUTION SVCS LOCATION | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-03 | CA: INSTALL MAIL SLOT CABINETS AT NEW DISTRIBUTION SVCS LOCATION | 082 | CLOSED | 631.104 | 0 | 454.428 | 454.428
PJ0004906 | 3 MAIL SORTING CABINETS FOR NEW DISTRIBUTION SVCS LOCATION | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-03 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 774.64 | 0 | 0 | 0
PJ0004906 | 3 MAIL SORTING CABINETS FOR NEW DISTRIBUTION SVCS LOCATION | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-03 | IN: FABRICATION OF 3 MAIL SORTING CABINETS - BLDG. 82 | 082 | CLOSED | 256.224 | 0 | 160.14 | 160.14
PJ0004906 Total | [7 empty] | 8283.556 | 0 | 7236.156 | 7236.156
PJ0004904 | ASSESS CONDITION - ARCH VILLAGE STRUCTURES 95 (MAINT) | MCNALLY, CURTIS | CLOSED | 2014-04-21 | CP: PROJECT CONTINGENCY | 095 | CLOSED | 0 | 0 | 0 | 0
PJ0004904 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0004903 | SP 14/15: REMOVE PODS FROM ARCHITECTURAL VILLAGE - 95 | MCNALLY, CURTIS | CLOSED | 2014-04-21 | AD: BOB'S CRANE SERVICE | 095 | CLOSED | 642 | 0 | 2059.75 | 2059.75
PJ0004903 | SP 14/15: REMOVE PODS FROM ARCHITECTURAL VILLAGE - 95 | MCNALLY, CURTIS | CLOSED | 2014-04-21 | CA:REMOVE FENCE | 095 | CLOSED | 1604.2703 | 0 | 112.776 | 112.776
PJ0004903 | SP 14/15: REMOVE PODS FROM ARCHITECTURAL VILLAGE - 95 | MCNALLY, CURTIS | CLOSED | 2014-04-21 | CP: PROJECT CONTINGENCY | 095 | CLOSED | 327.76 | 0 | 0 | 0
PJ0004903 | SP 14/15: REMOVE PODS FROM ARCHITECTURAL VILLAGE - 95 | MCNALLY, CURTIS | CLOSED | 2014-04-21 | EO:CLEAN SITE | 095 | CLOSED | 461.4498 | 0 | 99.528 | 99.528
PJ0004903 | SP 14/15: REMOVE PODS FROM ARCHITECTURAL VILLAGE - 95 | MCNALLY, CURTIS | CLOSED | 2014-04-21 | IN: SP 14/15: REMOVE PODS FROM ARCHITECTURAL VILLAGE - 95 | 095 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004903 Total | [7 empty] | 3163.5921 | 0 | 2400.166 | 2400.166
PJ0004902 | SR 14/15: REPLACE COLLAPSED SEWER LINE ON CA BLVD | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | AD: G.F. GARCIA AND SONS | GENERAL | CLOSED | 20330 | 0 | 20185.55 | 20185.55
PJ0004902 | SR 14/15: REPLACE COLLAPSED SEWER LINE ON CA BLVD | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2311.88 | 0 | 0 | 0
PJ0004902 | SR 14/15: REPLACE COLLAPSED SEWER LINE ON CA BLVD | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | IN: SR 14/15: REPLACE COLLAPSED SEWER LINE ON CA BLVD | GENERAL | CLOSED | 256.224 | 0 | 198.756 | 198.756
PJ0004902 | SR 14/15: REPLACE COLLAPSED SEWER LINE ON CA BLVD | GONZALES, ALBERT M. | CLOSED | 2014-04-28 | PL: ASSIST CONTRACTOR WITH SEWER LINE REPAIR | GENERAL | CLOSED | 1462.8505 | 0 | 424.398 | 424.398
PJ0004902 Total | [7 empty] | 24360.9545 | 0 | 20808.704 | 20808.704
PJ0004901 | ADDITIONS TO DOOR ACCESS SYSTEM - BLD 180 (NO OVERHEAD) | JUDD, PERRY | CLOSED | 2014-04-24 | AD: JOC 13.029.001 MAINO (NO OVERHEAD) | 180 | CLOSED | 9409.28 | 0 | 9409.28 | 9409.28
PJ0004901 | ADDITIONS TO DOOR ACCESS SYSTEM - BLD 180 (NO OVERHEAD) | JUDD, PERRY | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 0 | 0 | 0 | 0
PJ0004901 Total | [7 empty] | 9409.28 | 0 | 9409.28 | 9409.28
PJ0004900 | SR 14/15: CONSTRUCT NEW PATH TO SIDEWALK & ROAD - BLDG 46T | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: JOC MAINO 13.030.053 | 046T-M028 | CLOSED | 52728.7654 | 0 | 52728.7654 | 52728.7654
PJ0004900 | SR 14/15: CONSTRUCT NEW PATH TO SIDEWALK & ROAD - BLDG 46T | LAMPMAN, GREG | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 046T-M028 | CLOSED | 5298.5 | 0 | 0 | 0
PJ0004900 | SR 14/15: CONSTRUCT NEW PATH TO SIDEWALK & ROAD - BLDG 46T | LAMPMAN, GREG | CLOSED | 2014-04-24 | IN: 14/15: CONSTRUCT NEW PATH TO SIDEWALK & ROAD - BLDG 46T | 046T-M028 | CLOSED | 256.224 | 0 | 448.392 | 448.392
PJ0004900 Total | [7 empty] | 58283.4894 | 0 | 53177.1574 | 53177.1574
PJ0004899 | SR 14/15: REDESIGN INTERSECTION AT VILLAGE DR. AND TRUCKEE | NORTON, DAVE | CLOSED | 2014-04-24 | AD: ASAP REPROGRAPHICS | STREETS | CLOSED | 0 | 0 | 37.2681 | 37.2681
PJ0004899 | SR 14/15: REDESIGN INTERSECTION AT VILLAGE DR. AND TRUCKEE | NORTON, DAVE | CLOSED | 2014-04-24 | AD: NORTH COAST ENGINEERING | STREETS | CLOSED | 61865.26 | 0 | 57042.77 | 57042.77
PJ0004899 | SR 14/15: REDESIGN INTERSECTION AT VILLAGE DR. AND TRUCKEE | NORTON, DAVE | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 6235.98 | 0 | 0 | 0
PJ0004899 | SR 14/15: REDESIGN INTERSECTION AT VILLAGE DR. AND TRUCKEE | NORTON, DAVE | CLOSED | 2014-04-24 | IN: SR 14/15: REDESIGN INTERSECTION AT VILLAGE DR. AND TRUCKEE | STREETS | CLOSED | 494.508 | 0 | 70.644 | 70.644
PJ0004899 Total | [7 empty] | 68595.748 | 0 | 57150.6821 | 57150.6821
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | AD: KI FURNITURE | 003 | CLOSED | 118068.6043 | 0 | 118010.9206 | 118010.9206
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | AD: STATE FIRE MARSHAL FEES | 003 | CLOSED | 577.8 | 0 | 95.2514 | 95.2514
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 12644.9 | 0 | 0 | 0
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | CU: PROVIDE CLEAN UP DURING & AFTER CONSTRUCTION | 003 | CLOSED | 596.4925 | 0 | 527.8656 | 527.8656
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 003 | CLOSED | 0 | 0 | 33.6 | 33.6
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | IN: SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | 003 | CLOSED | 314.3658 | 0 | 282.576 | 282.576
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | LO:PROVIDE CONSTRUCTION CORE FOR CONTRACTOR | 003 | CLOSED | 243.696 | 0 | 60.924 | 60.924
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | MO: ASSIST WITH MOVING IN NEW SEATING | 003 | CLOSED | 402.192 | 0 | 208.458 | 208.458
PJ0004898 | SR 14/15: REPLACE AUDITORIUM SEATING - BLDG 03 RM 213 | HICKS, MICHAEL | CLOSED | 2014-04-24 | PA: PAINTING STAIR TREAD ADA STRIP & RISER FACES | 003 | CLOSED | 10667.1943 | 0 | 1832.694 | 1832.694
PJ0004898 Total | [7 empty] | 143515.2449 | 0 | 121052.2896 | 121052.2896
PJ0004897 | PRESSURE WASH HARDSCAPE - BLD 3 COURTYARD | LOOSLEY, SCOTT L. | CLOSED | 2014-04-24 | AD: COASTAL JANITORIAL | 003 | CLOSED | 411.95 | 0 | 411.95 | 411.95
PJ0004897 | PRESSURE WASH HARDSCAPE - BLD 3 COURTYARD | LOOSLEY, SCOTT L. | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 41.2 | 0 | 0 | 0
PJ0004897 Total | [7 empty] | 453.15 | 0 | 411.95 | 411.95
PJ0004894 | SR 14/15: ASBESTOS ABATEMENT IN MECHANICAL RM - ADMIN 01 RM 126 | BRENNAN, MICHAEL | CLOSED | 2014-04-24 | AD: APC CONTRACTORS | 001 | CLOSED | 7490 | 0 | 5708.45 | 5708.45
PJ0004894 | SR 14/15: ASBESTOS ABATEMENT IN MECHANICAL RM - ADMIN 01 RM 126 | BRENNAN, MICHAEL | CLOSED | 2014-04-24 | AD: MCKENNA ENVIRONMENTAL | 001 | CLOSED | 3846.65 | 0 | 3338.4 | 3338.4
PJ0004894 | SR 14/15: ASBESTOS ABATEMENT IN MECHANICAL RM - ADMIN 01 RM 126 | BRENNAN, MICHAEL | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1387.99 | 0 | 0 | 0
PJ0004894 | SR 14/15: ASBESTOS ABATEMENT IN MECHANICAL RM - ADMIN 01 RM 126 | BRENNAN, MICHAEL | CLOSED | 2014-04-24 | ES:SUPPOR FOR ABATEMENT | 001 | CLOSED | 1894.9127 | 0 | 263.832 | 263.832
PJ0004894 | SR 14/15: ASBESTOS ABATEMENT IN MECHANICAL RM - ADMIN 01 RM 126 | BRENNAN, MICHAEL | CLOSED | 2014-04-24 | IN: ASBESTOS ABATEMENT IN MECHANICAL RM - ADMIN 01 RM 126 | 001 | CLOSED | 142.8449 | 0 | 96.084 | 96.084
PJ0004894 Total | [7 empty] | 14762.3976 | 0 | 9406.766 | 9406.766
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: ASAP REPROGRAPHICS | 045 | CLOSED | 0 | 0 | 304.5541 | 304.5541
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: ENGLEKIRK AND SABOL | 045 | CLOSED | 1275.4186 | 0 | 1191.98 | 1191.98
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: GOSS ENGINEERING | 045 | OPEN | 21983.7064 | 2846.2 | 19383.05 | 22229.25
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: JOC MAINO 16-037.011.00 | 045 | CLOSED | 49039.0416 | 0 | 54287.1669 | 54287.1669
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: MCKENNA | 045 | CLOSED | 1474.46 | 0 | 1457.34 | 1457.34
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: ONTRAC SHIPPING | 045 | CLOSED | 0 | 0 | 67.0248 | 67.0248
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | AD: STATE FIRE MARSHAL | 045 | OPEN | 0 | 0 | 706.9918 | 706.9918
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | CP: PROJECT CONTINGENCY | 045 | OPEN | 5334.9 | 0 | 0 | 0
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | EL: ELECTRICAL SUPPORT | 045 | CLOSED | 708.708 | 0 | 199.728 | 199.728
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | ES: HVAC TRADE SUPPORT | 045 | CLOSED | 1444.608 | 0 | 1880.64 | 1880.64
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | IN: SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | 045 | CLOSED | 0 | 0 | 317.898 | 317.898
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | PM: SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | 045 | CLOSED | 0 | 0 | 0 | 0
PJ0004893 | SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | NORTON, DAVE | CONST_COMP | 2014-04-24 | SM: SR 14/15: RENOVATE HVAC FOR SCENE SHOP - BLD 45 RM 206 | 045 | OPEN | 0 | 0 | 0 | 0
PJ0004893 Total | [7 empty] | 81260.8426 | 2846.2 | 79796.3736 | 82642.5736
PJ0004892 | SR 14/15: PIPE REMOVAL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: JOC 15.036.003 STAPLES | 034 | CLOSED | 29671.6457 | 0 | 29671.6457 | 29671.6457
PJ0004892 | SR 14/15: PIPE REMOVAL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: MCKENNA | 034 | CLOSED | 6436.05 | 0 | 5457 | 5457
PJ0004892 | SR 14/15: PIPE REMOVAL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 3345.28 | 0 | 0 | 0
PJ0004892 | SR 14/15: PIPE REMOVAL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | ES: RELOCATE PNEUMATIC PIPING | 034 | CLOSED | 836.64 | 0 | 2436.108 | 2436.108
PJ0004892 | SR 14/15: PIPE REMOVAL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | IN:SR 14/15: PIPE RMVL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | 034 | CLOSED | 211.932 | 0 | 211.932 | 211.932
PJ0004892 | SR 14/15: PIPE REMOVAL, DUCT REPAIR, ASBESTOS CLEAN-UP -34 ATTIC | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | LO: ORANGE CORE 34-228A | 034 | CLOSED | 121.848 | 0 | 30.462 | 30.462
PJ0004892 Total | [7 empty] | 40623.3957 | 0 | 37807.1477 | 37807.1477
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: GOSS ENGINEERING | 046 | CLOSED | 8132 | 0 | 8132 | 8132
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: JOC 15.036.006 STAPLES | 046 | CLOSED | 131343.1955 | 0 | 130349.2618 | 130349.2618
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: MCKENNA | 046 | CLOSED | 5606.8 | 0 | 3488.2 | 3488.2
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: MEATHEAD MOVERS | 046 | CLOSED | 1158.81 | 0 | 1158.81 | 1158.81
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | AD: OBSESSION ENTERTAINMENT | 046 | CLOSED | 2514.928 | 0 | 2514.928 | 2514.928
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | CA: BARRACADE DOOR OPENING - ASSIST STAFF MOVE | 046 | CLOSED | 504.96 | 0 | 562.692 | 562.692
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 4385.76 | 0 | 0 | 0
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | CU: CLEAN CARPET | 046 | CLOSED | 1071.744 | 0 | 1371.9414 | 1371.9414
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 046 | CLOSED | 0 | 0 | 27.6 | 27.6
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | EL: PROVIDE SERVICE IN BLDG 26 ROOMS FOR TEMP OCCUPANCY FOR POLY | 046 | CLOSED | 386.568 | 0 | 96.642 | 96.642
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | ES: SUPPORT FOR CONTRACTOR DUCT RETROFIT. | 046 | CLOSED | 919.296 | 0 | 131.328 | 131.328
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | IN: SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | 046 | CLOSED | 1271.592 | 0 | 494.508 | 494.508
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | LO: CHANGE CORE IN HALL DOOR - BLD 26 RMS 110J & 110K | 046 | CLOSED | 0 | 0 | 30.462 | 30.462
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | LO: PROVIDE ORANGE CORE TO ROOM 100 & UPPER FLOOR | 046 | CLOSED | 243.696 | 0 | 182.772 | 182.772
PJ0004891 | SR 14/15: REMOVE LEAD FROM HVAC DUCTWORK - BLDG 46 | KUENTZEL, DOUGLAS A. | CLOSED | 2014-04-24 | MO: ASSIST MOVING THE SERVICE DEST TO BLDG 26 AND BACK AGAIN | 046 | CLOSED | 1340.64 | 0 | 135.216 | 135.216
PJ0004891 Total | [7 empty] | 158879.9895 | 0 | 148676.3612 | 148676.3612
PJ0004890 | SR 14/15: REPAIR/RESURFACE AREA BEHIND LABS - BLDG 8A | NORTON, DAVE | CLOSED | 2014-02-28 | AD: JOC 13.030.038 MAINO | 008A | CLOSED | 69732.4564 | 0 | 69807.3564 | 69807.3564
PJ0004890 | SR 14/15: REPAIR/RESURFACE AREA BEHIND LABS - BLDG 8A | NORTON, DAVE | CLOSED | 2014-02-28 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 5593.3 | 0 | 0 | 0
PJ0004890 | SR 14/15: REPAIR/RESURFACE AREA BEHIND LABS - BLDG 8A | NORTON, DAVE | CLOSED | 2014-02-28 | IN: SR 14/15: REPAIR/RESURFACE AREA BEHIND LABS - BLDG 8A | 008A | CLOSED | 64.056 | 0 | 224.196 | 224.196
PJ0004890 Total | [7 empty] | 75389.8124 | 0 | 70031.5524 | 70031.5524
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | AD: FLUID RESOURCE MGMT | GENERAL | OPEN | 9095 | 0 | 7361.6 | 7361.6
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | AD: SUN PACIFIC (?) | GENERAL | OPEN | 6634 | 0 | 0 | 0
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 2075.92 | 0 | 0 | 0
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | EL: SUPPORT FOR REPAIRS AND UPGRADES OF LIFT STATIONS | GENERAL | CLOSED | 900.0036 | 0 | 1195.896 | 1195.896
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | IN: SR 14/15: REPLACE MT. BISHOP LIFT STATION | GENERAL | ASSIGNED | 256.224 | 0 | 64.056 | 64.056
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | PL: REPLACE PUMP AND BRACE CONTROL PANEL AT PARKER LIFT STATION | GENERAL | OPEN | 3988.5544 | 0 | 1044.756 | 1044.756
PJ0004889 | SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GONZALES, ALBERT | IN_CONSTR | 2014-04-24 | SM: SR 14/15: REPLACE MT. BISHOP LIFT STATION CONTROLS BOX | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0004889 Total | [7 empty] | 22949.702 | 0 | 9666.308 | 9666.308
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: CAME SECURITY | 001 | CLOSED | 4734.75 | 0 | 6955 | 6955
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: ITS | 001 | CLOSED | 0 | 0 | 240.75 | 240.75
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: JOC 14.033.009 MAINO | 001 | CLOSED | 6985.9658 | 0 | 6985.9658 | 6985.9658
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: JOC 15.035.002 MAINO | 001 | CLOSED | 581363.421 | 0 | 581363.421 | 581363.421
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: MAINO LVPW | 001 | CLOSED | 2337.95 | 0 | 2337.95 | 2337.95
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: MCKENNA | 001 | CLOSED | 57876.3 | 0 | 20276.5 | 20276.5
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 535 | 0 | 6087.0588 | 6087.0588
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | AD: WAREHOUSE MATERIALS USED BY PROJECT MANAGER | 001 | CLOSED | 240 | 0 | 75.0422 | 75.0422
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | ANTS: PROGRAMMING FOR ADMIN FIRE ALARM UPGRADE | 001 | CLOSED | 406.656 | 0 | 847.2 | 847.2
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | CP: PROJECT CONTINGENCY | 001 | OPEN | 53645.89 | 0 | 0 | 0
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | EL: PROJECT SUPPORT FOR FIRE ALARM | 001 | CLOSED | 802.2504 | 0 | 827.904 | 827.904
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | ES: CONTRACTOR SUPPORT FOR ADMIN FIRE ALARM SYSTEM UPGRADE | 001 | CLOSED | 1575.936 | 0 | 1858.998 | 1858.998
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | IN: SR 14/15: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | 001 | CLOSED | 320.28 | 0 | 311.31 | 311.31
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | PA: TOUCH-UP FOR FIRE ALARM PROJECT AT ADMIN 01 | 001 | CLOSED | 1838.16 | 0 | 1436.28 | 1436.28
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | PM: DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0004887 | DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | DILLON, JEFFREY | CONST_COMP | 2014-04-24 | SM: DM 15/16: UPGRADE EMERGENCY FIRE ALARM SYSTEM - ADMN 01 | 001 | OPEN | 0 | 0 | 0 | 0
PJ0004887 Total | [7 empty] | 712662.5592 | 0 | 629603.3798 | 629603.3798
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | AD: BOBS CRANE | U-UDOR | CLOSED | 1070 | 0 | 294.25 | 294.25
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | AD: HPS MECHANICAL | U-UDOR | CLOSED | 10700 | 0 | 6760.26 | 6760.26
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | CA: PREP & CAULK UTILIDOR LIDS AFTER REPAIRS | U-UDOR | CLOSED | 1485.6102 | 0 | 579.7822 | 579.7822
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 1778.31 | 0 | 0 | 0
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | CPE: PROVIDE SUPPORT UTILIDOR VALVE REPLACEMENT - BLDG 2, 3 & 21 | U-UDOR | CLOSED | 2922.7046 | 0 | 5921.442 | 5921.442
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | ES: PROVIDE SUPPORT FOR UTILIDOR VALVE REPLACEMENT - ZONE 5 | U-UDOR | CLOSED | 1169.4758 | 0 | 2915.898 | 2915.898
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | IN: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | U-UDOR | CLOSED | 314.3658 | 0 | 317.898 | 317.898
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | LA: PROVIDE SUPPORT FOR UTILIDOR VALVE REPLACEMENT AT BLDG 03 | U-UDOR | CLOSED | 1012.9699 | 0 | 0 | 0
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | PA: PAINT BOLLARD FOR BLDG 03 UTILIDOR RUNOUT VALVE VAULT | U-UDOR | CLOSED | 153.816 | 0 | 61.908 | 61.908
PJ0004886 | SR 14/15: NEW VAULT & VALVES - BLDG 3 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | PL: PROVIDE SUPPORT FOR UTILIDOR VALVE REPALCEMENT | U-UDOR | CLOSED | 286.9716 | 0 | 357.912 | 357.912
PJ0004886 Total | [7 empty] | 20894.224 | 0 | 17209.3502 | 17209.3502
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: BOB'S CRANE | U-UDOR | CLOSED | 1177 | 0 | 1177 | 1177
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: BUEHLER AND BUEHLER | U-UDOR | CLOSED | 8346 | 0 | 8346 | 8346
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: CARPENTER RIGGING BAKERSFIELD | U-UDOR | CLOSED | 0 | 0 | 6831.44 | 6831.44
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: EARTH SYSTEMS PACIFIC | U-UDOR | CLOSED | 1212.31 | 0 | 502.365 | 502.365
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: FACILITIES PLANNING DESIGN FEES | U-UDOR | CLOSED | 642 | 0 | 642 | 642
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: JOC 14.034.026 MAINO | U-UDOR | CLOSED | 251431.4783 | 0 | 251431.4783 | 251431.4783
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | CA: CUT CAULKING AND RE-CAULK UTILITY LIDS | U-UDOR | CLOSED | 1857.1518 | 0 | 2254.146 | 2254.146
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 22762.67 | 0 | 0 | 0
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | CPE: REMOVE UTILITY LIDS AT VALVES (UTILDOR) | U-UDOR | CLOSED | 2484.7258 | 0 | 656.64 | 656.64
PJ0004885 | SR 14/15: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | LAMPMAN, GREG | CLOSED | 2014-04-24 | IN: INSTALL SPRING ASSIST DOORS/QUARTERING VALVES-UTILIDOR | U-UDOR | CLOSED | 1200.948 | 0 | 529.83 | 529.83
PJ0004885 Total | [7 empty] | 291114.2839 | 0 | 272370.8993 | 272370.8993
PJ0004884 | SR 14/15: BANK STABILIZATION - REPLACE BRIDGE - PARKER RANCH | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: JOC 13.031.020.00 MAINO | 122V | CLOSED | 288694.7633 | 0 | 288694.7633 | 288694.7633
PJ0004884 | SR 14/15: BANK STABILIZATION - REPLACE BRIDGE - PARKER RANCH | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: SWCA | 122V | CLOSED | 36218.43 | 0 | 7913.185 | 7913.185
PJ0004884 | SR 14/15: BANK STABILIZATION - REPLACE BRIDGE - PARKER RANCH | LAMPMAN, GREG | CLOSED | 2014-04-24 | AD: WALLACE GROUP | 122V | CLOSED | 13375 | 0 | 15459.36 | 15459.36
PJ0004884 | SR 14/15: BANK STABILIZATION - REPLACE BRIDGE - PARKER RANCH | LAMPMAN, GREG | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | 122V | CLOSED | 33854.44 | 0 | 0 | 0
PJ0004884 | SR 14/15: BANK STABILIZATION - REPLACE BRIDGE - PARKER RANCH | LAMPMAN, GREG | CLOSED | 2014-04-24 | IN: BANK STABILIZATION - REPLACE BRIDGE - PARKER RANCH | 122V | CLOSED | 256.224 | 0 | 512.448 | 512.448
PJ0004884 Total | [7 empty] | 372398.8573 | 0 | 312579.7563 | 312579.7563
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | AD: BOBS CRANE | U-UDOR | CLOSED | 3424 | 0 | 2648.25 | 2648.25
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | AD: G.F. GARCIA & SONS | U-UDOR | CLOSED | 42800 | 0 | 32463.8 | 32463.8
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | CA: PREP UTILIDOR LIDS TO PULL & SEAL LIDS AFTER REMOVAL | U-UDOR | CLOSED | 2536.2024 | 0 | 1333.4446 | 1333.4446
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 5598.89 | 0 | 0 | 0
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | ES: REMOVE LIDS FOR INSPECTION OF EXISITNG CONDITIONS | U-UDOR | CLOSED | 292.2048 | 0 | 1543.104 | 1543.104
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | IN: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | U-UDOR | CLOSED | 314.3658 | 0 | 317.898 | 317.898
PJ0004883 | SR 14/15: NEW VALVE BOX, VALVES, & RUN-OUT - BLDG 2 - UTILIDOR | KOLEGRAFF, KENNETH | CLOSED | 2014-04-24 | PL: Provide Support, mark utilities | U-UDOR | CLOSED | 286.9716 | 0 | 2525.724 | 2525.724
PJ0004883 Total | [7 empty] | 55252.6346 | 0 | 40832.2206 | 40832.2206
PJ0004882 | INSTALL VENTILATION TO SUPPORT LIQUID OPERATIONS IN 41-207 | BRENNAN, MICHAEL | CLOSED | 2014-04-17 | AD: JOHN WRIGHT CONSTRUCTION | 041A | CLOSED | 4066 | 0 | 3877.1771 | 3877.1771
PJ0004882 | INSTALL VENTILATION TO SUPPORT LIQUID OPERATIONS IN 41-207 | BRENNAN, MICHAEL | CLOSED | 2014-04-17 | CP: PROJECT CONTINGENCY | 041A | CLOSED | 498.65 | 0 | 0 | 0
PJ0004882 | INSTALL VENTILATION TO SUPPORT LIQUID OPERATIONS IN 41-207 | BRENNAN, MICHAEL | CLOSED | 2014-04-17 | IN: INSTALL VENTILATION TO SUPPORT LIQUID OPERATIONS IN 41-207 | 041A | CLOSED | 71.1022 | 0 | 64.056 | 64.056
PJ0004882 | INSTALL VENTILATION TO SUPPORT LIQUID OPERATIONS IN 41-207 | BRENNAN, MICHAEL | CLOSED | 2014-04-17 | LO: PROVIDE BOX AND LOCKSET | 041A | CLOSED | 849.4381 | 0 | 634.644 | 634.644
PJ0004882 Total | [7 empty] | 5485.1903 | 0 | 4575.8771 | 4575.8771
PJ0004881 | INSTALL CARPET RUNNER BETWEEN CUBICLES IN 01-218C | NORTON, DAVE | CLOSED | 2014-04-18 | AD: FLOOR CONNECTION | 001 | CLOSED | 1602.86 | 0 | 1602.86 | 1602.86
PJ0004881 | INSTALL CARPET RUNNER BETWEEN CUBICLES IN 01-218C | NORTON, DAVE | CLOSED | 2014-04-18 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 173.25 | 0 | 0 | 0
PJ0004881 | INSTALL CARPET RUNNER BETWEEN CUBICLES IN 01-218C | NORTON, DAVE | CLOSED | 2014-04-18 | IN: INSTALL CARPET RUNNER BETWEEN CUBICLES IN 01-218C | 001 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004881 Total | [7 empty] | 1840.166 | 0 | 1666.916 | 1666.916
PJ0004879 | WATER DAMAGE REMEDIATION FROM LEAKING HOSE - BLD 180 RM 542 | GRIFFIN, PATRICK E. | CLOSED | 2014-04-18 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 0 | 0 | 0 | 0
PJ0004879 | WATER DAMAGE REMEDIATION FROM LEAKING HOSE - BLD 180 RM 542 | GRIFFIN, PATRICK E. | CLOSED | 2014-04-18 | PA:TAPE, MUD, PRIME, AND PAINT REPAIRED WALLS AT CFS 542 | 180 | CLOSED | 0 | 0 | 618.375 | 618.375
PJ0004879 | WATER DAMAGE REMEDIATION FROM LEAKING HOSE - BLD 180 RM 542 | GRIFFIN, PATRICK E. | CLOSED | 2014-04-18 | WATER DAMAGE REMEDIATION BUILDING 180 ROOM 542 CENTER FOR SCI. | 180 | CLOSED | 0 | 0 | 712.41 | 712.41
PJ0004879 Total | [7 empty] | 0 | 0 | 1330.785 | 1330.785
PJ0004878 | INSTALL DISPLAY CASE - BLDG 11 FROM NEAR RM 224 TO NEAR RM 217 | MCNALLY, CURTIS | CLOSED | 2014-03-11 | CA: Provide and install new aluminum display cabinet | 011 | CLOSED | 871.509 | 0 | 678.84 | 678.84
PJ0004878 | INSTALL DISPLAY CASE - BLDG 11 FROM NEAR RM 224 TO NEAR RM 217 | MCNALLY, CURTIS | CLOSED | 2014-03-11 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 94.22 | 0 | 0 | 0
PJ0004878 | INSTALL DISPLAY CASE - BLDG 11 FROM NEAR RM 224 TO NEAR RM 217 | MCNALLY, CURTIS | CLOSED | 2014-03-11 | IN: INSTALL DISPLAY CASE - BLDG 11 FROM NEAR RM 217 | 011 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0004878 Total | [7 empty] | 1036.373 | 0 | 749.484 | 749.484
PJ0004875 | WINDOW CLEANING AT BLDG. 26 | HICKS, MICHAEL | CLOSED | 2014-03-26 | AD: COASTAL JANITORIAL | 026 | CLOSED | 592.78 | 0 | 592.78 | 592.78
PJ0004875 | WINDOW CLEANING AT BLDG. 26 | HICKS, MICHAEL | CLOSED | 2014-03-26 | CA: CLOSE TALL WINDOWS ON ALL FLOORS FOR WINDOW WASHING -26 #162 | 026 | CLOSED | 112.776 | 0 | 105.642 | 105.642
PJ0004875 | WINDOW CLEANING AT BLDG. 26 | HICKS, MICHAEL | CLOSED | 2014-03-26 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 96.23 | 0 | 0 | 0
PJ0004875 | WINDOW CLEANING AT BLDG. 26 | HICKS, MICHAEL | CLOSED | 2014-03-26 | IN: WINDOW CLEANING AT BLDG. 26 (WAS BRICK STRUCTURE REMOVAL) | 026 | CLOSED | 71.1022 | 0 | 32.028 | 32.028
PJ0004875 Total | [7 empty] | 872.8882 | 0 | 730.45 | 730.45
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | AD: ELECTRICRAFT | GENERAL | CLOSED | 224.7 | 0 | 1240.5259 | 1240.5259
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | AD: ENGLEKIRK AND SABOL | GENERAL | CLOSED | 535 | 0 | 535 | 535
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | AD: THOMA ELECTRIC | GENERAL | CLOSED | 535 | 0 | 1186.5765 | 1186.5765
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | CA: MAKE SIGN | GENERAL | CLOSED | 111.24 | 0 | 222.48 | 222.48
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 35.85 | 0 | 0 | 0
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | EL:INSPECTION OF TWO PANNELS. | GENERAL | CLOSED | 2465.4007 | 0 | 732.252 | 732.252
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | IN: INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | GENERAL | CLOSED | 192.168 | 0 | 128.112 | 128.112
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | LO: SUPPLY ONE PAD LOCK FOR EL PANEL | GENERAL | CLOSED | 121.848 | 0 | 20 | 20
PJ0004870 | INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | DUNN, TRAVIS | CLOSED | 2014-04-07 | PM: INSTALL 21-PANEL SOLAR PV ARRAYS ON BLDGS. 8 AND 20 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004870 Total | [7 empty] | 4221.2067 | 0 | 4064.9464 | 4064.9464
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | CA: CREATE 10 - 1X1X1.5 BOXES FOR GREEN&GOLD | 042R | CLOSED | 0 | 0 | 1263.252 | 1263.252
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | CA: REMOVE GLASS AND INSTALL PLEXIGLAS AT SW ENTR. -MOTT (MAINT) | 042 | CLOSED | 0 | 0 | 271.165 | 271.165
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | CP: PROJECT CONTINGENCY | 042R | CLOSED | 0 | 0 | 0 | 0
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | CU: SUPPORT FOR GREEN & GOLD EVENT - 5/2 | 042R | CLOSED | 0 | 0 | 1560.678 | 1560.678
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | EL: ELECTRICIAN SUPPORT FOR GREEN & GOLD - APR29-MAY3 | 042R | CLOSED | 0 | 0 | 1230.24 | 1230.24
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | ES: PLEASE HAVE ONE BSE WORK STANDY FOR GREEN & GOLD EVENT - MAY | 042R | CLOSED | 0 | 0 | 478.086 | 478.086
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | LA: SUPPORT FOR GREEN & GOLD EVENT - 5/2 | 042R | CLOSED | 0 | 0 | 77.928 | 77.928
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | PA: PAINT BOXES FOR GREEN & GOLD TRUSS - MOTT GYM | 042R | CLOSED | 0 | 0 | 367.416 | 367.416
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | PL: PM MEN'S AND WOMEN'S RRS FOR MAY 2 BANQUET-MOTT GYM (MAINT) | 042R | CLOSED | 0 | 0 | 326.46 | 326.46
PJ0004868 | SUPPORT FOR 2014 EVENING OF GREEN AND GOLD - MAY 2, 2014 | POPHAM, DONALD J. | CLOSED | 2014-04-08 | TR: CALLBACK FOR MECHANIC - 5/2 | 042R | CLOSED | 0 | 0 | 204.234 | 204.234
PJ0004868 Total | [7 empty] | 0 | 0 | 5779.459 | 5779.459
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | AD: ASAP REPROGRAPHICS | 065 | CLOSED | 0 | 0 | 220.464 | 220.464
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | AD: ENGLEKIRK AND SABOL | 065 | CLOSED | 1424.17 | 0 | 1424.17 | 1424.17
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | AD: ONTRAC SHIPPING | 065 | CLOSED | 0 | 0 | 32.41 | 32.41
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | AD: PMSM ARCHITECTS | 065 | CLOSED | 33036.25 | 0 | 33036.25 | 33036.25
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 535 | 0 | 0 | 0
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 141.02 | 0 | 0 | 0
PJ0004867 | DESIGN NEW SALAD BAR (THE RED RADISH) INSIDE CIAO! | NORTON, DAVE | CLOSED | 2014-04-09 | IN: DESIGN NEW SALAD BAR INSIDE CIAO! | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004867 Total | [7 empty] | 35264.552 | 0 | 34841.406 | 34841.406
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: B&H PHOTO-VIDEO-PRO AUDIO | 007 | CLOSED | 1992.2009 | 0 | 1992.2009 | 1992.2009
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: CHAPMAN A/V SYSTEMS | 007 | CLOSED | 5189.5 | 0 | 4761.5 | 4761.5
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: DIGITAL NETWORK GROUP, INC | 007 | CLOSED | 199650.23 | 0 | 195055.1792 | 195055.1792
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: FLOOR CONNECTION | 007 | CLOSED | 2434.25 | 0 | 1706.65 | 1706.65
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: J.L. FASULO | 007 | CLOSED | 4895.25 | 0 | 4072.42 | 4072.42
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: MCMASTER-CARR - PURCHASE DOOR TO BE INSTALLED BY CONTRACTOR | 007 | CLOSED | 179.2999 | 0 | 179.2999 | 179.2999
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: PRO-CARD CUSTOMER AV PURCHASES | 007 | CLOSED | 7219.2793 | 0 | 8969.8314 | 8969.8314
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: PUGLIESE INTERIOR STYEMS, INC. | 007 | CLOSED | 6313 | 0 | 6121.47 | 6121.47
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: SANTA MARIA ACOUSTICAL | 007 | CLOSED | 5076.08 | 0 | 5076.08 | 5076.08
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: THE SIGN PLACE (PODIUM LECTURN) | 007 | CLOSED | 2140 | 0 | 374.0613 | 374.0613
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | AD: ULINE (LADDER PURCHASE FOR CLIENT) | 007 | CLOSED | 350.3822 | 0 | 350.3822 | 350.3822
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | CA: SUPPORT & ASSIST W/MISC PICK UP ITEMS | 007 | CLOSED | 3780.6282 | 0 | 3292.182 | 3292.182
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 4692.09 | 0 | 0 | 0
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | EL: POWER TO PROJECTOR/CONDUIT PATHWAYS | 007 | CLOSED | 5177.127 | 0 | 7134.522 | 7134.522
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | EL: PROVIDE PLUG IN PROJECTOR SPACE | 007 | CLOSED | 2960.0339 | 0 | 852.696 | 852.696
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | ES:EVALUATE REMOTE TEMP SENSOR FOR SOFFIT | 007 | CLOSED | 1743.0451 | 0 | 1316.304 | 1316.304
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | IN: UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | 007 | CLOSED | 570.739 | 0 | 275.988 | 275.988
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | ITS: INSTALL & WIRE WEBCAMS | 007 | CLOSED | 3210 | 0 | 1888.6142 | 1888.6142
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | ITS: TELECOM AND DATA LINES FOR KECK LAB UPGRADE | 007 | CLOSED | 0 | 0 | 948.35 | 948.35
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | LO: | 007 | CLOSED | 965.544 | 0 | 638.028 | 638.028
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | MO: REMOVAL OF SURPLUS AV EQUIPMENT | 007 | CLOSED | 298.2924 | 0 | 42.255 | 42.255
PJ0004866 | UPGRADE MULTIMEDIA FOR THE KECK LAB BLDG 07 RM 002 | BRENNAN, MICHAEL | CLOSED | 2014-03-20 | PA: PAINTING TOUCH UP AT SOFFIT | 007 | CLOSED | 1342.5815 | 0 | 372.57 | 372.57
PJ0004866 Total | [7 empty] | 260179.5533 | 0 | 245420.5841 | 245420.5841
PJ0004865 | SMART ROOM RETROFIT - BLD 26 RM 303 | MOLLAN, CHERYL L. | CLOSED | 2014-03-21 | AD: APC CONTRACTORS | 026 | CLOSED | 344.0478 | 0 | 344.0478 | 344.0478
PJ0004865 | SMART ROOM RETROFIT - BLD 26 RM 303 | MOLLAN, CHERYL L. | CLOSED | 2014-03-21 | AD: MORELAND THOMPSON, INC. | 026 | CLOSED | 3852 | 0 | 3852 | 3852
PJ0004865 | SMART ROOM RETROFIT - BLD 26 RM 303 | MOLLAN, CHERYL L. | CLOSED | 2014-03-21 | CA:SUPPLY AND INSTALL NEW 12' SCREEN BOARD BLDG 26, RM 303 | 026 | CLOSED | 373.5173 | 0 | 344.73 | 344.73
PJ0004865 | SMART ROOM RETROFIT - BLD 26 RM 303 | MOLLAN, CHERYL L. | CLOSED | 2014-03-21 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 115.89 | 0 | 0 | 0
PJ0004865 | SMART ROOM RETROFIT - BLD 26 RM 303 | MOLLAN, CHERYL L. | CLOSED | 2014-03-21 | IN: SMART ROOM RETROFIT - BLD 26 RM 303 | 026 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004865 | SMART ROOM RETROFIT - BLD 26 RM 303 | MOLLAN, CHERYL L. | CLOSED | 2014-03-21 | PA:PAINT SCREEN BOARD FABRICATED BY CARPENTER SHOP | 026 | CLOSED | 178.092 | 0 | 59.364 | 59.364
PJ0004865 Total | [7 empty] | 4991.6591 | 0 | 4728.2538 | 4728.2538
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | AD: JOC 13.031.040 MAINO | 017 | CLOSED | 25258.3344 | 0 | 25258.3344 | 25258.3344
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | AD: PROJECT COORDINATION FEE | 017 | CLOSED | 2015.88 | 0 | 2015.88 | 2015.88
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 47.91 | 0 | 0 | 0
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | CPE: REPAIRS TO EXISTING COOLERS | 017 | CLOSED | 7085.7 | 0 | 9986.946 | 9986.946
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | EL: INSTALL ELECTRICAL TO (2) WALK IN COOLERS | 017 | CLOSED | 7540.7573 | 0 | 4872.096 | 4872.096
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | IN: CREATE DRAIN FOR COOLERS - BLDG. 017 CROPS | 017 | CLOSED | 256.224 | 0 | 452.598 | 452.598
PJ0004864 | CREATE 2 NEW COOLERS WITH SEWER HOOKUPS - BLDG. 017 CROPS | LAMPMAN, GREG | CLOSED | 2014-03-04 | PM: CREATE DRAIN FOR COOLERS - BLDG. 017 CROPS | 017 | CLOSED | 0 | 0 | 0 | 0
PJ0004864 Total | [7 empty] | 42204.8057 | 0 | 42585.8544 | 42585.8544
PJ0004859 | MODIFY BUILDING SIGNAGE: MOTT 042 | GONZALES, ALBERT M. | CLOSED | 2014-01-28 | AD: THE SIGN PLACE | 042 | CLOSED | 4280 | 0 | 3710.7065 | 3710.7065
PJ0004859 | MODIFY BUILDING SIGNAGE: MOTT 042 | GONZALES, ALBERT M. | CLOSED | 2014-01-28 | CA: ASSIST SIGN PLACE | 042 | CLOSED | 525.018 | 0 | 556.2 | 556.2
PJ0004859 | MODIFY BUILDING SIGNAGE: MOTT 042 | GONZALES, ALBERT M. | CLOSED | 2014-01-28 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 668.58 | 0 | 0 | 0
PJ0004859 | MODIFY BUILDING SIGNAGE: MOTT 042 | GONZALES, ALBERT M. | CLOSED | 2014-01-28 | IN: MODIFY BUILDING SIGNAGE: MOTT 042 | 042 | CLOSED | 282.576 | 0 | 176.61 | 176.61
PJ0004859 | MODIFY BUILDING SIGNAGE: MOTT 042 | GONZALES, ALBERT M. | CLOSED | 2014-01-28 | PA: PATCH AND PAINT HOLES FROM PREVIOUS SIGN(S) | 042 | CLOSED | 580.9812 | 0 | 557.172 | 557.172
PJ0004859 Total | [7 empty] | 6337.1552 | 0 | 5000.6885 | 5000.6885
PJ0004857 | SP 13/14: CLEAR ROOM FOR BOOK COLLECTION - BLD 52 E03 | MCNALLY, CURTIS | CLOSED | 2014-03-27 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 361.63 | 361.63
PJ0004857 | SP 13/14: CLEAR ROOM FOR BOOK COLLECTION - BLD 52 E03 | MCNALLY, CURTIS | CLOSED | 2014-03-27 | CA: REMOVE LAB TABLES AND CABINETS UNDER WINDOWS | 052 | CLOSED | 2247.9767 | 0 | 1218.498 | 1218.498
PJ0004857 | SP 13/14: CLEAR ROOM FOR BOOK COLLECTION - BLD 52 E03 | MCNALLY, CURTIS | CLOSED | 2014-03-27 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 1010.27 | 0 | 0 | 0
PJ0004857 | SP 13/14: CLEAR ROOM FOR BOOK COLLECTION - BLD 52 E03 | MCNALLY, CURTIS | CLOSED | 2014-03-27 | EL: REMOVE ALL ELECTRICAL DEVICES AND CONDIUT FROM LAB TABLES | 052 | CLOSED | 2520.6838 | 0 | 1973.1 | 1973.1
PJ0004857 | SP 13/14: CLEAR ROOM FOR BOOK COLLECTION - BLD 52 E03 | MCNALLY, CURTIS | CLOSED | 2014-03-27 | IN: REMOVE OVERHEAD CABINETS & SHELVING - BLD 52 E04/E05 | 052 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004857 | SP 13/14: CLEAR ROOM FOR BOOK COLLECTION - BLD 52 E03 | MCNALLY, CURTIS | CLOSED | 2014-03-27 | PL: DISCONNECT AND REMOVE ALL PIPING UNDER LAB TABLES | 052 | CLOSED | 3285.0481 | 0 | 2168.5118 | 2168.5118
PJ0004857 Total | [7 empty] | 9192.0906 | 0 | 5753.7678 | 5753.7678
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | AD: BKM | 001 | CLOSED | 2642.1189 | 0 | 2642.1189 | 2642.1189
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | AD: ITS DATA | 001 | CLOSED | 64.2 | 0 | 62.3275 | 62.3275
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | AD: STATE FIRE MARSHAL FEES | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | CA: SIGNAGE FOR HR OFFICE REMODEL | 001 | CLOSED | 274.728 | 0 | 65.715 | 65.715
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 3.91 | 0 | 0 | 0
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | EL: NEW WORKSTATION AND POSSIBLY RELOCATE RECEPTACLE | 001 | CLOSED | 128.856 | 0 | 363.096 | 363.096
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | IN: REMDL HUMAN RESOURCES OFFS - BLDG 01, RMS. 110, 112, & 129A | 001 | CLOSED | 141.288 | 0 | 70.644 | 70.644
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | MO:MOVE REFRIG AND TABLES | 001 | CLOSED | 268.128 | 0 | 96 | 96
PJ0004854 | REMODEL HUMAN RESOURCES OFFICES - BLDG 01, RMS. 110, 112, & 129A | DILLON, JEFFREY | CLOSED | 2014-03-03 | PM: REMODEL HUMAN RESOURCES OFFICES-BLDG 1, RMS 110, 112, & 129A | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0004854 Total | [7 empty] | 3523.2289 | 0 | 3299.9014 | 3299.9014
PJ0004852 | ELECTRICAL LINES WITH TWO ELECTRICAL SOCKETS - 192 ROOF | NORTON, DAVE | CLOSED | 2014-02-12 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 252.86 | 0 | 0 | 0
PJ0004852 | ELECTRICAL LINES WITH TWO ELECTRICAL SOCKETS - 192 ROOF | NORTON, DAVE | CLOSED | 2014-02-12 | EL: ELECTRICAL AND CONDUIT FOR NWETWORK CABLE TO ANTENNA- ROOF- | 192 | CLOSED | 2400.6802 | 0 | 1881.84 | 1881.84
PJ0004852 | ELECTRICAL LINES WITH TWO ELECTRICAL SOCKETS - 192 ROOF | NORTON, DAVE | CLOSED | 2014-02-12 | IN: BUILDING INSPECTION | 192 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004852 Total | [7 empty] | 2781.6522 | 0 | 2009.952 | 2009.952
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: APC CONTRACTORS | 002 | CLOSED | 5328.6 | 0 | 5328.6 | 5328.6
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: FLOOR CONNECTION | 002 | CLOSED | 4042.246 | 0 | 4042.246 | 4042.246
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: J.L. FASULO DRYWALL | 002 | CLOSED | 3055.0747 | 0 | 3049.5 | 3049.5
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: MCKENNA ENVIRONMENTAL | 002 | CLOSED | 1260.46 | 0 | 1260.46 | 1260.46
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: MORELAND THOMPSON | 002 | CLOSED | 411.95 | 0 | 411.95 | 411.95
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: SANTA MARIA ACOUSTICAL | 002 | CLOSED | 1770.85 | 0 | 1770.85 | 1770.85
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | AD: STATE FIRE MARSHAL FEES | 002 | CLOSED | 0 | 0 | 964.33 | 964.33
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 002 | CLOSED | 240 | 0 | 40.8 | 40.8
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | IN: PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | 002 | CLOSED | 256.224 | 0 | 234.078 | 234.078
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | LO: EDUCATION 02-10 OFFICES | 002 | CLOSED | 558.2958 | 0 | 58.044 | 58.044
PJ0004851 | PREPARE OFFICES FOR STAFF OCCUPANCY - BLDG. 02, RMS. 9A & 10 | GONZALES, ALBERT M. | CLOSED | 2014-03-17 | PA: PAINT ROOM 10 | 002 | CLOSED | 1825.6124 | 0 | 1117.824 | 1117.824
PJ0004851 Total | [7 empty] | 18749.3129 | 0 | 18278.682 | 18278.682
PJ0004850 | RENOVATE PRESIDENT'S SUITE: NEW CABINETS, TABLES & BEV STATION | GONZALES, ALBERT M. | CLOSED | 2014-03-05 | AD: MORRO BAY CABINETS | 061 | CLOSED | 47098.7036 | 0 | 47098.7036 | 47098.7036
PJ0004850 | RENOVATE PRESIDENT'S SUITE: NEW CABINETS, TABLES & BEV STATION | GONZALES, ALBERT M. | CLOSED | 2014-03-05 | AD: STATE FIRE MARSHAL FEES | 061 | CLOSED | 0 | 0 | 964.33 | 964.33
PJ0004850 | RENOVATE PRESIDENT'S SUITE: NEW CABINETS, TABLES & BEV STATION | GONZALES, ALBERT M. | CLOSED | 2014-03-05 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 3683.62 | 0 | 0 | 0
PJ0004850 | RENOVATE PRESIDENT'S SUITE: NEW CABINETS, TABLES & BEV STATION | GONZALES, ALBERT M. | CLOSED | 2014-03-05 | PL: RECONNECT SINK AND FAUCET | 061 | CLOSED | 321.168 | 0 | 346.896 | 346.896
PJ0004850 Total | [7 empty] | 51103.4916 | 0 | 48409.9296 | 48409.9296
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | AD: CAME SECURITY | 021 | CLOSED | 2996 | 0 | 2086.5 | 2086.5
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | AD: MACDONALD DOORS | 021 | CLOSED | 5928.228 | 0 | 5230.695 | 5230.695
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | AD: MORELAND THOMPSON, INC.(CXL) | 021 | CLOSED | 351.5485 | 0 | 0 | 0
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | AD: SPECTRUM COLOR IMAGES | 021 | CLOSED | 249.9948 | 0 | 110.21 | 110.21
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | ANTS: ART STORAGE SUPPORT | 021 | CLOSED | 271.104 | 0 | 135.552 | 135.552
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | CA: CAMPUS ART STORAGE | 021 | CLOSED | 15684.7487 | 0 | 16012.266 | 16012.266
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 182.86 | 0 | 0 | 0
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | IN: PREP SPACE TO STORE CAMPUS ART COLLECTION | 021 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | LO: LOCK SHOP SUPPORT FOR ART STORAGE MOVE | 021 | CLOSED | 387.7339 | 0 | 84.924 | 84.924
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | MO: MOVE ART FROM BLDGS 26 & 35 TO NEW LOCATION - BLDG 21 RM 129 | 021 | CLOSED | 4826.304 | 0 | 687.348 | 687.348
PJ0004849 | PREP SPACE TO STORE CAMPUS ART COLLECTION - BLD 21 RM 129 | GONZALES, ALBERT M. | CLOSED | 2014-01-30 | PL: PARTS SUPPORT FOR ART STORAGE | 021 | CLOSED | 557.952 | 0 | 70.692 | 70.692
PJ0004849 Total | [7 empty] | 31564.5859 | 0 | 24450.215 | 24450.215
PJ0004846 | SMARTROOM UPGRADE 186-A101 | MOLLAN, CHERYL L. | CLOSED | 2014-03-05 | AD: SANTA MARIA ACOUSTICAL | 186 | CLOSED | 4836.4 | 0 | 4836.4 | 4836.4
PJ0004846 | SMARTROOM UPGRADE 186-A101 | MOLLAN, CHERYL L. | CLOSED | 2014-03-05 | AD: STATE FIRE MARSHAL FEES | 186 | CLOSED | 0 | 0 | 237.95 | 237.95
PJ0004846 | SMARTROOM UPGRADE 186-A101 | MOLLAN, CHERYL L. | CLOSED | 2014-03-05 | AD: US MARKERBOARD | 186 | CLOSED | 746.2822 | 0 | 746.2822 | 746.2822
PJ0004846 | SMARTROOM UPGRADE 186-A101 | MOLLAN, CHERYL L. | CLOSED | 2014-03-05 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 637.58 | 0 | 0 | 0
PJ0004846 | SMARTROOM UPGRADE 186-A101 | MOLLAN, CHERYL L. | CLOSED | 2014-03-05 | EL:INSTALL NEW ELECTRICAL FOR PROJECTOR SCRE / RELOCATE E STROBE | 186 | CLOSED | 2400.6814 | 0 | 1605.288 | 1605.288
PJ0004846 | SMARTROOM UPGRADE 186-A101 | MOLLAN, CHERYL L. | CLOSED | 2014-03-05 | IN: SMARTROOM UPGRADE 186-A101 | 186 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004846 Total | [7 empty] | 8749.0556 | 0 | 7522.0042 | 7522.0042
PJ0004842 | REPLACE PROJECTOR (SMART ROOM RETROFIT) - BLDG 014 RM 256 | MOLLAN, CHERYL L. | CLOSED | 2014-02-28 | AD: MORELAND THOMPSON, INC. | 014 | CLOSED | 5542.6 | 0 | 5542.6 | 5542.6
PJ0004842 | REPLACE PROJECTOR (SMART ROOM RETROFIT) - BLDG 014 RM 256 | MOLLAN, CHERYL L. | CLOSED | 2014-02-28 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 586.2 | 0 | 0 | 0
PJ0004842 | REPLACE PROJECTOR (SMART ROOM RETROFIT) - BLDG 014 RM 256 | MOLLAN, CHERYL L. | CLOSED | 2014-02-28 | EH&S:TEST SAMPLE FOR ASBESTOS | 014 | CLOSED | 197.4 | 0 | 43.896 | 43.896
PJ0004842 | REPLACE PROJECTOR (SMART ROOM RETROFIT) - BLDG 014 RM 256 | MOLLAN, CHERYL L. | CLOSED | 2014-02-28 | IN: REPLACE PROJECTOR (SMART ROOM RETROFIT) - BLDG 014 RM 256 | 014 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004842 | REPLACE PROJECTOR (SMART ROOM RETROFIT) - BLDG 014 RM 256 | MOLLAN, CHERYL L. | CLOSED | 2014-02-28 | LO: INSTALL/REMOVE CONSTRUCTION CORES - BLDG. 14 RM. 256 | 014 | CLOSED | 116.088 | 0 | 58.044 | 58.044
PJ0004842 Total | [7 empty] | 6570.4 | 0 | 5772.652 | 5772.652
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | AD: MORELAND THOMPSON | 038 | CLOSED | 6275.55 | 0 | 6275.55 | 6275.55
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | CA: REMOVE TACK BOARDS & TOWEL DISPENSERS; INSTALL 2 SCREENS | 038 | CLOSED | 376.6718 | 0 | 834.228 | 834.228
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 397.28 | 0 | 0 | 0
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | CU: CLEAN RAISED CARPET FLOOR IN COMPUTER LAB - BLDG. 38 RM. 123 | 038 | CLOSED | 584.736 | 0 | 145.968 | 145.968
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | IN: UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | 038 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | PA:PAINT ROOM IN BLDG 38, ROOM 123 | 038 | CLOSED | 2614.56 | 0 | 2612.016 | 2612.016
PJ0004839 | UPGRADE LEARNING ENVIRONMENT (SMART ROOM) - BLDG 038 RM 123 | MOLLAN, CHERYL L. | CLOSED | 2014-02-25 | PL:REMOVE FAUCETS AND CAP-OFF AT COUNTER BLDG 38, ROOM 123 | 038 | CLOSED | 290.5494 | 0 | 130.584 | 130.584
PJ0004839 Total | [7 empty] | 10667.4592 | 0 | 10126.458 | 10126.458
PJ0004838 | CARD PANIC DEVICES - BLDG. 15 RM. 104 | NORTON, DAVE | CLOSED | 2014-01-24 | AD: AMERICAN AUTOMATIC DOORS | 015 | CLOSED | 15683.1184 | 0 | 15683.1184 | 15683.1184
PJ0004838 | CARD PANIC DEVICES - BLDG. 15 RM. 104 | NORTON, DAVE | CLOSED | 2014-01-24 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 2017.01 | 0 | 0 | 0
PJ0004838 | CARD PANIC DEVICES - BLDG. 15 RM. 104 | NORTON, DAVE | CLOSED | 2014-01-24 | EL: ADD ELECTRICAL FOR DOOR OPERATOR & CARD READER | 015 | CLOSED | 3000.6826 | 0 | 356.688 | 356.688
PJ0004838 | CARD PANIC DEVICES - BLDG. 15 RM. 104 | NORTON, DAVE | CLOSED | 2014-01-24 | IN: CARD READER HARDWARE AND PANIC DEVICES - BLDG. 15 RM. 104 | 015 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004838 | CARD PANIC DEVICES - BLDG. 15 RM. 104 | NORTON, DAVE | CLOSED | 2014-01-24 | LO:PROVIDE ELECT STRIKE OR PANIC HDWR | 015 | CLOSED | 819.4063 | 0 | 618.432 | 618.432
PJ0004838 Total | [7 empty] | 21648.3293 | 0 | 16786.3504 | 16786.3504
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | AD: DGS - ADVERTIZING FEES FOR RFP 2000007148 (DAKTRONICS) | 042 | CLOSED | 0 | 0 | 96.3 | 96.3
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | AD: ENGLEKIRK AND SABOL | 042 | CLOSED | 3287.04 | 0 | 1070 | 1070
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | AD: JOC 14.033.015 MAINO | 042 | CLOSED | 16362.975 | 0 | 59612.8244 | 59612.8244
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | AD: PROJECT MGT COSTS FOR SCOREBOARD INSTALLATION (ALT. FUNDING) | 042 | CLOSED | 38080 | 0 | 38080 | 38080
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | CA: DRILL 16 HOLES FOR DAKTRONICS TO SET WALL ANCHORS | 042 | CLOSED | 13224.4939 | 0 | 2586.78 | 2586.78
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 3929.84 | 0 | 0 | 0
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | EH&S: | 042 | CLOSED | 514.8 | 0 | 0 | 0
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | EL: PANEL 'K' INVESTIGATION AND UPGRADE | 042 | CLOSED | 29766.1442 | 0 | 19221.828 | 19221.828
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | EO: ASSIST DAKTRONICS WITH MAN LIFT | 042 | CLOSED | 74.646 | 0 | 27.69 | 27.69
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | IN: INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | 042 | CLOSED | 1024.896 | 0 | 647.148 | 647.148
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | ITS: DATA LINES FOR MARQUEE AT MOTT GYM | 042 | CLOSED | 4060 | 0 | 567.55 | 567.55
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | LO: INSTALL CONSTRUCTION CORE FOR DURATION OF CONSTRUCTION | 042 | CLOSED | 858.2958 | 0 | 30.462 | 30.462
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | MO: | 042 | CLOSED | 577.044 | 0 | 0 | 0
PJ0004835 | INSTALL SCOREBOARDS/VIDEO BOARDS AT MOTT GYM | MCNALLY, CURTIS | CLOSED | 2014-02-19 | PA: PAINT CONDUIT FOR MOTT SCOREBOARDS - 042 | 042 | CLOSED | 5019.9041 | 0 | 4334.412 | 4334.412
PJ0004835 Total | [7 empty] | 116780.079 | 0 | 126274.9944 | 126274.9944
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CA: ROBORODENTIA SUPPORT - APRIL 11, 2014 | GENERAL | CLOSED | 0 | 0 | 554.766 | 554.766
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CA: SUPPORT FOR 2014 OPEN HOUSE - APRIL 12 | GENERAL | CLOSED | 0 | 0 | 624.12 | 624.12
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CP: SUPPORT FOR 2014 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 463.2 | 463.2
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CU: SUPPORT FOR 2014 OPEN HOUSE - 4/12 | GENERAL | CLOSED | 0 | 0 | 4404.4147 | 4404.4147
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | EL: INSTALL SPIDER BOX FOR OPEN HOUSE RALLY - APRIL 10 | 043 | CLOSED | 0 | 0 | 75.024 | 75.024
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | EL: INSTALL THREE SPIDER BOXES AT MOTT GYM - FRIDAY APRIL 11 | GENERAL | CLOSED | 0 | 0 | 43.272 | 43.272
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | EL: SUPPORT FOR 2014 OPEN HOUSE - APRIL 11& 12 | GENERAL | CLOSED | 0 | 0 | 2104.46 | 2104.46
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | EO: SUPPORT FOR 2014 OPEN HOSUE - APRIL 12 | GENERAL | CLOSED | 0 | 0 | 130.255 | 130.255
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | LA: SUPPORT FOR 2014 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 4382.1464 | 4382.1464
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | PL: SUPPORT FOR OPEN HOUSE 4/12/2014 | GENERAL | CLOSED | 0 | 0 | 1055.705 | 1055.705
PJ0004833 | 2014 SUPPORT FOR OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2014-03-18 | RE: SUPPORT FOR 2014 OPEN HOUSE - 4/12 | GENERAL | CLOSED | 0 | 0 | 786.84 | 786.84
PJ0004833 Total | [7 empty] | 0 | 0 | 14624.2031 | 14624.2031
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CA: SUPPORT FOR 2104 SPRING COMMENCEMENT-6/14 - 6/15 | GENERAL | CLOSED | 0 | 0 | 10522.24 | 10522.24
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | CU: SUPPORT FOR SPRING COMMENCEMENT - 6/14 & 6/15 | GENERAL | CLOSED | 0 | 0 | 14075.8254 | 14075.8254
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | EL: SUPPORT FOR 2014 SPRING COMMENCEMENT - 6/14&6/15 | GENERAL | CLOSED | 0 | 0 | 1374.56 | 1374.56
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | ES: SUPPORT FOT 2014 SPRING COMMENCEMENT - 6/14&15 | GENERAL | CLOSED | 0 | 0 | 579 | 579
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | LA: SUPPORT FOR 2014 COMMENCEMENT 6/14 - 6/15 | GENERAL | CLOSED | 0 | 0 | 14671.9898 | 14671.9898
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | MO: SET UP AND TEAR DOWN FOR AERO POST COMMENCEMENT-6/14 | 041 | CLOSED | 0 | 0 | 60.36 | 60.36
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | MO: SUPPORT FOR 2014 SPRING COMMENCEMENT - JUNE 14 & 15 | GENERAL | CLOSED | 0 | 0 | 1169.475 | 1169.475
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | PA: SUPPORT FOR POST COMMENCEMENT - 6/14 & 6/15 | GENERAL | CLOSED | 0 | 0 | 94.05 | 94.05
PJ0004832 | 2014: SUPPORT FOR SPRING COMMENCEMENT | POPHAM, DONALD J. | CLOSED | 2014-03-18 | PL: SUPPORT FOR 2014 SPRING COMMENCEMENT - 6/14&6/15 | GENERAL | CLOSED | 0 | 0 | 2363.685 | 2363.685
PJ0004832 Total | [7 empty] | 0 | 0 | 44911.1852 | 44911.1852
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | AD: J.L. FASULO | 014 | CLOSED | 0 | 0 | 919 | 919
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | CA: CLOSE WALL AFTER DEMO OF EXISTING DRINKING FOUNTAIN | 014 | CLOSED | 0 | 0 | 296.13 | 296.13
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 014 | CLOSED | 0 | 0 | 33 | 33
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | EL: RELOCATE OUTLET FOR NEW MODEL DRINKING FOUNTAIN | 014 | CLOSED | 0 | 0 | 854.39 | 854.39
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | IN: REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | 014 | CLOSED | 0 | 0 | 53.38 | 53.38
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | PA: FINISH WALL FOR NEW DRINKING FOUNTAIN | 014 | CLOSED | 0 | 0 | 197.88 | 197.88
PJ0004831 | REPLACE DRINKING FOUNTAIN - BLD 14 1ST FLR BY RM 107 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2014-03-12 | PL: REPLACE DRINING FOUNTAIN - BLDG 14 1ST FLR BY RM 107 | 014 | CLOSED | 0 | 0 | 3245.7266 | 3245.7266
PJ0004831 Total | [7 empty] | 0 | 0 | 5599.5066 | 5599.5066
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | AD: JOC 13.030.022 MAINO | 171I | CLOSED | 173057.9373 | 0 | 170869.8729 | 170869.8729
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | AD: JOC 13.031.047 MAINO | 171I | CLOSED | 12389.1127 | 0 | 12389.1127 | 12389.1127
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | AD: PMSM ARCHITECTS | 171I | CLOSED | 2974.6 | 0 | 2974.6 | 2974.6
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | AD: STATE FIRE MARSHAL | 171I | CLOSED | 1407.05 | 0 | 580.79 | 580.79
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | CP: PROJECT CONTINGENCY | 171I | CLOSED | 14510.58 | 0 | 0 | 0
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | IN: INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | 171I | CLOSED | 384.336 | 0 | 384.336 | 384.336
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | LO: INSTALL ORANGE CORE FOR CONTRACTOR AT TACO'S TO GO | 171I | CLOSED | 58.044 | 0 | 58.044 | 58.044
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | PA: PAINT SOFFIT AND BACK WALL AT TACOS-TO-GO | 171I | CLOSED | 1069.824 | 0 | 608.13 | 608.13
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | PCVEL: SUPPORT FOR OUTSIDE CONTRACTOR AT TACOS TO GO | 171I | CLOSED | 67.416 | 0 | 235.956 | 235.956
PJ0004830 | INSTALL TACOS-TO-GO EXHAUST HOOD PER DESIGN FROM PJ 4391 | LAMPMAN, GREG | CLOSED | 2014-01-30 | PCVPL: SUPPORT FOR OUTSIDE CONTRACTOR AT TACOS TO GO | 171I | CLOSED | 56.388 | 0 | 225.552 | 225.552
PJ0004830 Total | [7 empty] | 205975.288 | 0 | 188326.3936 | 188326.3936
PJ0004829 | SR 13/14: REMEDIATE UTILIDOR FLOOD DAMAGE - UU 65 | HICKS, MICHAEL | CLOSED | 2014-03-17 | AD: BELFOR N2043001 | 065 | CLOSED | 26742.72 | 0 | 26742.72 | 26742.72
PJ0004829 | SR 13/14: REMEDIATE UTILIDOR FLOOD DAMAGE - UU 65 | HICKS, MICHAEL | CLOSED | 2014-03-17 | AD: J.L. FASULO DRYWALL | 065 | CLOSED | 2162 | 0 | 1962 | 1962
PJ0004829 | SR 13/14: REMEDIATE UTILIDOR FLOOD DAMAGE - UU 65 | HICKS, MICHAEL | CLOSED | 2014-03-17 | CA: INSTALL 6" RUBBER BASE IN CRAFT CENTER, WOOD BASE IN CORRIDO | 065 | CLOSED | 413.8932 | 0 | 450.495 | 450.495
PJ0004829 | SR 13/14: REMEDIATE UTILIDOR FLOOD DAMAGE - UU 65 | HICKS, MICHAEL | CLOSED | 2014-03-17 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0004829 | SR 13/14: REMEDIATE UTILIDOR FLOOD DAMAGE - UU 65 | HICKS, MICHAEL | CLOSED | 2014-03-17 | IN: SR 13/14: REMEDIATE UTILIDOR FLOOD DAMAGE - UU 65 | 065 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0004829 Total | [7 empty] | 29425.3732 | 0 | 29261.975 | 29261.975
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | AD: ALPHA FIRE | 186 | CLOSED | 0 | 0 | 190 | 190
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | CA:HOT WATER FLOOD DAMAGE SUPPORT AT 186 | 186 | CLOSED | 0 | 0 | 4068.835 | 4068.835
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 0 | 0 | 0 | 0
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | CPE:FLOOD DAMAGE SUPPORT AT 186 | 186 | CLOSED | 0 | 0 | 1758.03 | 1758.03
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | CU: CUSTODIAL SUPPORT FOR FLOOD REMEDIATION-186 | 186 | CLOSED | 0 | 0 | 32.09 | 32.09
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | EL:HOT WATER PIPE FLOOD SUPPORT AT 186 | 186 | CLOSED | 0 | 0 | 6621.04 | 6621.04
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | ES:SUPPORT FOR HOT WATER FLOOD AT 186 | 186 | CLOSED | 0 | 0 | 11714.625 | 11714.625
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | MO: SUPPORT FOR FLOOD REMEDIATION AT CONSTRUCTION MGT., BLDG 186 | 186 | CLOSED | 0 | 0 | 20.12 | 20.12
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | PL:SUPPORT FOR HOT WATER FLOOD AT 186 | 186 | CLOSED | 0 | 0 | 605.5 | 605.5
PJ0004827 | FLOODING FROM RUPTURED HOT WATER PIPE - 1ST FLR BLD 186 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-17 | RE: SUPPORT FOR FLOOD REMEDIATION AT CONSTRUCTION MGT., BLDG 186 | 186 | CLOSED | 0 | 0 | 188.54 | 188.54
PJ0004827 Total | [7 empty] | 0 | 0 | 25198.78 | 25198.78
PJ0004826 | REPAIR FIRE CURTAIN - BLDG. 06 PAC | LAMPMAN, GREG | CLOSED | 2014-03-13 | AD: BUEHLER AND BUEHLER | 006 | CLOSED | 13910 | 0 | 7096.5 | 7096.5
PJ0004826 | REPAIR FIRE CURTAIN - BLDG. 06 PAC | LAMPMAN, GREG | CLOSED | 2014-03-13 | AD: JOC 13.031.048 MAINO | 006 | CLOSED | 7744.1892 | 0 | 7753.8793 | 7753.8793
PJ0004826 | REPAIR FIRE CURTAIN - BLDG. 06 PAC | LAMPMAN, GREG | CLOSED | 2014-03-13 | AD: JOC 14.034.005 MAINO | 006 | CLOSED | 180841.4169 | 0 | 107013.7281 | 107013.7281
PJ0004826 | REPAIR FIRE CURTAIN - BLDG. 06 PAC | LAMPMAN, GREG | CLOSED | 2014-03-13 | AD: STATE FIRE MARSHAL FEES | 006 | CLOSED | 321 | 0 | 1207.6234 | 1207.6234
PJ0004826 | REPAIR FIRE CURTAIN - BLDG. 06 PAC | LAMPMAN, GREG | CLOSED | 2014-03-13 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 20609.56 | 0 | 0 | 0
PJ0004826 | REPAIR FIRE CURTAIN - BLDG. 06 PAC | LAMPMAN, GREG | CLOSED | 2014-03-13 | IN: REPAIR FIRE CURTAIN - BLDG. 06 PAC | 006 | CLOSED | 845.544 | 0 | 735.875 | 735.875
PJ0004826 Total | [7 empty] | 224271.7101 | 0 | 123807.6058 | 123807.6058
PJ0004825 | MOVE ART FROM FRONT LOBBY & REHANG IN BACK LOBBY-BLD 35 | GONZALES, ALBERT M. | CLOSED | 2014-03-13 | AD: TEMPLE BUILDERS | 035 | CLOSED | 2467.1525 | 0 | 1841.0099 | 1841.0099
PJ0004825 | MOVE ART FROM FRONT LOBBY & REHANG IN BACK LOBBY-BLD 35 | GONZALES, ALBERT M. | CLOSED | 2014-03-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 259.68 | 0 | 0 | 0
PJ0004825 | MOVE ART FROM FRONT LOBBY & REHANG IN BACK LOBBY-BLD 35 | GONZALES, ALBERT M. | CLOSED | 2014-03-13 | IN: MOVE ART FROM FRONT LOBBY & REHANG IN BACK LOBBY-BLD 35 | 035 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004825 Total | [7 empty] | 2790.8885 | 0 | 1873.0379 | 1873.0379
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | AD: ASAP REPROGRAPHICS | 014 | CLOSED | 0 | 0 | 212.3415 | 212.3415
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | AD: EMERSON NETWORK POWER | 014 | CLOSED | 1753.6444 | 0 | 1753.6337 | 1753.6337
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | AD: HPS MECHANICAL | 014 | CLOSED | 5348.93 | 0 | 5348.93 | 5348.93
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | AD: JOC 14.033.013 MAINO | 014 | CLOSED | 403620.05 | 0 | 383236.3895 | 383236.3895
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | AD: MCKENNA ENVIRONMENTAL | 014 | CLOSED | 31088.85 | 0 | 4075.63 | 4075.63
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | AD: SIEMENS | 014 | CLOSED | 126615.24 | 0 | 126615.24 | 126615.24
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 42603.8 | 0 | 0 | 0
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | CPE: SUPPORT CHILLER REPLACEMENT | 014 | CLOSED | 4592.521 | 0 | 5778.228 | 5778.228
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | EH&S: LAB CHARGES FOR SAMPLE ANALSYSIS (MATERIAL ONLY) | 014 | CLOSED | 0 | 0 | 48 | 48
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | EL: SUPPORT CHILLER REPLACEMENT | 014 | CLOSED | 6467.6903 | 0 | 3876.366 | 3876.366
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | ES: SUPPORT CHILLER REPLACEMENT | 014 | CLOSED | 4592.521 | 0 | 2108.676 | 2108.676
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | IN: REPLACE CHILLERS AT COMPUTER SCIENCE | 014 | CLOSED | 2825.76 | 0 | 1624.812 | 1624.812
PJ0004823 | REPLACE CHILLERS AT COMPUTER SCIENCE | KOLEGRAFF, KENNETH | CLOSED | 2014-02-25 | LO: INSTALL ORANGE CORES | 014 | CLOSED | 571.1118 | 0 | 91.386 | 91.386
PJ0004823 Total | [7 empty] | 630080.1184 | 0 | 534769.6327 | 534769.6327
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | AD: GARRATT CALLAHAN | U-UDOR | CLOSED | 1311.43 | 0 | 1311.43 | 1311.43
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | AD: GOSS ENGINEERING | U-UDOR | CLOSED | 8580 | 0 | 8580 | 8580
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | AD: JOC 13.030.006 MAINO | U-UDOR | CLOSED | 53307.54 | 0 | 53307.54 | 53307.54
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | AD: JOC 13.031.018 MAINO | U-UDOR | CLOSED | 404118.29 | 0 | 402285.59 | 402285.59
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | AD: JOC 14.033.031 MAINO | U-UDOR | CLOSED | 20225.54 | 0 | 20225.54 | 20225.54
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 15870.94 | 0 | 0 | 0
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | CPE:LIBRARY PIPING PROJECT SUPPORT | U-UDOR | CLOSED | 3742.5096 | 0 | 4021.91 | 4021.91
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | EL:LIBRARY PIPING MARK UTILITIES AND PROJECT SUPPORT | U-UDOR | CLOSED | 2000.006 | 0 | 358.7 | 358.7
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | ES:LIBRARY PIPING PROJECT SUPPORT | U-UDOR | CLOSED | 1889.7213 | 0 | 706.44 | 706.44
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | IN: REPAIR UTILIDOR NEAR LIBRARY & INSTALL TEMP PATCHES | U-UDOR | CLOSED | 1329.162 | 0 | 1303.84 | 1303.84
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | LA: MARK UTILITIES PROJECT SUPPORT LIBRARY PIPING (MAINT) | U-UDOR | CLOSED | 2149.4 | 0 | 7048.95 | 7048.95
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | LA: MATERIALS FOR IRRIGATION - DEXTER UTILITOR PROJECT (N/L) | U-UDOR | CLOSED | 0 | 0 | 3528.2667 | 3528.2667
PJ0004822 | SR 13/14: REPAIR UTILIDOR/INSTALL TEMP PATCHES 05,07,13,34,35,41 | BRENNAN, MICHAEL | CLOSED | 2014-03-11 | PL:LIBRARY PIPING MARK UTILITIES AND PROJECT SUPPORT | U-UDOR | CLOSED | 968.498 | 0 | 2336.37 | 2336.37
PJ0004822 Total | [7 empty] | 515493.0369 | 0 | 505014.5767 | 505014.5767
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | AD: G.F. GARCIA | GENERAL | CLOSED | 7797.84 | 0 | 7100.28 | 7100.28
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | AD: JOC 13.030.010 MAINO | GENERAL | CLOSED | 160419.66 | 0 | 110934.22 | 110934.22
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | AD: JOC 14.033.017 MAINO | GENERAL | CLOSED | 0 | 0 | 21462.74 | 21462.74
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | EL: GAS LINE REPLACEMENT | GENERAL | CLOSED | 750.002 | 0 | 1112.26 | 1112.26
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | IN: SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GENERAL | CLOSED | 213.52 | 0 | 533.8 | 533.8
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | LA: LANDSCAPING FOR GAS LINE REPAIRS | GENERAL | CLOSED | 2367.2737 | 0 | 119.8 | 119.8
PJ0004821 | SR 13/14: GAS LINE REPAIR - NEAR NATATORIUM | GONZALES, ALBERT M. | CLOSED | 2014-03-11 | PL: GAS REPLACEMENT ON VIA CARTA AND BYPASS | GENERAL | CLOSED | 7453.2911 | 0 | 14624.1415 | 14624.1415
PJ0004821 Total | [7 empty] | 179001.5868 | 0 | 155887.2415 | 155887.2415
PJ0004820 | RESPOND TO UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-05 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0004820 | RESPOND TO UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-05 | CPE:SUPPORT FOR LEAK BEHIND LIBRARY | U-UDOR | CLOSED | 0 | 0 | 1859.805 | 1859.805
PJ0004820 | RESPOND TO UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-05 | EL:SUPPORT FOR LEAK BEHIND LIBRARY | U-UDOR | CLOSED | 0 | 0 | 140.45 | 140.45
PJ0004820 | RESPOND TO UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-05 | ES: SUPPORT FOR LEAK BEHIND LIBRARY | U-UDOR | CLOSED | 0 | 0 | 26.015 | 26.015
PJ0004820 | RESPOND TO UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-05 | IN: REPAIR UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 | U-UDOR | CLOSED | 0 | 0 | 427.04 | 427.04
PJ0004820 | RESPOND TO UTILIDOR LEAKS: BLDS 05, 07, 13, 34, 35, 41 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-03-05 | PL:SUPPORT FOR LEAK BEHIND LIBRARY | U-UDOR | CLOSED | 0 | 0 | 655.915 | 655.915
PJ0004820 Total | [7 empty] | 0 | 0 | 3109.225 | 3109.225
PJ0004819 | SR 13/14: REPAIRS TO MUSTANG SUBSTATION BANK 2 - BLD 75 | POLVI, STEVEN | CLOSED | 2014-03-05 | AD: RK POWER ENGINEERING, INC. | 075 | CLOSED | 30980 | 0 | 18500 | 18500
PJ0004819 | SR 13/14: REPAIRS TO MUSTANG SUBSTATION BANK 2 - BLD 75 | POLVI, STEVEN | CLOSED | 2014-03-05 | AD: SD MYERS | 075 | CLOSED | 7500 | 0 | 19980 | 19980
PJ0004819 | SR 13/14: REPAIRS TO MUSTANG SUBSTATION BANK 2 - BLD 75 | POLVI, STEVEN | CLOSED | 2014-03-05 | CP: PROJECT CONTINGENCY | 075 | CLOSED | 0 | 0 | 0 | 0
PJ0004819 Total | [7 empty] | 38480 | 0 | 38480 | 38480
PJ0004813 | REPLACE CUSTOM CABINETRY - ASI CHILDRENS CENTER | LAMPMAN, GREG | CLOSED | 2014-02-27 | AD: FLOOR CONNECTION | 133 | CLOSED | 2193.5 | 0 | 2193.5 | 2193.5
PJ0004813 | REPLACE CUSTOM CABINETRY - ASI CHILDRENS CENTER | LAMPMAN, GREG | CLOSED | 2014-02-27 | AD: JOC 13.030.021 | 133 | CLOSED | 49770.2689 | 0 | 49770.2689 | 49770.2689
PJ0004813 | REPLACE CUSTOM CABINETRY - ASI CHILDRENS CENTER | LAMPMAN, GREG | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 1454.1 | 0 | 0 | 0
PJ0004813 | REPLACE CUSTOM CABINETRY - ASI CHILDRENS CENTER | LAMPMAN, GREG | CLOSED | 2014-02-27 | IN: REPLACE CUSTOM CABINETRY - ASI CHILDRENS CENTER | 133 | CLOSED | 640.56 | 0 | 160.14 | 160.14
PJ0004813 Total | [7 empty] | 54058.4289 | 0 | 52123.9089 | 52123.9089
PJ0004812 | REPLACE ENTRY DOOR GLASS & INTERIOR DOORS-BLDG 133 | LAMPMAN, GREG | CLOSED | 2014-02-27 | AD: JOC 13.030.020 MAINO | 133 | CLOSED | 44436.672 | 0 | 44436.672 | 44436.672
PJ0004812 | REPLACE ENTRY DOOR GLASS & INTERIOR DOORS-BLDG 133 | LAMPMAN, GREG | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 1543.89 | 0 | 0 | 0
PJ0004812 | REPLACE ENTRY DOOR GLASS & INTERIOR DOORS-BLDG 133 | LAMPMAN, GREG | CLOSED | 2014-02-27 | IN: REPLACE ENTRY DOOR GLASS & INTERIOR DOORS-BLDG 133 | 133 | CLOSED | 640.56 | 0 | 128.112 | 128.112
PJ0004812 | REPLACE ENTRY DOOR GLASS & INTERIOR DOORS-BLDG 133 | LAMPMAN, GREG | CLOSED | 2014-02-27 | LO:INSTALL CORES IN NEW DOORS | 133 | CLOSED | 348.264 | 0 | 87.066 | 87.066
PJ0004812 Total | [7 empty] | 46969.386 | 0 | 44651.85 | 44651.85
PJ0004811 | M&R ASI 14/15: TURF REPLACEMENT ASSESSMENT - SPORTS COMPLEX | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: SPORTS TURF SOLUTIONS | 160 | CLOSED | 3129.75 | 0 | 2487.75 | 2487.75
PJ0004811 | M&R ASI 14/15: TURF REPLACEMENT ASSESSMENT - SPORTS COMPLEX | HICKS, MICHAEL | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 414.61 | 0 | 0 | 0
PJ0004811 | M&R ASI 14/15: TURF REPLACEMENT ASSESSMENT - SPORTS COMPLEX | HICKS, MICHAEL | CLOSED | 2014-02-27 | IN: M&R UU 14/15: TURF REPLACEMENT ASSESSMENT - SPORTS COMPLEX | 160 | CLOSED | 142.8449 | 0 | 32.028 | 32.028
PJ0004811 Total | [7 empty] | 3687.2049 | 0 | 2519.778 | 2519.778
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: FLOOR CONNECTION | 065 | CLOSED | 150235.49 | 0 | 141063.7068 | 141063.7068
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: MORELAND THOMPSON, INC. | 065 | CLOSED | 18494.95 | 0 | 18494.95 | 18494.95
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 567.1 | 0 | 625.8537 | 625.8537
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 13353.37 | 0 | 0 | 0
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | EL:ELECTRICAL & SIGNALING WIRING FOR NEW MECHOSHADES IN LOUNGES | 065 | CLOSED | 15582.504 | 0 | 7855.008 | 7855.008
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | IN: INSTALL MECHANICAL SHADE SYSTEM - CHUMASH & 220-UU | 065 | CLOSED | 641.8411 | 0 | 413.982 | 413.982
PJ0004809 | M&R ASI 14/15: INSTALL MECHANICAL SHADE SYSTEM- CHUMASH & 220-UU | HICKS, MICHAEL | CLOSED | 2014-02-27 | PA: PAINTING TOUCH UP AT DRAPERY LOCATIONS - BLDG. 65 | 065 | CLOSED | 2846.3338 | 0 | 1178.67 | 1178.67
PJ0004809 Total | [7 empty] | 201721.5889 | 0 | 169632.1705 | 169632.1705
PJ0004808 | M&R ASI 14/15: DESIGN FOR LIGHTING RETROFIT - UNIVERSITY UNION | MCNALLY, CURTIS | CLOSED | 2014-02-27 | AD: STATE FIRE MARSHAL FEES | 065 | CLOSED | 0 | 0 | 550.3438 | 550.3438
PJ0004808 | M&R ASI 14/15: DESIGN FOR LIGHTING RETROFIT - UNIVERSITY UNION | MCNALLY, CURTIS | CLOSED | 2014-02-27 | AD: THOMA ELECTRIC | 065 | CLOSED | 10700 | 0 | 10379 | 10379
PJ0004808 | M&R ASI 14/15: DESIGN FOR LIGHTING RETROFIT - UNIVERSITY UNION | MCNALLY, CURTIS | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1134.29 | 0 | 0 | 0
PJ0004808 | M&R ASI 14/15: DESIGN FOR LIGHTING RETROFIT - UNIVERSITY UNION | MCNALLY, CURTIS | CLOSED | 2014-02-27 | IN: M&R UU 14/15: LIGHTING RETROFIT - UNIVERSITY UNION | 065 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004808 Total | [7 empty] | 11962.402 | 0 | 10961.3718 | 10961.3718
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: JOC 13.030.009 MAINO | 065 | CLOSED | 705789.655 | 0 | 687368.8346 | 687368.8346
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 065 | CLOSED | 4079.482 | 0 | 4079.482 | 4079.482
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: QUAGLINO ROOFING | 065 | CLOSED | 35481.2 | 0 | 35481.2 | 35481.2
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: SANTA MARIA ACOUSTICAL | 065 | CLOSED | 2230.95 | 0 | 2230.95 | 2230.95
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 67094.98 | 0 | 0 | 0
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | IN: M&R UU 14/15: REPLACE ROOF - UNIVERSITY UNION | 065 | CLOSED | 768.672 | 0 | 960.84 | 960.84
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | LO: CHANGE PADLOCK ON ROOF HATCH UU ROOM 301 | 065 | CLOSED | 146.088 | 0 | 59.022 | 59.022
PJ0004807 | M&R ASI 14/15: REPLACE ROOF - UNIVERSITY UNION | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | PL: UU ROOF DRAIN SUPPORT | 065 | CLOSED | 731.0988 | 0 | 424.398 | 424.398
PJ0004807 Total | [7 empty] | 816322.1258 | 0 | 730604.7266 | 730604.7266
PJ0004806 | M&R ASI 14/15: FACILITY CONDITION ASSESSMENT - REC CENTER | NEEL, JOEL | CLOSED | 2014-02-27 | AD: ISES CORP | 043 | CLOSED | 16688.79 | 0 | 16688.79 | 16688.79
PJ0004806 | M&R ASI 14/15: FACILITY CONDITION ASSESSMENT - REC CENTER | NEEL, JOEL | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 1768.78 | 0 | 0 | 0
PJ0004806 Total | [7 empty] | 18457.57 | 0 | 16688.79 | 16688.79
PJ0004805 | M&R ASI 14/15: REFINISH WOOD FLOORS - ALL GYMS - REC CENTER | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | AD: JOC 13.030.012 MAINO | 043 | CLOSED | 47603.6366 | 0 | 47603.6366 | 47603.6366
PJ0004805 | M&R ASI 14/15: REFINISH WOOD FLOORS - ALL GYMS - REC CENTER | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | AD: MCWIL | 043 | CLOSED | 1572.9 | 0 | 1572.9 | 1572.9
PJ0004805 | M&R ASI 14/15: REFINISH WOOD FLOORS - ALL GYMS - REC CENTER | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 817.06 | 0 | 0 | 0
PJ0004805 | M&R ASI 14/15: REFINISH WOOD FLOORS - ALL GYMS - REC CENTER | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | EL:CONTRACTOR SUPPORT FOR ELECTRICAL AT REC CENTER | 043 | CLOSED | 67.416 | 0 | 226.572 | 226.572
PJ0004805 | M&R ASI 14/15: REFINISH WOOD FLOORS - ALL GYMS - REC CENTER | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | IN: M&R UU 14/15: REFINISH WOOD FLOORS - ALL GYMS - REC CENTER | 043 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004805 Total | [7 empty] | 50189.1246 | 0 | 49531.2206 | 49531.2206
PJ0004804 | M&R ASI 14/15: REPLACE FLOORING OUTSIDE FITNESS STUDIOS- REC CTR | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: ATASCADERO GLASS | 043 | CLOSED | 642 | 0 | 465.45 | 465.45
PJ0004804 | M&R ASI 14/15: REPLACE FLOORING OUTSIDE FITNESS STUDIOS- REC CTR | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: VISALIA TILE | 043 | CLOSED | 88176.56 | 0 | 91838.1 | 91838.1
PJ0004804 | M&R ASI 14/15: REPLACE FLOORING OUTSIDE FITNESS STUDIOS- REC CTR | HICKS, MICHAEL | CLOSED | 2014-02-27 | CA:CARPENTRY SHOP TO REMOVE RUBBER BASE & REPLACE | 043 | CLOSED | 1004.2703 | 0 | 1218.312 | 1218.312
PJ0004804 | M&R ASI 14/15: REPLACE FLOORING OUTSIDE FITNESS STUDIOS- REC CTR | HICKS, MICHAEL | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 8396.01 | 0 | 0 | 0
PJ0004804 | M&R ASI 14/15: REPLACE FLOORING OUTSIDE FITNESS STUDIOS- REC CTR | HICKS, MICHAEL | CLOSED | 2014-02-27 | IN: REPLACE FLOORING - FITNESS STUDIOS - REC CENTER | 043 | CLOSED | 142.8449 | 0 | 160.14 | 160.14
PJ0004804 Total | [7 empty] | 98361.6852 | 0 | 93682.002 | 93682.002
PJ0004803 | M&R PARK 14/15: CAMPUS WIDE PARKING LOT TREE TRIMMING | HOSTICK, RONALD | CLOSED | 2014-02-27 | AD: GREENVALE TREE | GEN-PARK | CLOSED | 2675 | 0 | 1685.25 | 1685.25
PJ0004803 | M&R PARK 14/15: CAMPUS WIDE PARKING LOT TREE TRIMMING | HOSTICK, RONALD | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 453.95 | 0 | 0 | 0
PJ0004803 | M&R PARK 14/15: CAMPUS WIDE PARKING LOT TREE TRIMMING | HOSTICK, RONALD | CLOSED | 2014-02-27 | LA: SUPPORT FOR PARKING LOT TREE TRIMMING PROJECT | GEN-PARK | CLOSED | 1864.4274 | 0 | 2549.85 | 2549.85
PJ0004803 Total | [7 empty] | 4993.3774 | 0 | 4235.1 | 4235.1
PJ0004802 | M&R PARK 14/15: DORMS-SEAL&RESTRIPE LOT-CUT&PATCH ROOTS-R1A/R1F | NORTON, DAVE | CLOSED | 2014-02-27 | AD: JOC 13.029.055 MAINO | P-R01 | CLOSED | 57270.7121 | 0 | 57270.7121 | 57270.7121
PJ0004802 | M&R PARK 14/15: DORMS-SEAL&RESTRIPE LOT-CUT&PATCH ROOTS-R1A/R1F | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 2866.74 | 0 | 0 | 0
PJ0004802 | M&R PARK 14/15: DORMS-SEAL&RESTRIPE LOT-CUT&PATCH ROOTS-R1A/R1F | NORTON, DAVE | CLOSED | 2014-02-27 | IN: DORMS-SEAL&RESTRIPE LOT-CUT&PATCH ROOTS-R1A/R1F | P-R01 | CLOSED | 64.056 | 0 | 224.196 | 224.196
PJ0004802 Total | [7 empty] | 60201.5081 | 0 | 57494.9081 | 57494.9081
PJ0004801 | M&R PARK 14/15: VIA CARTA - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | AD: JOC 13.029.054 MAINO | P-H16 | CLOSED | 72610.2749 | 0 | 72610.2749 | 72610.2749
PJ0004801 | M&R PARK 14/15: VIA CARTA - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | P-H16 | CLOSED | 3633.72 | 0 | 0 | 0
PJ0004801 | M&R PARK 14/15: VIA CARTA - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | IN: M&R PARK 14/15: VIA CARTA - SEAL & RESTRIPE LOT | P-H16 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004801 Total | [7 empty] | 76308.0509 | 0 | 72674.3309 | 72674.3309
PJ0004800 | M&R PARK 14/15: SPORTS COMPLEX - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | AD: JOC 13.028.054 MAINO | P-H15 | CLOSED | 8598.7768 | 0 | 8195.0979 | 8195.0979
PJ0004800 | M&R PARK 14/15: SPORTS COMPLEX - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | P-H15 | CLOSED | 433.14 | 0 | 0 | 0
PJ0004800 | M&R PARK 14/15: SPORTS COMPLEX - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | IN: M&R PARK 14/15: SPORTS COMPLEX - SEAL & RESTRIPE LOT | P-H15 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004800 Total | [7 empty] | 9095.9728 | 0 | 8259.1539 | 8259.1539
PJ0004798 | M&R PARK 14/15: LIBRARY/UNIVERSITY DR. - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | AD: JOC 13.029.051 (PARTIAL) MAINO | P-H10 | CLOSED | 24588.8247 | 0 | 24588.8247 | 24588.8247
PJ0004798 | M&R PARK 14/15: LIBRARY/UNIVERSITY DR. - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | AD: JOC 13.031.029 MAINO | P-H10 | CLOSED | 8568.025 | 0 | 5807.8637 | 5807.8637
PJ0004798 | M&R PARK 14/15: LIBRARY/UNIVERSITY DR. - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | CA: INSTALL VAN-ACCESSIBLE SIGNS AT H-10 PARKING LOT | P-H10 | CLOSED | 405.552 | 0 | 230.5572 | 230.5572
PJ0004798 | M&R PARK 14/15: LIBRARY/UNIVERSITY DR. - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | P-H10 | CLOSED | 1561.11 | 0 | 0 | 0
PJ0004798 | M&R PARK 14/15: LIBRARY/UNIVERSITY DR. - SEAL & RESTRIPE LOT | NORTON, DAVE | CLOSED | 2014-02-27 | IN: LIBRARY/UNIVERSITY DR. - SEAL & RESTRIPE LOT | P-H10 | CLOSED | 192.168 | 0 | 160.14 | 160.14
PJ0004798 Total | [7 empty] | 35315.6797 | 0 | 30787.3856 | 30787.3856
PJ0004797 | M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 271 | NORTON, DAVE | CLOSED | 2014-02-27 | AD: TIM HAAHS | 271 | CLOSED | 9701.3262 | 0 | 9677.5401 | 9677.5401
PJ0004797 | M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 271 | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 271 | CLOSED | 977.2 | 0 | 0 | 0
PJ0004797 | M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 271 | NORTON, DAVE | CLOSED | 2014-02-27 | IN: M&R PARK 14/15: PCV PARKING STRUCTURE ANALYSIS - 271 | 271 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0004797 Total | [7 empty] | 10749.1702 | 0 | 9748.1841 | 9748.1841
PJ0004796 | M&R PARK 14/15: GRAND AVE PARKING STRUCTURE MAINT & ANALYSIS 130 | NORTON, DAVE | CLOSED | 2014-02-27 | AD: TIMOTHY HAAHS & ASSOCIATES | 130 | CLOSED | 9701.3262 | 0 | 9677.5401 | 9677.5401
PJ0004796 | M&R PARK 14/15: GRAND AVE PARKING STRUCTURE MAINT & ANALYSIS 130 | NORTON, DAVE | CLOSED | 2014-02-27 | CA:SIESMIC JOINT CLEAN & REFURBISH | 130 | CLOSED | 13500.4135 | 0 | 12860.088 | 12860.088
PJ0004796 | M&R PARK 14/15: GRAND AVE PARKING STRUCTURE MAINT & ANALYSIS 130 | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 2263.18 | 0 | 0 | 0
PJ0004796 | M&R PARK 14/15: GRAND AVE PARKING STRUCTURE MAINT & ANALYSIS 130 | NORTON, DAVE | CLOSED | 2014-02-27 | IN: GRAND AVE - PARKING STRUCTURE MAINTENANCE | 130 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004796 Total | [7 empty] | 25593.0317 | 0 | 22665.7401 | 22665.7401
PJ0004795 | M&R HOUS 14/15: UPGRADE LAUNDRY DRAIN SYSTEM-YOSEMITE/SO MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | AD: MAINO LVPW | RESIDENCE | CLOSED | 5350 | 0 | 2848.34 | 2848.34
PJ0004795 | M&R HOUS 14/15: UPGRADE LAUNDRY DRAIN SYSTEM-YOSEMITE/SO MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 3444.6 | 0 | 0 | 0
PJ0004795 | M&R HOUS 14/15: UPGRADE LAUNDRY DRAIN SYSTEM-YOSEMITE/SO MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | IN: MH 4795 UPGRADE LAUNDRY DRAIN SYSTEM-YOSEMITE/SO MTN | RESIDENCE | CLOSED | 423.864 | 0 | 70.644 | 70.644
PJ0004795 | M&R HOUS 14/15: UPGRADE LAUNDRY DRAIN SYSTEM-YOSEMITE/SO MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | PL:DORM LAUNDRY ROOMS | RESIDENCE | CLOSED | 25571.9863 | 0 | 7392.8904 | 7392.8904
PJ0004795 Total | [7 empty] | 34790.4503 | 0 | 10311.8744 | 10311.8744
PJ0004794 | M&R HOUS 14/15: MAIN LOUNGE ROOF DRAIN RETROFIT - YOSEMITE | LAMPMAN, GREG | CLOSED | 2014-02-27 | AD: QUAGLINO ROOFING | 114 | CLOSED | 2565.86 | 0 | 2565.86 | 2565.86
PJ0004794 | M&R HOUS 14/15: MAIN LOUNGE ROOF DRAIN RETROFIT - YOSEMITE | LAMPMAN, GREG | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 269.4 | 0 | 0 | 0
PJ0004794 | M&R HOUS 14/15: MAIN LOUNGE ROOF DRAIN RETROFIT - YOSEMITE | LAMPMAN, GREG | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: MAIN LOUNGE ROOF DRAIN RETROFIT - YOSEMITE | 114 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004794 Total | [7 empty] | 2963.372 | 0 | 2629.916 | 2629.916
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: ALPHA FIRE CORPORATION | 105 | CLOSED | 1935.63 | 0 | 1935.63 | 1935.63
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: ASAP REPRPGRAPHICS | 105 | CLOSED | 0 | 0 | 93.1435 | 93.1435
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: JOC 14.033.018 MAINO | 105 | CLOSED | 271434.8608 | 0 | 267071.4008 | 267071.4008
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: MCKENNA ENVIRONMENTAL | 105 | CLOSED | 11085.2 | 0 | 11085.2 | 11085.2
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: ON-TRAC SHIPPING | 105 | CLOSED | 0 | 0 | 26.6323 | 26.6323
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: STATE FIRE MARSHAL FEES | 105 | CLOSED | 7591.2 | 0 | 2963.91 | 2963.91
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | AD: THOMA ELECTRIC | 105 | CLOSED | 9095 | 0 | 9095 | 9095
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | ANTS:FIRE ALARM TESTING INTERFACE W/UPD | 105 | CLOSED | 754.3469 | 0 | 711.648 | 711.648
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 105 | CLOSED | 18020.78 | 0 | 0 | 0
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | EL: SUPPORT INSTALL OF FIRE ALARM SYSTEM | 105 | CLOSED | 4471.0267 | 0 | 1792.428 | 1792.428
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | 105 | CLOSED | 2409.1462 | 0 | 869.874 | 869.874
PJ0004793 | M&R HOUS 14/15: REPLACE BLDG FIRE ALARM SYSTEM - TRINITY | HICKS, MICHAEL | CLOSED | 2014-02-27 | PA: PAINTING FOR TRINITY FIRE ALARM SYS | 105 | CLOSED | 17009.862 | 0 | 2143.1 | 2143.1
PJ0004793 Total | [7 empty] | 343807.0526 | 0 | 297787.9666 | 297787.9666
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: APC CONTRACTORS | 110 | CLOSED | 5350 | 0 | 4772.2 | 4772.2
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: BENCHMARK WOODWORKING | 110 | CLOSED | 0 | 0 | 4592.7075 | 4592.7075
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: FLOOR CONNECTION | 110 | CLOSED | 1398.49 | 0 | 1398.49 | 1398.49
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: J.L. FASULO DRYWALL | 110 | CLOSED | 5757.67 | 0 | 5757.67 | 5757.67
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: MCKENNA ENVIRONMENTAL | 110 | CLOSED | 2889 | 0 | 2293.01 | 2293.01
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: SAN LUIS GLASS | 110 | CLOSED | 5350 | 0 | 4833.3184 | 4833.3184
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | CA: INSTALL CABINETS FOR SNACK SHACK | 110 | CLOSED | 1184.2703 | 0 | 1101.426 | 1101.426
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 1570.26 | 0 | 0 | 0
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | EL: ELECTRICAL WORK FOR TENAYA VENDING AREA | 110 | CLOSED | 1350.679 | 0 | 1875.708 | 1875.708
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | 110 | CLOSED | 256.224 | 0 | 288.252 | 288.252
PJ0004792 | M&R HOUS 14/15: UPGRADE VENDING AREA - TENAYA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | PA: SNACK SHACK PAINT | 110 | CLOSED | 2623.952 | 0 | 682.686 | 682.686
PJ0004792 Total | [7 empty] | 27730.5453 | 0 | 27595.4679 | 27595.4679
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: JOC 13.030.008 MAINO | RESIDENCE | CLOSED | 140720.0442 | 0 | 140720.0442 | 140720.0442
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 5029 | 0 | 3819.9 | 3819.9
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: REA AND LUKER | RESIDENCE | CLOSED | 5350 | 0 | 3488.2 | 3488.2
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 0 | 0 | 426.21 | 426.21
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 11804.12 | 0 | 0 | 0
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | EL: CSD REMODELS SUMMER 2014 | RESIDENCE | CLOSED | 1500.679 | 0 | 3680.526 | 3680.526
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | RESIDENCE | CLOSED | 384.336 | 0 | 448.392 | 448.392
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | LO: ASSIT REMODEL OF CSD UNITS | RESIDENCE | CLOSED | 232.176 | 0 | 174.132 | 174.132
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | PA: CSD REMODELS SUMMER 2014 | RESIDENCE | CLOSED | 3471.2249 | 0 | 1502.562 | 1502.562
PJ0004791 | M&R HOUS 14/15: CSD KITCHEN REMODEL - TRINITY & SEQUOIA | GONZALES, ALBERT M. | CLOSED | 2014-02-27 | PL: CSD REMODELS SUMMER 2014 | RESIDENCE | CLOSED | 10687.8986 | 0 | 16056.0252 | 16056.0252
PJ0004791 Total | [7 empty] | 179179.4787 | 0 | 170315.9914 | 170315.9914
PJ0004790 | M&R HOUS 14/15: INSTALL HOFFMAN HYDRO AIR VENTS - SIERRA MADRE | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | AD: GOSS ENGINEERING | 113 | CLOSED | 2942.5 | 0 | 2140 | 2140
PJ0004790 | M&R HOUS 14/15: INSTALL HOFFMAN HYDRO AIR VENTS - SIERRA MADRE | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | AD: JOC 13.030.026 MAINO | 113 | CLOSED | 390064.4233 | 0 | 390064.4233 | 390064.4233
PJ0004790 | M&R HOUS 14/15: INSTALL HOFFMAN HYDRO AIR VENTS - SIERRA MADRE | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 36922.66 | 0 | 0 | 0
PJ0004790 | M&R HOUS 14/15: INSTALL HOFFMAN HYDRO AIR VENTS - SIERRA MADRE | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | ES:PROVIDE CONTRACTOR SUPPORT FOR HOFFMAN HYDRONIC SIERRA MADRE | 113 | CLOSED | 1498.464 | 0 | 1279.938 | 1279.938
PJ0004790 | M&R HOUS 14/15: INSTALL HOFFMAN HYDRO AIR VENTS - SIERRA MADRE | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | IN: INSTALL HOFFMAN HYDRO AIR VENT-SIERRA MDRE TWRS | 113 | CLOSED | 384.336 | 0 | 624.546 | 624.546
PJ0004790 Total | [7 empty] | 431812.3833 | 0 | 394108.9073 | 394108.9073
PJ0004789 | M&R HOUS 14/15: REPLACE ROOF AT TOWER 3-SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | AD: JOC 13.030.024 MAINO | 113 | CLOSED | 105085.5239 | 0 | 105085.5239 | 105085.5239
PJ0004789 | M&R HOUS 14/15: REPLACE ROOF AT TOWER 3-SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | AD: QUAGLINO ROOFING | 113 | CLOSED | 10681.2429 | 0 | 11727.2 | 11727.2
PJ0004789 | M&R HOUS 14/15: REPLACE ROOF AT TOWER 3-SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 0 | 0 | 0 | 0
PJ0004789 | M&R HOUS 14/15: REPLACE ROOF AT TOWER 3-SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: REPLACE ROOF AT TOWER 3-SIERRA MADRE | 113 | CLOSED | 640.56 | 0 | 519.036 | 519.036
PJ0004789 Total | [7 empty] | 116407.3268 | 0 | 117331.7599 | 117331.7599
PJ0004788 | M&R HOUS 14/15: REPAVE/GRADE SIERRA MADRE RECREATION AREA | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | AD: JOC 13.030.028 MAINO | 113 | CLOSED | 43921.3172 | 0 | 43692.1981 | 43692.1981
PJ0004788 | M&R HOUS 14/15: REPAVE/GRADE SIERRA MADRE RECREATION AREA | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 4503.74 | 0 | 0 | 0
PJ0004788 | M&R HOUS 14/15: REPAVE/GRADE SIERRA MADRE RECREATION AREA | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: REPAVE/GRADE SIERRA MADRE RECREATION AREA | 113 | CLOSED | 384.336 | 0 | 192.168 | 192.168
PJ0004788 Total | [7 empty] | 48809.3932 | 0 | 43884.3661 | 43884.3661
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | AD: GOSS ENGINEERING | 113 | CLOSED | 3210 | 0 | 3210 | 3210
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | AD: JOC 13.030.025 MAINO | 113 | CLOSED | 165351.0162 | 0 | 165351.0162 | 165351.0162
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 17645.67 | 0 | 0 | 0
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | EL:PROVIDE POC FOR ELECTRICAL CONTRACTOR | 113 | CLOSED | 3600.6814 | 0 | 2512.38 | 2512.38
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | ES:PROVIDE PROJECT SUPPORT FOR SIERRA MADRE 1,1,2 MAU EF UPGRADE | 113 | CLOSED | 2098.464 | 0 | 2497.44 | 2497.44
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | IN: MECHANICAL/EXHAUST SYSTEM UPGRADE - SIERRA MADRE T0, T1, &T2 | 113 | CLOSED | 640.56 | 0 | 480.42 | 480.42
PJ0004787 | M&R HOUS 14/15: MECHANICAL/EXHAUST SYS UPGRADE - S. M. T 0/1/2 | MOLLAN, CHERYL L. | CLOSED | 2014-02-27 | LO:INSTALL ORANGE CORE ON ROOF ACCESS LADERS SIERRA MADRE | 113 | CLOSED | 468.264 | 0 | 58.044 | 58.044
PJ0004787 Total | [7 empty] | 193014.6556 | 0 | 174109.3002 | 174109.3002
PJ0004784 | M&R HOUS 14/15: RESURFACE COMMUNITY CENTER FLOOR-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | AD: FLOOR CONNECTION | 170 | CLOSED | 25455.3 | 0 | 25455.3 | 25455.3
PJ0004784 | M&R HOUS 14/15: RESURFACE COMMUNITY CENTER FLOOR-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 2633.18 | 0 | 0 | 0
PJ0004784 | M&R HOUS 14/15: RESURFACE COMMUNITY CENTER FLOOR-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | IN: RESURFACE COMMUNITY CENTER FLOOR-CERRO VISTA | 170 | CLOSED | 64.056 | 0 | 128.112 | 128.112
PJ0004784 | M&R HOUS 14/15: RESURFACE COMMUNITY CENTER FLOOR-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | PCV CA: REMOVE TOILET PARTITIONS | 170 | CLOSED | 376.6718 | 0 | 392.442 | 392.442
PJ0004784 | M&R HOUS 14/15: RESURFACE COMMUNITY CENTER FLOOR-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | PCV PL: REMOVE TOILETS | 170 | CLOSED | 436.1506 | 0 | 65.292 | 65.292
PJ0004784 Total | [7 empty] | 28965.3584 | 0 | 26041.146 | 26041.146
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | AD: ASAP REPROGRAPHICS | 170E | CLOSED | 0 | 0 | 68.6405 | 68.6405
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | AD: FLOOR CONNECTION | 170E | CLOSED | 3263.5 | 0 | 3263.5 | 3263.5
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | AD: JOC 14.033.006 MAINO | 170E | CLOSED | 133309.4061 | 0 | 124726.6365 | 124726.6365
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | AD: STATE FIRE MARSHAL FEES | 170E | CLOSED | 1000 | 0 | 527.5882 | 527.5882
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | 170E | CLOSED | 12169.99 | 0 | 0 | 0
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | EL: ELECTRICAL FOR CUSTODIAL BREAK RM PROJECT AT CERRO VISTA | 170E | CLOSED | 358.2197 | 0 | 338.247 | 338.247
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | IN: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | 170E | CLOSED | 825.1219 | 0 | 1165.626 | 1165.626
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | LA: LANDSCAPING FOR CUSTODIAL BREAK RM PROJECT AT CERRO VISTA | 170E | CLOSED | 222.5779 | 0 | 140.112 | 140.112
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | LO: LOCKS FOR FOR CUSTODIAL BREAK RM PROJECT AT CERRO VISTA | 170E | CLOSED | 1238.7374 | 0 | 391.386 | 391.386
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | PA: PAINTING FOR CUSTODIAL BREAK RM PROJECT AT CERRO VISTA | 170E | CLOSED | 8209.7413 | 0 | 2697.762 | 2697.762
PJ0004783 | M&R HOUS 14/15: CONSTRUCT NEW CUSTODIAL BREAK ROOM-CERRO VISTA | NORTON, DAVE | CLOSED | 2014-02-27 | PCV PL: PLUMBING FOR CUSTODIAL BREAK RM PROJECT AT CERRO VISTA | 170E | CLOSED | 365.0918 | 0 | 164.6016 | 164.6016
PJ0004783 Total | [7 empty] | 160962.3862 | 0 | 133484.0998 | 133484.0998
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | AD: GARCIA AND SONS | RESIDENCE | CLOSED | 5350 | 0 | 5136 | 5136
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | AD: MAINO LVPW | RESIDENCE | CLOSED | 5350 | 0 | 4859.94 | 4859.94
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | CA: NORTH MOUNTAIN HYDRATION STATIONS | RESIDENCE | CLOSED | 15341.2422 | 0 | 8801.67 | 8801.67
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 5327.34 | 0 | 0 | 0
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | EL: HYDRATION STATIONS AT N. MOUNTAIN DORMS (VARIOUS) | RESIDENCE | CLOSED | 3000.9857 | 0 | 2116.416 | 2116.416
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | IN: M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | RESIDENCE | CLOSED | 565.152 | 0 | 176.61 | 176.61
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | PCV PL: HYDRATION STATIONS FOR PCV AND CV (1 EACH) | RESIDENCE | CLOSED | 5122.44 | 0 | 4441.872 | 4441.872
PJ0004782 | M&R HOUS 14/15: INSTALL HYDRATION STATIONS - APTS & N MTN | GONZALES, ALBERT | CLOSED | 2014-02-27 | PL: INSTALL HYDRATION STATIONS AT NORTH MOUNTAIN DORMS | RESIDENCE | CLOSED | 12618.9266 | 0 | 10498.98 | 10498.98
PJ0004782 Total | [7 empty] | 52676.0865 | 0 | 36031.488 | 36031.488
PJ0004781 | M&R HOUS 14/15: FACILITY CONDITION ASSESSMENT - VARIOUS AREAS | NEEL, JOEL | CLOSED | 2014-02-27 | AD: ISES CORPORATION | RESIDENCE | CLOSED | 40949.1568 | 0 | 40930.71 | 40930.71
PJ0004781 | M&R HOUS 14/15: FACILITY CONDITION ASSESSMENT - VARIOUS AREAS | NEEL, JOEL | CLOSED | 2014-02-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004781 Total | [7 empty] | 40949.1568 | 0 | 40930.71 | 40930.71
PJ0004780 | EMERGENCY RESPONSE TO UTILIDOR LEAK 2/22/14 BLDG 46 & 60 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-02-25 | AD: BOB'S CRANE | U-UDOR | CLOSED | 0 | 0 | 1650 | 1650
PJ0004780 | EMERGENCY RESPONSE TO UTILIDOR LEAK 2/22/14 BLDG 46 & 60 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-02-25 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0004780 | EMERGENCY RESPONSE TO UTILIDOR LEAK 2/22/14 BLDG 46 & 60 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-02-25 | CPE: SUPPORT FOR UTILIDOR LEAK AT NATATORIUM - FEB. 2014 | U-UDOR | CLOSED | 0 | 0 | 5691.575 | 5691.575
PJ0004780 | EMERGENCY RESPONSE TO UTILIDOR LEAK 2/22/14 BLDG 46 & 60 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-02-25 | EL: SUPPORT FOR UTILIDOR LEAK AT NATATORIUM - FEB. 2014 | U-UDOR | CLOSED | 0 | 0 | 62.52 | 62.52
PJ0004780 | EMERGENCY RESPONSE TO UTILIDOR LEAK 2/22/14 BLDG 46 & 60 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-02-25 | ES: SUPPORT FOR UTILIDOR LEAK AT NATATORIUM - FEB. 2014 | U-UDOR | CLOSED | 0 | 0 | 26.015 | 26.015
PJ0004780 | EMERGENCY RESPONSE TO UTILIDOR LEAK 2/22/14 BLDG 46 & 60 (MAINT) | BRENNAN, MICHAEL | CLOSED | 2014-02-25 | PL: SUPPORT FOR UTILIDOR LEAK AT NATATORIUM - FEB. 2014 | U-UDOR | CLOSED | 0 | 0 | 891.51 | 891.51
PJ0004780 Total | [7 empty] | 0 | 0 | 8321.62 | 8321.62
PJ0004779 | MOTT BLEACHER MODIFICATION | DILLON, JEFFREY | HOLD | 2014-02-19 | PM: MOTT BLEACHER MODIFICATION | 042 | OPEN | 0 | 0 | 0 | 0
PJ0004779 | MOTT BLEACHER MODIFICATION | DILLON, JEFFREY | HOLD | 2014-02-19 | SM: MOTT BLEACHER MODIFICATION | 042 | OPEN | 0 | 0 | 0 | 0
PJ0004779 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | AD: MORRO BAY CABINETS | 051 | CLOSED | 4713.7887 | 0 | 4678.04 | 4678.04
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | AD: SAN LUIS MARBLE | 051 | CLOSED | 3711.7979 | 0 | 3711.7979 | 3711.7979
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | AD: WINE RACK PURCHASE | 051 | CLOSED | 802.5 | 0 | 545.35 | 545.35
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | CA: PRESIDENTS LAUNDRY ROOM REMODEL | 051 | CLOSED | 2468.9033 | 0 | 6435.486 | 6435.486
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 181.21 | 0 | 0 | 0
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | IN: INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | 051 | CLOSED | 256.224 | 0 | 170.022 | 170.022
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | PA: PAINT LAUNDRY ROOM AT PRESIDENT'S RESIDENCE | 051 | CLOSED | 0 | 0 | 495.264 | 495.264
PJ0004778 | INSTALL CABINETRY AND WINE RACK AT UNIVERSITY RESIDENCE | NORTON, DAVE | CLOSED | 2014-02-14 | PL: PRESIDENTS HOUSE LAUNDRY ROOM REMODEL | 051 | CLOSED | 1021.6482 | 0 | 1808.1719 | 1808.1719
PJ0004778 Total | [7 empty] | 13156.0721 | 0 | 17844.1318 | 17844.1318
PJ0004777 | WATER LEAK ON FIRE LINE - CAL POLY PIER 228 | GONZALES, ALBERT M. | CLOSED | 2014-02-20 | AD: PREMIER SCAFFOLD | 228 | CLOSED | 8421.97 | 0 | 8421.97 | 8421.97
PJ0004777 | WATER LEAK ON FIRE LINE - CAL POLY PIER 228 | GONZALES, ALBERT M. | CLOSED | 2014-02-20 | AD: RICK TEIXEIRA WELDING | 228 | CLOSED | 1070 | 0 | 1070 | 1070
PJ0004777 | WATER LEAK ON FIRE LINE - CAL POLY PIER 228 | GONZALES, ALBERT M. | CLOSED | 2014-02-20 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 1212.19 | 0 | 0 | 0
PJ0004777 | WATER LEAK ON FIRE LINE - CAL POLY PIER 228 | GONZALES, ALBERT M. | CLOSED | 2014-02-20 | EL: ASSIST WITH REPAIR | 228 | CLOSED | 1800.6814 | 0 | 539.328 | 539.328
PJ0004777 | WATER LEAK ON FIRE LINE - CAL POLY PIER 228 | GONZALES, ALBERT M. | CLOSED | 2014-02-20 | IN: WATER LEAK ON FIRE LINE - CAL POLY PIER 228 | 228 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004777 Total | [7 empty] | 12632.9534 | 0 | 10159.41 | 10159.41
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | AD: CAME SECURITY | 040 | CLOSED | 347.75 | 0 | 347.75 | 347.75
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | AD: FLOOR CONNECTION | 040 | CLOSED | 1600.2278 | 0 | 1600.2278 | 1600.2278
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | AD: J.L. FASULO DRYWALL | 040 | CLOSED | 2996 | 0 | 2162.47 | 2162.47
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | AD: THE SIGN PLACE | 040 | CLOSED | 454.75 | 0 | 480.43 | 480.43
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | ANTS: PROGRAMMING FOR PANIC BUTTONS IN BLDG. 40 RM. 112 | 040 | CLOSED | 96.096 | 0 | 24.024 | 24.024
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 673.07 | 0 | 0 | 0
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | EL:INSTALL NEW ELECTRICAL AND RECONFIGURE LIGHTING BLDG 40, 112 | 040 | CLOSED | 5100.6862 | 0 | 1586.1336 | 1586.1336
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | ES:RECONFIGURE EXISTING HVAC AND ADD NEW AS NEEDED BLDG 40,112 | 040 | CLOSED | 3701.1862 | 0 | 1774.884 | 1774.884
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | IN: DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | 040 | CLOSED | 128.112 | 0 | 160.14 | 160.14
PJ0004774 | DIVIDE OFFICE SPACE INTO TWO ROOMS - BLDG 40 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2014-02-12 | PA:PAINT NEW WALL BLDG 40, ROOM 112 | 040 | CLOSED | 1664.736 | 0 | 524.184 | 524.184
PJ0004774 Total | [7 empty] | 16762.6141 | 0 | 8660.2434 | 8660.2434
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPOOT BASEBALL V. UC IRVINE - 5/9-5/11 | 161 | CLOSED | 0 | 0 | 179.466 | 179.466
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPORT BASEBALL V. CALIFORNIA - 3/21 | 161 | CLOSED | 0 | 0 | 54.738 | 54.738
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPORT BASEBALL V. CSU FULLERTON - 4/17-4/19 | 161 | CLOSED | 0 | 0 | 128.964 | 128.964
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPORT BASEBALL V. KANSAS ST. - 2/14-2/16 | 161 | CLOSED | 0 | 0 | 86.628 | 86.628
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPORT BASEBALL V. UC DAVIS - 3/29 | 161 | CLOSED | 0 | 0 | 139.044 | 139.044
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPORT BASEBALL V. UCSB - 4/6 | 161 | CLOSED | 0 | 0 | 74.328 | 74.328
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | CU: SUPPORT BASEBALL V. WAGNER - 3/15 | 161 | CLOSED | 0 | 0 | 144.522 | 144.522
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | EL: SUPPLY ADDITIONAL POWER FOR DINING CONCESSIONS | 161 | CLOSED | 0 | 0 | 303.372 | 303.372
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. CALIFORNIA - 3/21-3/24 | 161 | CLOSED | 0 | 0 | 1468.368 | 1468.368
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. CSU BAKERSFIELD - 4/1 | 161 | CLOSED | 0 | 0 | 526.014 | 526.014
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. CSU FULLERTON - 4/17-4/19 | 161 | CLOSED | 0 | 0 | 2231.238 | 2231.238
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. N. ILLINOIS - 3/11-3/13 | 161 | CLOSED | 0 | 0 | 1521.192 | 1521.192
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. PEPPERDINE - 5/6 | 161 | CLOSED | 0 | 0 | 694.788 | 694.788
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. SANTA CLARA - 3/4 | 161 | CLOSED | 0 | 0 | 545.496 | 545.496
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. SJSU - 4/22 | 161 | CLOSED | 0 | 0 | 611.46 | 611.46
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. ST. MARY'S - 4/8 | 161 | CLOSED | 0 | 0 | 506.532 | 506.532
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. UC DAVIS - 3/28-3/30 | 161 | CLOSED | 0 | 0 | 2454.756 | 2454.756
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. UC IRVINE - 5/9-5/11 | 161 | CLOSED | 0 | 0 | 2074.1998 | 2074.1998
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. UCSB - 4/4-4/6 | 161 | CLOSED | 0 | 0 | 1529.292 | 1529.292
PJ0004772 | 13/14: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2014-02-13 | LA: SUPPORT BASEBALL V. WAGNER - 3/14-3/16 | 161 | CLOSED | 0 | 0 | 1606.548 | 1606.548
PJ0004772 Total | [7 empty] | 0 | 0 | 16880.9458 | 16880.9458
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: APC CONTRACTORS | 052 | CLOSED | 10807 | 0 | 10665.76 | 10665.76
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 28890 | 0 | 30263.8479 | 30263.8479
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 133.215 | 133.215
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: FLOOR CONNECTION | 052 | CLOSED | 5885 | 0 | 5505.15 | 5505.15
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: JOC 13.031.041 MAINO | 052 | CLOSED | 22362.7432 | 0 | 22304.5031 | 22304.5031
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: MACDONALD COMPANY | 052 | CLOSED | 1228.0604 | 0 | 1228.0604 | 1228.0604
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 052 | CLOSED | 5350 | 0 | 4798.95 | 4798.95
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 3349.7313 | 0 | 1832.1824 | 1832.1824
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: QUARESMA DRYWALL | 052 | CLOSED | 2861.18 | 0 | 2861.18 | 2861.18
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: SLO COUNTY AIR POLLUTION CONTROL DISTRICT FEES | 052 | CLOSED | 0 | 0 | 402 | 402
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 99.63 | 99.63
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | CA: REPLACE WINDOW IN BLDG 52 ROM D4 | 052 | CLOSED | 465.552 | 0 | 1002.21 | 1002.21
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 2906.44 | 0 | 0 | 0
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | EL: DISSCONNECT ELECTRICAL SERVICE AT 82A AND MINOR WORK AT 52 | 052 | CLOSED | 3000.6814 | 0 | 1432.908 | 1432.908
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | IN: SP 13/14: RELOCATE CP ARTS - 082A-M012 (#6) | 052 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | ITS: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | 052 | CLOSED | 0 | 0 | 3575.8 | 3575.8
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | LO: REKEY 052 ROOMS D1-D5 FOR CAL POLY ARTS DEPT | 052 | CLOSED | 978.2958 | 0 | 1567.146 | 1567.146
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | PA: PAINT ALL ROOMS BUILDING 52 ROOMS D1A-D5 | 052 | CLOSED | 3602.2916 | 0 | 4804.116 | 4804.116
PJ0004769 | SP 13/14: RELOCATE CAL POLY ARTS - 082A-M012 (# 6) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | PL: SUPPORT DEMO OF CAL POLY ARTS MODULAR | 052 | CLOSED | 3211.68 | 0 | 888.36 | 888.36
PJ0004769 Total | [7 empty] | 95154.8797 | 0 | 93621.2428 | 93621.2428
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 40660 | 0 | 47949.4178 | 47949.4178
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 262.578 | 262.578
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: COMP VIEW, INC. | 052 | CLOSED | 0 | 0 | 30043.7382 | 30043.7382
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: FLOOR CONNECTION | 052 | CLOSED | 11235 | 0 | 6493.5625 | 6493.5625
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: JOC 13.030.042 MAINO | 052 | CLOSED | 10908.65 | 0 | 8905.1392 | 8905.1392
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: JOC 13.031.044 MAINO | 052 | CLOSED | 0 | 0 | 9121.6858 | 9121.6858
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: JOC 14.033.016 MAINO | 052 | CLOSED | 0 | 0 | 6703.8282 | 6703.8282
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 12165.9 | 0 | 2748.2736 | 2748.2736
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 98.63 | 98.63
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 9068.58 | 0 | 0 | 0
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | EL:ELECTRICAL DEMOLITION OF E28-E30 | 052 | CLOSED | 5101.3663 | 0 | 3932.1242 | 3932.1242
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | IN: SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52(#2) | 052 | CLOSED | 256.224 | 0 | 198.756 | 198.756
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | ITS: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | 052 | CLOSED | 0 | 0 | 10569.92 | 10569.92
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | LO: RE-KEY FOR DEPARTMENT USE E28-E30 | 052 | CLOSED | 258.2958 | 0 | 224.088 | 224.088
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | PA: PAINT ROOMS E28-E30 | 052 | CLOSED | 3242.2916 | 0 | 3683.634 | 3683.634
PJ0004767 | SP 13/14: CONSTRUCT UNIVERSITY MEETING SPACE - BLD 52 (# 2) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | PL: PLUMBING DEMOLITION OF E28-E30 | 052 | CLOSED | 5559.5468 | 0 | 4579.8206 | 4579.8206
PJ0004767 Total | [7 empty] | 98455.8546 | 0 | 135515.1962 | 135515.1962
PJ0004766 | SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (# 1) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 98.63 | 98.63
PJ0004766 | SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (# 1) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 830.41 | 0 | 0 | 0
PJ0004766 | SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (# 1) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | CU:CUSTODIAL CLEANING OF BUILDING 52 | 052 | CLOSED | 7899.4057 | 0 | 5280.348 | 5280.348
PJ0004766 | SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (# 1) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | IN: SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (#1) | 052 | CLOSED | 512.448 | 0 | 256.224 | 256.224
PJ0004766 | SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (# 1) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | MO: MOVE FURNITURE TO SURPLUS | 052 | CLOSED | 3966.084 | 0 | 1917.237 | 1917.237
PJ0004766 | SP 13/14: CLEAN ENTIRE D-WING - BLD 52 (# 1) | MCNALLY, CURTIS | CLOSED | 2014-02-11 | PL: REMOVE SINK IN E4 | 052 | CLOSED | 522.336 | 0 | 604.32 | 604.32
PJ0004766 Total | [7 empty] | 13730.6837 | 0 | 8156.759 | 8156.759
PJ0004765 | INSTALL KITCHEN BREAK AREA - HOUSING DEPOT OFFICE - 371B RM 100 | NORTON, DAVE | CLOSED | 2014-02-03 | AD: MORRO BAY CABINETS | 371B | CLOSED | 5331.81 | 0 | 5331.81 | 5331.81
PJ0004765 | INSTALL KITCHEN BREAK AREA - HOUSING DEPOT OFFICE - 371B RM 100 | NORTON, DAVE | CLOSED | 2014-02-03 | CP: PROJECT CONTINGENCY | 371B | CLOSED | 1180.39 | 0 | 0 | 0
PJ0004765 | INSTALL KITCHEN BREAK AREA - HOUSING DEPOT OFFICE - 371B RM 100 | NORTON, DAVE | CLOSED | 2014-02-03 | IN: INSTALL KITCHEN BREAK AREA - HOUSING DEPOT - 371B RM 100 | 371B | CLOSED | 192.168 | 0 | 192.168 | 192.168
PJ0004765 | INSTALL KITCHEN BREAK AREA - HOUSING DEPOT OFFICE - 371B RM 100 | NORTON, DAVE | CLOSED | 2014-02-03 | PCV CA: INSTALL KITCHEN BREAK AREA - HOUSING DEPOT | 371B | CLOSED | 807.5984 | 0 | 225.552 | 225.552
PJ0004765 | INSTALL KITCHEN BREAK AREA - HOUSING DEPOT OFFICE - 371B RM 100 | NORTON, DAVE | CLOSED | 2014-02-03 | PCV EL: INSTALL KITCHEN BREAK AREA - HOUSING DEPOT | 371B | CLOSED | 4471.3627 | 0 | 2594.664 | 2594.664
PJ0004765 | INSTALL KITCHEN BREAK AREA - HOUSING DEPOT OFFICE - 371B RM 100 | NORTON, DAVE | CLOSED | 2014-02-03 | PCV PL: INSTALL KITCHEN BREAK AREA - HOUSING DEPOT | 371B | CLOSED | 1001.0988 | 0 | 130.584 | 130.584
PJ0004765 Total | [7 empty] | 12984.428 | 0 | 8474.778 | 8474.778
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: ASAP REPROGRAPHICS | 070 | CLOSED | 0 | 0 | 85.54 | 85.54
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: DIVISION OF STATE ARCHITECT | 070 | CLOSED | 2660 | 0 | 2660 | 2660
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: ENGLEKIRK AND SABOL | 070 | CLOSED | 2026 | 0 | 2026 | 2026
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: MAINO LVPW | 070 | CLOSED | 4860 | 0 | 4842 | 4842
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: ONTRACK SHIPPING | 070 | CLOSED | 0 | 0 | 101.83 | 101.83
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: PMSM ARCHITECTS | 070 | CLOSED | 69390 | 0 | 69390 | 69390
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | AD: WILLDAN ENGINEERING | 070 | CLOSED | 1786.72 | 0 | 1786.65 | 1786.65
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | IN: PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 | 070 | CLOSED | 213.52 | 0 | 160.14 | 160.14
PJ0004763 | PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-06 | PM: PROVIDE DESIGN FOR OFFICE EXPANSION - BLD 70 (NO OVERHEAD) | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0004763 Total | [7 empty] | 80936.24 | 0 | 81052.16 | 81052.16
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | AD: BKM FURNISHINGS | 192 | CLOSED | 32489.6833 | 0 | 31394.1745 | 31394.1745
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | AD: FLOOR CONNECTION | 192 | CLOSED | 3702.2 | 0 | 3702.2 | 3702.2
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | AD: STATE FIRE MARSHAL FEES | 192 | CLOSED | 0 | 0 | 807.8 | 807.8
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | AD: THE SIGN PLACE | 192 | CLOSED | 4077.7486 | 0 | 4077.7486 | 4077.7486
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 3698.8 | 0 | 0 | 0
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | CU: STRIP CONCRETE FLOOR FINISH | 192 | CLOSED | 510.9617 | 0 | 368.748 | 368.748
PJ0004762 | INTERIOR UPGRADES TO BUILDING 192 | HICKS, MICHAEL | CLOSED | 2014-02-04 | IN: INTERIOR UPGRADES TO BUILDING 192 | 192 | CLOSED | 285.0492 | 0 | 96.084 | 96.084
PJ0004762 Total | [7 empty] | 44764.4428 | 0 | 40446.7551 | 40446.7551
PJ0004761 | SP 13/14: MEMORIAL PLAZA CONCRETE WORK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-03 | AD: JOC 13.029.049 MAINO | 061 | CLOSED | 48782.6482 | 0 | 48782.6803 | 48782.6803
PJ0004761 | SP 13/14: MEMORIAL PLAZA CONCRETE WORK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-03 | AD: WALLACE GROUP | 061 | CLOSED | 1819 | 0 | 1409.725 | 1409.725
PJ0004761 | SP 13/14: MEMORIAL PLAZA CONCRETE WORK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 5252.31 | 0 | 0 | 0
PJ0004761 | SP 13/14: MEMORIAL PLAZA CONCRETE WORK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2014-02-03 | IN: SP 13/14: MEMORIAL PLAZA CONCRETE WORK - SPANOS STADIUM | 061 | CLOSED | 512.448 | 0 | 352.308 | 352.308
PJ0004761 Total | [7 empty] | 56366.4062 | 0 | 50544.7133 | 50544.7133
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | AD: MORRO BAY CABINETS | 061 | CLOSED | 13090.38 | 0 | 12638.3264 | 12638.3264
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | AD: PHIL'S CUSTOM WOODWORKING | 061 | CLOSED | 208.65 | 0 | 208.65 | 208.65
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | AD: TEMPLE BUILDERS | 061 | CLOSED | 1016.5 | 0 | 575.9275 | 575.9275
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | CA: REHANG PICTURES | 061 | CLOSED | 1566.1235 | 0 | 600.564 | 600.564
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 259.4 | 0 | 0 | 0
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | IN: PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | 061 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004760 | PAINTING AND LOCKS FOR PRESIDENT'S SUITE - SPANOS STADIUM | GONZALES, ALBERT M. | CLOSED | 2014-01-23 | PA:TOUCH UP PAINT IN PRESIDENTS SUITE | 061 | CLOSED | 1357.2728 | 0 | 99.09 | 99.09
PJ0004760 Total | [7 empty] | 17626.4383 | 0 | 14218.6419 | 14218.6419
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | AD: APC CONTRACTORS | 005 | CLOSED | 5296.5 | 0 | 5328.6 | 5328.6
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | AD: BRANDOW & JOHNSON | 005 | CLOSED | 4895.25 | 0 | 4895.25 | 4895.25
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | AD: ENGLEKIRK AND SABOL | 005 | CLOSED | 642 | 0 | 612.04 | 612.04
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | AD: MCKENNA ENVIRONMENTAL | 005 | CLOSED | 2664.3 | 0 | 2300.5 | 2300.5
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | AD: STATE FIRE MARSHAL FEES | 005 | CLOSED | 0 | 0 | 175.33 | 175.33
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | AD: VERNON EDWARDS | 005 | CLOSED | 620.6 | 0 | 577.8 | 577.8
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | CA: CORE CONCRETE AND DEMO WALL MATERIAL | 005 | CLOSED | 1034.2703 | 0 | 1558.7593 | 1558.7593
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 437.7 | 0 | 0 | 0
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | EL: REMOVE AND RE-INSTALL 1 LIGHT FIXTURE - BLDG. 5 RM. 225B | 005 | CLOSED | 269.664 | 0 | 194.778 | 194.778
PJ0004758 | PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | MCNALLY, CURTIS | CLOSED | 2014-01-15 | IN: PASSIVE COOLING SYSTEM FOR BLDG. 05 RM. 314 | 005 | CLOSED | 256.224 | 0 | 262.812 | 262.812
PJ0004758 Total | [7 empty] | 16116.5083 | 0 | 15905.8693 | 15905.8693
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | AD: INNOVATION COMMERCIAL FLOORING | 027 | CLOSED | 909.5 | 0 | 711.8175 | 711.8175
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | AD: JOC 13.030.005 MAINO | 027 | CLOSED | 9019.0086 | 0 | 9019.0086 | 9019.0086
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | AD: MCKENNA ENVIRONMENTAL | 027 | CLOSED | 4750.8 | 0 | 2132.51 | 2132.51
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 2313.02 | 0 | 0 | 0
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 027 | CLOSED | 0 | 0 | 16.8 | 16.8
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | EL: REMOVE ELECTRICAL AT CASHIER'S BOOTH | 027 | CLOSED | 2040.6814 | 0 | 766.068 | 766.068
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | ES: RELOCATE T-STAT | 027 | CLOSED | 3054.482 | 0 | 352.974 | 352.974
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | IN: DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | 027 | CLOSED | 128.112 | 0 | 224.196 | 224.196
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | LO: REMOVE LOCK FROM EXISTING DOOR | 027 | CLOSED | 116.088 | 0 | 116.088 | 116.088
PJ0004757 | DEMOLITION OF CASHIER BOOTH IN HEALTH CENTER LOBBY | NORTON, DAVE | CLOSED | 2014-01-10 | PA: PAINT TOUCH UP | 027 | CLOSED | 2974.56 | 0 | 440.184 | 440.184
PJ0004757 Total | [7 empty] | 25306.252 | 0 | 13779.6461 | 13779.6461
PJ0004756 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES -VARIOUS BLD(MAINT) | POLVI, STEVEN | CLOSED | 2014-01-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004756 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES -VARIOUS BLD(MAINT) | POLVI, STEVEN | CLOSED | 2014-01-27 | EL: CORRECT SFM INSPECTION DEFICIENCIES - BLDGS. 208 & 187 | GENERAL | CLOSED | 0 | 0 | 392.303 | 392.303
PJ0004756 | CORRECT FIRE MARSHAL INSPECTION DEFICIENCIES -VARIOUS BLD(MAINT) | POLVI, STEVEN | CLOSED | 2014-01-27 | LO: CORRECT SFM INSPECTION DEFICIENCIES - OS&Y VALVES - 187 & 22 | GENERAL | CLOSED | 0 | 0 | 166.74 | 166.74
PJ0004756 Total | [7 empty] | 0 | 0 | 559.043 | 559.043
PJ0004754 | SR 13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | LAMPMAN, GREG | CLOSED | 2014-01-27 | AD: JOC 13.029.048 MAINO | 013 | CLOSED | 32981.49 | 0 | 32981.49 | 32981.49
PJ0004754 | SR 13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | LAMPMAN, GREG | CLOSED | 2014-01-27 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0004754 | SR 13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | LAMPMAN, GREG | CLOSED | 2014-01-27 | EL: MOVE FLOOR OUTLET AS DIRECTED | 013 | CLOSED | 449.44 | 0 | 335.21 | 335.21
PJ0004754 | SR 13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | LAMPMAN, GREG | CLOSED | 2014-01-27 | IN: SR13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | 013 | CLOSED | 213.52 | 0 | 160.14 | 160.14
PJ0004754 | SR 13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | LAMPMAN, GREG | CLOSED | 2014-01-27 | LO: INSTALL ORANGE CORE FOR CONTRACTOR - BLDG. 13 RM. 113 | 013 | CLOSED | 0 | 0 | 48.37 | 48.37
PJ0004754 | SR 13/14: REPLACE RAISED FLOORING - BLD 13 RM 113 | LAMPMAN, GREG | CLOSED | 2014-01-27 | PA: PAINT EAST WALL OF BLDG. 13 RM. 113 AFTER FLOOR REPLACEMENT | 013 | CLOSED | 463.07 | 0 | 123.675 | 123.675
PJ0004754 Total | [7 empty] | 34107.52 | 0 | 33648.885 | 33648.885
PJ0004752 | HOSE BIB INSTALL FOR PRESCHOOL LAB PLAYGROUND | LAMPMAN, GREG | CLOSED | 2014-01-16 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 34.09 | 0 | 0 | 0
PJ0004752 | HOSE BIB INSTALL FOR PRESCHOOL LAB PLAYGROUND | LAMPMAN, GREG | CLOSED | 2014-01-16 | IN: HOSE BIB INSTALL FOR PRESCHOOL LAB PLAYGROUND | 038 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004752 | HOSE BIB INSTALL FOR PRESCHOOL LAB PLAYGROUND | LAMPMAN, GREG | CLOSED | 2014-01-16 | LA: INSTALL HOSE BIB | 038 | CLOSED | 276.6398 | 0 | 371.1196 | 371.1196
PJ0004752 Total | [7 empty] | 374.7858 | 0 | 435.1756 | 435.1756
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: APC CONTRACTORS | 042 | CLOSED | 9012.503 | 0 | 8866.02 | 8866.02
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: BENCHMARK WOODWORKS | 042 | CLOSED | 14462.12 | 0 | 14462.12 | 14462.12
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: FENCE FACTORY | 042 | CLOSED | 991.89 | 0 | 898.8 | 898.8
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: FLOOR CONNECTION | 042 | CLOSED | 30187.91 | 0 | 29331.91 | 29331.91
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: GOSS ENGINEERING | 042 | CLOSED | 6264.85 | 0 | 5982.6375 | 5982.6375
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: HOLLMAN LOCKERS | 042 | CLOSED | 148572.71 | 0 | 148533.2591 | 148533.2591
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: J.L. FASULO DRYWALL | 042 | CLOSED | 8674.49 | 0 | 8674.49 | 8674.49
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: MARCHESE CONSTRUCTION | 042 | CLOSED | 1599.65 | 0 | 1599.65 | 1599.65
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: MCKENNA ENVIRONMENTAL | 042 | CLOSED | 1585.74 | 0 | 1527.96 | 1527.96
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: MEATHEAD MOVERS | 042 | CLOSED | 2471.7 | 0 | 2471.7 | 2471.7
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: MORELAND THOMPSON | 042 | CLOSED | 3256.01 | 0 | 3256.01 | 3256.01
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: NORMAN S. WRIGHT-DUCKWORTH | 042 | CLOSED | 12077.625 | 0 | 12077.6357 | 12077.6357
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: REA AND LUKER | 042 | CLOSED | 1284 | 0 | 1284 | 1284
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | AD: TAYLOR RENTALS | 042 | CLOSED | 1070 | 0 | 2123.0405 | 2123.0405
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | CA: INSTALL OCCUPANT LOAD SIGN IN FOOTBALL LOCKER ROOM 42-114 | 042 | CLOSED | 225.552 | 0 | 144.45 | 144.45
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 042 | CLOSED | 300 | 0 | 19.2 | 19.2
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | EL: FOOTBALL LOCKER ROOM RENOVATION | 042 | CLOSED | 14080.1285 | 0 | 8370.762 | 8370.762
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | ES:FOOTBALL LOCKER ROOM | 042 | CLOSED | 14842.7908 | 0 | 27497.4344 | 27497.4344
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | IN: RENOVATE FOOTBALL LOCKER ROOM - 042 114 | 042 | CLOSED | 256.224 | 0 | 227.49 | 227.49
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | LO: FOOTBALL LOCKER ROOM | 042 | CLOSED | 532.176 | 0 | 1648.626 | 1648.626
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | MO: MOVE NEW FOOTBALL LOCKERS TO BLDG 80 STORAGE | 042 | CLOSED | 486 | 0 | 108.648 | 108.648
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | PA: PAINTING FOR FOOTBALL LOCKER ROOM RENOVATION - BLD 42 RM 114 | 042 | CLOSED | 2792.2916 | 0 | 2600.7821 | 2600.7821
PJ0004750 | RENOVATE FOOTBALL LOCKER ROOM - 042 114 | GONZALES, ALBERT M. | CLOSED | 2014-01-16 | PL: FOOTBALL LOCKER ROOM | 042 | CLOSED | 686.856 | 0 | 686.868 | 686.868
PJ0004750 Total | [7 empty] | 275713.2169 | 0 | 282393.4933 | 282393.4933
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: ALPHA FIRE CORP | 002 | CLOSED | 3317 | 0 | 3317 | 3317
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: ASAP REPROGRAPHICS | 002 | CLOSED | 0 | 0 | 248.376 | 248.376
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: FLOOR CONNECTION | 002 | CLOSED | 25729.4554 | 0 | 25729.4447 | 25729.4447
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: JOC 13.031.030 MAINO | 002 | CLOSED | 240091.2866 | 0 | 239953.6525 | 239953.6525
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: JOC 14.033.024 MAINO | 002 | CLOSED | 56727.3661 | 0 | 56727.3661 | 56727.3661
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: KI FURNISHINGS | 002 | CLOSED | 51231.7498 | 0 | 51231.7605 | 51231.7605
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: ONTRAC SHIPPING | 002 | CLOSED | 0 | 0 | 64.9597 | 64.9597
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: QUINTRON INTEGRATED SYSTEMS | 002 | CLOSED | 1198.4 | 0 | 1198.4 | 1198.4
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: RRM DESIGN GROUP | 002 | CLOSED | 43014 | 0 | 41598.1225 | 41598.1225
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: STATE FIRE MARSHAL | 002 | CLOSED | 3180.5857 | 0 | 7684.6865 | 7684.6865
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | AD: THE SIGN PLACE | 002 | CLOSED | 4026.41 | 0 | 4026.41 | 4026.41
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | CA: CREATE SIGNAGE FOR CIE, PER STATE FIRE MARSHAL - BLDG 2 RM | 002 | CLOSED | 564.96 | 0 | 508.5 | 508.5
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | CA: SECOND CARPENTRY PHASE FOR ADD'L SIGNS | 002 | CLOSED | 226.86 | 0 | 194.67 | 194.67
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 7530.96 | 0 | 0 | 0
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 002 | CLOSED | 300 | 0 | 168 | 168
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | EL: ELECTRICAL SHOP COORDINATION/DEMO | 002 | CLOSED | 3929.172 | 0 | 3077.214 | 3077.214
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | IN: DESIGN CTR FOR INNOVATION & ENTREPRENEURSHIP BLDG. 2 | 002 | CLOSED | 1425.8866 | 0 | 2917.638 | 2917.638
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | LO: PANIC HARDWARE AND LOCK REPLACEMENT | 002 | CLOSED | 2446.0297 | 0 | 11083.314 | 11083.314
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | MO: SURPLUS AND MOVE FURNITURE IN EXISTING SPACES | 002 | CLOSED | 1153.764 | 0 | 174.654 | 174.654
PJ0004747 | CTR FOR INNOVATION & ENTREPRENEURSHIP - BLD 2 RM 206, 210, 211 | DUNN, TRAVIS | CLOSED | 2014-01-15 | PA: PAINTING FOR CIE - BUILDING 2 | 002 | CLOSED | 15849.7602 | 0 | 9492.331 | 9492.331
PJ0004747 Total | [7 empty] | 461943.6461 | 0 | 459396.4995 | 459396.4995
PJ0004746 | NEW CARPET - BLD 11 RM 114 | MCNALLY, CURTIS | CLOSED | 2014-01-10 | AD: FLOOR CONNECTION | 011 | CLOSED | 2354 | 0 | 1844.7335 | 1844.7335
PJ0004746 | NEW CARPET - BLD 11 RM 114 | MCNALLY, CURTIS | CLOSED | 2014-01-10 | CA:REMOVE WALL MOUNTED SHELL AND INFILL INTERIOR DOOR | 011 | CLOSED | 1124.2703 | 0 | 1667.376 | 1667.376
PJ0004746 | NEW CARPET - BLD 11 RM 114 | MCNALLY, CURTIS | CLOSED | 2014-01-10 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 387.85 | 0 | 0 | 0
PJ0004746 | NEW CARPET - BLD 11 RM 114 | MCNALLY, CURTIS | CLOSED | 2014-01-10 | IN: NEW CARPET (CARPET ALREADY ON HAND) - BLD 11 RM 114 | 011 | CLOSED | 256.224 | 0 | 128.112 | 128.112
PJ0004746 | NEW CARPET - BLD 11 RM 114 | MCNALLY, CURTIS | CLOSED | 2014-01-10 | MO:MOVE FURNITURE | 011 | CLOSED | 144.18 | 0 | 72.432 | 72.432
PJ0004746 Total | [7 empty] | 4266.5243 | 0 | 3712.6535 | 3712.6535
PJ0004741 | SUN SHADE FOR WINDOWS IN ROLL-UP DOOR - BLDG. 192 RM. 102 | HICKS, MICHAEL | CLOSED | 2013-10-10 | AD: ATD WINDOW TINTING | 192 | CLOSED | 590.64 | 0 | 590.64 | 590.64
PJ0004741 | SUN SHADE FOR WINDOWS IN ROLL-UP DOOR - BLDG. 192 RM. 102 | HICKS, MICHAEL | CLOSED | 2013-10-10 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 65.47 | 0 | 0 | 0
PJ0004741 | SUN SHADE FOR WINDOWS IN ROLL-UP DOOR - BLDG. 192 RM. 102 | HICKS, MICHAEL | CLOSED | 2013-10-10 | IN: SUN SHADE FOR WINDOWS IN ROLL-UP DOOR - BLDG. 192 RM. 102 | 192 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004741 Total | [7 empty] | 720.166 | 0 | 654.696 | 654.696
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | AD: CAME SECURITY | 027 | CLOSED | 8768.65 | 0 | 8346 | 8346
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | AD: MACDONALD COMPANY | 027 | CLOSED | 393.225 | 0 | 388.196 | 388.196
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | ANTS:COORDINATION OF NEW SECURITY ACCESS DEVICES WITH UPD | 027 | CLOSED | 144.144 | 0 | 156.156 | 156.156
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | CA:CONTRACTOR SUPPORT FOR DRILLING HOLES IN LEAD PAINT | 027 | CLOSED | 129.6924 | 0 | 56.388 | 56.388
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 0 | 0 | 0 | 0
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | IN: INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | 027 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | LO:INSTALL NEW LOCK SET HEALTH CENTER ROOM 178 | 027 | CLOSED | 772.176 | 0 | 391.926 | 391.926
PJ0004740 | INSTALL CAME SECURITY SYSTEM - BLD 27 RMS 162 & 178 | MOLLAN, CHERYL L. | CLOSED | 2014-01-10 | PA:REMOVE PAINT ON JAMB AND REPAINT JAMB, BLDG 27, 162 | 027 | CLOSED | 416.184 | 0 | 118.728 | 118.728
PJ0004740 Total | [7 empty] | 10688.1274 | 0 | 9521.45 | 9521.45
PJ0004739 | SR 13/14: CLEANUP OF SEWER BACKUP - BLD 21 | HICKS, MICHAEL | CLOSED | 2014-01-09 | AD: BELFOR N2043001 | 021 | CLOSED | 16760.9 | 0 | 16760.9 | 16760.9
PJ0004739 | SR 13/14: CLEANUP OF SEWER BACKUP - BLD 21 | HICKS, MICHAEL | CLOSED | 2014-01-09 | CA:INSTALL RUBBER BASE IN VESTIBULE AND ROOM 05 | 021 | CLOSED | 413.8932 | 0 | 364.74 | 364.74
PJ0004739 | SR 13/14: CLEANUP OF SEWER BACKUP - BLD 21 | HICKS, MICHAEL | CLOSED | 2014-01-09 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0004739 | SR 13/14: CLEANUP OF SEWER BACKUP - BLD 21 | HICKS, MICHAEL | CLOSED | 2014-01-09 | ES: SUPPORT FOLLOWING SEWER OVERFLOW CLEAN-UP | 021 | CLOSED | 0 | 0 | 52.03 | 52.03
PJ0004739 | SR 13/14: CLEANUP OF SEWER BACKUP - BLD 21 | HICKS, MICHAEL | CLOSED | 2014-01-09 | IN: SR 13/14: CLEANUP OF SEWER BACKUP - BLD 21 | 021 | CLOSED | 106.76 | 0 | 26.69 | 26.69
PJ0004739 Total | [7 empty] | 17281.5532 | 0 | 17204.36 | 17204.36
PJ0004737 | REMOVE KRUKOW'S HUT (BAGGETT STADIUM) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-12-11 | CA: REMOVE KRUKOW'S HUT FROM BAGGETT STADIUM | 160 | CLOSED | 1506.1235 | 0 | 906.666 | 906.666
PJ0004737 | REMOVE KRUKOW'S HUT (BAGGETT STADIUM) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-12-11 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 243.35 | 0 | 0 | 0
PJ0004737 | REMOVE KRUKOW'S HUT (BAGGETT STADIUM) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-12-11 | IN: REMOVE KRUKOW'S HUT (BAGGETT STADIUM) | 160 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004737 | REMOVE KRUKOW'S HUT (BAGGETT STADIUM) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-12-11 | LA: FILL IN LAWN WHERE KRUKOW'S HUT WAS REMOVED | 160 | CLOSED | 863.424 | 0 | 233.784 | 233.784
PJ0004737 Total | [7 empty] | 2676.9535 | 0 | 1204.506 | 1204.506
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | AD: BELFOR JOC N2014002 | 061 | CLOSED | 66217.76 | 0 | 63159.27 | 63159.27
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | AD: FASULO DRYWALL | 061 | CLOSED | 2582 | 0 | 3547 | 3547
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | AD: FLOOR CONNECTION | 061 | CLOSED | 2400 | 0 | 1995 | 1995
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | AD: SANTA MARIA ACOUSTICAL - FRP REPLACEMENT | 061 | CLOSED | 4647 | 0 | 5778 | 5778
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | AD: TEMPLE BUILDERS | 061 | CLOSED | 1771 | 0 | 1827.99 | 1827.99
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | AD: VISALIA CERAMIC TILE | 061 | CLOSED | 10937 | 0 | 10937 | 10937
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | CA: INSTALL RUBBER COVE BASE & RR PARTITIONS - 061 MEN'S ROOM | 061 | CLOSED | 1266.8152 | 0 | 1267 | 1267
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | IN: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDG 60 & 61 | 061 | CLOSED | 320.28 | 0 | 266.9 | 266.9
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | LO: ADJUST DOOR CLOSER AT TICKET BOOTH AREA - SPANOS STADIUM 61 | 061 | CLOSED | 72.555 | 0 | 72.555 | 72.555
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | MO: MOVE TOILET PARTIONS & OTHER STORED ITESM - SPANOS STADIUM | 061 | CLOSED | 432 | 0 | 20.12 | 20.12
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | PA: PAINTING WALLS FROM CLEAN UP & REPAIRS | 061 | CLOSED | 2892.6874 | 0 | 915.195 | 915.195
PJ0004735 | SR 13/14: ASSESS & REPAIR SEWER BACK-UP DAMAGE - BLDGS 60 & 61 | HICKS, MICHAEL | CLOSED | 2014-01-08 | PL: SUPPORT FOR SEWER BACK-UP AT SPANOS STADIUM | 061 | CLOSED | 6930.6635 | 0 | 7911.51 | 7911.51
PJ0004735 Total | [7 empty] | 100469.7611 | 0 | 97697.54 | 97697.54
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | AD: DEEP BLUE INTEGRATION | 171A | CLOSED | 4174.07 | 0 | 4174.07 | 4174.07
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | AD: J.L. FASULO DRYWALL | 171A | CLOSED | 1070 | 0 | 1021.85 | 1021.85
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | AD: MACDONALD DOOR COMPANY | 171A | CLOSED | 2396.2008 | 0 | 2395.3876 | 2395.3876
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | AD: MORELAND THOMPSON ELECTRICAL | 171A | CLOSED | 6660.75 | 0 | 6660.75 | 6660.75
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | CP: PROJECT CONTINGENCY | 171A | CLOSED | 495.74 | 0 | 0 | 0
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | IN: ELECTROMAGNETIC DOOR HOLDERS/RELEASES ON FIRE DOORS - 171A | 171A | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004734 | ADD ELECTROMAGNETIC DOOR HOLDERS/RELEASES TO FIRE DOORS - 171A | GONZALES, ALBERT M. | CLOSED | 2013-12-31 | PA: PAINT DRYWALL PATCHES AT 9 LOCATIONS IN ALISO 171A | 171A | CLOSED | 1252.5815 | 0 | 231.21 | 231.21
PJ0004734 Total | [7 empty] | 16177.4543 | 0 | 14547.3236 | 14547.3236
PJ0004732 | CAME SECURITY PANIC BUTTON INSTALLATIONS - BLD 3 RM 100 | MOLLAN, CHERYL L. | CLOSED | 2013-12-03 | AD: CAME SECURITY | 003 | CLOSED | 642 | 0 | 642 | 642
PJ0004732 | CAME SECURITY PANIC BUTTON INSTALLATIONS - BLD 3 RM 100 | MOLLAN, CHERYL L. | CLOSED | 2013-12-03 | ANTS:CAME SECURITY PANIC BUTTON INSTALATIONS- BLD 3, RM 100 | 003 | CLOSED | 48.048 | 0 | 48.048 | 48.048
PJ0004732 | CAME SECURITY PANIC BUTTON INSTALLATIONS - BLD 3 RM 100 | MOLLAN, CHERYL L. | CLOSED | 2013-12-03 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 75.41 | 0 | 0 | 0
PJ0004732 | CAME SECURITY PANIC BUTTON INSTALLATIONS - BLD 3 RM 100 | MOLLAN, CHERYL L. | CLOSED | 2013-12-03 | IN: CAME SECURITY PANIC BUTTON INSTALLATIONS - BLD 3 RM 100 | 003 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004732 Total | [7 empty] | 829.514 | 0 | 754.104 | 754.104
PJ0004728 | RECONNECT HEATING SYSTEM IN MAIN LOUNGE - YOSEMITE 114 | LAMPMAN, GREG | CLOSED | 2013-12-06 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 1098.74 | 0 | 0 | 0
PJ0004728 | RECONNECT HEATING SYSTEM IN MAIN LOUNGE - YOSEMITE 114 | LAMPMAN, GREG | CLOSED | 2013-12-06 | ES: RE-CONNECT HEATER | 114 | CLOSED | 9731.2274 | 0 | 5090.904 | 5090.904
PJ0004728 | RECONNECT HEATING SYSTEM IN MAIN LOUNGE - YOSEMITE 114 | LAMPMAN, GREG | CLOSED | 2013-12-06 | IN: RECONNECT HEATING SYSTEM IN MAIN LOUNGE - YOSEMITE 114 | 114 | CLOSED | 192.168 | 0 | 170.022 | 170.022
PJ0004728 | RECONNECT HEATING SYSTEM IN MAIN LOUNGE - YOSEMITE 114 | LAMPMAN, GREG | CLOSED | 2013-12-06 | PA: PAINT AREA WHERE HEATER WAS REMOVED - YOSEMITE MAIN LOUNGE | 114 | CLOSED | 1064.28 | 0 | 178.092 | 178.092
PJ0004728 Total | [7 empty] | 12086.4154 | 0 | 5439.018 | 5439.018
PJ0004727 | REUPHOLSTER RED BENCHES IN UPSTAIRS LOBBY OF BONDERSON -BLDG.197 | LAMPMAN, GREG | CLOSED | 2013-11-14 | AD: RUSSCO | 197 | CLOSED | 1150.25 | 0 | 1150.25 | 1150.25
PJ0004727 | REUPHOLSTER RED BENCHES IN UPSTAIRS LOBBY OF BONDERSON -BLDG.197 | LAMPMAN, GREG | CLOSED | 2013-11-14 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 121.43 | 0 | 0 | 0
PJ0004727 | REUPHOLSTER RED BENCHES IN UPSTAIRS LOBBY OF BONDERSON -BLDG.197 | LAMPMAN, GREG | CLOSED | 2013-11-14 | IN: REUPHOLSTER RED BENCHES -UPSTAIRS LOBBY OF BONDERSON BLDG197 | 197 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004727 Total | [7 empty] | 1335.736 | 0 | 1214.306 | 1214.306
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | AD: J.L. FASULO | 034 | CLOSED | 2086.5 | 0 | 2086.5 | 2086.5
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | AD: PARC ENVIRONMENTAL | 034 | CLOSED | 3819.9 | 0 | 3819.9 | 3819.9
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | CA: REPLACE TILES AT FRONT OF DOORWAY - BLDG. 34, RM. 117 | 034 | CLOSED | 136.776 | 0 | 165.492 | 165.492
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 199.37 | 0 | 0 | 0
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | EH&S:PROVIDE CONTRACTOR SUPPORT FOR MATERIAL TESTING | 034 | CLOSED | 248.7 | 0 | 308.064 | 308.064
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | IN: REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | 034 | CLOSED | 64.056 | 0 | 128.112 | 128.112
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | LO:INSTALL ORGANGE CORE BLDG 34, ROOM 117 | 034 | CLOSED | 58.044 | 0 | 29.022 | 29.022
PJ0004725 | REMOVE TRIM AND PATCH WALL IN BLDG 34, ROOM 117 | MOLLAN, CHERYL L. | CLOSED | 2013-11-18 | PA:PAINT ROOM BLDG 34, 117 | 034 | CLOSED | 2022.192 | 0 | 2612.016 | 2612.016
PJ0004725 Total | [7 empty] | 8635.538 | 0 | 9149.106 | 9149.106
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | AD: CRAGHEAD | 112 | CLOSED | 5336.09 | 0 | 5522.27 | 5522.27
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | AD: EARTH SYSTEMS | 112 | CLOSED | 5521.2 | 0 | 3397.7101 | 3397.7101
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | AD: ENGLEKIRK AND SABOL | 112 | CLOSED | 3745 | 0 | 3531 | 3531
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | AD: MAINO CONSTRUCTION (LOW VALUE PUBLIC WORKS) | 112 | CLOSED | 4828.91 | 0 | 4828.91 | 4828.91
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 418.63 | 0 | 0 | 0
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | EH&S: | 112 | CLOSED | 257.4 | 0 | 18 | 18
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | EH&S: SAMPLES AND TESTING FOR VISTA GRANDE SOFFIT | 112 | CLOSED | 248.925 | 0 | 0 | 0
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | EL: PROVIDE 2 LIGHT TRIMS AT SOFFIT - VISTA GRANDE | 112 | CLOSED | 749.664 | 0 | 128.856 | 128.856
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | IN: STRUCTURAL ANALYSIS FOR BLDG SETTLEMENT -VISTA GRANDE | 112 | CLOSED | 192.168 | 0 | 64.056 | 64.056
PJ0004724 | STRUCTURAL ANALYSIS & RETROFIT FOR BLDG SETTLEMENT -VISTA GRANDE | NORTON, DAVE | CLOSED | 2013-12-16 | PA:PAINT PLYWOOD | 112 | CLOSED | 780.7213 | 0 | 453.744 | 453.744
PJ0004724 Total | [7 empty] | 22078.7083 | 0 | 17944.5461 | 17944.5461
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: AMERICAN MODULAR | RESIDENCE | CLOSED | 309023.7575 | 0 | 296124.9075 | 296124.9075
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: ASAP REPROGRAPHICS | RESIDENCE | CLOSED | 0 | 0 | 334.1396 | 334.1396
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: DEEP BLUE INTEGRATION | RESIDENCE | CLOSED | 5136 | 0 | 5366.05 | 5366.05
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: DIVISION OF STATE ARCHITECT | RESIDENCE | CLOSED | 1500 | 0 | 1500 | 1500
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: EARTH SYSTEMS PACIFIC | RESIDENCE | CLOSED | 6206 | 0 | 3397.25 | 3397.25
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: ENGLEKIRK AND SABOL | RESIDENCE | CLOSED | 802.5 | 0 | 802.5 | 802.5
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: JOC 14.033.007 MAINO | RESIDENCE | CLOSED | 130903.8 | 0 | 108039.612 | 108039.612
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: MORELAND THOMPSON | RESIDENCE | CLOSED | 3691.5 | 0 | 3691.5 | 3691.5
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: NORTH COAST ENGINEERING | RESIDENCE | CLOSED | 2680.35 | 0 | 2680.35 | 2680.35
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: ONTRAC & UPS SHIPPING | RESIDENCE | CLOSED | 0 | 0 | 38.5521 | 38.5521
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | AD: STATE FIRE MARSHAL | RESIDENCE | CLOSED | 0 | 0 | 3143.3711 | 3143.3711
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | ANTS: PROGRAM FIRE ALARM | RESIDENCE | CLOSED | 427.6272 | 0 | 169.44 | 169.44
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | CA: INSTALL EXTERIOR BUILDING SIGNAGE | RESIDENCE | CLOSED | 741.8532 | 0 | 652.464 | 652.464
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 19146.08 | 0 | 0 | 0
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | EH&S: FILE 10 DAY NOTICE FOR DEMO OF 2 BEDROOM RESIDENCE | RESIDENCE | CLOSED | 857.4 | 0 | 0 | 0
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | RESIDENCE | CLOSED | 0 | 0 | 93 | 93
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | EL:INSTALL OVERHEAD POWER SERVICE | RESIDENCE | CLOSED | 6600.6838 | 0 | 8345.9326 | 8345.9326
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | IN: INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | RESIDENCE | CLOSED | 1024.896 | 0 | 1200.948 | 1200.948
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | ITS: UTILITY INSTALLATION | RESIDENCE | CLOSED | 7276 | 0 | 4534 | 4534
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | LO: REMOVE AND INSTALL LOCK CORES | RESIDENCE | CLOSED | 1116.5916 | 0 | 213.234 | 213.234
PJ0004723 | INSTALL MODULAR FOR STUDENT AG HOUSING - BCEC | MCNALLY, CURTIS | CLOSED | 2013-12-17 | PL: DISCONNECT WATER AND SEWER TO AG RESIDENCE | RESIDENCE | CLOSED | 2071.6482 | 0 | 519.132 | 519.132
PJ0004723 Total | [7 empty] | 499206.6875 | 0 | 440846.3829 | 440846.3829
PJ0004722 | SP 13/14: CONCOURSE CORRECTION, PHASE 1 - BLD 061 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-12-17 | AD: JOC 13.029.008 MAINO (PARTIAL - SEE PJ 4335 FOR REMAINDER) | 061 | CLOSED | 51840.35 | 0 | 51840.35 | 51840.35
PJ0004722 | SP 13/14: CONCOURSE CORRECTION, PHASE 1 - BLD 061 (NO OVERHEAD) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-12-17 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004722 Total | [7 empty] | 51840.35 | 0 | 51840.35 | 51840.35
PJ0004721 | INSTALL WINDOW IN DOOR FOR SAFETY REASONS - BLDG. 192 RM. 211 | MARCHESE, JASON (WILL) | CLOSED | 2013-12-16 | AD: STATE FIRE MARSHAL FEES | 192 | CLOSED | 374.5 | 0 | 0 | 0
PJ0004721 | INSTALL WINDOW IN DOOR FOR SAFETY REASONS - BLDG. 192 RM. 211 | MARCHESE, JASON (WILL) | CLOSED | 2013-12-16 | AD: VORTEX DOORS | 192 | CLOSED | 4449.06 | 0 | 4449.06 | 4449.06
PJ0004721 | INSTALL WINDOW IN DOOR FOR SAFETY REASONS - BLDG. 192 RM. 211 | MARCHESE, JASON (WILL) | CLOSED | 2013-12-16 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 281.65 | 0 | 0 | 0
PJ0004721 | INSTALL WINDOW IN DOOR FOR SAFETY REASONS - BLDG. 192 RM. 211 | MARCHESE, JASON (WILL) | CLOSED | 2013-12-16 | IN: INSTALL WINDOW IN DOOR FOR SAFETY REASONS - BLDG 192 RM. 211 | 192 | CLOSED | 256.224 | 0 | 205.344 | 205.344
PJ0004721 Total | [7 empty] | 5361.434 | 0 | 4654.404 | 4654.404
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: ENGLEKIRK AND SABOL | 006 | CLOSED | 267.5 | 0 | 267.5 | 267.5
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: J.L. FASULO DRYWALL | 006 | CLOSED | 3210 | 0 | 1374.95 | 1374.95
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: MAINO (LOW-VALUE PUBLIC WORKS) | 006 | CLOSED | 5350 | 0 | 5186.29 | 5186.29
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: MCKENNA ENVIRONMENTAL | 006 | CLOSED | 214 | 0 | 214 | 214
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: MORELAND THOMPSON, INC. | 006 | CLOSED | 7987.55 | 0 | 7987.55 | 7987.55
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: PMSM ARCHITECTS | 006 | CLOSED | 4547.5 | 0 | 4547.5 | 4547.5
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: STATE FIRE MARSHAL FEES | 006 | CLOSED | 0 | 0 | 1271.16 | 1271.16
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 2192.06 | 0 | 0 | 0
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CU: CLEAN-UP FOR SMART ROOM UPGRADE - PAC 06 ROOM 124 | 006 | CLOSED | 191.184 | 0 | 145.968 | 145.968
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | EL:CONTRACTOR SUPPORT FOR BLDG 6, ROOM 124 | 006 | CLOSED | 134.832 | 0 | 168.54 | 168.54
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | IN: LECTURE HALL SMART ROOM UPGRADE 06-124 | 006 | CLOSED | 320.28 | 0 | 224.196 | 224.196
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | LO: INSTALL NEW ORANGE CORE FOR BLDG 6, ROOM 124 | 006 | CLOSED | 116.088 | 0 | 29.022 | 29.022
PJ0004720 | LECTURE HALL SMART ROOM UPGRADE 06-124 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | PA: PAINTING FOR LECTURE HALL SMART ROOM UPGRADE 06-124 | 006 | CLOSED | 1427.28 | 0 | 522.858 | 522.858
PJ0004720 Total | [7 empty] | 25958.274 | 0 | 21939.534 | 21939.534
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: (SR FUNDING) FLOOR CONNECTION | 033 | CLOSED | 12142.3921 | 0 | 12658.1321 | 12658.1321
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: (SR FUNDING) STATE FIRE MARSHAL FEES | 033 | CLOSED | 481.5 | 0 | 317.5118 | 317.5118
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: BKM | 033 | CLOSED | 1503.9064 | 0 | 1503.6924 | 1503.6924
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: CONSTRUCTED SOLUTIONS INC | 033 | CLOSED | 8253.0812 | 0 | 9378.9673 | 9378.9673
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: JL FASULO DRYWALL | 033 | CLOSED | 3639.07 | 0 | 3639.07 | 3639.07
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: JOC 14.034.001 MAINO | 033 | CLOSED | 64348.302 | 0 | 64348.302 | 64348.302
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: KI FURNITURE | 033 | CLOSED | 68738.3729 | 0 | 68430.5446 | 68430.5446
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: PMSM ARCHITECTS | 033 | CLOSED | 4766.8607 | 0 | 4766.85 | 4766.85
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: SCHOOL OUTFITTERS | 033 | CLOSED | 1269.555 | 0 | 1269.555 | 1269.555
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: SEISMIC PEER REVIEW | 033 | CLOSED | 267.5 | 0 | 267.5 | 267.5
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: STATE FIRE MARSHAL FEES | 033 | CLOSED | 481.5 | 0 | 1401.18 | 1401.18
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: THOMA ENGINEERING | 033 | CLOSED | 6955 | 0 | 6259.5 | 6259.5
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CA:CUT HOLE, INSTALL PAPER TOWEL DISPENSER AND SOAP | 033 | CLOSED | 111.24 | 0 | 531.7651 | 531.7651
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CP: (SR FUNDING) PROJECT CONTINGENCY | 033 | CLOSED | 3135.87 | 0 | 0 | 0
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 156.32 | 0 | 0 | 0
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CU: (SR FUNDING): CLEAN CLASSRM AFTER CONSTRUCTION BLD33, RM286 | 033 | CLOSED | 267.936 | 0 | 633.048 | 633.048
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 033 | CLOSED | 0 | 0 | 43.2 | 43.2
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | EL: (SR FUNDING)DISCONNECT ELECTRICAL, INSTALL NEW - BLD 33-286 | 033 | CLOSED | 20339.74 | 0 | 15305.784 | 15305.784
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | IN: (SR FUNDING) LECTURE HALL SMART ROOM UPGRADE 33-286 | 033 | CLOSED | 282.576 | 0 | 423.864 | 423.864
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | IN: LECTURE HALL SMART ROOM UPGRADE 33-286 (SEE WO0750834) | 033 | CLOSED | 384.336 | 0 | 378.66 | 378.66
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | LO: (SR FUNDING) CHANGE DOOR CORES TO ORANGE CORES, BLD33, 286 | 033 | CLOSED | 121.848 | 0 | 30.462 | 30.462
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | MO: (SR FUNDING)- CONTRACTOR SUPPORT BLDG 33, 286 | 033 | CLOSED | 335.16 | 0 | 33.804 | 33.804
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | PA: (SR FUNDING) PAINT CEILING, AROUND WINDOWS, BLD33, 286 | 033 | CLOSED | 3695.4 | 0 | 1780.52 | 1780.52
PJ0004719 | LECTURE HALL SMART ROOM UPGRADE 33-286 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | PL: (SR FUNDING)CONTRACTOR SUPPORT, LAB BENCH PL, BLD33, 286 | 033 | CLOSED | 3470.3609 | 0 | 1552.896 | 1552.896
PJ0004719 Total | [7 empty] | 205147.8271 | 0 | 194954.8083 | 194954.8083
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: BKM FURNITURE | 008 | CLOSED | 23540 | 0 | 21770.6694 | 21770.6694
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: FLOOR CONNECTION | 008 | CLOSED | 10212.7648 | 0 | 10374.827 | 10374.827
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: J.L. FASULO DRYWALL | 008 | CLOSED | 616.32 | 0 | 616.32 | 616.32
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 008 | CLOSED | 8610.825 | 0 | 8385.59 | 8385.59
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: MORELAND THOMPSON, INC. | 008 | CLOSED | 10914 | 0 | 10914 | 10914
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | AD: SANTA MARIA ACOUSTICAL | 008 | CLOSED | 7714.7 | 0 | 7714.7 | 7714.7
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CA:INSTALL COVEBASE AND CEILING TILE- CONTRACTOR ASSIST | 008 | CLOSED | 341.94 | 0 | 93.444 | 93.444
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CP: PROJECT CONTINGENCY | 008 | CLOSED | 863.17 | 0 | 0 | 0
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | CU:DEEP CLEANING AND UPPER LEVEL FLOOR WAXING BLDG 38, ROOM 123 | 008 | CLOSED | 196.776 | 0 | 1699.0788 | 1699.0788
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | IN: LECTURE HALL SMART ROOM UPGRADE 08-123 | 008 | CLOSED | 256.224 | 0 | 384.336 | 384.336
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | LO:CHANGE CORES TO ORANGE CORE DURING CONSTRUCTION BLD 8, ROOM 1 | 008 | CLOSED | 116.088 | 0 | 58.044 | 58.044
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | MO: REMOVE CHAIRS AND TABLES FROM BLDG 008, ROOM 123 | 008 | CLOSED | 64.8 | 0 | 24.144 | 24.144
PJ0004718 | LECTURE HALL SMART ROOM UPGRADE 08-123 | MOLLAN, CHERYL L. | CLOSED | 2013-12-10 | PA:PAINT FRONT WALL IN BLDG 8, ROOM 123 | 008 | CLOSED | 474.912 | 0 | 677.64 | 677.64
PJ0004718 Total | [7 empty] | 63922.5198 | 0 | 62712.7932 | 62712.7932
PJ0004717 | INSTALLATION OF CAMERAS AND MONITOR - BLDG. 124 RM. 123 | GONZALES, ALBERT M. | CLOSED | 2013-12-05 | AD: MORELAND THOMPSON | 124 | CLOSED | 2461 | 0 | 2295.15 | 2295.15
PJ0004717 | INSTALLATION OF CAMERAS AND MONITOR - BLDG. 124 RM. 123 | GONZALES, ALBERT M. | CLOSED | 2013-12-05 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 358.45 | 0 | 0 | 0
PJ0004717 | INSTALLATION OF CAMERAS AND MONITOR - BLDG. 124 RM. 123 | GONZALES, ALBERT M. | CLOSED | 2013-12-05 | IN: INSTALLATION OF CAMERAS AND MONITOR - BLDG. 124 RM. 123 | 124 | CLOSED | 128.112 | 0 | 224.196 | 224.196
PJ0004717 Total | [7 empty] | 2947.562 | 0 | 2519.346 | 2519.346
PJ0004716 | SR 13/14: SEAL ROAD IN FRONT OF GROUNDS SHOP | GONZALES, ALBERT M. | CLOSED | 2013-12-12 | AD: JOC 13.029.042 MAINO | STREETS | CLOSED | 30585 | 0 | 26495.68 | 26495.68
PJ0004716 | SR 13/14: SEAL ROAD IN FRONT OF GROUNDS SHOP | GONZALES, ALBERT M. | CLOSED | 2013-12-12 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 0 | 0 | 0 | 0
PJ0004716 | SR 13/14: SEAL ROAD IN FRONT OF GROUNDS SHOP | GONZALES, ALBERT M. | CLOSED | 2013-12-12 | IN: SR 13/14: SEAL ROAD IN FRONT OF GROUNDS SHOP | STREETS | CLOSED | 106.76 | 0 | 80.07 | 80.07
PJ0004716 Total | [7 empty] | 30691.76 | 0 | 26575.75 | 26575.75
PJ0004715 | INSTALL OWNER-PROVIDED CARPET IN ADMINISTRATIVE OFFICE 208 | LAMPMAN, GREG | CLOSED | 2013-11-11 | AD: FLOOR CONNECTION | 006 | CLOSED | 3290.25 | 0 | 3290.25 | 3290.25
PJ0004715 | INSTALL OWNER-PROVIDED CARPET IN ADMINISTRATIVE OFFICE 208 | LAMPMAN, GREG | CLOSED | 2013-11-11 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 566.64 | 0 | 0 | 0
PJ0004715 | INSTALL OWNER-PROVIDED CARPET IN ADMINISTRATIVE OFFICE 208 | LAMPMAN, GREG | CLOSED | 2013-11-11 | EL: INSTALL ELECTRICAL TO FURINTURE WHIP. | 006 | CLOSED | 2055.5131 | 0 | 822.576 | 822.576
PJ0004715 | INSTALL OWNER-PROVIDED CARPET IN ADMINISTRATIVE OFFICE 208 | LAMPMAN, GREG | CLOSED | 2013-11-11 | IN: INSTALL OWNER-PROVIDED CARPET IN ADMINISTRATIVE OFFICE | 006 | CLOSED | 320.28 | 0 | 64.056 | 64.056
PJ0004715 | INSTALL OWNER-PROVIDED CARPET IN ADMINISTRATIVE OFFICE 208 | LAMPMAN, GREG | CLOSED | 2013-11-11 | MO: MOVE FURNITURE FROM ROOM 208 TO LOADING DOCK - PAC 06 | 006 | CLOSED | 32.4 | 0 | 54.324 | 54.324
PJ0004715 Total | [7 empty] | 6265.0831 | 0 | 4231.206 | 4231.206
PJ0004712 | APPLY MANUFACTURER SUPPLIED SAMPLE "IDEA" PAINT | GONZALES, ALBERT M. | CLOSED | 2013-12-06 | AD: J.L. FASULO DRYWALL | 070 | CLOSED | 464.38 | 0 | 464.38 | 464.38
PJ0004712 | APPLY MANUFACTURER SUPPLIED SAMPLE "IDEA" PAINT | GONZALES, ALBERT M. | CLOSED | 2013-12-06 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 137.89 | 0 | 0 | 0
PJ0004712 | APPLY MANUFACTURER SUPPLIED SAMPLE "IDEA" PAINT | GONZALES, ALBERT M. | CLOSED | 2013-12-06 | IN: APPLY MANUFACTURER SUPPLIED SAMPLE "IDEA" PAINT | 070 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004712 | APPLY MANUFACTURER SUPPLIED SAMPLE "IDEA" PAINT | GONZALES, ALBERT M. | CLOSED | 2013-12-06 | PA: | 070 | CLOSED | 564.912 | 0 | 385.866 | 385.866
PJ0004712 Total | [7 empty] | 1231.238 | 0 | 882.274 | 882.274
PJ0004711 | QUARTERLY MAINTENANCE WALK-THROUGH 10/8/13 - PAC 06(NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2013-12-05 | CA:COMPLETE 10/8/13 FACILITY MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004711 | QUARTERLY MAINTENANCE WALK-THROUGH 10/8/13 - PAC 06(NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2013-12-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004711 | QUARTERLY MAINTENANCE WALK-THROUGH 10/8/13 - PAC 06(NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2013-12-05 | EL::COMPLETE 10/8/13 FACILITY MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 56.18 | 0 | 0 | 0
PJ0004711 | QUARTERLY MAINTENANCE WALK-THROUGH 10/8/13 - PAC 06(NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2013-12-05 | LO::COMPLETE 10/8/13 FACILITY MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 96.74 | 96.74
PJ0004711 | QUARTERLY MAINTENANCE WALK-THROUGH 10/8/13 - PAC 06(NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2013-12-05 | PA::COMPLETE 10/8/13 FACILITY MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 395.76 | 395.76
PJ0004711 Total | [7 empty] | 56.18 | 0 | 492.5 | 492.5
PJ0004709 | DESK TOP MODIFICATIONS - PROVOST'S OFFICE STE - BLDG. 01 RM 305A | GONZALES, ALBERT M. | CLOSED | 2013-12-02 | AD: EC WEST | 001 | CLOSED | 4356.5264 | 0 | 4364.0592 | 4364.0592
PJ0004709 | DESK TOP MODIFICATIONS - PROVOST'S OFFICE STE - BLDG. 01 RM 305A | GONZALES, ALBERT M. | CLOSED | 2013-12-02 | CA: DESK TOP MODIFICATION IN PROVOST RECEPTION AREA | 001 | CLOSED | 564.4439 | 0 | 895.932 | 895.932
PJ0004709 | DESK TOP MODIFICATIONS - PROVOST'S OFFICE STE - BLDG. 01 RM 305A | GONZALES, ALBERT M. | CLOSED | 2013-12-02 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 498.54 | 0 | 0 | 0
PJ0004709 | DESK TOP MODIFICATIONS - PROVOST'S OFFICE STE - BLDG. 01 RM 305A | GONZALES, ALBERT M. | CLOSED | 2013-12-02 | IN: DESK TOP MODIFICATIONS | 001 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004709 Total | [7 empty] | 5483.5663 | 0 | 5324.0472 | 5324.0472
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | AD: BUEHLER & BUEHLER (FOUNDATION DESIGN) | 071 | CLOSED | 5000 | 0 | 5000 | 5000
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | AD: ENGLEKIRK AND SABOL | 071 | CLOSED | 1000 | 0 | 1000 | 1000
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | AD: JOC 13.030.035 MAINO | 071 | CLOSED | 24835.78 | 0 | 24835.78 | 24835.78
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | AD: SAN LUIS AUTO/NAPA (10K LIFT) | 071 | CLOSED | 5403.55 | 0 | 5403.55 | 5403.55
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | AD: SNAP-ON TOOLS (18K LIFT) | 071 | CLOSED | 14732.1 | 0 | 14803.35 | 14803.35
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | CA: PURCHASE ANCHORS FOR 10K AUTO SHOP LIFTS | 071 | CLOSED | 593.98 | 0 | 383.6 | 383.6
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | CP: PROJECT CONTINGENCY | 071 | CLOSED | 4810.66 | 0 | 0 | 0
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 071 | CLOSED | 0 | 0 | 14 | 14
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | EL: SUPPORT FOR LIFT AT TRANSPORTATION | 071 | CLOSED | 1248.88 | 0 | 2170.26 | 2170.26
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | IN: REMOVE INGROUND VEHICLE LIFT AND PREP FOR NEW 4 POST LIFT | 071 | CLOSED | 320.28 | 0 | 373.66 | 373.66
PJ0004707 | REMOVE IN-GROUND VEHICLE LIFT AND INSTALL TWO 2-POST LIFTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-08 | PL: SUPPORT FOR LIFT AT TRANSPORTATION | 071 | CLOSED | 1505.84 | 0 | 54.41 | 54.41
PJ0004707 Total | [7 empty] | 59451.07 | 0 | 54038.61 | 54038.61
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT FOR CP WOMENS BBALL HOLIDAY BEACH CLASSIC-NOV 29-30 | 042 | CLOSED | 0 | 0 | 2818.98 | 2818.98
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT FOR W. BASKETBALL V. NEW MEXICO ST. - 11/18 | 042 | CLOSED | 0 | 0 | 508.248 | 508.248
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT Q. BASKETBALL V. CSU FULLERTON-1/23 | 042 | CLOSED | 0 | 0 | 423.621 | 423.621
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. CSU BASKERSFIELD - 12/7 | 042 | CLOSED | 0 | 0 | 765.276 | 765.276
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. CSU LONG BEACH - 2/15 | 042 | CLOSED | 0 | 0 | 1033.722 | 1033.722
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. CSU NORTHRIDGE-2/13 | 042 | CLOSED | 0 | 0 | 636.288 | 636.288
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. HAWAI'I - 2/8 | 042 | CLOSED | 0 | 0 | 836.964 | 836.964
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. UC DAVIS - 2/27 | 042 | CLOSED | 0 | 0 | 660.768 | 660.768
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. UC IRVINE-3/1 | 042 | CLOSED | 0 | 0 | 1147.908 | 1147.908
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. UC RIVERSIDE - 1/25 | 042 | CLOSED | 0 | 0 | 640.944 | 640.944
PJ0004703 | 13/14: SUPPORT FOR WOMEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-25 | CU: SUPPORT W. BASKETBALL V. UCSB-1/11 | 042 | CLOSED | 0 | 0 | 884.304 | 884.304
PJ0004703 Total | [7 empty] | 0 | 0 | 10357.023 | 10357.023
PJ0004702 | MOLD REMEDIATON - BLD 20 RMS 142/143 (MAINT) | POLVI, STEVEN | CLOSED | 2013-11-22 | CA:COMPLETE MOLD REMEDIATION AT 20-142A | 020 | CLOSED | 0 | 0 | 4919.0822 | 4919.0822
PJ0004702 | MOLD REMEDIATON - BLD 20 RMS 142/143 (MAINT) | POLVI, STEVEN | CLOSED | 2013-11-22 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 0 | 0 | 0 | 0
PJ0004702 | MOLD REMEDIATON - BLD 20 RMS 142/143 (MAINT) | POLVI, STEVEN | CLOSED | 2013-11-22 | EL:REMOVE PLUG MOLD IN 20-143 | 020 | CLOSED | 0 | 0 | 140.45 | 140.45
PJ0004702 | MOLD REMEDIATON - BLD 20 RMS 142/143 (MAINT) | POLVI, STEVEN | CLOSED | 2013-11-22 | PA:TAPE, MUD, PATCH, PRIME, AND PAINT REPLACED SHEET ROCK | 020 | CLOSED | 0 | 0 | 1261.485 | 1261.485
PJ0004702 | MOLD REMEDIATON - BLD 20 RMS 142/143 (MAINT) | POLVI, STEVEN | CLOSED | 2013-11-22 | PL:REMOVE EXISTING GAS LINE IN 20-142A (N/L) | 020 | CLOSED | 0 | 0 | 0 | 0
PJ0004702 Total | [7 empty] | 0 | 0 | 6321.0172 | 6321.0172
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | AD: CCI RENTALS FOR FALL COMMENCEMENT-12/19 | 043 | CLOSED | 0 | 0 | 423.0459 | 423.0459
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | CA: SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 | 043 | CLOSED | 0 | 0 | 1939.04 | 1939.04
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | CU: SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 | 043 | CLOSED | 0 | 0 | 1146.5407 | 1146.5407
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | EL: SUPPORT FOR 2013 FALL COMMENCEMENT - SAT 12/14 | 043 | CLOSED | 0 | 0 | 724.88 | 724.88
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | ES: PLEASE SCHEDULE HVAC TO BE OPERATING BY 6:00AM @ SAGE-12/14 | 112 | CLOSED | 0 | 0 | 26.015 | 26.015
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | MC: SUPPORT FOR FALL COMMENCEMENT - 12/14 | 043 | CLOSED | 0 | 0 | 256.53 | 256.53
PJ0004700 | SUPPORT FOR 2013 FALL COMMENCEMENT - 12/14 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-11-20 | PA: SUPPORT FOR FALL COMMENCEMENT - 12/14 | 043 | CLOSED | 0 | 0 | 395.76 | 395.76
PJ0004700 Total | [7 empty] | 0 | 0 | 4911.8116 | 4911.8116
PJ0004699 | SR 13/14: REPLACE CHALK BOARDS WITH WHITE BOARDS - BLD 24 RM 108 | NEEL, JOEL | CLOSED | 2013-11-20 | AD: BKM FURNITURE | 024 | CLOSED | 8500 | 0 | 8349.14 | 8349.14
PJ0004699 | SR 13/14: REPLACE CHALK BOARDS WITH WHITE BOARDS - BLD 24 RM 108 | NEEL, JOEL | CLOSED | 2013-11-20 | CA: RETROFIT WHITEBOARDS - BLDG. 24 RM. 108 | 024 | CLOSED | 3341.5249 | 0 | 1305.395 | 1305.395
PJ0004699 | SR 13/14: REPLACE CHALK BOARDS WITH WHITE BOARDS - BLD 24 RM 108 | NEEL, JOEL | CLOSED | 2013-11-20 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 0 | 0 | 0 | 0
PJ0004699 | SR 13/14: REPLACE CHALK BOARDS WITH WHITE BOARDS - BLD 24 RM 108 | NEEL, JOEL | CLOSED | 2013-11-20 | CU: MOVE CHAIRS | 024 | CLOSED | 109.32 | 0 | 54.66 | 54.66
PJ0004699 | SR 13/14: REPLACE CHALK BOARDS WITH WHITE BOARDS - BLD 24 RM 108 | NEEL, JOEL | CLOSED | 2013-11-20 | IN: REPLACE CHALK BOARDS WITH WHITE BOARDS - BLD 24 RM 108 | 024 | CLOSED | 237.541 | 0 | 80.07 | 80.07
PJ0004699 Total | [7 empty] | 12188.3859 | 0 | 9789.265 | 9789.265
PJ0004698 | SR 13/14: EMERGENCY REPAIRS - UTILIDOR - VARIOUS BUILDINGS | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | AD: BOB'S CRANE SERVICE | U-UDOR | CLOSED | 0 | 0 | 1650 | 1650
PJ0004698 | SR 13/14: EMERGENCY REPAIRS - UTILIDOR - VARIOUS BUILDINGS | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | AD: HPS MECHANICAL | U-UDOR | CLOSED | 0 | 0 | 3902.54 | 3902.54
PJ0004698 | SR 13/14: EMERGENCY REPAIRS - UTILIDOR - VARIOUS BUILDINGS | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | CA: SUPPORT FOR BLDG 2 LEAK | U-UDOR | CLOSED | 0 | 0 | 23.495 | 23.495
PJ0004698 | SR 13/14: EMERGENCY REPAIRS - UTILIDOR - VARIOUS BUILDINGS | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0004698 | SR 13/14: EMERGENCY REPAIRS - UTILIDOR - VARIOUS BUILDINGS | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | CPE: SUPPORT FOR BLDG 2 LEAK | U-UDOR | CLOSED | 0 | 0 | 8468.815 | 8468.815
PJ0004698 | SR 13/14: EMERGENCY REPAIRS - UTILIDOR - VARIOUS BUILDINGS | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | ES:SUPPORT FOR BLDG 2 LEAK | U-UDOR | CLOSED | 0 | 0 | 2087.1 | 2087.1
PJ0004698 Total | [7 empty] | 0 | 0 | 16131.95 | 16131.95
PJ0004697 | SR 13/14: AIR MOVEMENT STUDY - BLD 45 RM 206 SCENE SHOP | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | AD: GOSS ENGINEERING | 045 | CLOSED | 8460 | 0 | 8460 | 8460
PJ0004697 | SR 13/14: AIR MOVEMENT STUDY - BLD 45 RM 206 SCENE SHOP | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 0 | 0 | 0 | 0
PJ0004697 | SR 13/14: AIR MOVEMENT STUDY - BLD 45 RM 206 SCENE SHOP | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | IN: SR 13/14: AIR MOVEMENT STUDY - BLD 45 RM 206 SCENE SHOP | 045 | CLOSED | 475.082 | 0 | 26.69 | 26.69
PJ0004697 Total | [7 empty] | 8935.082 | 0 | 8486.69 | 8486.69
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | AD: BOB'S CRANE | 040 | CLOSED | 1100 | 0 | 1100 | 1100
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | AD: GARRATT CALLAHAN | 040 | CLOSED | 35400 | 0 | 34308.9 | 34308.9
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | AD: JWC CONSTRUCTION | 040 | CLOSED | 1500 | 0 | 1111.46 | 1111.46
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | CPE: WATER SOFTNER INSTALL | 040 | CLOSED | 2658.1878 | 0 | 0 | 0
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | EL: ADD OUTLET FOR WATER SOFTNER | 040 | CLOSED | 1000.002 | 0 | 433.71 | 433.71
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | IN: SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | 040 | CLOSED | 0 | 0 | 117.74 | 117.74
PJ0004696 | SR 13/14: QUICK FILL SOFT WATER SYSTEM - CENTRAL PLANT 40 | BRENNAN, MICHAEL | CLOSED | 2013-11-15 | PL: WATER SOFTNER INSTALL | 040 | CLOSED | 30110.0337 | 0 | 27007.8079 | 27007.8079
PJ0004696 Total | [7 empty] | 71768.2235 | 0 | 64079.6179 | 64079.6179
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | AD: BRANDOW & JOHNSON | 042A | CLOSED | 1070 | 0 | 1070 | 1070
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | AD: ENGLEKIRK AND SABOL | 042A | CLOSED | 535 | 0 | 535 | 535
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | AD: ONTRAC SHIPPING | 042A | CLOSED | 0 | 0 | 29.69 | 29.69
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | CA: CREATE TAGS FOR ELECTRICAL PANEL AT ANDERSON AQUATIC CTR 42A | 042A | CLOSED | 0 | 0 | 57.336 | 57.336
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 8.03 | 0 | 0 | 0
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | EL:INSTALL ELECTRICAL FOR SCOREBOARD AT ANDERSON | 042A | CLOSED | 12002.0465 | 0 | 6703.938 | 6703.938
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | IN: INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | 042A | CLOSED | 384.336 | 0 | 230.784 | 230.784
PJ0004693 | INSTALL SCOREBOARD - ANDERSON AQUATIC CENTER 042A | MOLLAN, CHERYL L. | CLOSED | 2013-10-30 | PA: PATCH AND PAINT WALL - ANDERSON AQUATIC CTR. 042A | 042A | CLOSED | 214.092 | 0 | 59.364 | 59.364
PJ0004693 Total | [7 empty] | 14213.5045 | 0 | 8686.112 | 8686.112
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CA: REPAIR PRESIDENT'S SEAT AT MOTT GYM BLEACHERS | 042 | CLOSED | 0 | 0 | 236.352 | 236.352
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT FOR M. BASKETBALL V. FRESNO ST. - 11/20 | 042 | CLOSED | 0 | 0 | 493.212 | 493.212
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. CSU FULLERTON - 2/20 | 042 | CLOSED | 0 | 0 | 682.344 | 682.344
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. CSU NORTHRIDGE-1/16 | 042 | CLOSED | 0 | 0 | 848.553 | 848.553
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. DOMINGUEZ HILLS - 12/14 | 042 | CLOSED | 0 | 0 | 742.284 | 742.284
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. HAWAI'I - 1/9 | 042 | CLOSED | 0 | 0 | 979.116 | 979.116
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. LONG BEACH ST. - 1/18 | 042 | CLOSED | 0 | 0 | 1478.346 | 1478.346
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. SANTA CLARA - 12/7 | 042 | CLOSED | 0 | 0 | 856.506 | 856.506
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. UC DAVIS - 1/30 | 042 | CLOSED | 0 | 0 | 682.614 | 682.614
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. UC IRVINE - 2/1 | 042 | CLOSED | 0 | 0 | 2101.722 | 2101.722
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. UC RIVERSIDE - | 042 | CLOSED | 0 | 0 | 1076.268 | 1076.268
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BASKETBALL V. UCSB - 3/8 | 042 | CLOSED | 0 | 0 | 1495.356 | 1495.356
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT M. BBALL V. BETHSEDA - 11/23 | 042 | CLOSED | 0 | 0 | 1016.772 | 1016.772
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | LA: MEN'S SOCCER V. CSULA - 4/5 | 042 | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | LA: SUPPORT MEN'S SOCCER ALUMNI GAME - 3/8 | 042 | CLOSED | 0 | 0 | 203.604 | 203.604
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | LA: SUPPORT MEN'S SOCCER V. STANFORD - 4/12 | 042 | CLOSED | 0 | 0 | 109.347 | 109.347
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | LA: SUPPORT MEN'S SOCCER V. UCLA - 4/19 | 042 | CLOSED | 0 | 0 | 272.748 | 272.748
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 11/12/2013 | 042 | CLOSED | 0 | 0 | 105 | 105
PJ0004691 | 13/14: SUPPORT MEN'S BASKETBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | SUPPLY RENTAL: NOV/DEC TRASHCAN RENTALS FOR MUSTANG BBQ | 042 | CLOSED | 0 | 0 | 63 | 63
PJ0004691 Total | [7 empty] | 0 | 0 | 13676.928 | 13676.928
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT FOR GREEN AND GOLD WRESTLING MATCH - 11/1 | 042 | CLOSED | 0 | 0 | 514.209 | 514.209
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT WRESTLING TOURNAMENT - 2/9 | 042 | CLOSED | 0 | 0 | 908.592 | 908.592
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT WRESTLING V. ARIZONA ST. - 2/14 | 042 | CLOSED | 0 | 0 | 719.352 | 719.352
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT WRESTLING V. N. DAKOTA ST.- 1/4 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT WRESTLING V. N. DAKOTA STATE - 1/4 | 042 | CLOSED | 0 | 0 | 960.12 | 960.12
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT WRESTLING V. STANFORD V. SDSU-2/9 | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU: SUPPORT WRSTLING V. BOISE ST. - 1/12 | 042 | CLOSED | 0 | 0 | 501.018 | 501.018
PJ0004690 | 13/14: SUPPORT FOR WRESTLING (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-11-08 | CU:SUPPORT WRESTLING V. MENLO COLLEGE-1/18 | 042 | CLOSED | 0 | 0 | 322.446 | 322.446
PJ0004690 Total | [7 empty] | 0 | 0 | 3925.737 | 3925.737
PJ0004689 | INSTALL COMMEMORATIVE BENCH - BLDG. 45 | LAMPMAN, GREG | CLOSED | 2013-10-07 | AD: QUICK CRETE | 045 | CLOSED | 1214.664 | 0 | 1214.664 | 1214.664
PJ0004689 | INSTALL COMMEMORATIVE BENCH - BLDG. 45 | LAMPMAN, GREG | CLOSED | 2013-10-07 | CA: POUR CONCRETE SLAB FOR BENCH AND INSTALL DONOR PLAQUE | 045 | CLOSED | 2247.9767 | 0 | 886.5451 | 886.5451
PJ0004689 | INSTALL COMMEMORATIVE BENCH - BLDG. 45 | LAMPMAN, GREG | CLOSED | 2013-10-07 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 429.09 | 0 | 0 | 0
PJ0004689 | INSTALL COMMEMORATIVE BENCH - BLDG. 45 | LAMPMAN, GREG | CLOSED | 2013-10-07 | EO: EXCAVATION AS NEED FOR A 26"X96" CONCRETE SLAB FOR A BENCH | 045 | CLOSED | 332.4235 | 0 | 447.876 | 447.876
PJ0004689 | INSTALL COMMEMORATIVE BENCH - BLDG. 45 | LAMPMAN, GREG | CLOSED | 2013-10-07 | IN: INSTALL A MEMORIAL BENCH IN FRONT OF BLDG. 45 | 045 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004689 | INSTALL COMMEMORATIVE BENCH - BLDG. 45 | LAMPMAN, GREG | CLOSED | 2013-10-07 | LA: MOVE PLANTS AND SPRINKLER SYS. AS NEEDED OF NEW BENCH. | 045 | CLOSED | 173.3898 | 0 | 194.82 | 194.82
PJ0004689 Total | [7 empty] | 4525.656 | 0 | 2872.0171 | 2872.0171
PJ0004687 | REPLACE IRRIGATION PUMP - SPORTS COMPLEX PUMP STATION (MAINT) | LOOSLEY, SCOTT L. | CLOSED | 2013-10-29 | CP: PROJECT CONTINGENCY | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0004687 | REPLACE IRRIGATION PUMP - SPORTS COMPLEX PUMP STATION (MAINT) | LOOSLEY, SCOTT L. | CLOSED | 2013-10-29 | EL: REPLACE SPORTS COMPLEX PUMP MOTOR | 160F | CLOSED | 0 | 0 | 84.27 | 84.27
PJ0004687 | REPLACE IRRIGATION PUMP - SPORTS COMPLEX PUMP STATION (MAINT) | LOOSLEY, SCOTT L. | CLOSED | 2013-10-29 | ES: CXLD | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0004687 | REPLACE IRRIGATION PUMP - SPORTS COMPLEX PUMP STATION (MAINT) | LOOSLEY, SCOTT L. | CLOSED | 2013-10-29 | LA: PUMP PURCHASE - PAID FOR FROM LANDSCAPING MAINT BUDGET (N/L) | 160F | CLOSED | 0 | 0 | 4564.95 | 4564.95
PJ0004687 | REPLACE IRRIGATION PUMP - SPORTS COMPLEX PUMP STATION (MAINT) | LOOSLEY, SCOTT L. | CLOSED | 2013-10-29 | PL: CXLD | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0004687 Total | [7 empty] | 0 | 0 | 4649.22 | 4649.22
PJ0004686 | PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | LAMPMAN, GREG | CLOSED | 2013-10-16 | AD: FLOOR CONNECTION | 020 | CLOSED | 7142.25 | 0 | 7142.25 | 7142.25
PJ0004686 | PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | LAMPMAN, GREG | CLOSED | 2013-10-16 | CA: BUY AND INSTALL WHITE BOARDS AND MOUNT LOCKER TO WALL | 020 | CLOSED | 2738.3797 | 0 | 2795.232 | 2795.232
PJ0004686 | PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | LAMPMAN, GREG | CLOSED | 2013-10-16 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 1557.18 | 0 | 0 | 0
PJ0004686 | PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | LAMPMAN, GREG | CLOSED | 2013-10-16 | CU: WAX FLOOR (NO LABOR) | 020 | CLOSED | 1215.0584 | 0 | 0 | 0
PJ0004686 | PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | LAMPMAN, GREG | CLOSED | 2013-10-16 | IN: PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | 020 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004686 | PAINT, WHITEBOARDS, AND VINYL FLOORING 20-145 | LAMPMAN, GREG | CLOSED | 2013-10-16 | PA: PAINT WALLS BEFORE OPEN HOUSE - BLDG. 20 RM 145 | 020 | CLOSED | 4347.9041 | 0 | 2045.16 | 2045.16
PJ0004686 Total | [7 empty] | 17128.8842 | 0 | 12110.754 | 12110.754
PJ0004685 | SUPPORT FOR CENTER FOR SCIENCE DEDICATION - 11/1/13 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CA: INSTALL FLAG SUPPORT FOR CSM DEDICATION - 11/1 | 180 | CLOSED | 0 | 0 | 296.94 | 296.94
PJ0004685 | SUPPORT FOR CENTER FOR SCIENCE DEDICATION - 11/1/13 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 0 | 0 | 0 | 0
PJ0004685 | SUPPORT FOR CENTER FOR SCIENCE DEDICATION - 11/1/13 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPLY AMERICAN FLAG FOR CENTER FOR SCIENCE. | 180 | CLOSED | 0 | 0 | 351.672 | 351.672
PJ0004685 | SUPPORT FOR CENTER FOR SCIENCE DEDICATION - 11/1/13 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPORT FOR CENTER FOR SCIENCE DEDICATION-11/1 | 180 | CLOSED | 0 | 0 | 262.224 | 262.224
PJ0004685 | SUPPORT FOR CENTER FOR SCIENCE DEDICATION - 11/1/13 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | EL: SPIDER BOXES FOR CENTER FOR SCIENCE DEDICATION-10/30 | 180 | CLOSED | 0 | 0 | 738.3 | 738.3
PJ0004685 | SUPPORT FOR CENTER FOR SCIENCE DEDICATION - 11/1/13 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT FOR CENTER FOR SCIENCE DEDICATION | 180 | CLOSED | 0 | 0 | 132.123 | 132.123
PJ0004685 Total | [7 empty] | 0 | 0 | 1781.259 | 1781.259
PJ0004684 | INSTALL CONDUIT & FEEDER FROM IMS-1AA TO ILP-OAE FOR TACOS TO GO | NEEL, JOEL | CLOSED | 2013-10-17 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 171I | CLOSED | 6545.19 | 0 | 5168.1 | 5168.1
PJ0004684 | INSTALL CONDUIT & FEEDER FROM IMS-1AA TO ILP-OAE FOR TACOS TO GO | NEEL, JOEL | CLOSED | 2013-10-17 | AD: PLCS PLUS | 171I | CLOSED | 513.6 | 0 | 513.6 | 513.6
PJ0004684 | INSTALL CONDUIT & FEEDER FROM IMS-1AA TO ILP-OAE FOR TACOS TO GO | NEEL, JOEL | CLOSED | 2013-10-17 | CP: PROJECT CONTINGENCY | 171I | CLOSED | 2791.73 | 0 | 0 | 0
PJ0004684 | INSTALL CONDUIT & FEEDER FROM IMS-1AA TO ILP-OAE FOR TACOS TO GO | NEEL, JOEL | CLOSED | 2013-10-17 | EL: INSTALL ELECTRIC METERS & SWITCHES FOR TACOS TO GO | 171I | CLOSED | 26507.9057 | 0 | 26984.592 | 26984.592
PJ0004684 Total | [7 empty] | 36358.4257 | 0 | 32666.292 | 32666.292
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPORT FOR SOFTBALL - 4/12 | 160 | CLOSED | 0 | 0 | 79.032 | 79.032
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPORT SOFTBALL GAMES - 3/28 - 3/31 | 160 | CLOSED | 0 | 0 | 124.26 | 124.26
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPORT SOFTBALL V. CSU FULLERTON - 4/27 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPORT SOFTBALL V. STONYBROOK - 3/8 | 160 | CLOSED | 0 | 0 | 237.768 | 237.768
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | CU: SUPPORT SOFTBALL V. UC RIVERSIDE - 5/9-5/10 | 160 | CLOSED | 0 | 0 | 198.384 | 198.384
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT FOR GREEN/GOLD SOFTBALL GAME - 10/18 | 160 | CLOSED | 0 | 0 | 658.56 | 658.56
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE - 10/26 | 160 | CLOSED | 0 | 0 | 311.712 | 311.712
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT FOR SOFTBALL SCRIMMAGES - 11/1 & 11/2 | 160 | CLOSED | 0 | 0 | 346.848 | 346.848
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT SOFTBALL MUSTANG CLASSIC TOURNAMENT - 3/7-3/9 | 160 | CLOSED | 0 | 0 | 6260.928 | 6260.928
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT SOFTBALL V. CSU FULLERTON - 4/27 | 160 | CLOSED | 0 | 0 | 332.28 | 332.28
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT SOFTBALL V. CSU NORTHRIDGE-3/29-3/30 | 160 | CLOSED | 0 | 0 | 1246.14 | 1246.14
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT SOFTBALL V. LONG BEACH ST.-4/26 | 160 | CLOSED | 0 | 0 | 1220.88 | 1220.88
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT SOFTBALL V. UC DAVIS - 4/12-4/13 | 160 | CLOSED | 0 | 0 | 712.6666 | 712.6666
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT SOFTBALL V. UC RIVERSIDE - 5/9-5/10 | 160 | CLOSED | 0 | 0 | 1294.1642 | 1294.1642
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | LA: SUPPORT W. SOFTBALL V. BAKERSFIELD - 4/22 | 160 | CLOSED | 0 | 0 | 728.088 | 728.088
PJ0004683 | 13/14: SUPPORT FOR SOFTBALL - BLD 160 | POPHAM, DONALD J. | CLOSED | 2013-10-28 | SUPPLY RENTAL: SOFTBALL ALUMNI GAME - 11/2 | 160 | CLOSED | 0 | 0 | 126.25 | 126.25
PJ0004683 Total | [7 empty] | 0 | 0 | 13910.7568 | 13910.7568
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | AD: JOC 13.029.040 MAINO | RESIDENCE | CLOSED | 40345.6447 | 0 | 32537.8119 | 32537.8119
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | AD: JOC 13.030.039 MAINO | RESIDENCE | CLOSED | 278170.575 | 0 | 232314.8583 | 232314.8583
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | AD: STATE FIRE MARSHAL FEES | RESIDENCE | CLOSED | 0 | 0 | 2104 | 2104
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | CA: ENGRAVED LEGENDS FOR ELECTRIC ENCLOSURES AT RED BRICK DORMS | RESIDENCE | CLOSED | 232.776 | 0 | 356.688 | 356.688
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 42284.1 | 0 | 0 | 0
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | EL: SUPPORT FOR HOUSING WIRELESS PHASE III (RESIDENCE HALLS) | RESIDENCE | CLOSED | 88210.9306 | 0 | 61598.436 | 61598.436
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | IN: HOUSING WIRELESS PROJECT - PHASE III (SEIRRA MADRE) | RESIDENCE | CLOSED | 5016.8659 | 0 | 1685.22 | 1685.22
PJ0004681 | HOUSING WIRELESS PROJECT - PHASE III (RESIDENCE HALLS) | HICKS, MICHAEL | CLOSED | 2013-10-24 | ITS: DATA NETWORK FOR HOUSING WIRELESS PROJECT | RESIDENCE | CLOSED | 0 | 0 | 13813.27 | 13813.27
PJ0004681 Total | [7 empty] | 454260.8922 | 0 | 344410.2842 | 344410.2842
PJ0004680 | WASH/CLEAN WINDOWS - BLD 2 RM 101 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-11 | AD: COASTAL JANITORIAL | 002 | CLOSED | 1070 | 0 | 909.7675 | 909.7675
PJ0004680 | WASH/CLEAN WINDOWS - BLD 2 RM 101 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-11 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 120.28 | 0 | 0 | 0
PJ0004680 Total | [7 empty] | 1190.28 | 0 | 909.7675 | 909.7675
PJ0004678 | SP 13/14: COORDINATE REPAIRS TO MODULAR - 46T | LAMPMAN, GREG | CLOSED | 2013-10-22 | AD: WILLIAMS SCOTSMAN | 046T-M028 | CLOSED | 0 | 0 | 41905.5442 | 41905.5442
PJ0004678 | SP 13/14: COORDINATE REPAIRS TO MODULAR - 46T | LAMPMAN, GREG | CLOSED | 2013-10-22 | CP: PROJECT CONTINGENCY | 046T-M028 | CLOSED | 0 | 0 | 0 | 0
PJ0004678 Total | [7 empty] | 0 | 0 | 41905.5442 | 41905.5442
PJ0004675 | SP 13/14: OCR 6C - CONCOURSE CORRECTION - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-16 | AD: JOC 13.028.053 MAINO | 061 | CLOSED | 124827.805 | 0 | 124827.7943 | 124827.7943
PJ0004675 | SP 13/14: OCR 6C - CONCOURSE CORRECTION - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-16 | CA: PEDESTRIAN DETOUR SIGNS FOR SPANOS CONCOURSE CORRECTIONS PJ | 061 | CLOSED | 289.164 | 0 | 188.244 | 188.244
PJ0004675 | SP 13/14: OCR 6C - CONCOURSE CORRECTION - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-16 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004675 | SP 13/14: OCR 6C - CONCOURSE CORRECTION - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-16 | EL: REPAIR SIGNAL WIRE FROM FLOW SWITCH IN SPANOS CONCOURSE | 061 | CLOSED | 988.992 | 0 | 168.54 | 168.54
PJ0004675 | SP 13/14: OCR 6C - CONCOURSE CORRECTION - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-16 | IN: SP 13/14: OCR 6C - CONCOURSE CORRECTION - SPANOS STADIUM | 061 | CLOSED | 1024.896 | 0 | 576.504 | 576.504
PJ0004675 Total | [7 empty] | 127130.857 | 0 | 125761.0823 | 125761.0823
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | AD: CONSTRUCTED SOLUTIONS, INC. | 013 | CLOSED | 42479.7704 | 0 | 42479.7704 | 42479.7704
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | AD: HPS MECHANICAL | 013 | CLOSED | 4047.81 | 0 | 4047.81 | 4047.81
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | AD: J.L. FASULO DRYWALL | 013 | CLOSED | 918.06 | 0 | 918.06 | 918.06
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | CA: INSTALL DISPENSERS IN LAB - BLDG. 13 ROOMS 111 & 112 | 013 | CLOSED | 469.164 | 0 | 274.618 | 274.618
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 1477.18 | 0 | 0 | 0
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | EH&S:TESTING OF LAB BENCH AND PAINT (N/L) | 013 | CLOSED | 60 | 0 | 76.8 | 76.8
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | EL:INSTALL NEW ELECTRICAL FOR BLDG 13 ROOM 112 | 013 | CLOSED | 3480.6862 | 0 | 2988.048 | 2988.048
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | IN:ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP 13-112 | 013 | CLOSED | 192.168 | 0 | 224.196 | 224.196
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | MO:REMOVE STEEL DESKS AND CASEWORK BLDG 13, ROOM 112 | 013 | CLOSED | 648 | 0 | 48.288 | 48.288
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | PA:REPAIR SMALL HOLES AND PAINT ROOM BLDG 13, ROOM 112 | 013 | CLOSED | 1604.736 | 0 | 594.936 | 594.936
PJ0004674 | ADDITION OF WALL CABINETS, WORKBENCHS, & SAFETY EQUIP IN 13-112 | MOLLAN, CHERYL L. | CLOSED | 2013-10-09 | PL: WATER SHUT-OFF FOR CONTRACTOR FOR EQUIP INSTALL AT 13-112 | 013 | CLOSED | 522.336 | 0 | 370.158 | 370.158
PJ0004674 Total | [7 empty] | 55899.9106 | 0 | 52022.6844 | 52022.6844
PJ0004672 | SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | NORTON, DAVE | CLOSED | 2013-10-15 | AD: FLINT TRADING INC | GENERAL | CLOSED | 43922.0983 | 0 | 43922.0983 | 43922.0983
PJ0004672 | SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | NORTON, DAVE | CLOSED | 2013-10-15 | AD: GOLDEN STATE | GENERAL | CLOSED | 47767.6355 | 0 | 47364.8447 | 47364.8447
PJ0004672 | SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | NORTON, DAVE | CLOSED | 2013-10-15 | AD: JOC 14.034.022 MAINO | GENERAL | CLOSED | 26326.0232 | 0 | 26326.0232 | 26326.0232
PJ0004672 | SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | NORTON, DAVE | CLOSED | 2013-10-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004672 | SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | NORTON, DAVE | CLOSED | 2013-10-15 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | GENERAL | CLOSED | 0 | 0 | 8.4 | 8.4
PJ0004672 | SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | NORTON, DAVE | CLOSED | 2013-10-15 | IN: SR 13/14: REPAVE AND PAINT 10 CAL POLY GREEN CROSSWALKS | GENERAL | CLOSED | 235.951 | 0 | 35.322 | 35.322
PJ0004672 Total | [7 empty] | 118251.708 | 0 | 117656.6882 | 117656.6882
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | AD: GOLDING GONCRETE CORING | 042 | CLOSED | 963 | 0 | 584.22 | 584.22
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | AD: TOWN AND COUNTRY FENCING | 042 | CLOSED | 6885.7282 | 0 | 6885.7175 | 6885.7175
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 370.41 | 0 | 0 | 0
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | IN: INSTALL FENCING FOR OUTDOOR WR MOTT - BLD 42 | 042 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | LA: AUGER HOLES FOR FENCE POSTS | 042 | CLOSED | 233.784 | 0 | 233.784 | 233.784
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | LO: INSTALL HARDWARE TO GATES | 042 | CLOSED | 904.176 | 0 | 584.22 | 584.22
PJ0004669 | INSTALL FENCING FOR OUTDOOR WEIGHT ROOM MOTT - BLD 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-27 | PA: PAINT DOOR HANDLE GUARDS | 042 | CLOSED | 142.728 | 0 | 59.364 | 59.364
PJ0004669 Total | [7 empty] | 9627.9382 | 0 | 8475.4175 | 8475.4175
PJ0004668 | SR 13/14: REPLACE BOILER TUBES ON BOILER 1 | BRENNAN, MICHAEL | CLOSED | 2013-10-10 | AD: R.F. MACDONALD | 040 | CLOSED | 41000 | 0 | 34937.5 | 34937.5
PJ0004668 | SR 13/14: REPLACE BOILER TUBES ON BOILER 1 | BRENNAN, MICHAEL | CLOSED | 2013-10-10 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004668 Total | [7 empty] | 41000 | 0 | 34937.5 | 34937.5
PJ0004667 | INSTALL ELECTRIC STRIKE/CARD ACCESS - BLD 34 RM 159B | MCNALLY, CURTIS | CLOSED | 2013-09-30 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 233.14 | 0 | 0 | 0
PJ0004667 | INSTALL ELECTRIC STRIKE/CARD ACCESS - BLD 34 RM 159B | MCNALLY, CURTIS | CLOSED | 2013-09-30 | IN: INSTALL ELECTRIC STRIKE/CARD ACCESS - BLD 34 RM 166A | 034 | CLOSED | 141.288 | 0 | 35.322 | 35.322
PJ0004667 | INSTALL ELECTRIC STRIKE/CARD ACCESS - BLD 34 RM 159B | MCNALLY, CURTIS | CLOSED | 2013-09-30 | LO: INSTALL ELECTRIFIED LATCH AT 34-159B | 034 | CLOSED | 751.1118 | 0 | 584.028 | 584.028
PJ0004667 | INSTALL ELECTRIC STRIKE/CARD ACCESS - BLD 34 RM 159B | MCNALLY, CURTIS | CLOSED | 2013-09-30 | PA: STRIP LEAD PAINTED DOOR FRAME AND TOUCH UP PAINT | 034 | CLOSED | 258.0548 | 0 | 216.678 | 216.678
PJ0004667 Total | [7 empty] | 1383.5946 | 0 | 836.028 | 836.028
PJ0004666 | SP 13/14: REMOVE FENCE FROM PARKING LOT AT MUSTANG VILLAGE | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-09 | AD: CENTRAL COAST FENCE | GENERAL | CLOSED | 1610.35 | 0 | 1610.35 | 1610.35
PJ0004666 | SP 13/14: REMOVE FENCE FROM PARKING LOT AT MUSTANG VILLAGE | KUENTZEL, DOUGLAS A. | CLOSED | 2013-10-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 161.04 | 0 | 0 | 0
PJ0004666 Total | [7 empty] | 1771.39 | 0 | 1610.35 | 1610.35
PJ0004665 | SR 13/14: INSTALL CLASSROOM SIGNS - ALL GEN. PURPOSE LECTURE RMS | MOLLAN, CHERYL L. | CLOSED | 2013-10-03 | AD: THE SIGN PLACE | GENERAL | CLOSED | 0 | 0 | 4718.82 | 4718.82
PJ0004665 | SR 13/14: INSTALL CLASSROOM SIGNS - ALL GEN. PURPOSE LECTURE RMS | MOLLAN, CHERYL L. | CLOSED | 2013-10-03 | CA:INSTALL CLASSROOM SIGNS IN ALL PURPOSE ROOMS | GENERAL | CLOSED | 4383.5197 | 0 | 3137.0725 | 3137.0725
PJ0004665 | SR 13/14: INSTALL CLASSROOM SIGNS - ALL GEN. PURPOSE LECTURE RMS | MOLLAN, CHERYL L. | CLOSED | 2013-10-03 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004665 | SR 13/14: INSTALL CLASSROOM SIGNS - ALL GEN. PURPOSE LECTURE RMS | MOLLAN, CHERYL L. | CLOSED | 2013-10-03 | IN: INSTALL CLASSROOM SIGNS - ALL GEN. PURPOSE LECTURE RMS | GENERAL | CLOSED | 53.38 | 0 | 26.69 | 26.69
PJ0004665 | SR 13/14: INSTALL CLASSROOM SIGNS - ALL GEN. PURPOSE LECTURE RMS | MOLLAN, CHERYL L. | CLOSED | 2013-10-03 | PA:PAINT / VARNISH DOORS WHERE SIGNS REMOVED | GENERAL | CLOSED | 3368.2 | 0 | 660.6 | 660.6
PJ0004665 Total | [7 empty] | 7805.0997 | 0 | 8543.1825 | 8543.1825
PJ0004663 | REPAIR BROKEN SPIGOT & ASSOCIATED DAMAGE - BLD 11 RM 103 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-10-02 | CA:RESPOND AND MAKE REPAIRS TO WATER DAMAGE AT 11-103 | 011 | CLOSED | 0 | 0 | 462.805 | 462.805
PJ0004663 | REPAIR BROKEN SPIGOT & ASSOCIATED DAMAGE - BLD 11 RM 103 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-10-02 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0004663 | REPAIR BROKEN SPIGOT & ASSOCIATED DAMAGE - BLD 11 RM 103 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-10-02 | CU:PROVIDE CLEAN-UP SUPPORT FOR FLOOD IN 11-103 (NO LABOR) | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0004663 | REPAIR BROKEN SPIGOT & ASSOCIATED DAMAGE - BLD 11 RM 103 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-10-02 | PA:TAPE, PATCH, AND PAINT WALL FROM FLOOD DAMAGE AT 11-103 | 011 | CLOSED | 0 | 0 | 123.675 | 123.675
PJ0004663 | REPAIR BROKEN SPIGOT & ASSOCIATED DAMAGE - BLD 11 RM 103 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-10-02 | PL:REPAIR DIONIZED WATER SPIGOT AT 11-103 | 011 | CLOSED | 0 | 0 | 81.615 | 81.615
PJ0004663 Total | [7 empty] | 0 | 0 | 668.095 | 668.095
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | AD: JOC 13.029.025 MAINO | U-UDOR | CLOSED | 168217.5 | 0 | 138422.94 | 138422.94
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | CA:CAULK AND FILL LID JOINTS | U-UDOR | CLOSED | 1325.5879 | 0 | 1608.645 | 1608.645
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | CPE:SUPPORT FOR BLDG 38 LEAK | U-UDOR | CLOSED | 4815.8553 | 0 | 3534.075 | 3534.075
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | U-UDOR | CLOSED | 0 | 0 | 12 | 12
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | EL: SUPPORT FOR BLDG 38 LEAK | U-UDOR | CLOSED | 1500.5658 | 0 | 1084.67 | 1084.67
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | ES: SUPPORT BLDG 38 LEAK | U-UDOR | CLOSED | 520.3 | 0 | 888.245 | 888.245
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | IN: SR 13/14: REPAIR LEAK / HOT WATER LINES - BLD 38 | U-UDOR | CLOSED | 2135.2 | 0 | 720.63 | 720.63
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | LA:SUPPORT FOR BLDG 38 LEAK | U-UDOR | CLOSED | 1367.2737 | 0 | 217.5237 | 217.5237
PJ0004662 | SR 13/14: REPAIR LEAK IN UTILIDOR RUN-OUT FOR BLD 38 | BRENNAN, MICHAEL | CLOSED | 2013-09-30 | PL:SUPPORT FOR BLDG 38 LEAK | U-UDOR | CLOSED | 1469.0421 | 0 | 588.4325 | 588.4325
PJ0004662 Total | [7 empty] | 181351.3248 | 0 | 147077.1612 | 147077.1612
PJ0004661 | INSPECTION OF UNIVERSITY HOUSE | GONZALES, ALBERT M. | CLOSED | 2013-09-30 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0004661 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0004659 | MOVE FOOTBALL PLAYCLOCK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-19 | CA: RELOCATE SPANOS STADIUM PLAYCLOCK | 061 | CLOSED | 766.656 | 0 | 486.738 | 486.738
PJ0004659 | MOVE FOOTBALL PLAYCLOCK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-19 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 192.4 | 0 | 0 | 0
PJ0004659 | MOVE FOOTBALL PLAYCLOCK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-19 | EL: DISCONNECT PLAYCLOCK AND RECONNECT AFTER MOVE - SPANOS STAD | 061 | CLOSED | 1797.984 | 0 | 2366.148 | 2366.148
PJ0004659 | MOVE FOOTBALL PLAYCLOCK - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2013-09-19 | IN: MOVE FOOTBALL PLAYCLOCK - SPANOS STADIUM | 061 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004659 Total | [7 empty] | 2821.096 | 0 | 2916.942 | 2916.942
PJ0004658 | PLANT STARKEY MEMORIAL TREE - 10/02/13 - ACROSS FROM CRANDALL | POPHAM, DONALD J. | CLOSED | 2013-09-25 | CA: INSTALL BASE & PLAQUE - STARKEY MEMORIAL TREE NEAR CRANDALL | 003 | CLOSED | 0 | 0 | 977.212 | 977.212
PJ0004658 | PLANT STARKEY MEMORIAL TREE - 10/02/13 - ACROSS FROM CRANDALL | POPHAM, DONALD J. | CLOSED | 2013-09-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004658 | PLANT STARKEY MEMORIAL TREE - 10/02/13 - ACROSS FROM CRANDALL | POPHAM, DONALD J. | CLOSED | 2013-09-25 | LA: INSTALL MEMORIAL TREE AT O'NEILL LAWN-10/1 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004658 | PLANT STARKEY MEMORIAL TREE - 10/02/13 - ACROSS FROM CRANDALL | POPHAM, DONALD J. | CLOSED | 2013-09-25 | SUPPLY RENTAL: STARKEY TREE DEDICATION - 10/2 | 003 | CLOSED | 0 | 0 | 59.25 | 59.25
PJ0004658 Total | [7 empty] | 0 | 0 | 1036.462 | 1036.462
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | AD: APC CONTRACTORS | 046T-M028 | CLOSED | 1584 | 0 | 1583 | 1583
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | AD: G.F. GARCIA AND SONS | 046T-M028 | CLOSED | 0 | 0 | 2461 | 2461
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | AD: GOSS ENGINEERING | 046T-M028 | CLOSED | 0 | 0 | 3600 | 3600
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | AD: JOC 13.029.037 MAINO | 046T-M028 | CLOSED | 285460 | 0 | 283244.56 | 283244.56
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | AD: MCKENNA | 046T-M028 | CLOSED | 0 | 0 | 845 | 845
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | CP: PROJECT CONTINGENCY | 046T-M028 | CLOSED | 0 | 0 | 0 | 0
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | CPE: ASSIST JOC WITH REPIPE | 046T-M028 | CLOSED | 3515.8553 | 0 | 4333.605 | 4333.605
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | EH&S: CONTRACTOR SUPPORT | 046T-M028 | CLOSED | 379 | 0 | 0 | 0
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | IN: SR 13/14:REPAIR UTILIDOR LEAK & DECK - BLD 46T | 046T-M028 | CLOSED | 237.541 | 0 | 1067.6 | 1067.6
PJ0004657 | SR 13/14:REPAIR UTILIDOR LEAK & DECK - PHASE I - BLD 46T | GONZALES, ALBERT M. | CLOSED | 2013-09-25 | PL: NATATORIUM UTILIDOR REROUTE PROJECT SUPPORT | 046T-M028 | CLOSED | 3337.7891 | 0 | 2197.645 | 2197.645
PJ0004657 Total | [7 empty] | 294514.1854 | 0 | 299332.41 | 299332.41
PJ0004655 | DETERMINE IF WALLS ARE CONSTRUCTED PER CODE - BLD 34 RM 127 | MCNALLY, CURTIS | CLOSED | 2013-09-20 | CA: DEMO/RECONSTRUCT PORTION OF EXISTING CONSTRUCTION | 034 | CLOSED | 8020.2236 | 0 | 1317.402 | 1317.402
PJ0004655 | DETERMINE IF WALLS ARE CONSTRUCTED PER CODE - BLD 34 RM 127 | MCNALLY, CURTIS | CLOSED | 2013-09-20 | EL: INSTALL DUPLEX RECEPTICLES | 034 | CLOSED | 4801.3627 | 0 | 2515.788 | 2515.788
PJ0004655 | DETERMINE IF WALLS ARE CONSTRUCTED PER CODE - BLD 34 RM 127 | MCNALLY, CURTIS | CLOSED | 2013-09-20 | IN: DETERMINE IF WALLS ARE CONSTRUCTED PER CODE - BLD 34 RM 127 | 034 | CLOSED | 213.947 | 0 | 192.168 | 192.168
PJ0004655 | DETERMINE IF WALLS ARE CONSTRUCTED PER CODE - BLD 34 RM 127 | MCNALLY, CURTIS | CLOSED | 2013-09-20 | PA:PAINT WALLS CONSTRUCTED BY DEPT. STAFF | 034 | CLOSED | 3891.2249 | 0 | 4192.116 | 4192.116
PJ0004655 Total | [7 empty] | 16926.7583 | 0 | 8217.474 | 8217.474
PJ0004654 | SP 13/14: RAILING - EAST, WEST, & SOUTH SIDES - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2013-09-20 | AD: JOC 13.029.023 MAINO | 061 | CLOSED | 120563.2772 | 0 | 126569.9041 | 126569.9041
PJ0004654 | SP 13/14: RAILING - EAST, WEST, & SOUTH SIDES - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2013-09-20 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 13007.51 | 0 | 0 | 0
PJ0004654 | SP 13/14: RAILING - EAST, WEST, & SOUTH SIDES - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2013-09-20 | IN: RAILING - EAST, WEST, & SOUTH SIDES - SPANOS STADIUM | 061 | CLOSED | 384.336 | 0 | 64.056 | 64.056
PJ0004654 | SP 13/14: RAILING - EAST, WEST, & SOUTH SIDES - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2013-09-20 | PA: RAILING - EAST, WEST, & SOUTH SIDES - SPANOS STADIUM | 061 | CLOSED | 9127.4686 | 0 | 7320.6712 | 7320.6712
PJ0004654 Total | [7 empty] | 143082.5918 | 0 | 133954.6313 | 133954.6313
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | AD: FLOOR CONNECTION | 034 | CLOSED | 2160.9399 | 0 | 2160.9399 | 2160.9399
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | CA:REMOVE LEAD PAINTED SHELVING UNITS- BLDG 34,113 | 034 | CLOSED | 3252.247 | 0 | 3229.0186 | 3229.0186
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 853.54 | 0 | 0 | 0
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 034 | CLOSED | 0 | 0 | 189.6 | 189.6
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | EL:REMOVE ABANDONED CONDUIT AND INSTALL NEW ELECTRI BLD 34 RM113 | 034 | CLOSED | 2985.8522 | 0 | 2072.088 | 2072.088
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | IN: CLEANUP AND REMODEL - BLD 34 RM 113 | 034 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004652 | CLEANUP AND REMODEL - BLD 34 RM 113 | MOLLAN, CHERYL L. | CLOSED | 2013-09-17 | PA:PATCH AND PAINT BLDG 34, RM 113 | 034 | CLOSED | 1427.28 | 0 | 1249.824 | 1249.824
PJ0004652 Total | [7 empty] | 10743.9151 | 0 | 8965.5265 | 8965.5265
PJ0004651 | AUTOMATIC DOOR OUTSIDE HEALTH EDUCATION - BLD 27 RM 10 | MOLLAN, CHERYL L. | CLOSED | 2013-09-13 | AD: STATE FIRE MARSHAL FEES | 027 | CLOSED | 481.5 | 0 | 0 | 0
PJ0004651 | AUTOMATIC DOOR OUTSIDE HEALTH EDUCATION - BLD 27 RM 10 | MOLLAN, CHERYL L. | CLOSED | 2013-09-13 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1296.43 | 0 | 0 | 0
PJ0004651 | AUTOMATIC DOOR OUTSIDE HEALTH EDUCATION - BLD 27 RM 10 | MOLLAN, CHERYL L. | CLOSED | 2013-09-13 | EL:INSTALL ELECTRICAL FOR AUTOMATIC DOOR OPENER HEALTH CENTER | 027 | CLOSED | 4604.7739 | 0 | 1922.292 | 1922.292
PJ0004651 | AUTOMATIC DOOR OUTSIDE HEALTH EDUCATION - BLD 27 RM 10 | MOLLAN, CHERYL L. | CLOSED | 2013-09-13 | IN: AUTOMATIC DOOR OUTSIDE HEALTH EDUCATION - BLD 27 RM 10 | 027 | CLOSED | 211.932 | 0 | 176.61 | 176.61
PJ0004651 | AUTOMATIC DOOR OUTSIDE HEALTH EDUCATION - BLD 27 RM 10 | MOLLAN, CHERYL L. | CLOSED | 2013-09-13 | LO:SUPPLY AND INSTALL NEW DOOR PUSH PAD AT HEALTH CENTER | 027 | CLOSED | 7413.3354 | 0 | 6471.306 | 6471.306
PJ0004651 Total | [7 empty] | 14007.9713 | 0 | 8570.208 | 8570.208
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | AD: GOSS ENGINEERING | 040 | CLOSED | 6000 | 0 | 4685 | 4685
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | AD: JOC 13.029.021 MAINO | 040 | CLOSED | 122340 | 0 | 112869.75 | 112869.75
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | CA: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 187.96 | 0 | 187.96 | 187.96
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | CPE: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 7692.7291 | 0 | 7692.62 | 7692.62
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | EL: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 2315.5822 | 0 | 2315.58 | 2315.58
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | EO: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 1009.3798 | 0 | 1216.67 | 1216.67
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | ES: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 4659.8224 | 0 | 4659.66 | 4659.66
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | IN: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | 040 | CLOSED | 2135.2 | 0 | 106.76 | 106.76
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | LA: REPAIR IRRIGATION DAMAGED BY HOT WATER LEAK - CENTRAL PLANT | 040 | CLOSED | 3668.0219 | 0 | 519.52 | 519.52
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | PCV ES: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 234.135 | 0 | 234.135 | 234.135
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | PCV PL: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 27.205 | 0 | 27.205 | 27.205
PJ0004650 | SR 13/14: CENTRAL PLANT CATASTROPHIC LEAK - CAMPUS CORE | BRENNAN, MICHAEL | CLOSED | 2013-09-16 | PL: SUPPORT FOR CENTRAL PLANT CATASTROPHIC LEAK | 040 | CLOSED | 4847.5819 | 0 | 4847.455 | 4847.455
PJ0004650 Total | [7 empty] | 155117.6173 | 0 | 139362.315 | 139362.315
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | AD: FLOOR CONNECTION | 006 | CLOSED | 7185.05 | 0 | 7185.05 | 7185.05
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | AD: J.L. FASULO DRYWALL | 006 | CLOSED | 1712 | 0 | 724.39 | 724.39
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | AD: JOC 14.034.009 MAINO | 006 | CLOSED | 7627.9016 | 0 | 7627.9016 | 7627.9016
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 2930.8 | 0 | 0 | 0
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | EL: INSTALL ELECTRICAL FOR TV - PAC | 006 | CLOSED | 3900.6862 | 0 | 1943.214 | 1943.214
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | IN: RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | 006 | CLOSED | 384.336 | 0 | 176.61 | 176.61
PJ0004647 | RENOVATE/UPGRADE GREENROOM & FOUNDERS ROOM - PAC RM 109 | LAMPMAN, GREG | CLOSED | 2013-09-11 | PA: PAINT ENTIRE GREENROOM AND RESTROOM | 006 | CLOSED | 5956.8373 | 0 | 2989.908 | 2989.908
PJ0004647 Total | [7 empty] | 29697.6111 | 0 | 20647.0736 | 20647.0736
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: A&J REFRIGERATION | 038 | OPEN | 5136 | 0 | 5094.27 | 5094.27
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: ASAP REPROGRAPHICS | 038 | OPEN | 0 | 0 | 49.6908 | 49.6908
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: FISHER SCI (60" PROTECTOR, BLOWER, AND 48' BSC) | 038 | OPEN | 25497.8004 | 0 | 14593.6551 | 14593.6551
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: GOSS ENGINEERING | 038 | OPEN | 13696 | 0 | 11114.625 | 11114.625
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: JOC 16.40.4644 NEWTON | 038 | OPEN | 19062.2319 | 934.8911 | 18127.3408 | 19062.2319
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: MCKENNA ENVIRONMENTAL | 038 | CLOSED | 1979.5 | 0 | 1423.1 | 1423.1
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: MORELAND THOMPSON, INC. | 038 | OPEN | 3852 | 0 | 3852 | 3852
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | AD: STATE FIRE MARSHAL FEES | 038 | OPEN | 0 | 0 | 1125.3725 | 1125.3725
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | CA: REMOVE CABINETS & ALTER COUNTER | 038 | ASSIGNED | 8818.8 | 0 | 10884.7578 | 10884.7578
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | CP: PROJECT CONTINGENCY | 038 | OPEN | 7747.82 | 0 | 0 | 0
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 038 | COMPLETE | 0 | 0 | 63 | 63
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | EL: INSTALLATION OF FUME HOOD & BSC - BLDG. 38 RM 133 | 038 | CLOSED | 12586.5504 | 0 | 10859.67 | 10859.67
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | ES: INSTALL FUME HOOD EXHAUST | 038 | ASSIGNED | 7646.4127 | 0 | 29145.486 | 29145.486
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | IN: CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | 038 | ASSIGNED | 565.6145 | 0 | 128.112 | 128.112
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | LO: ORANGE CORE NORTH DOOR | 038 | COMPLETE | 130.044 | 0 | 89.946 | 89.946
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | MO: REMOVE CABINETS FROM BLDG. 38 133/134 | 038 | CLOSED | 194.4 | 0 | 108.648 | 108.648
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | PA: PAINT WALLS | 038 | CLOSED | 3339.4368 | 0 | 2033.886 | 2033.886
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | PL: CONNECT FUME HOOD IN WET LAB 38-133 (REPLACES WO0241529) | 038 | COMPLETE | 0 | 0 | 2437.3727 | 2437.3727
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | PL: INSTALL FIXTURES | 038 | CLOSED | 6311.56 | 0 | 7248.3652 | 7248.3652
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | PM: CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0004644 | CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | KUENTZEL, DOUGLAS A. | PUNCH_LIST | 2013-09-04 | SM: CONVERT SPACE TO WET LAB - BLD 38 RMS 133/134 | 038 | OPEN | 0 | 0 | 0 | 0
PJ0004644 Total | [7 empty] | 116564.1707 | 934.8911 | 118379.2979 | 119314.189
PJ0004643 | SR 13/14: ABATE MONITORING WELLS | NEEL, JOEL | CLOSED | 2013-09-06 | AD: EARTH SYSTEMS PACIFIC | 009 | CLOSED | 10151.65 | 0 | 10138.7 | 10138.7
PJ0004643 | SR 13/14: ABATE MONITORING WELLS | NEEL, JOEL | CLOSED | 2013-09-06 | AD: JOC 13.029.032 MAINO | 009 | CLOSED | 25487.5 | 0 | 21281.74 | 21281.74
PJ0004643 | SR 13/14: ABATE MONITORING WELLS | NEEL, JOEL | CLOSED | 2013-09-06 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0004643 | SR 13/14: ABATE MONITORING WELLS | NEEL, JOEL | CLOSED | 2013-09-06 | IN: SR 13/14: ABATE MONITORING WELLS | 009 | CLOSED | 213.52 | 0 | 53.38 | 53.38
PJ0004643 Total | [7 empty] | 35852.67 | 0 | 31473.82 | 31473.82
PJ0004642 | INSTALL BIKE RACKS - RESIDENCES | GONZALES, ALBERT M. | CLOSED | 2013-09-04 | AD: PEAK RACKS | RESIDENCE | CLOSED | 5350 | 0 | 5026.86 | 5026.86
PJ0004642 | INSTALL BIKE RACKS - RESIDENCES | GONZALES, ALBERT M. | CLOSED | 2013-09-04 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 541.41 | 0 | 0 | 0
PJ0004642 | INSTALL BIKE RACKS - RESIDENCES | GONZALES, ALBERT M. | CLOSED | 2013-09-04 | IN: INSTALL BIKE RACKS - RESIDENCES | RESIDENCE | CLOSED | 64.056 | 0 | 128.112 | 128.112
PJ0004642 Total | [7 empty] | 5955.466 | 0 | 5154.972 | 5154.972
PJ0004641 | CENG PLAZA TILE ENGRAVING - BLD 192 RM 100E | MOLLAN, CHERYL L. | CLOSED | 2013-09-03 | AD: BURCH CONCRETE SOLUTIONS | 192 | CLOSED | 2033 | 0 | 2033 | 2033
PJ0004641 | CENG PLAZA TILE ENGRAVING - BLD 192 RM 100E | MOLLAN, CHERYL L. | CLOSED | 2013-09-03 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 209.71 | 0 | 0 | 0
PJ0004641 | CENG PLAZA TILE ENGRAVING - BLD 192 RM 100E | MOLLAN, CHERYL L. | CLOSED | 2013-09-03 | IN: CENG PLAZA TILE ENGRAVING - BLD 192 RM 100E | 192 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004641 Total | [7 empty] | 2306.766 | 0 | 2065.028 | 2065.028
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: CANNON ENGINEERING | 228 | OPEN | 5350 | 0 | 5350 | 5350
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: GOSS ENGINEERING | 228 | OPEN | 42800 | 18511 | 23754 | 42265
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: ITS (PLAN REVIEW) | 228 | OPEN | 1605 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: JOC 14.034.024 MAINO | 228 | CLOSED | 40038.33 | 0 | 38841 | 38841
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: MAINO (LVPW) | 228 | CLOSED | 5778 | 0 | 5342.51 | 5342.51
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: PG&E (PERMIT & ENGR FEES) | 228 | OPEN | 8025 | 0 | 2675 | 2675
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: STATE FIRE MARSHAL | 228 | OPEN | 1605 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | AD: WILDAN ENGINEERING | 228 | OPEN | 1605 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | CP: PROJECT CONTINGENCY | 228 | OPEN | 11249.88 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | EH&S: | 228 | OPEN | 514.944 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | EL: | 228 | OPEN | 1707.342 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | IN: CABLE TRAY INSTALLATION - CP PIER | 228 | ASSIGNED | 1186.8192 | 0 | 141.288 | 141.288
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | PL: SUPPORT FOR CABLE TRAY INSTALLATION AT CP PIER | 228 | CLOSED | 2283.5201 | 0 | 106.416 | 106.416
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | PM: UTILITY UPGRADES - CP PIER | 228 | OPEN | 0 | 0 | 0 | 0
PJ0004639 | ASSESS UTILITY UPGRADES - CP PIER 228 | ULM, AARON | DESIGN | 2013-07-25 | SM: ASSESS UTILITY UPGRADES - CP PIER 228 | 228 | OPEN | 0 | 0 | 0 | 0
PJ0004639 Total | [7 empty] | 123748.8353 | 18511 | 76210.214 | 94721.214
PJ0004638 | DESIGN REMODEL OF 1ST FLOOR OF BLDG 26 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | AD: REA AND LUKER | 026 | CLOSED | 20212.3 | 0 | 6063.69 | 6063.69
PJ0004638 | DESIGN REMODEL OF 1ST FLOOR OF BLDG 26 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | CP: PROJECT CONTINGENCY PHASE | 026 | CLOSED | 2250.55 | 0 | 0 | 0
PJ0004638 | DESIGN REMODEL OF 1ST FLOOR OF BLDG 26 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | CPE: | 026 | CLOSED | 555.6804 | 0 | 0 | 0
PJ0004638 | DESIGN REMODEL OF 1ST FLOOR OF BLDG 26 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | EL: | 026 | CLOSED | 600.0024 | 0 | 0 | 0
PJ0004638 | DESIGN REMODEL OF 1ST FLOOR OF BLDG 26 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | ES: | 026 | CLOSED | 555.6804 | 0 | 0 | 0
PJ0004638 | DESIGN REMODEL OF 1ST FLOOR OF BLDG 26 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | PL: | 026 | CLOSED | 581.0988 | 0 | 0 | 0
PJ0004638 Total | [7 empty] | 24755.312 | 0 | 6063.69 | 6063.69
PJ0004637 | INSPECT & CERTIFY FIRE SPRINKLERS -PCV & BOTH PARKING STRUCTURES | GRIFFIN, PATRICK E. | CLOSED | 2013-08-27 | AD: ALPHA FIRE | 171 | CLOSED | 10619.75 | 0 | 10619.75 | 10619.75
PJ0004637 | INSPECT & CERTIFY FIRE SPRINKLERS -PCV & BOTH PARKING STRUCTURES | GRIFFIN, PATRICK E. | CLOSED | 2013-08-27 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 1074.79 | 0 | 0 | 0
PJ0004637 | INSPECT & CERTIFY FIRE SPRINKLERS -PCV & BOTH PARKING STRUCTURES | GRIFFIN, PATRICK E. | CLOSED | 2013-08-27 | IN: INSPECT/CERTIFY FIRE SPRINKLERS-PCV &BOTH PARKING STRUCTURES | 171 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004637 Total | [7 empty] | 11822.652 | 0 | 10683.806 | 10683.806
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | AD: BELFOR - EMERGENCY CLEAN-UP SERVICE | 170D | CLOSED | 0 | 0 | 54692.1726 | 54692.1726
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | AD: BELFOR CSU JOC N2013001 (NO OVERHEAD) | 170D | CLOSED | 0 | 0 | 63616.19 | 63616.19
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | CA: SUPPORT FOR FLOOD REMEDIATION AT CERRO VISTA D301 & D401 | 170D | CLOSED | 0 | 0 | 404.478 | 404.478
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | CP: PROJECT CONTINGENCY | 170D | CLOSED | 0 | 0 | 0 | 0
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | IN: FLOOD REMEDIATION AT CERRO VISTA REMAULDO D301&D401 | 170D | CLOSED | 0 | 0 | 448.392 | 448.392
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | PCV EL: SUPPORT FOR FLOOD REMEDIATION AT CERRO VISTA D301 & D401 | 170D | CLOSED | 0 | 0 | 269.664 | 269.664
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | PCV ES: SUPPORT FOR FLOOD REMEDIATION AT CERRO VISTA D301&D401 | 170D | CLOSED | 0 | 0 | 1371.03 | 1371.03
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | PCV PL: SUPPORT FOR FLOOD REMEDIATION AT CERRO VISTA D301 & D401 | 170D | CLOSED | 0 | 0 | 391.752 | 391.752
PJ0004635 | SPRINKLER FLOOD REMEDIATION & CONSTRUCTION-CERRO VISTA D301&D401 | MOLLAN, CHERYL L. | CLOSED | 2013-08-26 | PL: SUPPORT FOR FLOOD REMEDIATION AT CERRO VISTA D301 & D401 | 170D | CLOSED | 0 | 0 | 348.564 | 348.564
PJ0004635 Total | [7 empty] | 0 | 0 | 121542.2426 | 121542.2426
PJ0004634 | INSTALL PANIC BUTTONS IN DEAN'S SUITE - BLD 192 RM 301 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | AD: CAME SECURITY | 192 | CLOSED | 2942.5 | 0 | 2942.5 | 2942.5
PJ0004634 | INSTALL PANIC BUTTONS IN DEAN'S SUITE - BLD 192 RM 301 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | ANTS: REMOTE ALARM SET UP AND INSTALL SUPPORT | 192 | CLOSED | 144.144 | 0 | 48.048 | 48.048
PJ0004634 | INSTALL PANIC BUTTONS IN DEAN'S SUITE - BLD 192 RM 301 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 393.96 | 0 | 0 | 0
PJ0004634 | INSTALL PANIC BUTTONS IN DEAN'S SUITE - BLD 192 RM 301 | GONZALES, ALBERT M. | CLOSED | 2013-08-23 | IN: INSTALL PANIC BUTTONS IN DEAN'S SUITE - BLD 192 RM 301 | 192 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004634 Total | [7 empty] | 3544.66 | 0 | 3054.604 | 3054.604
PJ0004633 | INSTALL FLOOD LIGHTS - BLD 34 RM 148 | MOLLAN, CHERYL L. | CLOSED | 2013-08-21 | AD: MORELAND THOMPSON | 034 | CLOSED | 4127.525 | 0 | 4127.525 | 4127.525
PJ0004633 | INSTALL FLOOD LIGHTS - BLD 34 RM 148 | MOLLAN, CHERYL L. | CLOSED | 2013-08-21 | AD: SANTA MARIA ACOUSTICAL | 034 | CLOSED | 6123.7705 | 0 | 6123.7705 | 6123.7705
PJ0004633 | INSTALL FLOOD LIGHTS - BLD 34 RM 148 | MOLLAN, CHERYL L. | CLOSED | 2013-08-21 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 319.2 | 0 | 0 | 0
PJ0004633 | INSTALL FLOOD LIGHTS - BLD 34 RM 148 | MOLLAN, CHERYL L. | CLOSED | 2013-08-21 | IN: INSTALL FLOOD LIGHTS - BLD 34 RM 148 & 145 | 034 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004633 Total | [7 empty] | 10698.6075 | 0 | 10379.4075 | 10379.4075
PJ0004632 | SP 13/14: FISHER VAV/DDC CONTROLS CONVERSION - BLD 33 | BRENNAN, MICHAEL | CLOSED | 2013-08-21 | AD: SIEMENS INDUSTRIES | 033 | CLOSED | 42788.23 | 0 | 42788.23 | 42788.23
PJ0004632 | SP 13/14: FISHER VAV/DDC CONTROLS CONVERSION - BLD 33 | BRENNAN, MICHAEL | CLOSED | 2013-08-21 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 6557.38 | 0 | 0 | 0
PJ0004632 | SP 13/14: FISHER VAV/DDC CONTROLS CONVERSION - BLD 33 | BRENNAN, MICHAEL | CLOSED | 2013-08-21 | EL:INSTALL 3 VFDS AT FISCHER SCIENCE | 033 | CLOSED | 12602.0465 | 0 | 7384.932 | 7384.932
PJ0004632 | SP 13/14: FISHER VAV/DDC CONTROLS CONVERSION - BLD 33 | BRENNAN, MICHAEL | CLOSED | 2013-08-21 | ES:VFD INSTALL FOR FISCHER SCIENCE | 033 | CLOSED | 7308.084 | 0 | 2098.65 | 2098.65
PJ0004632 | SP 13/14: FISHER VAV/DDC CONTROLS CONVERSION - BLD 33 | BRENNAN, MICHAEL | CLOSED | 2013-08-21 | IN: SP 13/14: FISHER VAV/DDC CONTROLS CONVERSION - BLD 33 | 033 | CLOSED | 1024.896 | 0 | 240.666 | 240.666
PJ0004632 Total | [7 empty] | 70280.6365 | 0 | 52512.478 | 52512.478
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | AD: ASAP REPROGRAPHICS (DIRECT PAY) | 009 | CLOSED | 0 | 0 | 73.27 | 73.27
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | AD: JOC 13.030.016 MAINO | 009 | CLOSED | 235859.03 | 0 | 234021.8721 | 234021.8721
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 009 | CLOSED | 2618.9748 | 0 | 5209.5839 | 5209.5839
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | AD: STATE FIRE MARSHAL FEES | 009 | CLOSED | 0 | 0 | 2367 | 2367
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | AD: THOMA ELECTRIC | 009 | CLOSED | 6313 | 0 | 6313 | 6313
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | ANTS: PROGRAMMING FOR FIRE ALARM | 009 | CLOSED | 427.6272 | 0 | 67.776 | 67.776
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 19347.33 | 0 | 0 | 0
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | EL:PURCHASE LIGHT FIXTURES AND PROVIDE CONTRACTOR SUPPORT | 009 | CLOSED | 5774.4372 | 0 | 5474.436 | 5474.436
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | IN: FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | 009 | CLOSED | 704.616 | 0 | 1264.092 | 1264.092
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | PL:PROVIDE CONTRACTOR SUPPORT FOR FIRE SPRINKLER INSTALL | 009 | CLOSED | 1181.0988 | 0 | 811.728 | 811.728
PJ0004631 | FIRE SPRINKLER INSTALLATION AT FARM SHOP - BLDG. 09 | MCNALLY, CURTIS | CLOSED | 2013-08-21 | PL:PROVIDE PROJECT SUPPORT | 009 | CLOSED | 1122.336 | 0 | 367.938 | 367.938
PJ0004631 Total | [7 empty] | 273348.45 | 0 | 255970.696 | 255970.696
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | AD: IES (TO BE INSTALLED BY JOC) | GENERAL | CLOSED | 195891.0311 | 0 | 192983.1991 | 192983.1991
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | AD: JOC 15.036.019 STAPLES | GENERAL | CLOSED | 235079.5778 | 0 | 235079.5778 | 235079.5778
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 20301.47 | 0 | 0 | 0
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | EL: PROVIDE ELECTRICAL CLEARANCE AND SUPPORT | GENERAL | CLOSED | 10219.92 | 0 | 29692.404 | 29692.404
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | IN: SP 13/14: LED STREET LIGHT RETROFIT | GENERAL | CLOSED | 1412.88 | 0 | 105.966 | 105.966
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | PM: SP 13/14: LED STREET LIGHT RETROFIT | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004630 | SP 13/14: LED STREET LIGHT RETROFIT | KUENTZEL, DOUGLAS A. | CONST_COMP | 2013-08-20 | SM: SP 13/14: LED STREET LIGHT RETROFIT | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0004630 Total | [7 empty] | 462904.8789 | 0 | 457861.1469 | 457861.1469
PJ0004628 | REMOVE INSULATION - POULTRY BLDG. 150E | WILWAND, MARK | CLOSED | 2013-08-16 | AD: JOC 13.029.003 MAINO | 150 | CLOSED | 27842.8873 | 0 | 27842.8873 | 27842.8873
PJ0004628 | REMOVE INSULATION - POULTRY BLDG. 150E | WILWAND, MARK | CLOSED | 2013-08-16 | CP: PROJECT CONTINGENCY | 150 | CLOSED | 2843.2 | 0 | 0 | 0
PJ0004628 | REMOVE INSULATION - POULTRY BLDG. 150E | WILWAND, MARK | CLOSED | 2013-08-16 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 150 | CLOSED | 0 | 0 | 6 | 6
PJ0004628 | REMOVE INSULATION - POULTRY BLDG. 150E | WILWAND, MARK | CLOSED | 2013-08-16 | IN: REMOVE & REPLACE INSULATION - BLDGS. 150 E&F | 150 | CLOSED | 256.224 | 0 | 192.168 | 192.168
PJ0004628 | REMOVE INSULATION - POULTRY BLDG. 150E | WILWAND, MARK | CLOSED | 2013-08-16 | LO: INSTALL (2) ORANGE KEY CORES AT BLDG. 150F | 150 | CLOSED | 58.044 | 0 | 87.066 | 87.066
PJ0004628 Total | [7 empty] | 31000.3553 | 0 | 28128.1213 | 28128.1213
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | AD: ATASCADERO GLASS (GLAZING) | 011 | CLOSED | 3210 | 0 | 1563.27 | 1563.27
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | AD: FASULO DRYWALL | 011 | CLOSED | 6028.38 | 0 | 6028.38 | 6028.38
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | AD: FLOOR CONNECTION | 011 | CLOSED | 1712 | 0 | 1254.04 | 1254.04
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | AD: STATE FIRE MARSHAL FEES | 011 | CLOSED | 107 | 0 | 0 | 0
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | CA:DISSASEMBLE/REASSEMBLE OFFICE DESK FOR MOVING CREW | 011 | CLOSED | 222.48 | 0 | 139.05 | 139.05
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 611.12 | 0 | 0 | 0
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | EL: INSTALL LIGHT SWITCH AND REWORK LIGHT WIRING | 011 | CLOSED | 743.1827 | 0 | 322.14 | 322.14
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | ES: REWORK SUPPPLY AND RETURN FOR 2 OFFICES | 011 | CLOSED | 1476.6144 | 0 | 1194.2377 | 1194.2377
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | IN: INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | 011 | CLOSED | 1130.304 | 0 | 247.254 | 247.254
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | MO:MOVE DESK AND BOOK SHELF TO HALL - MOVE BACK AFTER CARPET | 011 | CLOSED | 596.92 | 0 | 25.353 | 25.353
PJ0004625 | INSTALL WALL, CHANGE HVAC, MOD WINDOW - BLD 11 RM 212 | MCNALLY, CURTIS | CLOSED | 2013-08-15 | PA: PAINT NEWLY CONSTRUCTED WALL AND DOOR INFILL WALL | 011 | CLOSED | 2013.5627 | 0 | 1923.636 | 1923.636
PJ0004625 Total | [7 empty] | 17851.5637 | 0 | 12697.3607 | 12697.3607
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | AD: APC CONTRACTORS | 011 | CLOSED | 5232.3 | 0 | 3969.7 | 3969.7
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | AD: FLOOR CONNECTION | 011 | CLOSED | 5457 | 0 | 5393.2387 | 5393.2387
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | AD: MCKENNA ENVIRONMENTAL | 011 | CLOSED | 1510.84 | 0 | 1510.84 | 1510.84
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | AD: MEATHEAD MOVERS | 011 | CLOSED | 1323.59 | 0 | 1323.59 | 1323.59
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | AD: WLH BUILDERS | 011 | CLOSED | 5671 | 0 | 5671 | 5671
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | CA: ASSIST RUSSCO WITH INSTALLATION OF MODULAR FURNITURE 11-211D | 011 | CLOSED | 0 | 0 | 534.549 | 534.549
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 736.13 | 0 | 0 | 0
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | EL: INSTALL ADDITIONAL POWER OUTLET AND LIGHT FIXTURE | 011 | CLOSED | 2220.6802 | 0 | 2961.3862 | 2961.3862
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | IN: RENOVATE ROOM - BLD 11 RM 211C | 011 | CLOSED | 256.224 | 0 | 288.252 | 288.252
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | LO: PROVIDE/INSTALL LOCKSET FOR OFFICE 211C | 011 | CLOSED | 712.176 | 0 | 203.154 | 203.154
PJ0004622 | RENOVATE ROOM - BLD 11 RM 211C | MCNALLY, CURTIS | CLOSED | 2013-08-12 | PA: PAINT 4 OFFICES IN 2 PHASES | 011 | CLOSED | 5163.7343 | 0 | 1787.994 | 1787.994
PJ0004622 Total | [7 empty] | 28283.6744 | 0 | 23643.7039 | 23643.7039
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT VOLLEYBALL V. CSU FULLERTON - 11/23 | 042 | CLOSED | 0 | 0 | 1381.692 | 1381.692
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT VOLLEYBALL V. UC RIVERSIDE - 11/22 | 042 | CLOSED | 0 | 0 | 963.45 | 963.45
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT VOLLEYBALL V. UCSB- 11/2 | 042 | CLOSED | 0 | 0 | 1007.232 | 1007.232
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: VOLLEYBALL V. CSU LB - 9/28 | 042 | CLOSED | 0 | 0 | 1315.668 | 1315.668
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: VOLLEYBALL V. CSU NORTHRIDGE - 10/19 | 042 | CLOSED | 0 | 0 | 1045.572 | 1045.572
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: VOLLEYBALL V. HAWAI'I - 11/8 | 042 | CLOSED | 0 | 0 | 512.484 | 512.484
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: VOLLEYBALL V. UC IRVINE-9/27 | 042 | CLOSED | 0 | 0 | 733.032 | 733.032
PJ0004621 | 13/14 SUPPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU:VOLLEYBALL V. UC DAVIS - 10/18 | 042 | CLOSED | 0 | 0 | 1507.32 | 1507.32
PJ0004621 Total | [7 empty] | 0 | 0 | 8466.45 | 8466.45
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: ELEVATOR SUPPORT FOR M. SOCCER V. UCSB-10/25 | 162 | CLOSED | 0 | 0 | 2101.9294 | 2101.9294
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT M. SOCCER V. UCSB - 10/25 | 061 | CLOSED | 0 | 0 | 470.61 | 470.61
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: PROJECT CONTINGENCY | 162 | CLOSED | 0 | 0 | 0 | 0
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: SUPPORT M. SOCCER V. UCSB - 10/25 | 162 | CLOSED | 0 | 0 | 434.01 | 434.01
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: M. SOCCER V. PENN - 9/13 | 162 | CLOSED | 0 | 0 | 1737.42 | 1737.42
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: M. SOCCER V. SAN FRANCISCO - 9/20 | 162 | CLOSED | 0 | 0 | 1569.447 | 1569.447
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: M. SOCCER V. UC RIVERSIDE - 10/4 | 162 | CLOSED | 0 | 0 | 2125.71 | 2125.71
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: M. SOCCER V. YALE - 9/22 | 162 | CLOSED | 0 | 0 | 1129.269 | 1129.269
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT FOR M. SOCCER V. GONZAGA - 9/8 | 162 | CLOSED | 0 | 0 | 1894.974 | 1894.974
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT M. SOCCER V. SACRAMENTO ST. - 11/2 | 162 | CLOSED | 0 | 0 | 1914.828 | 1914.828
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT M. SOCCER V. SAN JOSE STATE - 9/15 | 162 | CLOSED | 0 | 0 | 1147.635 | 1147.635
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT M. SOCCER V. UC DAVIS - 10/22 | 162 | CLOSED | 0 | 0 | 1422.978 | 1422.978
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT M. SOCCER V. UCSB - 10/25 | 162 | CLOSED | 0 | 0 | 3860.598 | 3860.598
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT M. SOCCER V. UCSB - 10/25 | 162 | CLOSED | 0 | 0 | 337.608 | 337.608
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: FALL M. SOCCER PRACTICE LINING - 2013 | 162 | CLOSED | 0 | 0 | 642.906 | 642.906
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. CSU FULLERTON - 10/6 | 162 | CLOSED | 0 | 0 | 245.106 | 245.106
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. GONZAGA - 9/9 | 162 | CLOSED | 0 | 0 | 245.106 | 245.106
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. PENN - 9/13 | 162 | CLOSED | 0 | 0 | 468.9 | 468.9
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. SACRAMENTO ST. - 11/2 | 162 | CLOSED | 0 | 0 | 468.9 | 468.9
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. SAN FRANCISCO - 9/20 | 162 | CLOSED | 0 | 0 | 368.244 | 368.244
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. SAN JOSE ST. - 9/15 (N/L) | 162 | CLOSED | 0 | 0 | 0 | 0
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. UC DAVIS - 10/22 | 162 | CLOSED | 0 | 0 | 449.418 | 449.418
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. UC RIVERSIDE - 10/4 | 162 | CLOSED | 0 | 0 | 97.41 | 97.41
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. UCSB - 10/25 | 162 | CLOSED | 0 | 0 | 1105.1839 | 1105.1839
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: M. SOCCER V. YALE - 9/22 | 162 | CLOSED | 0 | 0 | 116.892 | 116.892
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT M. SOCCER V. CSU FULLERTON - 10/6 | 162 | CLOSED | 0 | 0 | 1192.95 | 1192.95
PJ0004620 | 13/14 SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT M. SOCCER V. UCSB - 10/25 | 162 | CLOSED | 0 | 0 | 428.592 | 428.592
PJ0004620 Total | [7 empty] | 0 | 0 | 25976.6243 | 25976.6243
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: PROJECT CONTINGENCY | 162 | CLOSED | 0 | 0 | 0 | 0
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT W. SOCCER V. CSU LONG BEACH-10/4 | 162 | CLOSED | 0 | 0 | 1395.87 | 1395.87
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT W. SOCCER V. UC IRVINE - 10/6 | 162 | CLOSED | 0 | 0 | 857.862 | 857.862
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPROT FOR W. SOCCER V. SAN JOSE STATE - 9/6 | 162 | CLOSED | 0 | 0 | 1079.337 | 1079.337
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: W. SOCCER V. CSU FULLERTON - 10/18 | 162 | CLOSED | 0 | 0 | 1317.702 | 1317.702
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: W. SOCCER V. UC RIVERSIDE - 10/20 | 162 | CLOSED | 0 | 0 | 1108.566 | 1108.566
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOR W. SOCCER EXHIBITION GAME - 8/12 | 162 | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOR W. SOCCER V. SAN JOSE STATE - 9/6 | 162 | CLOSED | 0 | 0 | 646.068 | 646.068
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOR WOMEN'S SOCCER ALUMNI GAME - 10/19 | 162 | CLOSED | 0 | 0 | 52.3937 | 52.3937
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT W. SOCCER V. CSU BAKERSFIELD - 4/26 | 162 | CLOSED | 0 | 0 | 194.82 | 194.82
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT W. SOCCER V. FRESNO CITY - 4/12 | 162 | CLOSED | 0 | 0 | 208.953 | 208.953
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT W. SOCCER V. LOYOLA - 8/23 | 162 | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT W. SOCCER V. SAC STATE - 8/30 | 162 | CLOSED | 0 | 0 | 167.178 | 167.178
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT W. SOCCER V. TBD - 5/10 | 162 | CLOSED | 0 | 0 | 194.82 | 194.82
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: W. SOCCER PRACTICE FIELD LINING - FALL 2013 | 162 | CLOSED | 0 | 0 | 662.388 | 662.388
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: W. SOCCER V. CSU FULLERTON - 10/18 | 162 | CLOSED | 0 | 0 | 299.6143 | 299.6143
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: W. SOCCER V. LONG BEACH ST. - 10/4 | 061 | CLOSED | 0 | 0 | 254.598 | 254.598
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: W. SOCCER V. UC IRVINE - 10/6 | 162 | CLOSED | 0 | 0 | 97.41 | 97.41
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: W. SOCCER V. UC RIVERWSIDE - 10/20 | 162 | CLOSED | 0 | 0 | 157.188 | 157.188
PJ0004619 | 13/14 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: WOMEN'S SOCCER V. PEPPERDINE - 8/17 | 162 | CLOSED | 0 | 0 | 308.976 | 308.976
PJ0004619 Total | [7 empty] | 0 | 0 | 9315.456 | 9315.456
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | AD: BKM FURNITURE | 002 | CLOSED | 3383.1153 | 0 | 3383.1153 | 3383.1153
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | AD: FLOOR CONNECTION | 002 | CLOSED | 11731.6619 | 0 | 11731.6619 | 11731.6619
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | CA: CIE RENOVATION SUPPORT | 002 | CLOSED | 6388.0673 | 0 | 4796.322 | 4796.322
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 2245.08 | 0 | 0 | 0
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | EL: PROJECT SUPPORT FOR CIE RENOVATION | 002 | CLOSED | 2250.0072 | 0 | 3414.084 | 3414.084
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | IN: RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | 002 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004618 | RENOVATE CENTER FOR INNOVATION & ENTREPRENEURSHIP | HICKS, MICHAEL | CLOSED | 2013-08-07 | MO:PROJECT SUPPORT FOR CIE RENOVATION | 002 | CLOSED | 194.4 | 0 | 169.008 | 169.008
PJ0004618 Total | [7 empty] | 26320.4437 | 0 | 23558.2472 | 23558.2472
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: CCI PORTABLE RESTROOM RENTAL FOR 10/12 | 061 | CLOSED | 0 | 0 | 1088.511 | 1088.511
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: CCI PORTABLE RESTROOMS RENTAL FOR 10/26 FOOTBALL | 061 | CLOSED | 0 | 0 | 1195.511 | 1195.511
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: CCI RENTAL FOR FOOTBALL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 919.451 | 919.451
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: CCI RENTAL FOR FOOTBALL V.SACRAMENTO ST. - 11/9 | 061 | CLOSED | 0 | 0 | 821.011 | 821.011
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: CENTRAL COAST IND. RENTAL - 10/5 | 061 | CLOSED | 0 | 0 | 675.7371 | 675.7371
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: CENTRAL COAST INDUSTRIES RENTAL - 8/30 | 061 | CLOSED | 0 | 0 | 247.2877 | 247.2877
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: MATRIX MOBILE MEDIA RENTAL - FOOTBALL V. E. WASHINGTON-11/16 | 061 | CLOSED | 0 | 0 | 192.6 | 192.6
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: OTIS ELEVATOR STANDBY FOR FOOTBALL GAME-11/16 | 061 | CLOSED | 0 | 0 | 2364.6679 | 2364.6679
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: OTIS ELEVATOR STANDBY FOR FOOTBALL V. N. ARIZONA ST.-10/26 | 061 | CLOSED | 0 | 0 | 2101.9294 | 2101.9294
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: OTIS ELEVATOR STANDBY FOR FOOTBALL V. WEBER ST.-10/12 | 061 | CLOSED | 0 | 0 | 2364.6679 | 2364.6679
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | AD: OTIS STANDBY ELEVATOR SUPPORT FOR FOOTBALL-10/5 | 061 | CLOSED | 0 | 0 | 2364.6679 | 2364.6679
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT FOOTBALL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 250.992 | 250.992
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT FOOTBALL V. N. ARIZONA - 10/26 | 061 | CLOSED | 0 | 0 | 250.992 | 250.992
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT FOOTBALL V. SACRAMENTO ST. - 11/9 | 061 | CLOSED | 0 | 0 | 260.58 | 260.58
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT FOOTBALL V. WEBER ST. - 10/12 | 061 | CLOSED | 0 | 0 | 316.707 | 316.707
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT FOR FOOTBALL V. SAN DIEGO - 8/31 | 061 | CLOSED | 0 | 0 | 507.918 | 507.918
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA: SUPPORT FOR FOOTBALL V. YALE-10/5 | 061 | CLOSED | 0 | 0 | 896.274 | 896.274
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CA; PLACE STANCHIONS FOR 2013 FALL FOOTBALL - 8/30 | 061 | CLOSED | 451.104 | 0 | 225.552 | 225.552
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: SUPPORT FOOTBALL V WEBER ST. - 10/12 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CP: SUPPORT FOOTBALL V. YALE - 10/5 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CPE: SUPPORT FOOTBALL V N. ARIZONA - 10/26 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CPE: SUPPORT FOOTBALL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CPE: SUPPORT FOOTBALL V. SACRAMENTO ST. - 11/9 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CPE: SUPPORT FOR FOOTBALL V. SAN DIEGO - 8/31 | 061 | CLOSED | 0 | 0 | 416.88 | 416.88
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: PREPARATION OF SPANOS STADIUM FOR FALL SPORTS - 8/24 | 061 | CLOSED | 0 | 0 | 4339.74 | 4339.74
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT FOOTBALL V. N. ARIZONE - 10/26 | 061 | CLOSED | 0 | 0 | 5029.452 | 5029.452
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT FOOTBALL V. SACRAMENTO ST. - 11/9 | 061 | CLOSED | 0 | 0 | 8426.895 | 8426.895
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT FOOTBALL V. YALE - 10/5 | 061 | CLOSED | 0 | 0 | 3976.236 | 3976.236
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT FOR FOOTBALL GREEN AND GOLD SCRIMMAGE - 5/2 | 061 | CLOSED | 0 | 0 | 459.978 | 459.978
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU: SUPPORT FOR FOOTBALL V. WEBER ST. - 10/12 | 061 | CLOSED | 0 | 0 | 4204.08 | 4204.08
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU:SUPPORT FOR FOOTBALL V UCSD - 8/31 | 061 | CLOSED | 0 | 0 | 3610.152 | 3610.152
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | CU:SUPPORT FOR FOOTBALL V. EASTERN WASHINGTON-11/16 | 061 | CLOSED | 0 | 0 | 4288.272 | 4288.272
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: INSTALL SPIDER BOX AT BUSINESS BLDG BEFORE 8/31 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT FOOTBALL V. N. ARIZONA - 10/26 | 061 | CLOSED | 0 | 0 | 562.68 | 562.68
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT FOOTBALL V. WEBER ST - 10/12 | 061 | CLOSED | 0 | 0 | 600.192 | 600.192
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT FOR FOOTBALL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 622.488 | 622.488
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT FOR FOOTBALL V. SACRAMENTO ST.-11/9 | 061 | CLOSED | 0 | 0 | 901.3421 | 901.3421
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT FOR FOOTBALL V. SAN DIEGO - 8/31 | 061 | CLOSED | 0 | 0 | 2173.8966 | 2173.8966
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | EL: SUPPORT FOR FOOTBALL V. YALE - 10/5 AT 2:00PM | 061 | CLOSED | 0 | 0 | 779.616 | 779.616
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: FOOTBAL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 6251.622 | 6251.622
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: FOOTBALL PRACTICE FIELD LINING - FALL 2013 | 061 | CLOSED | 0 | 0 | 2016.387 | 2016.387
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: FOOTBALL V. SACRAMENTO ST. - 11/9 | 061 | CLOSED | 0 | 0 | 7348.038 | 7348.038
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: INSTALL HASHMARKS AT UPPER TURF FIELDS | 061 | CLOSED | 0 | 0 | 77.928 | 77.928
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOOTBALL SPRING GAME - 5/3 | 061 | CLOSED | 0 | 0 | 720.834 | 720.834
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOOTBALL V. N. ARIZONA - 10/26 | 061 | CLOSED | 0 | 0 | 11463.6684 | 11463.6684
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOOTBALL V. WEBER ST. - 10/12 | 061 | CLOSED | 0 | 0 | 6619.272 | 6619.272
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOR FOOTBALL V. SAN DIEGO ST - 8/31 | 061 | CLOSED | 0 | 0 | 6737.736 | 6737.736
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | LA: SUPPORT FOR FOOTBALL V. YALE - 10/5 | 061 | CLOSED | 0 | 0 | 10647.114 | 10647.114
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOOTBALL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 522.846 | 522.846
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOOTBALL V. N. ARIZONA - 10/26 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOOTBALL V. N. ARIZONE - 10/26 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOOTBALL V. SACRAMENTO ST. - 11/9 | 061 | CLOSED | 0 | 0 | 482.67 | 482.67
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOOTBALL V. WEBER ST. - 10/12 | 061 | CLOSED | 0 | 0 | 486.516 | 486.516
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOR FOOTBALL V. SAN DIEGO - 8/31 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOR FOOTBALL V. YALE - 10/5 | 061 | CLOSED | 0 | 0 | 436.692 | 436.692
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | PL: SUPPORT FOR GREEN & GOLD FOOTBALL GAME ON SAT MAY 3 | 061 | CLOSED | 0 | 0 | 326.46 | 326.46
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | RE: SUPPORT FOR FOOTBALL V. E. WASHINGTON - 11/16 | 061 | CLOSED | 0 | 0 | 376.032 | 376.032
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | RE: SUPPORT FOR FOOTBALL V. N. ARIZONA - 10/26 | 061 | CLOSED | 0 | 0 | 376.032 | 376.032
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | RE: SUPPORT FOR FOOTBALL V. SAC. STATE - 11/9 | 061 | CLOSED | 0 | 0 | 376.032 | 376.032
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | RE: SUPPORT FOR FOOTBALL V. UNIV. SAN DIEGO - 8/31 | 061 | CLOSED | 0 | 0 | 329.028 | 329.028
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | RE: SUPPORT FOR FOOTBALL V. WEBER ST. - 10/12 | 061 | CLOSED | 0 | 0 | 329.028 | 329.028
PJ0004617 | 13/14 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2013-08-08 | RE: SUPPORT FOR FOOTBALL V. YALE - 10/5 | 061 | CLOSED | 0 | 0 | 305.526 | 305.526
PJ0004617 Total | [7 empty] | 451.104 | 0 | 115984.698 | 115984.698
PJ0004616 | SR 13/14: LEED EB - CAMPUS-WIDE | ELLIOT, DENNIS K | PUNCH_LIST | 2013-08-06 | AD: ENERNOC | GENERAL | CLOSED | 4494 | 0 | 4494 | 4494
PJ0004616 | SR 13/14: LEED EB - CAMPUS-WIDE | ELLIOT, DENNIS K | PUNCH_LIST | 2013-08-06 | AD: GREEN BUILDING CERTIFICATION INSTITUTE | GENERAL | OPEN | 10304.1 | 0 | 9630 | 9630
PJ0004616 | SR 13/14: LEED EB - CAMPUS-WIDE | ELLIOT, DENNIS K | PUNCH_LIST | 2013-08-06 | AD: MODE ASSOCIATES | GENERAL | OPEN | 64200 | 0 | 70620 | 70620
PJ0004616 | SR 13/14: LEED EB - CAMPUS-WIDE | ELLIOT, DENNIS K | PUNCH_LIST | 2013-08-06 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 7899.81 | 0 | 0 | 0
PJ0004616 | SR 13/14: LEED EB - CAMPUS-WIDE | ELLIOT, DENNIS K | PUNCH_LIST | 2013-08-06 | SM: SR 13/14: LEED EB - CAMPUS-WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0004616 Total | [7 empty] | 86897.91 | 0 | 84744 | 84744
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | AD: APC CONTRACTORS | RESIDENCE | CLOSED | 2664.3 | 0 | 2664.3 | 2664.3
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | CA: HOUSING HYDRATION STATION PROJECT SUPPORT | RESIDENCE | CLOSED | 6426.88 | 0 | 12045.876 | 12045.876
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 887.34 | 0 | 0 | 0
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | EL: HOUSING HYDRATION STATION PROJECT SUPPORT | RESIDENCE | CLOSED | 3420.6862 | 0 | 2490.468 | 2490.468
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | IN: INSTALL HYDRATION STATIONS AT RESIDENCE HALLS | RESIDENCE | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | PA: PAINT WALLS FOR HYDRATION STATIONS | RESIDENCE | CLOSED | 2623.952 | 0 | 118.728 | 118.728
PJ0004615 | INSTALL HYDRATION STATIONS AT S. MTN. RESIDENCE HALLS | GONZALES, ALBERT M. | CLOSED | 2013-08-05 | PL: HYDRATION STATIONS FOR HOUSING | RESIDENCE | CLOSED | 22980.1925 | 0 | 17085.072 | 17085.072
PJ0004615 Total | [7 empty] | 39067.4066 | 0 | 34500.528 | 34500.528
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | AD: COASTAL DEMO | 026 | CLOSED | 428 | 0 | 583.15 | 583.15
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | AD: ROSSI & CARR ELECTRICAL | 026 | CLOSED | 4815 | 0 | 4119.5 | 4119.5
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | CA:CONVERT 6 EXISTING CHALKBOARDS TO WHITEBOARDS | 026 | CLOSED | 4844.2703 | 0 | 2930.43 | 2930.43
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 2325.71 | 0 | 0 | 0
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | EL:ROUTE POWER FROM ROOM 218 TO NEW PANEL IN STORAGE OF 304 | 026 | CLOSED | 8642.0465 | 0 | 5429.748 | 5429.748
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | IN: ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | 026 | CLOSED | 256.224 | 0 | 192.168 | 192.168
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | LO: PROVIDE NEW LEVER HARDWARE AT CORIDOR SIDE OF 2 DOORS | 026 | CLOSED | 1132.176 | 0 | 29.022 | 29.022
PJ0004614 | ELECTRICAL FOR ROOM CONVERSION - BLD 26 RM 304 | MCNALLY, CURTIS | CLOSED | 2013-06-03 | PA:STRIP PAINT IN SPECIFIED LOCATIONS - PAINT ROOM | 026 | CLOSED | 2185.6124 | 0 | 2045.16 | 2045.16
PJ0004614 Total | [7 empty] | 24629.0392 | 0 | 15329.178 | 15329.178
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | CA:INSTALL NEW DOORS IN ROOM 7A AND 7B | 007 | CLOSED | 6807.9767 | 0 | 6490.344 | 6490.344
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 1045.85 | 0 | 0 | 0
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 007 | CLOSED | 0 | 0 | 37.2 | 37.2
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | EL:7A AND 7B - RELOCATE POWER OUTLETS AND LIGHT SWITCHES | 007 | CLOSED | 840.0024 | 0 | 1326.024 | 1326.024
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | IN: DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | 007 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | LO:PROVIDE/INSTALL (2) LOCKSETS AND DOOR CLOSERS | 007 | CLOSED | 1072.176 | 0 | 191.478 | 191.478
PJ0004613 | DOOR TO HALLWAY WITH RESTRICTED ACCESS - BLD 07 RM 07 | MCNALLY, CURTIS | CLOSED | 2013-07-31 | PA:TAPE TEXTURE AND PAINT | 007 | CLOSED | 1537.2728 | 0 | 2347.806 | 2347.806
PJ0004613 Total | [7 empty] | 11431.3899 | 0 | 10520.964 | 10520.964
PJ0004609 | PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-08-02 | AD: FLOOR CONNECTION | 006 | CLOSED | 0 | 0 | 2675 | 2675
PJ0004609 | PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-08-02 | CA: PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 | 006 | CLOSED | 0 | 0 | 635.69 | 635.69
PJ0004609 | PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-08-02 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004609 | PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-08-02 | CU: PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 (N/L) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004609 | PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-08-02 | LO: PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 | 006 | CLOSED | 0 | 0 | 24.185 | 24.185
PJ0004609 | PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-08-02 | PL: PAC MAINTENANCE WALK-THROUGH - TUE JULY 9, 2013 | 006 | CLOSED | 0 | 0 | 54.41 | 54.41
PJ0004609 Total | [7 empty] | 0 | 0 | 3389.285 | 3389.285
PJ0004608 | CONNECT ANALYTICAL EQUIPMENT TO WATER SUPPLY: BLDG 11-RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-29 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 421.58 | 0 | 0 | 0
PJ0004608 | CONNECT ANALYTICAL EQUIPMENT TO WATER SUPPLY: BLDG 11-RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-29 | IN: CONNECT ELECTRICAL & VENT TO ASHING FURNACE - BLD 011 RM 307 | 011 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004608 | CONNECT ANALYTICAL EQUIPMENT TO WATER SUPPLY: BLDG 11-RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-29 | PL: CONNECT WATER & DRAIN TO EQUIPMENT | 011 | CLOSED | 4087.8986 | 0 | 4596.0565 | 4596.0565
PJ0004608 Total | [7 empty] | 4637.5906 | 0 | 4628.0845 | 4628.0845
PJ0004607 | PULL-UP BARS, DIP BARS, & HORIZONTAL LADDER BARS NEAR TRACK | BRENNAN, MICHAEL | CLOSED | 2013-07-31 | CA: INSTALL DONATION PLAQUE - SPORTS FIELD EXERCISE EQUIP | F-02 | CLOSED | 55.62 | 0 | 139.05 | 139.05
PJ0004607 | PULL-UP BARS, DIP BARS, & HORIZONTAL LADDER BARS NEAR TRACK | BRENNAN, MICHAEL | CLOSED | 2013-07-31 | CP: PROJECT CONTINGENCY | F-02 | CLOSED | 438.47 | 0 | 0 | 0
PJ0004607 | PULL-UP BARS, DIP BARS, & HORIZONTAL LADDER BARS NEAR TRACK | BRENNAN, MICHAEL | CLOSED | 2013-07-31 | EL: mark utilties sports complex, rotc | F-02 | CLOSED | 64.428 | 0 | 64.428 | 64.428
PJ0004607 | PULL-UP BARS, DIP BARS, & HORIZONTAL LADDER BARS NEAR TRACK | BRENNAN, MICHAEL | CLOSED | 2013-07-31 | IN: PULL-UP BARS, DIP BARS, & HORIZONTAL LADDER BARS NEAR TRACK | F-02 | CLOSED | 64.056 | 0 | 208.638 | 208.638
PJ0004607 | PULL-UP BARS, DIP BARS, & HORIZONTAL LADDER BARS NEAR TRACK | BRENNAN, MICHAEL | CLOSED | 2013-07-31 | LA:mark utilities & relocate irrigation line | F-02 | CLOSED | 1671.8814 | 0 | 285.552 | 285.552
PJ0004607 Total | [7 empty] | 2294.4554 | 0 | 697.668 | 697.668
PJ0004604 | TI: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 | MOLLAN, CHERYL L. | CLOSED | 2013-07-30 | AD: ENGLEKIRK AND SABOL | 208 | CLOSED | 500 | 0 | 500 | 500
PJ0004604 | TI: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 | MOLLAN, CHERYL L. | CLOSED | 2013-07-30 | AD: ON TRAC SHIPPING | 208 | CLOSED | 0 | 0 | 16.32 | 16.32
PJ0004604 | TI: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 | MOLLAN, CHERYL L. | CLOSED | 2013-07-30 | CP: PROJECT CONTINGENCY | 208 | CLOSED | 148.68 | 0 | 0 | 0
PJ0004604 | TI: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 | MOLLAN, CHERYL L. | CLOSED | 2013-07-30 | IN: CAL POLY BUILDING PERMIT FEES | 208 | CLOSED | 123.85 | 0 | 123.85 | 123.85
PJ0004604 | TI: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 | MOLLAN, CHERYL L. | CLOSED | 2013-07-30 | IN: CAL POLY PLAN REVEIW FEES | 208 | CLOSED | 600 | 0 | 600 | 600
PJ0004604 | TI: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 | MOLLAN, CHERYL L. | CLOSED | 2013-07-30 | IN: MODIFY T-MOBILE ANTENNA FACILITIES - RADIO HILL 208 (MAINT) | 208 | CLOSED | 106.76 | 0 | 80.07 | 80.07
PJ0004604 Total | [7 empty] | 1479.29 | 0 | 1320.24 | 1320.24
PJ0004603 | SR 13/14: REPLACE CARPET - ATL 07 RMS 1 & 2 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-26 | AD: FLOOR CONNECTION | 007 | CLOSED | 18906.74 | 0 | 18874.74 | 18874.74
PJ0004603 | SR 13/14: REPLACE CARPET - ATL 07 RMS 1 & 2 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-26 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 0 | 0 | 0 | 0
PJ0004603 | SR 13/14: REPLACE CARPET - ATL 07 RMS 1 & 2 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-26 | EL: REMOVE/REPLACE COVER PLATES FOR RE-CARPET | 007 | CLOSED | 564.0472 | 0 | 421.35 | 421.35
PJ0004603 | SR 13/14: REPLACE CARPET - ATL 07 RMS 1 & 2 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-26 | MO: MOVE STAGE COMPONENTS | 007 | CLOSED | 270 | 0 | 75.45 | 75.45
PJ0004603 Total | [7 empty] | 19740.7872 | 0 | 19371.54 | 19371.54
PJ0004602 | RECONFIGURE BOOKCASES ON 3RD FLOOR - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-07-12 | CA: REMOVE ENDCAPS FROM BOOK SHELVES | 035 | CLOSED | 1566.1235 | 0 | 1663.884 | 1663.884
PJ0004602 | RECONFIGURE BOOKCASES ON 3RD FLOOR - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-07-12 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 163.01 | 0 | 0 | 0
PJ0004602 | RECONFIGURE BOOKCASES ON 3RD FLOOR - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-07-12 | IN: RECONFIGURE BOOKCASES ON 3RD FLOOR - BLD 35 | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004602 Total | [7 empty] | 1793.1895 | 0 | 1727.94 | 1727.94
PJ0004600 | TI: MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-07-25 | AD: CAL POLY FACILITES BUILDING PERMIT FEES | 208 | CLOSED | 600 | 0 | 600 | 600
PJ0004600 | TI: MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-07-25 | AD: CAL POLY FACILITIES PLAN REVIEW FEES | 208 | CLOSED | 534 | 0 | 534 | 534
PJ0004600 | TI: MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-07-25 | AD: ENGLEKIRK AND SABOL | 208 | CLOSED | 500 | 0 | 500 | 500
PJ0004600 | TI: MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-07-25 | AD: PROJECT COORDINATION FEE | 208 | CLOSED | 428 | 0 | 428 | 428
PJ0004600 | TI: MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-07-25 | CP: PROJECT CONTINGENCY | 208 | CLOSED | 381.41 | 0 | 0 | 0
PJ0004600 | TI: MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-07-25 | IN: (MAINT) MODIFICATION TO THE AT&T CELL SITE - RADIO HILL | 208 | CLOSED | 0 | 0 | 160.14 | 160.14
PJ0004600 Total | [7 empty] | 2443.41 | 0 | 2222.14 | 2222.14
PJ0004598 | REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | MOLLAN, CHERYL L. | CLOSED | 2013-07-22 | CA:SUPPLY AND INSTALL NEW FIRE RATED DOOR TO MATCH EXISTING | 133 | CLOSED | 1352.7798 | 0 | 1182.762 | 1182.762
PJ0004598 | REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | MOLLAN, CHERYL L. | CLOSED | 2013-07-22 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 233.69 | 0 | 0 | 0
PJ0004598 | REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | MOLLAN, CHERYL L. | CLOSED | 2013-07-22 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 133 | CLOSED | 0 | 0 | 14.4 | 14.4
PJ0004598 | REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | MOLLAN, CHERYL L. | CLOSED | 2013-07-22 | IN: REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | 133 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004598 | REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | MOLLAN, CHERYL L. | CLOSED | 2013-07-22 | LO:INSTALL LOCK AND CLOSER FOR FIRE DOOR AT BLD 133 | 133 | CLOSED | 232.176 | 0 | 770.64 | 770.64
PJ0004598 | REPLACE FIRE DOOR CUSTODIAL.ADULT RESTROOM - BLD 133 RM 111 | MOLLAN, CHERYL L. | CLOSED | 2013-07-22 | PA:VARNISH DOOR AT 133, ROOM 111 (NO LABOR) | 133 | CLOSED | 594.912 | 0 | 0 | 0
PJ0004598 Total | [7 empty] | 2477.6138 | 0 | 2031.858 | 2031.858
PJ0004596 | REMODEL TEACHING LAB - BLD 33 RM 356 | MCNALLY, CURTIS | CLOSED | 2013-07-17 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 819.73 | 0 | 0 | 0
PJ0004596 | REMODEL TEACHING LAB - BLD 33 RM 356 | MCNALLY, CURTIS | CLOSED | 2013-07-17 | EL: DISCONNECT POWER TO ALL TABLES AND REMOVE POWER FROM WALL | 033 | CLOSED | 3000.6862 | 0 | 969.816 | 969.816
PJ0004596 | REMODEL TEACHING LAB - BLD 33 RM 356 | MCNALLY, CURTIS | CLOSED | 2013-07-17 | IN: REMODEL TEACHING LAB - BLD 33 RM 356 | 033 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004596 | REMODEL TEACHING LAB - BLD 33 RM 356 | MCNALLY, CURTIS | CLOSED | 2013-07-17 | PL: DISCONNECT PLUMBING FROM TABLES - RECONNECT TO NEW TABLES | 033 | CLOSED | 3086.1469 | 0 | 7271.976 | 7271.976
PJ0004596 Total | [7 empty] | 7034.6751 | 0 | 8305.848 | 8305.848
PJ0004595 | ENCLOSE THE BREEZEWAY FOR STUDY AREA - BLDG 25 | NEEL, JOEL | CLOSED | 2013-07-17 | AD: OMNI DESIGN | GENERAL | CLOSED | 13118.2 | 0 | 3616.6 | 3616.6
PJ0004595 | ENCLOSE THE BREEZEWAY FOR STUDY AREA - BLDG 25 | NEEL, JOEL | CLOSED | 2013-07-17 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1343.85 | 0 | 0 | 0
PJ0004595 | ENCLOSE THE BREEZEWAY FOR STUDY AREA - BLDG 25 | NEEL, JOEL | CLOSED | 2013-07-17 | IN: ENCLOSE THE BREEZEWAY FOR STUDY AREA - BLDG 25 | GENERAL | CLOSED | 320.28 | 0 | 64.056 | 64.056
PJ0004595 Total | [7 empty] | 14782.33 | 0 | 3680.656 | 3680.656
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | AD: HPS MECHANICAL | 041B | CLOSED | 5209.7658 | 0 | 5209.7658 | 5209.7658
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | AD: SIERRA PACIFIC AUTOMATION, INC. | 041B | CLOSED | 3424 | 0 | 3257.9788 | 3257.9788
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | CA: PATCH WALL AND INFILL WALL AT OLD EQUIPMENT LOCATION | 041B | CLOSED | 1304.2703 | 0 | 780.324 | 780.324
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | CP: PROJECT CONTINGENCY | 041B | CLOSED | 1936.28 | 0 | 0 | 0
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | EL: INSTALL AND CONNECT DEPARTMENT SUPPLIED EQUIPMENT | 041B | CLOSED | 10202.0465 | 0 | 9514.152 | 9514.152
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | IN: REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | 041B | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004590 | REPLACE WIND TUNNEL VFD - BLD 41B RM 139 | MCNALLY, CURTIS | CLOSED | 2013-07-15 | PA:TAPE TEXTURE AND PAINT WALL PATCH IN WIND TUNNEL CONTROL ROOM | 041B | CLOSED | 504.1698 | 0 | 385.866 | 385.866
PJ0004590 Total | [7 empty] | 22708.6444 | 0 | 19276.1986 | 19276.1986
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | AD: FLOOR CONNECTION | RESIDENCE | CLOSED | 0 | 0 | 2792.7 | 2792.7
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | AD: PASO ROBLES GLASS | RESIDENCE | CLOSED | 0 | 0 | 8365.0353 | 8365.0353
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | CA: REMOVE CABINETS FROM CUSTODIAL BREAK ROOMS - SO. MTN. HALLS | RESIDENCE | CLOSED | 0 | 0 | 4372.542 | 4372.542
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | RESIDENCE | CLOSED | 0 | 0 | 19.2 | 19.2
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | EL: REMOVE OUTLETS FROM CABINETRY - BREAK RMS - SO. MTN. HALLS | RESIDENCE | CLOSED | 0 | 0 | 4506.2849 | 4506.2849
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | ES:MODIFY CONTROL SWITCH TO HVAC UNITS IN 6 RMS AT RED BRICKS | RESIDENCE | CLOSED | 0 | 0 | 617.3644 | 617.3644
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | IN: CONVERT CUSTODIAL BREAK ROOMS TO RA ROOMS - SO. MTN. HALLS | RESIDENCE | CLOSED | 0 | 0 | 544.476 | 544.476
PJ0004588 | CONVERT CUSTODIAL BREAK RMS TO RA RMS - SO. MTN. HALLS (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-07-15 | PA: PAINTING IN CUSTODIAL BREAK ROOMS - SO. MTN. HALLS | RESIDENCE | CLOSED | 0 | 0 | 3854.724 | 3854.724
PJ0004588 Total | [7 empty] | 0 | 0 | 25072.3265 | 25072.3265
PJ0004587 | REMODEL TEACHING LAB - BLD 02 RM 127 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-15 | CA:REMOVE COUNTER AND INSTALL HANGING HOOKS | 002 | CLOSED | 2087.0501 | 0 | 1069.74 | 1069.74
PJ0004587 | REMODEL TEACHING LAB - BLD 02 RM 127 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-15 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 265.19 | 0 | 0 | 0
PJ0004587 | REMODEL TEACHING LAB - BLD 02 RM 127 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-07-15 | PA: REPAIR/PAINT WALL AND LEDGER RAIL | 002 | CLOSED | 564.912 | 0 | 178.092 | 178.092
PJ0004587 Total | [7 empty] | 2917.1521 | 0 | 1247.832 | 1247.832
PJ0004585 | FP 13/14: DESIGN FOR EH&S OFFICE EXPANSION - BLD 80 RM 106 | MCNALLY, CURTIS | CLOSED | 2013-07-11 | AD: ASAP REPROGRAPHICS | 080 | CLOSED | 178.85 | 0 | 349.92 | 349.92
PJ0004585 | FP 13/14: DESIGN FOR EH&S OFFICE EXPANSION - BLD 80 RM 106 | MCNALLY, CURTIS | CLOSED | 2013-07-11 | AD: ENGLEKIRK AND SABOL | 080 | CLOSED | 1416 | 0 | 1416 | 1416
PJ0004585 | FP 13/14: DESIGN FOR EH&S OFFICE EXPANSION - BLD 80 RM 106 | MCNALLY, CURTIS | CLOSED | 2013-07-11 | AD: OMNI DESIGN | 080 | CLOSED | 31610 | 0 | 31610 | 31610
PJ0004585 | FP 13/14: DESIGN FOR EH&S OFFICE EXPANSION - BLD 80 RM 106 | MCNALLY, CURTIS | CLOSED | 2013-07-11 | AD: STATE FIRE MARSHAL | 080 | CLOSED | 0 | 0 | 712.17 | 712.17
PJ0004585 | FP 13/14: DESIGN FOR EH&S OFFICE EXPANSION - BLD 80 RM 106 | MCNALLY, CURTIS | CLOSED | 2013-07-11 | CP: PROJECT CONTINGENCY | 080 | CLOSED | 149.6 | 0 | 0 | 0
PJ0004585 Total | [7 empty] | 33354.45 | 0 | 34088.09 | 34088.09
PJ0004584 | INSTALL BRICK PAVERS AT MUSTANG MEMORIAL PLAZA - BLD 61 | PINHEIRO, RICK | CLOSED | 2013-07-09 | CA: INSTALL 5 ENGRAVED PAVERS AT SPANOS MEMORIAL PLAZA - 061 | 061 | CLOSED | 1077.8532 | 0 | 1050.462 | 1050.462
PJ0004584 | INSTALL BRICK PAVERS AT MUSTANG MEMORIAL PLAZA - BLD 61 | PINHEIRO, RICK | CLOSED | 2013-07-09 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 107.8 | 0 | 0 | 0
PJ0004584 Total | [7 empty] | 1185.6532 | 0 | 1050.462 | 1050.462
PJ0004583 | SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | GRIFFIN, PATRICK E. | CLOSED | 2013-07-12 | AD: P.E.S. - POWER ENGINEERING SERVICES | 075 | CLOSED | 9500 | 0 | 11000 | 11000
PJ0004583 | SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | GRIFFIN, PATRICK E. | CLOSED | 2013-07-12 | AD: RK POWER ENGINEERING, INC. | 075 | CLOSED | 7000 | 0 | 11160 | 11160
PJ0004583 | SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | GRIFFIN, PATRICK E. | CLOSED | 2013-07-12 | AD: SD MEYERS | 075 | CLOSED | 59513 | 0 | 59512.5 | 59512.5
PJ0004583 | SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | GRIFFIN, PATRICK E. | CLOSED | 2013-07-12 | CP: PROJECT CONTINGENCY | 075 | CLOSED | 0 | 0 | 0 | 0
PJ0004583 | SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | GRIFFIN, PATRICK E. | CLOSED | 2013-07-12 | EL:SUPPORT WORK FOR SUBSTATION TRANSFORMER REPAIR | 075 | CLOSED | 10618.5718 | 0 | 4479.88 | 4479.88
PJ0004583 | SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | GRIFFIN, PATRICK E. | CLOSED | 2013-07-12 | IN: SR 13/14: REPAIR BANK 1 TRANSFORMER AT SUBSTATION - BLD 75 | 075 | CLOSED | 427.04 | 0 | 53.38 | 53.38
PJ0004583 Total | [7 empty] | 87058.6118 | 0 | 86205.76 | 86205.76
PJ0004582 | SR 13/14: SCOPE & ESTM / REGRADE & RESURFACE BACK LOADING AREA | LAMPMAN, GREG | CLOSED | 2013-07-11 | AD: JOC 13.029.039 MAINO | 070A | CLOSED | 30794.08 | 0 | 30794.08 | 30794.08
PJ0004582 | SR 13/14: SCOPE & ESTM / REGRADE & RESURFACE BACK LOADING AREA | LAMPMAN, GREG | CLOSED | 2013-07-11 | CP: PROJECT CONTINGENCY | 070A | CLOSED | 0 | 0 | 0 | 0
PJ0004582 | SR 13/14: SCOPE & ESTM / REGRADE & RESURFACE BACK LOADING AREA | LAMPMAN, GREG | CLOSED | 2013-07-11 | IN: SR 13/14: SCOPE & ESTM/REGRADE & RESURFACE BACK LOADING AREA | 070A | CLOSED | 213.52 | 0 | 240.21 | 240.21
PJ0004582 Total | [7 empty] | 31007.6 | 0 | 31034.29 | 31034.29
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SPANOS THEATRE SUPPORT "INFUSION" | 044 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SPANOS THEATRE SUPPORT GENDER ROLES MOVIE - 4/17 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT BLACK CAT CABARET - 5/10 | 044 | CLOSED | 0 | 0 | 58.098 | 58.098
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT CORE DANCE PEROFRMANCE - 10/5 | 044 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT DRAMA PERFORMANCE - 3/8 | 044 | CLOSED | 0 | 0 | 197.916 | 197.916
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR "AS YOU LIKE IT" - 3/1 | 044 | CLOSED | 0 | 0 | 36.492 | 36.492
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR BLACK COMMENCEMENT - 6/14 | 044 | CLOSED | 0 | 0 | 36.492 | 36.492
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR CORE PERFORMANCE - 3/21 & 3/22 | 044 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR CPA GUITARS EVENT-SPANOS THEATRE-4/12 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR DELLOS DANCE PERFORMANCES - 6/21- 6/22 | 044 | CLOSED | 0 | 0 | 130.98 | 130.98
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR INSTITUTE FOR BRAIN POTENTIAL-3/7 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR SOAR - SPANOS THEATRE | 044 | CLOSED | 0 | 0 | 229.572 | 229.572
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR SPANOS THEATER EVENT-SOLAS-4/4 | 044 | CLOSED | 0 | 0 | 74.328 | 74.328
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR SPANOS THEATRE-BALLET SLO 12/3-12/5 | 044 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT FOR THE CRUCIBLE- SPANOS THEATRE 4/6 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT SPANOS THEATRE EVENT - CPA LEIPZIG QUARTET: 4/14 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT SPANOS THEATRE EVENT CPA NW DANCE PROJ-4/19 | 044 | CLOSED | 0 | 0 | 56.082 | 56.082
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT SPANOS THEATRE EVENT WOMEN CLOTHED - 4/15 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPORT SPANOS THEATRE EVENT-JUNE 29 (STUDIO) | 044 | CLOSED | 0 | 0 | 85.752 | 85.752
PJ0004581 | 13/14: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS (NO EST) | POPHAM, DONALD J. | CLOSED | 2013-07-10 | CU: SUPPROT FOR SPANOS THEATRE EVENTS - 4/12-4/13 | 044 | CLOSED | 0 | 0 | 79.032 | 79.032
PJ0004581 Total | [7 empty] | 0 | 0 | 1624.266 | 1624.266
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 5877.51 | 0 | 5342.51 | 5342.51
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 4010.36 | 0 | 4010.36 | 4010.36
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | AD: WLH BUILDING CO. | 035 | CLOSED | 989.75 | 0 | 989.75 | 989.75
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | CA: LIBRARY ROOM 103/104 | 035 | CLOSED | 2077.2275 | 0 | 2120.6876 | 2120.6876
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1792.93 | 0 | 0 | 0
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | EH&S: LAB CHARGES PROCESSED THROUGH UTILITIES ACCOUNT(MAT, ONLY) | 035 | CLOSED | 12 | 0 | 8.4 | 8.4
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | EL: RECONFIGURATION OF ROOM 103/104 | 035 | CLOSED | 7308.4562 | 0 | 8546.352 | 8546.352
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | IN: LIBRARY REMODEL 1ST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | 035 | CLOSED | 171.0295 | 0 | 160.14 | 160.14
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | PA: LIBRARY RM 103/104 | 035 | CLOSED | 589.5692 | 0 | 1365.372 | 1365.372
PJ0004580 | LIBRARY REMODEL FIRST FLOOR STAFF AREA 2 - BLD 35-103/104/104B | GONZALES, ALBERT M. | CLOSED | 2013-07-09 | PL: DISCONNECT PLUMBING FOR REMOVAL OF WALL | 035 | CLOSED | 3249.1375 | 0 | 3385.116 | 3385.116
PJ0004580 Total | [7 empty] | 26077.97 | 0 | 25928.6876 | 25928.6876
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | AD: CAME SECURITY | 051 | CLOSED | 0 | 0 | 360 | 360
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | AD: COASTAL JANITORIAL | 051 | CLOSED | 0 | 0 | 225 | 225
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | AD: IDLERS | 051 | CLOSED | 0 | 0 | 475.65 | 475.65
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | AD: RAYNE WATER CONDITIONING | 051 | CLOSED | 0 | 0 | 491.4 | 491.4
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | CA: REPAIR FENCE AT SIDE YARD GATE - PRESIDENT'S RESIDENCE 051 | 051 | CLOSED | 0 | 0 | 1347.91 | 1347.91
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | EL: MAINTENANCE OF PRESIDENT'S HOUSE | 051 | CLOSED | 0 | 0 | 184.152 | 184.152
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | LA: DRAINAGE AROUND STORAGE SHED | 051 | CLOSED | 0 | 0 | 1217.625 | 1217.625
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | LO: MAINTENANCE OF PRES RESIDENCE | 051 | CLOSED | 0 | 0 | 96.74 | 96.74
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | PA: PRESIDENT'S RESIDENCE MAINTENANCE FOR FISCAL 13/14 | 051 | CLOSED | 0 | 0 | 197.88 | 197.88
PJ0004577 | 13/14: MAINTENANCE NEEDS - UNIVERSITY HOUSE - BLDG 051 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-07-02 | PL: 13/14 MAINTENANCE NEEDS AT UNIVERSITY HOUSE - BLDG 51 | 051 | CLOSED | 0 | 0 | 108.82 | 108.82
PJ0004577 Total | [7 empty] | 0 | 0 | 4705.177 | 4705.177
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | AD: COASTAL JANITORIAL | GENERAL | CLOSED | 0 | 0 | 405 | 405
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | AD: WINDOW CLEANING AT PRESIDENT'S HOUSE - 9/25 | GENERAL | CLOSED | 0 | 0 | 130 | 130
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: INSTALL ALL TENT SIDES AT PRESIDENT'S RESIDENCE - 12/11 | GENERAL | CLOSED | 0 | 0 | 587.375 | 587.375
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: INSTALL TENT WITH SOUTH AND WEST WALLS INSTALLED-2/13 | 051 | CLOSED | 0 | 0 | 540.385 | 540.385
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: PLEASE RETRACT TENT TOP AT PRESIDENT'S HOUSE - 051 | GENERAL | CLOSED | 0 | 0 | 281.94 | 281.94
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: REMOVE ALL TENT SIDES AT THE PRESIDENT'S RESIDENCE- 8/21 | GENERAL | CLOSED | 0 | 0 | 140.97 | 140.97
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: REMOVE CLOUDS AND RETRACT TENT TOP AT PRES. RESIDENCE. | GENERAL | CLOSED | 0 | 0 | 610.87 | 610.87
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: REMOVE THE TENT SIDES AT PRESIDENT'S HOUSE - 5/7 | GENERAL | CLOSED | 0 | 0 | 187.96 | 187.96
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: RETRACT CANOPY TOP - 7/8/2013 | 051 | CLOSED | 0 | 0 | 281.94 | 281.94
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: RETRACT TENT FOR RAIN OR AS BEST AS POSSIBLE | GENERAL | CLOSED | 0 | 0 | 375.92 | 375.92
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: SET UP TENT AT PRESIDENT'S HOUSE ON TUESDAY APRIL 22. | 051 | CLOSED | 0 | 0 | 649.93 | 649.93
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA: SETUP CANOPY, SOUTH, AND WEST WALLS - AUGUST 2 | GENERAL | CLOSED | 0 | 0 | 493.395 | 493.395
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CA:INSTALL TENT SIDES AT PRESIDENT'S RESIDENCE - 5/21(TENTATIVE) | GENERAL | CLOSED | 187.96 | 0 | 164.465 | 164.465
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CU: SUPPORT FOR PRESIDENT'S DINNER - 12/12 | GENERAL | CLOSED | 0 | 0 | 112.085 | 112.085
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CU: SUPPORT FOR PRESIDENT'S DINNER - 6/14 | GENERAL | CLOSED | 0 | 0 | 126.12 | 126.12
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | CU: SUPPORT PRES. HOSPITALITY TENT - BBALL REGIONALS | GENERAL | CLOSED | 0 | 0 | 273.69 | 273.69
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | EL: SUPPORT FOR HOSPITALITY TENT - BB REGIONALS | GENERAL | CLOSED | 0 | 0 | 250.08 | 250.08
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | LA: BLOW PATIO WEDNESDAY MORNING - APRIL 23 | 051 | CLOSED | 0 | 0 | 32.47 | 32.47
PJ0004576 | 13/14: EVENT SUPPORT FOR PRESIDENT¿S OFFICE (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-07-02 | LA: CLEAN UPPER AND LOWER PATIO FRIDAY MORNING - 8/2 | GENERAL | CLOSED | 0 | 0 | 32.47 | 32.47
PJ0004576 Total | [7 empty] | 187.96 | 0 | 5677.065 | 5677.065
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | AD: J.L. FASULO DRYWALL | 014 | CLOSED | 6313 | 0 | 6293.74 | 6293.74
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 3210 | 0 | 2648.25 | 2648.25
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | CA: COMPUTER SCIENCE 115 CONFERENCE ROOM | 014 | CLOSED | 496.6718 | 0 | 233.952 | 233.952
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 1223.22 | 0 | 0 | 0
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | EL: COMPUTER SCIENCE ROOM 115E CONFERENCE ROOM | 014 | CLOSED | 660.0024 | 0 | 292.092 | 292.092
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | ES: CONFERENCE ROOM FOR CIO | 014 | CLOSED | 705.6804 | 0 | 187.308 | 187.308
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | IN: INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | 014 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004573 | INSTALL CONFERENCE ROOM SOUND WALLS - 14-115E | GONZALES, ALBERT M. | CLOSED | 2013-06-26 | PA: CONFERENCE ROOM 14-115E | 014 | CLOSED | 1177.2728 | 0 | 356.184 | 356.184
PJ0004573 Total | [7 empty] | 13913.9595 | 0 | 10139.638 | 10139.638
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: BKM OFFICE ENVIRONMENTS | 001 | CLOSED | 3515.6669 | 0 | 3515.6669 | 3515.6669
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: COAST PAINTING (DOOR REFINISHING) | 001 | CLOSED | 5760.345 | 0 | 5760.345 | 5760.345
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: FLOOR CONNECTION | 001 | CLOSED | 3745 | 0 | 3656.3184 | 3656.3184
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: GLASS DESIGNS BY MELISSA (DESIGN AND ART WORK) | 001 | CLOSED | 7693.3 | 0 | 7975.352 | 7975.352
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: SAN LUIS GLASS | 001 | CLOSED | 4280 | 0 | 4535.3555 | 4535.3555
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: SANTA MARIA ACOUSTICAL | 001 | CLOSED | 5322.18 | 0 | 5322.18 | 5322.18
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: SOUTHPAW SIGN COMPANY | 001 | CLOSED | 607.653 | 0 | 607.653 | 607.653
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CA: GLASS WALL AND SIGNAGE | 001 | CLOSED | 9574.8566 | 0 | 12491.586 | 12491.586
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1976.71 | 0 | 0 | 0
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | EL: PROJECT SUPPORT | 001 | CLOSED | 5160.6814 | 0 | 5214.384 | 5214.384
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | IN: REMODEL PRESIDENT'S SUITE - ADMN 01 RM 407 | 001 | CLOSED | 256.224 | 0 | 160.14 | 160.14
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | MO: PRESIDENTS OFFICE FURNITURE STORAGE | 001 | CLOSED | 259.2 | 0 | 66.396 | 66.396
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PA:PAINT HALWAY AND DOOR FRAMES | 001 | CLOSED | 3891.2249 | 0 | 3147.132 | 3147.132
PJ0004570 | REMODEL PRESIDENT'S SUITE - ADMIN 01 RM 407 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PL: BOTTLE FILL STATION | 001 | CLOSED | 2653.3999 | 0 | 3766.53 | 3766.53
PJ0004570 Total | [7 empty] | 54696.4417 | 0 | 56219.0388 | 56219.0388
PJ0004569 | CONVERT SPACES TO COMPUTER LABS - BLD 192 RM 330 & 331 | MCNALLY, CURTIS | CLOSED | 2013-06-26 | AD: CAME SECURITY | 192 | CLOSED | 3932.25 | 0 | 3317 | 3317
PJ0004569 | CONVERT SPACES TO COMPUTER LABS - BLD 192 RM 330 & 331 | MCNALLY, CURTIS | CLOSED | 2013-06-26 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 1353.25 | 0 | 0 | 0
PJ0004569 | CONVERT SPACES TO COMPUTER LABS - BLD 192 RM 330 & 331 | MCNALLY, CURTIS | CLOSED | 2013-06-26 | EL:SUPPLY ADDITIONAL POWER TO ROOM 331 FOR COMPUTER LAB | 192 | CLOSED | 7921.3663 | 0 | 4260.468 | 4260.468
PJ0004569 | CONVERT SPACES TO COMPUTER LABS - BLD 192 RM 330 & 331 | MCNALLY, CURTIS | CLOSED | 2013-06-26 | IN: CONVERT SPACES TO COMPUTER LABS - BLD 192 RM 330 & 331 | 192 | CLOSED | 256.224 | 0 | 128.112 | 128.112
PJ0004569 | CONVERT SPACES TO COMPUTER LABS - BLD 192 RM 330 & 331 | MCNALLY, CURTIS | CLOSED | 2013-06-26 | LO: INSTALL ELECTRONIC DOOR LATCH | 192 | CLOSED | 918.2958 | 0 | 202.32 | 202.32
PJ0004569 Total | [7 empty] | 14381.3861 | 0 | 7907.9 | 7907.9
PJ0004567 | REPLACE OUTDATED FOUNTAIN WITH HYDRATION STATION -BLD 115(MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-06-25 | CA: CHASE HALL HYDRATION STATION (NO LABOR) | 115 | CLOSED | 0 | 0 | 0 | 0
PJ0004567 | REPLACE OUTDATED FOUNTAIN WITH HYDRATION STATION -BLD 115(MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-06-25 | CP: PROJECT CONTINGENCY | 115 | CLOSED | 0 | 0 | 0 | 0
PJ0004567 | REPLACE OUTDATED FOUNTAIN WITH HYDRATION STATION -BLD 115(MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-06-25 | EL: CHASE HALL HYDRATION STATION WIRING | 115 | CLOSED | 0 | 0 | 485.21 | 485.21
PJ0004567 | REPLACE OUTDATED FOUNTAIN WITH HYDRATION STATION -BLD 115(MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-06-25 | PA: CHASE HALL HYDRATION STATION SUPPORT | 115 | CLOSED | 0 | 0 | 865.725 | 865.725
PJ0004567 | REPLACE OUTDATED FOUNTAIN WITH HYDRATION STATION -BLD 115(MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-06-25 | PL:CHASE HALL REMOVE AND REPLACE NEW DRINKING FOUNTAIN | 115 | CLOSED | 0 | 0 | 1802.52 | 1802.52
PJ0004567 Total | [7 empty] | 0 | 0 | 3153.455 | 3153.455
PJ0004566 | MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | MOLLAN, CHERYL L. | CLOSED | 2013-06-21 | AD: BUILDING PERMIT FEES | P-R01 | CLOSED | 123.85 | 0 | 123.85 | 123.85
PJ0004566 | MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | MOLLAN, CHERYL L. | CLOSED | 2013-06-21 | AD: ENGLEKIRK AND SABOL | P-R01 | CLOSED | 500 | 0 | 500 | 500
PJ0004566 | MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | MOLLAN, CHERYL L. | CLOSED | 2013-06-21 | AD: ON TRAC SHIPPING | P-R01 | CLOSED | 0 | 0 | 16.32 | 16.32
PJ0004566 | MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | MOLLAN, CHERYL L. | CLOSED | 2013-06-21 | AD: PLAN REVIEW FEES | P-R01 | CLOSED | 600 | 0 | 600 | 600
PJ0004566 | MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | MOLLAN, CHERYL L. | CLOSED | 2013-06-21 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 148.68 | 0 | 0 | 0
PJ0004566 | MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | MOLLAN, CHERYL L. | CLOSED | 2013-06-21 | IN: MODIFY T-MOBILE ANTENNA FACILITIES - R-1 LOT KLAMATH RD | P-R01 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004566 Total | [7 empty] | 1500.642 | 0 | 1304.226 | 1304.226
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | AD: FLOOR CONNECTION | 035 | CLOSED | 4280 | 0 | 4226.5 | 4226.5
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | AD: JOC 13.028.046 MAINO | 035 | CLOSED | 12950.5845 | 0 | 12950.5845 | 12950.5845
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 770.4 | 0 | 770.4 | 770.4
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 950.66 | 0 | 0 | 0
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | EL: JULIANS COFFEE ELECTRICAL | 035 | CLOSED | 11312.3866 | 0 | 13322.508 | 13322.508
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | IN: BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | LO: PROJECT SUPPORT | 035 | CLOSED | 429.4381 | 0 | 116.088 | 116.088
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | MO: MOVE EXISTING EQUIPMENT INTO JULIAN'S SERVICE AREA | 035 | CLOSED | 129.6 | 0 | 18.108 | 18.108
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | PA: PAINTING FOR SOUND WALL AND BACK ROOM AT JULIAN'S | 035 | CLOSED | 2113.952 | 0 | 1048.578 | 1048.578
PJ0004565 | BUILD SOUND WALL AND BACK ROOM AT JULIAN'S - BLD 35 2ND FL | GONZALES, ALBERT M. | CLOSED | 2013-06-19 | PL: JULIAN'S PLUMBING | 035 | CLOSED | 7599.5468 | 0 | 4651.032 | 4651.032
PJ0004565 Total | [7 empty] | 40664.6801 | 0 | 37231.9105 | 37231.9105
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: BKM FURNITURE | 001 | CLOSED | 21400 | 0 | 16234.1363 | 16234.1363
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: CAME SECURITY | 001 | CLOSED | 2675 | 0 | 1043.25 | 1043.25
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: FLOOR CONNECTION | 001 | CLOSED | 10700 | 0 | 9885.6016 | 9885.6016
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: J.L. FASULO DRYWALL | 001 | CLOSED | 5132.79 | 0 | 5132.79 | 5132.79
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: PHIL'S CUSTOM WOODWORKING | 001 | CLOSED | 12048.2 | 0 | 12048.2 | 12048.2
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: SOUTHPAW SIGN COMPANY | 001 | CLOSED | 8663.8435 | 0 | 8663.8542 | 8663.8542
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: SPECTRUM COLOR IMAGES | 001 | CLOSED | 1819 | 0 | 1282.2666 | 1282.2666
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | ANTS:LOBBY PANIC BUTTON ADMIN 200 | 001 | CLOSED | 213.8136 | 0 | 12.012 | 12.012
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CA: ASSSIT WITH RECONFIGURATION OF 2ND FLOOR LOBBY | 001 | CLOSED | 4589.6848 | 0 | 4649.574 | 4649.574
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1046.06 | 0 | 0 | 0
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | EL: PROJECT SUPPORT FOR ADMIN LOBBY | 001 | CLOSED | 16057.644 | 0 | 6235.404 | 6235.404
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | IN: LOBBY REMODEL - ADMIN 01 RM 200 | 001 | CLOSED | 128.112 | 0 | 224.196 | 224.196
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | MO: ASSIST CARPENTERS WITH MOVING OF BRONZE ART | 001 | CLOSED | 259.2 | 0 | 48.288 | 48.288
PJ0004562 | LOBBY REMODEL - ADMIN 01 RM 200 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PA: PAINTING FOR LOBBY REMODEL - ADMIN 01 RM 200 | 001 | CLOSED | 2974.56 | 0 | 653.004 | 653.004
PJ0004562 Total | [7 empty] | 87707.9079 | 0 | 66112.5767 | 66112.5767
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: FLOOR CONNECTION | 035 | CLOSED | 1189.1124 | 0 | 1189.1124 | 1189.1124
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CA: PATCH HOLES | 035 | CLOSED | 842.7798 | 0 | 157.89 | 157.89
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 792.1 | 0 | 0 | 0
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | EL: INSTALL PLUGMOLD | 035 | CLOSED | 3000.6814 | 0 | 4519.788 | 4519.788
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | IN: REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | 035 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | LO: CHANGE CORE | 035 | CLOSED | 669.4381 | 0 | 58.044 | 58.044
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | MO: PROJECT SUPPORT | 035 | CLOSED | 64.8 | 0 | 12.072 | 12.072
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PA: PAINT ROOM 512 | 035 | CLOSED | 942.5094 | 0 | 1441.254 | 1441.254
PJ0004560 | REMOVE SINK, CARPET, PATCH, PAINT - BLD 35 RM 512 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PL: REMOVE SINK 35-512 | 035 | CLOSED | 1081.6482 | 0 | 690.27 | 690.27
PJ0004560 Total | [7 empty] | 8647.1253 | 0 | 8100.4584 | 8100.4584
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 1894.97 | 0 | 915.92 | 915.92
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CA: HYDRATION STATIONS AT LIBRARY | 035 | CLOSED | 3338.9033 | 0 | 2925.528 | 2925.528
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 994.27 | 0 | 0 | 0
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | EL: HYDRATION STATIONS AT LIBRARY | 035 | CLOSED | 1831.0178 | 0 | 2739.384 | 2739.384
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | IN: INSTALL 4 HYDRATION STATIONS - BLD 35 | 035 | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PA: HYDRATION STATIONS AT LIBRARY | 035 | CLOSED | 1417.2728 | 0 | 669.744 | 669.744
PJ0004559 | INSTALL 4 HYDRATION STATIONS NEAR PUBLIC ELEVATORS - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-06-12 | PL: HYDRATION STATIONS AT LIBRARY | 035 | CLOSED | 11275.6974 | 0 | 13529.947 | 13529.947
PJ0004559 Total | [7 empty] | 20816.1874 | 0 | 20876.607 | 20876.607
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: CAL POLY BOOKSTORE TECH CENTER | 003 | CLOSED | 1285.9153 | 0 | 1170.8903 | 1170.8903
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: COMP VIEW | 003 | CLOSED | 4225.0127 | 0 | 4225.0127 | 4225.0127
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: CREDIT CARD PURCHASE - VIDEO TRIPOD FOR CONFERENCE ROOM | 003 | CLOSED | 0 | 0 | 37.3965 | 37.3965
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: FLOOR CONNECTION | 003 | CLOSED | 5350 | 0 | 3694.389 | 3694.389
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: MACDONALD DOOR | 003 | CLOSED | 326.3928 | 0 | 326.3928 | 326.3928
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: MORELAND THOMPSON | 003 | CLOSED | 5350 | 0 | 3995.38 | 3995.38
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | AD: SANTA MARIA ACOUSTICAL | 003 | CLOSED | 8560 | 0 | 8545.02 | 8545.02
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1506.25 | 0 | 0 | 0
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | IN: 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | 003 | CLOSED | 128.112 | 0 | 105.966 | 105.966
PJ0004557 | 3RD FLOOR CONFERENCE ROOM IMPROVEMENTS - BLD 3 RM 341 | GONZALES, ALBERT M. | CLOSED | 2013-06-06 | PA: BUSINESS 03-341 CONFERENCE ROOM | 003 | CLOSED | 618.3396 | 0 | 185.724 | 185.724
PJ0004557 Total | [7 empty] | 27350.0224 | 0 | 22286.1713 | 22286.1713
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 240750 | 0 | 268629.6097 | 268629.6097
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: CAME SECURITY | 052 | CLOSED | 1391 | 0 | 1391 | 1391
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 1337.607 | 1337.607
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: COMP VIEW, INC. | 052 | CLOSED | 0 | 0 | 26766.6385 | 26766.6385
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: FLOOR CONNECTION | 052 | CLOSED | 64200 | 0 | 31980.8983 | 31980.8983
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: JOC 13.030.042 MAINO | 052 | CLOSED | 87269.2 | 0 | 52216.4815 | 52216.4815
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: JOC 13.031.044 MAINO | 052 | CLOSED | 0 | 0 | 53486.2077 | 53486.2077
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: JOC 14.033.016 MAINO | 052 | CLOSED | 0 | 0 | 39308.804 | 39308.804
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: OFFICE MAX - STORAGE BOXES TO BE USED BY MOVING CREW | 052 | CLOSED | 0 | 0 | 1142.112 | 1142.112
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: PURCHASE MONITOR ARM ADAPTER TO BE INSTALLED BY CONTRACOR | 052 | CLOSED | 0 | 0 | 44.8651 | 44.8651
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: RRM DESIGN GROUP | 052 | CLOSED | 9228.75 | 0 | 9227.7335 | 9227.7335
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 98.63 | 98.63
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD:MCKENNA ENVIRONMENTAL | 052 | CLOSED | 12165.9 | 0 | 8560 | 8560
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | ANTS: PROGRAM ALARMS FOR EXTENDED ED. SPACE IN BLDG. 52 | 052 | CLOSED | 0 | 0 | 101.664 | 101.664
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | CA: TV MOUNTS, SIGN BRACKETS, HYDRATION STATIONS -BLDG 52 E-WING | 052 | CLOSED | 889.92 | 0 | 1004.454 | 1004.454
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 45894.68 | 0 | 0 | 0
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | EL: ELECTRICAL DEMOLITION OF ROOMS E31-E34 & E45-E47 | 052 | CLOSED | 12002.7326 | 0 | 12246.102 | 12246.102
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | IN: DESIGN/CONSTRUCT GRAD, EXT. ED SPACE - BLD 52, E31-E46 | 052 | CLOSED | 570.0984 | 0 | 583.092 | 583.092
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | ITS: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | 052 | CLOSED | 0 | 0 | 31726.04 | 31726.04
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | LO: RE KEY ALL DOORS FOR DEPARTMENT USE | 052 | CLOSED | 2833.7636 | 0 | 2954.85 | 2954.85
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | PA:PAINT ALL ROOMS E31-E34 AND E45-E47 | 052 | CLOSED | 19505.4824 | 0 | 14592.414 | 14592.414
PJ0004554 | SP 13/14: DESIGN/CONSTRUCT GRAD/EXT. ED SPACE - BLD 52, E31-E46 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | PL: PLUMBING DEMOLITION E31-E34 & E45-E47 | 052 | CLOSED | 33264.0809 | 0 | 15324.8755 | 15324.8755
PJ0004554 Total | [7 empty] | 529965.608 | 0 | 572724.0788 | 572724.0788
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: BKM OFFICE ENVIRONMENTS | 052 | CLOSED | 104860 | 0 | 51681.3745 | 51681.3745
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: COASTAL JANITORIAL | 052 | CLOSED | 0 | 0 | 642 | 642
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: COMP VIEW, INC. | 052 | CLOSED | 0 | 0 | 10014.6543 | 10014.6543
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: FLOOR CONNECTION | 052 | CLOSED | 28890 | 0 | 17836.0761 | 17836.0761
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: JOC 13.030.042 MAINO | 052 | CLOSED | 38180.275 | 0 | 22347.164 | 22347.164
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: JOC 13.031.044 MAINO | 052 | CLOSED | 0 | 0 | 22890.5849 | 22890.5849
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: JOC 14.033.016 MAINO | 052 | CLOSED | 0 | 0 | 16823.0536 | 16823.0536
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 6420 | 0 | 6870.684 | 6870.684
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: RRM DESIGN GROUP | 052 | CLOSED | 5350 | 0 | 5788.165 | 5788.165
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | AD: STATE FIRE MARSHAL FEES | 052 | CLOSED | 0 | 0 | 98.63 | 98.63
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | CA: REMOVE SIGNS IN HALLWAY BLDG.038-BY RMS 106,107,108,109&145 | 052 | CLOSED | 0 | 0 | 167.958 | 167.958
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 22034.12 | 0 | 0 | 0
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | EL: ELECTRICAL RENOVATION OF MUSTANG SUCCESS CENTER | 052 | CLOSED | 5101.3663 | 0 | 2218.458 | 2218.458
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | IN: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 E3-E11&E13-E25 | 052 | CLOSED | 512.448 | 0 | 512.448 | 512.448
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | ITS: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | 052 | CLOSED | 0 | 0 | 13644.34 | 13644.34
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | LO: RE-KEY ROOMS FOR DEPARTMENT USE | 052 | CLOSED | 2833.7636 | 0 | 444.132 | 444.132
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | PA: PAINT ALL ROOMS | 052 | CLOSED | 13691.2028 | 0 | 8083.998 | 8083.998
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | PA: TOUCH UP PAINT - BLDG 038 NEAR RMS 106,107,108,109,145 & 212 | 052 | CLOSED | 0 | 0 | 2352.504 | 2352.504
PJ0004553 | SP 13/14: DESIGN/CONSTRUCT STUDENT AREA - BLD 52 D37-D49&E48 | MCNALLY, CURTIS | CLOSED | 2013-06-11 | PL: REMOVE ALL PLUMBING IN ROOM E48 | 052 | CLOSED | 9919.0937 | 0 | 2366.7115 | 2366.7115
PJ0004553 Total | [7 empty] | 237792.2695 | 0 | 184782.9359 | 184782.9359
PJ0004550 | PAC MAINTENANCE WALK-THROUGH 4/9/2013 - BLDG. 06 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-06-14 | CA: PAC MAINTENANCE WALK THROUG FROM 4/9/13 | 006 | CLOSED | 0 | 0 | 313.035 | 313.035
PJ0004550 | PAC MAINTENANCE WALK-THROUGH 4/9/2013 - BLDG. 06 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-06-14 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004550 | PAC MAINTENANCE WALK-THROUGH 4/9/2013 - BLDG. 06 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-06-14 | ES: PAC MAINTENANCE WALK THROUG FROM 4/9/13 | 006 | CLOSED | 0 | 0 | 114.1307 | 114.1307
PJ0004550 | PAC MAINTENANCE WALK-THROUGH 4/9/2013 - BLDG. 06 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-06-14 | LO: PAC MAINTENANCE WALK THROUG FROM 4/9/13 | 006 | CLOSED | 0 | 0 | 386.74 | 386.74
PJ0004550 | PAC MAINTENANCE WALK-THROUGH 4/9/2013 - BLDG. 06 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-06-14 | PA: PAC MAINTENANCE WALK THROUG FROM 4/9/13 | 006 | CLOSED | 0 | 0 | 173.145 | 173.145
PJ0004550 | PAC MAINTENANCE WALK-THROUGH 4/9/2013 - BLDG. 06 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-06-14 | PL: PAC MAINTENANCE WALK THROUG FROM 4/9/13 | 006 | CLOSED | 0 | 0 | 190.435 | 190.435
PJ0004550 Total | [7 empty] | 0 | 0 | 1177.4857 | 1177.4857
PJ0004549 | REPLACE A PORTION OF THE 5TH FLOOR CARPET - LIBRARY BLDG. 035 | MAY, TOM | CLOSED | 2013-06-12 | AD: FLOOR CONNECTION | 035 | CLOSED | 36997.6254 | 0 | 36997.6254 | 36997.6254
PJ0004549 | REPLACE A PORTION OF THE 5TH FLOOR CARPET - LIBRARY BLDG. 035 | MAY, TOM | CLOSED | 2013-06-12 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 3474.08 | 0 | 0 | 0
PJ0004549 | REPLACE A PORTION OF THE 5TH FLOOR CARPET - LIBRARY BLDG. 035 | MAY, TOM | CLOSED | 2013-06-12 | IN: REPLACE A PORTION OF THE 5TH FL. CARPET - LIBRARY BLDG. 035 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004549 Total | [7 empty] | 40599.8174 | 0 | 37125.7374 | 37125.7374
PJ0004548 | DESIGN FOR EXHAUST HOOD ABOVE SERVICE LINE - BLD 112 | MCNALLY, CURTIS | CLOSED | 2013-06-12 | AD: ASAP REPROGRAPHICS | 112 | CLOSED | 102.648 | 0 | 102.648 | 102.648
PJ0004548 | DESIGN FOR EXHAUST HOOD ABOVE SERVICE LINE - BLD 112 | MCNALLY, CURTIS | CLOSED | 2013-06-12 | AD: ENGLEKIRK AND SABOL | 112 | CLOSED | 1498 | 0 | 1430.59 | 1430.59
PJ0004548 | DESIGN FOR EXHAUST HOOD ABOVE SERVICE LINE - BLD 112 | MCNALLY, CURTIS | CLOSED | 2013-06-12 | AD: GOSS ENGINEERING | 112 | CLOSED | 41302 | 0 | 22317.2575 | 22317.2575
PJ0004548 | DESIGN FOR EXHAUST HOOD ABOVE SERVICE LINE - BLD 112 | MCNALLY, CURTIS | CLOSED | 2013-06-12 | AD: ONTRAC SHIPPING | 112 | CLOSED | 0 | 0 | 68.02 | 68.02
PJ0004548 | DESIGN FOR EXHAUST HOOD ABOVE SERVICE LINE - BLD 112 | MCNALLY, CURTIS | CLOSED | 2013-06-12 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 4177.35 | 0 | 0 | 0
PJ0004548 Total | [7 empty] | 47079.998 | 0 | 23918.5155 | 23918.5155
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | AD: ITS LOCATE UTILITIES FOR SHS FOR SPRING & SUMMER BREAK WORK | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | AD: SOV SECURITY | RESIDENCE | OPEN | 0 | 863.88 | 0 | 863.88
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | AD: WESCO | RESIDENCE | OPEN | 0 | 1709.22 | 23.88 | 1733.1
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | CA: SIGNAGE & BANNER BRACKET DAMAGED BY BONESO@STUDENT HSING SO. | RESIDENCE | CLOSED | 0 | 0 | 364.329 | 364.329
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | CP: PROJECT CONTINGENCY | RESIDENCE | OPEN | 20000 | 0 | 0 | 0
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | CPE: LOCATE UTILITIES FOR SPRING/SUMMER BREAKS 2017 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | CPE: LOCATING FOR SPLICE BOX - SHS (BY 10/6/17) | RESIDENCE | CLOSED | 0 | 0 | 193.284 | 193.284
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: CLEAR EARTH SYSTEMS FOR BORING IN THE G-1/R-2 PARKING LOT | RESIDENCE | CLOSED | 0 | 0 | 341.472 | 341.472
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: CONNECT JOBSITE TRAILER GENERATOR FOR STUDENT HOUSING SOUTH | RESIDENCE | CLOSED | 0 | 0 | 191.016 | 191.016
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: HOUSING SOUTH UTILITY RE-LOCATION WORK - SUMMER 2017 | RESIDENCE | LONG_TERM | 0 | 0 | 13386.702 | 13386.702
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: LOCATE UTILITIES FOR FENCE INSTALLATION AROUND G-1/R-2 LOT | RESIDENCE | CLOSED | 0 | 0 | 212.616 | 212.616
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: LOCATE UTILITIES FOR SHS FOR SPRING & SUMMER BREAK WORK | RESIDENCE | CLOSED | 0 | 0 | 14287.206 | 14287.206
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: LOCATE UTILITIES FOR SPRING/SUMMER BREAKS 2017 | RESIDENCE | LONG_TERM | 0 | 0 | 2291.814 | 2291.814
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: LOCATE UTILITIES FOR STUDENT HOUSING SOUTH | RESIDENCE | CLOSED | 0 | 0 | 438.204 | 438.204
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: LOCATING FOR SPLICE BOX - SHS (BY 10/6/17) | RESIDENCE | CLOSED | 0 | 0 | 64.428 | 64.428
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: MANHOLE INVESTIGATIONS FOR STUDENT HOUSING SOUTH | RESIDENCE | CLOSED | 0 | 0 | 1604.274 | 1604.274
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: REMOVE & SAFE-OFF PARKING LOT LIGHTS & PHONES 9/20 & 9/21/15 | RESIDENCE | CLOSED | 0 | 0 | 2158.338 | 2158.338
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: REPAIR LIGHT POLE DAMAGED BY BONESO BROS - STUDENT HOUSING S | RESIDENCE | CLOSED | 0 | 0 | 2564.772 | 2564.772
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: SHS CONSTRUCTION POWER | RESIDENCE | LONG_TERM | 0 | 0 | 4348.89 | 4348.89
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | EL: SHUT DOWN SWITCH POSITION ON SWITCH 'B' FEEDING 500 KVA TEMP | RESIDENCE | CLOSED | 0 | 0 | 257.712 | 257.712
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | ES: BLDG 1 AHU SHUT-DOWN FOR LV CABLE PULL FOR HOUSING SOUTH | RESIDENCE | CLOSED | 0 | 0 | 252.798 | 252.798
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | ES: HOUSING SOUTH UTILITY RE-LOCATION WORK - SUMMER 2017 | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | ES: LOCATE UTILITIES FOR SHS FOR SPRING & SUMMER BREAK WORK | RESIDENCE | CLOSED | 0 | 0 | 98.496 | 98.496
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: HOUSING SOUTH UTILITY RE-LOCATION WORK - SUMMER 2017 | RESIDENCE | OPEN | 0 | 0 | 520.416 | 520.416
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: INSTALL STUB-UB AT VALVE BOX ADJACENT TO TRACK FOR HOUSING S | RESIDENCE | CLOSED | 0 | 0 | 265.5918 | 265.5918
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: LOCATE UTILITIES FOR SHS FOR SPRING & SUMMER BREAK WORK | RESIDENCE | CLOSED | 0 | 0 | 709.3493 | 709.3493
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: LOCATE UTILITIES FOR SPRING/SUMMER BREAKS 2017 | RESIDENCE | OPEN | 0 | 0 | 40.032 | 40.032
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: LOCATING FOR SPLICE BOX - SHS (BY 10/6/17) | RESIDENCE | COMPLETE | 0 | 0 | 0 | 0
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: SWEEP GRAND AVE. PRIOR TO HOUSING SOUTH HYDRANT TEST 9/1/15 | RESIDENCE | CLOSED | 0 | 0 | 40.032 | 40.032
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LA: TEMP IRRIGATION ROUTING BETWEEN YOSEMITE &THE KIOSK HOSE BIB | RESIDENCE | CLOSED | 0 | 0 | 2639.856 | 2639.856
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | LO: (24) EHV-1 PADLOCKS FOR ELECTRICAL AT STUDENT HOUSING SOUTH | RESIDENCE | CLOSED | 0 | 0 | 1409.736 | 1409.736
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | MO: DELIVER TABLE TO HOUSING SOUTH JOBSITE TRAILER | RESIDENCE | CLOSED | 0 | 0 | 16.902 | 16.902
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PA: REPAIR PAINT DAMAGE IN CODY VAN DORN'S OFFICE 01-128B | RESIDENCE | CLOSED | 0 | 0 | 123.816 | 123.816
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PCV CREW MGR: PROVIDE TREND DATA ON THE HEATING AND DHW AT PCV | RESIDENCE | CLOSED | 0 | 0 | 291.4858 | 291.4858
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PCV ES: RESPOND TO CALL - WIND DAMAGE TO HOUSING SOUTH FENCE | RESIDENCE | CLOSED | 0 | 0 | 32.832 | 32.832
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: CLEAR EARTH SYSTEMS FOR BORING IN THE G-1/R-2 PARKING LOT | RESIDENCE | ASSIGNED | 0 | 0 | 6144.0216 | 6144.0216
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: HOUSING SOUTH UTILITY RE-LOCATION WORK - SUMMER 2017 | RESIDENCE | LONG_TERM | 0 | 0 | 225.708 | 225.708
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: HYDRANT FLOW TEST FOR STUDENT HOUSING SOUTH | RESIDENCE | PEND_SCHED | 0 | 0 | 128.976 | 128.976
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: LOCATE UTILITIES FOR FENCE INSTALLATION AROUND G-1/R-2 LOT | RESIDENCE | CLOSED | 0 | 0 | 35.472 | 35.472
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: LOCATE UTILITIES FOR SHS FOR SPRING & SUMMER BREAK WORK | RESIDENCE | OPEN | 0 | 0 | 14282.208 | 14282.208
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: LOCATE UTILITIES FOR SPRING/SUMMER BREAKS 2017 | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: LOCATE UTILITIES FOR STUDENT HOUSING SOUTH | RESIDENCE | CLOSED | 0 | 0 | 7615.71 | 7615.71
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: LOCATING FOR SPLICE BOX - SHS (BY 10/6/17) | RESIDENCE | OPEN | 0 | 0 | 70.944 | 70.944
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | PL: SHS, GRAND AV H2O LINE TIE-INS | RESIDENCE | COMPLETE | 0 | 0 | 5611.3965 | 5611.3965
PJ0004547 | MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH - YAK¿IT¿UT¿U | RENDLER, ANNIE | IN_CONSTR | 2013-06-13 | SM: MJ: IN HOUSE SUPPORT FOR STUDENT HOUSING SOUTH | RESIDENCE | OPEN | 0 | 0 | 0 | 0
PJ0004547 Total | [7 empty] | 20000 | 2573.1 | 83284.716 | 85857.816
PJ0004546 | HANG TV IN DRC LOBBY - BLD 124 RM 119 | MCNALLY, CURTIS | CLOSED | 2013-03-01 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 53.32 | 0 | 0 | 0
PJ0004546 | HANG TV IN DRC LOBBY - BLD 124 RM 119 | MCNALLY, CURTIS | CLOSED | 2013-03-01 | EL: INSTALL ONE DUPLEX OUTLET AT TYP. HEIGHT FOR PRINTER | 124 | CLOSED | 405.1694 | 0 | 391.116 | 391.116
PJ0004546 | HANG TV IN DRC LOBBY - BLD 124 RM 119 | MCNALLY, CURTIS | CLOSED | 2013-03-01 | IN: HANG TV IN DRC LOBBY - BLD 124 RM 119 | 124 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004546 Total | [7 empty] | 586.6014 | 0 | 487.2 | 487.2
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | CA: SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE 15 & 16 | 061 | CLOSED | 0 | 0 | 7821.37 | 7821.37
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | CPE: SUPPORT FOR 2013 SPING COMMENCEMENT - JUNE 15 & 16 | 061 | CLOSED | 0 | 0 | 1077.8228 | 1077.8228
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | CU: COMMENCEMENT SUPPORT ON JUNE 15 & 16 | 061 | CLOSED | 0 | 0 | 11843.515 | 11843.515
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | CU: STADIUM CLEANUP OF EAST SIDE BLEACHERS - JUNE 12 | 061 | CLOSED | 0 | 0 | 1078.21 | 1078.21
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | CU:SPANOS STADIUM WEST SIDE PREPARATION FOR COMMENCEMENT. | 061 | CLOSED | 0 | 0 | 3219.94 | 3219.94
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | EL: SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE 15 & 16 | 061 | CLOSED | 0 | 0 | 846.97 | 846.97
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | LA: SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE 15&16 | 061 | CLOSED | 0 | 0 | 10899.4165 | 10899.4165
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | MO: SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE 15&16 | 061 | CLOSED | 0 | 0 | 1038.695 | 1038.695
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | PA: SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE 14 | 061 | CLOSED | 0 | 0 | 123.675 | 123.675
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | PL: SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE 15 & 16 | 061 | CLOSED | 0 | 0 | 1312.23 | 1312.23
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: CE/ENVE POST COMMENCEMENT - 6/15 | 061 | CLOSED | 0 | 0 | 21.5 | 21.5
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: COMPUTER SCIENCE POST COMMENCEMENT - 6/15 | 061 | CLOSED | 0 | 0 | 56 | 56
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: COSAM POST COMMENCEMENT - 6/16 | 061 | CLOSED | 0 | 0 | 54 | 54
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: ELECTRICAL ENGINEERING POST COMMENCEMENT-6/15 | 061 | CLOSED | 0 | 0 | 61 | 61
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: FSN POST COMMENCEMENT - 6/16 | 061 | CLOSED | 0 | 0 | 72 | 72
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: GRC POST COMMENCEMENT - 6/14 | 061 | CLOSED | 0 | 0 | 50 | 50
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: HISTORY POST COMMENCEMENT - 6/15 | 061 | CLOSED | 0 | 0 | 46 | 46
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: ME POST COMMENCEMENT - 6/15 | 061 | CLOSED | 0 | 0 | 68 | 68
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: OCOB POST COMMENCEMENT - 6/14 | 061 | CLOSED | 0 | 0 | 113 | 113
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: POLITICAL SCIENCE POST COMMENCEMENT - 6/15 | 061 | CLOSED | 0 | 0 | 50.5 | 50.5
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL: WVIT POST COMMENCEMENT - 6/16 | 061 | CLOSED | 0 | 0 | 81 | 81
PJ0004543 | SUPPORT FOR 2013 SPRING COMMENCEMENT - JUNE15 & 16 (PROJECT) | POPHAM, DONALD J. | CLOSED | 2013-05-31 | SUPPLY RENTAL; AGB POST COMMENCEMENT - 6/16 | 061 | CLOSED | 0 | 0 | 126 | 126
PJ0004543 Total | [7 empty] | 0 | 0 | 40060.8443 | 40060.8443
PJ0004542 | CHANGE LOCKSET ON STORAGE RM DOOR TO KEYPAD- BLD 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-29 | CP: PROJECT CONTINGENCY | 042S | CLOSED | 168.01 | 0 | 0 | 0
PJ0004542 | CHANGE LOCKSET ON STORAGE RM DOOR TO KEYPAD- BLD 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-29 | IN: CHANGE LOCKSET ON STORAGE RM DOOR TO KEYPAD - TENNIS COURTS | 042S | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004542 | CHANGE LOCKSET ON STORAGE RM DOOR TO KEYPAD- BLD 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-29 | LO: CHANGE LOCKSET ON STORAGE RM DOOR TO KEYPAD- BLD 42S | 042S | CLOSED | 1616.088 | 0 | 1082.46 | 1082.46
PJ0004542 Total | [7 empty] | 1848.154 | 0 | 1146.516 | 1146.516
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | AD: APC CONTRACTORS | 001 | CLOSED | 7511.4 | 0 | 7477.7806 | 7477.7806
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | AD: DOORWAYS | 001 | CLOSED | 1605 | 0 | 1522.61 | 1522.61
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | AD: FLOOR CONNECTION | 001 | CLOSED | 762.1182 | 0 | 481.5 | 481.5
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | AD: J.L. FASULO DRYWALL | 001 | CLOSED | 4055.3 | 0 | 4055.3 | 4055.3
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | AD: MCKENNA ENVIRONMENTAL | 001 | CLOSED | 4875.99 | 0 | 4477.95 | 4477.95
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | AD: SANTA MARIA ACOUSTICAL | 001 | CLOSED | 2016.95 | 0 | 1246.55 | 1246.55
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | CA: PROJECT SUPPORT FOR ADMIN 413 | 001 | CLOSED | 787.4052 | 0 | 1183.44 | 1183.44
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 367.87 | 0 | 0 | 0
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 001 | CLOSED | 0 | 0 | 6 | 6
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | EL: PROJECT SUPPORT FOR REMODEL OF ADMIN 413 | 001 | CLOSED | 659.328 | 0 | 67.416 | 67.416
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | IN: REMODEL OFFICE SUITE FOR VP FOR ADVANCEMENT 01-414 | 001 | CLOSED | 256.224 | 0 | 96.084 | 96.084
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | LO: ADMIN ROOM 413 PROJECT SUPPORT | 001 | CLOSED | 832.176 | 0 | 623.052 | 623.052
PJ0004541 | REMODEL OFFICE SUITE FOR VICE PRESIDENT FOR ADVANCEMENT 01-414 | GONZALES, ALBERT M. | CLOSED | 2013-05-28 | PA: PAINTING FOR REMODEL FOR VICE PRESIDENT FOR ADVANCEMENT | 001 | CLOSED | 1117.2728 | 0 | 2849.472 | 2849.472
PJ0004541 Total | [7 empty] | 24847.0342 | 0 | 24087.1546 | 24087.1546
PJ0004539 | INSTALL REPORTABLE SMOKE ALARMS IN CSD APTS- ALL RED BRICK DORMS | MOLLAN, CHERYL L. | CLOSED | 2013-05-28 | AD: DEEP BLUE INTEGRATION | RESIDENCE | CLOSED | 7354.3454 | 0 | 5933.1928 | 5933.1928
PJ0004539 | INSTALL REPORTABLE SMOKE ALARMS IN CSD APTS- ALL RED BRICK DORMS | MOLLAN, CHERYL L. | CLOSED | 2013-05-28 | ANTS:PROVIDE SUPPORT FOR DEEP BLUE INTEGRATION | RESIDENCE | CLOSED | 288.288 | 0 | 132.132 | 132.132
PJ0004539 | INSTALL REPORTABLE SMOKE ALARMS IN CSD APTS- ALL RED BRICK DORMS | MOLLAN, CHERYL L. | CLOSED | 2013-05-28 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 884.07 | 0 | 0 | 0
PJ0004539 | INSTALL REPORTABLE SMOKE ALARMS IN CSD APTS- ALL RED BRICK DORMS | MOLLAN, CHERYL L. | CLOSED | 2013-05-28 | IN: INSTALL REPORTABLE SMOKE ALARMS IN CSD APTS- RED BRICK DORMS | RESIDENCE | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004539 Total | [7 empty] | 8654.8154 | 0 | 6193.4368 | 6193.4368
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | AD: APC CONTRACTORS | 035 | CLOSED | 5291.15 | 0 | 5291.15 | 5291.15
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 5338.23 | 0 | 5338.23 | 5338.23
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | AD: MCKENNA ENVIRONMENTAL | 035 | CLOSED | 1048.6 | 0 | 1048.6 | 1048.6
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 386.14 | 0 | 0 | 0
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | EH&S: LAB CHARGES PROCESSED THROUGH UTILITIES ACCOUNT(MAT, ONLY) | 035 | CLOSED | 0 | 0 | 64.8 | 64.8
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | EL: DEMO ELECTRICAL ABOVE CIELING ROOM 101F | 035 | CLOSED | 750.0024 | 0 | 262.584 | 262.584
PJ0004537 | REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2013-05-23 | IN: REMODEL LIBRARY FIRST FLOOR STAFF AREA 1 - BLD 35 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004537 Total | [7 empty] | 12942.2344 | 0 | 12133.476 | 12133.476
PJ0004535 | SP 13/14: ADA ACCESSIBILITY FOR SPANOS STADIUM TAILGATING | MCNALLY, CURTIS | CLOSED | 2013-05-14 | AD: JOC 13.030.011 MAINO | GENERAL | CLOSED | 69442.5827 | 0 | 68929.4856 | 68929.4856
PJ0004535 | SP 13/14: ADA ACCESSIBILITY FOR SPANOS STADIUM TAILGATING | MCNALLY, CURTIS | CLOSED | 2013-05-14 | AD: WALLACE GROUP | GENERAL | CLOSED | 3531 | 0 | 3210 | 3210
PJ0004535 | SP 13/14: ADA ACCESSIBILITY FOR SPANOS STADIUM TAILGATING | MCNALLY, CURTIS | CLOSED | 2013-05-14 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 6536.42 | 0 | 0 | 0
PJ0004535 | SP 13/14: ADA ACCESSIBILITY FOR SPANOS STADIUM TAILGATING | MCNALLY, CURTIS | CLOSED | 2013-05-14 | IN: ADA ACCESSIBILITY FOR TAILGATING | GENERAL | CLOSED | 1024.896 | 0 | 448.392 | 448.392
PJ0004535 | SP 13/14: ADA ACCESSIBILITY FOR SPANOS STADIUM TAILGATING | MCNALLY, CURTIS | CLOSED | 2013-05-14 | LA: REPAIR BROKEN IRRIGATION LINES AT PERIMETER & VIA CARTA | GENERAL | CLOSED | 863.424 | 0 | 86.016 | 86.016
PJ0004535 Total | [7 empty] | 81398.3227 | 0 | 72673.8936 | 72673.8936
PJ0004534 | POWER WASH BUILDING 13 EXTERIOR | WILWAND, MARK | CLOSED | 2013-05-10 | AD: COASTAL JANITORIAL | 013 | CLOSED | 7281.35 | 0 | 7281.35 | 7281.35
PJ0004534 | POWER WASH BUILDING 13 EXTERIOR | WILWAND, MARK | CLOSED | 2013-05-10 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 529.09 | 0 | 0 | 0
PJ0004534 | POWER WASH BUILDING 13 EXTERIOR | WILWAND, MARK | CLOSED | 2013-05-10 | IN: POWER WASH BUILDING 13 EXTERIOR | 013 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004534 Total | [7 empty] | 7938.552 | 0 | 7409.462 | 7409.462
PJ0004533 | LIGHT POLE HIT BY CAR - VILLAGE DR, LOWER PARKING(UPD # 13-0661) | JOHNSON, BEN | CLOSED | 2013-05-28 | CA: PROVIDE CONCRETE FOR ONE LIGHT POLE HOLE | RESIDENCE | CLOSED | 0 | 0 | 153.42 | 153.42
PJ0004533 | LIGHT POLE HIT BY CAR - VILLAGE DR, LOWER PARKING(UPD # 13-0661) | JOHNSON, BEN | CLOSED | 2013-05-28 | CP: PROJECT CONTINGENCY (UPD # 13-0661) | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004533 | LIGHT POLE HIT BY CAR - VILLAGE DR, LOWER PARKING(UPD # 13-0661) | JOHNSON, BEN | CLOSED | 2013-05-28 | EL: LIGHT POLE HIT BY CAR - VILLAGE DR. | RESIDENCE | CLOSED | 0 | 0 | 3666.72 | 3666.72
PJ0004533 | LIGHT POLE HIT BY CAR - VILLAGE DR, LOWER PARKING(UPD # 13-0661) | JOHNSON, BEN | CLOSED | 2013-05-28 | EO: ASSIST ELECTRICIANS WITH REPLACING STREET LIGHT - PCV | RESIDENCE | CLOSED | 0 | 0 | 796.224 | 796.224
PJ0004533 | LIGHT POLE HIT BY CAR - VILLAGE DR, LOWER PARKING(UPD # 13-0661) | JOHNSON, BEN | CLOSED | 2013-05-28 | PCV CA: ASSIST ELECTRICIANS WITH REPLACING STREET LIGHT - PCV | RESIDENCE | CLOSED | 0 | 0 | 112.776 | 112.776
PJ0004533 Total | [7 empty] | 0 | 0 | 4729.14 | 4729.14
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | AD: G.F. GARCIA AND SONS | 051 | CLOSED | 5350 | 0 | 5168.1 | 5168.1
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | AD: J.L. FASULO DRYWALL | 051 | CLOSED | 7307.0407 | 0 | 7307.03 | 7307.03
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | AD: MAINO CONSTRUCTION (LOW VALUE PUBLIC WORKS) | 051 | CLOSED | 5269.75 | 0 | 4872.78 | 4872.78
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | AD: MORELAND THOMPSON, INC. | 051 | CLOSED | 0 | 0 | 1070 | 1070
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | IN: SP 13/14: RENOVATE STORAGE SHED - BLD 51 | 051 | CLOSED | 256.224 | 0 | 202.05 | 202.05
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | LO: PRESIDENTS SHED STORAGE | 051 | CLOSED | 738.2958 | 0 | 701.37 | 701.37
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | MO: MOVE PRESIDENTS PERSONAL ITEMS | 051 | CLOSED | 129.6 | 0 | 96.576 | 96.576
PJ0004532 | SP 13/14: RENOVATE STORAGE SHED - BLD 51 | GONZALES, ALBERT M. | CLOSED | 2013-05-24 | PA: PAINT STORAGE SHED AT PRESIDENT'S RESIDENCE | 051 | CLOSED | 1666.1989 | 0 | 712.368 | 712.368
PJ0004532 Total | [7 empty] | 20717.1094 | 0 | 20130.274 | 20130.274
PJ0004531 | FIRE DAMAGE RECONSTRUCTION - PCV CORRALITOS BLDG. 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-23 | AD: FLOOR CONNECTION | 171C | CLOSED | 535 | 0 | 535 | 535
PJ0004531 | FIRE DAMAGE RECONSTRUCTION - PCV CORRALITOS BLDG. 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-23 | AD: JOC 13.027.016 PUB CONSTRUCTION | 171C | CLOSED | 43634.6 | 0 | 32408.9304 | 32408.9304
PJ0004531 | FIRE DAMAGE RECONSTRUCTION - PCV CORRALITOS BLDG. 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-23 | CP: PROJECT CONTINGENCY | 171C | CLOSED | 4413.38 | 0 | 0 | 0
PJ0004531 | FIRE DAMAGE RECONSTRUCTION - PCV CORRALITOS BLDG. 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-23 | IN: FIRE DAMAGE RECONSTRUCTION - PCV CORRALITOS BLDG. 171C | 171C | CLOSED | 384.336 | 0 | 608.532 | 608.532
PJ0004531 Total | [7 empty] | 48967.316 | 0 | 33552.4624 | 33552.4624
PJ0004530 | 2013 CATA FARM SHOW SET-UP - JUNE 24, 2013 - FARM SHOP BLDG. 09 | POPHAM, DONALD J. | CLOSED | 2013-05-23 | CA: SET UP FOR THE CATA FARM SHOW - JUNE 24 | 009 | CLOSED | 0 | 0 | 313.734 | 313.734
PJ0004530 | 2013 CATA FARM SHOW SET-UP - JUNE 24, 2013 - FARM SHOP BLDG. 09 | POPHAM, DONALD J. | CLOSED | 2013-05-23 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0004530 | 2013 CATA FARM SHOW SET-UP - JUNE 24, 2013 - FARM SHOP BLDG. 09 | POPHAM, DONALD J. | CLOSED | 2013-05-23 | EL: PROVIDE ELECTRICITY FOR CATA FARM SHOW - JUNE 24 | 009 | CLOSED | 0 | 0 | 573.036 | 573.036
PJ0004530 Total | [7 empty] | 0 | 0 | 886.77 | 886.77
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | AD: ATD WINDOW TINTING | 001 | CLOSED | 194.74 | 0 | 194.74 | 194.74
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | AD: FLOOR CONNECTION | 001 | CLOSED | 2744.55 | 0 | 2744.55 | 2744.55
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | AD: JOC 13.028.025 MAINO | 001 | CLOSED | 14656.325 | 0 | 11963.7556 | 11963.7556
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | AD: MACDONALD CO. | 001 | CLOSED | 704.06 | 0 | 705.5045 | 705.5045
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | CA: CONSTRUCTION CLEANUP IN ADMIN 128 | 001 | CLOSED | 745.044 | 0 | 1022.79 | 1022.79
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 568.34 | 0 | 0 | 0
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) (N/L) | 001 | CLOSED | 0 | 0 | 135.6 | 135.6
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | EH&S: TESTING FOR RENOVATION OF OFFICE OF THE VP-ADMN(N/L) | 001 | CLOSED | 334.8 | 0 | 0 | 0
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | EL:DEMO AND INSTALL NEW ELECTRICAL FOR REMODEL 01-128 | 001 | CLOSED | 3451.0202 | 0 | 2531.3006 | 2531.3006
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | IN: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | 001 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | LO:LOCKS FOR REMODEL IN ADM 128 | 001 | CLOSED | 318.2958 | 0 | 440.886 | 440.886
PJ0004529 | SP13/14: RENOVATE OFFICE OF THE VICE PRESIDENT - ADMN 01 RM 128D | MAY, TOM | CLOSED | 2013-05-22 | PA:PAINT VP OFFICES IN ADMIN 128 | 001 | CLOSED | 2353.952 | 0 | 2364.552 | 2364.552
PJ0004529 Total | [7 empty] | 26327.3511 | 0 | 22359.9027 | 22359.9027
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | AD: BELFOR | 171C | CLOSED | 0 | 0 | 106637.1844 | 106637.1844
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | CP: PROJECT CONTINGENCY | 171C | CLOSED | 0 | 0 | 0 | 0
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | CU: EMERGENCY FIRE DAMAGE REMEDIATION - PCV CORRALITOS -171C | 171C | CLOSED | 0 | 0 | 459.144 | 459.144
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | EL:CONSTRUCTION SUPPORT FOR WATER REMEDIATION | 171C | CLOSED | 0 | 0 | 456.888 | 456.888
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | IN: EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | 171C | CLOSED | 0 | 0 | 320.28 | 320.28
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | PCV EL SUPPORT FOR WATER DAMAGE REMEDIATION DUE TO FIRE AT 171C | 171C | CLOSED | 0 | 0 | 1179.78 | 1179.78
PJ0004528 | EMERGENCY FIRE DAMAGE REMEDIATION - PCV 171C | MOLLAN, CHERYL L. | CLOSED | 2013-05-16 | PCV ES: SUPPORT FOR WATER DAMAGE REMEDIATION DUE TO FIRE AT 171C | 171C | CLOSED | 0 | 0 | 468.27 | 468.27
PJ0004528 Total | [7 empty] | 0 | 0 | 109521.5464 | 109521.5464
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | AD: DOW DIVERSIFIED | 011 | CLOSED | 1565.41 | 0 | 1565.41 | 1565.41
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | CA: HOOD REMOVAL COUNTER INFILL | 011 | CLOSED | 1082.208 | 0 | 434.469 | 434.469
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 669.47 | 0 | 0 | 0
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | EL: HOOD REMOVAL AND ASHING FURNACE INSTALLATION | 011 | CLOSED | 928.992 | 0 | 1028.904 | 1028.904
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | ES:REMOVE FUME HOOD & INSTALL VENT HOOD | 011 | CLOSED | 5598.6919 | 0 | 2797.764 | 2797.764
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | IN: INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | 011 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | MO: MOVE OLD HOOD FROM 11-307 TO BLDG. 13 | 011 | CLOSED | 129.6 | 0 | 36.216 | 36.216
PJ0004527 | INSTALL ASHING FURNACE AND HOOD - BLD 011 RM 307 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-09 | PA: PATCH / PAINT WALL AREAS AT REMOVED HOOD | 011 | CLOSED | 594.912 | 0 | 211.14 | 211.14
PJ0004527 Total | [7 empty] | 10697.3959 | 0 | 6169.987 | 6169.987
PJ0004526 | REMOVE DEPARTMENT OF TRANSPORTATION TRAILER - NEAR BLD 4 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-15 | AD: MAINO (LOW VALUE PUBLIC WORKS) | GENERAL | CLOSED | 5323.25 | 0 | 5143.49 | 5143.49
PJ0004526 | REMOVE DEPARTMENT OF TRANSPORTATION TRAILER - NEAR BLD 4 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-15 | AD: MCKENNA ENVIRONMENTAL | GENERAL | CLOSED | 1391 | 0 | 1136.34 | 1136.34
PJ0004526 | REMOVE DEPARTMENT OF TRANSPORTATION TRAILER - NEAR BLD 4 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-15 | AD: SLO COUNTY APCD - 10-DAY NESHAPS NOTICE FEES | GENERAL | CLOSED | 402 | 0 | 402 | 402
PJ0004526 | REMOVE DEPARTMENT OF TRANSPORTATION TRAILER - NEAR BLD 4 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-15 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 358.27 | 0 | 0 | 0
PJ0004526 | REMOVE DEPARTMENT OF TRANSPORTATION TRAILER - NEAR BLD 4 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-15 | IN: REMOVE DEPARTMENT OF TRANSPORTATION TRAILER - NEAR BLD 4 | GENERAL | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004526 Total | [7 empty] | 7538.576 | 0 | 6777.914 | 6777.914
PJ0004525 | REPAIR WATER DAMAGE CAUSED BY LEAK - BLG. 11 OUTSIDE RM. 305A | GRIFFIN, PATRICK E. | CLOSED | 2013-05-14 | CA: DAMAGE TO ROOM 211 DUE TO LEAK IN 305A&B - BLDG 11 | 011 | CLOSED | 0 | 0 | 607.435 | 607.435
PJ0004525 | REPAIR WATER DAMAGE CAUSED BY LEAK - BLG. 11 OUTSIDE RM. 305A | GRIFFIN, PATRICK E. | CLOSED | 2013-05-14 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0004525 | REPAIR WATER DAMAGE CAUSED BY LEAK - BLG. 11 OUTSIDE RM. 305A | GRIFFIN, PATRICK E. | CLOSED | 2013-05-14 | CU:ASSIST WITH WATER CLEANUP AT 11-211A | 011 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0004525 | REPAIR WATER DAMAGE CAUSED BY LEAK - BLG. 11 OUTSIDE RM. 305A | GRIFFIN, PATRICK E. | CLOSED | 2013-05-14 | ES: INVESTIGATE WATER LEAK - BLDG. 11 RMS 211 AND 305A/B | 011 | CLOSED | 0 | 0 | 52.03 | 52.03
PJ0004525 | REPAIR WATER DAMAGE CAUSED BY LEAK - BLG. 11 OUTSIDE RM. 305A | GRIFFIN, PATRICK E. | CLOSED | 2013-05-14 | PA:PATCH AND PAINT WALL AT 11-211 | 011 | CLOSED | 0 | 0 | 197.88 | 197.88
PJ0004525 | REPAIR WATER DAMAGE CAUSED BY LEAK - BLG. 11 OUTSIDE RM. 305A | GRIFFIN, PATRICK E. | CLOSED | 2013-05-14 | PL: REPAIR LEAKING HOSE BIB AND CHECK EVAP COOLE OUTSIDE 11-305A | 011 | CLOSED | 0 | 0 | 299.255 | 299.255
PJ0004525 Total | [7 empty] | 0 | 0 | 1265.92 | 1265.92
PJ0004524 | REPLACE DRC STORAGE SHED - BLDG 71 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-13 | CA: REPLACE DRC STORAGE SHED AT TRANSPORTATION | 071 | CLOSED | 1840.416 | 0 | 2155.812 | 2155.812
PJ0004524 | REPLACE DRC STORAGE SHED - BLDG 71 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-13 | CP: PROJECT CONTINGENCY | 071 | CLOSED | 209.41 | 0 | 0 | 0
PJ0004524 | REPLACE DRC STORAGE SHED - BLDG 71 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-13 | IN: REPLACE DRC STORAGE SHED - BLDG 71 | 071 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004524 Total | [7 empty] | 2113.882 | 0 | 2219.868 | 2219.868
PJ0004523 | FURNITURE RECONFIGURATION IN BLDG 46 | MAY, TOM | CLOSED | 2013-05-13 | AD: RUSSCO | 046 | CLOSED | 535 | 0 | 535 | 535
PJ0004523 | FURNITURE RECONFIGURATION IN BLDG 46 | MAY, TOM | CLOSED | 2013-05-13 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 89.59 | 0 | 0 | 0
PJ0004523 | FURNITURE RECONFIGURATION IN BLDG 46 | MAY, TOM | CLOSED | 2013-05-13 | EL: DISCONNECT WHIP FROM FURNITURE - BLDG. 046 MAIN ROOM | 046 | CLOSED | 134.832 | 0 | 206.5824 | 206.5824
PJ0004523 | FURNITURE RECONFIGURATION IN BLDG 46 | MAY, TOM | CLOSED | 2013-05-13 | IN: FURNITURE RECONFIGURATION IN BLDG 46 | 046 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004523 | FURNITURE RECONFIGURATION IN BLDG 46 | MAY, TOM | CLOSED | 2013-05-13 | MO: MOVE FURNITURE PANELS FROM BLDG. 46 TO BLDG. 50K | 046 | CLOSED | 162 | 0 | 54.324 | 54.324
PJ0004523 Total | [7 empty] | 985.478 | 0 | 859.9624 | 859.9624
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | AD: JOC 13.028.016 MAINO | 019 | CLOSED | 66459.0589 | 0 | 67299.0731 | 67299.0731
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | AD: MCKENNA ENVIRONMENTAL | 019 | CLOSED | 12112.4 | 0 | 12026.8 | 12026.8
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | AD: QUAGLINO ROOFING | 019 | CLOSED | 2963.9 | 0 | 2963.9 | 2963.9
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 3109.38 | 0 | 0 | 0
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIALS, ONLY) | 019 | CLOSED | 0 | 0 | 156 | 156
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | EH&S: TESTING FOR EMERGENCY ABATEMENT AT BLDG. 019 (N/L) | 019 | CLOSED | 107.1 | 0 | 12 | 12
PJ0004522 | EMERGENCY WASTE LINE/DUCT WORK REPAIR & HAZ MAT ABATEMENT BLD 19 | LAMPMAN, GREG | CLOSED | 2013-05-09 | IN: EMERGENCY WASTE LINE/DUCT REPAIR & HAZ MAT ABATEMENT BLD 19 | 019 | CLOSED | 192.168 | 0 | 192.168 | 192.168
PJ0004522 Total | [7 empty] | 84944.0069 | 0 | 82649.9411 | 82649.9411
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | AD: JOC 13.028.003 MAINO | 033 | CLOSED | 124994.46 | 0 | 123277.04 | 123277.04
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | AD: KNECHT'S PLUMBING AND HEATING | 033 | CLOSED | 2443.04 | 0 | 2442.48 | 2442.48
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 033 | CLOSED | 0 | 0 | 41 | 41
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | EL:BLDG 33 CADAVER LAB ELECTRICAL SUPPORT | 033 | CLOSED | 2800.5718 | 0 | 585.296 | 585.296
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | ES: 33-151 CADAVER LAB EXHAUST SUPPORT | 033 | CLOSED | 2779.4426 | 0 | 104.06 | 104.06
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | IN: SR 13/14:CONSTRUCTION PHASE FOR VENT SYSTEM BLDG 33 - RM 151 | 033 | CLOSED | 960.84 | 0 | 80.07 | 80.07
PJ0004520 | SR 13/14: CONSTRUCTION PHASE FOR VENT SYSTEM: BLDG 33 - RM 151 | BRENNAN, MICHAEL | CLOSED | 2013-05-10 | LO: 33-151 INSTALL ORANGE CORE | 033 | CLOSED | 107.8651 | 0 | 24.185 | 24.185
PJ0004520 Total | [7 empty] | 134086.2195 | 0 | 126554.131 | 126554.131
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | AD: CAME SECURITY | 040 | CLOSED | 17120 | 0 | 16504.75 | 16504.75
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | AD: ITS | 040 | CLOSED | 0 | 0 | 60.64 | 60.64
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | AD: JOC 15.036.005 STAPLES | 040 | CLOSED | 20470.7799 | 0 | 20470.7799 | 20470.7799
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | ANTS: | 040 | CLOSED | 492.192 | 0 | 135.552 | 135.552
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | CA: SIGNAGE FOR YARD AT BLDG. 40 | 040 | CLOSED | 225.552 | 0 | 278.255 | 278.255
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 4362.65 | 0 | 0 | 0
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | EL: SECURITY SYSTEM SUPPORT INSTALLATION AND REPAIRS | 040 | CLOSED | 1468.32 | 0 | 634.53 | 634.53
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | IN: SR 12/13: YARD IMPROVEMENTS - BLDG 40 | 040 | CLOSED | 256.224 | 0 | 256.68 | 256.68
PJ0004519 | SR 12/13: YARD SAFETY IMPROVEMENTS - BLDG 40 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-10 | LO: | 040 | CLOSED | 696.528 | 0 | 60.924 | 60.924
PJ0004519 Total | [7 empty] | 45092.2459 | 0 | 38402.1109 | 38402.1109
PJ0004518 | SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | MOLLAN, CHERYL L. | CLOSED | 2013-05-10 | AD: JOC 13.028.030 MAINO | 042A | CLOSED | 35049.01 | 0 | 35049.01 | 35049.01
PJ0004518 | SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | MOLLAN, CHERYL L. | CLOSED | 2013-05-10 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004518 | SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | MOLLAN, CHERYL L. | CLOSED | 2013-05-10 | CPE:CONSTRUCTION SUPPORT FOR POOL PUMP REPLACEMENT | 042A | CLOSED | 8802.0555 | 0 | 6701.85 | 6701.85
PJ0004518 | SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | MOLLAN, CHERYL L. | CLOSED | 2013-05-10 | EH&S: (N/L) | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004518 | SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | MOLLAN, CHERYL L. | CLOSED | 2013-05-10 | IN: SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | 042A | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0004518 | SR 12/13: REFURBISH ORIGINAL POOL PUMP: BLDG 42A | MOLLAN, CHERYL L. | CLOSED | 2013-05-10 | PL:PROVIDE CONSTRUCTION SUPPORT FOR POOL PUMP REPLACEMENT | 042A | CLOSED | 549.275 | 0 | 549.275 | 549.275
PJ0004518 Total | [7 empty] | 44507.1005 | 0 | 42406.895 | 42406.895
PJ0004517 | CAME SECURITY TO INSTALL PANIC BUTTONS - BLD 40 | WILWAND, MARK | CLOSED | 2013-05-07 | AD: CAME SECURITY | 040 | CLOSED | 882.75 | 0 | 882.75 | 882.75
PJ0004517 | CAME SECURITY TO INSTALL PANIC BUTTONS - BLD 40 | WILWAND, MARK | CLOSED | 2013-05-07 | ANTS: PANIC BUTTON PROGAMMING | 040 | CLOSED | 96.096 | 0 | 72.072 | 72.072
PJ0004517 | CAME SECURITY TO INSTALL PANIC BUTTONS - BLD 40 | WILWAND, MARK | CLOSED | 2013-05-07 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 104.29 | 0 | 0 | 0
PJ0004517 | CAME SECURITY TO INSTALL PANIC BUTTONS - BLD 40 | WILWAND, MARK | CLOSED | 2013-05-07 | IN: CAME SECURITY TO INSTALL PANIC BUTTONS - BLD 40 | 040 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004517 Total | [7 empty] | 1147.192 | 0 | 1018.878 | 1018.878
PJ0004515 | POWER WASH WINDOWS AND SIDEWALKS - BLD 03 | LOOSLEY, SCOTT L. | CLOSED | 2013-05-08 | AD: COASTAL JANITORIAL | 003 | CLOSED | 1278.65 | 0 | 1278.65 | 1278.65
PJ0004515 | POWER WASH WINDOWS AND SIDEWALKS - BLD 03 | LOOSLEY, SCOTT L. | CLOSED | 2013-05-08 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 154.1 | 0 | 0 | 0
PJ0004515 | POWER WASH WINDOWS AND SIDEWALKS - BLD 03 | LOOSLEY, SCOTT L. | CLOSED | 2013-05-08 | IN: POWER WASH WINDOWS AND SIDEWALKS - BLD 03 | 003 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004515 Total | [7 empty] | 1560.862 | 0 | 1342.706 | 1342.706
PJ0004513 | SCIENCE - FACILITY CONDITION ASSESSMENT - BLD 52 (NO OVERHEAD) | NEEL, JOEL | CLOSED | 2013-05-07 | AD: ISES CORP | 052 | CLOSED | 11925.63 | 0 | 11925.63 | 11925.63
PJ0004513 | SCIENCE - FACILITY CONDITION ASSESSMENT - BLD 52 (NO OVERHEAD) | NEEL, JOEL | CLOSED | 2013-05-07 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0004513 | SCIENCE - FACILITY CONDITION ASSESSMENT - BLD 52 (NO OVERHEAD) | NEEL, JOEL | CLOSED | 2013-05-07 | ES: SUPPORT FOR ASSESSMENT CONSULTANT AT SCIENCE BLDG. 052 (N/L) | 052 | CLOSED | 364.21 | 0 | 0 | 0
PJ0004513 Total | [7 empty] | 12289.84 | 0 | 11925.63 | 11925.63
PJ0004512 | MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | PRINCI, COLIN | IN_CONSTR | 2013-05-07 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 2000 | 0 | 0 | 0
PJ0004512 | MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | PRINCI, COLIN | IN_CONSTR | 2013-05-07 | EL: MARK UTILITIES FOR FERMENTATION SCIENCES (BY 1/10/18?) | GENERAL | CLOSED | 0 | 0 | 76.056 | 76.056
PJ0004512 | MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | PRINCI, COLIN | IN_CONSTR | 2013-05-07 | LA: MARK UTILITIES FOR FERMENTATION SCIENCES (BY 1/10/18?) | GENERAL | COMPLETE | 0 | 0 | 50.04 | 50.04
PJ0004512 | MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | PRINCI, COLIN | IN_CONSTR | 2013-05-07 | PL: MARK UTILITIES FOR FERMENTATION SCIENCES (BY 1/10/18?) | GENERAL | LONG_TERM | 0 | 0 | 3528.938 | 3528.938
PJ0004512 | MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | PRINCI, COLIN | IN_CONSTR | 2013-05-07 | PL: SUPPORT CONTRACTOR AT WINE & VITICULTURE INNOVATION CENTER | GENERAL | CLOSED | 0 | 0 | 293.814 | 293.814
PJ0004512 | MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | PRINCI, COLIN | IN_CONSTR | 2013-05-07 | SM: MJ: IN-HOUSE SUPPORT FOR WINE & VITICULTURE INNOVATION CTR | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0004512 Total | [7 empty] | 2000 | 0 | 3948.848 | 3948.848
PJ0004511 | SR 13/14: REPAIR CONDENSATE DAMAGE TO COLD BOXES 150-110 & 110A | LAMPMAN, GREG | CLOSED | 2013-05-08 | AD: JOC 13.031.039 MAINO | 150 | CLOSED | 17425.2603 | 0 | 17425.2603 | 17425.2603
PJ0004511 | SR 13/14: REPAIR CONDENSATE DAMAGE TO COLD BOXES 150-110 & 110A | LAMPMAN, GREG | CLOSED | 2013-05-08 | CP: PROJECT CONTINGENCY | 150 | CLOSED | 2525.71 | 0 | 0 | 0
PJ0004511 | SR 13/14: REPAIR CONDENSATE DAMAGE TO COLD BOXES 150-110 & 110A | LAMPMAN, GREG | CLOSED | 2013-05-08 | CPE: REMOVE AND RE-MOUNT FAN/COIL UNIT FOR NEW 4" THICK CEILING | 150 | CLOSED | 4806.6919 | 0 | 2413.515 | 2413.515
PJ0004511 | SR 13/14: REPAIR CONDENSATE DAMAGE TO COLD BOXES 150-110 & 110A | LAMPMAN, GREG | CLOSED | 2013-05-08 | EL REMOVE AND RE-INSTALL ELECTRICAL | 150 | CLOSED | 2640.6838 | 0 | 654.6 | 654.6
PJ0004511 | SR 13/14: REPAIR CONDENSATE DAMAGE TO COLD BOXES 150-110 & 110A | LAMPMAN, GREG | CLOSED | 2013-05-08 | IN: REPAIR CONDENSATE DAMAGE TO COLD BOXES 150-110 & 110A | 150 | CLOSED | 384.336 | 0 | 381.954 | 381.954
PJ0004511 Total | [7 empty] | 27782.682 | 0 | 20875.3293 | 20875.3293
PJ0004510 | REPLACE EXTERIOR DOOR SOUTH SIDE - BLD 4 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | CA: REMOVE AND REPLACE EXTERIOR DOOR | 004 | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004510 | REPLACE EXTERIOR DOOR SOUTH SIDE - BLD 4 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 0 | 0 | 0 | 0
PJ0004510 | REPLACE EXTERIOR DOOR SOUTH SIDE - BLD 4 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | LO: INSTALL NEW HARDWARE ON REPLACEMENT DOOR. | 004 | CLOSED | 0 | 0 | 120.925 | 120.925
PJ0004510 | REPLACE EXTERIOR DOOR SOUTH SIDE - BLD 4 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | PA: PAINT REPLACEMENT DOOR (NO LABOR) | 004 | CLOSED | 0 | 0 | 0 | 0
PJ0004510 Total | [7 empty] | 0 | 0 | 214.905 | 214.905
PJ0004509 | INVESTIGATE & REPAIR LEAK - BLD 70B ELECTRIC SHOP RESTRM (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-05-07 | CA: R&R PARTITIONS, SHELVING, AND FLOOR FOR PIPING REPAIR - 070B | 070B | CLOSED | 0 | 0 | 847.71 | 847.71
PJ0004509 | INVESTIGATE & REPAIR LEAK - BLD 70B ELECTRIC SHOP RESTRM (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-05-07 | CP: PROJECT CONTINGENCY | 070B | CLOSED | 0 | 0 | 0 | 0
PJ0004509 | INVESTIGATE & REPAIR LEAK - BLD 70B ELECTRIC SHOP RESTRM (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-05-07 | EL: REMOVE PERSONAL ITEMS AND SUPPLIES FROM SHOP RESTROOM 070B | 070B | CLOSED | 0 | 0 | 56.18 | 56.18
PJ0004509 | INVESTIGATE & REPAIR LEAK - BLD 70B ELECTRIC SHOP RESTRM (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-05-07 | PA: PAINT AS NEEDED, AFTER REPAIRS - ELEC. SHOP RESTROOM | 070B | CLOSED | 0 | 0 | 1088.34 | 1088.34
PJ0004509 | INVESTIGATE & REPAIR LEAK - BLD 70B ELECTRIC SHOP RESTRM (MAINT) | GONZALES, ALBERT M. | CLOSED | 2013-05-07 | PL: R&R FIXTURES FOR UNDER-FLOOR PIPING REPAIR -ELEC SHOP RESTRM | 070B | CLOSED | 0 | 0 | 571.305 | 571.305
PJ0004509 Total | [7 empty] | 0 | 0 | 2563.535 | 2563.535
PJ0004508 | SR 13/14: VIA CARTA WATER MAIN UPGRADE (CONSTRUCTION PHASE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | AD: JOC 13.028.044 MAINO | 048 | CLOSED | 349779.11 | 0 | 349779.11 | 349779.11
PJ0004508 | SR 13/14: VIA CARTA WATER MAIN UPGRADE (CONSTRUCTION PHASE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 0 | 0 | 0 | 0
PJ0004508 | SR 13/14: VIA CARTA WATER MAIN UPGRADE (CONSTRUCTION PHASE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | EL: MARK ELECTRICAL UTILITIES FOR POTHOLING | 048 | CLOSED | 224.72 | 0 | 252.81 | 252.81
PJ0004508 | SR 13/14: VIA CARTA WATER MAIN UPGRADE (CONSTRUCTION PHASE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | IN: SR 13/14: VIA CARTA WATER MAIN UPGRADE (CONSTRUCTION PHASE) | 048 | CLOSED | 1067.6 | 0 | 907.46 | 907.46
PJ0004508 | SR 13/14: VIA CARTA WATER MAIN UPGRADE (CONSTRUCTION PHASE) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-07 | PL: VIA CARTA WATER MAIN UPGRADE | 048 | CLOSED | 10477.65 | 0 | 11284.7798 | 11284.7798
PJ0004508 Total | [7 empty] | 361549.08 | 0 | 362224.1598 | 362224.1598
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | AD: BUEHLER AND BUEHLER | 061 | CLOSED | 1605 | 0 | 1605 | 1605
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | AD: ENGLEKIRK AND SABOL | 061 | CLOSED | 535 | 0 | 535 | 535
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | AD: VS ATHLETICS | 061 | CLOSED | 4339.92 | 0 | 5913.3015 | 5913.3015
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 16.43 | 0 | 0 | 0
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | IN: INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | 061 | CLOSED | 192.168 | 0 | 224.196 | 224.196
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | LA:GOAL NET POLES (NO LABOR) | 061 | CLOSED | 233.784 | 0 | 0 | 0
PJ0004507 | INSTALLATION OF GOAL POST NET SYSTEM - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-06 | MO: TRANSPORT GOAL POST POLES TO SPANOS STADIUM | 061 | CLOSED | 129.6 | 0 | 60.36 | 60.36
PJ0004507 Total | [7 empty] | 7051.902 | 0 | 8337.8575 | 8337.8575
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: ADT WINDOW TINTING | 035 | CLOSED | 310.3 | 0 | 310.3 | 310.3
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: FLOOR CONNECTION | 035 | CLOSED | 4987.9976 | 0 | 4931.5444 | 4931.5444
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 2594.75 | 0 | 2582.98 | 2582.98
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: SAN LUIS GLASS | 035 | CLOSED | 3210 | 0 | 3058.7341 | 3058.7341
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 770.4 | 0 | 770.4 | 770.4
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CA: INSTALL WHITE BOARDS, 1 IN ROOM 511 & 1 IN 510B - BLDG 035 | 035 | CLOSED | 1107.5984 | 0 | 1367.85 | 1367.85
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 749.48 | 0 | 0 | 0
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CPE: LIBRARY 510 REDUCTING AND REDISTRIBUTION | 035 | CLOSED | 14993.939 | 0 | 4098.138 | 4098.138
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | EL:REMOVE ELECTRICAL FOR WALL DEMO 35-510A/B | 035 | CLOSED | 2100.6814 | 0 | 1041.384 | 1041.384
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | IN: REMODEL ROOMS ROOMS 510A/B - LIBRARY BLDG 035 | 035 | CLOSED | 192.168 | 0 | 128.112 | 128.112
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | LO:ORDER HARDWARE AND INSTALL LOCKS ON NEW DOORS 35-510A | 035 | CLOSED | 3858.2958 | 0 | 3226.476 | 3226.476
PJ0004506 | COMBINE ROOMS ROOMS 510A & B - LIBRARY BLDG 035 | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | PA:PATCH AND PAINT REMODEL IN 35-510A | 035 | CLOSED | 1441.4426 | 0 | 1762.332 | 1762.332
PJ0004506 Total | [7 empty] | 36317.0529 | 0 | 23278.2505 | 23278.2505
PJ0004505 | DESIGN LANDSCAPING AND WALKWAY BEHIND BLDG 33 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | AD: BUEHLER AND BUEHLER | 033 | CLOSED | 6420 | 0 | 6420 | 6420
PJ0004505 | DESIGN LANDSCAPING AND WALKWAY BEHIND BLDG 33 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | AD: THE WALLACE GROUP | 033 | CLOSED | 18190 | 0 | 17183.9646 | 17183.9646
PJ0004505 | DESIGN LANDSCAPING AND WALKWAY BEHIND BLDG 33 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0004505 | DESIGN LANDSCAPING AND WALKWAY BEHIND BLDG 33 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 033 | CLOSED | 0 | 0 | 9.6 | 9.6
PJ0004505 | DESIGN LANDSCAPING AND WALKWAY BEHIND BLDG 33 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | IN: DESIGN LANDSCAPING AND WALKWAY BEHIND BLDG 33 | 033 | CLOSED | 192.168 | 0 | 64.056 | 64.056
PJ0004505 Total | [7 empty] | 24802.168 | 0 | 23677.6206 | 23677.6206
PJ0004504 | RELOCATE LIBRARY SHELVING - BLD 35 3RD TO 2ND FLR | MAY, TOM | CLOSED | 2013-04-30 | AD: TEMPLE BUILDERS | 035 | CLOSED | 1981.105 | 0 | 1981.0943 | 1981.0943
PJ0004504 | RELOCATE LIBRARY SHELVING - BLD 35 3RD TO 2ND FLR | MAY, TOM | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 204.52 | 0 | 0 | 0
PJ0004504 | RELOCATE LIBRARY SHELVING - BLD 35 3RD TO 2ND FLR | MAY, TOM | CLOSED | 2013-04-30 | IN: RELOCATE LIBRARY SHELVING - BLD 35 3RD TO 2ND FLR | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004504 Total | [7 empty] | 2249.681 | 0 | 2045.1503 | 2045.1503
PJ0004502 | REMOVE FENCING, INSTALL WINDSCREENS & LOGOS - TENNIS CRTS - 042S | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-01 | AD: JOC 13.027.012.01 PUB | 042S | CLOSED | 58909.8237 | 0 | 58803.669 | 58803.669
PJ0004502 | REMOVE FENCING, INSTALL WINDSCREENS & LOGOS - TENNIS CRTS - 042S | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-01 | CP: PROJECT CONTINGENCY | 042S | CLOSED | 5955.04 | 0 | 0 | 0
PJ0004502 | REMOVE FENCING, INSTALL WINDSCREENS & LOGOS - TENNIS CRTS - 042S | KUENTZEL, DOUGLAS A. | CLOSED | 2013-05-01 | IN: REMOVE FENCING, INSTALL WINDSCREENS & LOGOS - TENNIS CRTS | 042S | CLOSED | 640.56 | 0 | 416.364 | 416.364
PJ0004502 Total | [7 empty] | 65505.4237 | 0 | 59220.033 | 59220.033
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | AD: RICK TEIXEIRA | 114 | CLOSED | 0 | 0 | 3210 | 3210
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | CA:YOSEMITE REPIPE SUPPORT | 114 | CLOSED | 0 | 0 | 910.968 | 910.968
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 85742.24 | 0 | 0 | 0
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | CPE:SUPPORT FOR YOSEMITE REPIPE | 114 | CLOSED | 0 | 0 | 249.744 | 249.744
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | EL: SUPPORT FOR MJ0053 YOSEMITE REPIPE | 114 | CLOSED | 0 | 0 | 5922.012 | 5922.012
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | ES: SUPPORT FOR MJ0053 YOSEMITE REPIPE | 114 | CLOSED | 0 | 0 | 47329.7927 | 47329.7927
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | IN: MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | 114 | CLOSED | 0 | 0 | 0 | 0
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | LA: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | 114 | CLOSED | 0 | 0 | 8702.0742 | 8702.0742
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | LO: CHANGE CORES AT YOSEMITE TOWERS 3 AND 4 FOR SUMMER PROJECTS | 114 | CLOSED | 0 | 0 | 87.066 | 87.066
PJ0004501 | MJ: SUPPORT FOR RE-PIPE PROJECT - YOSEMITE HALL | KOLEGRAFF, KENNETH | CLOSED | 2013-04-30 | PL: SUPPORT FOR MJ0053 YOSEMITE REPIPE | 114 | CLOSED | 0 | 0 | 19330.704 | 19330.704
PJ0004501 Total | [7 empty] | 85742.24 | 0 | 85742.3609 | 85742.3609
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: ASAP REPROGRAPHICS | RESIDENCE | CLOSED | 0 | 0 | 52.49 | 52.49
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: JOC 13.028.012 MAINO | RESIDENCE | CLOSED | 131880.62 | 0 | 128490.89 | 128490.89
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 4652 | 0 | 4601 | 4601
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | EL:WORK WITH JOC CONTRACTOR WITH CSD KITCHEN REMODEL | RESIDENCE | CLOSED | 1000.002 | 0 | 887.06 | 887.06
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | IN: M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | RESIDENCE | CLOSED | 533.8 | 0 | 587.18 | 587.18
PJ0004500 | M&R HOUS 13/14: REMODEL CSD KITCHENS - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | PL:WORK WITH JOC CONTRACTOR ON CSD KITCHEN REMODEL | RESIDENCE | CLOSED | 7632.9557 | 0 | 10658.485 | 10658.485
PJ0004500 Total | [7 empty] | 145699.3777 | 0 | 145277.105 | 145277.105
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: APC CONTRACTORS | RESIDENCE | CLOSED | 5000 | 0 | 4536.89 | 4536.89
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: BENCHMARK | RESIDENCE | CLOSED | 0 | 0 | 1951.13 | 1951.13
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: J.L. FASULO DRYWALL | RESIDENCE | CLOSED | 1500 | 0 | 4983 | 4983
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 2750 | 0 | 2800 | 2800
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: PHIL'S CUSTOM WOODWORKING | RESIDENCE | CLOSED | 2500 | 0 | 4610 | 4610
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: SAN LUIS GLASS | RESIDENCE | CLOSED | 5000 | 0 | 4238.13 | 4238.13
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: SANTA MARIA ACOUSTICAL | RESIDENCE | CLOSED | 2279 | 0 | 2279 | 2279
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CA: SANTA LUCIA VENDING AREA | RESIDENCE | CLOSED | 5542.027 | 0 | 4710.7925 | 4710.7925
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | RESIDENCE | CLOSED | 0 | 0 | 15 | 15
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | EL: SANTA LUCIA VENDING AREA | RESIDENCE | CLOSED | 2375.8502 | 0 | 1547.98 | 1547.98
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | ES: VENDING AREA PROJECT SUPPORT - SANTA LUCIA | RESIDENCE | CLOSED | 2237.2817 | 0 | 838.645 | 838.645
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | IN: M&R HOUS 13/14: RETROFIT VENDING AREA - SOUTH MOUNTAIN | RESIDENCE | CLOSED | 213.52 | 0 | 133.45 | 133.45
PJ0004498 | M&R HOUS 13/14: RETROFIT VENDING AREA - SANTA LUCIA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | PA: | RESIDENCE | CLOSED | 2186.6267 | 0 | 742.05 | 742.05
PJ0004498 Total | [7 empty] | 31584.3056 | 0 | 33386.0675 | 33386.0675
PJ0004497 | M&R HOUS 13/14: INSTALL SHELVES IN RESTROOMS - CERRO VISTA | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 0 | 0 | 0 | 0
PJ0004497 | M&R HOUS 13/14: INSTALL SHELVES IN RESTROOMS - CERRO VISTA | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-30 | PCV CA: INSTALL SHELVES IN RESTROOMS AT CERRO VISTA | 170 | CLOSED | 9598 | 0 | 6721.055 | 6721.055
PJ0004497 Total | [7 empty] | 9598 | 0 | 6721.055 | 6721.055
PJ0004496 | M&R HOUS 13/14: REPLACE EXTERIOR SIGNAGE - CERRO VISTA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: SPECTRUM COLOR IMAGES | 170 | CLOSED | 14445 | 0 | 14045.9328 | 14045.9328
PJ0004496 | M&R HOUS 13/14: REPLACE EXTERIOR SIGNAGE - CERRO VISTA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 1688.86 | 0 | 0 | 0
PJ0004496 | M&R HOUS 13/14: REPLACE EXTERIOR SIGNAGE - CERRO VISTA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | IN: M&R HOUS 13/14: REPLACE EXTERIOR SIGNAGE - CERRO VISTA | 170 | CLOSED | 256.224 | 0 | 134.7 | 134.7
PJ0004496 | M&R HOUS 13/14: REPLACE EXTERIOR SIGNAGE - CERRO VISTA | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | PCV CA: ASSIST CONTRACTOR WITH SIGNAGE INSTALL | 170 | CLOSED | 802.527 | 0 | 824.826 | 824.826
PJ0004496 Total | [7 empty] | 17192.611 | 0 | 15005.4588 | 15005.4588
PJ0004495 | M&R HOUS 13/14: REPLACE SHOWER TILE - FREMONT | LAMPMAN, GREG | CLOSED | 2013-04-30 | AD: JOC 13.028.001 MAINO | 109 | CLOSED | 86332.12 | 0 | 82494.17 | 82494.17
PJ0004495 | M&R HOUS 13/14: REPLACE SHOWER TILE - FREMONT | LAMPMAN, GREG | CLOSED | 2013-04-30 | AD: MCKENNA ENVIRONMENTAL | 109 | CLOSED | 6276.62 | 0 | 2386 | 2386
PJ0004495 | M&R HOUS 13/14: REPLACE SHOWER TILE - FREMONT | LAMPMAN, GREG | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 109 | CLOSED | 6571.14 | 0 | 0 | 0
PJ0004495 | M&R HOUS 13/14: REPLACE SHOWER TILE - FREMONT | LAMPMAN, GREG | CLOSED | 2013-04-30 | IN: M&R HOUS 13/14: REPLACE SHOWER TILE - FREMONT | 109 | CLOSED | 1035.572 | 0 | 213.52 | 213.52
PJ0004495 Total | [7 empty] | 100215.452 | 0 | 85093.69 | 85093.69
PJ0004494 | M&R HOUS 13/14: INSTALL BACKFLOW FOR IRRIGATION - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: GARCIA AND SONS | RESIDENCE | CLOSED | 5350 | 0 | 4490.79 | 4490.79
PJ0004494 | M&R HOUS 13/14: INSTALL BACKFLOW FOR IRRIGATION - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 3383.75 | 0 | 0 | 0
PJ0004494 | M&R HOUS 13/14: INSTALL BACKFLOW FOR IRRIGATION - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | EL: UTILITY LOCATING FOR RED BRICK BACK FLOWS | RESIDENCE | CLOSED | 257.712 | 0 | 64.428 | 64.428
PJ0004494 | M&R HOUS 13/14: INSTALL BACKFLOW FOR IRRIGATION - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | EO: EXCAVATE SEWER FOR RED BRICK DORM BACK FLOWS | RESIDENCE | CLOSED | 821.952 | 0 | 1258.614 | 1258.614
PJ0004494 | M&R HOUS 13/14: INSTALL BACKFLOW FOR IRRIGATION - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | IN: MH4494 INST BACKFLOW FOR IRRIGATION - S. MOUNTAIN | RESIDENCE | CLOSED | 282.576 | 0 | 141.288 | 141.288
PJ0004494 | M&R HOUS 13/14: INSTALL BACKFLOW FOR IRRIGATION - SOUTH MOUNTAIN | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | PL: INSTALL BACKFLOWS AT SELECT LOCATIONS | RESIDENCE | CLOSED | 36917.5913 | 0 | 8889.8983 | 8889.8983
PJ0004494 Total | [7 empty] | 47013.5813 | 0 | 14845.0183 | 14845.0183
PJ0004493 | M&R HOUS 13/14: CLEAN / MODIFY SHOWER DUCTS - SEQUOIA | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | AD: JOC 13.028.049 MAINO | 106 | CLOSED | 78831.9 | 0 | 72724.62 | 72724.62
PJ0004493 | M&R HOUS 13/14: CLEAN / MODIFY SHOWER DUCTS - SEQUOIA | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | AD: MCKENNA ENVIRONMENTAL | 106 | CLOSED | 3500 | 0 | 4460 | 4460
PJ0004493 | M&R HOUS 13/14: CLEAN / MODIFY SHOWER DUCTS - SEQUOIA | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 106 | CLOSED | 0 | 0 | 0 | 0
PJ0004493 | M&R HOUS 13/14: CLEAN / MODIFY SHOWER DUCTS - SEQUOIA | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | IN: M&R HOUS 13/14: CLEAN / MODIFY SHOWER DUCTS - SANTA LUCIA | 106 | CLOSED | 320.28 | 0 | 186.83 | 186.83
PJ0004493 Total | [7 empty] | 82652.18 | 0 | 77371.45 | 77371.45
PJ0004492 | M&R HOUS 13/14: REPAIR / REPLACE CONCRETE WALKS | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | AD: JOC 13.028.034 MAINO | RESIDENCE | CLOSED | 119466.2 | 0 | 119091.37 | 119091.37
PJ0004492 | M&R HOUS 13/14: REPAIR / REPLACE CONCRETE WALKS | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004492 | M&R HOUS 13/14: REPAIR / REPLACE CONCRETE WALKS | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | IN: M&R HOUS 13/14: REPAIR / REPLACE CONCRETE WALKS | RESIDENCE | CLOSED | 533.8 | 0 | 533.8 | 533.8
PJ0004492 | M&R HOUS 13/14: REPAIR / REPLACE CONCRETE WALKS | GONZALES, ALBERT M. | CLOSED | 2013-04-30 | LA: REPAIR DAMAGES FROM CONCRETE WORK IN DORM AREAS | RESIDENCE | CLOSED | 2451.447 | 0 | 2804.5318 | 2804.5318
PJ0004492 Total | [7 empty] | 122451.447 | 0 | 122429.7018 | 122429.7018
PJ0004491 | M&R HOUS 13/14: REPLACE TRANSFORMER & DISTRIBUTION SYS - WHITNEY | GRIFFIN, PATRICK E. | CLOSED | 2013-04-30 | AD: PLCS PLUS | 103 | CLOSED | 0 | 0 | 360 | 360
PJ0004491 | M&R HOUS 13/14: REPLACE TRANSFORMER & DISTRIBUTION SYS - WHITNEY | GRIFFIN, PATRICK E. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 103 | CLOSED | 0 | 0 | 0 | 0
PJ0004491 | M&R HOUS 13/14: REPLACE TRANSFORMER & DISTRIBUTION SYS - WHITNEY | GRIFFIN, PATRICK E. | CLOSED | 2013-04-30 | EL:REPLACE TRANSFORMER AT WHITNEY | 103 | CLOSED | 16001.7104 | 0 | 17638.0416 | 17638.0416
PJ0004491 | M&R HOUS 13/14: REPLACE TRANSFORMER & DISTRIBUTION SYS - WHITNEY | GRIFFIN, PATRICK E. | CLOSED | 2013-04-30 | IN: REPLACE TRANSFORMER & DISTRIBUTION SYSTEM - 103 | 103 | CLOSED | 320.28 | 0 | 213.52 | 213.52
PJ0004491 Total | [7 empty] | 16321.9904 | 0 | 18211.5616 | 18211.5616
PJ0004490 | M&R HOUS 13/14: CLEAN VENTILATION SYSTEM -SIERRA MADRE - TWR 3 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | AD: GOSS ENGINEERING | 113 | CLOSED | 5000 | 0 | 3310 | 3310
PJ0004490 | M&R HOUS 13/14: CLEAN VENTILATION SYSTEM -SIERRA MADRE - TWR 3 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | AD: JOC 13.028.048 MAINO | 113 | CLOSED | 86657.5 | 0 | 63851.54 | 63851.54
PJ0004490 | M&R HOUS 13/14: CLEAN VENTILATION SYSTEM -SIERRA MADRE - TWR 3 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | CA: REMOVE PORTIONS OF CEILING & REPLACE WHEN PROJECT IS COMPLET | 113 | CLOSED | 2614.5236 | 0 | 701.295 | 701.295
PJ0004490 | M&R HOUS 13/14: CLEAN VENTILATION SYSTEM -SIERRA MADRE - TWR 3 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 0 | 0 | 0 | 0
PJ0004490 | M&R HOUS 13/14: CLEAN VENTILATION SYSTEM -SIERRA MADRE - TWR 3 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | EL:PROVIDE CONSTRUCTION SUPPORT FOR ELECTRICAL CONTRACTOR | 113 | CLOSED | 7751.1386 | 0 | 84.27 | 84.27
PJ0004490 | M&R HOUS 13/14: CLEAN VENTILATION SYSTEM -SIERRA MADRE - TWR 3 | MOLLAN, CHERYL L. | CLOSED | 2013-04-30 | IN: CLEAN VENTILATION SYSTEM -SANTA LUCIA ALL TOWERS | 113 | CLOSED | 437.1822 | 0 | 346.97 | 346.97
PJ0004490 Total | [7 empty] | 102460.3444 | 0 | 68294.075 | 68294.075
PJ0004489 | M&R HOUS 13/14: RE-ROOF W/SOLAR PANELS & LOWER ROOFS - BLDG 106 | MAY, TOM | CLOSED | 2013-04-30 | AD: JOC 13.028.011 MAINO | 106 | CLOSED | 279206.32 | 0 | 279206.32 | 279206.32
PJ0004489 | M&R HOUS 13/14: RE-ROOF W/SOLAR PANELS & LOWER ROOFS - BLDG 106 | MAY, TOM | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | 106 | CLOSED | 0 | 0 | 0 | 0
PJ0004489 | M&R HOUS 13/14: RE-ROOF W/SOLAR PANELS & LOWER ROOFS - BLDG 106 | MAY, TOM | CLOSED | 2013-04-30 | IN: RE-ROOF W/SOLAR PANELS & LOWER ROOFS - BLDG 106 | 106 | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0004489 Total | [7 empty] | 279419.84 | 0 | 279419.84 | 279419.84
PJ0004488 | M&R HOUS 13/14: FACILITY CONDITION ASSESSMENT | NEEL, JOEL | CLOSED | 2013-04-30 | AD: ISES CORPORATION | RESIDENCE | CLOSED | 37663.89 | 0 | 37663.89 | 37663.89
PJ0004488 | M&R HOUS 13/14: FACILITY CONDITION ASSESSMENT | NEEL, JOEL | CLOSED | 2013-04-30 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004488 | M&R HOUS 13/14: FACILITY CONDITION ASSESSMENT | NEEL, JOEL | CLOSED | 2013-04-30 | ES: SUPPORT FOR ASSESSMENT CONSULTANT AT HOUSING FACILITIES | RESIDENCE | CLOSED | 1352.78 | 0 | 1199.625 | 1199.625
PJ0004488 Total | [7 empty] | 39016.67 | 0 | 38863.515 | 38863.515
PJ0004487 | PANIC ALARM AT CHILDREN'S CENTER - BLD 133 RM 118A | MOLLAN, CHERYL L. | CLOSED | 2013-04-25 | AD: CAME SECURITY | 133 | CLOSED | 1738.75 | 0 | 0 | 0
PJ0004487 | PANIC ALARM AT CHILDREN'S CENTER - BLD 133 RM 118A | MOLLAN, CHERYL L. | CLOSED | 2013-04-25 | ANTS: PANIC ALARM AT CHILDREN'S CENTER - BLD 133 RM 118A | 133 | CLOSED | 96.096 | 0 | 24.024 | 24.024
PJ0004487 | PANIC ALARM AT CHILDREN'S CENTER - BLD 133 RM 118A | MOLLAN, CHERYL L. | CLOSED | 2013-04-25 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 189.89 | 0 | 0 | 0
PJ0004487 | PANIC ALARM AT CHILDREN'S CENTER - BLD 133 RM 118A | MOLLAN, CHERYL L. | CLOSED | 2013-04-25 | IN: PANIC ALARM AT CHILDREN'S CENTER - BLD 133 RM 118A | 133 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004487 Total | [7 empty] | 2088.792 | 0 | 88.08 | 88.08
PJ0004486 | SR 12/13:STRUCTURAL ASSESSMENT - POLY CANYON PED. BRIDGE(NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-04-26 | AD: BUEHLER AND BUEHLER | GENERAL | CLOSED | 12500 | 0 | 12500 | 12500
PJ0004486 | SR 12/13:STRUCTURAL ASSESSMENT - POLY CANYON PED. BRIDGE(NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-04-26 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004486 Total | [7 empty] | 12500 | 0 | 12500 | 12500
PJ0004484 | INSTALL PADDING ALONG NEW SOUTH BLEACHERS AT SPANOS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-22 | AD: HUMPHRYS/COVER SPORTS | 061 | CLOSED | 8042.3875 | 0 | 8604.6404 | 8604.6404
PJ0004484 | INSTALL PADDING ALONG NEW SOUTH BLEACHERS AT SPANOS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-22 | CA: INSTALL CONDUIT PIPING FOR PADDING SUSPENSION | 061 | CLOSED | 1389.312 | 0 | 2129.418 | 2129.418
PJ0004484 | INSTALL PADDING ALONG NEW SOUTH BLEACHERS AT SPANOS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-22 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 985.98 | 0 | 0 | 0
PJ0004484 | INSTALL PADDING ALONG NEW SOUTH BLEACHERS AT SPANOS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-22 | EL: SUPPLY CONDUIT AND CLAMPS FOR CA SHOP | 061 | CLOSED | 300 | 0 | 144.36 | 144.36
PJ0004484 | INSTALL PADDING ALONG NEW SOUTH BLEACHERS AT SPANOS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-22 | IN: INSTALL PADDING ALONG NEW SOUTH BLEACHERS AT SPANOS - BLD 61 | 061 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004484 Total | [7 empty] | 10845.7915 | 0 | 11006.5304 | 11006.5304
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: ASAP REPROGRAPHICS | 056 | CLOSED | 0 | 0 | 61.88 | 61.88
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: EARTH SYSTEMS PACIFIC | 056 | CLOSED | 6866.2756 | 0 | 5633.55 | 5633.55
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: ENGLEKIRK AND SABOL | 056 | CLOSED | 722.25 | 0 | 722.25 | 722.25
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: JOC 15.035.007 MAINO | 056 | CLOSED | 265854.3186 | 0 | 248461.9822 | 248461.9822
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 056 | CLOSED | 5082.5 | 0 | 5082.5 | 5082.5
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: NORTH COAST ENGINEERING | 056 | CLOSED | 3413.3 | 0 | 3413.3 | 3413.3
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: OMNI DESIGN | 056 | CLOSED | 16916.7 | 0 | 16916.7 | 16916.7
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: ONTRAC SHIPPING | 056 | CLOSED | 0 | 0 | 32.29 | 32.29
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: OVERHEAD FEES FOR IN-HOUSE WORK - NOV & DEC 2015, JAN 2016 | 056 | CLOSED | 0 | 0 | 1240.49 | 1240.49
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | AD: STATE FIRE MARSHAL | 056 | CLOSED | 0 | 0 | 922.0404 | 922.0404
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | CP: PROJECT CONTINGENCY | 056 | CLOSED | 12488.59 | 0 | 0 | 0
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | EL: SUPPLY 1 OUTLET & LIGHT FIXTURES - NEW SWINE UNIT BARN 056 | 056 | CLOSED | 9769.9714 | 0 | 1414.416 | 1414.416
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | IN: REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | 056 | CLOSED | 847.728 | 0 | 971.355 | 971.355
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | PL: INSTALL NEW WATER LINES TO THE NEW SWINE BARN | 056 | CLOSED | 4599.3893 | 0 | 4812.8906 | 4812.8906
PJ0004483 | REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | LAMPMAN, GREG | CLOSED | 2013-04-22 | PM: REPLACE EXISTING BOAR/SOW BARN - SWINE UNIT | 056 | CLOSED | 0 | 0 | 0 | 0
PJ0004483 Total | [7 empty] | 326561.0228 | 0 | 289685.6442 | 289685.6442
PJ0004481 | RECEPTION DESK MODIFICATIONS FOR ERGONOMICS - BLDG 27 -173 | WILWAND, MARK | CLOSED | 2013-04-11 | AD: FURNITURE INSTALLATION TEAM, INC. | 027 | CLOSED | 292.11 | 0 | 292.11 | 292.11
PJ0004481 | RECEPTION DESK MODIFICATIONS FOR ERGONOMICS - BLDG 27 -173 | WILWAND, MARK | CLOSED | 2013-04-11 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 68.99 | 0 | 0 | 0
PJ0004481 | RECEPTION DESK MODIFICATIONS FOR ERGONOMICS - BLDG 27 -173 | WILWAND, MARK | CLOSED | 2013-04-11 | EL: MOVE POWER AT ELEC./DATA POST - BLDG. 27, RM 173 | 027 | CLOSED | 269.664 | 0 | 448.536 | 448.536
PJ0004481 | RECEPTION DESK MODIFICATIONS FOR ERGONOMICS - BLDG 27 -173 | WILWAND, MARK | CLOSED | 2013-04-11 | IN: RECEPTION DESK MODIFICATIONS FOR ERGONOMICS - BLDG 27 -173 | 027 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004481 Total | [7 empty] | 758.876 | 0 | 868.758 | 868.758
PJ0004479 | M&R ASI 13/14: FACILITY CONDITION ASSESSMENT UU 65 | NEEL, JOEL | CLOSED | 2013-04-16 | AD: ISES CORPORTIONS | 065 | CLOSED | 18141.7216 | 0 | 18141.7216 | 18141.7216
PJ0004479 | M&R ASI 13/14: FACILITY CONDITION ASSESSMENT UU 65 | NEEL, JOEL | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1857.88 | 0 | 0 | 0
PJ0004479 | M&R ASI 13/14: FACILITY CONDITION ASSESSMENT UU 65 | NEEL, JOEL | CLOSED | 2013-04-16 | ES: SUPPORT FOR ASSESSMENT CONSULTANT AT UU 065 | 065 | CLOSED | 437.052 | 0 | 319.224 | 319.224
PJ0004479 Total | [7 empty] | 20436.6536 | 0 | 18460.9456 | 18460.9456
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: BOWEN ENG | 065 | OPEN | 19492.4575 | 3871.26 | 15621.1975 | 19492.4575
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: FASULO DRYWALL | 065 | OPEN | 390.55 | 0 | 390.55 | 390.55
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: JOC | 065 | OPEN | 115913.635 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: JOC 14.033.011 MAINO | 065 | OPEN | 29036.7291 | 0 | 27112.7942 | 27112.7942
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: MCKENNA ENVIRONMENTAL | 065 | OPEN | 10700 | 0 | 5307.2 | 5307.2
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: ONTRAC, UPS SHIPPING & ASAP REPROGRAPHICS | 065 | OPEN | 0 | 0 | 201.4061 | 201.4061
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: REPUBLIC ELEVATOR | 065 | OPEN | 61897.36 | 43328.152 | 18569.208 | 61897.36
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: SANTA MARIA ACOUSTICAL | 065 | OPEN | 834.6 | 0 | 834.6 | 834.6
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: STATE FIRE MARSHAL | 065 | OPEN | 7803.2532 | 0 | 7951.8976 | 7951.8976
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | AD: TYCO SIMPLEX GRINNELL | 065 | OPEN | 337312.1607 | 14859.411 | 305070.589 | 319930
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | ANTS: | 065 | OPEN | 677.76 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | CA: | 065 | CLOSED | 6706.38 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | CP: PROJECT CONTINGENCY | 065 | OPEN | 42435.65 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | EH&S: | 065 | OPEN | 377.472 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | EL:CONTRACTOR SUPPORT, PROJECT PLAN REVIEW, UU VOICE EVAC | 065 | LONG_TERM | 1417.416 | 0 | 962.856 | 962.856
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | ES: | 065 | OPEN | 262.656 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | IN: M&R UU 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | 065 | ASSIGNED | 1836.744 | 0 | 388.542 | 388.542
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | LO: | 065 | ASSIGNED | 899.2728 | 0 | 243.696 | 243.696
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | PA: PAINTING FOR FIRE ALARM UPGRADE PROJECT - BLDG 065 | 065 | ASSIGNED | 14200.68 | 0 | 5726.232 | 5726.232
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | PM: M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | 065 | OPEN | 0 | 0 | 0 | 0
PJ0004478 | M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | DILLON, JEFFREY | IN_CONSTR | 2013-04-16 | SM: M&R ASI 13/14: FIRE ALARM SYSTEM UPGRADE WITH VOICE EVAC | 065 | OPEN | 0 | 0 | 0 | 0
PJ0004478 Total | [7 empty] | 652194.7763 | 62058.823 | 388380.7684 | 450439.5914
PJ0004477 | M&R ASI 13/14: FACILITY MASTER PLAN STUDY - UU 65 | NEEL, JOEL | CLOSED | 2013-04-16 | AD: BRAILSFORD & DUNLAVEY | 065 | CLOSED | 373046.084 | 0 | 370929.7845 | 370929.7845
PJ0004477 | M&R ASI 13/14: FACILITY MASTER PLAN STUDY - UU 65 | NEEL, JOEL | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 2669.01 | 0 | 0 | 0
PJ0004477 Total | [7 empty] | 375715.094 | 0 | 370929.7845 | 370929.7845
PJ0004476 | M&R ASI 13/14: EVALUATE ROOFING SYSTEM - UU 65 205 CHUMASH | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | AD: ASAP REPROGRAPHICS | 065 | CLOSED | 0 | 0 | 8.292 | 8.292
PJ0004476 | M&R ASI 13/14: EVALUATE ROOFING SYSTEM - UU 65 205 CHUMASH | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | AD: QUAGLINO ROOFING | 065 | CLOSED | 3477.5 | 0 | 3477.5 | 3477.5
PJ0004476 | M&R ASI 13/14: EVALUATE ROOFING SYSTEM - UU 65 205 CHUMASH | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 354.16 | 0 | 0 | 0
PJ0004476 | M&R ASI 13/14: EVALUATE ROOFING SYSTEM - UU 65 205 CHUMASH | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | IN: M&R UU 13/14: EVALUATE ROOFING SYSTEM - UU 65 205 CHUMASH | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004476 Total | [7 empty] | 3895.716 | 0 | 3549.848 | 3549.848
PJ0004475 | M&R ASI 13/14: FLOOR REFINISHING - UU 205 CHUMASH | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | AD: MCWIL SPORTS SURFACES, INC. | 065 | CLOSED | 6453.17 | 0 | 6453.17 | 6453.17
PJ0004475 | M&R ASI 13/14: FLOOR REFINISHING - UU 205 CHUMASH | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 511.02 | 0 | 0 | 0
PJ0004475 | M&R ASI 13/14: FLOOR REFINISHING - UU 205 CHUMASH | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 065 | CLOSED | 0 | 0 | 33.6 | 33.6
PJ0004475 | M&R ASI 13/14: FLOOR REFINISHING - UU 205 CHUMASH | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | IN: M&R UU 13/14: FLOOR REFINISHING - UU 205 CHUMASH | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004475 Total | [7 empty] | 7028.246 | 0 | 6550.826 | 6550.826
PJ0004474 | M&R ASI 13/14: UPGRADE SOUND SYSTEM - UU 220 | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | AD: MORELAND THOMPSON, INC | 065 | CLOSED | 5216.25 | 0 | 5216.25 | 5216.25
PJ0004474 | M&R ASI 13/14: UPGRADE SOUND SYSTEM - UU 220 | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | AD: PRO SOUND | 065 | CLOSED | 53500 | 0 | 51664.0619 | 51664.0619
PJ0004474 | M&R ASI 13/14: UPGRADE SOUND SYSTEM - UU 220 | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | AD: SANTA MARIA ACOUSTICAL | 065 | CLOSED | 3231.4 | 0 | 3231.4 | 3231.4
PJ0004474 | M&R ASI 13/14: UPGRADE SOUND SYSTEM - UU 220 | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 588.56 | 0 | 0 | 0
PJ0004474 | M&R ASI 13/14: UPGRADE SOUND SYSTEM - UU 220 | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | IN: M&R UU 13/14: UPGRADE SOUND SYSTEM - UU 220 | 065 | CLOSED | 192.168 | 0 | 275.988 | 275.988
PJ0004474 | M&R ASI 13/14: UPGRADE SOUND SYSTEM - UU 220 | MOLLAN, CHERYL L. | CLOSED | 2013-04-16 | MO: REMOVE SCAFFOLDING FROM UU PLAZA | 065 | CLOSED | 134.064 | 0 | 11.268 | 11.268
PJ0004474 Total | [7 empty] | 62862.442 | 0 | 60398.9679 | 60398.9679
PJ0004473 | SR 13/14: CHILLER IMPROVEMENTS FOR TES SYSTEM - BLD 40 | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | AD: JOC 13.029.011 MAINO | 040 | CLOSED | 38374.46 | 0 | 38374.46 | 38374.46
PJ0004473 | SR 13/14: CHILLER IMPROVEMENTS FOR TES SYSTEM - BLD 40 | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | AD: SIEMENS | 040 | CLOSED | 13493.77 | 0 | 12611 | 12611
PJ0004473 | SR 13/14: CHILLER IMPROVEMENTS FOR TES SYSTEM - BLD 40 | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 1355.78 | 0 | 0 | 0
PJ0004473 | SR 13/14: CHILLER IMPROVEMENTS FOR TES SYSTEM - BLD 40 | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | CPE: SUPPORT FOR CHILLED WATER BY-PASS PIPING | 040 | CLOSED | 0 | 0 | 555.38 | 555.38
PJ0004473 | SR 13/14: CHILLER IMPROVEMENTS FOR TES SYSTEM - BLD 40 | GONZALES, ALBERT M. | CLOSED | 2013-04-16 | IN: SR 13/14: CHILLER IMPROVEMENTS FOR TES SYSTEM - BLD 40 | 040 | CLOSED | 64.056 | 0 | 53.38 | 53.38
PJ0004473 Total | [7 empty] | 53288.066 | 0 | 51594.22 | 51594.22
PJ0004470 | SR 12/13: DESIGN TO UPSIZE FIRE HYDRANT LINE TO OH - BLDG 48 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-16 | AD: WALLACE GROUP | 048 | CLOSED | 17950 | 0 | 10199.15 | 10199.15
PJ0004470 | SR 12/13: DESIGN TO UPSIZE FIRE HYDRANT LINE TO OH - BLDG 48 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 0 | 0 | 0 | 0
PJ0004470 Total | [7 empty] | 17950 | 0 | 10199.15 | 10199.15
PJ0004469 | M&R H/C 13/14: FACILITY CONDITION ASSESSMENT - HEALTH CENTER 027 | NEEL, JOEL | CLOSED | 2013-04-16 | AD: ISIS CORPORATION | 027 | CLOSED | 5248.992 | 0 | 5248.992 | 5248.992
PJ0004469 | M&R H/C 13/14: FACILITY CONDITION ASSESSMENT - HEALTH CENTER 027 | NEEL, JOEL | CLOSED | 2013-04-16 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 549.87 | 0 | 0 | 0
PJ0004469 | M&R H/C 13/14: FACILITY CONDITION ASSESSMENT - HEALTH CENTER 027 | NEEL, JOEL | CLOSED | 2013-04-16 | ES: SUPPORT FOR ASSESSMENT CONSULTANT AT HEALTH CENTER 027 | 027 | CLOSED | 249.744 | 0 | 249.744 | 249.744
PJ0004469 Total | [7 empty] | 6048.606 | 0 | 5498.736 | 5498.736
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | AD: FLOOR CONNECTION | 042 | CLOSED | 2285.3274 | 0 | 2285.3274 | 2285.3274
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 042 | CLOSED | 5168.1 | 0 | 5168.1 | 5168.1
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | AD: SANTA MARIA ACOUSTICAL | 042 | CLOSED | 3541.8605 | 0 | 3445.4 | 3445.4
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | CA: MATERIALS SUPPORT FOR SUSPENDED CEILING (NO LABOR) | 042 | CLOSED | 0 | 0 | 59.304 | 59.304
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 1125.36 | 0 | 0 | 0
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | EH&S: (N/L) | 042 | CLOSED | 137.4 | 0 | 0 | 0
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | EL:INSTALL ELECTRICAL OUTLETS FOR VOLLEYBALL LOCKER ROOM | 042 | CLOSED | 1713.072 | 0 | 2961.9264 | 2961.9264
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | IN: WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | 042 | CLOSED | 192.168 | 0 | 160.14 | 160.14
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | LO: CONSTRUCTION CORE CHANGES FOR W. VOLLEYBALL LOCKER RM. | 042 | CLOSED | 116.088 | 0 | 58.044 | 58.044
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | MO: OFF-LOAD LOCKERS TUESDAY, SEPT. 24TH AT APPROX. 12:00 | 042 | CLOSED | 129.6 | 0 | 234.432 | 234.432
PJ0004467 | WOMEN'S VOLLEYBALL LOCKER ROOM RENOVATION - BLD 42 RM 120D | PINHEIRO, RICK | CLOSED | 2013-04-02 | PA:PAINT WOMEN'S VOLLEYBALL LOCKER ROOM | 042 | CLOSED | 2893.952 | 0 | 1756.836 | 1756.836
PJ0004467 Total | [7 empty] | 17302.9279 | 0 | 16129.5098 | 16129.5098
PJ0004466 | INSPECT/SERVICE 6 ELEVATORS (ANNUAL INSPECTION) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2013-04-05 | AD: WON DOOR | 006 | CLOSED | 810 | 0 | 810 | 810
PJ0004466 | INSPECT/SERVICE 6 ELEVATORS (ANNUAL INSPECTION) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2013-04-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 81 | 0 | 0 | 0
PJ0004466 Total | [7 empty] | 891 | 0 | 810 | 810
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | AD: CENTRAL COAST FENCING | GEN-PARK | CLOSED | 294.25 | 0 | 294.25 | 294.25
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | AD: JOC 13.029.015 MAINO | GEN-PARK | CLOSED | 131469.1666 | 0 | 131469.1666 | 131469.1666
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | AD: JOC 13.031.043 MAINO | GEN-PARK | CLOSED | 8790.585 | 0 | 8790.585 | 8790.585
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 5076.14 | 0 | 0 | 0
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | EL:NEW ELECTRICAL AND CONSTRUCTION SUPPORT FOR UPD PARK LOT | GEN-PARK | CLOSED | 7200.6862 | 0 | 6686.994 | 6686.994
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | IN: M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | GEN-PARK | CLOSED | 384.336 | 0 | 288.252 | 288.252
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | LO:PURCHASE AND INSTALL LOCKS FOR ROLLING GATE AND MAN GATE | GEN-PARK | CLOSED | 410.22 | 0 | 2111.82 | 2111.82
PJ0004465 | M&R PARK 13/14: CREATE A PARKING LOT BEHIND BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2013-04-04 | PL:PROVIDE CONSTRUCTION SUPPORT FOR UPD PARKING LOT | GEN-PARK | CLOSED | 130.584 | 0 | 65.292 | 65.292
PJ0004465 Total | [7 empty] | 153755.9678 | 0 | 149706.3596 | 149706.3596
PJ0004464 | M&R PARK 13/14: CAMPUS WIDE PARKING LOT TREE TRIMMING | LOOSLEY, SCOTT L. | CLOSED | 2013-04-04 | AD: GREENVALE TREE COMPANY | GEN-PARK | CLOSED | 0 | 0 | 4863.15 | 4863.15
PJ0004464 | M&R PARK 13/14: CAMPUS WIDE PARKING LOT TREE TRIMMING | LOOSLEY, SCOTT L. | CLOSED | 2013-04-04 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 5000 | 0 | 0 | 0
PJ0004464 Total | [7 empty] | 5000 | 0 | 4863.15 | 4863.15
PJ0004463 | M&R PARK 13/14: PATCH & REPAIR DAMAGE LOT- H4C LOT | GONZALES, ALBERT M. | CLOSED | 2013-04-04 | AD: JOC 13.029.042 MAINO | P-H04 | CLOSED | 27271.625 | 0 | 27271.625 | 27271.625
PJ0004463 | M&R PARK 13/14: PATCH & REPAIR DAMAGE LOT- H4C LOT | GONZALES, ALBERT M. | CLOSED | 2013-04-04 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 0 | 0 | 0 | 0
PJ0004463 | M&R PARK 13/14: PATCH & REPAIR DAMAGE LOT- H4C LOT | GONZALES, ALBERT M. | CLOSED | 2013-04-04 | IN: M&R PARK 13/14: PATCH & REPAIR DAMAGE LOT- H4C LOT | P-H04 | CLOSED | 128.112 | 0 | 192.168 | 192.168
PJ0004463 Total | [7 empty] | 27399.737 | 0 | 27463.793 | 27463.793
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | AD: EARTH SYSTEMS (FOOTING INSPECTIONS) | 032J | CLOSED | 802.5 | 0 | 484.2285 | 484.2285
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | AD: FENCE FACTORY | 032J | CLOSED | 0 | 0 | 214.2782 | 214.2782
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | AD: G.F. GARCIA AND SONS | 032J | CLOSED | 2140 | 0 | 2140 | 2140
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | AD: JOC 13.028.026 MAINO | 032J | CLOSED | 176503.8509 | 0 | 176503.8616 | 176503.8616
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | AD: OVERHEAD ON MD BARNMASTER PURCHASE (BARN PURCHASED BY DEPT) | 032J | CLOSED | 9921.14 | 0 | 9921.14 | 9921.14
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | AD: WALLACE ENGINEERING | 032J | CLOSED | 4815 | 0 | 4815 | 4815
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | CA: INSTALL 3 FIRE EXTINGUISHERS AT NEW MARE BARN | 032J | CLOSED | 398.328 | 0 | 140.97 | 140.97
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | CP: PROJECT CONTINGENCY | 032J | CLOSED | 10587.19 | 0 | 0 | 0
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | EL: ELECTRICAL FOR MARE BARN # 2 | 032J | CLOSED | 30134.88 | 0 | 31992.138 | 31992.138
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | IN: INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | 032J | CLOSED | 2562.24 | 0 | 2209.932 | 2209.932
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | LO:TACK RMS DOOR HARDWARE | 032J | CLOSED | 3336.528 | 0 | 2006.112 | 2006.112
PJ0004462 | INSTALL 2ND NEW PREFAB 40-STALL MARE BARN - BLD 32J | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-29 | PL: WATER SERVICE, INTERIOR LINES, & FIXTURES FOR MARE BARN #2 & | 032J | CLOSED | 23752.56 | 0 | 40383.7519 | 40383.7519
PJ0004462 Total | [7 empty] | 264954.2169 | 0 | 270811.4122 | 270811.4122
PJ0004461 | RECONFIGURE ROOM - BLD 3 RM 114 | GONZALES, ALBERT M. | CLOSED | 2013-04-02 | AD: BKM FURNITURE | 003 | CLOSED | 7471.382 | 0 | 2134.6821 | 2134.6821
PJ0004461 | RECONFIGURE ROOM - BLD 3 RM 114 | GONZALES, ALBERT M. | CLOSED | 2013-04-02 | AD: REA AND LUKER | 003 | CLOSED | 3841.3 | 0 | 2688.91 | 2688.91
PJ0004461 | RECONFIGURE ROOM - BLD 3 RM 114 | GONZALES, ALBERT M. | CLOSED | 2013-04-02 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1144.08 | 0 | 0 | 0
PJ0004461 | RECONFIGURE ROOM - BLD 3 RM 114 | GONZALES, ALBERT M. | CLOSED | 2013-04-02 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 003 | CLOSED | 0 | 0 | 37.2 | 37.2
PJ0004461 | RECONFIGURE ROOM - BLD 3 RM 114 | GONZALES, ALBERT M. | CLOSED | 2013-04-02 | IN: RECONFIGURE ROOM - BLD 3 RM 114 | 003 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004461 Total | [7 empty] | 12584.874 | 0 | 4924.8481 | 4924.8481
PJ0004460 | APPLY FROSTED TINT TO CONFERENCE ROOM WINDOWS/DOOR | GALVEZ, CESAR | CLOSED | 2013-03-28 | AD: ATD WINDOW TINTING | 070 | CLOSED | 1365.32 | 0 | 1365.32 | 1365.32
PJ0004460 | APPLY FROSTED TINT TO CONFERENCE ROOM WINDOWS/DOOR | GALVEZ, CESAR | CLOSED | 2013-03-28 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 142.94 | 0 | 0 | 0
PJ0004460 | APPLY FROSTED TINT TO CONFERENCE ROOM WINDOWS/DOOR | GALVEZ, CESAR | CLOSED | 2013-03-28 | IN: APPLY FROSTED TINT TO CONFERENCE ROOM WINDOWS/DOOR | 070 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004460 Total | [7 empty] | 1572.316 | 0 | 1397.348 | 1397.348
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | AD: FLOOR CONNECTION | 011 | CLOSED | 2889 | 0 | 3072.5799 | 3072.5799
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | AD: SANTA MARIA ACOUSTICAL | 011 | CLOSED | 589.57 | 0 | 589.57 | 589.57
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | AD: WLH BUILDERS | 011 | CLOSED | 5020.44 | 0 | 5020.44 | 5020.44
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | CA:RENOVATE ROOMS 259-262 | 011 | CLOSED | 7223.93 | 0 | 6058.071 | 6058.071
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 1445.25 | 0 | 0 | 0
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | EL:ELECTRICAL RENOVATION | 011 | CLOSED | 3900.6862 | 0 | 2364.204 | 2364.204
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | IN: CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | 011 | CLOSED | 256.224 | 0 | 224.196 | 224.196
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | LO:REMOVE 2 EXTERIOR DOOR HARDWARE SETS, INSTALL 1 INTERIOR LOCK | 011 | CLOSED | 498.2958 | 0 | 462.882 | 462.882
PJ0004458 | CONVERT OFFICES TO DEPT. OFFICE CONFIG.- BLD 11 RMS 259-262 | MCNALLY, CURTIS | CLOSED | 2013-03-29 | PA:PAINT INTERIOR SPACE OF RENOVATION | 011 | CLOSED | 2462.164 | 0 | 2239.428 | 2239.428
PJ0004458 Total | [7 empty] | 24285.56 | 0 | 20031.3709 | 20031.3709
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: BKM FURNITURE | 003 | CLOSED | 13910 | 0 | 13197.1981 | 13197.1981
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: FLOOR CONNECTION | 003 | CLOSED | 5321.2919 | 0 | 5321.2919 | 5321.2919
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: JL FASULO DRYWALL | 003 | CLOSED | 5350 | 0 | 5389.2155 | 5389.2155
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: MACDONALD COMPANY | 003 | CLOSED | 5350 | 0 | 2832.1081 | 2832.1081
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: MORELAND THOMPSON | 003 | CLOSED | 7190.1539 | 0 | 7190.4 | 7190.4
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: REA AND LUKER | 003 | CLOSED | 14496.1995 | 0 | 10641.15 | 10641.15
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: SAN LUIS GLASS | 003 | CLOSED | 1284 | 0 | 1282.5341 | 1282.5341
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | AD: SANTA MARIA ACOUSTICAL | 003 | CLOSED | 1391 | 0 | 1203.75 | 1203.75
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | CA: INSTALL WHITE BOARD IN BLDG. 03 ROOM 114 | 003 | CLOSED | 285.552 | 0 | 1161.468 | 1161.468
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | EL: BUSINESS ADVISING CENTER PROJECT SUPPORT | 003 | CLOSED | 5017.764 | 0 | 2505.54 | 2505.54
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | ES: ADD RETURN AIR AND SUPPLY FOR BLDG. 003 OFFICE REMODEL | 003 | CLOSED | 2698.464 | 0 | 3537.168 | 3537.168
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | IN: REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | 003 | CLOSED | 640.56 | 0 | 416.364 | 416.364
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | LO: BUSINESS ADVISING CENTER ROOM 101 | 003 | CLOSED | 532.176 | 0 | 1259.118 | 1259.118
PJ0004456 | REMODEL ROOMS / REMOVE WALL - BLD 3 RMS 101/102 | GONZALES, ALBERT M. | CLOSED | 2013-03-26 | PA: PAINT ROOMS 101 A/B & BACKSIDE OF ROOM 114A (OR IS IT 103?) | 003 | CLOSED | 993.3715 | 0 | 2167.248 | 2167.248
PJ0004456 Total | [7 empty] | 64460.5328 | 0 | 58104.5537 | 58104.5537
PJ0004454 | M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | GONZALES, ALBERT M. | CLOSED | 2013-03-29 | AD: JOC 13.027.008 PUB | P-H12 | CLOSED | 21817.3 | 0 | 19231.1207 | 19231.1207
PJ0004454 | M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | GONZALES, ALBERT M. | CLOSED | 2013-03-29 | CP: PROJECT CONTINGENCY | P-H12 | CLOSED | 3181.81 | 0 | 0 | 0
PJ0004454 | M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | GONZALES, ALBERT M. | CLOSED | 2013-03-29 | EL: PROJECT SUPPORT | P-H12 | CLOSED | 719.328 | 0 | 134.604 | 134.604
PJ0004454 | M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | GONZALES, ALBERT M. | CLOSED | 2013-03-29 | EO:H-12 PARKING LOT TREE REMOVAL | P-H12 | CLOSED | 4341.12 | 0 | 3726.576 | 3726.576
PJ0004454 | M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | GONZALES, ALBERT M. | CLOSED | 2013-03-29 | IN: M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | P-H12 | CLOSED | 256.224 | 0 | 64.056 | 64.056
PJ0004454 | M&R PARK 13/14: PATCH AND REPAIR TREE ROOT DAMAGE - H12 LOT | GONZALES, ALBERT M. | CLOSED | 2013-03-29 | LA:PARKING LOT H-12 ROOT DAMAGE AND TREE REMOVAL | P-H12 | CLOSED | 899.28 | 0 | 715.374 | 715.374
PJ0004454 Total | [7 empty] | 31215.062 | 0 | 23871.7307 | 23871.7307
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | AD: PURCHASE KEY BOXES FROM SL001-204600-619001 | 070A | CLOSED | 51626.32 | 0 | 51230.02 | 51230.02
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | CA: PROVIDE SUPPORT FOR KEY BOX INSTALLATION(N/L) | 070A | CLOSED | 425.92 | 0 | 0 | 0
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | CP: PROJECT CONTINGENCY | 070A | CLOSED | 0 | 0 | 0 | 0
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | EL:SUPPROT FOR KEY BOX INSTALLATION AT CUSTODIAL WAREHOUSE | 070A | CLOSED | 499.44 | 0 | 115.24 | 115.24
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | IN: INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | 070A | CLOSED | 106.76 | 0 | 26.69 | 26.69
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | LO:INSTALL NEW KEY BOXES AT CUSTODIAL WAREHOUSE | 070A | CLOSED | 3919.6 | 0 | 4692.2 | 4692.2
PJ0004451 | INSTALL NEW KEY BOXES, REMOVE OLD - BLD 70A RM 302 (MAINT) | POLVI, STEVEN | CLOSED | 2013-03-28 | PA:PAINT AREAS WHERE KEY BOXES WERE REMOVED (N/L) | 070A | CLOSED | 395.76 | 0 | 0 | 0
PJ0004451 Total | [7 empty] | 56973.8 | 0 | 56064.15 | 56064.15
PJ0004450 | INSTALL PANIC ALARM BUTTON SYSTEM - BLDG 65 RM 217A | MOLLAN, CHERYL L. | CLOSED | 2013-03-27 | AD: CAME SECURITY | 065 | CLOSED | 1738.75 | 0 | 1738.75 | 1738.75
PJ0004450 | INSTALL PANIC ALARM BUTTON SYSTEM - BLDG 65 RM 217A | MOLLAN, CHERYL L. | CLOSED | 2013-03-27 | ANTS: PROGRAMMING FOR PANIC ALARM BUTTONS - BLDG 65 RM 217A | 065 | CLOSED | 96.096 | 0 | 24.024 | 24.024
PJ0004450 | INSTALL PANIC ALARM BUTTON SYSTEM - BLDG 65 RM 217A | MOLLAN, CHERYL L. | CLOSED | 2013-03-27 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 189.89 | 0 | 0 | 0
PJ0004450 | INSTALL PANIC ALARM BUTTON SYSTEM - BLDG 65 RM 217A | MOLLAN, CHERYL L. | CLOSED | 2013-03-27 | IN: INSTALL PANIC ALARM BUTTON SYSTEM - BLDG 65 RM 217A | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004450 Total | [7 empty] | 2088.792 | 0 | 1826.83 | 1826.83
PJ0004449 | INSTALL DRINKING FOUNTAIN - BLDG 40 (MAINT) | PIPAL, GAIL | CLOSED | 2013-03-25 | CA: SUPPORT FOR DRINKING FOUNTAIN REPLACEMENT - BLDG. 40 | 040 | CLOSED | 0 | 0 | 469.9 | 469.9
PJ0004449 | INSTALL DRINKING FOUNTAIN - BLDG 40 (MAINT) | PIPAL, GAIL | CLOSED | 2013-03-25 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004449 | INSTALL DRINKING FOUNTAIN - BLDG 40 (MAINT) | PIPAL, GAIL | CLOSED | 2013-03-25 | EL: SUPPORT FOR DRINKING FOUNTAIN REPLACEMENT - BLDG. 40 | 040 | CLOSED | 0 | 0 | 252.81 | 252.81
PJ0004449 | INSTALL DRINKING FOUNTAIN - BLDG 40 (MAINT) | PIPAL, GAIL | CLOSED | 2013-03-25 | PA: SUPPORT FOR DRINKING FOUNTAIN REPLACEMENT - BLDG. 40 | 040 | CLOSED | 0 | 0 | 247.35 | 247.35
PJ0004449 | INSTALL DRINKING FOUNTAIN - BLDG 40 (MAINT) | PIPAL, GAIL | CLOSED | 2013-03-25 | PCV PL: SUPPORT FOR DRINKING FOUNTAIN REPLACEMENT - BLDG. 40 | 040 | CLOSED | 0 | 0 | 726.6 | 726.6
PJ0004449 | INSTALL DRINKING FOUNTAIN - BLDG 40 (MAINT) | PIPAL, GAIL | CLOSED | 2013-03-25 | PL: REPLACE DRINKING FOUNTAIN - BLDG. 40 | 040 | CLOSED | 0 | 0 | 2536.94 | 2536.94
PJ0004449 Total | [7 empty] | 0 | 0 | 4233.6 | 4233.6
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | AD: COASTAL JANITORIAL | 051 | CLOSED | 0 | 0 | 583.15 | 583.15
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | AD: STATE FIRE MARSHAL FEES | GENERAL | CLOSED | 0 | 0 | 150.29 | 150.29
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | CU: SUPPORT FOR CHANCELLOR'S VISIT (MAINT) | GENERAL | CLOSED | 0 | 0 | 60.82 | 60.82
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | CU: SUPPORT FOR GREEN AND GOLD EVENT - MAY 2 | GENERAL | CLOSED | 0 | 0 | 1103.55 | 1103.55
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | EL: SUPPORT FOR GREEN & GOLD GALA - MAY 1 & 2 | GENERAL | CLOSED | 0 | 0 | 2284.846 | 2284.846
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | GR: SUPPORT FOR GREEN & GOLD GALA - MAY 1 & 2 | GENERAL | CLOSED | 0 | 0 | 532.74 | 532.74
PJ0004448 | SUPPORT FOR 2013 GREEN AND GOLD GALA EVENT - MAY 1 & 2 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-03-22 | PL: SUPPORT FOR CHANCELLOR VISIT: MAY 1&2 | GENERAL | CLOSED | 0 | 0 | 272.05 | 272.05
PJ0004448 Total | [7 empty] | 0 | 0 | 4987.446 | 4987.446
PJ0004447 | TENNANT IMPROVEMENT: MODIFY SPRINT ANTENNA & EQUIP - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-22 | AD: ENGLEKIRK AND SABOL | 208U | CLOSED | 500 | 0 | 500 | 500
PJ0004447 | TENNANT IMPROVEMENT: MODIFY SPRINT ANTENNA & EQUIP - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-22 | CP: PROJECT CONTINGENCY | 208U | CLOSED | 135.87 | 0 | 0 | 0
PJ0004447 | TENNANT IMPROVEMENT: MODIFY SPRINT ANTENNA & EQUIP - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-22 | IN: FACILITY SERVICES BUILDING PERMIT FEES | 208U | CLOSED | 123.85 | 0 | 123.85 | 123.85
PJ0004447 | TENNANT IMPROVEMENT: MODIFY SPRINT ANTENNA & EQUIP - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-22 | IN: FACILITY SERVICES PLAN REVIEW FEES | 208U | CLOSED | 600 | 0 | 600 | 600
PJ0004447 | TENNANT IMPROVEMENT: MODIFY SPRINT ANTENNA & EQUIP - RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-22 | IN: TI - MODIFY SPRINT ANTENNA & EQUIP - RADIO HILL (MAINT) | 208U | CLOSED | 0 | 0 | 80.07 | 80.07
PJ0004447 Total | [7 empty] | 1359.72 | 0 | 1303.92 | 1303.92
PJ0004446 | SR 13/14: DRAIN, PERFORM PM, SEAMS, GROUT, TILE -ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2013-03-21 | AD: JOC 13.028.031 MAINO | 042A | CLOSED | 34203.21 | 0 | 34203.21 | 34203.21
PJ0004446 | SR 13/14: DRAIN, PERFORM PM, SEAMS, GROUT, TILE -ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004446 | SR 13/14: DRAIN, PERFORM PM, SEAMS, GROUT, TILE -ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2013-03-21 | CPE:DRAIN POOL AND PROVIDE CONSTRUCTION SUPPORT | 042A | CLOSED | 52.03 | 0 | 52.03 | 52.03
PJ0004446 | SR 13/14: DRAIN, PERFORM PM, SEAMS, GROUT, TILE -ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2013-03-21 | IN: DRAIN, PERFORM PM, SEAMS, GROUT, TILE -ANDERSON POOL | 042A | CLOSED | 80.07 | 0 | 80.07 | 80.07
PJ0004446 | SR 13/14: DRAIN, PERFORM PM, SEAMS, GROUT, TILE -ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2013-03-21 | PL: PROVIDE PUMP AND HOSES TO DRAIN AND FILL POOL | 042A | CLOSED | 163.23 | 0 | 169.37 | 169.37
PJ0004446 Total | [7 empty] | 34498.54 | 0 | 34504.68 | 34504.68
PJ0004445 | SR 13/14: REPLACE UTILIDOR VALVES, PHASE 10 OF 20 (002 & 046) | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | AD: GOSS ENGINEERING | U-UDOR | CLOSED | 3000 | 0 | 2100 | 2100
PJ0004445 | SR 13/14: REPLACE UTILIDOR VALVES, PHASE 10 OF 20 (002 & 046) | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | AD: JOC 13.029.012 MAINO | U-UDOR | CLOSED | 80540.5 | 0 | 79530.23 | 79530.23
PJ0004445 | SR 13/14: REPLACE UTILIDOR VALVES, PHASE 10 OF 20 (002 & 046) | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0004445 | SR 13/14: REPLACE UTILIDOR VALVES, PHASE 10 OF 20 (002 & 046) | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | IN: SR 13/14: REPLACE UTILIDOR VALVES, PHASE 10 OF 20 | U-UDOR | CLOSED | 237.541 | 0 | 213.52 | 213.52
PJ0004445 | SR 13/14: REPLACE UTILIDOR VALVES, PHASE 10 OF 20 (002 & 046) | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | PL: UTILIDOR VALVE REPLACEMENT PROJECT SUPPORT | U-UDOR | CLOSED | 2411.1666 | 0 | 1239.475 | 1239.475
PJ0004445 Total | [7 empty] | 86189.2076 | 0 | 83083.225 | 83083.225
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | AD: G.F. GARCIA AND SONS | U-UDOR | CLOSED | 10651.4755 | 0 | 8190.4755 | 8190.4755
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0.42 | 0 | 0 | 0
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | CPE: SUPPORT FOR BLDG 40 POWER OUTAGE | U-UDOR | CLOSED | 787.968 | 0 | 1047.306 | 1047.306
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | EL: SUPPORT & INSTALLATION OF CONDUIT | U-UDOR | CLOSED | 4715.0392 | 0 | 3483.036 | 3483.036
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | ES: CONTROLS SUPPORT FOR BLDG 40 POWER OUTAGE | U-UDOR | CLOSED | 430.7558 | 0 | 1155.648 | 1155.648
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | IN: CONNECT UTILIDOR SUMP PUMP NEAR NATATORIUM TO SEWER | U-UDOR | CLOSED | 384.336 | 0 | 134.7 | 134.7
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | LA: SUPPORT AND TREE TRIMMING FOR EXCAVATION WORK | U-UDOR | CLOSED | 1268.1341 | 0 | 0 | 0
PJ0004444 | SR 13/14: CONNECT UTILIDOR SUMP PUMPS NEAR 40, 46, & 11 TO SEWER | KOLEGRAFF, KENNETH | CLOSED | 2013-03-21 | PL: SUPPORT LIFTING LIDS FOR JOB WALK | U-UDOR | CLOSED | 2043.9493 | 0 | 496.608 | 496.608
PJ0004444 Total | [7 empty] | 20282.0779 | 0 | 14507.7735 | 14507.7735
PJ0004443 | SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2013-03-21 | AD: G.F. GARCIA & SONS | GENERAL | OPEN | 1760 | 0 | 1760 | 1760
PJ0004443 | SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2013-03-21 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 10700 | 0 | 0 | 0
PJ0004443 | SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2013-03-21 | IN: SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GENERAL | ASSIGNED | 128.112 | 0 | 26.69 | 26.69
PJ0004443 | SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2013-03-21 | PL: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GENERAL | WORKING | 15162.6272 | 0 | 18412.211 | 18412.211
PJ0004443 | SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GONZALES, ALBERT | IN_CONSTR | 2013-03-21 | SM: SR 12/13: PRESSURE STUDY OF ALL FIRE HYDRANTS - CAMPUS WIDE | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0004443 Total | [7 empty] | 27750.7392 | 0 | 20198.901 | 20198.901
PJ0004442 | SR 13/14: RE-ROOF BCEC PEN AREA - BLD 55 | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | AD: JOC 13.028.010 MAINO | 055 | CLOSED | 127361.5 | 0 | 127361.5 | 127361.5
PJ0004442 | SR 13/14: RE-ROOF BCEC PEN AREA - BLD 55 | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | 055 | CLOSED | 0 | 0 | 0 | 0
PJ0004442 | SR 13/14: RE-ROOF BCEC PEN AREA - BLD 55 | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 055 | CLOSED | 16 | 0 | 16 | 16
PJ0004442 | SR 13/14: RE-ROOF BCEC PEN AREA - BLD 55 | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | EL:DETACH ELECTRICAL FOR ROOF REPLACEMENT AT BCEC | 055 | CLOSED | 7475.8502 | 0 | 8833.96 | 8833.96
PJ0004442 | SR 13/14: RE-ROOF BCEC PEN AREA - BLD 55 | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | IN: SR 13/14: RE-ROOF BCEC PEN AREA - BLD 55 | 055 | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0004442 Total | [7 empty] | 135066.8702 | 0 | 136424.98 | 136424.98
PJ0004441 | SR 13/14: RE-ROOF HERDSMAN HALL - BLD 16A | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | AD: JOC 13.028.032 MAINO | 016A | CLOSED | 19786.48 | 0 | 18878.56 | 18878.56
PJ0004441 | SR 13/14: RE-ROOF HERDSMAN HALL - BLD 16A | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | 016A | CLOSED | 0 | 0 | 0 | 0
PJ0004441 | SR 13/14: RE-ROOF HERDSMAN HALL - BLD 16A | GONZALES, ALBERT M. | CLOSED | 2013-03-21 | IN: SR 13/14: RE-ROOF HERDSMAN HALL - BLD 16A | 016A | CLOSED | 213.52 | 0 | 133.45 | 133.45
PJ0004441 Total | [7 empty] | 20000 | 0 | 19012.01 | 19012.01
PJ0004440 | SR 13/14: RE-ROOF CHORRO CREEK RANCH HOUSE & GARAGE 126V&U | MAY, TOM | CLOSED | 2013-03-21 | AD: JOC 13.028.009 MAINO | 126V | CLOSED | 25830.02 | 0 | 25830.02 | 25830.02
PJ0004440 | SR 13/14: RE-ROOF CHORRO CREEK RANCH HOUSE & GARAGE 126V&U | MAY, TOM | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | 126V | CLOSED | 0 | 0 | 0 | 0
PJ0004440 | SR 13/14: RE-ROOF CHORRO CREEK RANCH HOUSE & GARAGE 126V&U | MAY, TOM | CLOSED | 2013-03-21 | IN: SR 13/14: RE-ROOF CHORRO CREEK RANCH HOUSE & GARAGE 126V&U | 126V | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0004440 Total | [7 empty] | 26043.54 | 0 | 26043.54 | 26043.54
PJ0004439 | SR 13/14: RE-ROOF CHASE HALL 115 | MAY, TOM | CLOSED | 2013-03-21 | AD: JOC 13.028.008 MAINO | 115 | CLOSED | 49357.72 | 0 | 49357.72 | 49357.72
PJ0004439 | SR 13/14: RE-ROOF CHASE HALL 115 | MAY, TOM | CLOSED | 2013-03-21 | CP: PROJECT CONTINGENCY | 115 | CLOSED | 0 | 0 | 0 | 0
PJ0004439 | SR 13/14: RE-ROOF CHASE HALL 115 | MAY, TOM | CLOSED | 2013-03-21 | IN: SR 13/14: RE-ROOF CHASE HALL 115 | 115 | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0004439 Total | [7 empty] | 49571.24 | 0 | 49571.24 | 49571.24
PJ0004437 | SR 13/14: RE-ROOF PARTS OF KENNEDY LIBRARY | MAY, TOM | CLOSED | 2013-03-20 | AD: JOC 13.028.007 MAINO | 035 | CLOSED | 244403.74 | 0 | 244403.74 | 244403.74
PJ0004437 | SR 13/14: RE-ROOF PARTS OF KENNEDY LIBRARY | MAY, TOM | CLOSED | 2013-03-20 | AD: MCKENNA ENVIRONMENTAL | 035 | CLOSED | 4000 | 0 | 1370 | 1370
PJ0004437 | SR 13/14: RE-ROOF PARTS OF KENNEDY LIBRARY | MAY, TOM | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0004437 | SR 13/14: RE-ROOF PARTS OF KENNEDY LIBRARY | MAY, TOM | CLOSED | 2013-03-20 | IN: SR 13/14: RE-ROOF PARTS OF KENNEDY LIBRARY | 035 | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0004437 Total | [7 empty] | 248617.26 | 0 | 245987.26 | 245987.26
PJ0004435 | SR 13/14: REPAIR INTERSECTION OF CALIF BLVD & CAMPUS WAY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: JOC 13.028.047 MAINO | GENERAL | CLOSED | 94325.79 | 0 | 94325.79 | 94325.79
PJ0004435 | SR 13/14: REPAIR INTERSECTION OF CALIF BLVD & CAMPUS WAY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004435 | SR 13/14: REPAIR INTERSECTION OF CALIF BLVD & CAMPUS WAY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | EO:INTERSECTION OF CA AND CAMPUS WAY | GENERAL | CLOSED | 331.76 | 0 | 295.76 | 295.76
PJ0004435 | SR 13/14: REPAIR INTERSECTION OF CALIF BLVD & CAMPUS WAY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | IN: SR 13/14: REPAIR INTERSECTION OF CALIF BLVD & CAMPUS WAY | GENERAL | CLOSED | 320.28 | 0 | 133.45 | 133.45
PJ0004435 Total | [7 empty] | 94977.83 | 0 | 94755 | 94755
PJ0004434 | DM 15/16: MUSTANG WAY BIKE PATH | NORTON, DAVE | CLOSED | 2013-03-20 | AD: FLINT TRADING | GENERAL | CLOSED | 19010.7863 | 0 | 19010.7863 | 19010.7863
PJ0004434 | DM 15/16: MUSTANG WAY BIKE PATH | NORTON, DAVE | CLOSED | 2013-03-20 | AD: GOLDEN STATE SEALING & STRIPING | GENERAL | CLOSED | 89984.7637 | 0 | 89155.5137 | 89155.5137
PJ0004434 | DM 15/16: MUSTANG WAY BIKE PATH | NORTON, DAVE | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 3049.13 | 0 | 0 | 0
PJ0004434 | DM 15/16: MUSTANG WAY BIKE PATH | NORTON, DAVE | CLOSED | 2013-03-20 | IN: SR 15/16: MUSTANG WAY BIKE PATH | GENERAL | CLOSED | 282.576 | 0 | 70.644 | 70.644
PJ0004434 | DM 15/16: MUSTANG WAY BIKE PATH | NORTON, DAVE | CLOSED | 2013-03-20 | PL: SEWER CONNECTION ASSISTANCE | GENERAL | CLOSED | 755.904 | 0 | 319.248 | 319.248
PJ0004434 Total | [7 empty] | 113083.16 | 0 | 108556.192 | 108556.192
PJ0004433 | SR 13/14: CAMPUS ROAD STRIPING | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: GOLDEN STATE STRIPING | GENERAL | CLOSED | 11083 | 0 | 11083 | 11083
PJ0004433 | SR 13/14: CAMPUS ROAD STRIPING | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: JOC 13.029.018 MAINO | GENERAL | CLOSED | 38695.91 | 0 | 29244.84 | 29244.84
PJ0004433 | SR 13/14: CAMPUS ROAD STRIPING | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: WLH BUILDING CO. | GENERAL | CLOSED | 1500 | 0 | 1500 | 1500
PJ0004433 | SR 13/14: CAMPUS ROAD STRIPING | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | CA: SIGNAGE FOR BIKE LANE ON CALIFORNIA BLVD. | GENERAL | CLOSED | 315.8389 | 0 | 208.48 | 208.48
PJ0004433 | SR 13/14: CAMPUS ROAD STRIPING | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004433 | SR 13/14: CAMPUS ROAD STRIPING | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | IN: SR 13/14: CAMPUS ROAD STRIPING | GENERAL | CLOSED | 106.76 | 0 | 26.69 | 26.69
PJ0004433 Total | [7 empty] | 51701.5089 | 0 | 42063.01 | 42063.01
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: JOC 13.030.031 MAINO | 035 | CLOSED | 46437.24 | 0 | 44541.3 | 44541.3
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: MAINO (LOW-VALUE PUBLIC WORKS) | 035 | CLOSED | 4537.76 | 0 | 4537.76 | 4537.76
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: NORTH COAST ENGINEERING | 035 | CLOSED | 26970 | 0 | 18599.58 | 18599.58
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 6233.76 | 0 | 0 | 0
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | IN: SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | 035 | CLOSED | 320.28 | 0 | 299.08 | 299.08
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | LA: EXTERIOR ENTRY AT LIBRARY HARDSCAPE | 035 | CLOSED | 2078.2907 | 0 | 551.99 | 551.99
PJ0004432 | SR 13/14: RESURFACE AREA AROUND TREE IN FRONT OF LIBRARY | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | PL: RAISE DI FOR DRAINAGE | 035 | CLOSED | 2203.2911 | 0 | 841.1994 | 841.1994
PJ0004432 Total | [7 empty] | 88780.6218 | 0 | 69370.9094 | 69370.9094
PJ0004427 | SR 13/14: REPLACE SLIDING FIRE DOORS - KEN LIB 35 | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: MACDONALD COMPANY | 035 | CLOSED | 2500 | 0 | 630 | 630
PJ0004427 | SR 13/14: REPLACE SLIDING FIRE DOORS - KEN LIB 35 | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 1200 | 0 | 720 | 720
PJ0004427 | SR 13/14: REPLACE SLIDING FIRE DOORS - KEN LIB 35 | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0004427 | SR 13/14: REPLACE SLIDING FIRE DOORS - KEN LIB 35 | GONZALES, ALBERT M. | CLOSED | 2013-03-20 | IN: SR 13/14: REPLACE SLIDING FIRE DOORS - KEN LIB 35 | 035 | CLOSED | 106.76 | 0 | 133.45 | 133.45
PJ0004427 Total | [7 empty] | 3806.76 | 0 | 1483.45 | 1483.45
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: BRANDOW & JOHNSTON | 040 | OPEN | 4494 | 0 | 4494 | 4494
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: CAI SAFETY SYSTEMS | 040 | OPEN | 11395.5 | 0 | 11395.5 | 11395.5
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: EARTH SYSTEMS - SPECIAL INSPECTION | 040 | OPEN | 4970.15 | 4970.15 | 0 | 4970.15
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: ENGLEKIRK AND SABOL | 040 | OPEN | 535 | 535 | 0 | 535
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: JOC 16.041.4424.00 MAINO | 040 | OPEN | 90334.9319 | 90334.9319 | 0 | 90334.9319
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: MCKENNA ENVIRONMENTAL | 040 | OPEN | 3263.5 | 3263.5 | 0 | 3263.5
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | AD: ONTRAC | 040 | OPEN | 83.4386 | 0 | 83.4386 | 83.4386
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | CP: PROJECT CONTINGENCY | 040 | OPEN | 438.79 | 0 | 0 | 0
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | CPE: | 040 | OPEN | 2101.248 | 0 | 0 | 0
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | EL: | 040 | OPEN | 386.568 | 0 | 0 | 0
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | IN: SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | 040 | ASSIGNED | 847.728 | 0 | 70.644 | 70.644
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | LO: | 040 | OPEN | 243.696 | 0 | 0 | 0
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | PA: | 040 | OPEN | 3850.17 | 0 | 30.954 | 30.954
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | PM: SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | 040 | OPEN | 0 | 0 | 0 | 0
PJ0004424 | SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | KUENTZEL, DOUGLAS A. | DESIGN | 2013-03-20 | SM: SR 13/14: FALL PROTECTION ON TOP OF BOILERS - BLD 40 | 040 | OPEN | 0 | 0 | 0 | 0
PJ0004424 Total | [7 empty] | 122944.7205 | 99103.5819 | 16074.5366 | 115178.1185
PJ0004423 | SR 13/14: DEMO SWINE PENS - SWINE UNIT BLDG. 056 | MCNALLY, CURTIS | CLOSED | 2013-03-20 | AD: JOC 13.029.005 MAINO | 056 | CLOSED | 46016.9 | 0 | 46016.9 | 46016.9
PJ0004423 | SR 13/14: DEMO SWINE PENS - SWINE UNIT BLDG. 056 | MCNALLY, CURTIS | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | 056 | CLOSED | 0 | 0 | 0 | 0
PJ0004423 | SR 13/14: DEMO SWINE PENS - SWINE UNIT BLDG. 056 | MCNALLY, CURTIS | CLOSED | 2013-03-20 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 056 | CLOSED | 0 | 0 | 299 | 299
PJ0004423 | SR 13/14: DEMO SWINE PENS - SWINE UNIT BLDG. 056 | MCNALLY, CURTIS | CLOSED | 2013-03-20 | IN: SR 13/14: DEMO SWINE PENS - SWINE UNIT BLDG. 056 | 056 | CLOSED | 213.52 | 0 | 216.265 | 216.265
PJ0004423 Total | [7 empty] | 46230.42 | 0 | 46532.165 | 46532.165
PJ0004421 | SR 13/14: REPAIR ROAD BEHIND VISTA GRANDE - DEER RD | LAMPMAN, GREG | CLOSED | 2013-03-20 | AD: JOC 13.029.033 MAINO | STREETS | CLOSED | 163410.87 | 0 | 163410.87 | 163410.87
PJ0004421 | SR 13/14: REPAIR ROAD BEHIND VISTA GRANDE - DEER RD | LAMPMAN, GREG | CLOSED | 2013-03-20 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 0 | 0 | 0 | 0
PJ0004421 | SR 13/14: REPAIR ROAD BEHIND VISTA GRANDE - DEER RD | LAMPMAN, GREG | CLOSED | 2013-03-20 | IN: SR 13/14: REPAIR ROAD BEHIND VISTA GRANDE - DEER RD | STREETS | CLOSED | 800.7 | 0 | 400.35 | 400.35
PJ0004421 | SR 13/14: REPAIR ROAD BEHIND VISTA GRANDE - DEER RD | LAMPMAN, GREG | CLOSED | 2013-03-20 | LA: MAKE REPAIRS AS NEEDED | STREETS | CLOSED | 259.76 | 0 | 384.61 | 384.61
PJ0004421 | SR 13/14: REPAIR ROAD BEHIND VISTA GRANDE - DEER RD | LAMPMAN, GREG | CLOSED | 2013-03-20 | PL: ASSIST CONTRACTOR ON DEER ROAD REPAIR | STREETS | CLOSED | 272.05 | 0 | 163.23 | 163.23
PJ0004421 Total | [7 empty] | 164743.38 | 0 | 164359.06 | 164359.06
PJ0004419 | SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | CP: PROJECT CONTINGENCY | 074 | CLOSED | 0 | 0 | 0 | 0
PJ0004419 | SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | EH&S: (N/L) | 074 | CLOSED | 429 | 0 | 0 | 0
PJ0004419 | SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | EL: REROUTE POWER TO REMAINING 074D | 074 | CLOSED | 7044.96 | 0 | 7370.16 | 7370.16
PJ0004419 | SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | EO: ASSIST PLUMBERS WITH BLDG 74 DEMO | 074 | CLOSED | 0 | 0 | 82.94 | 82.94
PJ0004419 | SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | IN: SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | 074 | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0004419 | SR 13/14: DEMO BLD 74 & LANDSCAPE - OLD UPD 74 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | PL: UTILITY CLEARANCE AT 074 & 074C DEMOLITION | 074 | CLOSED | 2520.6437 | 0 | 3385.9257 | 3385.9257
PJ0004419 Total | [7 empty] | 10208.1237 | 0 | 11052.5457 | 11052.5457
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | AD: ENGLEKIRK AND SABOL | 042A | CLOSED | 1000 | 0 | 998 | 998
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | AD: JOC 13.028.036 MAINO | 042A | CLOSED | 17181.84 | 0 | 17181.84 | 17181.84
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | AD: ON TRAC SHIPPING | 042A | CLOSED | 0 | 0 | 30.07 | 30.07
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | AD: PMSM ARCHITECTS | 042A | CLOSED | 19950 | 0 | 19950 | 19950
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | AD: STATE FIRE MARSHAL FEES | 042A | CLOSED | 1000 | 0 | 0 | 0
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | IN: REROOF MECH. BLDG & ADD ROOF OVER TANK - ANDERSON POOL | 042A | CLOSED | 320.28 | 0 | 266.9 | 266.9
PJ0004416 | SR 13/14: REROOF PUMP RM & DESIGN ROOF FOR MECH RM - ANDERSON | MOLLAN, CHERYL L. | CLOSED | 2013-03-19 | PA:PAINT NEW PLYWOOD ON CEILING TO MATCH EXISTING | 042A | CLOSED | 296.82 | 0 | 1014.135 | 1014.135
PJ0004416 Total | [7 empty] | 39748.94 | 0 | 39440.945 | 39440.945
PJ0004415 | SR 13/14: RESURFACE TENNIS COURTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | AD: JOC 13.027.012.00 & .02 PUB CONSTRUCTION | 042S | CLOSED | 58962.65 | 0 | 58862.44 | 58862.44
PJ0004415 | SR 13/14: RESURFACE TENNIS COURTS | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-19 | CP: PROJECT CONTINGENCY | 042S | CLOSED | 0 | 0 | 0 | 0
PJ0004415 Total | [7 empty] | 58962.65 | 0 | 58862.44 | 58862.44
PJ0004412 | WASH THE WINDOWS AT BLDGS 186 A & B | LOOSLEY, SCOTT L. | CLOSED | 2013-03-18 | AD: COASTAL JANITORIAL | 186 | CLOSED | 2273.75 | 0 | 2273.75 | 2273.75
PJ0004412 | WASH THE WINDOWS AT BLDGS 186 A & B | LOOSLEY, SCOTT L. | CLOSED | 2013-03-18 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 227.38 | 0 | 0 | 0
PJ0004412 Total | [7 empty] | 2501.13 | 0 | 2273.75 | 2273.75
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: ASAP REPROGRAPHICS | 014 | CLOSED | 13.9956 | 0 | 11.66 | 11.66
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: CAME SECURITY | 014 | CLOSED | 6634 | 0 | 6634 | 6634
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: DEEP BLUE | 014 | CLOSED | 21259.83 | 0 | 20763.35 | 20763.35
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: ITS | 014 | CLOSED | 20785.1673 | 0 | 12970.7433 | 12970.7433
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: JOC 16.037.001 MAINO | 014 | CLOSED | 130903.8 | 0 | 122378.0828 | 122378.0828
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: REA AND LUKER | 014 | CLOSED | 46460.042 | 0 | 39567.7333 | 39567.7333
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: RUSSCO | 014 | CLOSED | 1523.9368 | 0 | 1424.2449 | 1424.2449
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: STATE FIRE MARSHAL | 014 | CLOSED | 2140 | 0 | 2963.9749 | 2963.9749
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | AD: TRI COUNTY | 014 | CLOSED | 3210 | 0 | 2771.3 | 2771.3
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 23911.78 | 0 | 0 | 0
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 014 | CLOSED | 138 | 0 | 138 | 138
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | IN: OPS OFFICE/MTG ROOM DESIGN/BUILD - BLD 14 RM 105 | 014 | CLOSED | 640.56 | 0 | 1046.484 | 1046.484
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | LO: | 014 | CLOSED | 4331.088 | 0 | 4798.608 | 4798.608
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | MO: MOVE DOOR TO 14-112 AND TWO TABLES TO 46 | 014 | CLOSED | 64.8 | 0 | 18.108 | 18.108
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | PA: PAINT 14-105 | 014 | CLOSED | 9971.856 | 0 | 3095.406 | 3095.406
PJ0004411 | OPS OFFICE/MEETING ROOM DESIGN/BUILD - BLD 14 RM 105 | LAMPMAN, GREG | CLOSED | 2013-03-18 | PM: OPS OFFICE/MEETING ROOM DESIGN/BUILD-BLD 14 RM 105 | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0004411 Total | [7 empty] | 271988.8557 | 0 | 218581.6952 | 218581.6952
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: ASAP REPROGRAPHICS | 035 | CLOSED | 0 | 0 | 329.508 | 329.508
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: COASTAL ROLL-OFF | 035 | CLOSED | 1070 | 0 | 908.1518 | 908.1518
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: DIVISION OF STATE ARCHITECT | 035 | CLOSED | 1000 | 0 | 0 | 0
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: FLOOR CONNECTION | 035 | CLOSED | 32610.8073 | 0 | 32415.65 | 32415.65
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: MAINO (LOW VALUE PUBLIC WORKS) | 035 | CLOSED | 11834.2 | 0 | 11652.3 | 11652.3
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: MEATHEAD MOVERS | 035 | CLOSED | 2675 | 0 | 2651.46 | 2651.46
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: REA AND LUKER | 035 | CLOSED | 79862.125 | 0 | 72430.6005 | 72430.6005
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | AD: STATE FIRE MARSHAL FEES | 035 | CLOSED | 0 | 0 | 328.75 | 328.75
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 13703.17 | 0 | 0 | 0
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | EO: ASSIST COASTAL ROLL-OFF WITH MOVING FURNITURE AT LIBRARY | 035 | CLOSED | 398.112 | 0 | 99.528 | 99.528
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | IN: CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FL | 035 | CLOSED | 640.56 | 0 | 346.632 | 346.632
PJ0004410 | CTLT OFFICE SPACE DESIGN/DEMO/DECOMMISSION - BLD 35 3RD FLOOR | KOLEGRAFF, KENNETH | CLOSED | 2013-03-18 | LA: ASSIST COASTAL ROLL-OFF WITH MOVING FURNITURE AT LIBRARY | 035 | CLOSED | 311.712 | 0 | 86.712 | 86.712
PJ0004410 Total | [7 empty] | 144105.6863 | 0 | 121249.2923 | 121249.2923
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | AD: FLOOR CONNECTION | 065 | CLOSED | 1019.5816 | 0 | 1011.15 | 1011.15
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | AD: J.L. FASULO DRYWALL | 065 | CLOSED | 1324.4781 | 0 | 1356.5781 | 1356.5781
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | AD: JOC 13.028.005 MAINO | 065 | CLOSED | 224676.2353 | 0 | 224554.3516 | 224554.3516
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | AD: MORELAND THOMPSON | 065 | CLOSED | 2273.1936 | 0 | 2273.1936 | 2273.1936
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | AD: OMNI DESIGN | 065 | CLOSED | 44544.1 | 0 | 39644.249 | 39644.249
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | CA: CARP SHOP STOCK TO BE USED BY ELECTRIC SHOP (NO LABOR) | 065 | CLOSED | 0 | 0 | 492 | 492
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | CA: INSTALL NEW COVE BASE - UU EPICENTER REMODEL - BLDG 65 RM201 | 065 | CLOSED | 292.776 | 0 | 526.722 | 526.722
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 16019.49 | 0 | 0 | 0
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | EH&S: ANALYZE MATERIAL SAMPLES FOR UU EPICENTER REMODEL - (N/L) | 065 | CLOSED | 600.9 | 0 | 0 | 0
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 065 | CLOSED | 0 | 0 | 74.4 | 74.4
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | EL:DISCONNECT FOR DEMO BY CONTRACTOR-INSTALL NEW LIGHTING | 065 | CLOSED | 34504.7851 | 0 | 46258.974 | 46258.974
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | ES:CONSTRUCTION SUPPORT FOR UU-EPICENTER REMODEL | 065 | CLOSED | 1629.8254 | 0 | 405.834 | 405.834
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | IN: RENOVATE UU EPICENTER - UU 65 RM 201 | 065 | CLOSED | 1217.064 | 0 | 903.372 | 903.372
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | LO:EPICENTER REMODEL AT UU | 065 | CLOSED | 258.2958 | 0 | 553.242 | 553.242
PJ0004409 | RENOVATE UU EPICENTER - UU 65 RM 201 | MOLLAN, CHERYL L. | CLOSED | 2013-03-15 | PA:PAINT NEW WALLS AND EXISTING CEILING-EPICENTER UU | 065 | CLOSED | 3921.84 | 0 | 5130.948 | 5130.948
PJ0004409 Total | [7 empty] | 332282.5649 | 0 | 323185.0143 | 323185.0143
PJ0004408 | DESIGN ADA ACCESS FOR JUNE COMMENCEMENT (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2013-03-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004408 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: ALPHA FIRE | 180 | CLOSED | 3605.9 | 0 | 829.8171 | 829.8171
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: ASAP REPROGRAPHICS | 180 | CLOSED | 0 | 0 | 24.96 | 24.96
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: BECKER'S DRAPERIES | 180 | CLOSED | 139.1 | 0 | 139.1 | 139.1
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: BKM | 180 | CLOSED | 28825.265 | 0 | 29330.1766 | 29330.1766
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: DOORWAYS | 180 | CLOSED | 4815 | 0 | 3486.06 | 3486.06
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: HPS MECHANICAL | 180 | CLOSED | 5350 | 0 | 5228.02 | 5228.02
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: J.L. FASULO DRYWALL | 180 | CLOSED | 5324.32 | 0 | 6466.01 | 6466.01
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: M.T.I. ELECTRICAL | 180 | CLOSED | 13584.72 | 0 | 13584.72 | 13584.72
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: MACDONALD COMPANY | 180 | CLOSED | 0 | 0 | 1941.9965 | 1941.9965
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: PHIL'S CUSTOM WOODWORKING | 180 | CLOSED | 0 | 0 | 256.8 | 256.8
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: SANTA MARIA ACOUSTICAL | 180 | CLOSED | 3638 | 0 | 4635.24 | 4635.24
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | AD: ZGF ARCHITECTS | 180 | CLOSED | 6099.9951 | 0 | 6527 | 6527
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | CA: BLAKESLEE INSTITUTE EQUIPMENT REMOVAL | 180 | CLOSED | 6186.1235 | 0 | 491.418 | 491.418
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | CP: PROJECT CONTINGENCY | 180 | CLOSED | 107.72 | 0 | 0 | 0
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | EL: BLAKESLEE INSTITUTE PROJECT SUPPORT | 180 | CLOSED | 9000.6814 | 0 | 7392.708 | 7392.708
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | ES: BLAKESLEE PROJECT SUPPORT | 180 | CLOSED | 3701.1862 | 0 | 6013.146 | 6013.146
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | IN: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | 180 | CLOSED | 320.28 | 0 | 384.336 | 384.336
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | LO: BLAKESLEE INSTITUTE PROJECT SUPPORT | 180 | CLOSED | 4116.5916 | 0 | 1368.618 | 1368.618
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | MO: RELOCATE BLAKESLEE INSTITUTE FROM 33-270 TO 180-111 | 180 | CLOSED | 129.6 | 0 | 96.576 | 96.576
PJ0004407 | SP 12/13: BLAKESLEE INSTITUTE -CONVERT TO OFFICE -BLD 180 RM 110 | GONZALES, ALBERT M. | CLOSED | 2013-02-05 | PA: BLAKESLEE INSTITUTE BLDG 180 | 180 | CLOSED | 2798.1218 | 0 | 3281.916 | 3281.916
PJ0004407 Total | [7 empty] | 97742.6045 | 0 | 91478.6182 | 91478.6182
PJ0004406 | BIRD REMEDIATION - REC CENTER POOL DECK - BLDG 43 | GALVEZ, CESAR | CLOSED | 2013-03-13 | AD: OVERHEAD ON AVIARY MANAGEMENT CONTRACT | 043C | CLOSED | 0 | 0 | 443.52 | 443.52
PJ0004406 | BIRD REMEDIATION - REC CENTER POOL DECK - BLDG 43 | GALVEZ, CESAR | CLOSED | 2013-03-13 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 708.31 | 0 | 0 | 0
PJ0004406 | BIRD REMEDIATION - REC CENTER POOL DECK - BLDG 43 | GALVEZ, CESAR | CLOSED | 2013-03-13 | IN: BIRD REMEDIATION - REC CENTER POOL DECK - BLDG 43 | 043C | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004406 Total | [7 empty] | 836.422 | 0 | 571.632 | 571.632
PJ0004405 | INSTALL PANIC BUTTONS AT TICKET OFFICE - PAC BLDG. 06 | LAMPMAN, GREG | CLOSED | 2013-03-12 | AD: CAME SECURITY | 006 | CLOSED | 4253.25 | 0 | 4253.25 | 4253.25
PJ0004405 | INSTALL PANIC BUTTONS AT TICKET OFFICE - PAC BLDG. 06 | LAMPMAN, GREG | CLOSED | 2013-03-12 | ANTS: PROGRAMMING FOR PANIC BUTTONS AT PAC | 006 | CLOSED | 240.24 | 0 | 132.132 | 132.132
PJ0004405 | INSTALL PANIC BUTTONS AT TICKET OFFICE - PAC BLDG. 06 | LAMPMAN, GREG | CLOSED | 2013-03-12 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 474.97 | 0 | 0 | 0
PJ0004405 | INSTALL PANIC BUTTONS AT TICKET OFFICE - PAC BLDG. 06 | LAMPMAN, GREG | CLOSED | 2013-03-12 | IN: INSTALL PANIC BUTTONS AT PAC - BLDG. 06 | 006 | CLOSED | 256.224 | 0 | 96.084 | 96.084
PJ0004405 Total | [7 empty] | 5224.684 | 0 | 4481.466 | 4481.466
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | AD: BELFOR | 170A | CLOSED | 0 | 0 | 64424.0901 | 64424.0901
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | AD: JOC 13.027.005 PUB | 170A | CLOSED | 41984.0608 | 0 | 41984.0715 | 41984.0715
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | CP: PROJECT CONTINGENCY | 170A | CLOSED | 2545.79 | 0 | 0 | 0
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | EL:EMERGENCY ELECTRICAL SUPPORT FOR CERRO VISTA- 170A | 170A | CLOSED | 202.248 | 0 | 168.54 | 168.54
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | IN: FLOOD REMEDIATION - BELFOR - CV - 303, 304 & 403, 404 | 170A | CLOSED | 1281.12 | 0 | 1281.12 | 1281.12
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | PCV CA:EMERGENCY CARPENTRY SUPPORT FOR CERRO VISTA 170A | 170A | CLOSED | 18212.028 | 0 | 14140.584 | 14140.584
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | PCV EL:EMERGENCY ELECTRICAL SUPPORT FOR CERRO VISTA 170A | 170A | CLOSED | 808.992 | 0 | 1196.634 | 1196.634
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | PCV ES:EMERGENCY SUPPORT FOR CERRO VISTA 170A | 170A | CLOSED | 2737.44 | 0 | 4518.721 | 4518.721
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | PCV PA:PAINT UPPER UNITS 404 AND 403 OF MORRO | 170A | CLOSED | 4645.356 | 0 | 3874.914 | 3874.914
PJ0004403 | FLOOD REMEDIATION - BELFOR - 170A CV - 303, 304 & 403, 404 | MOLLAN, CHERYL L. | CLOSED | 2013-03-11 | PCV PL:EMERGENCY SUPPORT FOR CERRO VISTA 170A | 170A | CLOSED | 5717.52 | 0 | 4627.368 | 4627.368
PJ0004403 Total | [7 empty] | 78134.5548 | 0 | 136216.0426 | 136216.0426
PJ0004402 | SP 12/13: CAMPUS BANNER OPTIONS - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2013-03-07 | AD: BRITTEN BANNERS, INC. | GENERAL | CLOSED | 2140 | 0 | 2301.5272 | 2301.5272
PJ0004402 | SP 12/13: CAMPUS BANNER OPTIONS - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2013-03-07 | AD: BUEHLER AND BUEHLER | GENERAL | CLOSED | 25145 | 0 | 19795 | 19795
PJ0004402 | SP 12/13: CAMPUS BANNER OPTIONS - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2013-03-07 | CA:PURCHASE AND INSTALL BANNER BRACKETS ON GRAND AVE POLES | GENERAL | CLOSED | 10011.3541 | 0 | 11465.904 | 11465.904
PJ0004402 | SP 12/13: CAMPUS BANNER OPTIONS - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2013-03-07 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 477.34 | 0 | 0 | 0
PJ0004402 | SP 12/13: CAMPUS BANNER OPTIONS - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2013-03-07 | EL: REMOVE BASE COVERS ON MUSTANG WAY LIGHT POLES | GENERAL | CLOSED | 1439.3316 | 0 | 134.832 | 134.832
PJ0004402 | SP 12/13: CAMPUS BANNER OPTIONS - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2013-03-07 | IN: ASSESS CAMPUS BANNER OPTIONS - CAMPUS WIDE | GENERAL | CLOSED | 320.28 | 0 | 166.728 | 166.728
PJ0004402 Total | [7 empty] | 39533.3057 | 0 | 33863.9912 | 33863.9912
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | AD: FLOOR CONNECTION | 042 | CLOSED | 5196.0591 | 0 | 5157.1325 | 5157.1325
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | AD: MAINO CONSTRUCTION (LOW VALUE PUBLIC WORKS) | 042 | CLOSED | 4798.95 | 0 | 4798.95 | 4798.95
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | AD: WLH BUILDING CO. (FUNDED BY FAC. PLAN.) | 042 | CLOSED | 0 | 0 | 3462.75 | 3462.75
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | CA: SUPPORT FOR MOTT WEIGHT ROOM PROJECT 042-124A | 042 | CLOSED | 596.4786 | 0 | 934.812 | 934.812
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 1733.38 | 0 | 0 | 0
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | CU: CLEAN-UP FOR MOTT WEIGHT ROOM FLOOR REPAIR PROJECT | 042 | CLOSED | 65.592 | 0 | 612.12 | 612.12
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | EH&S: LAB CHARGES PROCESSED THROUGH UTILITIES ACCOUNT(MAT, ONLY) | 042 | CLOSED | 0 | 0 | 37.2 | 37.2
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | EH&S: REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A (N/L) | 042 | CLOSED | 326.1 | 0 | 0 | 0
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | EL: SUPPORT FOR MOTT WEIGHT ROOM PROJECT - 42-124A | 042 | CLOSED | 18796.4561 | 0 | 18823.032 | 18823.032
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | ES: VENTILATION FOR WEIGHT ROOM FLOOR PRJECT - 042 MOTT | 042 | CLOSED | 513.8483 | 0 | 328.062 | 328.062
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | IN: REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | 042 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | PA: PAINTING FOR WEIGHT ROOM FLOOR PROJECT - 042 MOTT | 042 | CLOSED | 8285.1769 | 0 | 8608.086 | 8608.086
PJ0004400 | REPAIR WEIGHT ROOM FLOOR - BLD 42 RM 124A | PIPAL, GAIL | CLOSED | 2013-03-05 | PL: INSTALL HYDRATION STATION AT MOTT WEIGHT ROOM | 042 | CLOSED | 1541.7517 | 0 | 1152.738 | 1152.738
PJ0004400 Total | [7 empty] | 42110.0167 | 0 | 44171.1065 | 44171.1065
PJ0004399 | TENNANT IMPROVEMENT: MODIFY VERIZON CELL SITE AT RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: ENGLEKIRK AND SABOL (SEISMIC PEER REVIEW) | 208 | CLOSED | 500 | 0 | 500 | 500
PJ0004399 | TENNANT IMPROVEMENT: MODIFY VERIZON CELL SITE AT RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: ON TRAC (SHIPPING CHARGES) | 208 | CLOSED | 37.27 | 0 | 74.47 | 74.47
PJ0004399 | TENNANT IMPROVEMENT: MODIFY VERIZON CELL SITE AT RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | CP: PROJECT CONTINGENCY | 208 | CLOSED | 98.6 | 0 | 0 | 0
PJ0004399 | TENNANT IMPROVEMENT: MODIFY VERIZON CELL SITE AT RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | IN: FACILITY SERVICES BUILDING PERMIT FEES | 208 | CLOSED | 123.85 | 0 | 123.85 | 123.85
PJ0004399 | TENNANT IMPROVEMENT: MODIFY VERIZON CELL SITE AT RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | IN: FACILITY SERVICES PLAN REVIEW FEES | 208 | CLOSED | 600 | 0 | 600 | 600
PJ0004399 | TENNANT IMPROVEMENT: MODIFY VERIZON CELL SITE AT RADIO HILL | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | IN: TI - MODIFY VERIZON CELL SITE AT RADIO HILL (MAINT) | 208 | CLOSED | 0 | 0 | 213.52 | 213.52
PJ0004399 Total | [7 empty] | 1359.72 | 0 | 1511.84 | 1511.84
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: CAL POLY FACILITIES BUILDING PERMIT FEES | GEN-AUX | CLOSED | 123.85 | 0 | 123.85 | 123.85
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: CAL POLY FACILITIES PLAN REVIEW FEES | GEN-AUX | CLOSED | 600 | 0 | 600 | 600
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: ENGLEKIRK AND SABOL (SEISMIC PEER REVIEW) | GEN-AUX | CLOSED | 500 | 0 | 500 | 500
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: ON TRAC SHIPPING | GEN-AUX | CLOSED | 32.17 | 0 | 32.17 | 32.17
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | AD: PROJECT COORDINATION FEE | GEN-AUX | CLOSED | 360 | 0 | 360 | 360
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | CP: PROJECT CONTINGENCY | GEN-AUX | CLOSED | 691.92 | 0 | 0 | 0
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | EL: REPAIRS TO AT&T CELL SITE AT R-1 LOT - CONTRACTOR ERROR | GEN-AUX | CLOSED | 0 | 0 | 3153.9 | 3153.9
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | EL:INSTALL NEW ELECTRICAL FOR AT&T TOWER PER PLAN | GEN-AUX | CLOSED | 5400.6838 | 0 | 3030.852 | 3030.852
PJ0004398 | PLAN REVIEW FOR AT&T CELL SITE MODIFICATIONS AT R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2013-03-06 | IN: (MAINT) PLAN REVIEW FOR AT&T CELL SITE MODS AT R-1 PARKING | GEN-AUX | CLOSED | 213.52 | 0 | 613.87 | 613.87
PJ0004398 Total | [7 empty] | 7922.1438 | 0 | 8414.642 | 8414.642
PJ0004397 | INSTALL BIRD NETTING AT PCV - ALISO BLDG. 171A | GONZALES, ALBERT M. | CLOSED | 2013-03-05 | AD: JOC 12.026.015 PRE CON | 171A | CLOSED | 53786.3962 | 0 | 53786.3962 | 53786.3962
PJ0004397 | INSTALL BIRD NETTING AT PCV - ALISO BLDG. 171A | GONZALES, ALBERT M. | CLOSED | 2013-03-05 | CP: PROJECT CONTINGENCY | 171A | CLOSED | 4714.29 | 0 | 0 | 0
PJ0004397 | INSTALL BIRD NETTING AT PCV - ALISO BLDG. 171A | GONZALES, ALBERT M. | CLOSED | 2013-03-05 | IN: INSTALL BIRD NETTING AT PCV - ALISO BLDG. 171A | 171A | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004397 Total | [7 empty] | 58628.7982 | 0 | 53914.5082 | 53914.5082
PJ0004395 | TINT WINDOWS IN ANTS OFFICES WEST SIDE ENTRANCE - BLDG 58 | GALVEZ, CESAR | CLOSED | 2013-02-25 | AD: ATD WINDOW TINTING | 058 | CLOSED | 1086.05 | 0 | 1086.05 | 1086.05
PJ0004395 | TINT WINDOWS IN ANTS OFFICES WEST SIDE ENTRANCE - BLDG 58 | GALVEZ, CESAR | CLOSED | 2013-02-25 | CA: REPLACE 1 PLEXIGLASS WINDOW WITH GLASS - BLDG 58 | 058 | CLOSED | 180.7586 | 0 | 200.664 | 200.664
PJ0004395 | TINT WINDOWS IN ANTS OFFICES WEST SIDE ENTRANCE - BLDG 58 | GALVEZ, CESAR | CLOSED | 2013-02-25 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 133.82 | 0 | 0 | 0
PJ0004395 | TINT WINDOWS IN ANTS OFFICES WEST SIDE ENTRANCE - BLDG 58 | GALVEZ, CESAR | CLOSED | 2013-02-25 | IN: TINT WINDOWS IN ANTS OFFICES WEST SIDE ENTRANCE - BLDG 58 | 058 | CLOSED | 71.1022 | 0 | 64.056 | 64.056
PJ0004395 Total | [7 empty] | 1471.7308 | 0 | 1350.77 | 1350.77
PJ0004393 | QUARTERLY MAINTENANCE WALK AT THE PAC 06 - JAN. 2013 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-25 | CA: PAC QUARTERLY MAINTENANCE ITEMS - JAN 2013 | 006 | CLOSED | 0 | 0 | 1007.35 | 1007.35
PJ0004393 | QUARTERLY MAINTENANCE WALK AT THE PAC 06 - JAN. 2013 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004393 | QUARTERLY MAINTENANCE WALK AT THE PAC 06 - JAN. 2013 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-25 | ES:PAC QUARTERLY MAINTENANCE ITEMS - JAN 2013 | 006 | CLOSED | 208.12 | 0 | 78.045 | 78.045
PJ0004393 | QUARTERLY MAINTENANCE WALK AT THE PAC 06 - JAN. 2013 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-25 | LO:PAC QUARTERLY MAINTENANCE ITEMS - JAN 2013 | 006 | CLOSED | 0 | 0 | 72.555 | 72.555
PJ0004393 | QUARTERLY MAINTENANCE WALK AT THE PAC 06 - JAN. 2013 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-25 | PA:PAC QUARTERLY MAINTENANCE ITEMS - JAN 2013 | 006 | CLOSED | 0 | 0 | 24.735 | 24.735
PJ0004393 Total | [7 empty] | 208.12 | 0 | 1182.685 | 1182.685
PJ0004391 | DESIGN CONVERSION: PEET'S COFFEE TO TACOS TO GO -171I | LAMPMAN, GREG | CLOSED | 2013-02-14 | AD: ASAP REPROGRAPHICS | 171I | CLOSED | 0 | 0 | 239.43 | 239.43
PJ0004391 | DESIGN CONVERSION: PEET'S COFFEE TO TACOS TO GO -171I | LAMPMAN, GREG | CLOSED | 2013-02-14 | AD: DIVISION OF STATE ARCHITECT | 171I | CLOSED | 1250 | 0 | 1250 | 1250
PJ0004391 | DESIGN CONVERSION: PEET'S COFFEE TO TACOS TO GO -171I | LAMPMAN, GREG | CLOSED | 2013-02-14 | AD: PMSM ARCHITECTS | 171I | CLOSED | 53072 | 0 | 51701.116 | 51701.116
PJ0004391 | DESIGN CONVERSION: PEET'S COFFEE TO TACOS TO GO -171I | LAMPMAN, GREG | CLOSED | 2013-02-14 | AD: STATE FIRE MARSHAL FEES | 171I | CLOSED | 0 | 0 | 1315 | 1315
PJ0004391 | DESIGN CONVERSION: PEET'S COFFEE TO TACOS TO GO -171I | LAMPMAN, GREG | CLOSED | 2013-02-14 | CP: PROJECT CONTINGENCY | 171I | CLOSED | 4057.2 | 0 | 0 | 0
PJ0004391 Total | [7 empty] | 58379.2 | 0 | 54505.546 | 54505.546
PJ0004388 | REMOVE CARPET & INSTALL HARD FLOORING-BLD 43A RMS 254-256(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-11 | AD: FLOOR CONNECTION | 043A | CLOSED | 3790 | 0 | 3790 | 3790
PJ0004388 | REMOVE CARPET & INSTALL HARD FLOORING-BLD 43A RMS 254-256(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-11 | CP: PROJECT CONTINGENCY | 043A | CLOSED | 0 | 0 | 0 | 0
PJ0004388 | REMOVE CARPET & INSTALL HARD FLOORING-BLD 43A RMS 254-256(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-11 | EH&S: REMOVE CARPET & INSTALL HARD FLOORING-BLD 43A RMS 254-256 | 043A | CLOSED | 0 | 0 | 79.25 | 79.25
PJ0004388 | REMOVE CARPET & INSTALL HARD FLOORING-BLD 43A RMS 254-256(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2013-02-11 | IN: REMOVE CARPET & INSTALL HARD FLOORING-BLD 43A RMS 254-256 | 043A | CLOSED | 106.76 | 0 | 53.38 | 53.38
PJ0004388 Total | [7 empty] | 3896.76 | 0 | 3922.63 | 3922.63
PJ0004387 | INSTALL PLUGMOLD ALONG WINDOW MULLIONS - BLD 35-2ND, 3RD& 4TH FL | GONZALES, ALBERT M. | CLOSED | 2013-02-08 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 798.95 | 0 | 0 | 0
PJ0004387 | INSTALL PLUGMOLD ALONG WINDOW MULLIONS - BLD 35-2ND, 3RD& 4TH FL | GONZALES, ALBERT M. | CLOSED | 2013-02-08 | EL:PURCHASE AND INSTALL PLUGMOLD ON 2ND & 4TH FLOOR | 035 | CLOSED | 7861.3663 | 0 | 9127.212 | 9127.212
PJ0004387 | INSTALL PLUGMOLD ALONG WINDOW MULLIONS - BLD 35-2ND, 3RD& 4TH FL | GONZALES, ALBERT M. | CLOSED | 2013-02-08 | IN: INSTALL PLUGMOLD ALONG WINDOW MULLIONS - BLD 35-2ND & 4TH FL | 035 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004387 Total | [7 empty] | 8788.4283 | 0 | 9191.268 | 9191.268
PJ0004385 | HOUSING WIRELESS PROJECT - PHASES 1 & 2 - PCV AND CV APTS | BRENNAN, MICHAEL | CLOSED | 2013-02-19 | AD: JOC 13.027.007 PUB | RESIDENCE | CLOSED | 130903.8 | 0 | 88110.3484 | 88110.3484
PJ0004385 | HOUSING WIRELESS PROJECT - PHASES 1 & 2 - PCV AND CV APTS | BRENNAN, MICHAEL | CLOSED | 2013-02-19 | AD: MATERIALS INSTALLED BY JOC | RESIDENCE | CLOSED | 0 | 0 | 1361.44 | 1361.44
PJ0004385 | HOUSING WIRELESS PROJECT - PHASES 1 & 2 - PCV AND CV APTS | BRENNAN, MICHAEL | CLOSED | 2013-02-19 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 15062.87 | 0 | 0 | 0
PJ0004385 | HOUSING WIRELESS PROJECT - PHASES 1 & 2 - PCV AND CV APTS | BRENNAN, MICHAEL | CLOSED | 2013-02-19 | IN: HOUSING WIRELESS PROJECT - PHASE 1 - PCV AND CV | RESIDENCE | CLOSED | 2851.1326 | 0 | 288.252 | 288.252
PJ0004385 Total | [7 empty] | 148817.8026 | 0 | 89760.0404 | 89760.0404
PJ0004384 | INSTALL UV FILM, TINT OR OTHER LIGHT FILTER -BLD 58 RM 107 | GALVEZ, CESAR | CLOSED | 2013-02-05 | AD: ADT WINDOW TINTING | 058 | CLOSED | 2483.47 | 0 | 2483.47 | 2483.47
PJ0004384 | INSTALL UV FILM, TINT OR OTHER LIGHT FILTER -BLD 58 RM 107 | GALVEZ, CESAR | CLOSED | 2013-02-05 | AD: COASTAL JANITORIAL | 058 | CLOSED | 233.5596 | 0 | 218.28 | 218.28
PJ0004384 | INSTALL UV FILM, TINT OR OTHER LIGHT FILTER -BLD 58 RM 107 | GALVEZ, CESAR | CLOSED | 2013-02-05 | CA: REPLACE 8 PLEXIGLASS WINDOWS WITH GLASS - BLDG 58 | 058 | CLOSED | 1244.2703 | 0 | 1010.034 | 1010.034
PJ0004384 | INSTALL UV FILM, TINT OR OTHER LIGHT FILTER -BLD 58 RM 107 | GALVEZ, CESAR | CLOSED | 2013-02-05 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 145.59 | 0 | 0 | 0
PJ0004384 | INSTALL UV FILM, TINT OR OTHER LIGHT FILTER -BLD 58 RM 107 | GALVEZ, CESAR | CLOSED | 2013-02-05 | IN: INSTALL UV FILM, TINT OR OTHER LIGHT FILTER -BLD 58 RM 107 | 058 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004384 Total | [7 empty] | 4170.9459 | 0 | 3775.84 | 3775.84
PJ0004383 | INSTALL TV MONITOR IN CAREER SERVICES LOBBY - BLD 124 LOBBY | MCNALLY, CURTIS | CLOSED | 2013-02-08 | CA: REMOVE BULLETIN, CORNER SHELF, DRILL HOLES & MOUNT BRACKET | 124 | CLOSED | 733.0078 | 0 | 218.244 | 218.244
PJ0004383 | INSTALL TV MONITOR IN CAREER SERVICES LOBBY - BLD 124 LOBBY | MCNALLY, CURTIS | CLOSED | 2013-02-08 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 238.96 | 0 | 0 | 0
PJ0004383 | INSTALL TV MONITOR IN CAREER SERVICES LOBBY - BLD 124 LOBBY | MCNALLY, CURTIS | CLOSED | 2013-02-08 | EL: INSTALL POWER OUTLET FOR MONITOR HIGH ON WALL | 124 | CLOSED | 2700.6802 | 0 | 475.908 | 475.908
PJ0004383 | INSTALL TV MONITOR IN CAREER SERVICES LOBBY - BLD 124 LOBBY | MCNALLY, CURTIS | CLOSED | 2013-02-08 | IN: INSTALL TV MONITOR IN CAREER SERVICES LOBBY - BLD 124 LOBBY | 124 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004383 Total | [7 empty] | 3800.7599 | 0 | 790.236 | 790.236
PJ0004382 | RENOVATE OFFICE COMPLEX - BLDG 25 RMS 125 A-E | KUENTZEL, DOUGLAS A. | CLOSED | 2013-02-05 | AD: ASAP REPROGRAPHICS | 025 | CLOSED | 0 | 0 | 75 | 75
PJ0004382 | RENOVATE OFFICE COMPLEX - BLDG 25 RMS 125 A-E | KUENTZEL, DOUGLAS A. | CLOSED | 2013-02-05 | AD: FURNITURE INSTALLATION TEAM | 025 | CLOSED | 4391.5261 | 0 | 4720.8935 | 4720.8935
PJ0004382 | RENOVATE OFFICE COMPLEX - BLDG 25 RMS 125 A-E | KUENTZEL, DOUGLAS A. | CLOSED | 2013-02-05 | CP: PROJECT CONTINGENCY | 025 | CLOSED | 1183.25 | 0 | 0 | 0
PJ0004382 | RENOVATE OFFICE COMPLEX - BLDG 25 RMS 125 A-E | KUENTZEL, DOUGLAS A. | CLOSED | 2013-02-05 | EL: INSTALL CEILING FANS | 025 | CLOSED | 6901.3663 | 0 | 9873.906 | 9873.906
PJ0004382 | RENOVATE OFFICE COMPLEX - BLDG 25 RMS 125 A-E | KUENTZEL, DOUGLAS A. | CLOSED | 2013-02-05 | IN: RENOVATE OFFICE COMPLEX - BLDG 25 RMS 125 A-E | 025 | CLOSED | 256.224 | 0 | 64.056 | 64.056
PJ0004382 Total | [7 empty] | 12732.3664 | 0 | 14733.8555 | 14733.8555
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | AD: (SR FUNDING) JOC 13.028.050 MAINO | 038 | CLOSED | 26243.91 | 0 | 25613.36 | 25613.36
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | AD: (SR FUNDING) PARC ENVIRONMENTAL | 038 | CLOSED | 4800 | 0 | 4400 | 4400
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | CA:SMART ROOM UPGRADES BLDG 38 RMS 201,202,222,225,226,227 | 038 | CLOSED | 2891.64 | 0 | 2038.842 | 2038.842
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | EH&S: (SR FUNDING) (N/L) | 038 | CLOSED | 164.5 | 0 | 0 | 0
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | EL:SMART ROOM UPGRADES BLDG 38 RMS 201,202,222,225,226,227 | 038 | CLOSED | 6444.96 | 0 | 11499.084 | 11499.084
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | IN: (DEPT FUNDING) INSPECTION FOR SMARTROOM UPGRADES - 038 | 038 | CLOSED | 0 | 0 | 352.308 | 352.308
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | IN: (SR FUNDING) INSPECTION FOR SMARTROOM UPGRADES - 038 | 038 | CLOSED | 213.52 | 0 | 26.69 | 26.69
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | LO: (SR FUNDING) ORANGE CORES - 38 RMS 201,202,222,225,226,227 | 038 | CLOSED | 53.859 | 0 | 120.925 | 120.925
PJ0004381 | SR13/14: SMARTRM UPGRADES - 38 - 201,202,222,225,226,227(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2013-02-06 | MO: (SR FUNDING) MOVE TAB ARM CHAIRS AT BLDG 38 | 038 | CLOSED | 648 | 0 | 90.54 | 90.54
PJ0004381 Total | [7 empty] | 41460.389 | 0 | 44141.749 | 44141.749
PJ0004380 | SEAL VENT ABOVE DOOR & PAINT OVER (NO ESTIMATE) - BLD 81 RM 5 | GALVEZ, CESAR | CLOSED | 2013-02-06 | CA: COVER/PATCH APROX: 12'X12" HOLE ABOVE DOOR - 081-0005 | 081 | CLOSED | 266.3359 | 0 | 256.026 | 256.026
PJ0004380 | SEAL VENT ABOVE DOOR & PAINT OVER (NO ESTIMATE) - BLD 81 RM 5 | GALVEZ, CESAR | CLOSED | 2013-02-06 | CP: PROJECT CONTINGENCY | 081 | CLOSED | 176.34 | 0 | 0 | 0
PJ0004380 | SEAL VENT ABOVE DOOR & PAINT OVER (NO ESTIMATE) - BLD 81 RM 5 | GALVEZ, CESAR | CLOSED | 2013-02-06 | EL: TERMINATE ELECTRCIAL AND REMOVE VENT/FAN FROM WALL- 081-0005 | 081 | CLOSED | 1254.679 | 0 | 84 | 84
PJ0004380 | SEAL VENT ABOVE DOOR & PAINT OVER (NO ESTIMATE) - BLD 81 RM 5 | GALVEZ, CESAR | CLOSED | 2013-02-06 | IN: SEAL VENT ABOVE DOOR & PAINT OVER - BLD 81 RM 5 | 081 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004380 | SEAL VENT ABOVE DOOR & PAINT OVER (NO ESTIMATE) - BLD 81 RM 5 | GALVEZ, CESAR | CLOSED | 2013-02-06 | PA: PATCH AND PAINT HOLE ABOVE DOOR AND OFFICE -081-0005 | 081 | CLOSED | 653.64 | 0 | 892.296 | 892.296
PJ0004380 Total | [7 empty] | 2415.0509 | 0 | 1296.378 | 1296.378
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | CA: REMOVE AND SET UP WEST SIDE BLEACHERS AT MOTT GYM-4/19 | GENERAL | CLOSED | 0 | 0 | 438.81 | 438.81
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | CA: SUPPORT FOR OPEN HOUSE - APRIL 19 2013 | GENERAL | CLOSED | 0 | 0 | 2172.36 | 2172.36
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | CU: SUPPORT FOR 2013 OPEN HOUSE - 4/20 | GENERAL | CLOSED | 0 | 0 | 4524.4043 | 4524.4043
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | EL: SUPPORT FOR 2013 OPEN HOUSE - APRIL 20 | GENERAL | CLOSED | 0 | 0 | 2182.17 | 2182.17
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | EO: SUPPORT FOR 2013 OPEN HOUSE- 4/20 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | LA: SUPPORT FOR 2013 OPEN HOUSE - APRIL 20 | GENERAL | CLOSED | 0 | 0 | 4467.794 | 4467.794
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | PL: SUPPORT FOR 2013 OPEN HOUSE-APRIL 20 | GENERAL | CLOSED | 0 | 0 | 393.575 | 393.575
PJ0004379 | SUPPORT FOR OPEN HOUSE // APRIL 19 2013 (MAINT) | POPHAM, DONALD J. | CLOSED | 2013-02-07 | RE: SUPPORT FOR 2013 OPEN HOUSE-4/20 | GENERAL | CLOSED | 0 | 0 | 794.78 | 794.78
PJ0004379 Total | [7 empty] | 0 | 0 | 14973.8933 | 14973.8933
PJ0004378 | HANG FOUR TVS & RELOCATE BULLETIN BOARDS - H.C. BLD 27 | LAMPMAN, GREG | CLOSED | 2013-02-04 | AD: JOC 13.028.017 MAINO | 027 | CLOSED | 2219.5866 | 0 | 2219.5866 | 2219.5866
PJ0004378 | HANG FOUR TVS & RELOCATE BULLETIN BOARDS - H.C. BLD 27 | LAMPMAN, GREG | CLOSED | 2013-02-04 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 278.61 | 0 | 0 | 0
PJ0004378 | HANG FOUR TVS & RELOCATE BULLETIN BOARDS - H.C. BLD 27 | LAMPMAN, GREG | CLOSED | 2013-02-04 | IN: HANG FOUR TVS & RELOCATE BULLETIN BOARDS - H.C. BLD 27 | 027 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004378 Total | [7 empty] | 2626.3086 | 0 | 2283.6426 | 2283.6426
PJ0004375 | SR 12/13: ISOLATE/REPAIR UTILIDOR LEAKS -CAMPUS WIDE(SEE PJ4445) | PIPAL, GAIL | CLOSED | 2013-02-01 | CA: PROVIDE SUPPORT FOR UTILIDOR LEAK | GENERAL | CLOSED | 0 | 0 | 234.95 | 234.95
PJ0004375 | SR 12/13: ISOLATE/REPAIR UTILIDOR LEAKS -CAMPUS WIDE(SEE PJ4445) | PIPAL, GAIL | CLOSED | 2013-02-01 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004375 | SR 12/13: ISOLATE/REPAIR UTILIDOR LEAKS -CAMPUS WIDE(SEE PJ4445) | PIPAL, GAIL | CLOSED | 2013-02-01 | EL: PROVIDE SUPPORT FOR UTILIDOR LEAK | GENERAL | CLOSED | 0 | 0 | 56.18 | 56.18
PJ0004375 | SR 12/13: ISOLATE/REPAIR UTILIDOR LEAKS -CAMPUS WIDE(SEE PJ4445) | PIPAL, GAIL | CLOSED | 2013-02-01 | PL: PROVIDE SUPPORT FOR UTILIDOR LEAK | GENERAL | CLOSED | 0 | 0 | 380.87 | 380.87
PJ0004375 Total | [7 empty] | 0 | 0 | 672 | 672
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | AD: JOC 13.028.004 MAINO | 042 | CLOSED | 13714.2542 | 0 | 13714.2542 | 13714.2542
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 785.86 | 0 | 0 | 0
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 042 | CLOSED | 0 | 0 | 72.6 | 72.6
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | EH&S: LEAD SAMPLING FOR MOTT GYM HOOP REMOVAL - BLDG. 042 (N/L) | 042 | CLOSED | 326.1 | 0 | 0 | 0
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | EL:DISCONNECT FOR SAFE DEMO- REWIRE SHOTCLOCKS | 042 | CLOSED | 11546.3239 | 0 | 10216.1849 | 10216.1849
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | IN: REMOVE OLD N, S, & W HOOPS & REWIRE SHOT CLOCKS - BLDG. 42 | 042 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004373 | REMOVE OLD N, S, & W HOOPS & REWIRE ELECTRICAL TO SHOT CLOCKS 42 | MOLLAN, CHERYL L. | CLOSED | 2013-02-01 | PA:PAINT CONDUIT WHITE TO MATCH EXISTING | 042 | CLOSED | 5361.84 | 0 | 287.292 | 287.292
PJ0004373 Total | [7 empty] | 31798.4341 | 0 | 24354.3871 | 24354.3871
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | AD: FLOOR CONNECTION | 052 | CLOSED | 15515 | 0 | 12311.5163 | 12311.5163
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | AD: JOC 13.027.006 PUB | 052 | CLOSED | 31307.8255 | 0 | 27483.378 | 27483.378
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | AD: MCKENNA ENVIRONMENTAL | 052 | CLOSED | 4815 | 0 | 4191.19 | 4191.19
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | CA: BLDG 52 ROOM E27 MODIFY CABINET | 052 | CLOSED | 1244.2703 | 0 | 440.205 | 440.205
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 3383.68 | 0 | 0 | 0
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | EH&S: SMART CLASSROOM UPGRADE - BLD 52 RM E27 (N/L) | 052 | CLOSED | 153.201 | 0 | 0 | 0
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | EL:SMART CLASSROOM ELECTRICAL UPGRADES BLDG 52-E27 | 052 | CLOSED | 7621.3663 | 0 | 8528.4 | 8528.4
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | ES:REROUTE SIGNAL WIRING | 052 | CLOSED | 675.6804 | 0 | 3968.0076 | 3968.0076
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | IN: SMART CLASSROOM UPGRADE - BLD 52 RM E27 | 052 | CLOSED | 1281.12 | 0 | 576.504 | 576.504
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | LO:ORANGE CORE LOCKS | 052 | CLOSED | 189.4381 | 0 | 174.132 | 174.132
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | PA:PAINT CLASSROOM | 052 | CLOSED | 4999.296 | 0 | 4899.138 | 4899.138
PJ0004371 | SMART ROOM UPGRADE - BLD 52 RM E27 | BRENNAN, MICHAEL | CLOSED | 2013-01-29 | PL:TERMINATE PLUMBING AT LECTERN | 052 | CLOSED | 761.0988 | 0 | 130.584 | 130.584
PJ0004371 Total | [7 empty] | 71946.9764 | 0 | 62703.0549 | 62703.0549
PJ0004370 | INSTALL AWNING OVER BACK DOOR - BLD 58 | GALVEZ, CESAR | CLOSED | 2012-11-30 | AD: SHORELINE AWNING | 058 | CLOSED | 936.25 | 0 | 936.25 | 936.25
PJ0004370 | INSTALL AWNING OVER BACK DOOR - BLD 58 | GALVEZ, CESAR | CLOSED | 2012-11-30 | CA: PRE DRILL HOLES FOR AWNING - BLDG 058-107 EXT DOOR | 058 | CLOSED | 56.388 | 0 | 28.194 | 28.194
PJ0004370 | INSTALL AWNING OVER BACK DOOR - BLD 58 | GALVEZ, CESAR | CLOSED | 2012-11-30 | CP: PROJECT CONTINGENCY (N/L) | 058 | CLOSED | 4.55 | 0 | 0 | 0
PJ0004370 | INSTALL AWNING OVER BACK DOOR - BLD 58 | GALVEZ, CESAR | CLOSED | 2012-11-30 | EL: TERMINATE/MOVE PHOTO CELL ON LIGHT (ON 24/7) - BLD 58 | 058 | CLOSED | 101.124 | 0 | 288.744 | 288.744
PJ0004370 | INSTALL AWNING OVER BACK DOOR - BLD 58 | GALVEZ, CESAR | CLOSED | 2012-11-30 | IN: INSTALL AWNING OVER BACK DOOR - BLD 58 | 058 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004370 Total | [7 empty] | 1162.368 | 0 | 1317.244 | 1317.244
PJ0004366 | INSTALL PANIC ALARMS - REC CTR 43 RM 110C | MOLLAN, CHERYL L. | CLOSED | 2013-01-23 | ANTS: PROGRAMMING FOR PANIC ALARM AT REC CENTER 43-110C | 043 | CLOSED | 96.096 | 0 | 48.048 | 48.048
PJ0004366 | INSTALL PANIC ALARMS - REC CTR 43 RM 110C | MOLLAN, CHERYL L. | CLOSED | 2013-01-23 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 16.02 | 0 | 0 | 0
PJ0004366 | INSTALL PANIC ALARMS - REC CTR 43 RM 110C | MOLLAN, CHERYL L. | CLOSED | 2013-01-23 | IN: INSTALL PANIC ALARMS - REC CTR 43 RM 110C | 043 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004366 Total | [7 empty] | 176.172 | 0 | 112.104 | 112.104
PJ0004364 | SR 12/13: REPLACE FLOORING - BLD 20 RM 126 | LAMPMAN, GREG | CLOSED | 2013-01-23 | AD: FLOOR CONNECTION | 020 | CLOSED | 3610 | 0 | 3610 | 3610
PJ0004364 | SR 12/13: REPLACE FLOORING - BLD 20 RM 126 | LAMPMAN, GREG | CLOSED | 2013-01-23 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 0 | 0 | 0 | 0
PJ0004364 | SR 12/13: REPLACE FLOORING - BLD 20 RM 126 | LAMPMAN, GREG | CLOSED | 2013-01-23 | EL: REMOVE POWER POLE. | 020 | CLOSED | 447.1928 | 0 | 185.96 | 185.96
PJ0004364 | SR 12/13: REPLACE FLOORING - BLD 20 RM 126 | LAMPMAN, GREG | CLOSED | 2013-01-23 | IN: SR 12/13: REPLACE FLOORING - BLD 20 RM 126 | 020 | CLOSED | 53.38 | 0 | 26.69 | 26.69
PJ0004364 Total | [7 empty] | 4110.5728 | 0 | 3822.65 | 3822.65
PJ0004362 | TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B | HOGAN, MIKE | CLOSED | 2013-01-17 | AD: CAL POLY BUILDING PERMIT FEES | 083 | CLOSED | 1509.5 | 0 | 1509.5 | 1509.5
PJ0004362 | TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B | HOGAN, MIKE | CLOSED | 2013-01-17 | AD: CAL POLY PLAN REVIEW FEES | 083 | CLOSED | 1500 | 0 | 1500 | 1500
PJ0004362 | TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B | HOGAN, MIKE | CLOSED | 2013-01-17 | AD: STATE FIRE MARSHAL REVIEW AND INSPECTION FEES | 083 | CLOSED | 1112.8 | 0 | 0 | 0
PJ0004362 | TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B | HOGAN, MIKE | CLOSED | 2013-01-17 | ANTS: PROGRAM ALARMS FOR H.T. HARVEY LAB SPACE 1B - TECH PARK | 083 | CLOSED | 80.08 | 0 | 140.14 | 140.14
PJ0004362 | TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B | HOGAN, MIKE | CLOSED | 2013-01-17 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 332.15 | 0 | 0 | 0
PJ0004362 | TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B | HOGAN, MIKE | CLOSED | 2013-01-17 | IN: TENANT IMPROVMENT: H.T. HARVEY TECH PARK SPACE 1B (MAINT) | 083 | CLOSED | 0 | 0 | 1494.64 | 1494.64
PJ0004362 Total | [7 empty] | 4534.53 | 0 | 4644.28 | 4644.28
PJ0004361 | SR 12/13: SURVEY FIRE ALARM - ADMN 01 | GRIFFIN, PATRICK E. | CLOSED | 2013-01-17 | AD: ALPHA FIRE | 001 | CLOSED | 1250 | 0 | 1250 | 1250
PJ0004361 | SR 12/13: SURVEY FIRE ALARM - ADMN 01 | GRIFFIN, PATRICK E. | CLOSED | 2013-01-17 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0004361 Total | [7 empty] | 1250 | 0 | 1250 | 1250
PJ0004360 | REMOVE (9) 4' X 6' BOARDS & SHELVING FROM WALLS - BLD 124 RM 113 | GONZALES, ALBERT M. | CLOSED | 2013-01-15 | CA: REMOVE NINE (9) BULLETIN BOARDS (5/18/13) | 124 | CLOSED | 1536.1235 | 0 | 959.22 | 959.22
PJ0004360 | REMOVE (9) 4' X 6' BOARDS & SHELVING FROM WALLS - BLD 124 RM 113 | GONZALES, ALBERT M. | CLOSED | 2013-01-15 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 314.56 | 0 | 0 | 0
PJ0004360 | REMOVE (9) 4' X 6' BOARDS & SHELVING FROM WALLS - BLD 124 RM 113 | GONZALES, ALBERT M. | CLOSED | 2013-01-15 | MO: SURPLUS PICKUP NINE (9) BULLETINS & SHELVING 5/20 - BLDG 124 | 124 | CLOSED | 64.8 | 0 | 6.036 | 6.036
PJ0004360 | REMOVE (9) 4' X 6' BOARDS & SHELVING FROM WALLS - BLD 124 RM 113 | GONZALES, ALBERT M. | CLOSED | 2013-01-15 | PA: PATCH & PAINT SO, EAST & NO. WALLS AFTER 5/18 WKD - BLD 124 | 124 | CLOSED | 1544.736 | 0 | 927.096 | 927.096
PJ0004360 Total | [7 empty] | 3460.2195 | 0 | 1892.352 | 1892.352
PJ0004359 | SR 12/13: CONNECT POWER AND ADD LIGHTING FOR DRIVEWAY GATE | GONZALES, ALBERT M. | CLOSED | 2013-01-16 | CA:POUR CONCRETE FOR LIGHT POST AT DRIVEWAY 51 | 051 | CLOSED | 1427.76 | 0 | 883.5697 | 883.5697
PJ0004359 | SR 12/13: CONNECT POWER AND ADD LIGHTING FOR DRIVEWAY GATE | GONZALES, ALBERT M. | CLOSED | 2013-01-16 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 1287.63 | 0 | 0 | 0
PJ0004359 | SR 12/13: CONNECT POWER AND ADD LIGHTING FOR DRIVEWAY GATE | GONZALES, ALBERT M. | CLOSED | 2013-01-16 | EL:INSTALL LIGHTING AND GATE POWER AT 51 | 051 | CLOSED | 5696.64 | 0 | 13786.67 | 13786.67
PJ0004359 | SR 12/13: CONNECT POWER AND ADD LIGHTING FOR DRIVEWAY GATE | GONZALES, ALBERT M. | CLOSED | 2013-01-16 | EO:TRENCH FOR ELECTRIC GATE AND LIGHT AT 51 | 051 | CLOSED | 1712.45 | 0 | 2641.9 | 2641.9
PJ0004359 | SR 12/13: CONNECT POWER AND ADD LIGHTING FOR DRIVEWAY GATE | GONZALES, ALBERT M. | CLOSED | 2013-01-16 | IN: SR 12/13: CONNECT POWER AND ADD LIGHTING FOR DRIVEWAY GATE | 051 | CLOSED | 285.0492 | 0 | 106.76 | 106.76
PJ0004359 Total | [7 empty] | 10409.5292 | 0 | 17418.8997 | 17418.8997
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | AD: J.L. FASULO DRYWALL | 036 | CLOSED | 3595.2 | 0 | 3595.2 | 3595.2
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | AD: JOC 13.028.005 MAINO | 036 | CLOSED | 29453.355 | 0 | 26139.9609 | 26139.9609
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 4061.9 | 0 | 0 | 0
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | EL: CLEAN UP (E) ELECTRICAL AND HOOK UP HVAC UNIT | 036 | CLOSED | 3300.6838 | 0 | 2167.176 | 2167.176
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | IN: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | 036 | CLOSED | 256.224 | 0 | 448.392 | 448.392
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | LO: INSTALL ONE EXTERIOR LOCK AND CLOSURE. | 036 | CLOSED | 2076.5916 | 0 | 1129.464 | 1129.464
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | PA: PAINT WALLS AND CEILING WITH CP-2 PAINT | 036 | CLOSED | 3242.2916 | 0 | 1453.32 | 1453.32
PJ0004356 | SP 12/13: RENOVATE OLD LIVE SCAN AREA FOR USE BY AUDITORS-BLD 36 | LAMPMAN, GREG | CLOSED | 2013-01-15 | PL: REMOVE GAS LINE FOR RENO AT OLD LIVE SCAN AREA | 036 | CLOSED | 130.584 | 0 | 65.292 | 65.292
PJ0004356 Total | [7 empty] | 46116.83 | 0 | 34998.8049 | 34998.8049
PJ0004353 | INSTALL ELECTRICAL AND BRACKET FOR FLATSCREEN TV - MPC 155-C106 | GALVEZ, CESAR | CLOSED | 2013-01-08 | CA: INSTALL TV BRACKET AND MOUNTS IN HALLWAY BY RM 100 -BLDG 155 | 155 | CLOSED | 610.6718 | 0 | 673.572 | 673.572
PJ0004353 | INSTALL ELECTRICAL AND BRACKET FOR FLATSCREEN TV - MPC 155-C106 | GALVEZ, CESAR | CLOSED | 2013-01-08 | CP: PROJECT CONTINGENCY | 155 | CLOSED | 195.04 | 0 | 0 | 0
PJ0004353 | INSTALL ELECTRICAL AND BRACKET FOR FLATSCREEN TV - MPC 155-C106 | GALVEZ, CESAR | CLOSED | 2013-01-08 | EL: PROVIDE ELECTRICAL FROM CEILING DOWN TO TV - BLDG 155 | 155 | CLOSED | 1980.6802 | 0 | 1734.336 | 1734.336
PJ0004353 | INSTALL ELECTRICAL AND BRACKET FOR FLATSCREEN TV - MPC 155-C106 | GALVEZ, CESAR | CLOSED | 2013-01-08 | IN: INSTALL ELECTRICAL AND BRACKET FOR FLATSCREEN TV-MPC155-C106 | 155 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004353 Total | [7 empty] | 2850.448 | 0 | 2471.964 | 2471.964
PJ0004351 | DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | NORTON, DAVE | CLOSED | 2012-12-27 | AD: ASAP REPROGRAPHICS | 170E | CLOSED | 0 | 0 | 93.6 | 93.6
PJ0004351 | DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | NORTON, DAVE | CLOSED | 2012-12-27 | AD: ENGLEKIRK AND SABOL | 170E | CLOSED | 1070 | 0 | 535 | 535
PJ0004351 | DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | NORTON, DAVE | CLOSED | 2012-12-27 | AD: OMNI DESIGN | 170E | CLOSED | 12759.7607 | 0 | 12759.75 | 12759.75
PJ0004351 | DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | NORTON, DAVE | CLOSED | 2012-12-27 | AD: ON TRAC SHIPPING | 170E | CLOSED | 0 | 0 | 29.6604 | 29.6604
PJ0004351 | DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | NORTON, DAVE | CLOSED | 2012-12-27 | CP: PROJECT CONTINGENCY | 170E | CLOSED | 1480.91 | 0 | 0 | 0
PJ0004351 | DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | NORTON, DAVE | CLOSED | 2012-12-27 | IN: DESIGN CUSTODIAL BREAKROOM, CERRO VISTA BLDG 170E | 170E | CLOSED | 256.224 | 0 | 64.056 | 64.056
PJ0004351 Total | [7 empty] | 15566.8947 | 0 | 13482.0664 | 13482.0664
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: BUEHLER & BUEHLER | 035 | CLOSED | 3424 | 0 | 3424 | 3424
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: FLOOR CONNECTION | 035 | CLOSED | 7257.3606 | 0 | 7257.3606 | 7257.3606
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 3510.67 | 0 | 3510.67 | 3510.67
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: JOC 13.028.019 MAINO | 035 | CLOSED | 97086.985 | 0 | 95730.3534 | 95730.3534
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: MORELAND THOMPSON (SPLIT FUNDING) | 035 | CLOSED | 6772.3403 | 0 | 9719.88 | 9719.88
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: MORLEAND THOMPSON | 035 | CLOSED | 5457 | 0 | 5457 | 5457
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 3852 | 0 | 3595.2 | 3595.2
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | CA: INSTALL GLASS BOARDS - LIBRARY ROOM 216 | 035 | CLOSED | 1127.76 | 0 | 3260.388 | 3260.388
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | EL:WORK WITH JOC CONTRACTOR IN LIB 216 REMODEL | 035 | CLOSED | 16922.7362 | 0 | 18424.332 | 18424.332
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | ES:WORK WITH JOC CONTRACTOR ON LIB 216 REMODEL | 035 | CLOSED | 6208.8517 | 0 | 4588.317 | 4588.317
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | IN: REMODEL COMPUTER LAB - BLD 35 RM 216B | 035 | CLOSED | 512.448 | 0 | 96.084 | 96.084
PJ0004350 | REMODEL COMPUTER LAB - BLD 35 RM 216B | GONZALES, ALBERT M. | CLOSED | 2013-01-07 | PA: PAINTING FOR COMPUTER LAB REMODEL - BLD 35 RM 216B | 035 | CLOSED | 3002.2916 | 0 | 3403.392 | 3403.392
PJ0004350 Total | [7 empty] | 155134.4435 | 0 | 158466.977 | 158466.977
PJ0004348 | SR 12/13: REPAIR EXPANSION TANK - BLD 40 | BRENNAN, MICHAEL | CLOSED | 2013-01-08 | AD: DAWSON COMPANY | 040 | CLOSED | 17856.72 | 0 | 17956.16 | 17956.16
PJ0004348 | SR 12/13: REPAIR EXPANSION TANK - BLD 40 | BRENNAN, MICHAEL | CLOSED | 2013-01-08 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004348 | SR 12/13: REPAIR EXPANSION TANK - BLD 40 | BRENNAN, MICHAEL | CLOSED | 2013-01-08 | CPE: REPAIR EXPANSION TANK - BLD 40 | 040 | CLOSED | 1737.2817 | 0 | 2838.605 | 2838.605
PJ0004348 Total | [7 empty] | 19594.0017 | 0 | 20794.765 | 20794.765
PJ0004347 | SR 12/13: INSTALL ADA LEVER HANDLES ON HALL DOORS - BLD 47 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-01-03 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0004347 | SR 12/13: INSTALL ADA LEVER HANDLES ON HALL DOORS - BLD 47 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-01-03 | LO: INSTALL LEVER HANDLE SETS ON HALLWAY ENTRANCE DOORS | 047 | CLOSED | 12928.1952 | 0 | 8782.9 | 8782.9
PJ0004347 Total | [7 empty] | 12928.1952 | 0 | 8782.9 | 8782.9
PJ0004346 | SR 12/13: INSTALL PUSH BUTTON DOOR OPENER - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-01-03 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0004346 | SR 12/13: INSTALL PUSH BUTTON DOOR OPENER - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-01-03 | EL: PROVIDE ELECTRICAL FOR ADA PUSH-PAD DOOR OPENER AT BLDG 10 | 010 | CLOSED | 1200.5658 | 0 | 647.56 | 647.56
PJ0004346 | SR 12/13: INSTALL PUSH BUTTON DOOR OPENER - BLD 10 | KUENTZEL, DOUGLAS A. | CLOSED | 2013-01-03 | LO: SUPPLY AND INSTALL ADA PUSH-PAD DOOR OPENER AT BLDG 10 | 010 | CLOSED | 4045.7395 | 0 | 3495.305 | 3495.305
PJ0004346 Total | [7 empty] | 5246.3053 | 0 | 4142.865 | 4142.865
PJ0004345 | INSTALL PANIC ALARMS, BLDG 11 - RMS 243 & 244 | MOLLAN, CHERYL L. | CLOSED | 2012-12-21 | ANTS: PROGRAMMING FOR PANIC ALARM - BLDG 11 ROOMS 243 & 244 | 011 | CLOSED | 96.096 | 0 | 48.048 | 48.048
PJ0004345 | INSTALL PANIC ALARMS, BLDG 11 - RMS 243 & 244 | MOLLAN, CHERYL L. | CLOSED | 2012-12-21 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 12.81 | 0 | 0 | 0
PJ0004345 | INSTALL PANIC ALARMS, BLDG 11 - RMS 243 & 244 | MOLLAN, CHERYL L. | CLOSED | 2012-12-21 | IN: INSTALL PANIC ALARMS, BLDG 11 - RMS 243 & 244 | 011 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0004345 Total | [7 empty] | 140.934 | 0 | 80.076 | 80.076
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | AD: COSTCO - PURCHASE PATIO UMBRELLAS | 036 | CLOSED | 0 | 0 | 277.3226 | 277.3226
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | AD: ENGLEKIRK AND SABOL | 036 | CLOSED | 535 | 0 | 535 | 535
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | AD: JOC 13.029.024 MAINO | 036 | CLOSED | 59997.575 | 0 | 55818.7435 | 55818.7435
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | AD: ONTRAC SHIPPING | 036 | CLOSED | 0 | 0 | 34.656 | 34.656
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | AD: QUICK CRETE PRODUCTS | 036 | CLOSED | 4603.3112 | 0 | 4603.3005 | 4603.3005
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | CA: INSTALL NEW DOWNSPOUT AT BLDG. 36 | 036 | CLOSED | 458.328 | 0 | 210.366 | 210.366
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 1480.2 | 0 | 0 | 0
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | EO:CONSTRUCTION SUPPORT FOR LANDSCAPING UPD PLAZA | 036 | CLOSED | 497.64 | 0 | 696.696 | 696.696
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | IN: SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | 036 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | LA:LANDSCAPE FOR UPD FRONT AT BLDG 36 | 036 | CLOSED | 3358.56 | 0 | 3301.5922 | 3301.5922
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | LO: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | 036 | CLOSED | 82.044 | 0 | 116.088 | 116.088
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | PA: PAINT NEW DOWNSPOUT AT BLDG 36 GREEN | 036 | CLOSED | 178.728 | 0 | 59.364 | 59.364
PJ0004342 | SP 13/14: EXTERIOR BEAUTIFICATION AND SECURITY FOR BLD 36 | MOLLAN, CHERYL L. | CLOSED | 2012-12-18 | PL:PROVIDE POC FOR IRRIGATION AT UPD FRONT PLANTER | 036 | CLOSED | 2343.9493 | 0 | 979.476 | 979.476
PJ0004342 Total | [7 empty] | 73791.5595 | 0 | 66888.8288 | 66888.8288
PJ0004341 | SP 12/13: EMS PANEL UPGRADES - CAMPUS WIDE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | AD: MATERIALS TO BE INSTALLED BY SIEMENS | GENERAL | CLOSED | 0 | 0 | 11168.38 | 11168.38
PJ0004341 | SP 12/13: EMS PANEL UPGRADES - CAMPUS WIDE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | AD: SIEMENS | GENERAL | CLOSED | 0 | 0 | 26382.2838 | 26382.2838
PJ0004341 | SP 12/13: EMS PANEL UPGRADES - CAMPUS WIDE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004341 Total | [7 empty] | 0 | 0 | 37550.6638 | 37550.6638
PJ0004340 | SP 12/13: UPGRADE SCADA SERVER AND SOFTWARE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | AD: PLC PLUS | GENERAL | CLOSED | 21019.0372 | 0 | 26223.6553 | 26223.6553
PJ0004340 | SP 12/13: UPGRADE SCADA SERVER AND SOFTWARE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | AD: ROYAL WHOLESALE ELECTRIC - SOFTWARE TO BE INSTALLED BY PLC+ | GENERAL | CLOSED | 7544.9231 | 0 | 7092.94 | 7092.94
PJ0004340 | SP 12/13: UPGRADE SCADA SERVER AND SOFTWARE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | ANTS: PURCHASE NEW SERVER FOR SCADA | GENERAL | CLOSED | 5439.084 | 0 | 4809.924 | 4809.924
PJ0004340 | SP 12/13: UPGRADE SCADA SERVER AND SOFTWARE | ELLIOT, DENNIS K | CLOSED | 2012-12-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004340 Total | [7 empty] | 34003.0443 | 0 | 38126.5193 | 38126.5193
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | AD: AMERICAN LEAK DETECTION | 065 | CLOSED | 428 | 0 | 347.75 | 347.75
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | AD: BOB'S CRANE | 065 | CLOSED | 0 | 0 | 588.5 | 588.5
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | AD: JOC 13.030.034 MAINO | 065 | CLOSED | 91087.2275 | 0 | 89818.261 | 89818.261
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | CA: SEAL UTILIDOR LIDS AFTER REPLACEMENT | 065 | CLOSED | 511.104 | 0 | 1429.9352 | 1429.9352
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 10012.79 | 0 | 0 | 0
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | CPE: UU VICTAULIC REPLACEMENT SUPPORT | 065 | CLOSED | 1967.6656 | 0 | 0 | 0
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | ES:UU VICTAULIC REPLACEMENT | 065 | CLOSED | 4579.0264 | 0 | 1475.1 | 1475.1
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | IN: REPLACE LEAKING VICTAULIC FITTINGS - UU 65 RM 107, 118, 208 | 065 | CLOSED | 256.224 | 0 | 384.336 | 384.336
PJ0004339 | M&R ASI 14/15:REPLACE VICTAULIC FITTINGS- UU 65 RM 107, 118, 208 | GONZALES, ALBERT M. | CLOSED | 2012-09-24 | PL: UU VICTAULIC REPLACEMENT SUPPORT (N/L) | 065 | CLOSED | 2343.9493 | 0 | 0 | 0
PJ0004339 Total | [7 empty] | 111185.9867 | 0 | 94043.8822 | 94043.8822
PJ0004338 | PANIC ALARM SYSTEM - ASI STUDENT GOVERNMENT - UU 65 RM 202A | MOLLAN, CHERYL L. | CLOSED | 2012-12-10 | ANTS: PROGRAM ALARMS AT BUILDING 65 ROOM 202 - UU | 065 | CLOSED | 192.192 | 0 | 144.144 | 144.144
PJ0004338 | PANIC ALARM SYSTEM - ASI STUDENT GOVERNMENT - UU 65 RM 202A | MOLLAN, CHERYL L. | CLOSED | 2012-12-10 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 25.62 | 0 | 0 | 0
PJ0004338 | PANIC ALARM SYSTEM - ASI STUDENT GOVERNMENT - UU 65 RM 202A | MOLLAN, CHERYL L. | CLOSED | 2012-12-10 | IN: PANIC ALARM SYSTEM - ASI STUDENT GOVERNMENT - UU 65 RM 202A | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004338 Total | [7 empty] | 281.868 | 0 | 208.2 | 208.2
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | AD: COASTAL DEMO | 061 | CLOSED | 650 | 0 | 650 | 650
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | AD: EARTH SYSTEMS PACIFIC | 061 | CLOSED | 10101.78 | 0 | 10101.78 | 10101.78
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | AD: G.F. GARCIA | 061 | CLOSED | 19632.91 | 0 | 19632.91 | 19632.91
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | AD: JOC 12.024.035 STAPLES | 061 | CLOSED | 117152.01 | 0 | 115935.5 | 115935.5
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | AD: TOWN AND COUNTRY FENCING | 061 | CLOSED | 2800 | 0 | 2639 | 2639
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | CA: INSTALL RAILING FITTINGS AT SOUTH END BLEACHERS - SPANOS 061 | 061 | CLOSED | 625.92 | 0 | 642.295 | 642.295
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | EL: SUPPORT FOR ADA ACCESS PATH AT SPANOS STADIUM SOUTH END ZONE | 061 | CLOSED | 2997.2 | 0 | 3399.74 | 3399.74
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | EO: UTILITY TRENCHING, DRAINAGE PIPE, AND SELECT DEMOLITION | 061 | CLOSED | 663.52 | 0 | 2606.695 | 2606.695
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | IN: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - SS 061 | 061 | CLOSED | 2135.2 | 0 | 3042.66 | 3042.66
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | LA: SUPPORT FOR ADA ACCESS PATH AT SPANOS STADIUM SOUTH END ZONE | 061 | CLOSED | 1498.8 | 0 | 1831.745 | 1831.745
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | LO: SUPPLY EXIT GATE PADLOCKS (6) | 061 | CLOSED | 593.48 | 0 | 210.11 | 210.11
PJ0004337 | FP 12/13: CONSTRUCT ADA ACCESS PATH - SO ENDZONE BLEACHERS - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-11 | PL: REROUTE GAS PIPE TO SPANOS AND ADJUST FIELD DRAINAGE INLETS | 061 | CLOSED | 2091.12 | 0 | 248.76 | 248.76
PJ0004337 Total | [7 empty] | 160941.94 | 0 | 160941.195 | 160941.195
PJ0004336 | SR 12/13: RELAMPING UPPER & LOWER SPORTS COMPLEX FIELDS | GALVEZ, CESAR | CLOSED | 2012-12-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004336 | SR 12/13: RELAMPING UPPER & LOWER SPORTS COMPLEX FIELDS | GALVEZ, CESAR | CLOSED | 2012-12-10 | EL: COMPLETE GROUP RE-LAMP OF UPPER & LOWER SPORTS FIELD | GENERAL | CLOSED | 25575.8 | 0 | 24492.8423 | 24492.8423
PJ0004336 | SR 12/13: RELAMPING UPPER & LOWER SPORTS COMPLEX FIELDS | GALVEZ, CESAR | CLOSED | 2012-12-10 | EO: RE-LAMP OF UPPER & LOWER SPORT COMPLEX FIELDS SUPPORT | GENERAL | CLOSED | 5317.6 | 0 | 221.82 | 221.82
PJ0004336 | SR 12/13: RELAMPING UPPER & LOWER SPORTS COMPLEX FIELDS | GALVEZ, CESAR | CLOSED | 2012-12-10 | ES: SURVEY THE RELAMPING OF THE UPPER AND LOWER SPORTS COMPLEX | GENERAL | CLOSED | 832.48 | 0 | 884.51 | 884.51
PJ0004336 | SR 12/13: RELAMPING UPPER & LOWER SPORTS COMPLEX FIELDS | GALVEZ, CESAR | CLOSED | 2012-12-10 | LA: RE-LAMP OF UPPER & LOWER SPORT COMPLEX FIELDS SUPPORT | GENERAL | CLOSED | 2597.6 | 0 | 0 | 0
PJ0004336 Total | [7 empty] | 34323.48 | 0 | 25599.1723 | 25599.1723
PJ0004335 | FP 12/13: CABLE TRAY PROJECT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-10 | AD: JOC 13.029.008 MAINO (PARTIAL - SEE PJ 4722 FOR REMAINDER) | 061 | CLOSED | 35000 | 0 | 35000 | 35000
PJ0004335 | FP 12/13: CABLE TRAY PROJECT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-10 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004335 | FP 12/13: CABLE TRAY PROJECT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-10 | EL: CABLE TRENCH CLEARANCE | 061 | CLOSED | 224.72 | 0 | 84.27 | 84.27
PJ0004335 | FP 12/13: CABLE TRAY PROJECT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-12-10 | IN: FP 12/13: CABLE TRAY PROJECT - SPANOS STADIUM 061 | 061 | CLOSED | 213.52 | 0 | 613.87 | 613.87
PJ0004335 Total | [7 empty] | 35438.24 | 0 | 35698.14 | 35698.14
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | AD: (SR FUNDING) BUEHLER AND BUEHLER | 042S | CLOSED | 2500 | 0 | 1250 | 1250
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | AD: EARTH SYSTEMS | 042S | CLOSED | 2140 | 0 | 1246.6677 | 1246.6677
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | AD: ENGLEKIRK AND SABOL | 042S | CLOSED | 1284 | 0 | 535 | 535
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | AD: PLANNING OVERHEAD COSTS | 042S | CLOSED | 6921.33 | 0 | 6921.33 | 6921.33
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | CP: PROJECT CONTINGENCY | 042S | CLOSED | 1634.76 | 0 | 0 | 0
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | EL:INSTALL ELECTRICAL TO NEW SCOREBOARD | 042S | CLOSED | 4035.5131 | 0 | 4385.7475 | 4385.7475
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | IN: INSTALL SCOREBOARD AT TENNIS COURTS - 042S | 042S | CLOSED | 1024.896 | 0 | 768.672 | 768.672
PJ0004334 | INSTALL SCOREBOARD AT TENNIS COURTS - 042S | LAMPMAN, GREG | CLOSED | 2012-12-06 | LO: SUPPLY PADLOCKS TO ELECTRICIANS FOR TENNIS CRT SCOREBOARD | 042S | CLOSED | 0 | 0 | 623.226 | 623.226
PJ0004334 Total | [7 empty] | 19540.4991 | 0 | 15730.6432 | 15730.6432
PJ0004329 | SMART ROOM UPGRADE - BLD 26 RM 103 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-11-29 | CA:SMART ROOM UPGRADE, BLDG 26- RM 103 | 026 | CLOSED | 623.88 | 0 | 460.05 | 460.05
PJ0004329 | SMART ROOM UPGRADE - BLD 26 RM 103 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-11-29 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0004329 | SMART ROOM UPGRADE - BLD 26 RM 103 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-11-29 | EL:ADJUST LIGHTING CONTROL IN FRONT OF NEW SCREEN | 026 | CLOSED | 428.496 | 0 | 583.74 | 583.74
PJ0004329 Total | [7 empty] | 1052.376 | 0 | 1043.79 | 1043.79
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | AD: BENCHMARK WOODWORKING | 108 | CLOSED | 2000 | 0 | 5853.37 | 5853.37
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | AD: FASULO DRYWALL | 108 | CLOSED | 1000 | 0 | 426 | 426
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | AD: MCKENNA ENVIRONMENTAL | 108 | CLOSED | 4000 | 0 | 2402 | 2402
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | AD: PARC ENVIRONMENTAL | 108 | CLOSED | 5000 | 0 | 4170 | 4170
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | AD: SAN LUIS GLASS | 108 | CLOSED | 4000 | 0 | 4031.5 | 4031.5
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | CA:BUILD NEW VENDING AREA | 108 | CLOSED | 9421.042 | 0 | 10109.7225 | 10109.7225
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | CP: PROJECT CONTINGENCY | 108 | CLOSED | 0 | 0 | 0 | 0
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | EH&S: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 (N/L) | 108 | CLOSED | 114.5 | 0 | 0 | 0
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | EL:LIGHTING AND POWER FOR NEW VENDING AREA | 108 | CLOSED | 2375.8502 | 0 | 1500.365 | 1500.365
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | ES: MOVE THERMOSTAT AND INSULATE PIPING | 110 | CLOSED | 2237.2817 | 0 | 1982.2192 | 1982.2192
PJ0004328 | M&R HOUS 12/13: RECONFIGURE LOUNGE VENDING AREA-SEQUOIA BLDG 108 | GONZALES, ALBERT M. | CLOSED | 2012-11-28 | IN: RECONFIGURE MAIN LOUNGE VENDING AREA-SEQUOIA BLDG 108 | 108 | CLOSED | 213.52 | 0 | 160.14 | 160.14
PJ0004328 Total | [7 empty] | 30362.1939 | 0 | 30635.3167 | 30635.3167
PJ0004327 | INSTALL DASHBOARD SYSTEM TO MONITOR ENERGY USE | ELLIOT, DENNIS K | CLOSED | 2012-11-21 | AD: ITS CHARGES FOR LUCID INSTALLATION | RESIDENCE | CLOSED | 400 | 0 | 80 | 80
PJ0004327 | INSTALL DASHBOARD SYSTEM TO MONITOR ENERGY USE | ELLIOT, DENNIS K | CLOSED | 2012-11-21 | AD: LUCID DESIGN | RESIDENCE | CLOSED | 38327.4 | 0 | 38327.4 | 38327.4
PJ0004327 | INSTALL DASHBOARD SYSTEM TO MONITOR ENERGY USE | ELLIOT, DENNIS K | CLOSED | 2012-11-21 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 2758.33 | 0 | 0 | 0
PJ0004327 | INSTALL DASHBOARD SYSTEM TO MONITOR ENERGY USE | ELLIOT, DENNIS K | CLOSED | 2012-11-21 | EL:INSTALL ELECTRIC METER AT SANTA LUCIA | RESIDENCE | CLOSED | 5096.64 | 0 | 3148.464 | 3148.464
PJ0004327 | INSTALL DASHBOARD SYSTEM TO MONITOR ENERGY USE | ELLIOT, DENNIS K | CLOSED | 2012-11-21 | ES:CONNECT 6 WATER METERS TO EMS - RED BRICKS | RESIDENCE | CLOSED | 6755.904 | 0 | 8594.1017 | 8594.1017
PJ0004327 Total | [7 empty] | 53338.274 | 0 | 50149.9657 | 50149.9657
PJ0004325 | INSTALL CABLE FOR 3RD CAMERA: BASKETBALL REPLAY - MOTT 42 RM 102 | JUDD, PERRY | CLOSED | 2012-11-16 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 555.12 | 0 | 0 | 0
PJ0004325 | INSTALL CABLE FOR 3RD CAMERA: BASKETBALL REPLAY - MOTT 42 RM 102 | JUDD, PERRY | CLOSED | 2012-11-16 | EL: INSTALL CAT 5 CABLE FOR FOURTH CAMERA AT MOTT GYM - 042 | 042 | CLOSED | 5551.0262 | 0 | 3882.732 | 3882.732
PJ0004325 Total | [7 empty] | 6106.1462 | 0 | 3882.732 | 3882.732
PJ0004323 | LIBRARY LOBBY REMODEL - BLD 35 | MAY, TOM | CLOSED | 2012-11-15 | CA: REMOVE GLASS IN KENNEDY LIBRARY LOBBY - BLDG. 035 | 035 | CLOSED | 406.6718 | 0 | 1003.968 | 1003.968
PJ0004323 | LIBRARY LOBBY REMODEL - BLD 35 | MAY, TOM | CLOSED | 2012-11-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 221.89 | 0 | 0 | 0
PJ0004323 | LIBRARY LOBBY REMODEL - BLD 35 | MAY, TOM | CLOSED | 2012-11-15 | EL:INSTALL OUTLET IN LIBRARY LOBBY FOR SECURITY GATE | 035 | CLOSED | 540.3389 | 0 | 565.104 | 565.104
PJ0004323 | LIBRARY LOBBY REMODEL - BLD 35 | MAY, TOM | CLOSED | 2012-11-15 | IN: LIBRARY LOBBY REMODEL - BLD 35 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004323 | LIBRARY LOBBY REMODEL - BLD 35 | MAY, TOM | CLOSED | 2012-11-15 | LO:INSTALL HANDLES AND REMOVE ALARMS LIB LOBBY | 035 | CLOSED | 609.4381 | 0 | 302.616 | 302.616
PJ0004323 Total | [7 empty] | 1906.4508 | 0 | 1999.8 | 1999.8
PJ0004322 | HYDRATION STATION INSTALLATIONS - BLDG 35 1ST & 2ND FLOORS | MAY, TOM | CLOSED | 2012-11-15 | CA: SUPPORT PLUMBING SHOP TO INSTALL HYDARTION STATIONS | 035 | CLOSED | 670.9266 | 0 | 1197.852 | 1197.852
PJ0004322 | HYDRATION STATION INSTALLATIONS - BLDG 35 1ST & 2ND FLOORS | MAY, TOM | CLOSED | 2012-11-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 440.78 | 0 | 0 | 0
PJ0004322 | HYDRATION STATION INSTALLATIONS - BLDG 35 1ST & 2ND FLOORS | MAY, TOM | CLOSED | 2012-11-15 | EL: ELECTRICAL FOR HYDRATION STATIONS - BLDG 35 1ST & 2ND FLOORS | 035 | CLOSED | 269.664 | 0 | 896.676 | 896.676
PJ0004322 | HYDRATION STATION INSTALLATIONS - BLDG 35 1ST & 2ND FLOORS | MAY, TOM | CLOSED | 2012-11-15 | IN: HYDRATION STATION INSTALLATION - BLD 35 2ND FLR | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004322 | HYDRATION STATION INSTALLATIONS - BLDG 35 1ST & 2ND FLOORS | MAY, TOM | CLOSED | 2012-11-15 | PA:SUPPORT PLUMBING SHOP WITH HYDRATION STAION INSTALL | 035 | CLOSED | 324.1698 | 0 | 482.184 | 482.184
PJ0004322 | HYDRATION STATION INSTALLATIONS - BLDG 35 1ST & 2ND FLOORS | MAY, TOM | CLOSED | 2012-11-15 | PL:INSTALL HIGH/LOW HYDRATION STATIONS | 035 | CLOSED | 6045.0481 | 0 | 5650.446 | 5650.446
PJ0004322 Total | [7 empty] | 7814.6445 | 0 | 8291.214 | 8291.214
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | AD: AGGSON'S GLASS | 035 | CLOSED | 1225.792 | 0 | 1225.792 | 1225.792
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | AD: FLOOR CONNECTION | 035 | CLOSED | 2354 | 0 | 2318.1336 | 2318.1336
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | AD: J.L FASULO DRYWALL | 035 | CLOSED | 3745 | 0 | 4222.22 | 4222.22
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 1556.85 | 0 | 1556.4113 | 1556.4113
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | AD: TEMPLE BUILDERS | 035 | CLOSED | 5136 | 0 | 4899.851 | 4899.851
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | CA: INSTALL DOORSTOP - SPECIAL COLLECTIONS OFFICE 35-409 | 035 | CLOSED | 74.388 | 0 | 41.646 | 41.646
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 951.06 | 0 | 0 | 0
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | EH&S: SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 (N/L) | 035 | CLOSED | 68.7 | 0 | 36 | 36
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | EL:SPECIAL COLLECTIONS REMODEL | 035 | CLOSED | 2400.6814 | 0 | 3093.252 | 3093.252
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | IN: SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | 035 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | LO:SPECIAL COLLECTIONS LOCKSET | 035 | CLOSED | 1116.5916 | 0 | 730.464 | 730.464
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | PA:PAINT NEW OFFICE SPACE | 035 | CLOSED | 3242.2916 | 0 | 2151.396 | 2151.396
PJ0004321 | SPECIAL COLLECTIONS OFFICE REMODEL - BLD 35 RM 409 | BRENNAN, MICHAEL | CLOSED | 2012-11-15 | PL: CAP WATER AND DRAIN LINES | 035 | CLOSED | 2343.9493 | 0 | 404.124 | 404.124
PJ0004321 Total | [7 empty] | 24471.5279 | 0 | 20935.5139 | 20935.5139
PJ0004320 | BROKEN FREON LINE - S. SIDE OF LIBRARY (MAINT) - SEE WO0212327 | SHAW, KEVIN | CLOSED | 2012-11-15 | CA: CONSTRUCT FENCE, MOVE BIKE RACK AND ASSIST | 035 | CLOSED | 0 | 0 | 960.28 | 960.28
PJ0004320 | BROKEN FREON LINE - S. SIDE OF LIBRARY (MAINT) - SEE WO0212327 | SHAW, KEVIN | CLOSED | 2012-11-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0004320 | BROKEN FREON LINE - S. SIDE OF LIBRARY (MAINT) - SEE WO0212327 | SHAW, KEVIN | CLOSED | 2012-11-15 | CPE: REPLACE NEW CONDENSER | 035 | CLOSED | 0 | 0 | 3966.06 | 3966.06
PJ0004320 | BROKEN FREON LINE - S. SIDE OF LIBRARY (MAINT) - SEE WO0212327 | SHAW, KEVIN | CLOSED | 2012-11-15 | EL: RECONNECT CONDENSER | 035 | CLOSED | 0 | 0 | 724.53 | 724.53
PJ0004320 Total | [7 empty] | 0 | 0 | 5650.87 | 5650.87
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | AD: BELFOR (CSU JOC # S2012011) | 170C | CLOSED | 80768.9714 | 0 | 80768.9714 | 80768.9714
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | AD: BELFOR (EMERGENCY RESPONSE CONTRACT) | 170C | CLOSED | 53175.8756 | 0 | 49281.5678 | 49281.5678
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | CA:PROVIDE CARPENTRY SUPPORT FOR FLOOD AT CERRO VISTA C201 | 170C | CLOSED | 6428.232 | 0 | 5356.86 | 5356.86
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | CP: PROJECT CONTINGENCY | 170C | CLOSED | 0 | 0 | 0 | 0
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | IN: BROKEN FIRE SPRINKLER ¿CERRO VISTA BLDG C C101&C201B | 170C | CLOSED | 691.8048 | 0 | 576.504 | 576.504
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | PA:PROVIDE PAINTING SUPPORT FOR FLOOD AT CERRO VISTA C201 | 170C | CLOSED | 2938.518 | 0 | 2448.765 | 2448.765
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | PCV EL:PROVIDE ELECT SUPPORT FOR FLOOD AT CERRO VISTA C201 | 170C | CLOSED | 647.1936 | 0 | 539.328 | 539.328
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | PCVES: REMOVE THE HEATER IN C101 | 170C | CLOSED | 599.3856 | 0 | 499.488 | 499.488
PJ0004319 | BROKEN FIRE SPRINKLER (FLOOD) ¿CERRO VISTA BLDG C C101&C201B | GRIFFIN, PATRICK E. | CLOSED | 2012-11-15 | PCVPL:PROVIDE PLUMBING SUPPORT FOR CERRO VISTA FLOOD C201 | 170C | CLOSED | 456.4848 | 0 | 430.368 | 430.368
PJ0004319 Total | [7 empty] | 145706.4658 | 0 | 139901.8522 | 139901.8522
PJ0004317 | RESTROOM VENTILATION ASSESSMENT - BLD 113 SIERRA MADRE | BRENNAN, MICHAEL | CLOSED | 2012-11-06 | AD: GOSS ENGINEERING | 113 | CLOSED | 4922 | 0 | 4922 | 4922
PJ0004317 | RESTROOM VENTILATION ASSESSMENT - BLD 113 SIERRA MADRE | BRENNAN, MICHAEL | CLOSED | 2012-11-06 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 568.44 | 0 | 0 | 0
PJ0004317 | RESTROOM VENTILATION ASSESSMENT - BLD 113 SIERRA MADRE | BRENNAN, MICHAEL | CLOSED | 2012-11-06 | EL: CANCELED | 113 | CLOSED | 134.832 | 0 | 0 | 0
PJ0004317 | RESTROOM VENTILATION ASSESSMENT - BLD 113 SIERRA MADRE | BRENNAN, MICHAEL | CLOSED | 2012-11-06 | ES: CANCELED | 113 | CLOSED | 499.488 | 0 | 0 | 0
PJ0004317 | RESTROOM VENTILATION ASSESSMENT - BLD 113 SIERRA MADRE | BRENNAN, MICHAEL | CLOSED | 2012-11-06 | IN: RESTROOM VENTILATION ASSESSMENT - BLD 113 SIERRA MADRE | 113 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004317 Total | [7 empty] | 6252.872 | 0 | 4954.028 | 4954.028
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | AD: ENGLEKIRK AND SABOL | 371B | CLOSED | 1070 | 0 | 535 | 535
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | AD: JOC 12.026.001 PRE CON | 371B | CLOSED | 121781.5471 | 0 | 121781.5685 | 121781.5685
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | AD: MORELAND THOMPSON | 371B | CLOSED | 5350 | 0 | 5269.75 | 5269.75
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | AD: O'BRIEN FIRE PROTECTIN (LOW-VALUE PUBLIC WORKS) | 371B | CLOSED | 5350 | 0 | 4547.5 | 4547.5
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | AD: OMNI DESIGN (SUBCONTRACT TO SMITH STRUCTURAL) | 371B | CLOSED | 10700 | 0 | 3691.5 | 3691.5
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | CP: PROJECT CONTINGENCY | 371B | CLOSED | 11212.95 | 0 | 0 | 0
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | IN: MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | 371B | CLOSED | 1921.68 | 0 | 1056.924 | 1056.924
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | PCV EL: UPDATE EXTERIOR ELECTRIC CAR OUTLETS -HOUSING DEPOT 371B | 371B | CLOSED | 1678.656 | 0 | 33.708 | 33.708
PJ0004315 | MEZZANINE AND PALLET RACK INSTALLATION - 371B HOUSING DEPOT | BRENNAN, MICHAEL | CLOSED | 2012-11-05 | PCV PL: INSTALL SEISMIC STRAPPING ON WATERHEATER - HOUSING DEPOT | 371B | CLOSED | 1953.312 | 0 | 685.326 | 685.326
PJ0004315 Total | [7 empty] | 161018.1451 | 0 | 137601.2765 | 137601.2765
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | AD: ASAP REPROGRAPHICS (DIRECT PAY) | 018A | CLOSED | 0 | 0 | 56.16 | 56.16
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | AD: EARTH SYSTEMS | 018A | CLOSED | 1980.7305 | 0 | 826.5215 | 826.5215
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | AD: G.F. GARCIA AND SONS | 018A | CLOSED | 8638.9874 | 0 | 8638.9767 | 8638.9767
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | AD: JOC 12.024.023 STAPLES | 018A | CLOSED | 161914.7112 | 0 | 161914.7112 | 161914.7112
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | AD: JOC 12.026.011.00 PRE CON | 018A | CLOSED | 198555.406 | 0 | 196672.527 | 196672.527
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | AD: WLH BUILDING COMPANY | 018A | CLOSED | 545.7 | 0 | 545.7 | 545.7
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | CP: PROJECT CONTINGENCY | 018A | CLOSED | 30337.24 | 0 | 0 | 0
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | CPE: CONSTRUCTION FOR NEW LAB | 018A | CLOSED | 730.9127 | 0 | 825.756 | 825.756
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | CPE: DEMO, SAFE OFF, AND LAY-OUT - DPTC 111C | 018A | CLOSED | 32780.4942 | 0 | 38808.738 | 38808.738
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | EL: DEMO, SAFE OFF, AND LAY-OUT - DPTC 111C | 018A | CLOSED | 30765.7529 | 0 | 34007.8862 | 34007.8862
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | EL: ELECTRICAL FOR NEW LAB | 018A | CLOSED | 780.0024 | 0 | 978.06 | 978.06
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | ES: REMOVE STEAM LINE FROM DPTC RM. 111D - BDLG 018A | 018A | CLOSED | 499.488 | 0 | 131.916 | 131.916
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | IN: CONSTRUCT LAB SPACE - BLD 18A RM 111C | 018A | CLOSED | 2138.8298 | 0 | 2850.492 | 2850.492
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | IN: CONSTRUCT LAB SPACE IN STORAGE AREA - BLD 18A RM 111C | 018A | CLOSED | 1281.12 | 0 | 1281.12 | 1281.12
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | LO: INSTALL LOCKS AND CLOSERS | 018A | CLOSED | 3396.5916 | 0 | 2652.126 | 2652.126
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | PA: PAINT WALLS AND CEILINGS WITH CP-2 | 018A | CLOSED | 5285.1769 | 0 | 2601.69 | 2601.69
PJ0004314 | CONSTRUCT LAB SPACE - BLD 18A RM 111C (SEE 4019 FOR DESIGN) | LAMPMAN, GREG | CLOSED | 2012-11-07 | PL: DEMO, SAFE OFF, AND LAY-OUT - DPTC 111C | 018A | CLOSED | 45240.9342 | 0 | 64873.6048 | 64873.6048
PJ0004314 Total | [7 empty] | 524872.0778 | 0 | 517665.9854 | 517665.9854
PJ0004312 | SP 12/13: RETURN TO AG USE-MUSTANG VILLAGE PARKG (NO OH) (N/L) | NEEL, JOEL | CLOSED | 2012-11-02 | AD: CENTRAL COAST FENCE (NO OVERHEAD) | OFFCAMPUS | CLOSED | 5000 | 0 | 4567 | 4567
PJ0004312 | SP 12/13: RETURN TO AG USE-MUSTANG VILLAGE PARKG (NO OH) (N/L) | NEEL, JOEL | CLOSED | 2012-11-02 | CP: PROJECT CONTINGENCY | OFFCAMPUS | CLOSED | 0 | 0 | 0 | 0
PJ0004312 | SP 12/13: RETURN TO AG USE-MUSTANG VILLAGE PARKG (NO OH) (N/L) | NEEL, JOEL | CLOSED | 2012-11-02 | LO: PROVIDE MASTER LOCK - MUSTANG VILLAGE PARKING LOT PROJECT | OFFCAMPUS | CLOSED | 0 | 0 | 0 | 0
PJ0004312 Total | [7 empty] | 5000 | 0 | 4567 | 4567
PJ0004309 | MAINTENANCE WALK-THRU 10/09/2012 - PAC 06 (NO ESTIMATE) | GALVEZ, CESAR | CLOSED | 2012-10-29 | CA: FACILITY INSPECTION MAINTENANCE REPAIRS - PAC 006 | 006 | CLOSED | 0 | 0 | 1386.23 | 1386.23
PJ0004309 | MAINTENANCE WALK-THRU 10/09/2012 - PAC 06 (NO ESTIMATE) | GALVEZ, CESAR | CLOSED | 2012-10-29 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004309 | MAINTENANCE WALK-THRU 10/09/2012 - PAC 06 (NO ESTIMATE) | GALVEZ, CESAR | CLOSED | 2012-10-29 | ES: FACILITY INSPECTION MAINTENANCE REPAIRS - PAC 006 | 006 | CLOSED | 260.15 | 0 | 156.09 | 156.09
PJ0004309 | MAINTENANCE WALK-THRU 10/09/2012 - PAC 06 (NO ESTIMATE) | GALVEZ, CESAR | CLOSED | 2012-10-29 | LO: FACILITY INSPECTION MAINTENANCE REPAIRS - PAC 006 | 006 | CLOSED | 0 | 0 | 1277.9 | 1277.9
PJ0004309 | MAINTENANCE WALK-THRU 10/09/2012 - PAC 06 (NO ESTIMATE) | GALVEZ, CESAR | CLOSED | 2012-10-29 | PA: FACILITY INSPECTION MAINTENANCE REPAIRS - PAC 006 | 006 | CLOSED | 0 | 0 | 173.145 | 173.145
PJ0004309 Total | [7 empty] | 260.15 | 0 | 2993.365 | 2993.365
PJ0004308 | INSTALL FIRE SUPPRESSION UNDER VENT HOOD - BLD 155 | LAMPMAN, GREG | CLOSED | 2012-10-26 | AD: MID-COAST FIRE PROTECTION | 155 | CLOSED | 1100.709 | 0 | 1111.0345 | 1111.0345
PJ0004308 | INSTALL FIRE SUPPRESSION UNDER VENT HOOD - BLD 155 | LAMPMAN, GREG | CLOSED | 2012-10-26 | ANTS: FIRE ALARM TESTING AT MEATS PROCESSING CTR- SUPPORT VENDOR | 155 | CLOSED | 24.024 | 0 | 24.024 | 24.024
PJ0004308 | INSTALL FIRE SUPPRESSION UNDER VENT HOOD - BLD 155 | LAMPMAN, GREG | CLOSED | 2012-10-26 | CP: PROJECT CONTINGENCY | 155 | CLOSED | 98.86 | 0 | 0 | 0
PJ0004308 | INSTALL FIRE SUPPRESSION UNDER VENT HOOD - BLD 155 | LAMPMAN, GREG | CLOSED | 2012-10-26 | EL:FIRE ALARM TEST AT MEATS PROCESING @ 1:00 ON 1/31/13 (MAINT) | 155 | CLOSED | 0 | 0 | 56.18 | 56.18
PJ0004308 | INSTALL FIRE SUPPRESSION UNDER VENT HOOD - BLD 155 | LAMPMAN, GREG | CLOSED | 2012-10-26 | IN: INSTALL FIRE SUPPRESSION UNDER VENT HOOD - BLD 155 | 155 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004308 Total | [7 empty] | 1351.705 | 0 | 1319.3505 | 1319.3505
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | AD: COASTAL DEMO - TO ASSIST PLUMBING SHOP | 024 | CLOSED | 0 | 0 | 308.16 | 308.16
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | AD: OVERHEAD ON DEPARTMENT PURCHASED EQUIPMENT | 024 | CLOSED | 1400 | 0 | 1400 | 1400
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | CA:POUR CONCRETE SLAB | 024 | CLOSED | 3709.8299 | 0 | 1953.0235 | 1953.0235
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 2867.31 | 0 | 0 | 0
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | EL:POWER TO COMPRESSOR | 024 | CLOSED | 13352.3866 | 0 | 10262.904 | 10262.904
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | EO:ASSIST CARPENTERS WITH CONCRETE REMOVAL (N/L) | 024 | CLOSED | 199.056 | 0 | 0 | 0
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | IN: INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | 024 | CLOSED | 256.224 | 0 | 192.168 | 192.168
PJ0004307 | INSTALL LARGE ROTARY SCREW COMPRESSOR - BLD 24 RM 106L | MCNALLY, CURTIS | CLOSED | 2012-10-25 | PL:AIR LINES FOR COMPRESSOR | 024 | CLOSED | 11086.2468 | 0 | 10297.608 | 10297.608
PJ0004307 Total | [7 empty] | 32871.0532 | 0 | 24413.8635 | 24413.8635
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | CA: CREATE SIGNS FOR 2012 FALL COMMENCEMENT - 12/8 | 043 | CLOSED | 0 | 0 | 244.215 | 244.215
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | CA: INSTALL DISABLED RAMP FOR FALL COMMENCEMENT-DEC 5 | 043 | CLOSED | 0 | 0 | 1823.6 | 1823.6
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | CU: SUPPORT FOR 2012 FALL COMMENCEMENT - 12/8 | 043 | CLOSED | 0 | 0 | 191.125 | 191.125
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | EL: SUPPORT FOR FALL COMMENCEMENT - DEC 8 | 043 | CLOSED | 0 | 0 | 662.36 | 662.36
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | ES: PROGRAM HVAC AT SAGE RESTAURANT TO BE ON BY 7AM - 12/8 | 043 | CLOSED | 52.03 | 0 | 52.03 | 52.03
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | MO: SUPPORT FOR 2012 FALL COMMENCEMENT - DEC 8 | 043 | CLOSED | 0 | 0 | 173.535 | 173.535
PJ0004306 | SUPPORT FOR 2012 FALL COMMENCEMENT - BLD 43 | POPHAM, DONALD J. | CLOSED | 2012-10-24 | PA: SUPPORT FOR 2012 FALL COMMENCEMENT - 12/7 | 043 | CLOSED | 0 | 0 | 74.205 | 74.205
PJ0004306 Total | [7 empty] | 52.03 | 0 | 3221.07 | 3221.07
PJ0004304 | INSTALL 3 METER PANEL // POWER & DATA - SPORTS COMPLEX | LAMPMAN, GREG | CLOSED | 2012-10-17 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 940.85 | 0 | 0 | 0
PJ0004304 | INSTALL 3 METER PANEL // POWER & DATA - SPORTS COMPLEX | LAMPMAN, GREG | CLOSED | 2012-10-17 | EL: INSTALL ELECTRICAL FOR 3 CONTRACTOR TRAILERS | GENERAL | CLOSED | 9016.5334 | 0 | 10216.596 | 10216.596
PJ0004304 | INSTALL 3 METER PANEL // POWER & DATA - SPORTS COMPLEX | LAMPMAN, GREG | CLOSED | 2012-10-17 | EO: PROVIDE A TRENCH FOR ELECTRICAL WORK | GENERAL | CLOSED | 1993.5458 | 0 | 3093.084 | 3093.084
PJ0004304 | INSTALL 3 METER PANEL // POWER & DATA - SPORTS COMPLEX | LAMPMAN, GREG | CLOSED | 2012-10-17 | IN: INSTALL 3 METER PANEL // POWER & DATA - SPORTS COMPLEX | GENERAL | CLOSED | 192.168 | 0 | 170.022 | 170.022
PJ0004304 Total | [7 empty] | 12143.0972 | 0 | 13479.702 | 13479.702
PJ0004302 | INSTALL CARPETING - BLD 008 RM 123B | LAMPMAN, GREG | CLOSED | 2012-10-15 | AD: FLOOR CONNECTION | 008 | CLOSED | 946.95 | 0 | 946.95 | 946.95
PJ0004302 | INSTALL CARPETING - BLD 008 RM 123B | LAMPMAN, GREG | CLOSED | 2012-10-15 | CP: PROJECT CONTINGENCY | 008 | CLOSED | 101.1 | 0 | 0 | 0
PJ0004302 | INSTALL CARPETING - BLD 008 RM 123B | LAMPMAN, GREG | CLOSED | 2012-10-15 | IN: INSTALL CARPETING - BLD 008 RM 123B | 008 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004302 Total | [7 empty] | 1112.106 | 0 | 1011.006 | 1011.006
PJ0004300 | SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | GALVEZ, CESAR | CLOSED | 2012-10-10 | CA: SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | 163 | CLOSED | 3040.031 | 0 | 2306.322 | 2306.322
PJ0004300 | SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | GALVEZ, CESAR | CLOSED | 2012-10-10 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 2725.04 | 0 | 0 | 0
PJ0004300 | SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | GALVEZ, CESAR | CLOSED | 2012-10-10 | EO: SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | 163 | CLOSED | 4458.3929 | 0 | 3033.768 | 3033.768
PJ0004300 | SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | GALVEZ, CESAR | CLOSED | 2012-10-10 | LA: SPORTS COMPLEX SOFTBALL FIELD MODIFICATIONS - BLD 163 | 163 | CLOSED | 19752.9602 | 0 | 23510.43 | 23510.43
PJ0004300 Total | [7 empty] | 29976.4242 | 0 | 28850.52 | 28850.52
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | AD: EC WEST | 001 | CLOSED | 306.448 | 0 | 264.2579 | 264.2579
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | AD: PURCHASE POWER SUPPLY | 001 | CLOSED | 0 | 0 | 10.71 | 10.71
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | AD: SMART OFFICE INTERIORS | 001 | CLOSED | 8926.2075 | 0 | 8919.3381 | 8919.3381
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | CA: INSTALL FULL LITE AND WHT BRD | 001 | CLOSED | 1666.861 | 0 | 1066.284 | 1066.284
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1114.91 | 0 | 0 | 0
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | EL: ELECTRICAL CHANGES IN OFFICE | 001 | CLOSED | 1575.5107 | 0 | 1300.9897 | 1300.9897
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | IN: REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | 001 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | MO:REMOVE DESK | 001 | CLOSED | 72.252 | 0 | 48.288 | 48.288
PJ0004299 | REPLACE CURRENT DOOR W/ GLASS DOOR - ADM 01 RM 209E | BRENNAN, MICHAEL | CLOSED | 2012-09-25 | PA:TOUCH UP PAINT | 001 | CLOSED | 1237.2728 | 0 | 712.368 | 712.368
PJ0004299 Total | [7 empty] | 15027.574 | 0 | 12450.3477 | 12450.3477
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | AD: CAME SECURITY - SERVICE CANCELATION FEE | 081 | CLOSED | 300 | 0 | 80.25 | 80.25
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | AD: RUSSCO | 081 | CLOSED | 6421.2947 | 0 | 5715.0198 | 5715.0198
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | AD: TEMPLE BUILDERS | 081 | CLOSED | 4280 | 0 | 4063.4213 | 4063.4213
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | CP: PROJECT CONTINGENCY | 081 | CLOSED | 1103.78 | 0 | 0 | 0
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | EL:ELECTRICAL WORK FOR REMODEL 81-01 | 081 | CLOSED | 1800.6802 | 0 | 1612.296 | 1612.296
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | IN: CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | 081 | CLOSED | 192.168 | 0 | 192.168 | 192.168
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | LO: INSTALL MORTISE LOCKS ON NEW DOORS TO RM 1 & ELECTR. CLOSET | 081 | CLOSED | 1338.2958 | 0 | 1112.58 | 1112.58
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | MO: MOVE FURNITURE FROM BLDG. 81 RM. 01 TO STORAGE UNIT | 081 | CLOSED | 259.2 | 0 | 24.144 | 24.144
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | PA:PAINT OUT ROOMS IN 81 | 081 | CLOSED | 2293.952 | 0 | 1610.418 | 1610.418
PJ0004297 | CONSULT FOR SPACE ARRANGEMENTS-STUDENT ACADEMIC SVCS -BLD 81 | MAY, TOM | CLOSED | 2012-09-26 | PL: REMOVE OLD PLUMBING IN BLDG 81, ROOM 1 AND LOBBY | 081 | CLOSED | 652.92 | 0 | 871.92 | 871.92
PJ0004297 Total | [7 empty] | 18642.2907 | 0 | 15282.2171 | 15282.2171
PJ0004296 | INSTALL XOS REPLAY SYSTEM - MOTT 42 RM 102 | JUDD, PERRY | CLOSED | 2012-09-25 | AD: GRAND PERFORMANCE | 042 | CLOSED | 1339.64 | 0 | 1337.5 | 1337.5
PJ0004296 | INSTALL XOS REPLAY SYSTEM - MOTT 42 RM 102 | JUDD, PERRY | CLOSED | 2012-09-25 | AD: PERMIT FEES | 042 | CLOSED | 350 | 0 | 350 | 350
PJ0004296 | INSTALL XOS REPLAY SYSTEM - MOTT 42 RM 102 | JUDD, PERRY | CLOSED | 2012-09-25 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 168.96 | 0 | 0 | 0
PJ0004296 Total | [7 empty] | 1858.6 | 0 | 1687.5 | 1687.5
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: ASAP REPROGRAPHICS (DIRECT PAY) | 192 | CLOSED | 0 | 0 | 112.67 | 112.67
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: BKM | 192 | CLOSED | 4200.2743 | 0 | 4200.2743 | 4200.2743
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: DIVISION OF STATE ARCHITECT | 192 | CLOSED | 1400 | 0 | 1400 | 1400
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: ENGLEKIRK AND SABOL | 192 | CLOSED | 1904.6 | 0 | 1904.6 | 1904.6
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: FLOOR CONNECTION | 192 | CLOSED | 21400 | 0 | 20113.6781 | 20113.6781
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: JOC 12.026.014 PRE CON | 192 | CLOSED | 232912.5068 | 0 | 232912.4961 | 232912.4961
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: KI FURNITURE | 192 | CLOSED | 90950 | 0 | 83531.5509 | 83531.5509
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: MORELAND THOMPSON | 192 | CLOSED | 6128.96 | 0 | 6128.96 | 6128.96
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: PARTS TO BE INSTALLED BY JOC & AV CONTRACTOR (MAINT) | 192 | CLOSED | 0 | 0 | 18859.09 | 18859.09
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: PMSM ARCHITECTS | 192 | CLOSED | 55105 | 0 | 52544.9715 | 52544.9715
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: PRE CON (LOW-VALUE PUBLIC WORKS) | 192 | CLOSED | 9822.6963 | 0 | 5350 | 5350
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: RAT SOUND SYSTEMS | 192 | CLOSED | 107000 | 0 | 85812.7481 | 85812.7481
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | AD: SHIPPING CHARGES | 192 | CLOSED | 0 | 0 | 12.38 | 12.38
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | ANTS: PROGRAM ALARMS FOR LECTURE ROOM PROJECT - BLDG 192 RM 106A | 192 | CLOSED | 0 | 0 | 36.036 | 36.036
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 22239.71 | 0 | 0 | 0
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | EL:INSTALL NEW SUB-PANEL, PROJECT SUPPORT | 192 | CLOSED | 13502.0525 | 0 | 7894.32 | 7894.32
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | ES: | 192 | CLOSED | 2476.2018 | 0 | 561.924 | 561.924
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | IN: CONVERT SPACE TO LARGE CAPACITY LECTURE ROOM - BLDG 192-106A | 192 | CLOSED | 4357.0891 | 0 | 3971.472 | 3971.472
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | ITS: TELECOM AND DATA LINES FOR 192-106 | 192 | CLOSED | 0 | 0 | 3700.96 | 3700.96
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | LO:LOCKS FOR NEW CLASSROOM | 192 | CLOSED | 3692.0594 | 0 | 1420.176 | 1420.176
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | MO:MOVE CHAIRS FROM 192-242 TO 192-106 | 192 | CLOSED | 518.4 | 0 | 90.54 | 90.54
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | PA:PAINT NEW CLASSROOM | 192 | CLOSED | 9006.0259 | 0 | 7201.11 | 7201.11
PJ0004295 | CONVERT SPACE TO LARGE CAPACITY LECTURE RM - BLD 192-106A | BRENNAN, MICHAEL | CLOSED | 2012-09-24 | PL: PROJECT SUPPORT FOR FIRE LINE INSTALL AT 192 - 106 | 192 | CLOSED | 1999.241 | 0 | 298.374 | 298.374
PJ0004295 Total | [7 empty] | 588614.8172 | 0 | 538058.331 | 538058.331
PJ0004294 | SR 12/13: REROOF TWO ROOFS - KENNEDY LIBRARY 35 | LAMPMAN, GREG | CLOSED | 2012-09-19 | AD: JOC 12.025.004 EVERLAST | 035 | CLOSED | 93761.57 | 0 | 93761.57 | 93761.57
PJ0004294 | SR 12/13: REROOF TWO ROOFS - KENNEDY LIBRARY 35 | LAMPMAN, GREG | CLOSED | 2012-09-19 | AD: MCKENNA ENVIRONMENTAL | 035 | CLOSED | 4540 | 0 | 3010 | 3010
PJ0004294 | SR 12/13: REROOF TWO ROOFS - KENNEDY LIBRARY 35 | LAMPMAN, GREG | CLOSED | 2012-09-19 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0004294 | SR 12/13: REROOF TWO ROOFS - KENNEDY LIBRARY 35 | LAMPMAN, GREG | CLOSED | 2012-09-19 | IN: SR 12/13: REROOF TWO ROOFS - KENNEDY LIBRARY 35 | 035 | CLOSED | 320.28 | 0 | 266.9 | 266.9
PJ0004294 Total | [7 empty] | 98621.85 | 0 | 97038.47 | 97038.47
PJ0004293 | SR 12/13: PROVIDE EMERGENCY GENERATOR FOR LIGHTING - BLD 186 | JOHNSON, BEN | CLOSED | 2012-09-19 | AD: QUINN POWER SYSTEMS | 186 | CLOSED | 26242.91 | 0 | 26242.91 | 26242.91
PJ0004293 | SR 12/13: PROVIDE EMERGENCY GENERATOR FOR LIGHTING - BLD 186 | JOHNSON, BEN | CLOSED | 2012-09-19 | CA: EMERGENCY LIGHTING BACK UP GENERATOR AT EDES - BLDG. 186 | 186 | CLOSED | 375.92 | 0 | 732.755 | 732.755
PJ0004293 | SR 12/13: PROVIDE EMERGENCY GENERATOR FOR LIGHTING - BLD 186 | JOHNSON, BEN | CLOSED | 2012-09-19 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 0 | 0 | 0 | 0
PJ0004293 | SR 12/13: PROVIDE EMERGENCY GENERATOR FOR LIGHTING - BLD 186 | JOHNSON, BEN | CLOSED | 2012-09-19 | EL: EMERGENCY LIGHTING BACK UP GENERATOR AT EDES - BLDG. 186 | 186 | CLOSED | 12607.9016 | 0 | 12662.6604 | 12662.6604
PJ0004293 Total | [7 empty] | 39226.7316 | 0 | 39638.3254 | 39638.3254
PJ0004292 | SR 12/13: REPAIR BOILER AT CENTRAL PLANT BLD 40 | BISCHEL, JOSEPH W | CLOSED | 2012-09-19 | AD: R.F. MACDONALD | 040 | CLOSED | 53575.65 | 0 | 54567.62 | 54567.62
PJ0004292 | SR 12/13: REPAIR BOILER AT CENTRAL PLANT BLD 40 | BISCHEL, JOSEPH W | CLOSED | 2012-09-19 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004292 Total | [7 empty] | 53575.65 | 0 | 54567.62 | 54567.62
PJ0004288 | ADD BUILDING NUMBER TO SIGNAGE - JESPERSEN - BLDG 116 | MOLLAN, CHERYL L. | CLOSED | 2012-09-12 | CA:INSTALL NEW SIGNS AND TEXT ON EXISTING SIGNS, BLDG 116 | 116 | CLOSED | 1358.525 | 0 | 1006.182 | 1006.182
PJ0004288 | ADD BUILDING NUMBER TO SIGNAGE - JESPERSEN - BLDG 116 | MOLLAN, CHERYL L. | CLOSED | 2012-09-12 | CP: PROJECT CONTINGENCY | 116 | CLOSED | 142.26 | 0 | 0 | 0
PJ0004288 | ADD BUILDING NUMBER TO SIGNAGE - JESPERSEN - BLDG 116 | MOLLAN, CHERYL L. | CLOSED | 2012-09-12 | IN: SIGNAGE FOR EXTENDED EDUCATION - JESPERSEN - BLDG 116 | 116 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004288 Total | [7 empty] | 1564.841 | 0 | 1070.238 | 1070.238
PJ0004287 | REFINISH FLOOR IN PAC PAVILION - BLD 6 RM 128 | LAMPMAN, GREG | CLOSED | 2012-09-12 | AD: JOC 12.025.006 EVERLAST | 006 | CLOSED | 12584.7943 | 0 | 12584.7943 | 12584.7943
PJ0004287 | REFINISH FLOOR IN PAC PAVILION - BLD 6 RM 128 | LAMPMAN, GREG | CLOSED | 2012-09-12 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1293.8 | 0 | 0 | 0
PJ0004287 | REFINISH FLOOR IN PAC PAVILION - BLD 6 RM 128 | LAMPMAN, GREG | CLOSED | 2012-09-12 | IN: REFINISH FLOOR IN PAC PAVILION - BLD 6 RM 128 | 006 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004287 Total | [7 empty] | 14006.7063 | 0 | 12648.8503 | 12648.8503
PJ0004286 | REMODEL LIBRARY ART GALLERY - BLD 35 | MAY, TOM | CLOSED | 2012-09-11 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 3160.7265 | 0 | 3165.2205 | 3165.2205
PJ0004286 | REMODEL LIBRARY ART GALLERY - BLD 35 | MAY, TOM | CLOSED | 2012-09-11 | CA:DEMO OLD DISPLAY BOARDS INSTALL NEW BRDS | 035 | CLOSED | 7448.2003 | 0 | 10172.724 | 10172.724
PJ0004286 | REMODEL LIBRARY ART GALLERY - BLD 35 | MAY, TOM | CLOSED | 2012-09-11 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1377.56 | 0 | 0 | 0
PJ0004286 | REMODEL LIBRARY ART GALLERY - BLD 35 | MAY, TOM | CLOSED | 2012-09-11 | EL: DEMO OLD TRACKS AND INSTALL NEW POWER | 035 | CLOSED | 1980.6814 | 0 | 1781.904 | 1781.904
PJ0004286 | REMODEL LIBRARY ART GALLERY - BLD 35 | MAY, TOM | CLOSED | 2012-09-11 | IN: REMODEL LIBRARY ART GALLERY - BLD 35 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004286 | REMODEL LIBRARY ART GALLERY - BLD 35 | MAY, TOM | CLOSED | 2012-09-11 | PA:PAINT LIBRARY ART GALLERY | 035 | CLOSED | 1885.6124 | 0 | 1986.609 | 1986.609
PJ0004286 Total | [7 empty] | 15980.8926 | 0 | 17234.5695 | 17234.5695
PJ0004285 | CONVERT FIELD FOR FOR RUGBY TOURNAMENT - BLD 163 | LOOSLEY, SCOTT L. | CLOSED | 2012-09-10 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 52.03 | 0 | 0 | 0
PJ0004285 | CONVERT FIELD FOR FOR RUGBY TOURNAMENT - BLD 163 | LOOSLEY, SCOTT L. | CLOSED | 2012-09-10 | LA: CONVERT FIELD 4 FOR RUGBY TOURNAMENT - BLD 163 | 163 | CLOSED | 520.1694 | 0 | 839.844 | 839.844
PJ0004285 Total | [7 empty] | 572.1994 | 0 | 839.844 | 839.844
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | CA: INSTALL ADA RAMP AT REC CENTER ON 9/7 FOR FALL CONF/WOW | 043 | CLOSED | 1804.416 | 0 | 958.596 | 958.596
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | CA: SUPPLY AND OPERATE MAN-LIFT FOR WOW-A-0RAMA-SEPT 14 | GENERAL | CLOSED | 0 | 0 | 363.768 | 363.768
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | CU: SUPPORT FOR WOW CLUB SHOWCASE - 9/17 | GENERAL | CLOSED | 0 | 0 | 72.984 | 72.984
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | EL: INSTALL ONE SPIDER BOX AT MOTT LAWN BEFORE 9/12 | GENERAL | CLOSED | 0 | 0 | 370.788 | 370.788
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | EL: INSTALL ONE SPIDER BOX AT REC CENTER MAIN GYM - 9/7 | 043 | CLOSED | 0 | 0 | 235.956 | 235.956
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | GR: REPAIR RUTS FROM WOW-O-RAMA SETUP | GENERAL | CLOSED | 0 | 0 | 38.964 | 38.964
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | LA:SUPPORT FOR WOW CLUB SHOWCASE ON SEPT 17 | P-H16 | CLOSED | 0 | 0 | 834.777 | 834.777
PJ0004283 | 2012: SUPPORT FOR WOW | POPHAM, DONALD J. | CLOSED | 2012-09-06 | MC: MOVE ADA RAMPS TO REC CENTER - 9/7 | 043 | CLOSED | 0 | 0 | 102.612 | 102.612
PJ0004283 Total | [7 empty] | 1804.416 | 0 | 2978.445 | 2978.445
PJ0004279 | TRIP HAZARD ON SIDEWALK FROM GRAND TO YOSEMITE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-08-28 | AD: MAINO CONSTRUCTION (LOW-VALUE PUBLIC WORKS) | RESIDENCE | CLOSED | 4990 | 0 | 5125.58 | 5125.58
PJ0004279 | TRIP HAZARD ON SIDEWALK FROM GRAND TO YOSEMITE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-08-28 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004279 | TRIP HAZARD ON SIDEWALK FROM GRAND TO YOSEMITE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-08-28 | EO:REMOVE CONCRETE WALKWAY AT YOSEMITE | RESIDENCE | CLOSED | 1327.04 | 0 | 1109.1 | 1109.1
PJ0004279 | TRIP HAZARD ON SIDEWALK FROM GRAND TO YOSEMITE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-08-28 | PL: REPAIR LINE BROKEN WHEN YOSEMITE WALKAY WAS REMOVED | RESIDENCE | CLOSED | 0 | 0 | 267.49 | 267.49
PJ0004279 Total | [7 empty] | 6317.04 | 0 | 6502.17 | 6502.17
PJ0004278 | SP 12/13: DESIGN: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | AD: PMSM | 061 | CLOSED | 20865 | 0 | 20134.8641 | 20134.8641
PJ0004278 | SP 12/13: DESIGN: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 401.31 | 0 | 0 | 0
PJ0004278 Total | [7 empty] | 21266.31 | 0 | 20134.8641 | 20134.8641
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | AD: ASAP REPROGRAPHICS | 061 | CLOSED | 0 | 0 | 44.06 | 44.06
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | AD: CENTRAL COAST INDUSTRIES | 061 | CLOSED | 200.732 | 0 | 602.196 | 602.196
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | AD: HAYER | 061 | CLOSED | 749.9951 | 0 | 802.5 | 802.5
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | AD: JOC 13.028.042 MAINO | 061 | CLOSED | 93565.0265 | 0 | 93565.0265 | 93565.0265
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | AD: WAREHOUSE MATERIALS TO BE USED BY CONTRACTOR | 061 | CLOSED | 0 | 0 | 78.1597 | 78.1597
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 10205.41 | 0 | 0 | 0
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 061 | CLOSED | 0 | 0 | 14.4 | 14.4
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | IN: SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | 061 | CLOSED | 1281.12 | 0 | 1569.372 | 1569.372
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | LO: INSTALL NEW LOCKS | 061 | CLOSED | 4938.0892 | 0 | 2525.724 | 2525.724
PJ0004277 | SP 12/13: ADA RESTROOMS, EAST SIDE - SPANOS STADIUM | LAMPMAN, GREG | CLOSED | 2012-08-28 | PA: PAINT WALLS AND CEILING | 061 | CLOSED | 3313.952 | 0 | 1993.68 | 1993.68
PJ0004277 Total | [7 empty] | 114254.3248 | 0 | 101195.1182 | 101195.1182
PJ0004275 | INSTALL CARPET SQUARES & BASE COVE TO MATCH OCIO AREA-BLD14-111 | MOLLAN, CHERYL L. | CLOSED | 2012-08-07 | AD: FLOOR CONNECTION | 014 | CLOSED | 5477.7259 | 0 | 5479.6626 | 5479.6626
PJ0004275 | INSTALL CARPET SQUARES & BASE COVE TO MATCH OCIO AREA-BLD14-111 | MOLLAN, CHERYL L. | CLOSED | 2012-08-07 | CA:REMOVE COVEBASE AND WALL HUNG OVERHEADS | 014 | CLOSED | 338.328 | 0 | 336.6809 | 336.6809
PJ0004275 | INSTALL CARPET SQUARES & BASE COVE TO MATCH OCIO AREA-BLD14-111 | MOLLAN, CHERYL L. | CLOSED | 2012-08-07 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 760.89 | 0 | 0 | 0
PJ0004275 | INSTALL CARPET SQUARES & BASE COVE TO MATCH OCIO AREA-BLD14-111 | MOLLAN, CHERYL L. | CLOSED | 2012-08-07 | IN: CARPET SQUARES & BASE COVE TO MATCH OCIO AREA-BLD14-111 | 014 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004275 | INSTALL CARPET SQUARES & BASE COVE TO MATCH OCIO AREA-BLD14-111 | MOLLAN, CHERYL L. | CLOSED | 2012-08-07 | PA:PATCH HOLES AND PAINT IN VANILLA BEAN BLDG14 111 COMPLEX | 014 | CLOSED | 1664.736 | 0 | 1872.756 | 1872.756
PJ0004275 Total | [7 empty] | 8369.7919 | 0 | 7721.1275 | 7721.1275
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | LO. INSTALL LOCK IN ONE DOOR | 027 | CLOSED | 802.7246 | 0 | 2002.704 | 2002.704
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | AD: (SR FUNDING) JOC 13.028.018.01 MAINO | 027 | CLOSED | 0 | 0 | 9872.57 | 9872.57
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | AD: JOC 13.028.018.00 MAINO | 027 | CLOSED | 52011.9296 | 0 | 41448.3867 | 41448.3867
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | AD: MACDONALD COMPANY | 027 | CLOSED | 331.7 | 0 | 337.05 | 337.05
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | AD: MCKENNA ENVIRONMENTAL | 027 | CLOSED | 3631.58 | 0 | 3631.58 | 3631.58
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | ANTS: PROGRAM ALARMS FOR PHARMACY COUNTER REMODEL-H.C. 27 RM 125 | 027 | CLOSED | 384.384 | 0 | 132.132 | 132.132
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | CA: DRILL HOLES TO MOUNT SECURITY EQUIPMENT-H/C PHARMACY COUNTER | 027 | CLOSED | 112.776 | 0 | 56.388 | 56.388
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1165.82 | 0 | 0 | 0
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | EL: REMODEL THE ELECTRICAL | 027 | CLOSED | 5401.3627 | 0 | 6089.748 | 6089.748
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | ES: MOVE THERMOSTAT TO NEW LOCATION - H/C BLDG. 24, RM. 125 | 027 | CLOSED | 307.308 | 0 | 218.7049 | 218.7049
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | IN: M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | 027 | CLOSED | 640.56 | 0 | 480.42 | 480.42
PJ0004273 | M&R H/C 13/14: PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | LAMPMAN, GREG | CLOSED | 2012-08-10 | PA: PAINTING FOR PHARMACY COUNTER REMODEL - H.C. 27 RM 125 | 027 | CLOSED | 2484.864 | 0 | 2511.648 | 2511.648
PJ0004273 Total | [7 empty] | 67275.009 | 0 | 66781.3316 | 66781.3316
PJ0004272 | REMOVAL OF LIBRARY SHELVING - BLD 35 RM 111 | BRENNAN, MICHAEL | CLOSED | 2012-08-01 | CA:REMOVE SHELVES | 035 | CLOSED | 2007.9767 | 0 | 815.724 | 815.724
PJ0004272 | REMOVAL OF LIBRARY SHELVING - BLD 35 RM 111 | BRENNAN, MICHAEL | CLOSED | 2012-08-01 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 207.21 | 0 | 0 | 0
PJ0004272 | REMOVAL OF LIBRARY SHELVING - BLD 35 RM 111 | BRENNAN, MICHAEL | CLOSED | 2012-08-01 | IN: REMOVAL OF LIBRARY SHELVING - BLD 35 RM 111 | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004272 Total | [7 empty] | 2279.2427 | 0 | 879.78 | 879.78
PJ0004271 | INSTALL A/V SMART ROOM - BLD 46 SMALL CONFERENCE ROOM (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2012-08-16 | CA: SUPPORT FOR SMART ROOM INSTALLATION - CRANDALL SM CONF RM 46 | 046 | CLOSED | 683.88 | 0 | 290.58 | 290.58
PJ0004271 | INSTALL A/V SMART ROOM - BLD 46 SMALL CONFERENCE ROOM (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2012-08-16 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 0 | 0 | 0 | 0
PJ0004271 | INSTALL A/V SMART ROOM - BLD 46 SMALL CONFERENCE ROOM (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2012-08-16 | IN: INSTALL A/V SMART ROOM - BLD 46 SMALL CONFERENCE ROOM | 046 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004271 Total | [7 empty] | 811.992 | 0 | 418.692 | 418.692
PJ0004270 | ORDER AND INSTALL CONCRETE MEMORAL BENCH - ADMIN - 001 | GALVEZ, CESAR | CLOSED | 2012-08-15 | AD: QUICK CRETE PURCHASE | GENERAL | CLOSED | 1241.6815 | 0 | 1241.6815 | 1241.6815
PJ0004270 | ORDER AND INSTALL CONCRETE MEMORAL BENCH - ADMIN - 001 | GALVEZ, CESAR | CLOSED | 2012-08-15 | CA:INSTALL PLAQUE ON MEMORIAL BENCH (9/24-10/3) - ADMIN 001 | GENERAL | CLOSED | 56.388 | 0 | 59.388 | 59.388
PJ0004270 | ORDER AND INSTALL CONCRETE MEMORAL BENCH - ADMIN - 001 | GALVEZ, CESAR | CLOSED | 2012-08-15 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 151.14 | 0 | 0 | 0
PJ0004270 | ORDER AND INSTALL CONCRETE MEMORAL BENCH - ADMIN - 001 | GALVEZ, CESAR | CLOSED | 2012-08-15 | EO: PLACE MEMORIAL BENCH AT ADMIN BUILDING (9/24-10/3) | GENERAL | CLOSED | 149.292 | 0 | 177.456 | 177.456
PJ0004270 | ORDER AND INSTALL CONCRETE MEMORAL BENCH - ADMIN - 001 | GALVEZ, CESAR | CLOSED | 2012-08-15 | IN: INSTALL MEMORAL BENCH WITH CONCRETE PAD - ADMIN LAWN - 001 | GENERAL | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004270 | ORDER AND INSTALL CONCRETE MEMORAL BENCH - ADMIN - 001 | GALVEZ, CESAR | CLOSED | 2012-08-15 | MO: ASSIST ROAD CREW WITH MOVING OF BENCH - ADMIN | GENERAL | CLOSED | 0 | 0 | 44.472 | 44.472
PJ0004270 Total | [7 empty] | 1662.5575 | 0 | 1587.0535 | 1587.0535
PJ0004268 | CHANGE DOORS TO FULL GLASS - 4 LOCATIONS - BLD 170G RM 115 | BRENNAN, MICHAEL | CLOSED | 2012-08-06 | CP: PROJECT CONTINGENCY | 170G | CLOSED | 539.94 | 0 | 0 | 0
PJ0004268 | CHANGE DOORS TO FULL GLASS - 4 LOCATIONS - BLD 170G RM 115 | BRENNAN, MICHAEL | CLOSED | 2012-08-06 | IN: CHANGE DOORS TO FULL GLASS - 4 LOCATIONS - BLD 170G RM 115 | 170G | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004268 | CHANGE DOORS TO FULL GLASS - 4 LOCATIONS - BLD 170G RM 115 | BRENNAN, MICHAEL | CLOSED | 2012-08-06 | LO:EXCHANGE HARDWARE | 170G | CLOSED | 258.2958 | 0 | 203.154 | 203.154
PJ0004268 | CHANGE DOORS TO FULL GLASS - 4 LOCATIONS - BLD 170G RM 115 | BRENNAN, MICHAEL | CLOSED | 2012-08-06 | PA:PAINT NEW DOORS | 170G | CLOSED | 1170.7852 | 0 | 1127.916 | 1127.916
PJ0004268 | CHANGE DOORS TO FULL GLASS - 4 LOCATIONS - BLD 170G RM 115 | BRENNAN, MICHAEL | CLOSED | 2012-08-06 | PCV CA:INSTALL DOORS | 170G | CLOSED | 3906.1235 | 0 | 2366.85 | 2366.85
PJ0004268 Total | [7 empty] | 5939.2004 | 0 | 3761.976 | 3761.976
PJ0004267 | SR 12/13: ENGINEERING STUDY FOR BOILER ADDITION - CENTRAL PLANT | ELLIOT, DENNIS K | CLOSED | 2012-08-13 | AD: GOSS ENGINEERING | 040 | CLOSED | 42935 | 0 | 30054.5 | 30054.5
PJ0004267 | SR 12/13: ENGINEERING STUDY FOR BOILER ADDITION - CENTRAL PLANT | ELLIOT, DENNIS K | CLOSED | 2012-08-13 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004267 Total | [7 empty] | 42935 | 0 | 30054.5 | 30054.5
PJ0004266 | SP 12/13: CONSTRUCT MEMORIAL PLAZA PATH OF TRAVEL | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: DIVISION OF STATE ARCHITECT | 061 | CLOSED | 500 | 0 | 500 | 500
PJ0004266 | SP 12/13: CONSTRUCT MEMORIAL PLAZA PATH OF TRAVEL | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: JOC 13.027.002 PUB | 061 | CLOSED | 68767.5518 | 0 | 68767.5518 | 68767.5518
PJ0004266 | SP 12/13: CONSTRUCT MEMORIAL PLAZA PATH OF TRAVEL | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 198.96 | 0 | 0 | 0
PJ0004266 | SP 12/13: CONSTRUCT MEMORIAL PLAZA PATH OF TRAVEL | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | EL: INSTALL EXIT LIGHTS UNDER SOUTH BLEACHERS - SPANOS 061 | 061 | CLOSED | 4044.96 | 0 | 3775.296 | 3775.296
PJ0004266 | SP 12/13: CONSTRUCT MEMORIAL PLAZA PATH OF TRAVEL | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | IN: MODIFY CURB RAMPS, LANDINGS, POT IN C4 &TO SPANOS PLAZA | 061 | CLOSED | 512.448 | 0 | 544.476 | 544.476
PJ0004266 | SP 12/13: CONSTRUCT MEMORIAL PLAZA PATH OF TRAVEL | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | LA: INFILL LANDSCAPE FOR MEMORIAL PLAZA PATH OF TRAVEL | 061 | CLOSED | 3748.2 | 0 | 1890.684 | 1890.684
PJ0004266 Total | [7 empty] | 77772.1198 | 0 | 75478.0078 | 75478.0078
PJ0004264 | SP 12/13: CONSTRUCTION -MODIFY CONCOURSE RAMPS (ADA)- SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: EER, INC. | 061 | CLOSED | 35487.62 | 0 | 35487.62 | 35487.62
PJ0004264 | SP 12/13: CONSTRUCTION -MODIFY CONCOURSE RAMPS (ADA)- SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | CA: REMOVE AND REINSTALL HANDRAIL EXTENSIONS | 061 | CLOSED | 3247.728 | 0 | 3673.206 | 3673.206
PJ0004264 | SP 12/13: CONSTRUCTION -MODIFY CONCOURSE RAMPS (ADA)- SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 2931.39 | 0 | 0 | 0
PJ0004264 | SP 12/13: CONSTRUCTION -MODIFY CONCOURSE RAMPS (ADA)- SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | IN: CONSTRUCTION -MODIFY CONCOURSE RAMPS (ADA)- SPANOS 061 | 061 | CLOSED | 768.672 | 0 | 416.364 | 416.364
PJ0004264 Total | [7 empty] | 42435.41 | 0 | 39577.19 | 39577.19
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: ADA SIGN DEPOT | 061 | CLOSED | 2675 | 0 | 2100.9022 | 2100.9022
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: DUCHARME | 061 | CLOSED | 2675 | 0 | 2623.212 | 2623.212
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: FLOOR CONNECTION | 061 | CLOSED | 4280 | 0 | 807.85 | 807.85
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: RICK TEIXEIRA WELDING | 061 | CLOSED | 4815 | 0 | 4514.0625 | 4514.0625
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | AD: SOUTHERN BLEACHER | 061 | CLOSED | 5350 | 0 | 4327.6471 | 4327.6471
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | CA: INSTALL VARIOUS ADA ALTERATION AT BLDG 61. | 061 | CLOSED | 18188.64 | 0 | 22282.3564 | 22282.3564
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 6754.12 | 0 | 0 | 0
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | EL: PROVIDE POWER FOR PUSH PAD DOOR OPENERS | 061 | CLOSED | 7193.28 | 0 | 6172.932 | 6172.932
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | IN: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | 061 | CLOSED | 1024.896 | 0 | 1889.652 | 1889.652
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | LO:INSTALL PUSH PAD OPENERS | 061 | CLOSED | 13857.408 | 0 | 8168.22 | 8168.22
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | PA: PAINT FINISHVARIOUS ALTERATIONS | 061 | CLOSED | 3749.472 | 0 | 2658.8388 | 2658.8388
PJ0004263 | SP 12/13: CONSTRUCTION- COMPLETE WEST SIDE MODS - SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-08-03 | PL: RELOCATE LAVATORY - WEST SIDE SPANOS STADIUM RM 102 | 061 | CLOSED | 2689.344 | 0 | 65.292 | 65.292
PJ0004263 Total | [7 empty] | 73252.16 | 0 | 55610.9649 | 55610.9649
PJ0004260 | FP 12/13: PURCHASE TEMP FLOORING FOR ADA SEATING -SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2012-08-03 | AD: AMERICAN TURF AND CARPET | 061 | CLOSED | 52877.24 | 0 | 53497.38 | 53497.38
PJ0004260 | FP 12/13: PURCHASE TEMP FLOORING FOR ADA SEATING -SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004260 Total | [7 empty] | 52877.24 | 0 | 53497.38 | 53497.38
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: EARTH SYSTEMS | 061 | CLOSED | 3745 | 0 | 1312.248 | 1312.248
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: ENGLEKIRK AND SABOL | 061 | CLOSED | 1382.44 | 0 | 1382.44 | 1382.44
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: HAYER | 061 | CLOSED | 1785.9049 | 0 | 1785.9049 | 1785.9049
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: JOC 13.028.002 MAINO | 061 | CLOSED | 381802.75 | 0 | 89001.9259 | 89001.9259
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: JOC 13.029.022.00 MAINO | 061 | CLOSED | 139227.2658 | 0 | 496048.0303 | 496048.0303
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: MCKENNA ENVIRONMENTAL | 061 | CLOSED | 13556.9 | 0 | 12940.58 | 12940.58
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 38386.14 | 0 | 0 | 0
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | EH&S: (N/L) | 061 | CLOSED | 1374 | 0 | 0 | 0
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIALS, ONLY) | 061 | CLOSED | 0 | 0 | 429.6 | 429.6
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | EL: PROVIDE ELECTRICAL SUPPORT FOR WHEELCHAIR COMPANION SEATS | 061 | CLOSED | 7269.36 | 0 | 13733.496 | 13733.496
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | IN:SP 12/13:WHEELCHAIR AREA &22 COMPANION SEATS - EAST BLEACHERS | 061 | CLOSED | 12811.2 | 0 | 2338.044 | 2338.044
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | LA: SPANOS ADA E. SIDE BLEACHER WHEELCHAIR AREA PROJECT | 061 | CLOSED | 22990.224 | 0 | 20039.5952 | 20039.5952
PJ0004259 | SP 12/13:WHEELCHAIR AREA & COMPANION SEATS - ADA -EAST BLEACHERS | LAMPMAN, GREG | CLOSED | 2012-08-03 | MO: MOVE SHELVING FROM STORAGE UNDER EAST SIDE BLEACHERS - 061 | 061 | CLOSED | 777.6 | 0 | 262.566 | 262.566
PJ0004259 Total | [7 empty] | 625108.7847 | 0 | 639274.4303 | 639274.4303
PJ0004258 | SP 12/13: DESIGN ADA SEATING, ROUTE & SIGNAGE - SPANOS STAD | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: ASAP REPROGRAPHICS | 061 | CLOSED | 140.08 | 0 | 140.08 | 140.08
PJ0004258 | SP 12/13: DESIGN ADA SEATING, ROUTE & SIGNAGE - SPANOS STAD | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: DIVISION OF STATE ARCHITECT | 061 | CLOSED | 1848 | 0 | 1180 | 1180
PJ0004258 | SP 12/13: DESIGN ADA SEATING, ROUTE & SIGNAGE - SPANOS STAD | LAMPMAN, GREG | CLOSED | 2012-08-03 | AD: PMSM | 061 | CLOSED | 47941.4142 | 0 | 42196.2311 | 42196.2311
PJ0004258 | SP 12/13: DESIGN ADA SEATING, ROUTE & SIGNAGE - SPANOS STAD | LAMPMAN, GREG | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 4345.59 | 0 | 0 | 0
PJ0004258 Total | [7 empty] | 54275.0842 | 0 | 43516.3111 | 43516.3111
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | AD: (FP FUNDING) JOC 12.025.002.00 EVERLAST | GENERAL | CLOSED | 152925 | 0 | 135568.91 | 135568.91
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | AD: (FP FUNDING) JOC 13.029.004 MAINO | GENERAL | CLOSED | 0 | 0 | 33733.83 | 33733.83
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | AD: JOC 12.025.002.01 EVERLAST | GENERAL | CLOSED | 61088.44 | 0 | 59413.676 | 59413.676
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | AD: NORTH COAST ENGINEERING | GENERAL | CLOSED | 12128.45 | 0 | 12128.45 | 12128.45
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 3520.24 | 0 | 0 | 0
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | IN: PATH OF TRAVEL & SIGNAGE - KEN LIB BUS STOP TO SPANOS | GENERAL | CLOSED | 2562.24 | 0 | 2786.436 | 2786.436
PJ0004256 | SP 12/13, FP 12/13:ADA PATH OFTRAVEL/KEN LIB BUS STOP TO STADIUM | MCNALLY, CURTIS | CLOSED | 2012-08-03 | LA:REPAIR DAMAGED IRRIGATION | GENERAL | CLOSED | 779.28 | 0 | 58.446 | 58.446
PJ0004256 Total | [7 empty] | 233003.65 | 0 | 243689.748 | 243689.748
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | AD: PURCHASE OF PODIUM LAMP FOR PRES. OFFICE - 10/25 (N/L) | 051 | CLOSED | 0 | 0 | 119.352 | 119.352
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: INSTALL SOUTH AND WEST WALL AT PRES. RES. TENT - 8/3 | 051 | CLOSED | 187.96 | 0 | 140.97 | 140.97
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: INSTALL SOUTH AND WEST WALLS AND CLOUDS - APRIL 11 | 051 | CLOSED | 0 | 0 | 328.93 | 328.93
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: INSTALL SOUTH AND WEST WALLS AT 051 BEFORE 3PM ON 9/20 | 051 | CLOSED | 0 | 0 | 140.97 | 140.97
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: PLEASE REMOVE ALL WALLS AND CLOUDS BEFORE THURS APR 25 | 051 | CLOSED | 0 | 0 | 328.93 | 328.93
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: REMOVE ALL TENT SIDES AT PRES. RESIDENCE ON FRIDAY 3/22 | 051 | CLOSED | 0 | 0 | 328.93 | 328.93
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: REMOVE ALL TENT SIDES AT PRES. RESIDENCE ON FRIDAY 9/7 | 051 | CLOSED | 187.96 | 0 | 140.97 | 140.97
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: SET UP 3 TENT SIDES AT PRES. HOUSE - NOV 2 | 051 | CLOSED | 0 | 0 | 516.89 | 516.89
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: SET UP TENT AT RESIDENCE FOR CANOPY ONLY - 9/27 | 051 | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: SET UP THE TENT TOP AND THREE SIDES AT UNIV. HOUSE | 051 | CLOSED | 0 | 0 | 657.86 | 657.86
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CA: TAKE DOWN TENT SIDES AND ROLL UP TOP AT UH51 | 051 | CLOSED | 0 | 0 | 610.87 | 610.87
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CU: SUPPORT FOR PRESIDENT'S CABINET EVENT - 11/2 | 051 | CLOSED | 0 | 0 | 228.075 | 228.075
PJ0004252 | 12/13: EVENT SUPPORT AT PRESIDENT'S RESIDENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-07-30 | CU: SUPPORT FOR PRESIDENT'S DINNER - 2/4 | 051 | CLOSED | 0 | 0 | 30.41 | 30.41
PJ0004252 Total | [7 empty] | 375.92 | 0 | 3667.137 | 3667.137
PJ0004250 | 12/13 MAINTENANCE NEEDS - UNIVERSITY HOUSE (MAINT) - BLDG. 051 | MAY, TOM | CLOSED | 2012-07-26 | AD: HAMON OVERHEAD DOOR | 051 | CLOSED | 0 | 0 | 461.1 | 461.1
PJ0004250 | 12/13 MAINTENANCE NEEDS - UNIVERSITY HOUSE (MAINT) - BLDG. 051 | MAY, TOM | CLOSED | 2012-07-26 | CA:12/13 MAINTANENCE AT UH | 051 | CLOSED | 187.96 | 0 | 1327.93 | 1327.93
PJ0004250 | 12/13 MAINTENANCE NEEDS - UNIVERSITY HOUSE (MAINT) - BLDG. 051 | MAY, TOM | CLOSED | 2012-07-26 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0004250 | 12/13 MAINTENANCE NEEDS - UNIVERSITY HOUSE (MAINT) - BLDG. 051 | MAY, TOM | CLOSED | 2012-07-26 | CPE: SUPPORT FOR PRESIDENT'S RESIDENCE MAINTENANCE PROJECT | 051 | CLOSED | 0 | 0 | 286.165 | 286.165
PJ0004250 | 12/13 MAINTENANCE NEEDS - UNIVERSITY HOUSE (MAINT) - BLDG. 051 | MAY, TOM | CLOSED | 2012-07-26 | EL: 2012/2013 MAINTENANCE AT UNIVERSITY HOUSE | 051 | CLOSED | 0 | 0 | 1899.63 | 1899.63
PJ0004250 | 12/13 MAINTENANCE NEEDS - UNIVERSITY HOUSE (MAINT) - BLDG. 051 | MAY, TOM | CLOSED | 2012-07-26 | PL:PRESIDENT'S RESIDENCE MAINTENANCE FOR 2012/2013 | 051 | CLOSED | 0 | 0 | 424.8 | 424.8
PJ0004250 Total | [7 empty] | 187.96 | 0 | 4399.625 | 4399.625
PJ0004249 | DRAIN 15 RESEARCH POOLS AT AERO HANGER - 04 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-07-25 | CP: PROJECT CONTINGENCY | 004N | CLOSED | 0 | 0 | 0 | 0
PJ0004249 | DRAIN 15 RESEARCH POOLS AT AERO HANGER - 04 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-07-25 | EL:SHUT OFF ALL POWER TO RESEARCH POOLS AT 004 | 004N | CLOSED | 112.36 | 0 | 28.09 | 28.09
PJ0004249 | DRAIN 15 RESEARCH POOLS AT AERO HANGER - 04 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-07-25 | LO: INSTALL PADLOCKS WITH ORANGE CORES AT POOL COMPOUND 004 | 004N | CLOSED | 72.555 | 0 | 48.37 | 48.37
PJ0004249 | DRAIN 15 RESEARCH POOLS AT AERO HANGER - 04 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2012-07-25 | PL:PUMP OUT RESEARCH POOLS AT 004 | 004N | CLOSED | 870.56 | 0 | 2313.93 | 2313.93
PJ0004249 Total | [7 empty] | 1055.475 | 0 | 2390.39 | 2390.39
PJ0004248 | NEW CARPET - BLD 35 RM 114 | BRENNAN, MICHAEL | CLOSED | 2012-07-23 | AD: FLOOR CONNECTION | 035 | CLOSED | 17060.8076 | 0 | 17060.8076 | 17060.8076
PJ0004248 | NEW CARPET - BLD 35 RM 114 | BRENNAN, MICHAEL | CLOSED | 2012-07-23 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1712.49 | 0 | 0 | 0
PJ0004248 | NEW CARPET - BLD 35 RM 114 | BRENNAN, MICHAEL | CLOSED | 2012-07-23 | IN: NEW CARPET - BLD 35 RM 114 | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004248 Total | [7 empty] | 18837.3536 | 0 | 17124.8636 | 17124.8636
PJ0004247 | BOOKSTORE TV MOUNTS REVIEW AND PERMIT - 065-101 | HOGAN, MIKE | CLOSED | 2012-07-24 | AD: ENGLEKIRK AND SABOL | 065 | CLOSED | 535 | 0 | 535 | 535
PJ0004247 | BOOKSTORE TV MOUNTS REVIEW AND PERMIT - 065-101 | HOGAN, MIKE | CLOSED | 2012-07-24 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 66.31 | 0 | 0 | 0
PJ0004247 | BOOKSTORE TV MOUNTS REVIEW AND PERMIT - 065-101 | HOGAN, MIKE | CLOSED | 2012-07-24 | IN: BOOKSTORE TV MOUNTS REVIEW - 065-101 | 065 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004247 Total | [7 empty] | 729.422 | 0 | 599.056 | 599.056
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | AD: JOC PRE CON | 043 | CLOSED | 409074.375 | 0 | 0 | 0
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | CA: FABRICATE AND INSTALL TICKET COUNTER DRAWERS | 043 | CLOSED | 0 | 0 | 3599.007 | 3599.007
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 43166.15 | 0 | 0 | 0
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | EL: FURNISH AND INSTALL OUTLETS IN FLOOR BOX - REC CTR 043-132H | 043 | CLOSED | 0 | 0 | 783.768 | 783.768
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | ES: SUPPORT FOR REC CENTER POST-CONSTRUCTION WORK | 043 | CLOSED | 2779.0264 | 0 | 4200.786 | 4200.786
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | IN:MJ: POST CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | 043 | CLOSED | 5124.48 | 0 | 1505.316 | 1505.316
PJ0004246 | MJ: POST-CONSTRUCTION WORK FOR REC CENTER EXPANSION - BLDG 43 | JUDD, PERRY | CLOSED | 2012-07-24 | LA: SUPPORT FOR REC CENTER POST-CONSTRUCTION WORK | 043 | CLOSED | 11777.2014 | 0 | 7975.818 | 7975.818
PJ0004246 Total | [7 empty] | 471921.2328 | 0 | 18064.695 | 18064.695
PJ0004245 | FP 12/13:SURVEY ONLY-ADA PATHWAY N.PERIMETER BUS STOP TO STADIUM | NEEL, JOEL | CLOSED | 2012-07-24 | AD: NORTH COAST ENGINEERING | GENERAL | CLOSED | 14499 | 0 | 14499 | 14499
PJ0004245 | FP 12/13:SURVEY ONLY-ADA PATHWAY N.PERIMETER BUS STOP TO STADIUM | NEEL, JOEL | CLOSED | 2012-07-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004245 Total | [7 empty] | 14499 | 0 | 14499 | 14499
PJ0004243 | ART INSTALLATION IN MAIN LIBRARY STAIRWELL - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2012-07-16 | AD: TEMPLE BUILDERS | 035 | CLOSED | 1605.6527 | 0 | 1605.6527 | 1605.6527
PJ0004243 | ART INSTALLATION IN MAIN LIBRARY STAIRWELL - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2012-07-16 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 384.47 | 0 | 0 | 0
PJ0004243 | ART INSTALLATION IN MAIN LIBRARY STAIRWELL - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2012-07-16 | EL:INSTALL ELECTRICAL FOR ART INSTALLATION IN LIB | 035 | CLOSED | 1500.0036 | 0 | 329.292 | 329.292
PJ0004243 | ART INSTALLATION IN MAIN LIBRARY STAIRWELL - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2012-07-16 | IN: ART INSTALLATION IN MAIN LIBRARY STAIRWELL - BLD 35 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004243 | ART INSTALLATION IN MAIN LIBRARY STAIRWELL - BLD 35 | GONZALES, ALBERT M. | CLOSED | 2012-07-16 | IN: STATE FIRE MARSHAL | 035 | CLOSED | 200 | 0 | 0 | 0
PJ0004243 Total | [7 empty] | 3818.2383 | 0 | 2063.0567 | 2063.0567
PJ0004242 | 12/13: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2012-07-16 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004242 | 12/13: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2012-07-16 | CU: SUPPORT WRESTLING TOURNAMENT - 1/6 | 042 | CLOSED | 0 | 0 | 866.67 | 866.67
PJ0004242 | 12/13: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2012-07-16 | CU: SUPPORT WRESTLING V. CAL BAPTIST - 12/7 | 042 | CLOSED | 0 | 0 | 683.472 | 683.472
PJ0004242 | 12/13: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2012-07-16 | CU: SUPPORT WRESTLING V. CENTRAL MICHIGAN - 2/17 | 042 | CLOSED | 0 | 0 | 952.632 | 952.632
PJ0004242 | 12/13: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2012-07-16 | CU: WRESTLING V. AIR FORCE - 1/20 | 042 | CLOSED | 0 | 0 | 538.32 | 538.32
PJ0004242 | 12/13: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2012-07-16 | CU:WRESTLING V. CSU BAKERSFIELD - 1/12 | 042 | CLOSED | 0 | 0 | 709.656 | 709.656
PJ0004242 Total | [7 empty] | 0 | 0 | 3750.75 | 3750.75
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT FOR BASKETBALL V. ST. MARY'S - NOV 29 | 042 | CLOSED | 0 | 0 | 583.872 | 583.872
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT FOR W. BASKETBALL V. CSULB - 3/9 | 042 | CLOSED | 0 | 0 | 1158.66 | 1158.66
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT W. BASKETBALL TOURNAMENT - 11/24 | 042 | CLOSED | 0 | 0 | 1754.724 | 1754.724
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT W. BASKETBALL V. SAN DIEGO - 11/17 | 042 | CLOSED | 0 | 0 | 985.284 | 985.284
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT W. BASKETBALL V. STEPHEN AUSTIN UNIV - 11/23 | 042 | CLOSED | 0 | 0 | 729.84 | 729.84
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT WM'S BBALL V. CSU NORTHRIDGE - 2/21 | 042 | CLOSED | 0 | 0 | 784.317 | 784.317
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT WM'S BBALL V. HAWAI'I - 2/23 | 042 | CLOSED | 0 | 0 | 1704.594 | 1704.594
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT WM. BASKETBALL V. PACIFIC - 1/12 | 042 | CLOSED | 0 | 0 | 928.608 | 928.608
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT WM. BASKETBALL V. UC DAVIS - 1/10 | 042 | CLOSED | 0 | 0 | 675.072 | 675.072
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: W. BASKETBALL V. UC IRVINE - 3/7 | 042 | CLOSED | 0 | 0 | 710.4 | 710.4
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: W. BBALLL V. CSU FULLERTON - JAN 31 | 042 | CLOSED | 0 | 0 | 630.672 | 630.672
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: WM. BASKETBALL V. LOYOLA - 12/20 | 042 | CLOSED | 0 | 0 | 488.304 | 488.304
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: WM. BBALL V. UC RIVERSIDE - 2/2 | 042 | CLOSED | 0 | 0 | 662.472 | 662.472
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: WOMEN'S BASKETBALL V. SAN FRANCISCO - 12/18 | 042 | CLOSED | 0 | 0 | 679.272 | 679.272
PJ0004241 | 12/13: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: WOMENS BBALL V. UCSB - 1/19 | 042 | CLOSED | 0 | 0 | 843.84 | 843.84
PJ0004241 Total | [7 empty] | 0 | 0 | 13319.931 | 13319.931
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: M. BASKETBALL V. PACIFIC - 2/7 | 042 | CLOSED | 0 | 0 | 808.794 | 808.794
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: M. BASKETBALL V. UCDAVIS - 2/9 | 042 | CLOSED | 0 | 0 | 2082.108 | 2082.108
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: M. BASKETBALL V. UCSB - 2/16 | 042 | CLOSED | 0 | 0 | 1032.546 | 1032.546
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: MEN'S BASKETBALL BRACKET BUSTER GAME - 2/23 | 042 | CLOSED | 0 | 0 | 1465.842 | 1465.842
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: MEN'S BASKETBALL V. CSU NORTHRIDGE - 1/26 | 042 | CLOSED | 0 | 0 | 860.886 | 860.886
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: MEN'S BASKETBALL V. UC RIVERSIDE - 3/7 | 042 | CLOSED | 0 | 0 | 559.797 | 559.797
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT FOR M. BASKETBALL V. CSU FULLERTON - 3/9 | 042 | CLOSED | 0 | 0 | 1049.184 | 1049.184
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT M. BASKETBALL EXHIBITION - OCT 27 | 042 | CLOSED | 0 | 0 | 1067.04 | 1067.04
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT M. BASKETBALL V. EAST. NEW MEXICO - 12/14 | 042 | CLOSED | 0 | 0 | 955.47 | 955.47
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT M. BASKETBALL V. FRESNO ST. - 11/19 | 042 | CLOSED | 0 | 0 | 866.685 | 866.685
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT M. BASKETBALL V. HAWAII - 1/24 | 042 | CLOSED | 0 | 0 | 821.04 | 821.04
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT M. BASKETBALL V. LONG BEACH ST. - 1/3 | 042 | CLOSED | 0 | 0 | 649.872 | 649.872
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT M. BASKETBALL V. UC IRVIINE - 1/5 | 042 | CLOSED | 0 | 0 | 1018.146 | 1018.146
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT MEN'S BASKETBALL V. MENLO COLLEGE - 12/8 | 042 | CLOSED | 0 | 0 | 835.596 | 835.596
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT MEN'S BASKETBALL V. N. COLORADO - 11/15 | 042 | CLOSED | 0 | 0 | 729.84 | 729.84
PJ0004240 | 12/13: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: W. BASKETBALL V. SAN DIEGO ST. - 12/16 | 042 | CLOSED | 0 | 0 | 1209 | 1209
PJ0004240 Total | [7 empty] | 0 | 0 | 16011.846 | 16011.846
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT FOR SOFTBALL ALUMNI GAME - NOV. 3 | 161 | CLOSED | 0 | 0 | 192.144 | 192.144
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE - NOV. 2 @ SPM | 161 | CLOSED | 0 | 0 | 379.452 | 379.452
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE - OCT. 13 | 161 | CLOSED | 0 | 0 | 200.712 | 200.712
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE - OCT. 19 | 161 | CLOSED | 0 | 0 | 253.266 | 253.266
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT FOR SOFTBALL SCRIMMAGE - OCT. 27 | 161 | CLOSED | 0 | 0 | 262.56 | 262.56
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT SOFTBALL MUSTANG CLASSIC - MAR 8-10 | 161 | CLOSED | 0 | 0 | 5971.806 | 5971.806
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT SOFTBALL V. CSU LONG BEACH/FRESNO ST. - MAR 23-25 | 161 | CLOSED | 0 | 0 | 1509.954 | 1509.954
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT SOFTBALL V. HAWAI'I - APR 19-20 | 161 | CLOSED | 0 | 0 | 1386.7057 | 1386.7057
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT SOFTBALL V. PACIFIC - APR 6-7 | 161 | CLOSED | 0 | 0 | 1420.74 | 1420.74
PJ0004239 | 12/13: SUPPORT FOR SOFTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT SOFTBALL V. UCSB - APR 10 & APR 17 | 161 | CLOSED | 0 | 0 | 864.078 | 864.078
PJ0004239 Total | [7 empty] | 0 | 0 | 12441.4177 | 12441.4177
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT BASEBALL V. NORTHRIDGE - MAY 17-19 | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT BASEBALL V. RIVERSIDE - 5/4 | 160 | CLOSED | 0 | 0 | 114.966 | 114.966
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT BASEBALL V. UC DAVIS - 3/30 | 160 | CLOSED | 0 | 0 | 92.784 | 92.784
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | CU: SUPPORT FOR BASEBALL V. SEATTLE - 2/23 | 160 | CLOSED | 0 | 0 | 189.72 | 189.72
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. CSU BAKERSFIELD - MAY14 | 160 | CLOSED | 0 | 0 | 433.62 | 433.62
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. CSU FULLERTON - APR 19-21 | 160 | CLOSED | 0 | 0 | 1382.5616 | 1382.5616
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. CSU NORTHRIDGE - MAY 17-19 | 160 | CLOSED | 0 | 0 | 1388.256 | 1388.256
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. HAWAI'I - APR 12-14 | 160 | CLOSED | 0 | 0 | 1559.028 | 1559.028
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. HOLYCROSS- MAR 5-6 | 160 | CLOSED | 0 | 0 | 1054.146 | 1054.146
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. NOTRE DAME - MAR 13-16 | 160 | CLOSED | 0 | 0 | 1668.582 | 1668.582
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. PEPPERDINE - MAR 26 | 160 | CLOSED | 0 | 0 | 383.97 | 383.97
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. SAN JOSE STATE - MAR 12 | 160 | CLOSED | 0 | 0 | 455.592 | 455.592
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. SANTA CLARA - APR 16 | 160 | CLOSED | 0 | 0 | 409.122 | 409.122
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. SEATTLE: 2/22-2/24 | 160 | CLOSED | 0 | 0 | 1417.755 | 1417.755
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. UC DAVIS - MAR 28-30 | 160 | CLOSED | 0 | 0 | 1349.088 | 1349.088
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. UC RIVERSIDE - MAY 3-7 | 160 | CLOSED | 0 | 0 | 1555.4257 | 1555.4257
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT BASEBALL V. UCSB - MAR 22 & 24 | 160 | CLOSED | 0 | 0 | 914.754 | 914.754
PJ0004238 | 12/13: SUPPORT FOR BASEBALL | POPHAM, DONALD J. | CLOSED | 2012-07-17 | LA: SUPPORT FOR ALUMNI BASEBALL GAME - 2/9 | 160 | CLOSED | 0 | 0 | 162.35 | 162.35
PJ0004238 Total | [7 empty] | 0 | 0 | 14630.1082 | 14630.1082
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: SUPPORT FOR VOLLEYBALL V. IDAHO - 8/30 | 042 | CLOSED | 0 | 0 | 821.07 | 821.07
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: SUPPORT VOLLEYBALL V. CSU LONG BEACH - 11/24 | 042 | CLOSED | 0 | 0 | 821.07 | 821.07
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: SUPPORT VOLLEYBALL V. PACIFIC - 11/10/2012 | 042 | CLOSED | 0 | 0 | 1131.252 | 1131.252
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: SUPPORT VOLLEYBALL V. UC DAVIS - 11/9 | 042 | CLOSED | 0 | 0 | 437.904 | 437.904
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: SUPPORT VOLLEYBALL V. UC IRVINE - 11/23 | 042 | CLOSED | 0 | 0 | 821.07 | 821.07
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: VOLLEYBALL V. CSU FULLERTON - OCT 20 | 042 | CLOSED | 0 | 0 | 733.302 | 733.302
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: VOLLEYBALL V. CSU NORTHRIDGE - 10/6 | 042 | CLOSED | 0 | 0 | 656.856 | 656.856
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: VOLLEYBALL V. HAWAII - SEPT 5 | 042 | CLOSED | 0 | 0 | 711.36 | 711.36
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: VOLLEYBALL V. RIVERSIDE - OCT 19 | 042 | CLOSED | 0 | 0 | 675.792 | 675.792
PJ0004237 | 12/13: SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2012-07-02 | CU: VOLLEYBALL V. UCSB - 9/29 | 042 | CLOSED | 0 | 0 | 857.562 | 857.562
PJ0004237 Total | [7 empty] | 0 | 0 | 7667.238 | 7667.238
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR W. SOCCER V. USC - 8/11 | GENERAL | CLOSED | 0 | 0 | 1003.53 | 1003.53
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR W. SOCCER V. WESTMONT - AUG 9 | GENERAL | CLOSED | 0 | 0 | 720.717 | 720.717
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR WOMEN'S SOCCER V. CAL - 8/31 | GENERAL | CLOSED | 0 | 0 | 1021.776 | 1021.776
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT W. SOCCER V. CSU BASKERSFIELD - 8/19 | GENERAL | CLOSED | 0 | 0 | 729.84 | 729.84
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT W. SOCCER V. HAWAII - OCT 14 | GENERAL | CLOSED | 0 | 0 | 981.354 | 981.354
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT W. SOCCER V. PACIFIC - SEPT 28 | GENERAL | CLOSED | 0 | 0 | 921.423 | 921.423
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: W. SOCCER V. OREGON ST. - SEPT 9 | GENERAL | CLOSED | 0 | 0 | 894.054 | 894.054
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: W. SOCCER V. UC DAVIS - 9/30 | GENERAL | CLOSED | 0 | 0 | 985.284 | 985.284
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: W. SOCCER V. UCSB - 10/28 | GENERAL | CLOSED | 0 | 0 | 963.108 | 963.108
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: WOMEN'S SOCCER V. ST. MARY'S - 9/7 | GENERAL | CLOSED | 0 | 0 | 729.84 | 729.84
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: LINING OF PRACTICE FIELDS FOR WOMEN'S SOCCER | GENERAL | CLOSED | 0 | 0 | 896.172 | 896.172
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. CAL, - AUG 31 | GENERAL | CLOSED | 0 | 0 | 453.27 | 453.27
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. CSU BAKERSFIELD - AUG 19 | GENERAL | CLOSED | 0 | 0 | 323.616 | 323.616
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. CSU NORTHRIDGE - OCT 12 | GENERAL | CLOSED | 0 | 0 | 644.508 | 644.508
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. OREGON ST. - SEPT 9 | GENERAL | CLOSED | 0 | 0 | 72.834 | 72.834
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. ST. MARYS - SEPT 7 | GENERAL | CLOSED | 0 | 0 | 523.92 | 523.92
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. U. OF HAWAII - OCT 14 | GENERAL | CLOSED | 0 | 0 | 135.918 | 135.918
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. UC DAVIS - SEPT 30 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. UCSB - OCT 28 | GENERAL | CLOSED | 0 | 0 | 272.748 | 272.748
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. UNIV. OF PACIFIC - SEPT 28 | GENERAL | CLOSED | 0 | 0 | 523.92 | 523.92
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. USC (EXHIBITION) - AUG 11 | GENERAL | CLOSED | 0 | 0 | 195.102 | 195.102
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR W. SOCCER V. WESTMONT (EXHIBITION) - AUG 9 | GENERAL | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT WM SOCCER V. CENT. CALIF. HEAT - 5/11 | GENERAL | CLOSED | 0 | 0 | 175.338 | 175.338
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT WMS SOCCER V. CSU MONTEREY BAY - 4/21 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004236 | 12/13: SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: W SOCCER V. SF COLLEGE/FOOTHILL COLLEGE - 4/28 | GENERAL | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0004236 Total | [7 empty] | 0 | 0 | 13557.912 | 13557.912
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: SUPPORT MEN'S SOCCER V. UCSB - 11/3 | 061 | CLOSED | 0 | 0 | 692.274 | 692.274
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CP: SUPPORT M. SOCCER V. UCSB - NOV 3 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: M. SOCCER V. ARMY - SEPT 16 | 061 | CLOSED | 0 | 0 | 967.038 | 967.038
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: M. SOCCER V. HARVARD - 9.21 | 061 | CLOSED | 0 | 0 | 1012.653 | 1012.653
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: M. SOCCER V. SACRAMENTO STATE - OCT 12 | 061 | CLOSED | 0 | 0 | 1003.53 | 1003.53
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: M. SOCCER V. UCLA - 9/23 | 061 | CLOSED | 0 | 0 | 1459.68 | 1459.68
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: M. SOCCER V. VALPARAISO - SEPT 9 | 061 | CLOSED | 0 | 0 | 784.578 | 784.578
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: MEN'S SOCCER V. SACRAMENTO ST. - OCT 27 | 061 | CLOSED | 0 | 0 | 2353.734 | 2353.734
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR M. SOCCER V. UCSB - NOV 3 | 061 | CLOSED | 0 | 0 | 2878.938 | 2878.938
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR MEN'S SOCCER EXHIBITION - 4/20 | 061 | CLOSED | 0 | 0 | 1304.718 | 1304.718
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR SOCCER ON 4/21 | 061 | CLOSED | 0 | 0 | 1761.486 | 1761.486
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT M. SOCCER V. SANFRANCISCO - 8/11 | 061 | CLOSED | 0 | 0 | 948.792 | 948.792
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT M. SOCCER V. TEMPLE - SEPT 14 | 061 | CLOSED | 0 | 0 | 1806.354 | 1806.354
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT MEN'S SOCCER V. UC DAVIS - OCT 16 | 061 | CLOSED | 0 | 0 | 866.685 | 866.685
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT MEN'S SOCCER V. UC IRVINE - OCT 7 | 061 | CLOSED | 0 | 0 | 1125.474 | 1125.474
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: CALLBACK FOR SCOREBOARD ISSUE - SEPT 21 | 061 | CLOSED | 0 | 0 | 229.608 | 229.608
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: SUPPRT M. SOCCER V. UCSB - NOV 3 | 061 | CLOSED | 0 | 0 | 337.608 | 337.608
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: MEN'S SOCCER V. CSU NORTHRIDGE - OCT 5 | 061 | CLOSED | 0 | 0 | 1094.76 | 1094.76
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: STRIPING LOWER FIELDS FOR SOCCER - APR 26 | 061 | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOR MEN'S SOCCER V CSU MONTEREY BAY/BIOLA- 4/6 | 061 | CLOSED | 0 | 0 | 264.246 | 264.246
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V FRESNO PACIFIC/VENTURA FUSION-4/13 | 061 | CLOSED | 0 | 0 | 175.338 | 175.338
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. ARMY - 9/16 | 061 | CLOSED | 0 | 0 | 204.114 | 204.114
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. AZUZA PACIFIC - MAR 2 | 061 | CLOSED | 0 | 0 | 378.252 | 378.252
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. CSU NORTHRIDGE - 10/5 | 061 | CLOSED | 0 | 0 | 646.824 | 646.824
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. HARVARD - 9/21 | 061 | CLOSED | 0 | 0 | 675.48 | 675.48
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. SACRAMENTO ST. - 10/27 | 061 | CLOSED | 0 | 0 | 552.696 | 552.696
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. TEMPLE UNIV. - 9/14 | 061 | CLOSED | 0 | 0 | 489.516 | 489.516
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. UC DAVIS - 10/16 | 061 | CLOSED | 0 | 0 | 559.308 | 559.308
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. UC IRVINE - 10/7 | 061 | CLOSED | 0 | 0 | 246.96 | 246.96
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. UCLA - 9/23 | 061 | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. UCSB - 11/3 | 061 | CLOSED | 0 | 0 | 888.048 | 888.048
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. UNIV. OF SAN FRANCISCO-8/11 | 061 | CLOSED | 0 | 0 | 370.44 | 370.44
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MEN'S SOCCER V. VALPARAISO UNIV - 9/9 | 061 | CLOSED | 0 | 0 | 131.28 | 131.28
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT MNS SOCCER V. STANFORD - 4/20 | 061 | CLOSED | 0 | 0 | 202.602 | 202.602
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA:LINING FOR MEN'S SOCCER PRACTICES. (7/1/2012 - 12/31/2012) | 061 | CLOSED | 0 | 0 | 993.582 | 993.582
PJ0004235 | 12/13: SUPPORT FOR MEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2012-07-13 | PL: SUPPORT M. SOCCER V. UCSB - NOV 3 | 061 | CLOSED | 0 | 0 | 254.31 | 254.31
PJ0004235 Total | [7 empty] | 0 | 0 | 28397.946 | 28397.946
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | AD: ELEVATOR SUPPORT FOR FOOTBALL GAME - 10/20 | 061 | CLOSED | 0 | 0 | 2040.7 | 2040.7
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | AD: ELEVATOR SUPPORT FOR FOOTBALL GAME - NOV 3 | 061 | CLOSED | 0 | 0 | 1530.53 | 1530.53
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | AD: ELEVATOR SUPPORT FOR SEPT 22 FOOTBALL GAME-9/22 | 061 | CLOSED | 0 | 0 | 2040.7 | 2040.7
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | AD: OTIS ELEVATOR SUPPORT FOR SEPT 1 FOOTBALL GAME | GENERAL | CLOSED | 0 | 0 | 2040.7 | 2040.7
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | AD: RENTAL CABLE RAMP FOR FOOTBALL GAMES | 061 | CLOSED | 0 | 0 | 975.4441 | 975.4441
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: INSTALL HANDRAIL AROUND CAMERA RISER - SPANOS STADIUM | 061D | CLOSED | 0 | 0 | 164.856 | 164.856
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: SUPPORT FOR FOOTBALL V. CSU SAN DIEGO - SEPT 1 | 061 | CLOSED | 902.208 | 0 | 592.074 | 592.074
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: SUPPORT FOR FOOTBALL V. IDAHO ST. - NOV. 10 | 061 | CLOSED | 0 | 0 | 576.813 | 576.813
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: SUPPORT FOR FOOTBALL V. N. COLORADO - OCT 13 | 061 | CLOSED | 0 | 0 | 504.738 | 504.738
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: SUPPORT FOR FOOTBALL V. PORTLAND ST. - OCT 20 | 061 | CLOSED | 0 | 0 | 758.484 | 758.484
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CA: SUPPORT FOR FOOTBALL V. UC DAVIS - SEPT 22 | 061 | CLOSED | 0 | 0 | 507.918 | 507.918
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: FOOTBALL V. N. COLORADO - OCT 13 | 061 | CLOSED | 0 | 0 | 3696.312 | 3696.312
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: FOOTBALL V. PORTLAND ST. - OCT 20 | 061 | CLOSED | 0 | 0 | 3457.5 | 3457.5
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: FOOTBALL V. UC DAVIS | 061 | CLOSED | 0 | 0 | 3922.89 | 3922.89
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOOTBALL V. UCSD - 9/1/2012 | 061 | CLOSED | 0 | 0 | 3144.04 | 3144.04
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR FOOTBALL SCRIMMAGE - 5/4 | 061 | CLOSED | 0 | 0 | 721.908 | 721.908
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | CU: SUPPORT FOR FOOTBALL V. IDAHO ST. - 11/10 | 061 | CLOSED | 0 | 0 | 4072.086 | 4072.086
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: INSTALL SPIDER BOX FOR O'NEILL BBQ - NOV. 10 BEFORE 12:00PM | 003 | CLOSED | 0 | 0 | 225.072 | 225.072
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: INSTALL SPIDER BOX FOR O'NEILL BBQ - OCT 13 BEFORE 12:00PM | 003 | CLOSED | 0 | 0 | 502.344 | 502.344
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: INSTALL SPIDER BOX FOR O'NEILL BBQ - OCT 20 BEFORE 12:00PM | 003 | CLOSED | 0 | 0 | 371.316 | 371.316
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: INSTALL SPIDER BOX FOR O'NEILL BBQ - SEPT 1 BEFORE 12:00PM | 003 | CLOSED | 0 | 0 | 139.74 | 139.74
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: INSTALL SPIDER BOX FOR O'NEILL BBQ - SEPT 22 BEFORE 12:00PM | 003 | CLOSED | 0 | 0 | 227.676 | 227.676
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: SUPPORT FOR FOOTBALL V. CSU SAN DIEGO - SEPT 1 | 061 | CLOSED | 0 | 0 | 712.6704 | 712.6704
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: SUPPORT FOR FOOTBALL V. IDAHO ST. - NOV 10 | 061D | CLOSED | 0 | 0 | 1096.644 | 1096.644
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: SUPPORT FOR FOOTBALL V. N. COLORADO - OCT 13 | 061 | CLOSED | 0 | 0 | 1470.9479 | 1470.9479
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: SUPPORT FOR FOOTBALL V. PORTLAND ST. - OCT 20 | 061 | CLOSED | 0 | 0 | 547.464 | 547.464
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | EL: SUPPORT FOR FOOTBALL V. UC DAVIS - SEPT 22 | 061 | CLOSED | 0 | 0 | 2122.1621 | 2122.1621
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | ES: SUPPORT FOR FOOTBALL V. CSU SAN DIEGO - SEPT 1 | 061 | CLOSED | 312.18 | 0 | 347.4 | 347.4
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | ES: SUPPORT FOR FOOTBALL V. IDAHO ST. - NOV 10 | 061 | CLOSED | 0 | 0 | 382.14 | 382.14
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | ES: SUPPORT FOR FOOTBALL V. N. COLORADO - OCT 13 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | ES: SUPPORT FOR FOOTBALL V. PORTLAND ST. - OCT 20 | 061 | CLOSED | 0 | 0 | 412.128 | 412.128
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | ES: SUPPORT FOR FOOTBALL V. UC DAVIS - SEPT 22 | 061 | CLOSED | 0 | 0 | 382.14 | 382.14
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | GR: LINING FOR FOOTBALL PRACTICES | 061 | CLOSED | 0 | 0 | 2297.76 | 2297.76
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | GR: SUPPORT FOOTBALL V. IDAHO ST. - NOV 10 | 061 | CLOSED | 0 | 0 | 7103.322 | 7103.322
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | GR: SUPPORT FOOTBALL V. NORTHERN COLORADO - 10/13 | 061 | CLOSED | 0 | 0 | 6311.694 | 6311.694
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | GR: SUPPORT FOOTBALL V. PORTLAND ST - OCT 20 (HOMECOMING) | 061 | CLOSED | 0 | 0 | 5776.35 | 5776.35
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | GR: SUPPORT FOR FOOTBALL V. CSU SAN DIEGO - SEPT 1 | 061 | CLOSED | 0 | 0 | 9440.706 | 9440.706
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | GR: SUPPORT FOR FOOTBALL V. UC DAVIS - 9/22 | 061 | CLOSED | 0 | 0 | 8460.24 | 8460.24
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: LINING FOR BAND PRACTICES ON TRACK FIELD | GENERAL | CLOSED | 0 | 0 | 935.136 | 935.136
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | LA: SUPPORT FOOTBALL SPRING GAME - 5/3 | 061 | CLOSED | 0 | 0 | 447.5783 | 447.5783
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | PL: SUPPORT FOR FOOTBALL V. CSU SAN DIEGO - SEPT 1 | 061 | CLOSED | 0 | 0 | 421.224 | 421.224
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | PL: SUPPORT FOR FOOTBALL V. IDAHO ST. - NOV. 10 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | PL: SUPPORT FOR FOOTBALL V. N. COLORADO - OCT 13 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | PL: SUPPORT FOR FOOTBALL V. PORTLAND ST. - OCT 20 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | PL: SUPPORT FOR FOOTBALL V. UC DAVIS - SEPT 22 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: FOOTBALL V. IDAHO ST. - NOV 10 | 061 | CLOSED | 0 | 0 | 399.534 | 399.534
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: FOOTBALL V. NORTH. COLORADO - OCT 13 | 061 | CLOSED | 0 | 0 | 423.036 | 423.036
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: FOOTBALL V. NORTH. COLORADO - OCT 13 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: FOOTBALL V. PORTLAND ST. - OCT 20 | 061 | CLOSED | 0 | 0 | 423.036 | 423.036
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: SUPPORT FOR FOOTBALL V. N. DAKOTA - SEPT 29 | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: SUPPORT FOR FOOTBALL V. UC DAVIS - 9/22 | 061 | CLOSED | 0 | 0 | 188.016 | 188.016
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | RE: SUPPORT FOR FOOTBALL V. UCSD - 9/1 | 061 | CLOSED | 0 | 0 | 399.534 | 399.534
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | SUPPLY RENTAL:SUPPLY RENTAL FOR FOOTBALL V. CSUSD - 9/1 | 061 | CLOSED | 0 | 0 | 55 | 55
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | SUPPLY RENTAL:SUPPLY RENTAL FOR FOOTBALL V. N. COLORADO-10/13 | 061 | CLOSED | 0 | 0 | 55 | 55
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | SUPPLY RENTAL:SUPPLY RENTAL FOR FOOTBALL V. PORTLAND-10/20 | 061 | CLOSED | 0 | 0 | 55 | 55
PJ0004234 | 12/13 SUPPORT FOR FOOTBALL | POPHAM, DONALD J. | CLOSED | 2012-07-13 | SUPPLY RENTAL:SUPPLY RENTAL FOR FOOTBALL V. UC DAVIS - 9/22 | 061 | CLOSED | 0 | 0 | 55 | 55
PJ0004234 Total | [7 empty] | 1214.388 | 0 | 84444.6638 | 84444.6638
PJ0004233 | M&R ASI 12/13:REPLACE FLOORING - UU 065-220 | MOLLAN, CHERYL L. | CLOSED | 2012-07-17 | AD: FLOOR CONNECTION | 065 | CLOSED | 16397.1615 | 0 | 16397.1615 | 16397.1615
PJ0004233 | M&R ASI 12/13:REPLACE FLOORING - UU 065-220 | MOLLAN, CHERYL L. | CLOSED | 2012-07-17 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1257.73 | 0 | 0 | 0
PJ0004233 | M&R ASI 12/13:REPLACE FLOORING - UU 065-220 | MOLLAN, CHERYL L. | CLOSED | 2012-07-17 | EH&S: M&R UU 12/13:REPLACE FLOORING - UU 065-220 | 065 | CLOSED | 394.8 | 0 | 95.34 | 95.34
PJ0004233 | M&R ASI 12/13:REPLACE FLOORING - UU 065-220 | MOLLAN, CHERYL L. | CLOSED | 2012-07-17 | IN: M&R UU 12/13:REPLACE FLOORING - UU 065-220 | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004233 Total | [7 empty] | 18177.8035 | 0 | 16620.6135 | 16620.6135
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | AD: (SR FUNDING) PARC ENVIRONMENTAL | 005 | CLOSED | 2270 | 0 | 2270 | 2270
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | AD: MCKENNA ENVIRONMENTAL | 005 | CLOSED | 2856.9 | 0 | 1947.4 | 1947.4
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | CA: CUT DOOR OPENING TO WALL - BLDG 005 ROOM 311/313 | 005 | CLOSED | 2285.856 | 0 | 2285.844 | 2285.844
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 429.09 | 0 | 0 | 0
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | EL: DISCONNECT AND RECONNECT POWER - BLDG 005-311/313 | 005 | CLOSED | 1320.0036 | 0 | 1580.316 | 1580.316
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | IN: INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | 005 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | LO: ORDER AND INSTALL MORTISE LOCKSET FOR NEW DOOR - BLDG 05-311 | 005 | CLOSED | 774.132 | 0 | 759.486 | 759.486
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | MO: REMOVE ONE LARGE CREDENSA AND FURNITURE FROM WALL - BLDG 005 | 005 | CLOSED | 162 | 0 | 120.72 | 120.72
PJ0004227 | INSTALL NEW DOOR BETWEEN 311 & 313, & PAINT - BLD 005 | GALVEZ, CESAR | CLOSED | 2012-07-13 | PA: PATCH & PAINT BOTH SIDES OF WALL TOUCHING ROOM 311 & 313 | 005 | CLOSED | 312.738 | 0 | 312.738 | 312.738
PJ0004227 Total | [7 empty] | 10538.8316 | 0 | 9404.616 | 9404.616
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | AD: ASAP REPROGRAPHICS | 065 | CLOSED | 0 | 0 | 113.62 | 113.62
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | AD: CAL POLY BUILDING PERMIT FEES | 065 | CLOSED | 1782.3 | 0 | 1782.3 | 1782.3
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | AD: CAL POLY PLAN REVIEW FEES | 065 | CLOSED | 1586.25 | 0 | 1586.25 | 1586.25
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | AD: ENGLEKIRK AND SABOL - SEISMIC PEER REVIEW (NO OVERHEAD) | 065 | CLOSED | 500 | 0 | 500 | 500
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | AD: FIRE WATCH (PERFORMED BY UPD STUDENT ASSISTANT ON 3/6/13) | 065 | CLOSED | 64.2 | 0 | 52.97 | 52.97
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | AD: PROJECT COORDINATION FEES (4% OF CONSTRUCTION COSTS) | 065 | CLOSED | 9005.12 | 0 | 8416 | 8416
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | CA:PROVIDE CONSTRUCTION SUPPORT FOR YC PROJECT AT UU | 065 | CLOSED | 225.552 | 0 | 366.522 | 366.522
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1712.77 | 0 | 0 | 0
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | EH&S: YOGURT CREATIONS TENNANT IMPROVMENTS (N/L) | 065 | CLOSED | 514.8 | 0 | 369.6 | 369.6
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | EL:PROVIDE CONSTRUCTION SUPPORT FOR YC PROJECT AT UU | 065 | CLOSED | 1047.6442 | 0 | 3915.828 | 3915.828
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | ES:PROVIDE CONSTRUCTION SUPPORT FOR YC PROJECT AT UU | 065 | CLOSED | 979.1194 | 0 | 312.18 | 312.18
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | IN: OVERSIGHT FOR YOGURT CREATIONS TI - UU 65 RM 112 (MAINT) | 065 | CLOSED | 0 | 0 | 2946.576 | 2946.576
PJ0004226 | PROJECT COORDINATION FOR YOGURT CREATIONS TI - UU 65 RM 112 | MOLLAN, CHERYL L. | CLOSED | 2012-07-11 | PL:PROVIDE CONSTRUCTION SUPPORT FOR YC PROJECT AT UU | 065 | CLOSED | 1018.4179 | 0 | 326.46 | 326.46
PJ0004226 Total | [7 empty] | 18436.1734 | 0 | 20688.306 | 20688.306
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR 9/29 SPANOS THEATRE EVENT | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR ALICE PERFORMANCE - APR 6 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR CHARLES PHOENIX EVENT - 4/21 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR DREW MATINEE - APRIL 7 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR FROG AND TOAD PERFORMANCES - MAR1-9 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR GODS EAR PERFORMANCE - 11/8-11/10 | 044 | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR JUMPBRUSH - 8/7 | 044 | CLOSED | 0 | 0 | 114.786 | 114.786
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR PACIFIC QUARTET EVENT - OCT 14 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR SOAR | 044 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR SPANOS EVENT ON SEPT 15 | 044 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR SPANOS THEATER EVENT - 8/15-8/18 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT FOR UPWARD BOUND EVENT - JULY 28 | 044 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0004223 | 12/13 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-BLD 44(NO EST) | POPHAM, DONALD J. | CLOSED | 2012-07-09 | CU: SUPPORT PEOPLE TO PEOPLE PERFORMANCE - 10/14 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004223 Total | [7 empty] | 0 | 0 | 836.298 | 836.298
PJ0004222 | M&R PARK 12/13: MISC LOT WORK TO INCLUDE TREE TRIMMING -GEN PARK | MEAD, GEORGE | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 433.61 | 0 | 0 | 0
PJ0004222 | M&R PARK 12/13: MISC LOT WORK TO INCLUDE TREE TRIMMING -GEN PARK | MEAD, GEORGE | CLOSED | 2012-07-02 | LA: MISC. LOT WORK TO INCLUDE TREE TRIMMING FOR FISCAL 12/13 | GEN-PARK | CLOSED | 4335.9139 | 0 | 3736.008 | 3736.008
PJ0004222 Total | [7 empty] | 4769.5239 | 0 | 3736.008 | 3736.008
PJ0004221 | M&R PARK 12/13: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | GALVEZ, CESAR | CLOSED | 2012-07-02 | AD: COASTAL ROLLOFF | P-R01 | CLOSED | 1080.0045 | 0 | 1080.0045 | 1080.0045
PJ0004221 | M&R PARK 12/13: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | GALVEZ, CESAR | CLOSED | 2012-07-02 | AD: JOC 12.024.029 STAPLES | P-R01 | CLOSED | 20330 | 0 | 18134.9164 | 18134.9164
PJ0004221 | M&R PARK 12/13: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | GALVEZ, CESAR | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 1924.23 | 0 | 0 | 0
PJ0004221 | M&R PARK 12/13: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | GALVEZ, CESAR | CLOSED | 2012-07-02 | EO: EXCAVATE/DEMO ASPHALT, FILL AND COMPACT NEW BASE - R01 LOT | P-R01 | CLOSED | 11322.24 | 0 | 3368.208 | 3368.208
PJ0004221 | M&R PARK 12/13: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | GALVEZ, CESAR | CLOSED | 2012-07-02 | IN: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | P-R01 | CLOSED | 192.168 | 0 | 192.168 | 192.168
PJ0004221 | M&R PARK 12/13: RESTRIPE, REPAIR ROOT DAMAGE - RESIDENCES R-01 | GALVEZ, CESAR | CLOSED | 2012-07-02 | LA:SAW CUT TREE ROOTS GREATER THAN 2" DIAMETER-R01 LOT (N/L) | P-R01 | CLOSED | 311.712 | 0 | 0 | 0
PJ0004221 Total | [7 empty] | 35160.3545 | 0 | 22775.2969 | 22775.2969
PJ0004220 | M&R PARK 12/13: SEAL COAT & RESTRIPE - NORTH OF OH 48 | GALVEZ, CESAR | CLOSED | 2012-07-02 | AD: GOLDEN STATE STRIPING | GEN-PARK | CLOSED | 2082.113 | 0 | 2079.3738 | 2079.3738
PJ0004220 | M&R PARK 12/13: SEAL COAT & RESTRIPE - NORTH OF OH 48 | GALVEZ, CESAR | CLOSED | 2012-07-02 | CA: INSTALL ACCESSIBLE PARKING SIGN AND POST ON PLANTER | 048 | CLOSED | 490.9266 | 0 | 290.352 | 290.352
PJ0004220 | M&R PARK 12/13: SEAL COAT & RESTRIPE - NORTH OF OH 48 | GALVEZ, CESAR | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 270.12 | 0 | 0 | 0
PJ0004220 | M&R PARK 12/13: SEAL COAT & RESTRIPE - NORTH OF OH 48 | GALVEZ, CESAR | CLOSED | 2012-07-02 | IN: M&R PARK 12/13: SEAL COAT & RESTRIPE - NORTH OF OH 48 | GEN-PARK | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004220 Total | [7 empty] | 2971.2716 | 0 | 2497.8378 | 2497.8378
PJ0004219 | M&R PARK 12/13: RESTRIPE - GROUNDS H-4C | GALVEZ, CESAR | CLOSED | 2012-07-02 | AD: GOLDEN STATE SEALING AND STRIPING, INC. | P-H04 | CLOSED | 765.05 | 0 | 764.729 | 764.729
PJ0004219 | M&R PARK 12/13: RESTRIPE - GROUNDS H-4C | GALVEZ, CESAR | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 82.91 | 0 | 0 | 0
PJ0004219 | M&R PARK 12/13: RESTRIPE - GROUNDS H-4C | GALVEZ, CESAR | CLOSED | 2012-07-02 | IN: M&R PARK 12/13: RESTRIPE - GROUNDS H-4C (N/L) | P-H04 | CLOSED | 64.056 | 0 | 0 | 0
PJ0004219 Total | [7 empty] | 912.016 | 0 | 764.729 | 764.729
PJ0004216 | M&R PARK 12/13: RESTRIPE - DAIRY PARKING | GALVEZ, CESAR | CLOSED | 2012-07-02 | AD: GOLDEN STATE STRIPING | GEN-PARK | CLOSED | 1261.4337 | 0 | 1260.7703 | 1260.7703
PJ0004216 | M&R PARK 12/13: RESTRIPE - DAIRY PARKING | GALVEZ, CESAR | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 138.95 | 0 | 0 | 0
PJ0004216 | M&R PARK 12/13: RESTRIPE - DAIRY PARKING | GALVEZ, CESAR | CLOSED | 2012-07-02 | IN: M&R PARK 12/13: RESTRIPE - DAIRY PARKING | GEN-PARK | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004216 Total | [7 empty] | 1528.4957 | 0 | 1388.8823 | 1388.8823
PJ0004214 | M&R PARK 12/13: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | JUDD, PERRY | CLOSED | 2012-07-02 | AD: QUINN POWER SYSTEMS | GEN-PARK | CLOSED | 28315.2602 | 0 | 28079.9137 | 28079.9137
PJ0004214 | M&R PARK 12/13: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | JUDD, PERRY | CLOSED | 2012-07-02 | CA: INSTALL CONCRETE PAD FOR GENERATOR - PARKING STRUCTURE 130 | GEN-PARK | CLOSED | 3409.8299 | 0 | 3204.582 | 3204.582
PJ0004214 | M&R PARK 12/13: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | JUDD, PERRY | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 0 | 0 | 0 | 0
PJ0004214 | M&R PARK 12/13: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | JUDD, PERRY | CLOSED | 2012-07-02 | EL: INSTALL GENERATOR TO REPLACE BATTERY BACKUP SYSTEM - 130 | GEN-PARK | CLOSED | 11402.0465 | 0 | 11527.1875 | 11527.1875
PJ0004214 | M&R PARK 12/13: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | JUDD, PERRY | CLOSED | 2012-07-02 | EO: PREPARE PAD FOR CONCRETE FOUNDATION FOR GENERATOR - 130 | GEN-PARK | CLOSED | 2214.9956 | 0 | 3481.992 | 3481.992
PJ0004214 | M&R PARK 12/13: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | JUDD, PERRY | CLOSED | 2012-07-02 | IN: PARKING STRUCTURE EMERGENCY LIGHTING-130,271,371 | GEN-PARK | CLOSED | 1425.8866 | 0 | 64.056 | 64.056
PJ0004214 Total | [7 empty] | 46768.0188 | 0 | 46357.7312 | 46357.7312
PJ0004213 | M&R PARK 12/13: GRAND AVE PARKING STRUCTURE MAINTENANCE - 130 | PIPAL, GAIL | CLOSED | 2012-07-02 | CA: ROUTINE MAINTENANCE OF SEISMIC EXPANSION JOINT PLATES | 130 | CLOSED | 5117.8066 | 0 | 5996.958 | 5996.958
PJ0004213 | M&R PARK 12/13: GRAND AVE PARKING STRUCTURE MAINTENANCE - 130 | PIPAL, GAIL | CLOSED | 2012-07-02 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 635.23 | 0 | 0 | 0
PJ0004213 | M&R PARK 12/13: GRAND AVE PARKING STRUCTURE MAINTENANCE - 130 | PIPAL, GAIL | CLOSED | 2012-07-02 | IN: M&R PARK 12/13: GRAND AVE PARKING STRUCTURE MAINTENANCE -130 | 130 | CLOSED | 640.56 | 0 | 64.056 | 64.056
PJ0004213 Total | [7 empty] | 6393.5966 | 0 | 6061.014 | 6061.014
PJ0004209 | ENGINEERING STUDY FOR CHILLER REPLACEMENT ¿ COMP. SCI. 014 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: ENGLEKIRK AND SABOL | 014 | CLOSED | 2150.7 | 0 | 2150.7 | 2150.7
PJ0004209 | ENGINEERING STUDY FOR CHILLER REPLACEMENT ¿ COMP. SCI. 014 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: GOSS ENGINEERING | 014 | CLOSED | 55195.95 | 0 | 55195.95 | 55195.95
PJ0004209 | ENGINEERING STUDY FOR CHILLER REPLACEMENT ¿ COMP. SCI. 014 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: ONTRAC SHIPPING | 014 | CLOSED | 0 | 0 | 66.92 | 66.92
PJ0004209 | ENGINEERING STUDY FOR CHILLER REPLACEMENT ¿ COMP. SCI. 014 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 1997.54 | 0 | 0 | 0
PJ0004209 Total | [7 empty] | 59344.19 | 0 | 57413.57 | 57413.57
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: ASAP REPROGRAPHICS | 053 | CLOSED | 0 | 0 | 128.3 | 128.3
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: ENGLEKIRK AND SABOL | 053 | CLOSED | 898.88 | 0 | 895 | 895
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: GOSS ENGINEERING | 053 | CLOSED | 17905 | 0 | 17905 | 17905
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 0 | 0 | 0 | 0
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | EH&S: PROVIDE EXHAUST SYSTEM FOR CADAVER LAB - SCI NORTH (N/L) | 053 | CLOSED | 458 | 0 | 0 | 0
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | IN: SR 12/13: PROVIDE EXHAUST SYSTEM FOR CADAVER LAB - SCI NORTH | 053 | CLOSED | 427.04 | 0 | 587.18 | 587.18
PJ0004208 | SR 12/13: DESIGN, ONLY, FOR CADAVER LAB EXHAUST SYSTEM-SCI N. 53 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | LA:POT-HOLE, EXPOSURE LOWER FLOOR ROOF | 053 | CLOSED | 779.28 | 0 | 472.58 | 472.58
PJ0004208 Total | [7 empty] | 20468.2 | 0 | 19988.06 | 19988.06
PJ0004207 | SR 12/13: REPLACE VFDS - BLDS 6, 26, 186 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: UNJUSTIFED ¿ SIEMENS | GENERAL | CLOSED | 13325 | 0 | 13325 | 13325
PJ0004207 | SR 12/13: REPLACE VFDS - BLDS 6, 26, 186 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004207 | SR 12/13: REPLACE VFDS - BLDS 6, 26, 186 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | EL:REMOVE AND INSTALL POWER TO VFD'S | GENERAL | CLOSED | 6213.5 | 0 | 4906.87 | 4906.87
PJ0004207 | SR 12/13: REPLACE VFDS - BLDS 6, 26, 186 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | ES: ORDER AND INSTALL VFDS FOR BLDGS 6, 26, AND 186 | GENERAL | CLOSED | 14383.2453 | 0 | 16962.5168 | 16962.5168
PJ0004207 | SR 12/13: REPLACE VFDS - BLDS 6, 26, 186 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | IN: SR 12/13: VFD'S REPLACEMENTS - BLDS 6, 26, 186 | GENERAL | CLOSED | 1014.22 | 0 | 53.38 | 53.38
PJ0004207 Total | [7 empty] | 34935.9653 | 0 | 35247.7668 | 35247.7668
PJ0004206 | SR 12/13: REPLACE/REPAIR AIR HANDLER, 2 DRIVES & MOTOR -BUSINESS | MAY, TOM | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0004206 | SR 12/13: REPLACE/REPAIR AIR HANDLER, 2 DRIVES & MOTOR -BUSINESS | MAY, TOM | CLOSED | 2012-06-22 | EL: REPLACE AIR HANDLER MOTORS & DRIVES | 003 | CLOSED | 3900.5718 | 0 | 1544.09 | 1544.09
PJ0004206 | SR 12/13: REPLACE/REPAIR AIR HANDLER, 2 DRIVES & MOTOR -BUSINESS | MAY, TOM | CLOSED | 2012-06-22 | ES:REPLACE AIR HANDLER MOTOR & DRIVE - AHU-2 | 003 | CLOSED | 11815.8553 | 0 | 11654.5125 | 11654.5125
PJ0004206 | SR 12/13: REPLACE/REPAIR AIR HANDLER, 2 DRIVES & MOTOR -BUSINESS | MAY, TOM | CLOSED | 2012-06-22 | IN: REPLACE/REPAIR AIR HANDLER, 2 DRIVES & MOTOR -BUSINESS | 003 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0004206 Total | [7 empty] | 15823.1871 | 0 | 13305.3625 | 13305.3625
PJ0004205 | SR 12/13, M&R ASI12/13: REPAIR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-22 | AD: JOC 12.024.006 STAPLES | 162F | CLOSED | 235446.27 | 0 | 235446.27 | 235446.27
PJ0004205 | SR 12/13, M&R ASI12/13: REPAIR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 162F | CLOSED | 0 | 0 | 0 | 0
PJ0004205 Total | [7 empty] | 235446.27 | 0 | 235446.27 | 235446.27
PJ0004203 | SR 12/13: ARC FLASH -PROTECTIVE DEVICE CORRECTIONS - CAMPUS WIDE | JOHNSON, BEN | CLOSED | 2012-06-22 | AD: POWER ENGINEERING SERVICES | GENERAL | CLOSED | 47752.8 | 0 | 44000 | 44000
PJ0004203 | SR 12/13: ARC FLASH -PROTECTIVE DEVICE CORRECTIONS - CAMPUS WIDE | JOHNSON, BEN | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004203 | SR 12/13: ARC FLASH -PROTECTIVE DEVICE CORRECTIONS - CAMPUS WIDE | JOHNSON, BEN | CLOSED | 2012-06-22 | EL: ASSIST POWER ENGINEERING WITH ARC FLASH SURVEY -FISCAL 12/13 | GENERAL | CLOSED | 2247.2 | 0 | 402.77 | 402.77
PJ0004203 Total | [7 empty] | 50000 | 0 | 44402.77 | 44402.77
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: APC CONTRACTORS | 053 | CLOSED | 4250 | 0 | 3619.8 | 3619.8
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: ASAP REPROGRAPHICS (DIRECT PAY) | 053 | CLOSED | 0 | 0 | 44.71 | 44.71
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: DIVISION OF STATE ARCHITECT | 053 | CLOSED | 600 | 0 | 600 | 600
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: J.L. FASULO DRYWALL | 053 | CLOSED | 2500 | 0 | 1141 | 1141
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: OTIS ELEVATOR | 053 | CLOSED | 209512.11 | 0 | 245542.53 | 245542.53
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: PMSM ARCHITECTS | 053 | CLOSED | 24550 | 0 | 24550 | 24550
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: PSC ENVIRONMENTAL | 053 | CLOSED | 5334.85 | 0 | 5334.85 | 5334.85
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: SANTA MARIA ACOUSTICAL | 053 | CLOSED | 3854 | 0 | 2448.35 | 2448.35
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | AD: STATE FIRE MARSHAL FEES | 053 | CLOSED | 0 | 0 | 1850.8 | 1850.8
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | ANTS: PROGRAM ALARMS FOR ELEVATOR CONTROLS - BLDG. 53 | 053 | CLOSED | 800.8 | 0 | 50.05 | 50.05
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | CP: PROJECT CONTINGENCY | 053 | OPEN | 600 | 0 | 0 | 0
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 053 | CLOSED | 0 | 0 | 0 | 0
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | EL: ASSIST WITH ELEVATOR WORK AT SCI. N. BLDG. 053 | 053 | CLOSED | 4437.54 | 0 | 10560.67 | 10560.67
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | ES: PROJECT SUPPORT FOR ELEVATOR MODERNIZATION | 053 | CLOSED | 566.24 | 0 | 412.98 | 412.98
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | IN: SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | 053 | CLOSED | 992.3342 | 0 | 408.585 | 408.585
PJ0004202 | SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | GONZALES, ALBERT | CONST_COMP | 2012-06-22 | SM: SR 12/13: ELEVATOR MODERNIZATION - SCI NORTH 53 | 053 | OPEN | 0 | 0 | 0 | 0
PJ0004202 Total | [7 empty] | 257997.8742 | 0 | 296564.325 | 296564.325
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: ASAP REPROGRAPHICS (DIRECT PAY) | 082 | CLOSED | 311.04 | 0 | 311.04 | 311.04
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: DIVISION OF STATE ARCHITECT | 082 | CLOSED | 2200 | 0 | 880 | 880
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: ENGLEKIRK AND SABOL | 082 | CLOSED | 2000 | 0 | 2090 | 2090
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: JOC 13.029.006 MAINO | 082 | CLOSED | 512169.22 | 0 | 494123.9045 | 494123.9045
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: JOC 14.033.023 MAINO | 082 | CLOSED | 0 | 0 | 18078.83 | 18078.83
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: PMSM | 082 | CLOSED | 67372.13 | 0 | 59803.35 | 59803.35
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: STATE FIRE MARSHAL FEES | 082 | CLOSED | 390 | 0 | 3578.91 | 3578.91
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 1332.62 | 0 | 0 | 0
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIAL ONLY) | 082 | CLOSED | 0 | 0 | 97.5 | 97.5
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | EL: INSTALL METER & SUBPANEL AT CORP WHSE FOR DISTRIBUTION SVCS | 082 | CLOSED | 6423.6152 | 0 | 15778.825 | 15778.825
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | IN: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | 082 | CLOSED | 1067.6 | 0 | 1227.74 | 1227.74
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | ITS: DATA LINE INSTALLATION - DISTRIBUTION SVCS (TRACKING, ONLY) | 082 | CLOSED | 12064 | 0 | 12064 | 12064
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | LO: SUPPLY AND INSTALL LOCKS AND CLOSER | 082 | CLOSED | 4645.7395 | 0 | 3678.87 | 3678.87
PJ0004200 | SR 12/13: MODIFY CORP WHSE TO ACCEPT DISTRIBUTION SERV PROGRAM | LAMPMAN, GREG | CLOSED | 2012-06-22 | PA: PAINT NEW OFFICES AND RESTROOM | 082 | CLOSED | 6784.8801 | 0 | 5878.335 | 5878.335
PJ0004200 Total | [7 empty] | 616760.8448 | 0 | 617591.3045 | 617591.3045
PJ0004199 | SR 12/13: ROAD STRIPING AND SEALING - CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2012-06-22 | AD: GOLDEN STATE STRIPING | STREETS | CLOSED | 17028.22 | 0 | 17028.22 | 17028.22
PJ0004199 | SR 12/13: ROAD STRIPING AND SEALING - CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2012-06-22 | AD: JOC 12.024.031 STAPLES | STREETS | CLOSED | 14123.06 | 0 | 14123.06 | 14123.06
PJ0004199 | SR 12/13: ROAD STRIPING AND SEALING - CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2012-06-22 | CA: INSTALL VARIOUS SIGNS WITH POST THROUGHOUT CAMPUS | STREETS | CLOSED | 2176.53 | 0 | 2176.5322 | 2176.5322
PJ0004199 | SR 12/13: ROAD STRIPING AND SEALING - CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 0 | 0 | 0 | 0
PJ0004199 | SR 12/13: ROAD STRIPING AND SEALING - CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2012-06-22 | IN: SR 12/13: ROAD STRIPING AND SEALING - CAMPUS WIDE | STREETS | CLOSED | 160.14 | 0 | 160.14 | 160.14
PJ0004199 Total | [7 empty] | 33487.95 | 0 | 33487.9522 | 33487.9522
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: JOC 12.025.010 EVERLAST | U-UDOR | CLOSED | 113682.94 | 0 | 113682.93 | 113682.93
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | AD: PURCHASE SPACE HEATERS AND EXTENSION CORDS FOR OFFICES | U-UDOR | CLOSED | 0 | 0 | 295.82 | 295.82
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | CPE: SUPPORT FOR VALVE REPLACEMENT | U-UDOR | CLOSED | 10762.8179 | 0 | 12274.935 | 12274.935
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | ES: SUPPORT FOR VALVE REPLACEMENT | U-UDOR | CLOSED | 1438.1092 | 0 | 1433.76 | 1433.76
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | IN: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | U-UDOR | CLOSED | 1067.6 | 0 | 1014.22 | 1014.22
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | LA: SUPPORT FOR VALVE REPLACEMENT (N/L) | U-UDOR | CLOSED | 1945.2397 | 0 | 0 | 0
PJ0004195 | SR 12/13: REPLACE UTILIDOR VALVES - SO MT, KEN LIB, ENG 3, 4 &13 | BRENNAN, MICHAEL | CLOSED | 2012-06-22 | PL: SUPPORT FOR VALVE PROJECT | U-UDOR | CLOSED | 7527.3724 | 0 | 7051.0213 | 7051.0213
PJ0004195 Total | [7 empty] | 136424.0792 | 0 | 135752.6863 | 135752.6863
PJ0004194 | SR 12/13: RE-COAT DECK - ENG 13 | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: JOC 12.024.025 STAPLES | 013 | CLOSED | 88916.62 | 0 | 88916.62 | 88916.62
PJ0004194 | SR 12/13: RE-COAT DECK - ENG 13 | LAMPMAN, GREG | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 3000 | 0 | 0 | 0
PJ0004194 | SR 12/13: RE-COAT DECK - ENG 13 | LAMPMAN, GREG | CLOSED | 2012-06-22 | EL DISCONNECT POWER AND RE-CONNECT TO TWO CONDENCERS | 013 | CLOSED | 1350.5668 | 0 | 287.9 | 287.9
PJ0004194 | SR 12/13: RE-COAT DECK - ENG 13 | LAMPMAN, GREG | CLOSED | 2012-06-22 | ES: DISCONNECT AND RE-CONECT 2 CONDENSERS | 013 | CLOSED | 1258.1878 | 0 | 841.11 | 841.11
PJ0004194 | SR 12/13: RE-COAT DECK - ENG 13 | LAMPMAN, GREG | CLOSED | 2012-06-22 | IN: SR 12/13: RE-COAT DECK - ENG 13 | 013 | CLOSED | 533.8 | 0 | 266.9 | 266.9
PJ0004194 Total | [7 empty] | 95059.1746 | 0 | 90312.53 | 90312.53
PJ0004192 | SR 12/13: DESIGN, ONLY - CORP YARD FENCING | LAMPMAN, GREG | CLOSED | 2012-06-22 | AD: NORTH COAST ENGINEERING | GENERAL | CLOSED | 13200 | 0 | 6658 | 6658
PJ0004192 | SR 12/13: DESIGN, ONLY - CORP YARD FENCING | LAMPMAN, GREG | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004192 | SR 12/13: DESIGN, ONLY - CORP YARD FENCING | LAMPMAN, GREG | CLOSED | 2012-06-22 | IN: SR 12/13: INSTALL CORP YARD FENCING | GENERAL | CLOSED | 2135.2 | 0 | 53.38 | 53.38
PJ0004192 Total | [7 empty] | 15335.2 | 0 | 6711.38 | 6711.38
PJ0004191 | SR 12/13: REPAIR/REPLACE RAIN GUTTERS AND DOWNSPOUTS - BLD 55 | JUDD, PERRY | CLOSED | 2012-06-22 | AD: FIVE STAR RAIN GUTTERS | 055 | CLOSED | 6720 | 0 | 6720 | 6720
PJ0004191 | SR 12/13: REPAIR/REPLACE RAIN GUTTERS AND DOWNSPOUTS - BLD 55 | JUDD, PERRY | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 055 | CLOSED | 0 | 0 | 0 | 0
PJ0004191 | SR 12/13: REPAIR/REPLACE RAIN GUTTERS AND DOWNSPOUTS - BLD 55 | JUDD, PERRY | CLOSED | 2012-06-22 | EO: TRENCHING FOR RAIN GUTTERS AT BCEC - 055 | 055 | CLOSED | 663.52 | 0 | 697.93 | 697.93
PJ0004191 | SR 12/13: REPAIR/REPLACE RAIN GUTTERS AND DOWNSPOUTS - BLD 55 | JUDD, PERRY | CLOSED | 2012-06-22 | PL: INSTALL PIPING AT FOR GUTTERS AT BCEC - 055 | 055 | CLOSED | 2305.84 | 0 | 628.775 | 628.775
PJ0004191 Total | [7 empty] | 9689.36 | 0 | 8046.705 | 8046.705
PJ0004190 | SR 12/13: INSTALL CONCRETE SLAB/PAVERS BEHIND MOTT GYM | JUDD, PERRY | CLOSED | 2012-06-22 | AD: JOC 12.024.016.00 STAPLES (PARTIAL) | 042 | CLOSED | 8994 | 0 | 8994 | 8994
PJ0004190 | SR 12/13: INSTALL CONCRETE SLAB/PAVERS BEHIND MOTT GYM | JUDD, PERRY | CLOSED | 2012-06-22 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004190 Total | [7 empty] | 8994 | 0 | 8994 | 8994
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | AD: EARTH SYSTEMS | GEN-PARK | CLOSED | 6232.34 | 0 | 3374.39 | 3374.39
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | AD: JOC 12.024.005.00 & .01 STAPLES | GEN-PARK | CLOSED | 576017.5 | 0 | 567453.54 | 567453.54
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | AD: TOWN AND COUNTRY FENCING | GEN-PARK | CLOSED | 4879 | 0 | 4879.14 | 4879.14
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | AD: UNJUSTIFIED - JOC 12.024.005.02 STAPLES (FP FUNDING - NO OH) | GEN-PARK | CLOSED | 53959.92 | 0 | 62523.72 | 62523.72
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | AD: WALLACE GROUP | GEN-PARK | CLOSED | 1470.24 | 0 | 1495.9 | 1495.9
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | CA: INSTALL ADDITIONAL SIGNAGE FOR TAILGATING LOT | GEN-PARK | CLOSED | 1377.76 | 0 | 659.965 | 659.965
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | EL: SUPPORT FOR CONSTRUCTION - NEW TAILGAITING LOT | GEN-PARK | CLOSED | 2894.3876 | 0 | 2233.21 | 2233.21
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | IN: NEW PARKING LOT ON CAMPUS WAY | GEN-PARK | CLOSED | 1281.12 | 0 | 1174.36 | 1174.36
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | LA: SUPPORT FOR CONSTRUCTION - NEW TAILGAITING LOT | GEN-PARK | CLOSED | 1627.3584 | 0 | 2834.05 | 2834.05
PJ0004189 | NEW TAILGATING PARKING LOT ON CAMPUS WAY (NO OVERHEAD) | BRENNAN, MICHAEL | CLOSED | 2012-06-21 | PL: SUPPORT FOR CONSTRUCTION - NEW TAILGAITING LOT | GEN-PARK | CLOSED | 3394.0679 | 0 | 3315.635 | 3315.635
PJ0004189 Total | [7 empty] | 653133.6939 | 0 | 649943.91 | 649943.91
PJ0004184 | AUDIO VISUAL SYSTEM FOR ROOM 111 - BLDG 03 RM 111 | BRENNAN, MICHAEL | CLOSED | 2012-06-15 | AD: SIGNAL PERFECT, LTD. | 003 | CLOSED | 174908.8875 | 0 | 174908.8875 | 174908.8875
PJ0004184 | AUDIO VISUAL SYSTEM FOR ROOM 111 - BLDG 03 RM 111 | BRENNAN, MICHAEL | CLOSED | 2012-06-15 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 3024.83 | 0 | 0 | 0
PJ0004184 Total | [7 empty] | 177933.7175 | 0 | 174908.8875 | 174908.8875
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: EARTH SYSTEMS | 032 | CLOSED | 1391 | 0 | 1391 | 1391
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: ENGLEKIRK AND SABOL | 032 | CLOSED | 1092.47 | 0 | 1092.47 | 1092.47
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: FENCE FACTORY | 032 | CLOSED | 1214.985 | 0 | 1214.985 | 1214.985
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: FLUID RESOURCE MANAGEMENT (ASSIST PLUMBERS) | 032J | CLOSED | 0 | 0 | 481.5 | 481.5
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: JOC 12.026.009 PRE CON | 032 | CLOSED | 38021.808 | 0 | 38021.808 | 38021.808
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: MCKENNA ENVIRONMENTAL | 032 | CLOSED | 10308.6047 | 0 | 5328.6 | 5328.6
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: NORTH COAST ENGINEERING | 032 | CLOSED | 12840 | 0 | 12766.17 | 12766.17
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: SHIPPING CHARGES (TO ENGLEKIRK AND SABOL) | 032 | CLOSED | 0 | 0 | 5.22 | 5.22
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | AD: STATE FIRE MARSHAL FEES | 032J | CLOSED | 0 | 0 | 420 | 420
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | CP: PROJECT CONTINGENCY | 032 | CLOSED | 5644.94 | 0 | 0 | 0
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | EL: ABANDON ELECTRICAL SERVICE AT OLD STUDENT HORSE BARN | 032 | CLOSED | 539.328 | 0 | 318.588 | 318.588
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | EO: SUPPORT FOR PLUMBING AND ELECTRICAL AT MARE BARN PROJECT 032 | 032 | CLOSED | 398.112 | 0 | 1064.736 | 1064.736
PJ0004183 | DEMO & PREP FOR 2ND NEW 40-STALL MARE BARN - BLDG 032 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-06-13 | PL: LOCATE EXISTING WATER SUPPLIES AT HORSE UNIT | 032 | CLOSED | 1044.672 | 0 | 2482.626 | 2482.626
PJ0004183 Total | [7 empty] | 72495.9197 | 0 | 64587.703 | 64587.703
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | AD: COASTAL DEMO | 042A | CLOSED | 375 | 0 | 375 | 375
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | AD: FENCE FACTORY | 042A | CLOSED | 9304.48 | 0 | 5402.24 | 5402.24
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | AD: HPS MECHANICAL | 042A | CLOSED | 4139 | 0 | 4139 | 4139
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | AD: KIRK CONSTRUCTION | 042A | CLOSED | 6289.9 | 0 | 4354.1 | 4354.1
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | AD: PARKING PERMITS FOR CONTRACTORS-PD FROM PLUMBING RL002 (N/L) | 042A | CLOSED | 10 | 0 | 35 | 35
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | AD: STATE FIRE MARSHAL FEES | 042A | CLOSED | 186.66 | 0 | 186.66 | 186.66
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | CA: SIGNAGE FOR ROAD BETWEEN ANDERSON AQUATIC CTR & TENNIS COURT | 042A | CLOSED | 1807.2029 | 0 | 231.96 | 231.96
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | CA:INSTALL SPLASH GUARD BY POC OF CHEM LINES | 042A | CLOSED | 988.7945 | 0 | 1197.9 | 1197.9
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | CPE: PROVIDE SUPPORT FOR CHEM LINES AT ANDERSON AQUATIC CENTER | 042A | CLOSED | 2287.0774 | 0 | 2131.81 | 2131.81
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | EL:PROVIDE ELECTRICAL SUPPORT FOR UNDERGROUND CHEMICAL POOL LINE | 042A | CLOSED | 3983.9326 | 0 | 3993 | 3993
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | IN: SR 12/13: REROUTE POOL CHEMICAL LINES - ANDERSON POOL - 42A | 042A | CLOSED | 186.83 | 0 | 186.83 | 186.83
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | LO:INSTALL LOCK ON GATE AT ANDERSON AQUATIC CENTER (N/L) | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | PA: PATCH AND PAINT ANDERSON AQUATIC CENTER | 042A | CLOSED | 2478.8 | 0 | 1569.18 | 1569.18
PJ0004182 | SR 12/13: RE-ROUTE CHEMICAL LINES AT ANDERSON POOL - 42A | MOLLAN, CHERYL L. | CLOSED | 2012-06-13 | PL:INSTALL NEW CHEMICAL POOL LINES FOR ANDERSON AQUATIC PER PLAN | 042A | CLOSED | 53703.6206 | 0 | 57444.6545 | 57444.6545
PJ0004182 Total | [7 empty] | 85741.298 | 0 | 81247.3345 | 81247.3345
PJ0004181 | SURVEY LOT FOR TAILGATING LOCATION - P-H16 | NEEL, JOEL | CLOSED | 2012-06-12 | AD: NORTH COAST ENGINEERING | P-H16 | CLOSED | 3156.5 | 0 | 631.3 | 631.3
PJ0004181 | SURVEY LOT FOR TAILGATING LOCATION - P-H16 | NEEL, JOEL | CLOSED | 2012-06-12 | CP: PROJECT CONTINGENCY | P-H16 | CLOSED | 315.65 | 0 | 0 | 0
PJ0004181 Total | [7 empty] | 3472.15 | 0 | 631.3 | 631.3
PJ0004180 | TELEVISION & MONITOR INSTALLATION OUTSIDE CHUMASH AUD. & RM 220 | MOLLAN, CHERYL L. | CLOSED | 2012-06-11 | AD: MORELAND THOMPSON, INC. | 065 | CLOSED | 1776.2 | 0 | 1776.2 | 1776.2
PJ0004180 | TELEVISION & MONITOR INSTALLATION OUTSIDE CHUMASH AUD. & RM 220 | MOLLAN, CHERYL L. | CLOSED | 2012-06-11 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 226.58 | 0 | 0 | 0
PJ0004180 | TELEVISION & MONITOR INSTALLATION OUTSIDE CHUMASH AUD. & RM 220 | MOLLAN, CHERYL L. | CLOSED | 2012-06-11 | IN: TELEVISION & MONITOR INSTALLATION OUTSIDE CHUMASH & RM 220 | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004180 Total | [7 empty] | 2130.892 | 0 | 1904.312 | 1904.312
PJ0004178 | PURCHASE & INSTALL N.& 7 S. SIDE HOOPS & CONNECT SHOT CLOCKS 042 | MOLLAN, CHERYL L. | CLOSED | 2012-06-08 | AD: COURTS AND GREENS | 042 | CLOSED | 48406.8 | 0 | 36012.7118 | 36012.7118
PJ0004178 | PURCHASE & INSTALL N.& 7 S. SIDE HOOPS & CONNECT SHOT CLOCKS 042 | MOLLAN, CHERYL L. | CLOSED | 2012-06-08 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 4476.66 | 0 | 0 | 0
PJ0004178 | PURCHASE & INSTALL N.& 7 S. SIDE HOOPS & CONNECT SHOT CLOCKS 042 | MOLLAN, CHERYL L. | CLOSED | 2012-06-08 | EL: CONNECT SHOT CLOCK TO ELECTRICAL - MOTT GYM 042 | 042 | CLOSED | 9335.7648 | 0 | 3933.264 | 3933.264
PJ0004178 | PURCHASE & INSTALL N.& 7 S. SIDE HOOPS & CONNECT SHOT CLOCKS 042 | MOLLAN, CHERYL L. | CLOSED | 2012-06-08 | IN: REMOVE W SIDE DROP DOWN HOOP & INSTALL NEW N & S HOOPS - 042 | 042 | CLOSED | 192.168 | 0 | 128.112 | 128.112
PJ0004178 Total | [7 empty] | 62411.3928 | 0 | 40074.0878 | 40074.0878
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | CP: PROJECT CONTINGENCY | 060 | CLOSED | 289.22 | 0 | 0 | 0
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | EH&S: LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER RM - BLDG 060 | 060 | CLOSED | 2176.05 | 0 | 304.242 | 304.242
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | EO: ASSIST RECYCLING COORD. IN SCAP METAL REMOVAL - LOCKERS 060 | 060 | CLOSED | 149.292 | 0 | 631.896 | 631.896
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | IN: LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | 060 | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | LA: CLEAN UP AFTER SCRAP METAL REMOVAL - MEN'S LOCKERS BLDG. 60 | 060 | CLOSED | 116.892 | 0 | 116.892 | 116.892
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | MO: ASSIST RECYCLING COORD. IN SCAP METAL REMOVAL - LOCKERS 060 | 060 | CLOSED | 259.2 | 0 | 60.36 | 60.36
PJ0004177 | LOCKER REMOVAL FROM CRANDALL MEN¿S LOCKER ROOM - BLDG 060 | GALVEZ, CESAR | CLOSED | 2012-06-07 | RE: REMOVE SCRAP METAL - LOCKERS FROM MEN'S LOCKER RM. BLDG. 60 | 060 | CLOSED | 126.72 | 0 | 126.72 | 126.72
PJ0004177 Total | [7 empty] | 3181.43 | 0 | 1336.194 | 1336.194
PJ0004175 | REOPENING AND SEALING DOORS - ADMIN RM 413 | BRENNAN, MICHAEL | CLOSED | 2012-05-30 | CA:REMOVE DOOR AND SEAL OPENING | 001 | CLOSED | 1855.1969 | 0 | 703.0614 | 703.0614
PJ0004175 | REOPENING AND SEALING DOORS - ADMIN RM 413 | BRENNAN, MICHAEL | CLOSED | 2012-05-30 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 391.55 | 0 | 0 | 0
PJ0004175 | REOPENING AND SEALING DOORS - ADMIN RM 413 | BRENNAN, MICHAEL | CLOSED | 2012-05-30 | LO:RECONFIGURE HANDLES ON EXISTING DOORS | 001 | CLOSED | 558.2958 | 0 | 87.066 | 87.066
PJ0004175 | REOPENING AND SEALING DOORS - ADMIN RM 413 | BRENNAN, MICHAEL | CLOSED | 2012-05-30 | PA:PATCH AND PAINT AFTER CARPENTERS | 001 | CLOSED | 1357.2728 | 0 | 534.912 | 534.912
PJ0004175 Total | [7 empty] | 4162.3155 | 0 | 1325.0394 | 1325.0394
PJ0004174 | TEMP BLEACHERS FOR SOUTH SIDE STADIUM - SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-31 | AD: MIKE BROWN GRANDSTANDS | 061 | CLOSED | 21942 | 0 | 21942 | 21942
PJ0004174 | TEMP BLEACHERS FOR SOUTH SIDE STADIUM - SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-31 | CA: MARK WHEELCHAIR SPACES FOR TEMP BLEACHER PROJECT - 61 SPANOS | 061 | CLOSED | 625.92 | 0 | 1014.465 | 1014.465
PJ0004174 | TEMP BLEACHERS FOR SOUTH SIDE STADIUM - SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-31 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004174 | TEMP BLEACHERS FOR SOUTH SIDE STADIUM - SPANOS 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-31 | IN: TEMP BLEACHERS FOR SOUTH SIDE STADIUM - SPANOS 061 | 061 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0004174 Total | [7 empty] | 22674.68 | 0 | 23063.225 | 23063.225
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | AD: PROJECT COORDINATION FEE | P-R01 | CLOSED | 3800 | 0 | 3800 | 3800
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 1838.66 | 0 | 0 | 0
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | EL:PROVIDE NEW ELECTRICAL WITH METER FOR VERIZON CELL TOWER | P-R01 | CLOSED | 14101.3663 | 0 | 15577.223 | 15577.223
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | EO:VERIZON CELL; GROUND SUPPORT FOR NEW POLE AND ELECTRICAL LINE | P-R01 | CLOSED | 995.28 | 0 | 640.578 | 640.578
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | IN: (MAINT) VERIZON TEMP CELL TRANSMITTER - P-R01-I PARKING LOT | P-R01 | CLOSED | 0 | 0 | 613.87 | 613.87
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | IN: CAL POLY BUILDING PERMIT FEES | P-R01 | CLOSED | 1055.6 | 0 | 1055.6 | 1055.6
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | IN: CAL POLY PLAN REVEIW FEES | P-R01 | CLOSED | 939.48 | 0 | 939.48 | 939.48
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | IN: VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | P-R01 | CLOSED | 384.336 | 0 | 288.252 | 288.252
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | LA: SUPPORT FOR NEW VERIZON CELL TOWER AT P-R01-I PARKING LOT | P-R01 | CLOSED | 2139.996 | 0 | 86.712 | 86.712
PJ0004173 | VERIZON TEMPORARY CELL TRANSMITTER - P-R01-I PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2012-05-29 | PL: SUPPORT FOR WATER PUMP DURING ELECT. SHUTDOWN -VERIZON TOWER | P-R01 | CLOSED | 511.752 | 0 | 65.292 | 65.292
PJ0004173 Total | [7 empty] | 25766.4703 | 0 | 23067.007 | 23067.007
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | AD: JOC 12.025.001 EVERLAST | 018C | CLOSED | 5993.7976 | 0 | 5993.8939 | 5993.8939
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | AD: PARC ENVIRONMENTAL (CPC FUNDING) | 018C | CLOSED | 1230.5 | 0 | 1230.5 | 1230.5
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | CA: WEATHER STRIPPING ON NEW AI LAB DOOR - BLDG. 18C (CPC FUNDS) | 018C | CLOSED | 373.5173 | 0 | 169.164 | 169.164
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | CP: PROJECT CONTINGENCY (CPF FUNDING) | 018C | CLOSED | 177.61 | 0 | 0 | 0
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | CP: PROJECT CONTINGENCY (STATE FUNDING) | 018C | CLOSED | 37.99 | 0 | 0 | 0
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | EH&S: SAMPLING FOR AI LAB REMODEL - BLD 18CSC (CPF FUNDING) | 018C | CLOSED | 128.808 | 0 | 128.808 | 128.808
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | EL: R&R 2 LIGHT FIXTURES - DPTC AI LAB - 18C (CPF FUNDING) | 018C | CLOSED | 790.4897 | 0 | 775.5095 | 775.5095
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | IN: REMODEL ROOM - BLD 18C AI LAB | 018C | CLOSED | 320.28 | 0 | 160.14 | 160.14
PJ0004172 | REMODEL ROOM - BLD 18C AI LAB | JUDD, PERRY | CLOSED | 2012-05-25 | LO: HARDWARE FOR NEW AI LAB DOOR - BLDG. 18C (CPF FUNDING) | 018C | CLOSED | 669.4381 | 0 | 718.476 | 718.476
PJ0004172 Total | [7 empty] | 9722.4307 | 0 | 9176.4914 | 9176.4914
PJ0004171 | BUILDING SIGN FOR LEPRINO FOODS - BLD 18A | JUDD, PERRY | CLOSED | 2012-05-24 | AD: THE SIGN PLACE | 018A | CLOSED | 3465.6979 | 0 | 3465.6979 | 3465.6979
PJ0004171 | BUILDING SIGN FOR LEPRINO FOODS - BLD 18A | JUDD, PERRY | CLOSED | 2012-05-24 | CP: PROJECT CONTINGENCY | 018A | CLOSED | 346.57 | 0 | 0 | 0
PJ0004171 Total | [7 empty] | 3812.2679 | 0 | 3465.6979 | 3465.6979
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMIININE PRODUCT MACHINE - BLDG 34- 232 | GENERAL | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMIININE PRODUCT MACHINES - BLDG 186 VARIOUS ROOMS | GENERAL | CLOSED | 0 | 0 | 1394.62 | 1394.62
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMIININE PRODUCT MACHINES - BLDG 2-RM 006, 102 & 208 | GENERAL | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMIININE PRODUCT MACHINES - BLDG 21-003,112,202,216 | GENERAL | CLOSED | 0 | 0 | 986.79 | 986.79
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMIININE PRODUCT MACHINES - BLDG 60- WLR BY RM 009 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 007-RM 012 | GENERAL | CLOSED | 140.97 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 008- RM 112 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 013-RM 130 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 024-RM 100 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 041-RM 112, 216 | GENERAL | CLOSED | 140.97 | 0 | 461.63 | 461.63
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 048-RM 102 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 061- 1ST FLOOR WRRS | GENERAL | CLOSED | 0 | 0 | 281.94 | 281.94
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 115 - RM 107 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 124- RM 115, 220 | GENERAL | CLOSED | 0 | 0 | 352.31 | 352.31
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 150-RM 105, 107 | GENERAL | CLOSED | 140.97 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 162D | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 18A-RM 107, 121 | GENERAL | CLOSED | 140.97 | 0 | 280.47 | 280.47
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 197-RM 112 | GENERAL | CLOSED | 140.97 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 26- RM 114 & 203 | GENERAL | CLOSED | 0 | 0 | 70.485 | 70.485
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 5-RM 227 & 315 | GENERAL | CLOSED | 0 | 0 | 161.11 | 161.11
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - AG ERHART 10-249 | GENERAL | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 011-RM 109, 263, 309 | GENERAL | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 042-RM 105, 116, 120 | GENERAL | CLOSED | 140.97 | 0 | 373.765 | 373.765
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 192-RM 112, 216, 316 | GENERAL | CLOSED | 0 | 0 | 678.09 | 678.09
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 20-137 & 212 | GENERAL | CLOSED | 0 | 0 | 276.025 | 276.025
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - BLDG 3-RM 115,210,309,427 | GENERAL | CLOSED | 0 | 0 | 573.315 | 573.315
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - ENGL 22-203 & 304 | GENERAL | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - MATH 38-128, 149 & 223 | GENERAL | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES - W SIDE BLEACHERS- BLDG 61 | GENERAL | CLOSED | 0 | 0 | 187.96 | 187.96
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES -BLDG 025 RMS 118, 220, 322 | GENERAL | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT ADMIN - BLDG 001 | GENERAL | CLOSED | 93.98 | 0 | 70.485 | 70.485
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT FISHER - BLDG 033 | GENERAL | CLOSED | 0 | 0 | 234.95 | 234.95
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT FON - BLDG 047 | GENERAL | CLOSED | 0 | 0 | 418.22 | 418.22
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT MUSIC - BLDG 045 | GENERAL | CLOSED | 93.98 | 0 | 140.97 | 140.97
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT PAC - BLDG 006 | GENERAL | CLOSED | 93.98 | 0 | 46.99 | 46.99
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT SCI. NO. - BLDG 053 | GENERAL | CLOSED | 0 | 0 | 187.96 | 187.96
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES AT THEATRE - BLDG 044 | GENERAL | CLOSED | 93.98 | 0 | 70.485 | 70.485
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE FEMININE PRODUCT MACHINES-BLDG 027-RM 16,165,174&185 | GENERAL | CLOSED | 0 | 0 | 627.9 | 627.9
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE MALE/FEMININE PROD. MACHINES, BLG 14-109,110,225,241 | GENERAL | CLOSED | 0 | 0 | 281.94 | 281.94
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE MALE/FEMININE PRODUCT MACHINES - BLD 35-106, 108, 116 | GENERAL | CLOSED | 0 | 0 | 258.445 | 258.445
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | LO: SUPPORT REMOVAL OF FEMININE PRODUCTS DISPENSERS CAMPUSWIDE | GENERAL | CLOSED | 0 | 0 | 48.37 | 48.37
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCT MACHINE REMOVAL - ENGL 22 | GENERAL | CLOSED | 0 | 0 | 197.88 | 197.88
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCT MACHINE REMOVAL- MATH 038 | GENERAL | CLOSED | 395.76 | 0 | 296.82 | 296.82
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCT MACHINE REMOVAL-AG ERHART | GENERAL | CLOSED | 395.76 | 0 | 519.435 | 519.435
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL (N/L) | GENERAL | CLOSED | 395.76 | 0 | 0 | 0
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 001 | GENERAL | CLOSED | 395.76 | 0 | 395.76 | 395.76
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 025 | GENERAL | CLOSED | 0 | 0 | 593.64 | 593.64
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 044 | GENERAL | CLOSED | 395.76 | 0 | 247.35 | 247.35
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 045 | GENERAL | CLOSED | 395.76 | 0 | 197.88 | 197.88
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 11-263 | GENERAL | CLOSED | 0 | 0 | 49.47 | 49.47
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 162D | GENERAL | CLOSED | 395.76 | 0 | 395.76 | 395.76
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 192 | GENERAL | CLOSED | 0 | 0 | 197.88 | 197.88
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 24-100 | GENERAL | CLOSED | 395.76 | 0 | 247.35 | 247.35
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL - 48-102 | GENERAL | CLOSED | 395.76 | 0 | 346.29 | 346.29
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL -027-165 | GENERAL | CLOSED | 0 | 0 | 346.29 | 346.29
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER FEMININE PRODUCTS MACHINE REMOVAL-MOTT 042 | GENERAL | CLOSED | 395.76 | 0 | 395.76 | 395.76
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER REMOVAL OF FEMININE PRODUCT MACHINES - 033 | GENERAL | CLOSED | 395.76 | 0 | 1360.425 | 1360.425
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER REMOVAL OF FEMININE PRODUCT MACHINES - 047 | GENERAL | CLOSED | 395.76 | 0 | 1236.75 | 1236.75
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER REMOVAL OF FEMININE PRODUCT MACHINES - 053 | GENERAL | CLOSED | 395.76 | 0 | 494.7 | 494.7
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT AFTER REMOVAL OF FEMININE PRODUCT MACHINES - 061 | GENERAL | CLOSED | 395.76 | 0 | 321.555 | 321.555
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT FEM. PROD. MACHINE REMOVAL-BLD 002 -06, 102, 208 | GENERAL | CLOSED | 0 | 0 | 1583.04 | 1583.04
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT FEMININE PRODUCT MACHINE REMOVAL - BLDG 34- 232 | GENERAL | CLOSED | 395.76 | 0 | 197.88 | 197.88
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT FEMININE PRODUCT MACHINE REMOVAL - BLDG 60 WLR | GENERAL | CLOSED | 310.48 | 0 | 1681.98 | 1681.98
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT FEMININE PRODUCT MACHINE REMOVAL - BLG26-114,203 | GENERAL | CLOSED | 0 | 0 | 445.23 | 445.23
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT FEMININE PRODUCT MACHINE REMOVAL- BLD 20-137/212 | GENERAL | CLOSED | 395.76 | 0 | 2770.32 | 2770.32
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT MALE/FEM. MACHINE REMOVAL 14-109,110,225,241 | GENERAL | CLOSED | 395.76 | 0 | 890.46 | 890.46
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA: PATCH/PAINT MALE/FEMALE MACHINE REMOVAL-BLDG 35-106, 108,116 | GENERAL | CLOSED | 395.76 | 0 | 1335.69 | 1335.69
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA:PATCH/PAINT AFTER FEMININE PROD MACHINE REMOVAL 115-107 (N/L) | GENERAL | CLOSED | 395.76 | 0 | 0 | 0
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA:PATCH/PAINT AFTER FEMININE PROD MACHINE REMOVAL 13-130 (N/L) | GENERAL | CLOSED | 395.76 | 0 | 0 | 0
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA:PATCH/PAINT FEMININE PRODUCT MACHINE REMOVAL -BLDG 008 RM 112 | GENERAL | CLOSED | 0 | 0 | 296.82 | 296.82
PJ0004170 | REMOVE ALL MALE & FEMININE PRODUCT DISPENSERS CAMPUSWIDE (MAINT) | GALVEZ, CESAR | CLOSED | 2012-05-25 | PA:PATCH/PAINT FEMININE PRODUCT MACHINE REMOVAL-BLDG 124-115 | GENERAL | CLOSED | 310.48 | 0 | 890.46 | 890.46
PJ0004170 Total | [7 empty] | 9757.9 | 0 | 27572.85 | 27572.85
PJ0004169 | PAC MAINTENANCE WALK-THRU APRIL 2012 - PAC (NO EST) | GALVEZ, CESAR | CLOSED | 2012-05-25 | AD: RICK TEIXEIRA WELDING (N/L) | 006 | CLOSED | 0 | 0 | 175 | 175
PJ0004169 | PAC MAINTENANCE WALK-THRU APRIL 2012 - PAC (NO EST) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REMOVE IMBEDDED PEN MARK ON STEEL BENCH ON PAC PLAZA. | 006 | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0004169 | PAC MAINTENANCE WALK-THRU APRIL 2012 - PAC (NO EST) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CA: REPAIR LISTED ITEMS FROM JULY 2012 MAINTENANCE WALK-THRU | 006 | CLOSED | 939.8 | 0 | 892.81 | 892.81
PJ0004169 | PAC MAINTENANCE WALK-THRU APRIL 2012 - PAC (NO EST) | GALVEZ, CESAR | CLOSED | 2012-05-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004169 | PAC MAINTENANCE WALK-THRU APRIL 2012 - PAC (NO EST) | GALVEZ, CESAR | CLOSED | 2012-05-25 | ES: REPAIR LISTED ITEMS FROM JULY 2012 MAINTENANCE WALK-THRU | 006 | CLOSED | 156.09 | 0 | 286.165 | 286.165
PJ0004169 | PAC MAINTENANCE WALK-THRU APRIL 2012 - PAC (NO EST) | GALVEZ, CESAR | CLOSED | 2012-05-25 | LO: REPAIR LISTED ITEMS FROM JULY 2012 MAINTENANCE WALK-THRU | 006 | CLOSED | 0 | 0 | 169.295 | 169.295
PJ0004169 Total | [7 empty] | 1095.89 | 0 | 1617.25 | 1617.25
PJ0004168 | REWORK SMART RM CAPABILITIES & WHITEBOARD - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-05-22 | CA: REMOVE TVS REINSTALL WHITEBOARD | 003 | CLOSED | 3612.247 | 0 | 3373.818 | 3373.818
PJ0004168 | REWORK SMART RM CAPABILITIES & WHITEBOARD - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-05-22 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 436.04 | 0 | 0 | 0
PJ0004168 | REWORK SMART RM CAPABILITIES & WHITEBOARD - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-05-22 | EL: REMOVE PLUG BEHIND TVS | 003 | CLOSED | 360.0012 | 0 | 101.124 | 101.124
PJ0004168 | REWORK SMART RM CAPABILITIES & WHITEBOARD - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-05-22 | IN: REWORK SMART RM CAPABILITIES & WHITEBOARD - BLD 3 RM 112 | 003 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004168 | REWORK SMART RM CAPABILITIES & WHITEBOARD - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-05-22 | PA: TOUCH UP PAINT AFTER CA COMPLETE | 003 | CLOSED | 324.1698 | 0 | 333.456 | 333.456
PJ0004168 Total | [7 empty] | 4796.514 | 0 | 3872.454 | 3872.454
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | AD: APC CONTRACTORS | 057 | CLOSED | 0 | 0 | 3910 | 3910
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | AD: SANTA MARIA ACOUSTICAL | 057 | CLOSED | 0 | 0 | 2600 | 2600
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | CA: REPLACE DAMAGED SIDING & BUILDING STRUCTURE - VET CLINIC 057 | 057 | CLOSED | 1879.6 | 0 | 23626.1579 | 23626.1579
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | CP: PROJECT CONTINGENCY | 057 | CLOSED | 0 | 0 | 0 | 0
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | EL: RE-WORK ELECT. SUPPLY, ADD NEW FEED, CLEAN UP HANGING WIRES | 057 | CLOSED | 12470.9276 | 0 | 14005.315 | 14005.315
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | EO: ASSIST ELECTRICIANS AT VET CLINIC (EXTERIOR UPDATE PROJECT) | 057 | CLOSED | 0 | 0 | 1038.69 | 1038.69
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | EO: WASP CONTROL | 057 | CLOSED | 0 | 0 | 106.41 | 106.41
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | IN: UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | 057 | CLOSED | 106.76 | 0 | 293.59 | 293.59
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | LA: TRIM/REMOVE SHRUBS AWAY FROM BUILDING FOR PAINTING | 057 | CLOSED | 0 | 0 | 64.94 | 64.94
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | LO: VET CLINIC MAINTENANCE | 057 | CLOSED | 0 | 0 | 1810.585 | 1810.585
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | PA: PREP & PAINT AFFECTED EXTERIOR AREAS - VET CLINIC 057 | 057 | CLOSED | 0 | 0 | 26565.39 | 26565.39
PJ0004164 | UPDATE EXTERIOR - VET CLINIC 57 (MAINT) | GONZALES, ALBERT M. | CLOSED | 2012-05-22 | PL: DISCONNECT WATER LINE ALONG BUILDING | 057 | CLOSED | 0 | 0 | 782.315 | 782.315
PJ0004164 Total | [7 empty] | 14457.2876 | 0 | 74803.3929 | 74803.3929
PJ0004163 | SERVICES FOR CATA FARM SHOW 6/19/12 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2012-05-21 | CA: SUPPORT FOR 2012 CATA FARM SHOW JUNE 19 | 009 | CLOSED | 676.656 | 0 | 451.104 | 451.104
PJ0004163 | SERVICES FOR CATA FARM SHOW 6/19/12 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2012-05-21 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0004163 | SERVICES FOR CATA FARM SHOW 6/19/12 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2012-05-21 | EL: SUPPORT FOR 2012 CATA FARM SHOW - JUNE 19 | 009 | CLOSED | 0 | 0 | 640.452 | 640.452
PJ0004163 Total | [7 empty] | 676.656 | 0 | 1091.556 | 1091.556
PJ0004161 | RESURFACE BATHTUBS IN ALL CSD APARTMENTS - SO MTN | GALVEZ, CESAR | CLOSED | 2012-05-18 | AD: PREMIER RESTORATIONS | RESIDENCE | CLOSED | 2935.545 | 0 | 2935.545 | 2935.545
PJ0004161 | RESURFACE BATHTUBS IN ALL CSD APARTMENTS - SO MTN | GALVEZ, CESAR | CLOSED | 2012-05-18 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0.77 | 0 | 0 | 0
PJ0004161 | RESURFACE BATHTUBS IN ALL CSD APARTMENTS - SO MTN | GALVEZ, CESAR | CLOSED | 2012-05-18 | PL: SUPPORT / ASSIST CONTRACTOR WITH BATHTUB RESURFACING | RESIDENCE | CLOSED | 241.5804 | 0 | 651.288 | 651.288
PJ0004161 | RESURFACE BATHTUBS IN ALL CSD APARTMENTS - SO MTN | GALVEZ, CESAR | CLOSED | 2012-05-18 | PL: UNJUSTIFIED (NO LABOR) | RESIDENCE | CLOSED | 409.7076 | 0 | 0 | 0
PJ0004161 Total | [7 empty] | 3587.603 | 0 | 3586.833 | 3586.833
PJ0004160 | REPLACE FAULTY BREAKERS - PAC 06 | GALVEZ, CESAR | CLOSED | 2012-05-18 | AD: INDEPENDENT ELECTRIC SUPPLY | 006 | CLOSED | 6382.55 | 0 | 6382.55 | 6382.55
PJ0004160 | REPLACE FAULTY BREAKERS - PAC 06 | GALVEZ, CESAR | CLOSED | 2012-05-18 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 980.21 | 0 | 0 | 0
PJ0004160 | REPLACE FAULTY BREAKERS - PAC 06 | GALVEZ, CESAR | CLOSED | 2012-05-18 | EL: COMMENCE WITH PAC FAULTY BREAKERS REPAIRS | 006 | CLOSED | 3419.3304 | 0 | 2620.284 | 2620.284
PJ0004160 Total | [7 empty] | 10782.0904 | 0 | 9002.834 | 9002.834
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | AD: JOC 11.023.024 | RESIDENCE | CLOSED | 101299.57 | 0 | 101299.57 | 101299.57
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 5900 | 0 | 4652 | 4652
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | EL: SUPPORT FOR CSD KITCHEN REMODEL | RESIDENCE | CLOSED | 1623.6 | 0 | 806.0546 | 806.0546
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | ES: SUPPORT FOR CSD KITCHEN REMODEL | RESIDENCE | CLOSED | 1040.6 | 0 | 26.015 | 26.015
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | IN: M&R HOUS 12/13: REMODEL CSD KITCHEN - SOUTH MTN | RESIDENCE | CLOSED | 1067.6 | 0 | 934.15 | 934.15
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | ITS: REMODEL CSD KITCHEN - SOUTH MOUNTAIN HALL(PD FROM PJ FUNDS) | RESIDENCE | CLOSED | 1100 | 0 | 1715.5 | 1715.5
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | PA: SUPPROT FOR CSD KITCHEN REMODEL (NO LABOR) | RESIDENCE | CLOSED | 697.88 | 0 | 123.04 | 123.04
PJ0004157 | M&R HOUS 12/13: REMODEL CSD KITCHENS - SOUTH MTN | BRENNAN, MICHAEL | CLOSED | 2012-05-17 | PL: SUPPROT FOR CSD KITCHEN REMODEL | RESIDENCE | CLOSED | 1088.2 | 0 | 1519.04 | 1519.04
PJ0004157 Total | [7 empty] | 113817.45 | 0 | 111075.3696 | 111075.3696
PJ0004156 | M&R HOUS 12/13: RENOVATE BBQ SPACE - NORTH MTN | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | AD: JOC 13.028.015 MAINO | RESIDENCE | CLOSED | 36501.42 | 0 | 36501.42 | 36501.42
PJ0004156 | M&R HOUS 12/13: RENOVATE BBQ SPACE - NORTH MTN | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | AD: OMNI DESIGN | RESIDENCE | CLOSED | 3500 | 0 | 3500 | 3500
PJ0004156 | M&R HOUS 12/13: RENOVATE BBQ SPACE - NORTH MTN | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004156 | M&R HOUS 12/13: RENOVATE BBQ SPACE - NORTH MTN | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | IN: M&R HOUS 12/13: RENOVATE BBQ SPACE - NORTH MTN | RESIDENCE | CLOSED | 320.28 | 0 | 186.83 | 186.83
PJ0004156 | M&R HOUS 12/13: RENOVATE BBQ SPACE - NORTH MTN | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | LA: IRRIGATION / PLANTING RELOCATION (NO LABOR) | RESIDENCE | CLOSED | 1289.04 | 0 | 0 | 0
PJ0004156 Total | [7 empty] | 41610.74 | 0 | 40188.25 | 40188.25
PJ0004154 | M&R HOUS 12/13: RENOVATE REC AREA (INSTALL BBQ) - SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | AD: JOC 13.030.027 MAINO | 113 | CLOSED | 18509.5234 | 0 | 18509.5234 | 18509.5234
PJ0004154 | M&R HOUS 12/13: RENOVATE REC AREA (INSTALL BBQ) - SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 2067.02 | 0 | 0 | 0
PJ0004154 | M&R HOUS 12/13: RENOVATE REC AREA (INSTALL BBQ) - SIERRA MADRE | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-17 | IN: M&R HOUS 12/13: RENOVATE RECREATION AREA - SIERRA MADRE 113 | 113 | CLOSED | 384.336 | 0 | 352.308 | 352.308
PJ0004154 Total | [7 empty] | 20960.8794 | 0 | 18861.8314 | 18861.8314
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | AD: FRM-HYDRANT FLOW/PRESSURE READINGS NEAR SIERRA MADRE(204109) | 113 | CLOSED | 0 | 0 | 1444.5 | 1444.5
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | ANTS: PROGRAM ALARMS FOR SIERRA MADRE FIRE SPRINKLER PROJECT | 113 | CLOSED | 0 | 0 | 396.396 | 396.396
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | CA: SUPPORT FOR SIERRA MADRE FIRE SPRINKLER PROJECT - BLDG 113 | 113 | CLOSED | 0 | 0 | 281.94 | 281.94
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 25000 | 0 | 0 | 0
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 113 | CLOSED | 0 | 0 | 25.2 | 25.2
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | EH&S: SUPPORT FOR FIRE SPRINKLERS - SIERRA MADRE PROJECT (N/L) | 113 | CLOSED | 0 | 0 | 76.26 | 76.26
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | EL: LOCATE & MARK UTILITIES FOR SIERRA MADRE FIRE SPRINKLER PJ | 113 | CLOSED | 0 | 0 | 1128.756 | 1128.756
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | EL: SUPPORT FOR FIRE SPRINKLERS - SIERRA MADRE PROJECT - 113 | 113 | CLOSED | 0 | 0 | 239.76 | 239.76
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | LA: LOCATE A & MARK UTILITIES FOR SIERRA MADRE FIRE SPRINKLER PJ | 113 | CLOSED | 0 | 0 | 214.302 | 214.302
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | LA: SUPPORT FOR SIERRA MADRE FIRE SPINKLER PROJECT - PHASE II | 113 | CLOSED | 0 | 0 | 58.446 | 58.446
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | LA: SUPPORT FOR SIERRA MADRE FIRE SPRINKLER PROJECT - BLDG 113 | 113 | CLOSED | 0 | 0 | 4922.5325 | 4922.5325
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | LO: PROVIDE 3 CABLES AND 3 PADLOCKS FOR SPRINKLER VALVES | 113 | CLOSED | 0 | 0 | 131.844 | 131.844
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | LO: PROVIDE PADLOCK FOR VALVES | 113 | CLOSED | 0 | 0 | 193.044 | 193.044
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | PA:PAINT NEW GATE | 113 | CLOSED | 0 | 0 | 1038.87 | 1038.87
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | PL: ASSIST FRM- HYDRANT FLOW/PRESSURE READINGS NEAR SM (205648) | 113 | CLOSED | 0 | 0 | 130.584 | 130.584
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | PL: LOCATE A & MARK UTILITIES FOR SIERRA MADRE FIRE SPRINKLER PJ | 113 | CLOSED | 0 | 0 | 8410.3148 | 8410.3148
PJ0004150 | MJ: IN-HOUSE SUPPORT FOR FIRE SPRINKLERS ¿ SIERRA MADRE 113 | JUDD, PERRY | CLOSED | 2012-05-16 | PL:SUPPORT FOR FIRE SPRINKLERS - SIERRA MADRE 113 | 113 | CLOSED | 0 | 0 | 9198.534 | 9198.534
PJ0004150 Total | [7 empty] | 25000 | 0 | 27891.2833 | 27891.2833
PJ0004149 | FP 11/12: ADA COMPLIANCE FOR COMMENCEMENT - SPANOS 61 | POPHAM, DONALD J. | CLOSED | 2012-05-15 | AD: AMERICAN TURF AND CARPET | 061 | CLOSED | 0 | 0 | 10479.42 | 10479.42
PJ0004149 | FP 11/12: ADA COMPLIANCE FOR COMMENCEMENT - SPANOS 61 | POPHAM, DONALD J. | CLOSED | 2012-05-15 | AD: JOC 11.023.044 STAPLES | 061 | CLOSED | 16989.85 | 0 | 16989.85 | 16989.85
PJ0004149 | FP 11/12: ADA COMPLIANCE FOR COMMENCEMENT - SPANOS 61 | POPHAM, DONALD J. | CLOSED | 2012-05-15 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004149 | FP 11/12: ADA COMPLIANCE FOR COMMENCEMENT - SPANOS 61 | POPHAM, DONALD J. | CLOSED | 2012-05-15 | IN: FP 11/12: ADA COMPLIANCE FOR COMMENCEMENT - SPANOS 61 | 061 | CLOSED | 53.38 | 0 | 53.38 | 53.38
PJ0004149 Total | [7 empty] | 17043.23 | 0 | 27522.65 | 27522.65
PJ0004148 | ADD DOOR RESTRICTORS, ELEVATOR - ADMIN 01 (MAINT) | JUDD, PERRY | CLOSED | 2012-05-14 | AD: OTIS ELEVATOR | 001 | CLOSED | 2534 | 0 | 2533.41 | 2533.41
PJ0004148 | ADD DOOR RESTRICTORS, ELEVATOR - ADMIN 01 (MAINT) | JUDD, PERRY | CLOSED | 2012-05-14 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0004148 Total | [7 empty] | 2534 | 0 | 2533.41 | 2533.41
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | AD: JOC 12.025.009 EVERLAST | 192 | CLOSED | 69211.8372 | 0 | 68237.7199 | 68237.7199
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | AD: WLH BUILDING COMPANY | 192 | CLOSED | 1657.0769 | 0 | 1657.0769 | 1657.0769
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | CA: REMOVE COLLEGE ADVANCEMENT SIGNS OUTSIDE RMS 108A&B - BLD 13 | 013 | CLOSED | 56.388 | 0 | 28.194 | 28.194
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 6405.56 | 0 | 0 | 0
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | EL: PROVIDE ASSISTANCE FOR FIRE ALARM SYSTEM - 192-301 | 192 | CLOSED | 269.664 | 0 | 33.708 | 33.708
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | IN: FINISH DEAN'S OFFICE SPACE (192 - 301) | 192 | CLOSED | 1281.12 | 0 | 864.756 | 864.756
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | PA: PAINT NEW WALLS | 192 | CLOSED | 6485.1769 | 0 | 4079.412 | 4079.412
PJ0004147 | FINISH DEAN'S OFFICE SPACE (192 - 301) | LAMPMAN, GREG | CLOSED | 2012-05-09 | PL: MOVE PLUMBING FOR NEW SINK | 192 | CLOSED | 4706.1469 | 0 | 4661.1 | 4661.1
PJ0004147 Total | [7 empty] | 90072.9699 | 0 | 79561.9668 | 79561.9668
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: ASAP REPROGRAPHICS | 024 | CLOSED | 279.26 | 0 | 289.85 | 289.85
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: DIVISION OF STATE ARCHITECT | 024 | CLOSED | 800 | 0 | 800 | 800
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: HAYER CONSULTANTS, INC. | 024 | CLOSED | 428 | 0 | 428 | 428
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: JOC 12.024.032 STAPLES | 024 | CLOSED | 97827.4036 | 0 | 97827.4036 | 97827.4036
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: MECA | 024 | CLOSED | 1777.7943 | 0 | 1777.7943 | 1777.7943
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: OVERHEAD ON STARBUCKS CONTRACT | 024 | CLOSED | 10640 | 0 | 10640 | 10640
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: PHILLIP METSCH SWEENEY MOORE ARICHITECTS (PMSM) | 024 | CLOSED | 36968.5 | 0 | 36968.5 | 36968.5
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | AD: PLC+ PROGRAMING | 024 | CLOSED | 967.815 | 0 | 967.815 | 967.815
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 164.8 | 0 | 0 | 0
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | CU: UNLOAD STARBUCKS KIOSK FROM TRUCK | 024 | CLOSED | 131.184 | 0 | 145.968 | 145.968
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | EL: ELECTRICAL FOR STARBUCKS KIOSK | 024 | CLOSED | 9641.04 | 0 | 9856.542 | 9856.542
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | IN: INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | 024 | CLOSED | 2113.848 | 0 | 2113.848 | 2113.848
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | LO:INSTALL ORANGE CORE LOCKS ON DOORS AT CAMPUS MARKET (BLDG 24) | 024 | CLOSED | 58.044 | 0 | 58.044 | 58.044
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | MO: PICK UP PALLETS FOR STARBUCKS PROJECT, WHEN CALLED | 024 | CLOSED | 291.6 | 0 | 108.648 | 108.648
PJ0004146 | INSTALL STARBUCKS KIOSK - BLD 24 RM 114A | JUDD, PERRY | CLOSED | 2012-05-04 | PL: PLUMBING SUPPORT FOR STARBUCKS KIOSK | 024 | CLOSED | 1492.602 | 0 | 1599.438 | 1599.438
PJ0004146 Total | [7 empty] | 163581.8909 | 0 | 163581.8509 | 163581.8509
PJ0004145 | MOVE ELECTRICAL OUTLET - BLD 53 RM 203 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-04 | CA: MOVE TABLE AND ADD LEG - BLDG 53 ROOM 203 | 053 | CLOSED | 511.104 | 0 | 142.794 | 142.794
PJ0004145 | MOVE ELECTRICAL OUTLET - BLD 53 RM 203 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-04 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 95.95 | 0 | 0 | 0
PJ0004145 | MOVE ELECTRICAL OUTLET - BLD 53 RM 203 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-05-04 | EL: REFEED TABLE OUTLETS - BLDG 53 ROOM 203 | 053 | CLOSED | 299.664 | 0 | 567.552 | 567.552
PJ0004145 Total | [7 empty] | 906.718 | 0 | 710.346 | 710.346
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | AD: COASTAL DEMO | 065 | CLOSED | 802.5 | 0 | 577.8 | 577.8
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | AD: KIRK CONSTRUCTION | 065 | CLOSED | 1856.236 | 0 | 1856.236 | 1856.236
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | AD: PARC ENVIRONMENTAL | 065 | CLOSED | 6388.97 | 0 | 6870.47 | 6870.47
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | CA: INSTALL NEW TILE IN CUSTODIAL CLOSET - YOGURT CREATIONS UU | 065 | CLOSED | 3455.52 | 0 | 876.48 | 876.48
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 6399.56 | 0 | 0 | 0
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | EH&S: REMOVE WALL&INSTALL GREASE TRAP-YOGURT SHOP-UU(N/L) | 065 | CLOSED | 1691.4 | 0 | 0 | 0
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | EL: YOGURT CREATIONS ELECTRICAL WORK | 065 | CLOSED | 68135.1432 | 0 | 67883.6011 | 67883.6011
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | EO: PLUMBING SUPPORT - REMOVE DEBRIS FOR YOGURT SHOP PROJECT | 065 | CLOSED | 199.056 | 0 | 276.984 | 276.984
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | ES: DETERMINE EXISTING VENTILATION SPACE FOR YOGURT CREATIONS | 065 | CLOSED | 561.924 | 0 | 249.744 | 249.744
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | IN:REMOVE WALL&INSTALL GREASE TRAP-YOGURT SHOP-UU 65 RM 112/112A | 065 | CLOSED | 896.784 | 0 | 1088.952 | 1088.952
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | LA: REMOVE DIRT/CONCRETE FOR NEW SEWER LINE -YOGURT SHOP PROJECT | 065 | CLOSED | 311.712 | 0 | 935.136 | 935.136
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | LO:CHANGE CORE TO ORANGE-INSTALL NEW LOCKSET | 065 | CLOSED | 116.088 | 0 | 828.132 | 828.132
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | MO:MOVING SUPPORT FOR YOGURT CREATIONS PROJECT-UU 112/112A (N/L) | 065 | CLOSED | 291.6 | 0 | 0 | 0
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | PCV CA: REPAIR HOLES AND WALL IN SHEETROCK - YOGURT CREATIONS | 065 | CLOSED | 571.104 | 0 | 212.244 | 212.244
PJ0004144 | M&R ASI 12/13:YOGURT CREATIONS INFRASTRUCTURE- UU 65 RM 112/112A | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | PL:PROVIDE SEWER AND WATER POC FOR TENNANT IMIPROVEMENT | 065 | CLOSED | 13628.7173 | 0 | 8618.982 | 8618.982
PJ0004144 Total | [7 empty] | 105306.3145 | 0 | 90274.7611 | 90274.7611
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | AD: FLOOR CONNECTION | 065 | CLOSED | 2204.2 | 0 | 2204.2 | 2204.2
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | AD: JOC 12.026.003 PRECON | 065 | CLOSED | 80006.147 | 0 | 77094.1955 | 77094.1955
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | AD: JOC 13.028.037 MAINO | 065 | CLOSED | 12717.378 | 0 | 12717.378 | 12717.378
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 7491.21 | 0 | 0 | 0
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | EL:DISCONNECT ELECTRICAL - PROVIDE CONSTRUCTION SUPPORT | 065 | CLOSED | 3060.685 | 0 | 1057.392 | 1057.392
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | IN: DEMO HALF WALL/REPLACE FLOORING -BOWLING-UU 65-118 | 065 | CLOSED | 384.336 | 0 | 352.308 | 352.308
PJ0004143 | M&R ASI 12/13: DEMO HALF WALL/REPLACE FLOORING-BOWLING-UU 65-118 | MOLLAN, CHERYL L. | CLOSED | 2012-05-01 | PA: PAINTING FOR HALF WALL/FLOORING PROJECT AT UU BOWLING ALLEY | 065 | CLOSED | 474.912 | 0 | 1899.648 | 1899.648
PJ0004143 Total | [7 empty] | 106338.868 | 0 | 95325.1215 | 95325.1215
PJ0004142 | RR FIXTURES, SLATWALL, & FLOORING - EL CORRAL - UU 65 RM 101 | LAMPMAN, GREG | CLOSED | 2012-04-27 | AD: JOC 12.024.001 STAPLES | 065 | CLOSED | 268016.1573 | 0 | 265994.1569 | 265994.1569
PJ0004142 | RR FIXTURES, SLATWALL, & FLOORING - EL CORRAL - UU 65 RM 101 | LAMPMAN, GREG | CLOSED | 2012-04-27 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 4674.16 | 0 | 0 | 0
PJ0004142 | RR FIXTURES, SLATWALL, & FLOORING - EL CORRAL - UU 65 RM 101 | LAMPMAN, GREG | CLOSED | 2012-04-27 | EL: TURN SMOKE ALARM SYSTEM AT BOOKSTORE OFF AND ON, AS NEEDED | 065 | CLOSED | 1348.32 | 0 | 1771.836 | 1771.836
PJ0004142 | RR FIXTURES, SLATWALL, & FLOORING - EL CORRAL - UU 65 RM 101 | LAMPMAN, GREG | CLOSED | 2012-04-27 | IN: RR FIXTURES, SLATWALL & FLOORING - EL CORRAL - UU 65 RM 101 | 065 | CLOSED | 512.448 | 0 | 576.504 | 576.504
PJ0004142 | RR FIXTURES, SLATWALL, & FLOORING - EL CORRAL - UU 65 RM 101 | LAMPMAN, GREG | CLOSED | 2012-04-27 | LO: INSTALL CONSTRUCTION CORES FOR BOOKSTORE RENO | 065 | CLOSED | 232.176 | 0 | 145.11 | 145.11
PJ0004142 Total | [7 empty] | 274783.2613 | 0 | 268487.6069 | 268487.6069
PJ0004141 | FP 11/12: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | JUDD, PERRY | CLOSED | 2012-04-25 | AD: JOC 12.024.016.00 (PARTIAL) AND 12.024.016.01 | GENERAL | CLOSED | 196221.7 | 0 | 195545.53 | 195545.53
PJ0004141 | FP 11/12: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | JUDD, PERRY | CLOSED | 2012-04-25 | AD: NORTH COAST ENGINEERING | GENERAL | CLOSED | 27773 | 0 | 27773 | 27773
PJ0004141 | FP 11/12: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | JUDD, PERRY | CLOSED | 2012-04-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004141 | FP 11/12: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | JUDD, PERRY | CLOSED | 2012-04-25 | EL: SUPPORT FOR PATH OF TRAVEL BETWEEN 43 AND 130 | GENERAL | CLOSED | 1000.5658 | 0 | 809.0638 | 809.0638
PJ0004141 | FP 11/12: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | JUDD, PERRY | CLOSED | 2012-04-25 | IN: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | GENERAL | CLOSED | 2135.2 | 0 | 827.39 | 827.39
PJ0004141 | FP 11/12: DESIGN/CONSTRUCT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | JUDD, PERRY | CLOSED | 2012-04-25 | LA: SUPPORT ADA PATH OF TRAVEL BETWN 43 & GAP 130 | GENERAL | CLOSED | 578.2907 | 0 | 406.11 | 406.11
PJ0004141 Total | [7 empty] | 227708.7565 | 0 | 225361.0938 | 225361.0938
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: ASAP REPROGRAPHICS | 192 | CLOSED | 125.3 | 0 | 125.3 | 125.3
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: DEEP BLUE INTEGRATION | 192 | CLOSED | 3068.225 | 0 | 3068.225 | 3068.225
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: DIVISION OF STATE ARCHITECT | 192 | CLOSED | 480 | 0 | 480 | 480
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: FLOOR CONNECTION | 192 | CLOSED | 4061.72 | 0 | 4061.72 | 4061.72
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: JOC 13.028.024 AND 13.030.030 MAINO | 192 | CLOSED | 179538.7775 | 0 | 179538.7775 | 179538.7775
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: PMSM ARCHTECTS | 192 | CLOSED | 45619.45 | 0 | 45619.45 | 45619.45
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | AD: STATE FIRE MARSHAL FEES | 192 | CLOSED | 140 | 0 | 140 | 140
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | CU: FINAL CLEANUP FOR CYBER TECH LAB PROJECT - BLDG 192 | 192 | CLOSED | 114.786 | 0 | 114.786 | 114.786
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | IN:CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | 192 | CLOSED | 1313.148 | 0 | 1313.148 | 1313.148
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | LO: PROVIDE LOCKS AND CLOSER AS PER PLANS | 192 | CLOSED | 3560.274 | 0 | 3560.106 | 3560.106
PJ0004137 | CYBER SECURITY LAB DEVELOPMENT/RENO - BLD 192-311,312,319&333 | LAMPMAN, GREG | CLOSED | 2012-04-23 | PA: PAINT WALLS AND CEILINGS WITH CP-2 | 192 | CLOSED | 6216.144 | 0 | 6215.988 | 6215.988
PJ0004137 Total | [7 empty] | 244237.8245 | 0 | 244237.5005 | 244237.5005
PJ0004136 | FP 11/12: CONSTRUCT SOUTH END ZONE BLEACHERS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-04-20 | AD: JOC 11.023.020 STAPLES | 061 | CLOSED | 600645.64 | 0 | 600645.64 | 600645.64
PJ0004136 | FP 11/12: CONSTRUCT SOUTH END ZONE BLEACHERS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-04-20 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004136 | FP 11/12: CONSTRUCT SOUTH END ZONE BLEACHERS - BLD 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-04-20 | PL: VERIFY CONTRACTOR POTHOLING FOR UTILITY CLEARANCES | 061 | CLOSED | 2400.0251 | 0 | 4374.4824 | 4374.4824
PJ0004136 Total | [7 empty] | 603045.6651 | 0 | 605020.1224 | 605020.1224
PJ0004135 | PLUMBING LEAK REPAIR - BLDG 10-109A MRR (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-18 | CA:LEAKING PLUMBING SUPPORT AT AG ERHART | 010 | CLOSED | 0 | 0 | 3458.3546 | 3458.3546
PJ0004135 | PLUMBING LEAK REPAIR - BLDG 10-109A MRR (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-18 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0004135 | PLUMBING LEAK REPAIR - BLDG 10-109A MRR (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-18 | PA:PATCH, PREP, AND PAINT WALLS FROM PLUMBING LEAK REPAIRS | 010 | CLOSED | 0 | 0 | 1137.81 | 1137.81
PJ0004135 | PLUMBING LEAK REPAIR - BLDG 10-109A MRR (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-18 | PL:REPAIR LEAKING TOILET PLUMBING AT AG ERHART | 010 | CLOSED | 0 | 0 | 10742.1998 | 10742.1998
PJ0004135 Total | [7 empty] | 0 | 0 | 15338.3644 | 15338.3644
PJ0004132 | ENGRAVE TILES AT CENG PLAZA | MOLLAN, CHERYL L. | CLOSED | 2012-04-13 | AD: BURCH CONCRETE SOLUTIONS | GENERAL | CLOSED | 3745 | 0 | 3861.3625 | 3861.3625
PJ0004132 | ENGRAVE TILES AT CENG PLAZA | MOLLAN, CHERYL L. | CLOSED | 2012-04-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 380.91 | 0 | 0 | 0
PJ0004132 | ENGRAVE TILES AT CENG PLAZA | MOLLAN, CHERYL L. | CLOSED | 2012-04-13 | IN: ENGRAVE TILES AT CENG PLAZA | GENERAL | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004132 Total | [7 empty] | 4189.966 | 0 | 3925.4185 | 3925.4185
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | CA: REPAIR MISC ITEMS (SEE TASK LIST) BEFORE JUNE- BLDG 55A | 055A | CLOSED | 0 | 0 | 13326.052 | 13326.052
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | CP: PROJECT CONTINGENCY | 055A | CLOSED | 0 | 0 | 0 | 0
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | CU: STRIP AND WAX ALL FLOORS BEFORE JUNE - BLDG 55A | 055A | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | EL: PLACE COVER PLATES OVER EXPOSED ELECTRICAL - BLDG 55A | 055A | CLOSED | 0 | 0 | 62.63 | 62.63
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | ES: PM AND SERVICE BOTH HEATER UNITS BEFORE JUNE - BLDG 55A | 055A | CLOSED | 0 | 0 | 260.15 | 260.15
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | LO: REMOVE LOCKSET TO OLD DOORWAY IN BEDROOM BEFORE JUNE - 55A | 055A | CLOSED | 0 | 0 | 48.37 | 48.37
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | PA: TAPE, MUD, PAINT APARTMENT BEFORE JUNE (SEE TASK LIST)- 55A | 055A | CLOSED | 0 | 0 | 8832.86 | 8832.86
PJ0004131 | CLEAN UP STUDENT RESIDENCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2012-04-13 | PL: REMOVE AND REINSTALL WATER HEATER - BCEC BLDG 55A | 055A | CLOSED | 0 | 0 | 4938.5438 | 4938.5438
PJ0004131 Total | [7 empty] | 0 | 0 | 27577.9258 | 27577.9258
PJ0004127 | SR 11/12: PAINT EAST BLEACHER STRUCTURE - SPANOS STADIUM 61 | ALTON, JOSHUA R | CLOSED | 2012-04-10 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004127 | SR 11/12: PAINT EAST BLEACHER STRUCTURE - SPANOS STADIUM 61 | ALTON, JOSHUA R | CLOSED | 2012-04-10 | PA: PAINT EAST BLEACHERS, ENCAPSULATE LEAD PAINT - SPANOS 061 | 061 | CLOSED | 49745.6 | 0 | 47720.78 | 47720.78
PJ0004127 Total | [7 empty] | 49745.6 | 0 | 47720.78 | 47720.78
PJ0004124 | ANNUAL WON DOOR SERVICE FOR (6) FIREGUARD ELEVATOR DOORS- PAC 06 | GALVEZ, CESAR | CLOSED | 2012-03-29 | AD: WONDOOR | 006 | CLOSED | 1398 | 0 | 1440.63 | 1440.63
PJ0004124 | ANNUAL WON DOOR SERVICE FOR (6) FIREGUARD ELEVATOR DOORS- PAC 06 | GALVEZ, CESAR | CLOSED | 2012-03-29 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004124 Total | [7 empty] | 1398 | 0 | 1440.63 | 1440.63
PJ0004123 | SMART ROOM UPGRADES - BLD 42 RM 205E (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CA:SMART ROOM UPGRADE- BLDG 42 ROOM 205E | 042 | CLOSED | 377.94 | 0 | 611.124 | 611.124
PJ0004123 | SMART ROOM UPGRADES - BLD 42 RM 205E (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004123 | SMART ROOM UPGRADES - BLD 42 RM 205E (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | EL:SMART ROOM UPGRADE BLDG 42- ROOM 205E | 042 | CLOSED | 2465.4 | 0 | 3941.232 | 3941.232
PJ0004123 | SMART ROOM UPGRADES - BLD 42 RM 205E (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | IN: SMART ROOM UPGRADES - BLD 42 RM 205E | 042 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004123 | SMART ROOM UPGRADES - BLD 42 RM 205E (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | PA:PAINT AS NEEDED | 042 | CLOSED | 802.368 | 0 | 540.912 | 540.912
PJ0004123 Total | [7 empty] | 3709.764 | 0 | 5157.324 | 5157.324
PJ0004122 | SMART ROOM UPGRADES - BLD 38 RMS 220 & 221 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CA:SMART ROOM BLDG 38, ROOMS 220,221 | 038 | CLOSED | 755.88 | 0 | 743.652 | 743.652
PJ0004122 | SMART ROOM UPGRADES - BLD 38 RMS 220 & 221 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0004122 | SMART ROOM UPGRADES - BLD 38 RMS 220 & 221 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | EL:SMART ROOM BLDG 38, RM 220, 221 | 038 | CLOSED | 4930.8 | 0 | 3176.04 | 3176.04
PJ0004122 | SMART ROOM UPGRADES - BLD 38 RMS 220 & 221 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | IN: SMART ROOM UPGRADES - BLD 38 RMS 220 & 221 | 038 | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004122 | SMART ROOM UPGRADES - BLD 38 RMS 220 & 221 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | PA:SMART ROOM BLDG 38 RM 220,221 | 038 | CLOSED | 1604.736 | 0 | 518.304 | 518.304
PJ0004122 Total | [7 empty] | 7355.472 | 0 | 4534.08 | 4534.08
PJ0004121 | SMART ROOM UPGRADES - BLD 33 RMS 289 & 457 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CA:SMART ROOMS BLDG 33, ROOM 289, 457 | 033 | CLOSED | 755.88 | 0 | 1804.188 | 1804.188
PJ0004121 | SMART ROOM UPGRADES - BLD 33 RMS 289 & 457 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0004121 | SMART ROOM UPGRADES - BLD 33 RMS 289 & 457 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | EL:SMART ROOMS BLDG 33, ROOM 289, 457 | 033 | CLOSED | 4930.8 | 0 | 6410.7 | 6410.7
PJ0004121 | SMART ROOM UPGRADES - BLD 33 RMS 289 & 457 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | IN: SMART ROOM UPGRADES - BLD 33 RMS 289 & 457 | 033 | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004121 | SMART ROOM UPGRADES - BLD 33 RMS 289 & 457 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | PA:PAINT AS NEEDED- SMART ROOM UPGRADE- BLDG 33, 457 | 033 | CLOSED | 1604.736 | 0 | 571.932 | 571.932
PJ0004121 Total | [7 empty] | 7355.472 | 0 | 8882.904 | 8882.904
PJ0004120 | SMART ROOM UPGRADES - BLD 21 RMS 204, 236, 237 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CA:SMART ROOM BLDG 21, ROOMS 204, 236, 237 | 021 | CLOSED | 1133.82 | 0 | 857.628 | 857.628
PJ0004120 | SMART ROOM UPGRADES - BLD 21 RMS 204, 236, 237 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0004120 | SMART ROOM UPGRADES - BLD 21 RMS 204, 236, 237 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | EL:SMART ROOM BLDG 21, ROOMS 204, 236, 237 | 021 | CLOSED | 7396.2 | 0 | 6853.6615 | 6853.6615
PJ0004120 | SMART ROOM UPGRADES - BLD 21 RMS 204, 236, 237 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | IN: SMART ROOM UPGRADES - BLD 21 RMS 204, 236, 237 | 021 | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004120 | SMART ROOM UPGRADES - BLD 21 RMS 204, 236, 237 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | PA: SMART ROOM BLDG 21, ROOMS 204, 236, 237 | 021 | CLOSED | 2407.104 | 0 | 356.184 | 356.184
PJ0004120 Total | [7 empty] | 11001.18 | 0 | 8163.5575 | 8163.5575
PJ0004119 | SMART ROOM UPGRADES - BLD 14 RM 252 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CA:SMART ROOM INSTALLATION BLDG 14, ROOM 252 | 014 | CLOSED | 377.94 | 0 | 256.698 | 256.698
PJ0004119 | SMART ROOM UPGRADES - BLD 14 RM 252 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0004119 | SMART ROOM UPGRADES - BLD 14 RM 252 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | EL:SMART ROOM INSTALLATION BLDG 14, ROOM 252 | 014 | CLOSED | 2465.4 | 0 | 2680.368 | 2680.368
PJ0004119 | SMART ROOM UPGRADES - BLD 14 RM 252 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | IN: SMART ROOM UPGRADES - BLD 14 RM 252 | 014 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004119 | SMART ROOM UPGRADES - BLD 14 RM 252 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | PA:SMART ROOM INSTALLATION BLDG 14, ROOM 252 | 014 | CLOSED | 802.368 | 0 | 208.092 | 208.092
PJ0004119 Total | [7 empty] | 3709.764 | 0 | 3209.214 | 3209.214
PJ0004118 | SMART ROOM UPGRADES - BLD 10 CONF RM 241 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CA:SMART ROOM BLDG 10, RM 241 | 010 | CLOSED | 377.94 | 0 | 411.216 | 411.216
PJ0004118 | SMART ROOM UPGRADES - BLD 10 CONF RM 241 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0004118 | SMART ROOM UPGRADES - BLD 10 CONF RM 241 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | EL:SMART ROOM BLDG 10, RM 241 | 010 | CLOSED | 2465.4 | 0 | 1359.54 | 1359.54
PJ0004118 | SMART ROOM UPGRADES - BLD 10 CONF RM 241 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | IN: SMART ROOM UPGRADES - BLD 10 CONF RM 241 | 010 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004118 | SMART ROOM UPGRADES - BLD 10 CONF RM 241 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-04-06 | PA:SMART ROOM BLDG 10, RM 241 | 010 | CLOSED | 802.368 | 0 | 600.276 | 600.276
PJ0004118 Total | [7 empty] | 3709.764 | 0 | 2435.088 | 2435.088
PJ0004117 | SMART ROOM UPGRADES - BLD 03 RMS 104 & 205 (NO ESTIMATE) | BRENNAN, MICHAEL | CLOSED | 2012-04-06 | CA:SMART ROOM 03-104 | 003 | CLOSED | 676.656 | 0 | 717.984 | 717.984
PJ0004117 | SMART ROOM UPGRADES - BLD 03 RMS 104 & 205 (NO ESTIMATE) | BRENNAN, MICHAEL | CLOSED | 2012-04-06 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0004117 | SMART ROOM UPGRADES - BLD 03 RMS 104 & 205 (NO ESTIMATE) | BRENNAN, MICHAEL | CLOSED | 2012-04-06 | EL: SMART ROOM INSTALL BLDG 03 104 AND 205 | 003 | CLOSED | 0 | 0 | 3097.692 | 3097.692
PJ0004117 | SMART ROOM UPGRADES - BLD 03 RMS 104 & 205 (NO ESTIMATE) | BRENNAN, MICHAEL | CLOSED | 2012-04-06 | PA:SMART ROOMS BLDG 03 104 AND 205 | 003 | CLOSED | 0 | 0 | 837.732 | 837.732
PJ0004117 Total | [7 empty] | 676.656 | 0 | 4653.408 | 4653.408
PJ0004115 | SP 12/13: INSTALL MOTION SENSORS - CHASE - BLD 115 | ELLIOT, DENNIS K | CLOSED | 2012-03-26 | CP: PROJECT CONTINGENCY | 115 | CLOSED | 531.47 | 0 | 0 | 0
PJ0004115 | SP 12/13: INSTALL MOTION SENSORS - CHASE - BLD 115 | ELLIOT, DENNIS K | CLOSED | 2012-03-26 | EL:INSTALL MOTION SENSORS IN CHASE HALL | 115 | CLOSED | 5251.0202 | 0 | 5425.884 | 5425.884
PJ0004115 | SP 12/13: INSTALL MOTION SENSORS - CHASE - BLD 115 | ELLIOT, DENNIS K | CLOSED | 2012-03-26 | IN: SP 11/12: INSTALL MOTION SENSORS - CHASE HALL BLD 115 | 115 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0004115 Total | [7 empty] | 5846.5462 | 0 | 5457.912 | 5457.912
PJ0004114 | SP 12/13: LED LIGHTING RETROFIT - ART GALLERY - BLD 34 RM 171 | ELLIOT, DENNIS K | CLOSED | 2012-03-26 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0004114 | SP 12/13: LED LIGHTING RETROFIT - ART GALLERY - BLD 34 RM 171 | ELLIOT, DENNIS K | CLOSED | 2012-03-26 | EL: MATERIALS, ONLY | 034 | CLOSED | 5566.596 | 0 | 5157.36 | 5157.36
PJ0004114 Total | [7 empty] | 5566.596 | 0 | 5157.36 | 5157.36
PJ0004113 | SP 11/12: IRRIGATION UPGRADE - TRACK BUILDING & SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-03-26 | AD: JOHN DEER LANDSCAPES, INC | 061 | CLOSED | 10469.4578 | 0 | 11228.4944 | 11228.4944
PJ0004113 | SP 11/12: IRRIGATION UPGRADE - TRACK BUILDING & SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-03-26 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004113 | SP 11/12: IRRIGATION UPGRADE - TRACK BUILDING & SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2012-03-26 | LA: IRRIGATION UPGRADE - TRACK BUILDING & SPANOS STADIUM (N/L) | 061 | CLOSED | 2207.124 | 0 | 0 | 0
PJ0004113 Total | [7 empty] | 12676.5818 | 0 | 11228.4944 | 11228.4944
PJ0004112 | REFINISH MAPLE STAGE FLOOR - BLD 06 | LAMPMAN, GREG | CLOSED | 2012-03-21 | AD: JOC 11.023.029 STAPLES | 006 | CLOSED | 14537.2019 | 0 | 14537.2019 | 14537.2019
PJ0004112 | REFINISH MAPLE STAGE FLOOR - BLD 06 | LAMPMAN, GREG | CLOSED | 2012-03-21 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1466.53 | 0 | 0 | 0
PJ0004112 | REFINISH MAPLE STAGE FLOOR - BLD 06 | LAMPMAN, GREG | CLOSED | 2012-03-21 | IN: REFINISH MAPLE STAGE FLOOR - BLD 06 | 006 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004112 Total | [7 empty] | 16131.8439 | 0 | 14665.3139 | 14665.3139
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | CA: CONSTRUCTION SUPPORT & REPOUR OF CONCRETE SLAB - TENAYA | 110 | CLOSED | 1139.8 | 0 | 1527.4203 | 1527.4203
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 0 | 0 | 0 | 0
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | EL:INSTALL IRRIGATION CONTROLLER AT TENAYA | 110 | CLOSED | 337.08 | 0 | 382.97 | 382.97
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | EO: SUPPORT IRRIGATION UPGRADE AT TENAYA | 110 | CLOSED | 2488.2 | 0 | 5709.615 | 5709.615
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | IN: IRRIGATION UPGRADE MAINTENANCE PROJECT - TENEYA 110 | 110 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | ITS: IRRIGATION UPGRADE MAINTENANCE PROJECT - TENEYA 110 (MAINT) | RESIDENCE | CLOSED | 0 | 0 | 446.15 | 446.15
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | LA:INSTALL NEW IRRIGATION SYSTEM | RESIDENCE | CLOSED | 29482 | 0 | 11930.6023 | 11930.6023
PJ0004111 | IRRIGATION UPGRADE MAINTENANCE PROJECT - TENAYA 110 (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-03-21 | PL:INSTALL NEW VALVES FOR IRRIGATION SYSTEM | RESIDENCE | CLOSED | 2421.7891 | 0 | 13882.205 | 13882.205
PJ0004111 Total | [7 empty] | 35975.6291 | 0 | 33985.7226 | 33985.7226
PJ0004108 | POWER WASH BREEZEWAY - BLDG 03 | GALVEZ, CESAR | CLOSED | 2012-03-15 | AD: COASTAL JANITORIAL | 003 | CLOSED | 831.39 | 0 | 831.39 | 831.39
PJ0004108 | POWER WASH BREEZEWAY - BLDG 03 | GALVEZ, CESAR | CLOSED | 2012-03-15 | CA: TEMP REMOVE GREEN BULLETIN BOARD FROM WALL & PLACE IN RM401 | 003 | CLOSED | 84.582 | 0 | 28.194 | 28.194
PJ0004108 | POWER WASH BREEZEWAY - BLDG 03 | GALVEZ, CESAR | CLOSED | 2012-03-15 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 91.6 | 0 | 0 | 0
PJ0004108 Total | [7 empty] | 1007.572 | 0 | 859.584 | 859.584
PJ0004107 | REPAIR VANDALISM DAMAGE - EDU 02 MRR 202 (UPD # 12-0354) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-14 | CA:REPAIR VANDALISM DAMAGE AT EDUCATION MEN'S RR 202 | 002 | CLOSED | 0 | 0 | 283.44 | 283.44
PJ0004107 | REPAIR VANDALISM DAMAGE - EDU 02 MRR 202 (UPD # 12-0354) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-14 | CP: PROJECT CONTINGENCY (UPD CASE # 12-0354) | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0004107 | REPAIR VANDALISM DAMAGE - EDU 02 MRR 202 (UPD # 12-0354) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-14 | EL:REPAIR VANDALISM AT EDUCATION 02 ROOM 202 - MEN'S RR | 002 | CLOSED | 0 | 0 | 168.54 | 168.54
PJ0004107 | REPAIR VANDALISM DAMAGE - EDU 02 MRR 202 (UPD # 12-0354) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-14 | PA:PATCH, PREP, AND PAINT AREA OF VANDALISM AT EDUCATION 202 | 002 | CLOSED | 0 | 0 | 296.82 | 296.82
PJ0004107 Total | [7 empty] | 0 | 0 | 748.8 | 748.8
PJ0004102 | MAINTENANCE INSPECTION (MAINTENANCE WALK-THRU) 1-17-12 - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2012-03-12 | CA:COMPLETE PAC FACILITY MAINTENANCE | 006 | CLOSED | 0 | 0 | 328.93 | 328.93
PJ0004102 | MAINTENANCE INSPECTION (MAINTENANCE WALK-THRU) 1-17-12 - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2012-03-12 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0004102 | MAINTENANCE INSPECTION (MAINTENANCE WALK-THRU) 1-17-12 - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2012-03-12 | LO:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 193.48 | 193.48
PJ0004102 | MAINTENANCE INSPECTION (MAINTENANCE WALK-THRU) 1-17-12 - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2012-03-12 | PA:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 24.735 | 24.735
PJ0004102 | MAINTENANCE INSPECTION (MAINTENANCE WALK-THRU) 1-17-12 - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2012-03-12 | PL:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 163.23 | 163.23
PJ0004102 Total | [7 empty] | 0 | 0 | 710.375 | 710.375
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CA: INSTALL OCOB BANENRS AT ONEILL LAWN | 003 | CLOSED | 225.552 | 0 | 385.602 | 385.602
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CA: SETUP THE NORTH, SOUTH AND EAST BLEACHERS AT MOTT GYM | 061 | CLOSED | 187.96 | 0 | 634.365 | 634.365
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CA: SUPPORT FOR 2012 SPRING COMMENCEMENT - JUNE 9&10 | 061 | CLOSED | 0 | 0 | 6153.36 | 6153.36
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CA: UNBOLT BIKE RACKS ALONG CHAIN LINK FENCE AT SPANOS ST. | 061 | CLOSED | 46.99 | 0 | 117.475 | 117.475
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CA:UNBOLT BIKE RACKS AT LEFT SIDE LIBRARY | 061 | CLOSED | 93.98 | 0 | 164.465 | 164.465
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CP: SUPPORT FOR 2012 SPRING COMMENCEMENT - JUN9 & 10 | 061 | CLOSED | 0 | 0 | 463.2 | 463.2
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CU: 2012 SPRING COMMENCEMENT SUPPORT | 061 | CLOSED | 0 | 0 | 9492.8492 | 9492.8492
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | CU: CLEANUP SPANOS STADIUM FOR COMMENCEMENT - JUNE 2 | 061 | CLOSED | 0 | 0 | 2934.565 | 2934.565
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | EL: SUPPORT FOR 2012 SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 893.42 | 893.42
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | EO: SUPPORT FOR 2012 SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 295.76 | 295.76
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | ES: STEEL ROD MODIFICATION - 2012 SPRING COMMENCEMENT | 061 | CLOSED | 416.24 | 0 | 104.06 | 104.06
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | ES: SUPPORT FOR 2012 SPRING COMMENCEMENT | 061 | CLOSED | 52.03 | 0 | 52.03 | 52.03
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | LA: SUPPORT FOR 2012 SPRING COMMENCEMENT-JUNE 9-10 | 061 | CLOSED | 0 | 0 | 12987.0305 | 12987.0305
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | MC: 2012 SPRING COMMENCEMENT SUPPORT | 061 | CLOSED | 0 | 0 | 955.7 | 955.7
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | PA: SUPPORT FOR 2012 SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 148.41 | 148.41
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | PL: SUPPORT FOR 2012 SPRING COMMENCEMENT | 061 | CLOSED | 0 | 0 | 1046.92 | 1046.92
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: AGB POST COMMENCEMENT - 6/8 | 010 | CLOSED | 0 | 0 | 125 | 125
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: CE/ENVE POST COMMENCEMENT - JUNE 10 | 061 | CLOSED | 0 | 0 | 34 | 34
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: CSC POST COMMENCEMENT CEREMONT - 6/9 | 061 | CLOSED | 0 | 0 | 35.5 | 35.5
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: EE SPRING COMMENCEMENT - JUNE 10 | 061 | CLOSED | 0 | 0 | 45.5 | 45.5
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: FSN POST COMMENCEMENT - JUNE 9 | 061 | CLOSED | 0 | 0 | 56 | 56
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: GRAPHIC COMM POST COMMENCEMENT-JUNE 9 | 061 | CLOSED | 0 | 0 | 50 | 50
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: JOURNALISM COMMENCEMENT - JUNE 9 | 061 | CLOSED | 0 | 0 | 28.5 | 28.5
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: MAT ENGR POST COMMENCEMENT-6/10 | 061 | CLOSED | 0 | 0 | 50 | 50
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: ME POST COMMENCEMENT - JUNE 10 | 061 | CLOSED | 0 | 0 | 50 | 50
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: OCOB POST COMMENCEMENT | 061 | CLOSED | 0 | 0 | 124 | 124
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: SOC SCIENCES POST COMMENCEMENT-JUNE 9 | 061 | CLOSED | 0 | 0 | 41 | 41
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL: WINE & VIT POST COMMENCEMENT- JUNE 9 | 061 | CLOSED | 0 | 0 | 71 | 71
PJ0004101 | 2012 SPRING COMMENCEMENT - JUNE 9 & 10, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-03-08 | SUPPLY RENTAL:RPTA POST COMMENCEMENT - JUNE 9 | 061 | CLOSED | 0 | 0 | 22.5 | 22.5
PJ0004101 Total | [7 empty] | 1022.752 | 0 | 37562.2117 | 37562.2117
PJ0004098 | MJ: INVESTIGATION FOR FIRE SPRINKLERS - SO. MTN. RESIDENCE HALLS | UYTTEWAAL, JOHAN M | CLOSED | 2012-03-08 | AD: FLUID RESOURCE MGT. - ASSIST PLUMBERS | RESIDENCE | CLOSED | 0 | 0 | 1926 | 1926
PJ0004098 | MJ: INVESTIGATION FOR FIRE SPRINKLERS - SO. MTN. RESIDENCE HALLS | UYTTEWAAL, JOHAN M | CLOSED | 2012-03-08 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0004098 | MJ: INVESTIGATION FOR FIRE SPRINKLERS - SO. MTN. RESIDENCE HALLS | UYTTEWAAL, JOHAN M | CLOSED | 2012-03-08 | PL: HYDRANT FLOW & PRESSURE READINGS - SO. MTN. RESIDENCE HALLS | RESIDENCE | CLOSED | 5000 | 0 | 950.904 | 950.904
PJ0004098 Total | [7 empty] | 5000 | 0 | 2876.904 | 2876.904
PJ0004097 | REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B (MAINT) | MAY, TOM | CLOSED | 2012-03-06 | CA: CAULK NORTH WINDOW UNDER RED METAL PITCHED ROOF - BLDG 47 | 047 | CLOSED | 187.96 | 0 | 180.965 | 180.965
PJ0004097 | REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B (MAINT) | MAY, TOM | CLOSED | 2012-03-06 | CA: REMOVE/REPLACE DAMAGED SHEETROCK FON 47-24B | 047 | CLOSED | 0 | 0 | 1812.115 | 1812.115
PJ0004097 | REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B (MAINT) | MAY, TOM | CLOSED | 2012-03-06 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0004097 | REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B (MAINT) | MAY, TOM | CLOSED | 2012-03-06 | ES: REMOVE WALL-HUNG HEATING UNIT- REINSTALL LATER - FON 47-24B | 047 | CLOSED | 0 | 0 | 1110.7794 | 1110.7794
PJ0004097 | REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B (MAINT) | MAY, TOM | CLOSED | 2012-03-06 | IN: REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B | 047 | CLOSED | 0 | 0 | 80.07 | 80.07
PJ0004097 | REPAIR WATER DAMAGE NEAR WINDOW - BLD 47 RM 24B (MAINT) | MAY, TOM | CLOSED | 2012-03-06 | PA:PRESSURE WASH AND PAINT ELASTOMERIC ON THE OUTSIDE OF 47-24B | 047 | CLOSED | 0 | 0 | 618.375 | 618.375
PJ0004097 Total | [7 empty] | 187.96 | 0 | 3802.3044 | 3802.3044
PJ0004096 | REPLACE ELECTRIC WATER HEATER - BLD 15 MRR 113 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-05 | CA:PROVIDE WATER LEAK REMEDIATION AT CORPORATION 15 | 015 | CLOSED | 0 | 0 | 225.552 | 225.552
PJ0004096 | REPLACE ELECTRIC WATER HEATER - BLD 15 MRR 113 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-05 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 0 | 0 | 0 | 0
PJ0004096 | REPLACE ELECTRIC WATER HEATER - BLD 15 MRR 113 (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2012-03-05 | PL: PROVIDE LEAK REMEDIATION AT CORPORATION 15 - 113 | 015 | CLOSED | 0 | 0 | 287.676 | 287.676
PJ0004096 Total | [7 empty] | 0 | 0 | 513.228 | 513.228
PJ0004095 | SR 11/12: CONSTRUCTION PHASE FOR NEW RAIL CAR - GILARDI BRIDGE | LAMPMAN, GREG | CLOSED | 2012-03-02 | AD: EARTH SYSTEMS | GENERAL | CLOSED | 9668.4 | 0 | 4403.46 | 4403.46
PJ0004095 | SR 11/12: CONSTRUCTION PHASE FOR NEW RAIL CAR - GILARDI BRIDGE | LAMPMAN, GREG | CLOSED | 2012-03-02 | AD: JOC 11.023.010.01 STAPLES | GENERAL | CLOSED | 297970.22 | 0 | 293007.53 | 293007.53
PJ0004095 | SR 11/12: CONSTRUCTION PHASE FOR NEW RAIL CAR - GILARDI BRIDGE | LAMPMAN, GREG | CLOSED | 2012-03-02 | AD: JOC 12.024.038 | GENERAL | CLOSED | 9853.92 | 0 | 9853.92 | 9853.92
PJ0004095 | SR 11/12: CONSTRUCTION PHASE FOR NEW RAIL CAR - GILARDI BRIDGE | LAMPMAN, GREG | CLOSED | 2012-03-02 | AD: SWCA | GENERAL | CLOSED | 49000 | 0 | 22394.54 | 22394.54
PJ0004095 | SR 11/12: CONSTRUCTION PHASE FOR NEW RAIL CAR - GILARDI BRIDGE | LAMPMAN, GREG | CLOSED | 2012-03-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004095 Total | [7 empty] | 366492.54 | 0 | 329659.45 | 329659.45
PJ0004094 | SR 11/12: DESIGN ADA COMPLIANT RESTOOMS - BLD 14 RMS 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2012-03-02 | AD: REA AND LUKER ARCHITECTS | 014 | CLOSED | 5360 | 0 | 4916.81 | 4916.81
PJ0004094 | SR 11/12: DESIGN ADA COMPLIANT RESTOOMS - BLD 14 RMS 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2012-03-02 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0004094 Total | [7 empty] | 5360 | 0 | 4916.81 | 4916.81
PJ0004092 | LOCATE UTILITIES AND SUPPORT GRADING (NO ESTIMATE) - BLD 57 | GALVEZ, CESAR | CLOSED | 2012-03-02 | CP: PROJECT CONTINGENCY | 057 | CLOSED | 0 | 0 | 0 | 0
PJ0004092 | LOCATE UTILITIES AND SUPPORT GRADING (NO ESTIMATE) - BLD 57 | GALVEZ, CESAR | CLOSED | 2012-03-02 | EL: LOCATE UTILITIES AND SUPPORT RE-GRADING AT VET CLINIC - 057 | 057 | CLOSED | 0 | 0 | 337.08 | 337.08
PJ0004092 | LOCATE UTILITIES AND SUPPORT GRADING (NO ESTIMATE) - BLD 57 | GALVEZ, CESAR | CLOSED | 2012-03-02 | IN: LOCATE UTILITIES AND SUPPORT GRADING - BLD 57 | 057 | CLOSED | 0 | 0 | 96.084 | 96.084
PJ0004092 | LOCATE UTILITIES AND SUPPORT GRADING (NO ESTIMATE) - BLD 57 | GALVEZ, CESAR | CLOSED | 2012-03-02 | PL: LOCATE UTILITIES AND SUPPORT RE-GRADING AT VET CLINIC - 057 | 057 | CLOSED | 0 | 0 | 65.292 | 65.292
PJ0004092 Total | [7 empty] | 0 | 0 | 498.456 | 498.456
PJ0004090 | INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-02-29 | CA:DEMO WING WALLS INSTALL DISPLAY BRACKETS | 003 | CLOSED | 1924.416 | 0 | 3574.974 | 3574.974
PJ0004090 | INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-02-29 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 416.95 | 0 | 0 | 0
PJ0004090 | INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-02-29 | CU:03-112 CLEAN UP AFTER PROJECT | 003 | CLOSED | 65.592 | 0 | 49.194 | 49.194
PJ0004090 | INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-02-29 | EL:ADD OUTLET INSTALL CONDUIT | 003 | CLOSED | 720.0024 | 0 | 581.196 | 581.196
PJ0004090 | INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-02-29 | IN: INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | 003 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0004090 | INSTALL TWO (2) SCREEN DISPLAYS - BLD 3 RM 112 | BRENNAN, MICHAEL | CLOSED | 2012-02-29 | PA:DRYWALL REPAIRS AND PAINT | 003 | CLOSED | 1427.28 | 0 | 834.108 | 834.108
PJ0004090 Total | [7 empty] | 4586.2684 | 0 | 5071.5 | 5071.5
PJ0004089 | INSTALL MEMORIAL BENCH AT O'NEIL GREEN - BLD 003 (NO EST) | GALVEZ, CESAR | CLOSED | 2012-03-01 | CA: INSTALL PLAQUE ON MEMORIAL BENCH @ O'NEEL GREEN | GENERAL | CLOSED | 84.582 | 0 | 1477.122 | 1477.122
PJ0004089 | INSTALL MEMORIAL BENCH AT O'NEIL GREEN - BLD 003 (NO EST) | GALVEZ, CESAR | CLOSED | 2012-03-01 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0004089 | INSTALL MEMORIAL BENCH AT O'NEIL GREEN - BLD 003 (NO EST) | GALVEZ, CESAR | CLOSED | 2012-03-01 | IN: INSTALL MEMORIAL BENCH AT O'NEIL GREEN - BLD 003 | GENERAL | CLOSED | 0 | 0 | 32.028 | 32.028
PJ0004089 | INSTALL MEMORIAL BENCH AT O'NEIL GREEN - BLD 003 (NO EST) | GALVEZ, CESAR | CLOSED | 2012-03-01 | LA: MEMORIAL BENCH INSTALLATION @ O'NEIL GREEN | GENERAL | CLOSED | 0 | 0 | 176.976 | 176.976
PJ0004089 Total | [7 empty] | 84.582 | 0 | 1686.126 | 1686.126
PJ0004088 | ANTENNA TOWER - BLD 20 IN FRONT OF RM 123 | LAMPMAN, GREG | CLOSED | 2012-03-01 | AD: EARTH SYSTEMS | 020 | CLOSED | 1086.692 | 0 | 280.5326 | 280.5326
PJ0004088 | ANTENNA TOWER - BLD 20 IN FRONT OF RM 123 | LAMPMAN, GREG | CLOSED | 2012-03-01 | AD: ENGLEKIRK & SABOL - STRUCTURAL REVIEW | 020 | CLOSED | 535 | 0 | 535 | 535
PJ0004088 | ANTENNA TOWER - BLD 20 IN FRONT OF RM 123 | LAMPMAN, GREG | CLOSED | 2012-03-01 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 66.31 | 0 | 0 | 0
PJ0004088 | ANTENNA TOWER - BLD 20 IN FRONT OF RM 123 | LAMPMAN, GREG | CLOSED | 2012-03-01 | EL: INSTALL POWER TO TOWER WINCH MOTOR - BLDG 20 NEAR RM 123 | 020 | CLOSED | 840.0024 | 0 | 883.404 | 883.404
PJ0004088 | ANTENNA TOWER - BLD 20 IN FRONT OF RM 123 | LAMPMAN, GREG | CLOSED | 2012-03-01 | IN: ANTENNA TOWER - BLD 20 IN FRONT OF RM 123 | 020 | CLOSED | 256.224 | 0 | 256.224 | 256.224
PJ0004088 Total | [7 empty] | 2784.2284 | 0 | 1955.1606 | 1955.1606
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | AD: J.L. FASULO DRYWALL | 042 | CLOSED | 1284 | 0 | 1284 | 1284
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | AD: PARC ENVIRONMENTAL | 042 | CLOSED | 3745 | 0 | 4387 | 4387
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 797 | 0 | 0 | 0
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | EH&S: REMOVE WALLS MENS BASKETBALL LOCKER RM ENTRY - 42-113(N/L) | 042 | CLOSED | 308.7 | 0 | 0 | 0
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | EL: BASKETBALL LOCKER ROOM RENOVATION | 042 | CLOSED | 1140.0036 | 0 | 1450.692 | 1450.692
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | IN:REMOVE WALLS MENS BASKETBALL LOCKER RM ENTRANCE - BLDG 42-113 | 042 | CLOSED | 64.056 | 0 | 96.084 | 96.084
PJ0004087 | REMOVE WALLS MENS BASKETBALL LOCKER ROOM ENTRANCE - BLDG 42-113 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | PA:PATCH AND PAINT AFTER WALL REMOVAL AT MEN'S LOCKER ROOM | 042 | CLOSED | 1057.2728 | 0 | 593.64 | 593.64
PJ0004087 Total | [7 empty] | 8396.0324 | 0 | 7811.416 | 7811.416
PJ0004086 | PROPOSED STAND ALONE MEZZANINE STORAGE - BLD 21 RM 13 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | AD: ENGLEKIRK AND SABOL | 021 | CLOSED | 535 | 0 | 535 | 535
PJ0004086 | PROPOSED STAND ALONE MEZZANINE STORAGE - BLD 21 RM 13 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 408.88 | 0 | 0 | 0
PJ0004086 | PROPOSED STAND ALONE MEZZANINE STORAGE - BLD 21 RM 13 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | IN: PROPOSED STAND ALONE MEZZANINE STORAGE - BLD 21 RM 13 | 021 | CLOSED | 256.224 | 0 | 224.196 | 224.196
PJ0004086 | PROPOSED STAND ALONE MEZZANINE STORAGE - BLD 21 RM 13 | MOLLAN, CHERYL L. | CLOSED | 2012-02-28 | PL: REMOVE SINK & PIPING TO SINK & CAPP-OFF. 021 ENG WEST RM 13 | 021 | CLOSED | 2300.0999 | 0 | 1689.9958 | 1689.9958
PJ0004086 Total | [7 empty] | 3500.2039 | 0 | 2449.1918 | 2449.1918
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | AD: JOC 11.023.034 STAPLES | 113 | CLOSED | 181848.4581 | 0 | 181848.4581 | 181848.4581
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | AD: THOMA ELECTRIC | 113 | CLOSED | 7383 | 0 | 7383 | 7383
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | ANTS:PROGRAM FIRE ALARMS | 113 | CLOSED | 2138.6165 | 0 | 312.312 | 312.312
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 15075.67 | 0 | 0 | 0
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | EL: SUPPORT FOR SIERRA MADRE FIRE ALARMS PROJECT | 113 | CLOSED | 7202.0465 | 0 | 472.812 | 472.812
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | ES: SUPPORT FOR SIERRA MADRE FIRE ALARMS PROJECT (LEAKS) | 113 | CLOSED | 624.36 | 0 | 31.218 | 31.218
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | IN: ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | 113 | CLOSED | 2851.1326 | 0 | 2145.876 | 2145.876
PJ0004083 | ADDRESSABLE FIRE ALARMS SIERRA MADRE - BLD 113 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | PA: SUPPORT FOR SIERRA MADRE FIRE ALARMS PROJECT (N/L) | 113 | CLOSED | 7321.4426 | 0 | 60 | 60
PJ0004083 Total | [7 empty] | 224444.7263 | 0 | 192253.6761 | 192253.6761
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | AD: JOC 11.023.035 STAPLES | 114 | CLOSED | 209623.2934 | 0 | 209623.3148 | 209623.3148
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | AD: THOMA ELECTRIC | 114 | CLOSED | 7383 | 0 | 7383 | 7383
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | ANTS:PROGRAM FIRE ALARMS | 114 | CLOSED | 2138.6165 | 0 | 2306.304 | 2306.304
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 4100.17 | 0 | 0 | 0
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | EL:SUPPORT FOR FIRE ALARMS | 114 | CLOSED | 7202.0465 | 0 | 1070.652 | 1070.652
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | IN: ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | 114 | CLOSED | 2851.1326 | 0 | 2145.876 | 2145.876
PJ0004082 | ADDRESSABLE FIRE ALARMS YOSEMITE - BLD 114 | BRENNAN, MICHAEL | CLOSED | 2012-02-27 | PA:SUPPORT/MATERIALS FOR FIRE ALARMS (N/L) | 114 | CLOSED | 8642.2916 | 0 | 60 | 60
PJ0004082 Total | [7 empty] | 241940.5506 | 0 | 222589.1468 | 222589.1468
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | AD: (SP) BOB'S CRANE SERVICE | 024 | CLOSED | 588.5 | 0 | 588.5 | 588.5
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | AD: (SP) STAPLES (LOW VALUE PUBLIC WORKS) | 024 | CLOSED | 2338.3459 | 0 | 2338.3459 | 2338.3459
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | AD: JOC 11.023.007 STAPLES | 024 | CLOSED | 57766.732 | 0 | 35615.9023 | 35615.9023
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | CA: CORE DRILLING FOR ELECTRICAL - BLDG 24 ROOM 106 | 024 | CLOSED | 451.104 | 0 | 507.492 | 507.492
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 20842.01 | 0 | 0 | 0
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | EL: SUPPLY ELECTRICAL | 024 | CLOSED | 208674.6718 | 0 | 194335.8271 | 194335.8271
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | EO: ASSIST ELECTRIC SHOP WITH 480V UPGRADE AT BLDG. 24 | 024 | CLOSED | 199.056 | 0 | 49.764 | 49.764
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | IN: 480V ELECTRICAL UPGRADE FOR NEW EQUIPMENT - BLDG 24-106 | 024 | CLOSED | 960.84 | 0 | 704.616 | 704.616
PJ0004081 | 480V ELECTRICAL UPGRADE FOR NEW EQUIP. - 24-106 (SEE PJ 3706) | LAMPMAN, GREG | CLOSED | 2012-02-27 | PL: CONTRACTOR SUPPORT FOR BLDG 24 ELECTRICAL UPGRADE PROJECT | 024 | CLOSED | 1305.84 | 0 | 261.168 | 261.168
PJ0004081 Total | [7 empty] | 293127.0997 | 0 | 234401.6153 | 234401.6153
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | CA: INSTALLATION OF BANNERS AT O'NEILL LAWN - APR 13 | 003 | CLOSED | 0 | 0 | 60.816 | 60.816
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | CA: SUPPORT FOR 2012 OPEN HOUSE - APR 14 | GENERAL | CLOSED | 0 | 0 | 2533.58 | 2533.58
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | CP: OPEN HOUSE SUPPORT 2012 | GENERAL | CLOSED | 0 | 0 | 492.15 | 492.15
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | CU: SUPPORT FOR 2012 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 4692.185 | 4692.185
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | EL: SUPPORT FOR 2012 OPEN HOUSE - APR 14 | GENERAL | CLOSED | 0 | 0 | 2048.28 | 2048.28
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | EO: CLEANUP OF POLY CANYON VILLAGE (TRASH) | 095 | CLOSED | 0 | 0 | 415.476 | 415.476
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | GR: SUPPORT FOR DESIGN VILLAGE CLEAN UP | 095 | CLOSED | 0 | 0 | 116.892 | 116.892
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | LA: SUPPORT FOR 2012 OPEN HOUSE - APRIL 14 | GENERAL | CLOSED | 0 | 0 | 4542.212 | 4542.212
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | MC: ASSIST WITH OPEN HOUSE - APR 12, 13, ETC | GENERAL | CLOSED | 0 | 0 | 160.96 | 160.96
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | PL: SUPPORT FOR 2012 OPEN HOUSE - APRIL 14 | GENERAL | CLOSED | 0 | 0 | 1209.725 | 1209.725
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | RC: CLEAN UP OF 2012 DESIGN VILALGE COMPETITION | 095 | CLOSED | 0 | 0 | 211.2 | 211.2
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | RE: ASSIST WITH OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 777.18 | 777.18
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: AERO OPEN HOUSE - APR 12 | 041 | CLOSED | 0 | 0 | 40 | 40
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: AG RODEO - APR 12 | GENERAL | CLOSED | 0 | 0 | 77 | 77
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: BMED/CENV/ME ADMITTED STUDENTS DAY 0- APR 13 | 007 | CLOSED | 0 | 0 | 41 | 41
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: CAFES OPEN HOUSE - APR 12 | GENERAL | CLOSED | 0 | 0 | 125 | 125
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: CSC OPEN HOUSE - APR 13 | GENERAL | CLOSED | 0 | 0 | 48 | 48
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: DESIGN VILLAGE 2012 - APR 14 | GENERAL | CLOSED | 0 | 0 | 43 | 43
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: OCOB OPEN HOUSE - APR 13 | GENERAL | CLOSED | 0 | 0 | 150 | 150
PJ0004079 | SUPPORT FOR 2012 OPEN HOUSE - APRIL 14, 2012 (MAINT) | POPHAM, DONALD J. | CLOSED | 2012-02-21 | SUPPLY RENTAL: OPEN HOUSE EE DEPT - APR 12 | GENERAL | CLOSED | 0 | 0 | 43 | 43
PJ0004079 Total | [7 empty] | 0 | 0 | 17827.656 | 17827.656
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | ANTS: PROGRAM AND TEST FOR FIRE PANEL INSTALLATION - UPD 036 | 036 | CLOSED | 0 | 0 | 216.216 | 216.216
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | ANTS: PROGRAMMING FOR SECURITY ALARM AT UPD BLDG. 36 | 036 | CLOSED | 0 | 0 | 48.048 | 48.048
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | CA: INFILL WALL THAT SEPARATES RESTROOMS FROM OFFICES - UPD 036 | 036 | CLOSED | 0 | 0 | 473.892 | 473.892
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | CA: INSTALL 5 BOLLARDS AT GENERATOR/PROPANE TANK AT UPD - 036 | 036 | CLOSED | 0 | 0 | 683.0801 | 683.0801
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | CA: INSTALL PAPER TOWEL DISPENSERS IN RESTRMS - 036 UPD REMODEL | 036 | CLOSED | 0 | 0 | 288.78 | 288.78
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 4724.84 | 0 | 0 | 0
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | EL: PROVIDE WHOLE BUILDING GROUNDING FOR BLDG 36 - UPD RENO PJ | 036 | CLOSED | 0 | 0 | 1754.94 | 1754.94
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | EL: SUPPLY TEMP POWER FOR NEW UPD OFFICE PROJECT - BLDG. 36 | 036 | CLOSED | 0 | 0 | 2645.328 | 2645.328
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | EO: DRILL HOLES FOR BOLLARDS AT UPD GENERATOR/PROPANE TANK - 036 | 036 | CLOSED | 0 | 0 | 887.28 | 887.28
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | LO: LOCKS FOR UPD REMODEL | 036 | CLOSED | 0 | 0 | 327.75 | 327.75
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | LO: REPAIR LOCK ON EVIDENCE ROOM - UPD - BLDG. 36 | 036 | CLOSED | 0 | 0 | 145.11 | 145.11
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | PA: GYP-BOARD FINISH & PAINT FOR WALL BETWEEN RR & OFFICES - UPD | 036 | CLOSED | 0 | 0 | 1668.828 | 1668.828
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | PL: SUPPLY STEEL PIPE FOR BOLLARDS AT UPD - 036 (N/L) | 036 | CLOSED | 0 | 0 | 416.22 | 416.22
PJ0004078 | MJ: IN-HOUSE SUPPORT FOR RENOVATION FOR UPD OFFICES - BLD 36 | NEEL, JOEL | CLOSED | 2012-02-21 | PL: VIDEO EXPLORATION OF SEWER - UPD REMODEL BLDG 36 | 036 | CLOSED | 0 | 0 | 522.336 | 522.336
PJ0004078 Total | [7 empty] | 4724.84 | 0 | 10077.8081 | 10077.8081
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | AD: DAHL INSULATION | 114A | CLOSED | 0 | 0 | 950 | 950
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | AD: KNECHT'S | 114A | CLOSED | 0 | 0 | 1896.04 | 1896.04
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | CA: SUPPLY AND PLACE BARRICADES AROUND CONDENSATE LEAK - YOS T0 | 114A | CLOSED | 0 | 0 | 117.475 | 117.475
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | CP: PROJECT CONTINGENCY | 114A | CLOSED | 0 | 0 | 0 | 0
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | EO: SUPPORT FOR CONDENSATE LINE LEAK AT YOSEMITE TOWER 0 | 114A | CLOSED | 0 | 0 | 1156.04 | 1156.04
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | ES: REPLACE LEAKING CONDENSATE LINE AT YOSEMITE TOWER 0 | 114A | CLOSED | 0 | 0 | 1370.19 | 1370.19
PJ0004076 | REPLACE LEAKING CONDENSATE LINE - YOS T0 (NO ESTIMATE) | MAY, TOM | CLOSED | 2012-02-16 | LA: SUPPORT FOR CONDENSATE LINE LEAK AT YOSEMITE TOWER 0 | 114A | CLOSED | 0 | 0 | 97.41 | 97.41
PJ0004076 Total | [7 empty] | 0 | 0 | 5587.155 | 5587.155
PJ0004075 | SR 11/12: REPLACE TRANSPORTATION FURNACE - BLD 71 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-16 | CP: PROJECT CONTINGENCY | 071 | CLOSED | 0 | 0 | 0 | 0
PJ0004075 | SR 11/12: REPLACE TRANSPORTATION FURNACE - BLD 71 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-16 | ES: REPLACE TRANSPORTATION FURNACE (ABOVE OFFICES) - BLD 71 | 071 | CLOSED | 5861.65 | 0 | 6431.3814 | 6431.3814
PJ0004075 | SR 11/12: REPLACE TRANSPORTATION FURNACE - BLD 71 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-16 | PL: EXTEND GAS PIPE FOR TRANSPORTATION FURNACE REPLACEMENT | 071 | CLOSED | 260.15 | 0 | 301.4916 | 301.4916
PJ0004075 Total | [7 empty] | 6121.8 | 0 | 6732.873 | 6732.873
PJ0004074 | INSTALL POLYCARD SYSTEM FOR GRAD STUDY RMS -LIBRARY 35-301 & 401 | BRENNAN, MICHAEL | CLOSED | 2012-02-15 | AD: CAME SECURITY | 035 | CLOSED | 12171.25 | 0 | 12171.25 | 12171.25
PJ0004074 | INSTALL POLYCARD SYSTEM FOR GRAD STUDY RMS -LIBRARY 35-301 & 401 | BRENNAN, MICHAEL | CLOSED | 2012-02-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1148.72 | 0 | 0 | 0
PJ0004074 | INSTALL POLYCARD SYSTEM FOR GRAD STUDY RMS -LIBRARY 35-301 & 401 | BRENNAN, MICHAEL | CLOSED | 2012-02-15 | EL:INSTALL CONDUIT AND POWER FOR LOCKS IN 35--301/401 | 035 | CLOSED | 570.3389 | 0 | 522.924 | 522.924
PJ0004074 | INSTALL POLYCARD SYSTEM FOR GRAD STUDY RMS -LIBRARY 35-301 & 401 | BRENNAN, MICHAEL | CLOSED | 2012-02-15 | IN: INSTALL POLYCARD SYSTEM IN GRAD STUDY RMS -LIB. 35-301 & 401 | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004074 | INSTALL POLYCARD SYSTEM FOR GRAD STUDY RMS -LIBRARY 35-301 & 401 | BRENNAN, MICHAEL | CLOSED | 2012-02-15 | LO:INSTALL ELECTRIC STRIKES IN 35-301/401 | 035 | CLOSED | 1356.5916 | 0 | 1831.368 | 1831.368
PJ0004074 Total | [7 empty] | 15310.9565 | 0 | 14589.598 | 14589.598
PJ0004073 | DISCONNECT MODULAR DESKS AND WIRING - BLD 14 RM 114 | MOLLAN, CHERYL L. | CLOSED | 2012-02-10 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0004073 | DISCONNECT MODULAR DESKS AND WIRING - BLD 14 RM 114 | MOLLAN, CHERYL L. | CLOSED | 2012-02-10 | EL: DISCONNECT ELECTRICAL FROM MODULAR DESKS - BLDG 14 - 114/115 | 014 | CLOSED | 539.328 | 0 | 134.832 | 134.832
PJ0004073 Total | [7 empty] | 539.328 | 0 | 134.832 | 134.832
PJ0004072 | CORRECT DRAINAGE ISSUE IN FRONT OF CIAO PIZZA DOOR - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2012-01-25 | AD: MAINO (LVPW) | 065 | CLOSED | 3691.5 | 0 | 3691.5 | 3691.5
PJ0004072 | CORRECT DRAINAGE ISSUE IN FRONT OF CIAO PIZZA DOOR - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2012-01-25 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0004072 | CORRECT DRAINAGE ISSUE IN FRONT OF CIAO PIZZA DOOR - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2012-01-25 | IN: CORRECT DRAINAGE IN FRONT OF CIAO PIZZA DOOR - BLSG 065 | 065 | CLOSED | 70.644 | 0 | 70.644 | 70.644
PJ0004072 | CORRECT DRAINAGE ISSUE IN FRONT OF CIAO PIZZA DOOR - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2012-01-25 | PA: TOUCH UP PAINT WHERE DOWNSPOUT WAS REMOVED - CIAO | 065 | CLOSED | 675.264 | 0 | 393.228 | 393.228
PJ0004072 | CORRECT DRAINAGE ISSUE IN FRONT OF CIAO PIZZA DOOR - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2012-01-25 | PM: CORRECT DRAINAGE ISSUE IN FRONT OF CIAO PIZZA DOOR-BLDG 065 | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0004072 Total | [7 empty] | 4437.408 | 0 | 4155.372 | 4155.372
PJ0004071 | INSTALL PANIC BUTTONS - BLD 11 RMS 240/241 | MAY, TOM | CLOSED | 2012-02-10 | ANTS: PROGRAM PANIC BUTTON ALARMS - BLDG 11 ROOMS 240 & 241 | 011 | CLOSED | 0 | 0 | 36.036 | 36.036
PJ0004071 | INSTALL PANIC BUTTONS - BLD 11 RMS 240/241 | MAY, TOM | CLOSED | 2012-02-10 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 31.71 | 0 | 0 | 0
PJ0004071 | INSTALL PANIC BUTTONS - BLD 11 RMS 240/241 | MAY, TOM | CLOSED | 2012-02-10 | EL:INSTALL RACEWAY AND OUTLET IN 11-242 | 011 | CLOSED | 285.1694 | 0 | 299.292 | 299.292
PJ0004071 | INSTALL PANIC BUTTONS - BLD 11 RMS 240/241 | MAY, TOM | CLOSED | 2012-02-10 | IN: INSTALL PANIC BUTTONS - BLD 11 RMS 240/241 | 011 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0004071 Total | [7 empty] | 348.9074 | 0 | 367.356 | 367.356
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | AD: GOLDING CONCRETE SAWING | 035 | CLOSED | 428 | 0 | 428 | 428
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | AD: JOC 11.023.043 STAPLES | 035 | CLOSED | 7417.882 | 0 | 7367.0998 | 7367.0998
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | CA:FORM AND POUR CONCRETE SIDEWALK AT LIBRARY NORTH SIDE | 035 | CLOSED | 2427.9767 | 0 | 2362.932 | 2362.932
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 671.52 | 0 | 0 | 0
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | EL:RELOCATE PLUGMOLD IN LIBRARY, ROOM 114C | 035 | CLOSED | 570.3389 | 0 | 1404.708 | 1404.708
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | EO:PREP FOR SIDEWALK NORTH SIDE OF LIBRARY | 035 | CLOSED | 199.056 | 0 | 493.404 | 493.404
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | IN: EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | LA:PREP FOR SIDEWALK ON NORTH SIDE OF LIBRARY (NO LABOR) | 035 | CLOSED | 173.3898 | 0 | 0 | 0
PJ0004069 | EMERGENCY EXIT CHANGES - LIBRARY 35 RM 111 & 114C | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | LO:CORE PREP FOR NEW EMERGENCY EXIT AT LIBRARY 114C | 035 | CLOSED | 142.4288 | 0 | 281.904 | 281.904
PJ0004069 Total | [7 empty] | 12094.6482 | 0 | 12402.1038 | 12402.1038
PJ0004067 | REPAIR WALLS & CEILING - SPANOS STADIUM LOCKER ROOM - BLD 61 | LAMPMAN, GREG | CLOSED | 2012-02-07 | AD: JOC 11.023.031 STAPLES | 061 | CLOSED | 3423.1761 | 0 | 3423.1761 | 3423.1761
PJ0004067 | REPAIR WALLS & CEILING - SPANOS STADIUM LOCKER ROOM - BLD 61 | LAMPMAN, GREG | CLOSED | 2012-02-07 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 252.6 | 0 | 0 | 0
PJ0004067 | REPAIR WALLS & CEILING - SPANOS STADIUM LOCKER ROOM - BLD 61 | LAMPMAN, GREG | CLOSED | 2012-02-07 | IN: REPAIR SPANOS STADIUM LOCKER ROOM - BLD 61 | 061 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004067 | REPAIR WALLS & CEILING - SPANOS STADIUM LOCKER ROOM - BLD 61 | LAMPMAN, GREG | CLOSED | 2012-02-07 | PA: PAINT FLOOR AND REPAIR WALL | 061 | CLOSED | 4724.04 | 0 | 2819.79 | 2819.79
PJ0004067 | REPAIR WALLS & CEILING - SPANOS STADIUM LOCKER ROOM - BLD 61 | LAMPMAN, GREG | CLOSED | 2012-02-07 | PL: REMOVE TOILETS AND RE-INSTALL AFTER FLOOR IS FINISHED | 061 | CLOSED | 772.92 | 0 | 1910.862 | 1910.862
PJ0004067 Total | [7 empty] | 9300.8481 | 0 | 8249.9121 | 8249.9121
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | AD: BELSON OUTDOORS - BENCH PURCHASE | 003 | CLOSED | 13060.46 | 0 | 13797.74 | 13797.74
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | AD: DORMAN HYDRO SEEDING | 003 | CLOSED | 904.15 | 0 | 904.15 | 904.15
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | AD: JOC 12.024.004 STAPLES | 003 | CLOSED | 110426.996 | 0 | 95549.3629 | 95549.3629
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | AD: OVERHEAD ON GORDIAN REFUND FOR JOC 12.024.004.01 | 003 | CLOSED | 0 | 0 | -8.57 | -8.57
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | CA: OCOB SEAT WALL | 003 | CLOSED | 1653.312 | 0 | 741.9661 | 741.9661
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 86.55 | 0 | 0 | 0
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | EL: PROVIDE ELEECTRICAL LIGHTING AND OUTLET IN SEATWALL | 003 | CLOSED | 6301.8862 | 0 | 6215.52 | 6215.52
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | IN: WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 CRTYD | 003 | CLOSED | 1024.896 | 0 | 992.868 | 992.868
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | LA:PROJECT SUPPORT FOR SEATWALLS | 003 | CLOSED | 20794.6757 | 0 | 10689.8406 | 10689.8406
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | MO: UNLOAD AND PLACE BENCHES IN BLDG 3 COURTYARD | 003 | CLOSED | 259.2 | 0 | 84.504 | 84.504
PJ0004066 | WIDEN WALKWAY, PROVIDE SEATING & GREEN WASTE MGT-BLD 3 COURTYARD | BRENNAN, MICHAEL | CLOSED | 2012-02-06 | PL-OCOB SEATWALL PROJECT | 003 | CLOSED | 11145.696 | 0 | 12607.6111 | 12607.6111
PJ0004066 Total | [7 empty] | 165657.8218 | 0 | 141574.9927 | 141574.9927
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | AD: PARC ENVIRONMENTAL | 065 | CLOSED | 2086.5 | 0 | 1979.5 | 1979.5
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | CA: DRINKING FOUNTAIN INSTALLATION SUPPORT - UU 065 | 065 | CLOSED | 3109.8299 | 0 | 2442.006 | 2442.006
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1378.06 | 0 | 0 | 0
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | EL: HYDRATION STATION INSTALLATION SUPPORT - UU 065 | 065 | CLOSED | 900.0036 | 0 | 272.043 | 272.043
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | IN: INSTALL 3 HYDRATION STATIONS - UU 65 | 065 | CLOSED | 142.8449 | 0 | 128.112 | 128.112
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | PA: UU HYDRATION STATIONS GYP BD FINISH AND WALL PAINT. | 065 | CLOSED | 528.3396 | 0 | 706.728 | 706.728
PJ0004065 | INSTALL 3 HYDRATION STATIONS - UU 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2012-02-02 | PL: INSTALL HYDRATION STATIONS - UU 065 | 065 | CLOSED | 7012.9468 | 0 | 4004.274 | 4004.274
PJ0004065 Total | [7 empty] | 15158.5247 | 0 | 9532.663 | 9532.663
PJ0004063 | ESTM DESIGN, ONLY, FOR 2ND FLR RENOVATION - UU 65 | MOLLAN, CHERYL L. | CLOSED | 2012-01-31 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0004063 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0004059 | PROVIDE ELECTRICAL FROM CHEDA TO NELSON RES & MIDDLECAMP PUMP | LAMPMAN, GREG | CLOSED | 2012-02-02 | CA: CONCRETE FOR OVERHEAD LINES FROM CHEDA ***5 HOLES*** | GENERAL | CLOSED | 525.552 | 0 | 597.168 | 597.168
PJ0004059 | PROVIDE ELECTRICAL FROM CHEDA TO NELSON RES & MIDDLECAMP PUMP | LAMPMAN, GREG | CLOSED | 2012-02-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2913.44 | 0 | 0 | 0
PJ0004059 | PROVIDE ELECTRICAL FROM CHEDA TO NELSON RES & MIDDLECAMP PUMP | LAMPMAN, GREG | CLOSED | 2012-02-02 | EL:INSTALL OVER HEAD LINES TO NELSON RES. | GENERAL | CLOSED | 33429.2465 | 0 | 37284.162 | 37284.162
PJ0004059 | PROVIDE ELECTRICAL FROM CHEDA TO NELSON RES & MIDDLECAMP PUMP | LAMPMAN, GREG | CLOSED | 2012-02-02 | IN: PROVIDE ELECTRICAL FRM CHEDA TO NELSON RES & MIDDLECAMP PUMP | GENERAL | CLOSED | 960.84 | 0 | 64.056 | 64.056
PJ0004059 Total | [7 empty] | 37829.0785 | 0 | 37945.386 | 37945.386
PJ0004058 | SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | BRENNAN, MICHAEL | CLOSED | 2012-02-02 | AD: JOC 11.023.023 STAPLES | 021 | CLOSED | 58066.23 | 0 | 58066.23 | 58066.23
PJ0004058 | SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | BRENNAN, MICHAEL | CLOSED | 2012-02-02 | AD: MECA | 021 | CLOSED | 16716.96 | 0 | 16637.97 | 16637.97
PJ0004058 | SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | BRENNAN, MICHAEL | CLOSED | 2012-02-02 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0004058 | SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | BRENNAN, MICHAEL | CLOSED | 2012-02-02 | EH&S: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 (N/L) | 021 | CLOSED | 916 | 0 | 6258 | 6258
PJ0004058 | SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | BRENNAN, MICHAEL | CLOSED | 2012-02-02 | ES:AIR HANDLER CLEANER | 021 | CLOSED | 1248.72 | 0 | 182.105 | 182.105
PJ0004058 | SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | BRENNAN, MICHAEL | CLOSED | 2012-02-02 | IN: SR 11/12: DUCT CLEANING & INSULATION ABATEMENT - BLDG 21 | 021 | CLOSED | 427.04 | 0 | 106.76 | 106.76
PJ0004058 Total | [7 empty] | 77374.95 | 0 | 81251.065 | 81251.065
PJ0004056 | REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | MAY, TOM | CLOSED | 2012-01-24 | CA:CUT LOOSE MARQUEE SIGNS AT CAMPUS MARKET AND 14 | GENERAL | CLOSED | 250.9266 | 0 | 212.94 | 212.94
PJ0004056 | REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | MAY, TOM | CLOSED | 2012-01-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2.7 | 0 | 0 | 0
PJ0004056 | REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | MAY, TOM | CLOSED | 2012-01-24 | EL:DISCONNECT ELECTRICAL TO MARQUEE SIGNS AT MARKET AND 14 | GENERAL | CLOSED | 1260.679 | 0 | 675.792 | 675.792
PJ0004056 | REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | MAY, TOM | CLOSED | 2012-01-24 | EO:ASSIST IN REMOVAL OF MARQUEES AT 14 AND CAMPUS MARKET | GENERAL | CLOSED | 0 | 0 | 592.932 | 592.932
PJ0004056 | REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | MAY, TOM | CLOSED | 2012-01-24 | IN: REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | GENERAL | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004056 | REMOVAL ASI MARQUEES AT CAMPUS MARKET & DEXTER LAWN | MAY, TOM | CLOSED | 2012-01-24 | LA: SUPPORT FOR ASI MARQUEE REMOVAL -CAMPUS MARKET & DEXTER LAWN | GENERAL | CLOSED | 170.892 | 0 | 97.41 | 97.41
PJ0004056 Total | [7 empty] | 1749.2536 | 0 | 1643.13 | 1643.13
PJ0004054 | INSTALL EQUIPMENT FOR SMART ROOM - BLD 34 RM 149 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-01-24 | CA:SMART ROOM- BLDG 34, ROOM 149 | 034 | CLOSED | 0 | 0 | 596.13 | 596.13
PJ0004054 | INSTALL EQUIPMENT FOR SMART ROOM - BLD 34 RM 149 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-01-24 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0004054 | INSTALL EQUIPMENT FOR SMART ROOM - BLD 34 RM 149 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-01-24 | EL:SMART ROOM BLDG 34, ROOM 149 | 034 | CLOSED | 0 | 0 | 2722.4364 | 2722.4364
PJ0004054 | INSTALL EQUIPMENT FOR SMART ROOM - BLD 34 RM 149 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-01-24 | IN: INSTALL EQUIPMENT FOR SMART ROOM - BLD 34 RM 149 | 034 | CLOSED | 0 | 0 | 32.028 | 32.028
PJ0004054 | INSTALL EQUIPMENT FOR SMART ROOM - BLD 34 RM 149 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2012-01-24 | PA:PATCH AND PAINT AS NEEDED AFTER SMART ROOM UPGRADE | 034 | CLOSED | 0 | 0 | 237.456 | 237.456
PJ0004054 Total | [7 empty] | 0 | 0 | 3588.0504 | 3588.0504
PJ0004053 | LUNCH AREA BEHIND BLD 70 (MAINT) | GALVEZ, CESAR | CLOSED | 2012-01-24 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0004053 | LUNCH AREA BEHIND BLD 70 (MAINT) | GALVEZ, CESAR | CLOSED | 2012-01-24 | EO: MOVE THREE 5FT PLANTERS FROM BACK OF BLDG 36 TO BLDG 70 | 070 | CLOSED | 0 | 0 | 706.93 | 706.93
PJ0004053 | LUNCH AREA BEHIND BLD 70 (MAINT) | GALVEZ, CESAR | CLOSED | 2012-01-24 | LA: PREP PICNIC AREA AND PROVIDE PLANTERS - BLDG 70 | 070 | CLOSED | 0 | 0 | 268.34 | 268.34
PJ0004053 | LUNCH AREA BEHIND BLD 70 (MAINT) | GALVEZ, CESAR | CLOSED | 2012-01-24 | PL: IDENTIFY WATER SOURCE AND INSTALL HOSE BIB - BLDG 70 | 070 | CLOSED | 0 | 0 | 122.82 | 122.82
PJ0004053 Total | [7 empty] | 0 | 0 | 1098.09 | 1098.09
PJ0004052 | INSTALL 5 NEW BIKE LOCKERS BEHIND MOTT GYM "CAL POLY" WALL - 042 | GALVEZ, CESAR | CLOSED | 2012-01-24 | CA: REMOVE 5 WALL MOUNTED BIKE RACKS AND MOUNT 5 BIKE LOCKERS | 042 | CLOSED | 475.104 | 0 | 1140.954 | 1140.954
PJ0004052 | INSTALL 5 NEW BIKE LOCKERS BEHIND MOTT GYM "CAL POLY" WALL - 042 | GALVEZ, CESAR | CLOSED | 2012-01-24 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 60.39 | 0 | 0 | 0
PJ0004052 | INSTALL 5 NEW BIKE LOCKERS BEHIND MOTT GYM "CAL POLY" WALL - 042 | GALVEZ, CESAR | CLOSED | 2012-01-24 | LA: FUMIGATE BIKE LOCKERS BEHIND MOTT GYM | 042 | CLOSED | 38.964 | 0 | 58.446 | 58.446
PJ0004052 | INSTALL 5 NEW BIKE LOCKERS BEHIND MOTT GYM "CAL POLY" WALL - 042 | GALVEZ, CESAR | CLOSED | 2012-01-24 | MO: HALL WALL MOUNTED BIKE RACKS AND BIKE LOCKERS | 042 | CLOSED | 518.4 | 0 | 48.288 | 48.288
PJ0004052 Total | [7 empty] | 1092.858 | 0 | 1247.688 | 1247.688
PJ0004051 | SP 11/12: ADD 12 KV LINE TO CHEDA RANCH FROM CAMPUS SYSTEM | POLVI, STEVEN | IN_CONSTR | 2012-01-23 | CP: PROJECT CONTINGENCY | 121V | OPEN | 3021.09 | 0 | 0 | 0
PJ0004051 | SP 11/12: ADD 12 KV LINE TO CHEDA RANCH FROM CAMPUS SYSTEM | POLVI, STEVEN | IN_CONSTR | 2012-01-23 | EL: INSTALL NEW OVER HEAD LINES TO CHEDA RANCH. | 121V | CLOSED | 29826.9106 | 0 | 36402.768 | 36402.768
PJ0004051 | SP 11/12: ADD 12 KV LINE TO CHEDA RANCH FROM CAMPUS SYSTEM | POLVI, STEVEN | IN_CONSTR | 2012-01-23 | IN: SP 11/12: ADD 12 KV LINE TO CHEDA RANCH FROM CAMPUS SYSTEM | 121V | CLOSED | 384.336 | 0 | 64.056 | 64.056
PJ0004051 | SP 11/12: ADD 12 KV LINE TO CHEDA RANCH FROM CAMPUS SYSTEM | POLVI, STEVEN | IN_CONSTR | 2012-01-23 | SM: SP 11/12: ADD 12 KV LINE TO CHEDA RANCH FROM CAMPUS SYSTEM | 121V | OPEN | 0 | 0 | 0 | 0
PJ0004051 Total | [7 empty] | 33232.3366 | 0 | 36466.824 | 36466.824
PJ0004050 | FARM SHOP - BLD 9 - AG SHOW - FEB 2ND 2012 (PD BY CHECK) | POPHAM, DONALD J. | CLOSED | 2012-01-24 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0004050 | FARM SHOP - BLD 9 - AG SHOW - FEB 2ND 2012 (PD BY CHECK) | POPHAM, DONALD J. | CLOSED | 2012-01-24 | EL:SUPPLY POWER FOR DISPLAY BOOTHS - FARM SHOP BEFORE FEB 2 | 009 | CLOSED | 0 | 0 | 344.688 | 344.688
PJ0004050 | FARM SHOP - BLD 9 - AG SHOW - FEB 2ND 2012 (PD BY CHECK) | POPHAM, DONALD J. | CLOSED | 2012-01-24 | PERMIT: AG SHOWCASE EVENT - FEB 2 (MAINT) | 009 | CLOSED | 0 | 0 | 160.14 | 160.14
PJ0004050 Total | [7 empty] | 0 | 0 | 504.828 | 504.828
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | AD: RUSSCO | 003 | CLOSED | 13737.73 | 0 | 6744.317 | 6744.317
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | AD: THE SIGN PLACE | 003 | CLOSED | 1605 | 0 | 827.6664 | 827.6664
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | CA:REMOVE DESK DRAWERS | 003 | CLOSED | 867.5984 | 0 | 1157.442 | 1157.442
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 2165.49 | 0 | 0 | 0
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | EL: CONNECT MODULAR FURNITURE TO POWER - 03-100 | 003 | CLOSED | 2700.6838 | 0 | 1857.504 | 1857.504
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | IN: INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | 003 | CLOSED | 192.168 | 0 | 96.084 | 96.084
PJ0004048 | INTERIOR OFFICE IMPROVEMENT 03-100 ADVISING CENTER | BRENNAN, MICHAEL | CLOSED | 2012-01-20 | PA:REPAINT ADVISING CENTER 03-100 | 003 | CLOSED | 2413.952 | 0 | 1372.008 | 1372.008
PJ0004048 Total | [7 empty] | 23682.6222 | 0 | 12055.0214 | 12055.0214
PJ0004047 | ORDER AND INSTALL PAVERS FOR MUSTANG MEMORIAL PLAZA | MAY, TOM | CLOSED | 2012-01-18 | AD: (MX046) PURCHASE CORRECTED PAVER FOR SUSAN SPARLING | 061 | CLOSED | 0 | 0 | 65.544 | 65.544
PJ0004047 | ORDER AND INSTALL PAVERS FOR MUSTANG MEMORIAL PLAZA | MAY, TOM | CLOSED | 2012-01-18 | CA:INSTALL PAVERS AT SPANOS MEMORIAL PLAZA | 061 | CLOSED | 466.9266 | 0 | 392.706 | 392.706
PJ0004047 | ORDER AND INSTALL PAVERS FOR MUSTANG MEMORIAL PLAZA | MAY, TOM | CLOSED | 2012-01-18 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 49.9 | 0 | 0 | 0
PJ0004047 | ORDER AND INSTALL PAVERS FOR MUSTANG MEMORIAL PLAZA | MAY, TOM | CLOSED | 2012-01-18 | IN: ORDER AND INSTALL PAVERS FOR MUSTANG MEMORIAL PLAZA | 061 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0004047 Total | [7 empty] | 548.8546 | 0 | 490.278 | 490.278
PJ0004046 | INSTALL GALLERY DISPLAY RAILS - BLD 35 RM 111C | BRENNAN, MICHAEL | CLOSED | 2012-01-12 | CA:INSTALL GALLERY RAIL SYSTEM | 035 | CLOSED | 1184.2703 | 0 | 981.804 | 981.804
PJ0004046 | INSTALL GALLERY DISPLAY RAILS - BLD 35 RM 111C | BRENNAN, MICHAEL | CLOSED | 2012-01-12 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 171.89 | 0 | 0 | 0
PJ0004046 | INSTALL GALLERY DISPLAY RAILS - BLD 35 RM 111C | BRENNAN, MICHAEL | CLOSED | 2012-01-12 | PA:114C PATCH AND PAINT HOLES | 035 | CLOSED | 534.912 | 0 | 208.092 | 208.092
PJ0004046 Total | [7 empty] | 1891.0723 | 0 | 1189.896 | 1189.896
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | AD: FENCE FACTORY - 3-MONTH RENTAL | 113B | CLOSED | 0 | 0 | 892.0162 | 892.0162
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | AD: G.F. GARCIA AND SONS | 113B | CLOSED | 0 | 0 | 5348.93 | 5348.93
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | AD: MAINO CONSTRUCTION | 113B | CLOSED | 0 | 0 | 5296.5 | 5296.5
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | AD: UNITED RENTALS (DIRECT-PAY) | 113B | CLOSED | 0 | 0 | 1688.1 | 1688.1
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | CA: INSTALL SIGNAGE AT CO-GEN (KEEP OUT) | 113B | CLOSED | 169.164 | 0 | 49.686 | 49.686
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | CP: PROJECT CONTINGENCY | 113B | CLOSED | 0 | 0 | 0 | 0
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | EL: ELECTRICAL UTILITY LOCATING AND REPAIRS FOR S.M. T1 LEAK | 113B | CLOSED | 0 | 0 | 827.676 | 827.676
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | EO: REMOVE STOCKPILED SOIL FROM SIERRA MADRE EXCAVATION | 113B | CLOSED | 0 | 0 | 1644.54 | 1644.54
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | ES: REPAIR HEATING HOT WATER LEAKS - SIERRA MADRE T1 | 113B | CLOSED | 0 | 0 | 63192.9489 | 63192.9489
PJ0004045 | HEATING HOT WATER LEAKS SIERRA MADRE T/1 LOOP - 113B (NO EST) | KUENTZEL, DOUGLAS A. | CLOSED | 2012-01-18 | LA: LANDSCAPE REPAIRS FOR SIERRA MADRE T1 LEAK | 113B | CLOSED | 0 | 0 | 2545.9006 | 2545.9006
PJ0004045 Total | [7 empty] | 169.164 | 0 | 81486.2977 | 81486.2977
PJ0004044 | PROVIDE LOCKS FOR LACTATION STATIONS - VARIOUS BLDS (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-01-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004044 | PROVIDE LOCKS FOR LACTATION STATIONS - VARIOUS BLDS (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2012-01-18 | LO: INSTALL NEW LOCKS FOR LACTATION STATIONS-BLDG 1,33,14 | GENERAL | CLOSED | 690.22 | 0 | 690.625 | 690.625
PJ0004044 Total | [7 empty] | 690.22 | 0 | 690.625 | 690.625
PJ0004042 | SR 11/12: EMERGENCY REPAIR OF CHILLER #1 - BLD 40 | NEEL, JOEL | CLOSED | 2012-01-10 | AD: PERRY'S ELECTRONIC MOTORS & CONTROLS | 040 | CLOSED | 0 | 0 | 4834.87 | 4834.87
PJ0004042 | SR 11/12: EMERGENCY REPAIR OF CHILLER #1 - BLD 40 | NEEL, JOEL | CLOSED | 2012-01-10 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0004042 Total | [7 empty] | 0 | 0 | 4834.87 | 4834.87
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | AD: FLOOR CONNECTION | 001 | CLOSED | 0 | 0 | 5979.4703 | 5979.4703
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | AD: FURNITURE INSTALLATION TEAM | 001 | CLOSED | 0 | 0 | 974.9198 | 974.9198
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | CA: REMOVE CABINET, CUT BOTTOM OF DOOR, & HANG WHITEBOARD | 001 | CLOSED | 0 | 0 | 738.63 | 738.63
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | CU: CLEAN WINDOWS | 001 | CLOSED | 0 | 0 | 145.968 | 145.968
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | EL: INSTALL NEW "T" BAR LIGHT COVERS | 001 | CLOSED | 0 | 0 | 186.5846 | 186.5846
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | IN: CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 | 001 | CLOSED | 0 | 0 | 64.056 | 64.056
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | MO:MOVE FURINTURE | 001 | CLOSED | 0 | 0 | 24.144 | 24.144
PJ0004041 | CARPET SQUARES, ELECTRICAL, CLEAN & PAINT - BLD 001-117 (NO EST) | LAMPMAN, GREG | CLOSED | 2011-12-21 | PA: PATCH HOLES AND PAINT | 001 | CLOSED | 0 | 0 | 1164.444 | 1164.444
PJ0004041 Total | [7 empty] | 0 | 0 | 9278.2167 | 9278.2167
PJ0004039 | M&R PARK 11/12: RESEAL & RESTRIPE ADMIN PARKING LOT P-A01 | GALVEZ, CESAR | CLOSED | 2011-12-16 | AD: JOC 11.023.016 STAPLES | P-A01 | CLOSED | 8697.8588 | 0 | 8697.8588 | 8697.8588
PJ0004039 | M&R PARK 11/12: RESEAL & RESTRIPE ADMIN PARKING LOT P-A01 | GALVEZ, CESAR | CLOSED | 2011-12-16 | CP: PROJECT CONTINGENCY | P-A01 | CLOSED | 882.6 | 0 | 0 | 0
PJ0004039 | M&R PARK 11/12: RESEAL & RESTRIPE ADMIN PARKING LOT P-A01 | GALVEZ, CESAR | CLOSED | 2011-12-16 | IN: M&R PARK 11/12: RESEAL & RESTRIPE ADMIN PARKING LOT P-A01 | P-A01 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0004039 Total | [7 empty] | 9708.5708 | 0 | 8729.8868 | 8729.8868
PJ0004038 | PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | MAY, TOM | CLOSED | 2011-12-14 | AD: COASTAL DEMO (CORE DRILLING FOR PLUMBERS) | 057 | CLOSED | 0 | 0 | 318.325 | 318.325
PJ0004038 | PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | MAY, TOM | CLOSED | 2011-12-14 | CP: PROJECT CONTINGENCY | 057 | CLOSED | 272.79 | 0 | 0 | 0
PJ0004038 | PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | MAY, TOM | CLOSED | 2011-12-14 | EL:NEW ELECTRICAL FOR W/D IN MEN'S RR AT VET CLINIC | 057 | CLOSED | 342.0012 | 0 | 425.22 | 425.22
PJ0004038 | PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | MAY, TOM | CLOSED | 2011-12-14 | ES:NEW VENT FOR DRYER IN MEN'S RR IN VET CLINIC | 057 | CLOSED | 337.8402 | 0 | 399.54 | 399.54
PJ0004038 | PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | MAY, TOM | CLOSED | 2011-12-14 | IN: PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | 057 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004038 | PREP AREA FOR WASHER & DRYER - VET CLINIC BLDG 57 | MAY, TOM | CLOSED | 2011-12-14 | PL:PLUMB FOR NEW W/D IN MEN'S RR IN VET CLINIC | 057 | CLOSED | 1983.9493 | 0 | 1750.584 | 1750.584
PJ0004038 Total | [7 empty] | 3000.6367 | 0 | 2957.725 | 2957.725
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | AD: FLOOR CONNECTION | 035 | CLOSED | 1016.5 | 0 | 853.1538 | 853.1538
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 4943.4 | 0 | 4943.4107 | 4943.4107
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 1149.18 | 0 | 1149.18 | 1149.18
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | CA: NEW BLINDS AND CARPET REPAIR AT 35-111F | 035 | CLOSED | 437.358 | 0 | 265.266 | 265.266
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 6.59 | 0 | 0 | 0
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | EL:EXTEND OUTLET BOXES IN 35-111F | 035 | CLOSED | 174.3377 | 0 | 209.928 | 209.928
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | IN: REMODEL - BLD 35 RM 111F (OFFICE) | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004037 | REMODEL - BLD 35 RM 111F (OFFICE) | MAY, TOM | CLOSED | 2011-12-13 | PA:PAINT WALLS IN 35-111F | 035 | CLOSED | 1381.4426 | 0 | 683.64 | 683.64
PJ0004037 Total | [7 empty] | 9172.8643 | 0 | 8168.6345 | 8168.6345
PJ0004035 | SR 11/12: REPLACE SCALLOPED ROOF AREA - MOTT GYM 42 | BRENNAN, MICHAEL | CLOSED | 2011-12-12 | AD: JOC 11.023.012 STAPLES | 042 | CLOSED | 22352.36 | 0 | 22352.36 | 22352.36
PJ0004035 | SR 11/12: REPLACE SCALLOPED ROOF AREA - MOTT GYM 42 | BRENNAN, MICHAEL | CLOSED | 2011-12-12 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004035 | SR 11/12: REPLACE SCALLOPED ROOF AREA - MOTT GYM 42 | BRENNAN, MICHAEL | CLOSED | 2011-12-12 | IN: SR 11/12: REPLACE SCALLOPED ROOF AREA - MOTT GYM 42 | 042 | CLOSED | 53.38 | 0 | 26.69 | 26.69
PJ0004035 Total | [7 empty] | 22405.74 | 0 | 22379.05 | 22379.05
PJ0004034 | ELECTRONIC KEYPUNCH DOOR LOCK INSTALLATION - BLD 13 RM 125B | BRENNAN, MICHAEL | CLOSED | 2011-12-09 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 175.38 | 0 | 0 | 0
PJ0004034 | ELECTRONIC KEYPUNCH DOOR LOCK INSTALLATION - BLD 13 RM 125B | BRENNAN, MICHAEL | CLOSED | 2011-12-09 | LO:INSTALL ELEC KEYPAD | 013 | CLOSED | 1753.867 | 0 | 1006.764 | 1006.764
PJ0004034 Total | [7 empty] | 1929.247 | 0 | 1006.764 | 1006.764
PJ0004032 | MODIFY EXISTING LAB FOR NEW EQUIP INSTALL - BREEDING BARN | LAMPMAN, GREG | CLOSED | 2011-12-06 | AD: JOC 11.022.051 STAPLES | 032C | CLOSED | 2807.7335 | 0 | 2807.8405 | 2807.8405
PJ0004032 | MODIFY EXISTING LAB FOR NEW EQUIP INSTALL - BREEDING BARN | LAMPMAN, GREG | CLOSED | 2011-12-06 | CP: PROJECT CONTINGENCY | 032C | CLOSED | 338.61 | 0 | 0 | 0
PJ0004032 | MODIFY EXISTING LAB FOR NEW EQUIP INSTALL - BREEDING BARN | LAMPMAN, GREG | CLOSED | 2011-12-06 | EL: REMOVE (E) LIGHTS AND RE-INSTALL | 032C | CLOSED | 450.3389 | 0 | 487.394 | 487.394
PJ0004032 | MODIFY EXISTING LAB FOR NEW EQUIP INSTALL - BREEDING BARN | LAMPMAN, GREG | CLOSED | 2011-12-06 | IN: MODIFY EXISTING LAB FOR NEW EQUIP INSTALL - BREEDING BARN | 032C | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0004032 Total | [7 empty] | 3724.7944 | 0 | 3359.2905 | 3359.2905
PJ0004030 | INSTALL TRILOGY DOOR LOCK SYSTEM - BLDG. 192 EXTERIOR DOOR | MAY, TOM | CLOSED | 2011-12-05 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 242.39 | 0 | 0 | 0
PJ0004030 | INSTALL TRILOGY DOOR LOCK SYSTEM - BLDG. 192 EXTERIOR DOOR | MAY, TOM | CLOSED | 2011-12-05 | EL:ELECTRICAL FOR TRILOGY LOCK AT EAST ENTRANCE 192 | 192 | CLOSED | 434.833 | 0 | 307.284 | 307.284
PJ0004030 | INSTALL TRILOGY DOOR LOCK SYSTEM - BLDG. 192 EXTERIOR DOOR | MAY, TOM | CLOSED | 2011-12-05 | IN: INSTALL POLYCARD DOOR LOCK SYSTEM - BLDG. 192 EXTERIOR DOOR | 192 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0004030 | INSTALL TRILOGY DOOR LOCK SYSTEM - BLDG. 192 EXTERIOR DOOR | MAY, TOM | CLOSED | 2011-12-05 | LO:ORDER AND INSTALL A TRILOGY LOCK TO THE EAST ENTRANCE 192 | 192 | CLOSED | 1956.5916 | 0 | 1673.892 | 1673.892
PJ0004030 Total | [7 empty] | 2665.8426 | 0 | 2013.204 | 2013.204
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | AD: G.F. GARCIA | GENERAL | CLOSED | 4526.1 | 0 | 4527.0095 | 4527.0095
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | CA:INSTALL SIGN FOR PED ACCESS AT POLY DRIVE | GENERAL | CLOSED | 1052.7798 | 0 | 631.098 | 631.098
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 435.74 | 0 | 0 | 0
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | EL: REPLACE LIGHTING CONDUIT FOR SIDEWALK REMOVAL ON VILLAGE DR. | GENERAL | CLOSED | 599.328 | 0 | 1039.5095 | 1039.5095
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | EO:ASSIST LA IN PLANTING OF AREA WHERE SIDEWALK WAS REMOVED | GENERAL | CLOSED | 442.8996 | 0 | 1398.048 | 1398.048
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | IN: REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | GENERAL | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004029 | REMOVE SIDEWALK: W SIDE OF VILLAGE DRIVE, N OF TRUCKEE | MAY, TOM | CLOSED | 2011-11-29 | LA:PLANT AREA WHERE SIDEWALK WAS REMOVED AT PCV | GENERAL | CLOSED | 4264.4274 | 0 | 2154.4272 | 2154.4272
PJ0004029 Total | [7 empty] | 11385.3308 | 0 | 9814.1482 | 9814.1482
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | CA: SUPPORT FOR 2011 FALL COMMENCEMENT - DEC 10 | 042 | CLOSED | 0 | 0 | 9161.54 | 9161.54
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | CU: SUPPORT FOR 2011 FALL COMMENCEMENT | 042 | CLOSED | 0 | 0 | 6139.9087 | 6139.9087
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | EL: SUPPORT FOR 2011 FALL COMMENCEMENT - DEC 10 | 042 | CLOSED | 0 | 0 | 500.16 | 500.16
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | LA: SUPPORT FOR 2011 FALL COMMENCEMENT - DEC 10 | 042 | CLOSED | 0 | 0 | 2857.5475 | 2857.5475
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | LO: REPAIR DOOR GOING INTO LOTT GYM. | 042 | CLOSED | 0 | 0 | 266.035 | 266.035
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | MO: SUPPORT FOR 2011 FALL COMMENCEMENT - DEC 10 | 042 | CLOSED | 0 | 0 | 714.26 | 714.26
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | PA: TOUCH UP HAND RAILS/STAGE FOR 2011 FALL COMMENCEMENT-DEC 9 | 042 | CLOSED | 0 | 0 | 222.615 | 222.615
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | PERMIT: 2011 FALL COMMENCEMENT (N/L) | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004028 | 2011 FALL COMMENCEMENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-11-29 | PL: SUPPORT FOR 2011 FALL COMMENCEMENT - DEC 10 | 042 | CLOSED | 0 | 0 | 357.16 | 357.16
PJ0004028 Total | [7 empty] | 0 | 0 | 20219.2262 | 20219.2262
PJ0004026 | SR 11/12: RE-ROOF OFFICE TOWER - BLD 05 | MAY, TOM | CLOSED | 2011-11-22 | AD: JOC 11.023.005 STAPLES | 005 | CLOSED | 85838.96 | 0 | 85690.05 | 85690.05
PJ0004026 | SR 11/12: RE-ROOF OFFICE TOWER - BLD 05 | MAY, TOM | CLOSED | 2011-11-22 | CA: INSTALL A SIGN TO RESTRICT ACCESS TO ROOF OF BLDG. 5 | 005 | CLOSED | 1313.8932 | 0 | 174.965 | 174.965
PJ0004026 | SR 11/12: RE-ROOF OFFICE TOWER - BLD 05 | MAY, TOM | CLOSED | 2011-11-22 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 0 | 0 | 0 | 0
PJ0004026 | SR 11/12: RE-ROOF OFFICE TOWER - BLD 05 | MAY, TOM | CLOSED | 2011-11-22 | IN: SR 11/12: RE-ROOF OFFICE TOWER - BLD 05 | 005 | CLOSED | 53.38 | 0 | 53.38 | 53.38
PJ0004026 Total | [7 empty] | 87206.2332 | 0 | 85918.395 | 85918.395
PJ0004025 | SR 11/12: PRUNE TREES CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2011-11-22 | AD: GREENVALE TREE COMPANY | GENERAL | CLOSED | 15000 | 0 | 14563.5 | 14563.5
PJ0004025 | SR 11/12: PRUNE TREES CAMPUS WIDE | GALVEZ, CESAR | CLOSED | 2011-11-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004025 Total | [7 empty] | 15000 | 0 | 14563.5 | 14563.5
PJ0004021 | SR 11/12: COMMISSION BTU METERS - GENERAL CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-11-22 | AD: SIEMENS | GENERAL | CLOSED | 67037 | 0 | 67037.12 | 67037.12
PJ0004021 | SR 11/12: COMMISSION BTU METERS - GENERAL CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-11-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0004021 Total | [7 empty] | 67037 | 0 | 67037.12 | 67037.12
PJ0004020 | WASH EXTERIOR WINDOWS - BUILDINGS 186A & 186B (SEE TASKS) | LOOSLEY, SCOTT L. | CLOSED | 2011-11-08 | AD: COASTAL JANITORIAL | 186 | CLOSED | 1002.59 | 0 | 1002.59 | 1002.59
PJ0004020 | WASH EXTERIOR WINDOWS - BUILDINGS 186A & 186B (SEE TASKS) | LOOSLEY, SCOTT L. | CLOSED | 2011-11-08 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 100.26 | 0 | 0 | 0
PJ0004020 Total | [7 empty] | 1102.85 | 0 | 1002.59 | 1002.59
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | AD: ASAP REPROGRAPHICS | 018A | CLOSED | 0 | 0 | 290.14 | 290.14
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | AD: ENGLEKIRK - PLAN CHECK - NO OVERHEAD | 018A | CLOSED | 2150 | 0 | 2150 | 2150
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | AD: NORTH COAST ENGINEERING | 018A | CLOSED | 4016.78 | 0 | 4016.78 | 4016.78
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | AD: PMSM ARCHITECTS | 018A | CLOSED | 71690 | 0 | 70580.4849 | 70580.4849
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | AD: SHIPPING CHARGES - PLANS TO ENGLEKIRK | 018A | CLOSED | 0 | 0 | 30.12 | 30.12
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | CP: PROJECT CONTINGENCY | 018A | CLOSED | 3668.46 | 0 | 0 | 0
PJ0004019 | DESIGN TO CONVERT STORAGE AREA TO LAB-DPTC (PJ4314-CONSTRUCTION) | LAMPMAN, GREG | CLOSED | 2011-11-17 | IN: DESIGN STORAGE AREA FOR NEW LAB - DPTC | 018A | CLOSED | 512.448 | 0 | 320.28 | 320.28
PJ0004019 Total | [7 empty] | 82037.688 | 0 | 77387.8049 | 77387.8049
PJ0004017 | NEED POWER AND MOUNT FOR PROJECTOR - BLD 26 RM 110C (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | CA: UNBOLT CABINET, PURCHASE, INSTALL NEW 6ft WHITEBOARD 26-110C | 026 | CLOSED | 0 | 0 | 325.296 | 325.296
PJ0004017 | NEED POWER AND MOUNT FOR PROJECTOR - BLD 26 RM 110C (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0004017 | NEED POWER AND MOUNT FOR PROJECTOR - BLD 26 RM 110C (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | EL: INSTALL ELECTRICAL FOR CEILING-MOUNTED PROJECTOR 26-110C | 026 | CLOSED | 0 | 0 | 202.248 | 202.248
PJ0004017 | NEED POWER AND MOUNT FOR PROJECTOR - BLD 26 RM 110C (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | IN: NEED POWER AND MOUNT FOR PROJECTOR - BLD 26 RM 110C | 026 | CLOSED | 0 | 0 | 32.028 | 32.028
PJ0004017 Total | [7 empty] | 0 | 0 | 559.572 | 559.572
PJ0004016 | NEW CARPET INSTALLATION - BLDG 116 2ND FLOOR | GRIFFIN, PATRICK E. | CLOSED | 2011-11-15 | AD: JOC 11.023.004 STAPLES | 116 | CLOSED | 26935.8911 | 0 | 26935.8697 | 26935.8697
PJ0004016 | NEW CARPET INSTALLATION - BLDG 116 2ND FLOOR | GRIFFIN, PATRICK E. | CLOSED | 2011-11-15 | CP: PROJECT CONTINGENCY | 116 | CLOSED | 2720.1 | 0 | 0 | 0
PJ0004016 | NEW CARPET INSTALLATION - BLDG 116 2ND FLOOR | GRIFFIN, PATRICK E. | CLOSED | 2011-11-15 | IN: NEW CARPET INSTALLATION - BLDG 116 2ND FLOOR | 116 | CLOSED | 256.224 | 0 | 64.056 | 64.056
PJ0004016 | NEW CARPET INSTALLATION - BLDG 116 2ND FLOOR | GRIFFIN, PATRICK E. | CLOSED | 2011-11-15 | MO: CANCLED | 116 | CLOSED | 0 | 0 | 0 | 0
PJ0004016 Total | [7 empty] | 29912.2151 | 0 | 26999.9257 | 26999.9257
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | AD: EMPIRE CONSTRUCTION | 070 | CLOSED | 4600 | 0 | 2528.49 | 2528.49
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | CA:DISASSEMBLE FURNITURE,KEYBOARD TRAY,BUILD NEW OFFICES | 070 | CLOSED | 12053.7407 | 0 | 12631.1225 | 12631.1225
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | CU:CLEAN CARPET IN ROOM 103E, BLDG 70 | 070 | CLOSED | 159.32 | 0 | 127.605 | 127.605
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | EL:INSTALL NEW ELECTRICAL FOR OFFICES BLDG 70 | 070 | CLOSED | 6001.7054 | 0 | 3806.164 | 3806.164
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | ES:RELOCATE AND ADD NEW HVAC AS NEEDED FOR NEW OFFICES | 070 | CLOSED | 4632.2309 | 0 | 1077.32 | 1077.32
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | IN: REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | 070 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | ITS: FACEPLATES&ACTIVATION -OFFICE MOVES FOR TRAILER REMOVAL 070 | 070 | CLOSED | 2930.68 | 0 | 742.1 | 742.1
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | LO:REMOVE CORES FROM TRAILER BEHIND 70, CHANGE OFFICE CORES | 070 | CLOSED | 893.48 | 0 | 869.295 | 869.295
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | MO:MOVE OFFICE FURNITURE IN BLDG 70 AND TO E-SURPLUS | 070 | CLOSED | 810 | 0 | 281.68 | 281.68
PJ0004014 | REMODELS DUE TO REMOVAL OF TRAILER - BLD 70 | MOLLAN, CHERYL L. | CLOSED | 2011-11-14 | PA:PAINT ROOMS 119, 103E AND NEW CONSTRUCTED WALLS AND OFFICE | 070 | CLOSED | 4311.31 | 0 | 2720.85 | 2720.85
PJ0004014 Total | [7 empty] | 36499.227 | 0 | 24891.3865 | 24891.3865
PJ0004013 | 11/12: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004013 | 11/12: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: GREEN/GOLD WRESLTING MATCH - NOV 13 | 042 | CLOSED | 0 | 0 | 315.444 | 315.444
PJ0004013 | 11/12: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S WRESTLING - 1/8 | 042 | CLOSED | 0 | 0 | 383.166 | 383.166
PJ0004013 | 11/12: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S WRESTLING - JAN 15 | 042 | CLOSED | 0 | 0 | 437.904 | 437.904
PJ0004013 | 11/12: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S WRESTLING - JAN 6 | 042 | CLOSED | 0 | 0 | 729.84 | 729.84
PJ0004013 | 11/12: SUPPORT FOR WRESTLING | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WRESTLING V ARIZONA ST. - 1/27 | 042 | CLOSED | 0 | 0 | 656.856 | 656.856
PJ0004013 Total | [7 empty] | 0 | 0 | 2523.21 | 2523.21
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR W. BBALL V CSULB - FEB 23 | 042 | CLOSED | 0 | 0 | 583.872 | 583.872
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR W. BBALL V. PACIFIC - 1/26 | 042 | CLOSED | 0 | 0 | 574.749 | 574.749
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR W. BBALL V. UC DAVIS - JAN 28 | 042 | CLOSED | 0 | 0 | 821.07 | 821.07
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WMS BBALL V.UC IRVINE - 1/14 | 042 | CLOSED | 0 | 0 | 729.84 | 729.84
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WOMEN'S BASKET BALL ON NOV 30 | 042 | CLOSED | 0 | 0 | 356.736 | 356.736
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WOMEN'S BASKETBALL - 11/26 | 042 | CLOSED | 0 | 0 | 982.608 | 982.608
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WOMEN'S BASKETBALL - NOV 27 | 042 | CLOSED | 0 | 0 | 585.042 | 585.042
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WOMEN'S BASKETBALL GAME - DEC 31 | 042 | CLOSED | 0 | 0 | 821.07 | 821.07
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WOMEN'S BASKETBALL GAME - NOV 20 | 042 | CLOSED | 0 | 0 | 585.18 | 585.18
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR WOMEN'S BASKETBALL GAME - NOV 25 7:00PM | 042 | CLOSED | 0 | 0 | 515.904 | 515.904
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT WOMEN'S BASKETBALL V FULLERTON - FEB 11 | 042 | CLOSED | 0 | 0 | 711.594 | 711.594
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: WOMEN'S BBALL V. CSU FULLERTON (PLAYOFF) - MAR 6 (MO007) | 042 | CLOSED | 0 | 0 | 583.872 | 583.872
PJ0004012 | 11/12: SUPPORT FOR WOMEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CUL SUPPORT FOR WOMEN'S BBALL V. CSU NORTHRIDGE | 042 | CLOSED | 0 | 0 | 1295.232 | 1295.232
PJ0004012 Total | [7 empty] | 0 | 0 | 9146.769 | 9146.769
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CA: REMOVE CHAIRBACKS FOR TELEVISED BASKETBALL GAME-MAR2 | 042 | CLOSED | 0 | 0 | 140.97 | 140.97
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CA: REMOVE CHAIRBACKS ON BLEACHERS FOR TELEVISED GAME-1/20 | 042 | CLOSED | 0 | 0 | 197.358 | 197.358
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CA: SUPPORT FOR MEN'S BBALL V. UCSB (TELEVISED) - JAN 2 | 042 | CLOSED | 0 | 0 | 704.85 | 704.85
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: CLEAN UP OF BLEACHERS BEFORE SEASON - 11/8 | 042 | CLOSED | 0 | 0 | 145.968 | 145.968
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: MEN'S BBALL V. PACIFIC - MAR 3 | 042 | CLOSED | 0 | 0 | 1277.22 | 1277.22
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL - 11/18 | 042 | CLOSED | 0 | 0 | 682.272 | 682.272
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL - DEC 29 | 042 | CLOSED | 0 | 0 | 720.717 | 720.717
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL - DEC 6 | 042 | CLOSED | 0 | 0 | 492.642 | 492.642
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL - FEB 11 | 042 | CLOSED | 0 | 0 | 1204.236 | 1204.236
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL - NOV 12 | 042 | CLOSED | 0 | 0 | 438.12 | 438.12
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL GAME - DEC 14 | 042 | CLOSED | 0 | 0 | 437.904 | 437.904
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BASKETBALL GAME - NOV 30 | 042 | CLOSED | 0 | 0 | 476.781 | 476.781
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BBALL - JAN 7 | 042 | CLOSED | 0 | 0 | 802.824 | 802.824
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BBALL V CSU BAKERSFIELD - NOV 16 | 042 | CLOSED | 0 | 0 | 595.38 | 595.38
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BBALL V CSULB - 1/19 | 042 | CLOSED | 0 | 0 | 620.364 | 620.364
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BBALL V UC RIVERSIDE - FEB 9 | 042 | CLOSED | 0 | 0 | 583.872 | 583.872
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR MEN'S BBALL V. CSU NORTHRIDGE - 1/21 | 042 | CLOSED | 0 | 0 | 1131.252 | 1131.252
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT FOR PRE SEASON MEN'S BASKETBALL GAME - NOV 6 | 042 | CLOSED | 0 | 0 | 441.966 | 441.966
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPORT MEN'S BBALL V. UC DAVIS - MAR 1 | 042 | CLOSED | 0 | 0 | 675.102 | 675.102
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | CU: SUPPROT FOR MEN'S BASKETBALL - JAN 2 | 042 | CLOSED | 0 | 0 | 912.3 | 912.3
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | EL: SUPPORT FOR MEN'S BASKETBALL V UCSB(TELEVISED)- JAN 2 7PM | 042 | CLOSED | 0 | 0 | 604.728 | 604.728
PJ0004011 | 11/12: SUPPORT FOR MEN'S BASKETBALL | POPHAM, DONALD J. | CLOSED | 2011-11-14 | EL: SUPPORT FOR TELEVISED BASKETBALL GAME - JAN 21 | 042 | CLOSED | 0 | 0 | 525.168 | 525.168
PJ0004011 Total | [7 empty] | 0 | 0 | 13811.994 | 13811.994
PJ0004009 | REFURBISH/REPLACE HARMAN HALL & GREENROOM CARPET | LAMPMAN, GREG | CLOSED | 2011-11-09 | AD: JOC 11.023.015.01 STAPLES | 006 | CLOSED | 39844.7135 | 0 | 35830.7797 | 35830.7797
PJ0004009 | REFURBISH/REPLACE HARMAN HALL & GREENROOM CARPET | LAMPMAN, GREG | CLOSED | 2011-11-09 | AD: FLOOR CONNECTION | 006 | CLOSED | 39930.7094 | 0 | 39929.7036 | 39929.7036
PJ0004009 | REFURBISH/REPLACE HARMAN HALL & GREENROOM CARPET | LAMPMAN, GREG | CLOSED | 2011-11-09 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 3417.53 | 0 | 0 | 0
PJ0004009 | REFURBISH/REPLACE HARMAN HALL & GREENROOM CARPET | LAMPMAN, GREG | CLOSED | 2011-11-09 | IN: REFURBISH/REPLACE HARMAN HALL & GREENROOM CARPET | 006 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0004009 Total | [7 empty] | 83321.0649 | 0 | 75856.5673 | 75856.5673
PJ0004008 | REMODEL PROVOST'S OFFICE - ADMIN 001-305 | MAY, TOM | CLOSED | 2011-11-09 | AD: RUSSCO | 001 | CLOSED | 4186.9314 | 0 | 4186.9314 | 4186.9314
PJ0004008 | REMODEL PROVOST'S OFFICE - ADMIN 001-305 | MAY, TOM | CLOSED | 2011-11-09 | AD: TEMPLE BUILDERS | 001 | CLOSED | 2350.255 | 0 | 2350.255 | 2350.255
PJ0004008 | REMODEL PROVOST'S OFFICE - ADMIN 001-305 | MAY, TOM | CLOSED | 2011-11-09 | CA: INSTALL COVE BASSE IN ADMIN 305A AND PROVOST OFFICE | 001 | CLOSED | 229.164 | 0 | 171.93 | 171.93
PJ0004008 | REMODEL PROVOST'S OFFICE - ADMIN 001-305 | MAY, TOM | CLOSED | 2011-11-09 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 235.36 | 0 | 0 | 0
PJ0004008 | REMODEL PROVOST'S OFFICE - ADMIN 001-305 | MAY, TOM | CLOSED | 2011-11-09 | IN: REMODEL PROVOST'S OFFICE - ADMIN 001-305 | 001 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0004008 | REMODEL PROVOST'S OFFICE - ADMIN 001-305 | MAY, TOM | CLOSED | 2011-11-09 | PA:PATCH AND PAINT ADM 305A | 001 | CLOSED | 1057.2728 | 0 | 979.506 | 979.506
PJ0004008 Total | [7 empty] | 8123.0392 | 0 | 7752.6784 | 7752.6784
PJ0004007 | REMOVAL OF SHELVING - BLDG 045-216B | MOLLAN, CHERYL L. | CLOSED | 2011-11-09 | CA:REMOVE SHELVING FROM UPPER WALL AND CEILING. | 045 | CLOSED | 1244.2703 | 0 | 833.616 | 833.616
PJ0004007 | REMOVAL OF SHELVING - BLDG 045-216B | MOLLAN, CHERYL L. | CLOSED | 2011-11-09 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 322.58 | 0 | 0 | 0
PJ0004007 | REMOVAL OF SHELVING - BLDG 045-216B | MOLLAN, CHERYL L. | CLOSED | 2011-11-09 | IN: REMOVAL OF SHELVING - BLDG 045-216B | 045 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0004007 | REMOVAL OF SHELVING - BLDG 045-216B | MOLLAN, CHERYL L. | CLOSED | 2011-11-09 | PA:PATCH HOLES AND PAINT ROOM. | 045 | CLOSED | 1724.1 | 0 | 755.004 | 755.004
PJ0004007 Total | [7 empty] | 3419.0623 | 0 | 1716.732 | 1716.732
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V UC IRVINE - APR 6 | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V. CSY BAKERSFIELD-SAT MAY 12 | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V. OKLAHOMA ST - SAT FEB 18 | 160 | CLOSED | 0 | 0 | 147.582 | 147.582
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V. PACIFIC - APR 28 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V. SDSU - SAT MAR 24 (DBL HDR) | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V. UCSB - SAT MAY 19 | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR BASEBALL V. WASHINGTON - SAT MAR 10 | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. CSU BAKERSFIELD - MAY 11-13 | 160 | CLOSED | 0 | 0 | 1282.548 | 1282.548
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. CSU LONG BEACH - MAR 30 - APR 1 | 160 | CLOSED | 0 | 0 | 1393.134 | 1393.134
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. DARTMOUTH - MAR 21 | 160 | CLOSED | 0 | 0 | 642.906 | 642.906
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. FRESNO ST. - APR 17 | 160 | CLOSED | 0 | 0 | 662.388 | 662.388
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. PACIFIC - APR 27-APR 29 | 160 | CLOSED | 0 | 0 | 1475.454 | 1475.454
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. PEPPERDINE - MAY 1 | 160 | CLOSED | 0 | 0 | 467.568 | 467.568
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. SAN DIEGO ST - MAR 23 - MAR 25 | 160 | CLOSED | 0 | 0 | 1113.798 | 1113.798
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. UC IRVINE - APR 5-APR 7 | 160 | CLOSED | 0 | 0 | 1436.49 | 1436.49
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT BASEBALL V. UC SANTA BARBARA - MAY 18-20 | 160 | CLOSED | 0 | 0 | 1403.832 | 1403.832
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR ALUMNI BASEBALL GAME - FEB 11 | 160 | CLOSED | 0 | 0 | 437.67 | 437.67
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR BASEBALL CAMP - DECEMBER 10TH AND 17TH | 160 | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR BASEBALL V. OKLAHOMA ST - 2/17-2/19 | 160 | CLOSED | 0 | 0 | 1936.74 | 1936.74
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR BASEBALL V. SANTA CLARA - 2/21 | 160 | CLOSED | 0 | 0 | 526.014 | 526.014
PJ0004006 | 11/12: SUPPORT FOR BASEBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR BASEBALL V. WASHINGTON - MAR 9-11 | 160 | CLOSED | 0 | 0 | 1730.916 | 1730.916
PJ0004006 Total | [7 empty] | 0 | 0 | 15284.376 | 15284.376
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR SOFTBALL V BALL STATE/LIPSCOMB - SAT MAR 24 | 161 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR SOFTBALL V. CSU NORTHRIDGE - APR 15 | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | CU: SUPPORT FOR SOFTBALL V. UC DAVIS - SAT APR 21 | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR SOFTBALL GAME ON 11/12/11 | 161 | CLOSED | 0 | 0 | 58.446 | 58.446
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR SOFTBALL V. LIPSCOMB - MAR 23-25 | 161 | CLOSED | 0 | 0 | 4681.188 | 4681.188
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT FOR SOFTBALL V. UC RIVERSIDE - MAY 11 & 12 | 161 | CLOSED | 0 | 0 | 737.484 | 737.484
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT SOFTBALL V. CSU FULLERTON - MAR 31 - APR 1 | 161 | CLOSED | 0 | 0 | 1664.532 | 1664.532
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT SOFTBALL V. CSU NORTHRIDGE - APR 14 & APR 15 | 161 | CLOSED | 0 | 0 | 1040.262 | 1040.262
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT SOFTBALL V. UC DAVIS - APR 21 & 22 | 161 | CLOSED | 0 | 0 | 780.126 | 780.126
PJ0004005 | 11/12: SUPPORT FOR SOFTBALL (PROJECT) | POPHAM, DONALD J. | CLOSED | 2011-11-09 | LA: SUPPORT SOFTBALL V. UCLA - MAR 27 | 161 | CLOSED | 0 | 0 | 441.78 | 441.78
PJ0004005 Total | [7 empty] | 0 | 0 | 9551.4 | 9551.4
PJ0004004 | SR 11/12: DESIGN TO RE-ROUTE CHEMICAL LINES AT ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | AD: GOSS ENGINEERING | 042A | CLOSED | 10310 | 0 | 10310 | 10310
PJ0004004 | SR 11/12: DESIGN TO RE-ROUTE CHEMICAL LINES AT ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | CP: PROJECT CONTINGENCY | 042A | CLOSED | 0 | 0 | 0 | 0
PJ0004004 | SR 11/12: DESIGN TO RE-ROUTE CHEMICAL LINES AT ANDERSON POOL | MOLLAN, CHERYL L. | CLOSED | 2011-11-10 | IN: SR 11/12: RE-ROUTE CHEMMICAL LINES AT MOTT POOL | 042A | CLOSED | 106.76 | 0 | 320.28 | 320.28
PJ0004004 Total | [7 empty] | 10416.76 | 0 | 10630.28 | 10630.28
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: ENGLEKIRK AND SABOL | 171 | CLOSED | 2345.44 | 0 | 2345.44 | 2345.44
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: HAYER CONSULTANTS - PLAN REVIEW | 171 | CLOSED | 2616.4282 | 0 | 2616.4282 | 2616.4282
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: JOC 11.022.013.04 STAPLES | 171 | CLOSED | 8248.9617 | 0 | 5919.4433 | 5919.4433
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: JOC 11.022.048 STAPLES | 171 | CLOSED | 295505.7627 | 0 | 295505.7627 | 295505.7627
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: JOC 11.023.011.01 STAPLES | 171 | CLOSED | 13147.9032 | 0 | 13147.9032 | 13147.9032
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: JOC 11.023.014 STAPLES | 171 | CLOSED | 89581.1062 | 0 | 89581.1062 | 89581.1062
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: OMNI DESIGN | 171 | CLOSED | 6002.7 | 0 | 6002.7 | 6002.7
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: OVERHEAD ON GORDIAN REFUND FOR JOC 11.022.013.05 | 171 | CLOSED | 0 | 0 | -2.97 | -2.97
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: STAPLES (LOW VALUE PUBLIC WORKS) | 171 | CLOSED | 3172.1327 | 0 | 3172.1327 | 3172.1327
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | AD: TOSTE GRADING AND PAVING | 171 | CLOSED | 0 | 0 | 2303.7742 | 2303.7742
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | ANTS: PROGRAM ALARMS AT POLY CANYON VILLAGE WAREHOUSE | 171 | CLOSED | 192.192 | 0 | 48.048 | 48.048
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | CP: PROJECT CONTINGENCY | 371 | CLOSED | 31013.69 | 0 | 0 | 0
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | EL: PURCHASE TRANSFORMER FOR PCV WAREHOUSE | 171 | CLOSED | 7200 | 0 | 6327.384 | 6327.384
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | IN: SITE WORK & GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | 171 | CLOSED | 1537.344 | 0 | 1697.484 | 1697.484
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | LA: LANDSCAPING FOR NEW PCV WAREHOUSE | 171 | CLOSED | 0 | 0 | 8020.61 | 8020.61
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | PA: PAINT METAL AT LOADING DOCK - NEW PCV WAREHOUSE | 171 | CLOSED | 0 | 0 | 237.456 | 237.456
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | PCV EL: ADDITIONAL OUTLETS FOR NEW PCV WAREHOUSE | 171 | CLOSED | 0 | 0 | 1011.24 | 1011.24
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | PCV PL: INSTALL IRRIGATION BACKFLOW FOR NEW PCV WAREHOUSE | 171 | CLOSED | 0 | 0 | 1205.352 | 1205.352
PJ0004002 | MJ:SITE WORK AND GRADING FOR FUTURE WAREHOUSE - WEST OF BLDG 371 | BRENNAN, MICHAEL | CLOSED | 2011-11-09 | PL:SUPPORT FOR SITE WORK | 171 | CLOSED | 4242.336 | 0 | 3828.966 | 3828.966
PJ0004002 Total | [7 empty] | 464805.9967 | 0 | 442968.2605 | 442968.2605
PJ0003998 | ADDITIONAL ELECTRICAL/DATA CONNECTIONS - BLD 10 RM 138 | LAMPMAN, GREG | CLOSED | 2011-11-01 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 181.25 | 0 | 0 | 0
PJ0003998 | ADDITIONAL ELECTRICAL/DATA CONNECTIONS - BLD 10 RM 138 | LAMPMAN, GREG | CLOSED | 2011-11-01 | EL: INSTALL ELECTRICAL IN EXISTING RACEWAY SEE PLAN | 010 | CLOSED | 1620.679 | 0 | 2144.196 | 2144.196
PJ0003998 | ADDITIONAL ELECTRICAL/DATA CONNECTIONS - BLD 10 RM 138 | LAMPMAN, GREG | CLOSED | 2011-11-01 | IN: ADDITIONAL ELECTRICAL/DATA CONNECTIONS - BLD 10 RM 138 | 010 | CLOSED | 192.168 | 0 | 160.14 | 160.14
PJ0003998 Total | [7 empty] | 1994.097 | 0 | 2304.336 | 2304.336
PJ0003996 | SR 11/12: ASSESS THE CONDITION OF THE RODEO ARENA LIGHTING - 77 | MAY, TOM | CLOSED | 2011-11-04 | IN: ASSESS THE CONDITION OF THE RODEO ARENA LIGHTING - 77 | 077 | CLOSED | 106.76 | 0 | 80.07 | 80.07
PJ0003996 Total | [7 empty] | 106.76 | 0 | 80.07 | 80.07
PJ0003995 | REPAIR 3" SUPPLY WATER LEAK - YOS T9 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-11-04 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 0 | 0 | 0 | 0
PJ0003995 | REPAIR 3" SUPPLY WATER LEAK - YOS T9 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-11-04 | EO:EXCAVATE AREA FOR WATER LEAK AT YOS T-9 | 114 | CLOSED | 0 | 0 | 923.64 | 923.64
PJ0003995 | REPAIR 3" SUPPLY WATER LEAK - YOS T9 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-11-04 | LA:PROVIDE SUPPORT FOR YOS T-9 WATER MAIN LEAK (NO LABOR) | 114 | CLOSED | 0 | 0 | 0 | 0
PJ0003995 | REPAIR 3" SUPPLY WATER LEAK - YOS T9 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-11-04 | PL:REPAIR 3' WATER MAIN LEAK AT YOS TOWER 9 | 114 | CLOSED | 0 | 0 | 2413.26 | 2413.26
PJ0003995 | REPAIR 3" SUPPLY WATER LEAK - YOS T9 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-11-04 | REPAIR DAMAGE | 114 | CLOSED | 0 | 0 | 2303.62 | 2303.62
PJ0003995 Total | [7 empty] | 0 | 0 | 5640.52 | 5640.52
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | AD: JOC 15.036.001 STAPLES | 061 | CLOSED | 342744.3046 | 0 | 342645.4259 | 342645.4259
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | AD: JOC 16.039.003 NEWTON | 061 | CLOSED | 20906.1201 | 0 | 20721.7163 | 20721.7163
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | AD: MAINO LVPW | 061 | CLOSED | 642 | 0 | 642 | 642
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | AD: MCKENNA | 061 | CLOSED | 5275.1 | 0 | 4350.62 | 4350.62
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | AD: RF KOEBER, INC (LVPW) | 061 | CLOSED | 5209.83 | 0 | 5209.83 | 5209.83
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 2175.38 | 0 | 0 | 0
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | EH&S: LAB CHARGES FOR SAMPLE ANALYSIS (MATERIALS ONLY) | 061 | CLOSED | 54 | 0 | 54 | 54
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | IN: SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | 061 | CLOSED | 706.44 | 0 | 1165.626 | 1165.626
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | LO: INSTALL ORANGE CORES IN THE PRESIDENTS SUITE BALCONY DOORS | 061 | CLOSED | 365.544 | 0 | 91.386 | 91.386
PJ0003994 | SP 14/15: REPAIR HOLES CAUSED BY BIRDS - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-11-03 | PA: PAINT FOR SPANOS LOGOS | 061 | CLOSED | 1155.264 | 0 | 418.668 | 418.668
PJ0003994 Total | [7 empty] | 379233.9827 | 0 | 375299.2722 | 375299.2722
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | AD: AIR POLLUTION CONTROL DISTRICT - NESHAPS 10-DAY NOTIFICATION | 070 | CLOSED | 0 | 0 | 402 | 402
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | CA:REMOVE PLATFORM AND AWNING FROM TRAILER | 070 | CLOSED | 0 | 0 | 3055.572 | 3055.572
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | EL: DISCONNECT POWER FROM TRAILER BEHIND BLDG. 70 - SEE DATES | 070 | CLOSED | 0 | 0 | 172.02 | 172.02
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | EO:CLEAN DIRT FROM DRIVEWAY AND REMOVE TRIPPING HAZARDS | 070 | CLOSED | 0 | 0 | 532.368 | 532.368
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | IN: REMOVE TRAILER BEHIND BUILDING - BUILDING 70 | 070 | CLOSED | 0 | 0 | 64.056 | 64.056
PJ0003993 | REMOVE TRAILER BEHIND BUILDING - BUILDING 70 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-11-03 | MO:MOVE AWNING FROM TRAILER BEHIND BLDG 70 | 070 | CLOSED | 0 | 0 | 24.144 | 24.144
PJ0003993 Total | [7 empty] | 0 | 0 | 4250.16 | 4250.16
PJ0003991 | INSTALL OUTLET & PARKING SPACE FOR 2 CARTS - BLD 117 | GALVEZ, CESAR | CLOSED | 2011-09-27 | CP: PROJECT CONTINGENCY | 117 | CLOSED | 121.39 | 0 | 0 | 0
PJ0003991 | INSTALL OUTLET & PARKING SPACE FOR 2 CARTS - BLD 117 | GALVEZ, CESAR | CLOSED | 2011-09-27 | EL: INSTALL TWO (2) 20AMP CIRCUITS FOR 2 GOLF CARTS -BLDG 117 | 117 | CLOSED | 714.3389 | 0 | 851.652 | 851.652
PJ0003991 | INSTALL OUTLET & PARKING SPACE FOR 2 CARTS - BLD 117 | GALVEZ, CESAR | CLOSED | 2011-09-27 | IN: INSTALL OUTLET & PARKING SPACE FOR 1 -2 CARTS - BLD 117 | 117 | CLOSED | 128.112 | 0 | 122.774 | 122.774
PJ0003991 | INSTALL OUTLET & PARKING SPACE FOR 2 CARTS - BLD 117 | GALVEZ, CESAR | CLOSED | 2011-09-27 | PA: PATCH/ PAINT STAIRWAY RETAINING WALL TO GOLF CART PARKING | 117 | CLOSED | 216.3817 | 0 | 219.06 | 219.06
PJ0003991 Total | [7 empty] | 1180.2226 | 0 | 1193.486 | 1193.486
PJ0003990 | INSTALL COUNTER TOP & ELECTRICAL OUTLETS - BLD 33 RM 473(NO EST) | LAMPMAN, GREG | CLOSED | 2011-11-01 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0003990 | INSTALL COUNTER TOP & ELECTRICAL OUTLETS - BLD 33 RM 473(NO EST) | LAMPMAN, GREG | CLOSED | 2011-11-01 | EL: INSTALL NEW ELECTRICAL OUTLETS IN BLDG. 33 RM. 473 | 033 | CLOSED | 0 | 0 | 1719.768 | 1719.768
PJ0003990 | INSTALL COUNTER TOP & ELECTRICAL OUTLETS - BLD 33 RM 473(NO EST) | LAMPMAN, GREG | CLOSED | 2011-11-01 | IN: INSTALL COUNTER TOP & ELECTRICAL OUTLETS - BLD 33 RM 473 | 033 | CLOSED | 0 | 0 | 96.084 | 96.084
PJ0003990 Total | [7 empty] | 0 | 0 | 1815.852 | 1815.852
PJ0003989 | RENOVATE COVE LIGHTING IN FOUNDERS ROOM 06-304 | GRIFFIN, PATRICK E. | CLOSED | 2011-10-28 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 132.44 | 0 | 0 | 0
PJ0003989 | RENOVATE COVE LIGHTING IN FOUNDERS ROOM 06-304 | GRIFFIN, PATRICK E. | CLOSED | 2011-10-28 | EL:REMOVE FLUORESCENT LIGHTING AND INSTALL LED FIXTURES- PAC | 006 | CLOSED | 1260.679 | 0 | 470.304 | 470.304
PJ0003989 | RENOVATE COVE LIGHTING IN FOUNDERS ROOM 06-304 | GRIFFIN, PATRICK E. | CLOSED | 2011-10-28 | IN: RENOVATE COVE LIGHTING IN FOUNDERS ROOM 06-304 | 006 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003989 Total | [7 empty] | 1457.175 | 0 | 534.36 | 534.36
PJ0003988 | INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-28 | CA: ASSIST ELECTRICIANS FAN INSTALLATIONS | 123B-M015 | CLOSED | 222.48 | 0 | 120 | 120
PJ0003988 | INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-28 | CP: PROJECT CONTINGENCY | 123B-M015 | CLOSED | 373.15 | 0 | 0 | 0
PJ0003988 | INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-28 | EL: INSTALL BETHROOM EXHAUST FANS | 123B-M015 | CLOSED | 3297.12 | 0 | 3081.544 | 3081.544
PJ0003988 | INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-28 | IN: INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | 123B-M015 | CLOSED | 211.932 | 0 | 211.932 | 211.932
PJ0003988 | INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-28 | PM: INSTALL EXHAUST FANS IN RESTROOMS - PETERSON RANCH MOBILES | 123B-M015 | CLOSED | 0 | 0 | 0 | 0
PJ0003988 Total | [7 empty] | 4104.682 | 0 | 3413.476 | 3413.476
PJ0003986 | CORRECT ITEMS FOUND IN 10/11/11 MAINTENANCE WALK-THRU - PAC 06 | MAY, TOM | CLOSED | 2011-11-02 | CA: CORRECT OCT. 2011 PAC MAINT WALK-THRU ITEMS | 006 | CLOSED | 0 | 0 | 928.865 | 928.865
PJ0003986 | CORRECT ITEMS FOUND IN 10/11/11 MAINTENANCE WALK-THRU - PAC 06 | MAY, TOM | CLOSED | 2011-11-02 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003986 | CORRECT ITEMS FOUND IN 10/11/11 MAINTENANCE WALK-THRU - PAC 06 | MAY, TOM | CLOSED | 2011-11-02 | CU: CORRECT OCT. 2011 PAC MAINT WALK-THRU ITEMS (N/L) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003986 | CORRECT ITEMS FOUND IN 10/11/11 MAINTENANCE WALK-THRU - PAC 06 | MAY, TOM | CLOSED | 2011-11-02 | LO: CORRECT OCT. 2011 PAC MAINT WALK-THRU ITEMS | 006 | CLOSED | 0 | 0 | 48.37 | 48.37
PJ0003986 | CORRECT ITEMS FOUND IN 10/11/11 MAINTENANCE WALK-THRU - PAC 06 | MAY, TOM | CLOSED | 2011-11-02 | PA: CORRECT OCT. 2011 PAC MAINT WALK-THRU ITEMS | 006 | CLOSED | 0 | 0 | 68.51 | 68.51
PJ0003986 Total | [7 empty] | 0 | 0 | 1045.745 | 1045.745
PJ0003985 | FP 11/12: DEVELOP PLANS FOR PARKING AT CAMPUS WAY | BRENNAN, MICHAEL | CLOSED | 2011-10-31 | AD: WALLACE GROUP | GEN-PARK | CLOSED | 85400 | 0 | 81289.74 | 81289.74
PJ0003985 | FP 11/12: DEVELOP PLANS FOR PARKING AT CAMPUS WAY | BRENNAN, MICHAEL | CLOSED | 2011-10-31 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 0 | 0 | 0 | 0
PJ0003985 | FP 11/12: DEVELOP PLANS FOR PARKING AT CAMPUS WAY | BRENNAN, MICHAEL | CLOSED | 2011-10-31 | IN: FP 11/12: DEVELOP PLANS FOR PARKING AT CAMPUS WAY | GEN-PARK | CLOSED | 53.38 | 0 | 53.38 | 53.38
PJ0003985 Total | [7 empty] | 85453.38 | 0 | 81343.12 | 81343.12
PJ0003984 | REPAIR LOWER ROOF - BLD 82 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-31 | AD: QUAGLINO ROOFING | 082 | CLOSED | 3370.5 | 0 | 3370.5 | 3370.5
PJ0003984 | REPAIR LOWER ROOF - BLD 82 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-31 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 337.05 | 0 | 0 | 0
PJ0003984 Total | [7 empty] | 3707.55 | 0 | 3370.5 | 3370.5
PJ0003983 | ANALYZE DAS SITES FOR ATT PROPOSAL | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-28 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003983 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003982 | REPAIR OR REPLACE HARDWARE - S. EXTERIOR DOOR - BLD 19 (NO EST) | MAY, TOM | CLOSED | 2011-10-28 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 0 | 0 | 0 | 0
PJ0003982 | REPAIR OR REPLACE HARDWARE - S. EXTERIOR DOOR - BLD 19 (NO EST) | MAY, TOM | CLOSED | 2011-10-28 | LO: REPAIR DOOR & INSTALL NEW CORE - BLDG 19 SW OF MAIN KITCHEN | 019 | CLOSED | 0 | 0 | 88.044 | 88.044
PJ0003982 Total | [7 empty] | 0 | 0 | 88.044 | 88.044
PJ0003981 | FIRE ALARM UPGRADE - BLD 192 (MAINT) | GALVEZ, CESAR | CLOSED | 2011-10-27 | AD: DEEP BLUE INTEGRATION | 192 | CLOSED | 0 | 0 | 1532.2 | 1532.2
PJ0003981 | FIRE ALARM UPGRADE - BLD 192 (MAINT) | GALVEZ, CESAR | CLOSED | 2011-10-27 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0003981 | FIRE ALARM UPGRADE - BLD 192 (MAINT) | GALVEZ, CESAR | CLOSED | 2011-10-27 | EL: UPGRADE FIRE ALARM PANEL AT ENGR. IV - BLDG. 192 | 192 | CLOSED | 0 | 0 | 208.8636 | 208.8636
PJ0003981 Total | [7 empty] | 0 | 0 | 1741.0636 | 1741.0636
PJ0003980 | REFURBISH CABINETS - BLD 27 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: TEMPLE BUILDERS | 027 | CLOSED | 910.57 | 0 | 1021.5076 | 1021.5076
PJ0003980 | REFURBISH CABINETS - BLD 27 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 94.26 | 0 | 0 | 0
PJ0003980 | REFURBISH CABINETS - BLD 27 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | IN: REFURBISH CABINETS - BLD 27 RM 115 | 027 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003980 Total | [7 empty] | 1036.858 | 0 | 1053.5356 | 1053.5356
PJ0003979 | INSTALL BIKE RACKS - SOUTH PERIMETER AT REC CENTER AREA (MAINT) | GALVEZ, CESAR | CLOSED | 2011-10-27 | CA: REMOVE, RELOCATE AND MOUNT NEW BIKE RACKS RACKS @ UU PLAZA | GENERAL | CLOSED | 0 | 0 | 4254.68 | 4254.68
PJ0003979 | INSTALL BIKE RACKS - SOUTH PERIMETER AT REC CENTER AREA (MAINT) | GALVEZ, CESAR | CLOSED | 2011-10-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003979 Total | [7 empty] | 0 | 0 | 4254.68 | 4254.68
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: ASAP REPROGRAPHICS | 014 | CLOSED | 0 | 0 | 44.82 | 44.82
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: ATD WINDOW TINTING | 014 | CLOSED | 4381.1471 | 0 | 4381.1471 | 4381.1471
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: ENGLEKIRK AND SABOL | 014 | CLOSED | 535 | 0 | 0 | 0
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: FLOOR CONNECTION | 014 | CLOSED | 14828.5201 | 0 | 14846.892 | 14846.892
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: JOC 11.023.028 STAPLES | 014 | CLOSED | 68751.8763 | 0 | 68751.8763 | 68751.8763
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: JOC 12.024.033 | 014 | CLOSED | 12141.4826 | 0 | 12141.4826 | 12141.4826
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: MCKENNA ENVIRONMENTAL | 014 | CLOSED | 4108.8 | 0 | 3852 | 3852
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: MORELAND THOMPSON, INC. | 014 | CLOSED | 5314.69 | 0 | 5383.5017 | 5383.5017
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | AD: REA AND LUKER ARCHITECTS | 014 | CLOSED | 14434.3 | 0 | 12963.05 | 12963.05
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 102.54 | 0 | 0 | 0
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | CPE: MATERIALS USED ON ES WORK ORDER 205329 (MAT, ONLY) | 014 | CLOSED | 0 | 0 | 4094.388 | 4094.388
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | EL:INSTALL STROBE- CONSTRUCTION SUPPORT BLDG 14- OCIO | 014 | CLOSED | 3300.0036 | 0 | 1279.1671 | 1279.1671
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | ES:INSTALL FLEX DUCT, NEW GRILLS AND BALANCE SYSTEM | 014 | CLOSED | 12537.7034 | 0 | 5658.258 | 5658.258
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | IN: OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | 014 | CLOSED | 384.336 | 0 | 768.672 | 768.672
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | LO:REMOVE CORES, INSTALL NEW HARDWARE AND CORES-BLDG 14, OCIO | 014 | CLOSED | 5898.1925 | 0 | 6072.258 | 6072.258
PJ0003978 | OFFICE REMODEL - BLD 14 RMS 113, 114, & 115 | MOLLAN, CHERYL L. | CLOSED | 2011-10-25 | PA:PATCH AND PAINT TENNANT IMPROVEMENT FOR OCIO- BLDG 14 | 014 | CLOSED | 13072.8 | 0 | 10455.126 | 10455.126
PJ0003978 Total | [7 empty] | 159791.3916 | 0 | 150692.6388 | 150692.6388
PJ0003977 | RESEARCH VENTILATION ISSUES IN RESTROOMS - SOUTH MOUNTAIN HALLS | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-24 | AD: GOSS ENGINEERING | RESIDENCE | CLOSED | 3317 | 0 | 3317 | 3317
PJ0003977 | RESEARCH VENTILATION ISSUES IN RESTROOMS - SOUTH MOUNTAIN HALLS | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-24 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 522.61 | 0 | 0 | 0
PJ0003977 | RESEARCH VENTILATION ISSUES IN RESTROOMS - SOUTH MOUNTAIN HALLS | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-24 | ES: VENTILATION RETROFIT | RESIDENCE | CLOSED | 1909.0986 | 0 | 2115.84 | 2115.84
PJ0003977 Total | [7 empty] | 5748.7086 | 0 | 5432.84 | 5432.84
PJ0003976 | INSTALL ACCESS FOR DIRECTV - BLD 65 ROOF | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-25 | AD: QUAGLINO ROOFING | 065 | CLOSED | 535 | 0 | 438.7 | 438.7
PJ0003976 | INSTALL ACCESS FOR DIRECTV - BLD 65 ROOF | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-25 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 255.44 | 0 | 0 | 0
PJ0003976 | INSTALL ACCESS FOR DIRECTV - BLD 65 ROOF | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-25 | EL: INSTALL CONDUIT PATH AND CABLE FOR DIRECTV - UU 065 ROOF | 065 | CLOSED | 3300.6802 | 0 | 1356.792 | 1356.792
PJ0003976 | INSTALL ACCESS FOR DIRECTV - BLD 65 ROOF | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-25 | IN: INSTALL ACCESS FOR DIRECTV - BLD 65 ROOF | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003976 Total | [7 empty] | 4219.2322 | 0 | 1923.604 | 1923.604
PJ0003975 | BANNER PLANNING - INSPECT POLE STABILITY - GENERAL | MOLLAN, CHERYL L. | CLOSED | 2011-10-24 | AD: BUEHLER AND BUEHLER | GENERAL | CLOSED | 4500 | 0 | 4500 | 4500
PJ0003975 | BANNER PLANNING - INSPECT POLE STABILITY - GENERAL | MOLLAN, CHERYL L. | CLOSED | 2011-10-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003975 Total | [7 empty] | 4500 | 0 | 4500 | 4500
PJ0003974 | SUPPLY POWER AND ANCHOR EQUIPMENT - DAIRY MILKING PARLOR | LAMPMAN, GREG | CLOSED | 2011-10-21 | AD: JOC 12.024.020 STAPLES | 018 | CLOSED | 6020.4941 | 0 | 6020.4941 | 6020.4941
PJ0003974 | SUPPLY POWER AND ANCHOR EQUIPMENT - DAIRY MILKING PARLOR | LAMPMAN, GREG | CLOSED | 2011-10-21 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 1069.19 | 0 | 0 | 0
PJ0003974 | SUPPLY POWER AND ANCHOR EQUIPMENT - DAIRY MILKING PARLOR | LAMPMAN, GREG | CLOSED | 2011-10-21 | EL: INSTALL OWNER SUPPLIED VFD | 018 | CLOSED | 4351.0262 | 0 | 4810.992 | 4810.992
PJ0003974 | SUPPLY POWER AND ANCHOR EQUIPMENT - DAIRY MILKING PARLOR | LAMPMAN, GREG | CLOSED | 2011-10-21 | IN: SUPPLY POWER AND ANCHOR EQUIPMENT - DAIRY MILKING PARLOR | 018 | CLOSED | 320.28 | 0 | 320.28 | 320.28
PJ0003974 Total | [7 empty] | 11760.9903 | 0 | 11151.7661 | 11151.7661
PJ0003973 | CONNECT NEW VFDS AND PUMPS AT ITRC - BLD 136 | POLVI, STEVEN | CLOSED | 2011-10-21 | CA: CORE 4 HOLES FOR ELECTRICIANS AT ITRC - BLD 136 | 136 | CLOSED | 1112.4 | 0 | 856.632 | 856.632
PJ0003973 | CONNECT NEW VFDS AND PUMPS AT ITRC - BLD 136 | POLVI, STEVEN | CLOSED | 2011-10-21 | CP: PROJECT CONTINGENCY | 136 | CLOSED | 3524.08 | 0 | 0 | 0
PJ0003973 | CONNECT NEW VFDS AND PUMPS AT ITRC - BLD 136 | POLVI, STEVEN | CLOSED | 2011-10-21 | EL: ITRC SWITCH GEAR UPGRADE & VFD CONNECTIONS - BLDG 136 | 136 | CLOSED | 40802.7326 | 0 | 32665.3034 | 32665.3034
PJ0003973 Total | [7 empty] | 45439.2126 | 0 | 33521.9354 | 33521.9354
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: AGGSON'S GLASS | 003 | CLOSED | 568.7157 | 0 | 568.7157 | 568.7157
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: ASAP REPROGRAPHICS | 003 | CLOSED | 0 | 0 | 215 | 215
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: DESIGN ARC | 003 | CLOSED | 107930.365 | 0 | 106840.3774 | 106840.3774
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: GORDON INDUSTRIAL PURCHASE - PARTS TO BE USED BY JOC | 003 | CLOSED | 18735.04 | 0 | 18648.0991 | 18648.0991
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: JOC 11.023.038 STAPLES | 003 | CLOSED | 185355.565 | 0 | 183436.2739 | 183436.2739
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: KI FURNITURE | 003 | CLOSED | 67614.2095 | 0 | 67178.131 | 67178.131
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: PURCHASE PLUG MOLD STRIP FOR BUSINESS DEPT TECH | 003 | CLOSED | 0 | 0 | 46.11 | 46.11
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: R.F. KOERBER | 003 | CLOSED | 7128.6289 | 0 | 7128.6289 | 7128.6289
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: SIGNAL PERFECTION LTD | 003 | CLOSED | 1338.5914 | 0 | 1341.0631 | 1341.0631
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | ANTS: ASSIST WITH FIRE AND SECURITY ALARM WORK AT BLDG 3 RM 111 | 003 | CLOSED | 120.12 | 0 | 72.072 | 72.072
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | CA: MAKE SIGNAGE FOR 03-111 | 003 | CLOSED | 1127.76 | 0 | 518.22 | 518.22
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 18475.49 | 0 | 0 | 0
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | CPE:MINI SPLIT AC UNIT | 003 | CLOSED | 7165.656 | 0 | 4964.664 | 4964.664
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | CU:FINAL ROOM CLEAN UP | 003 | CLOSED | 787.104 | 0 | 245.97 | 245.97
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | EL:INSTALL NEW SUB PANEL AND FIRE DEVICES | 003 | CLOSED | 13502.0525 | 0 | 13147.0123 | 13147.0123
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | IN: UPDATE SEATING & TECHNOLOGY IN TIERED CLASSRM - BLD 3 RM 111 | 003 | CLOSED | 1537.344 | 0 | 1441.26 | 1441.26
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | LO: SUPPORT FOR REMODEL | 003 | CLOSED | 2980.44 | 0 | 2343.984 | 2343.984
PJ0003972 | UPDATE SEATING AND TECHNOLOGY IN TIERED CLASSROOM - BLD 3 RM 111 | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | PA:PAINT CLASSROOM AFTER REMODEL | 003 | CLOSED | 6549.12 | 0 | 3092.682 | 3092.682
PJ0003972 Total | [7 empty] | 440916.202 | 0 | 411228.2634 | 411228.2634
PJ0003971 | DESIGN TO UPDATE SPACE FOR STUDY & SOCIALIZING - BLD 03 HALLWAY | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | AD: DESIGN ARC - SCHEMATIC DESIGN | 003 | CLOSED | 29438.91 | 0 | 26277.06 | 26277.06
PJ0003971 | DESIGN TO UPDATE SPACE FOR STUDY & SOCIALIZING - BLD 03 HALLWAY | BRENNAN, MICHAEL | CLOSED | 2011-10-21 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 2708.49 | 0 | 0 | 0
PJ0003971 Total | [7 empty] | 32147.4 | 0 | 26277.06 | 26277.06
PJ0003970 | INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | MOLLAN, CHERYL L. | CLOSED | 2011-10-21 | CA: CUT HOLES FOR ACCESS PANELS AND MOVE DISPENSERS 13-115A | 013 | CLOSED | 338.328 | 0 | 921.6 | 921.6
PJ0003970 | INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | MOLLAN, CHERYL L. | CLOSED | 2011-10-21 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 432.75 | 0 | 0 | 0
PJ0003970 | INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | MOLLAN, CHERYL L. | CLOSED | 2011-10-21 | EL:INSTALL NEW ELECTRICAL FOR WATER HEATER AND MOISTURE CONTROL | 013 | CLOSED | 2280.6814 | 0 | 1031.964 | 1031.964
PJ0003970 | INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | MOLLAN, CHERYL L. | CLOSED | 2011-10-21 | IN: INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | 013 | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0003970 | INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | MOLLAN, CHERYL L. | CLOSED | 2011-10-21 | PA: PATCH/PAINT AS NEEDED FOR REPAIRS TO ACCESS PANEL 13-115A | 013 | CLOSED | 534.912 | 0 | 1603.464 | 1603.464
PJ0003970 | INSTALL MOISTURE CONTROL SYSTEM - BLD 13 RM 115A | MOLLAN, CHERYL L. | CLOSED | 2011-10-21 | PL:INSTALL PLUMBING FOR MOISTURE CONTROLLER AND HOT WATER HEATER | 013 | CLOSED | 10650.0962 | 0 | 10220.863 | 10220.863
PJ0003970 Total | [7 empty] | 14364.8796 | 0 | 13873.975 | 13873.975
PJ0003968 | CAME TO INSTALL PANIC BUTTON - BLD 40 RM 120 | MAY, TOM | CLOSED | 2011-10-19 | ANTS:ASSIST WITH CAME SECURITY PANIC BUTTON FOR 40-120 | 040 | CLOSED | 96.096 | 0 | 36.036 | 36.036
PJ0003968 | CAME TO INSTALL PANIC BUTTON - BLD 40 RM 120 | MAY, TOM | CLOSED | 2011-10-19 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 12.81 | 0 | 0 | 0
PJ0003968 | CAME TO INSTALL PANIC BUTTON - BLD 40 RM 120 | MAY, TOM | CLOSED | 2011-10-19 | IN: CAME TO INSTALL PANIC BUTTON - BLD 40 RM 120 | 040 | CLOSED | 32.028 | 0 | 96.084 | 96.084
PJ0003968 Total | [7 empty] | 140.934 | 0 | 132.12 | 132.12
PJ0003967 | INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-18 | AD: BOB'S CRANE SERVICE | 031 | CLOSED | 588.5 | 0 | 588.5 | 588.5
PJ0003967 | INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-18 | CA: BARRACADE RD | 031 | CLOSED | 149.7452 | 0 | 28.194 | 28.194
PJ0003967 | INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-18 | CP: PROJECT CONTINGENCY | 031 | CLOSED | 368.55 | 0 | 0 | 0
PJ0003967 | INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-18 | EL: PROVIDE ELECT SERVICE TO AC UNIT | 031 | CLOSED | 1830.3413 | 0 | 2243.6654 | 2243.6654
PJ0003967 | INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-18 | ES: INSTALL AC UNIT SERVER RM | 031 | CLOSED | 7162.5782 | 0 | 5829.822 | 5829.822
PJ0003967 | INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-10-18 | IN: INSTALL A/C UNIT IN SERVER ROOM - BLD 31 RM 213 | 031 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0003967 Total | [7 empty] | 10227.8268 | 0 | 8722.2094 | 8722.2094
PJ0003966 | PLAN REVIEW TO INSTALL 6 HIGHBRIGHT MONITORS - BOOKSTORE WINDOW | LAMPMAN, GREG | CLOSED | 2011-10-18 | AD: ENGLEKIRK AND SABOL | 065 | CLOSED | 535 | 0 | 535 | 535
PJ0003966 | PLAN REVIEW TO INSTALL 6 HIGHBRIGHT MONITORS - BOOKSTORE WINDOW | LAMPMAN, GREG | CLOSED | 2011-10-18 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 120.71 | 0 | 0 | 0
PJ0003966 | PLAN REVIEW TO INSTALL 6 HIGHBRIGHT MONITORS - BOOKSTORE WINDOW | LAMPMAN, GREG | CLOSED | 2011-10-18 | IN:PLAN REVIEW TO INSTALL 6 HIGHBRIGHT MONITORS-BOOKSTORE WINDOW | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003966 Total | [7 empty] | 783.822 | 0 | 663.112 | 663.112
PJ0003965 | SUPPORT FOR PRESIDENT'S CABINET - NOV. 11, 2011 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-10-18 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 0 | 0 | 0 | 0
PJ0003965 | SUPPORT FOR PRESIDENT'S CABINET - NOV. 11, 2011 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-10-18 | CU: CUSTODIAL WORK DAY IN PREPARATION FOR PRES. CABINET. | 007 | CLOSED | 0 | 0 | 3053.5959 | 3053.5959
PJ0003965 | SUPPORT FOR PRESIDENT'S CABINET - NOV. 11, 2011 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-10-18 | CU: SUPPORT FOR PRESIDENT'S CABINET - NOV 11 | 007 | CLOSED | 0 | 0 | 1666.705 | 1666.705
PJ0003965 Total | [7 empty] | 0 | 0 | 4720.3009 | 4720.3009
PJ0003960 | CLEAN MOTT NORTHEAST STAIRWELL WINDOWS - MOTT 42 | LOOSLEY, SCOTT L. | CLOSED | 2011-10-12 | AD: COASTAL JANITORIAL | 042 | CLOSED | 123.05 | 0 | 123.05 | 123.05
PJ0003960 | CLEAN MOTT NORTHEAST STAIRWELL WINDOWS - MOTT 42 | LOOSLEY, SCOTT L. | CLOSED | 2011-10-12 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 12.31 | 0 | 0 | 0
PJ0003960 Total | [7 empty] | 135.36 | 0 | 123.05 | 123.05
PJ0003958 | SMART ROOM INSTALL OF A/V EQUIP - KEN LIB CAFE 35 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-09-13 | CA:KENNEDY LIBRARY CAFE - FOR SMART ROOM INSTALLATION: | 035 | CLOSED | 285.552 | 0 | 337.062 | 337.062
PJ0003958 | SMART ROOM INSTALL OF A/V EQUIP - KEN LIB CAFE 35 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-09-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0003958 | SMART ROOM INSTALL OF A/V EQUIP - KEN LIB CAFE 35 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-09-13 | EL:KENNEDY LIBRARY CAFE - FOR SMART ROOM INSTALLATION: | 035 | CLOSED | 1318.656 | 0 | 1853.94 | 1853.94
PJ0003958 | SMART ROOM INSTALL OF A/V EQUIP - KEN LIB CAFE 35 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-09-13 | IN: SMART ROOM INSTALL OF A/V EQUIP - KEN LIB CAFE 35 | 035 | CLOSED | 0 | 0 | 32.028 | 32.028
PJ0003958 | SMART ROOM INSTALL OF A/V EQUIP - KEN LIB CAFE 35 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-09-13 | PA:KENNEDY LIBRARY CAFE - FOR SMART ROOM INSTALLATION: | 035 | CLOSED | 0 | 0 | 118.728 | 118.728
PJ0003958 Total | [7 empty] | 1604.208 | 0 | 2341.758 | 2341.758
PJ0003955 | COMPLETE TOUCH-UP AFTER RENOVATION - BLDG 58-107 | LAMPMAN, GREG | CLOSED | 2011-08-12 | CA: INSTALL PAPER TOWEL DISP. | 058 | CLOSED | 0 | 0 | 173.1535 | 173.1535
PJ0003955 | COMPLETE TOUCH-UP AFTER RENOVATION - BLDG 58-107 | LAMPMAN, GREG | CLOSED | 2011-08-12 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 0 | 0 | 0 | 0
PJ0003955 | COMPLETE TOUCH-UP AFTER RENOVATION - BLDG 58-107 | LAMPMAN, GREG | CLOSED | 2011-08-12 | PA: PATCH HOLES IN WALL AND PAINT | 058 | CLOSED | 0 | 0 | 237.456 | 237.456
PJ0003955 Total | [7 empty] | 0 | 0 | 410.6095 | 410.6095
PJ0003952 | MOVE BLUE PHONE TO CORNER OF BLDG. 154 (MAINT) | MAY, TOM | CLOSED | 2011-09-27 | CA: INSTALL BLUE PHONE TO NORTH WALL OF ANC BUILDING | 154 | CLOSED | 0 | 0 | 645.815 | 645.815
PJ0003952 | MOVE BLUE PHONE TO CORNER OF BLDG. 154 (MAINT) | MAY, TOM | CLOSED | 2011-09-27 | CP: PROJECT CONTINGENCY | 154 | CLOSED | 0 | 0 | 0 | 0
PJ0003952 | MOVE BLUE PHONE TO CORNER OF BLDG. 154 (MAINT) | MAY, TOM | CLOSED | 2011-09-27 | EL: INSTALL POWER TO NEW BLUE PHONE ON N. WALL OF ANC BLDG. | GENERAL | CLOSED | 0 | 0 | 423.1304 | 423.1304
PJ0003952 | MOVE BLUE PHONE TO CORNER OF BLDG. 154 (MAINT) | MAY, TOM | CLOSED | 2011-09-27 | IN: MOVE BLUE PHONE TO CORNER OF BLDG. 154 | GENERAL | CLOSED | 0 | 0 | 53.38 | 53.38
PJ0003952 Total | [7 empty] | 0 | 0 | 1122.3254 | 1122.3254
PJ0003951 | HAZARD ANALYSIS REPORT ON THE MODULAR HOUSE - ARCH CANYON | LAMPMAN, GREG | CLOSED | 2011-09-26 | AD: MCKENNA ENVIRONMENTAL | 095 | CLOSED | 1257.25 | 0 | 1257.25 | 1257.25
PJ0003951 | HAZARD ANALYSIS REPORT ON THE MODULAR HOUSE - ARCH CANYON | LAMPMAN, GREG | CLOSED | 2011-09-26 | CP: PROJECT CONTINGENCY | 095 | CLOSED | 125.73 | 0 | 0 | 0
PJ0003951 Total | [7 empty] | 1382.98 | 0 | 1257.25 | 1257.25
PJ0003950 | ESTIMATING FOR RESIDENCE HALLS FIRE SPRINKLERS | LAMPMAN, GREG | CLOSED | 2011-09-26 | AD: ALPHA FIRE | RESIDENCE | CLOSED | 6955 | 0 | 6955 | 6955
PJ0003950 | ESTIMATING FOR RESIDENCE HALLS FIRE SPRINKLERS | LAMPMAN, GREG | CLOSED | 2011-09-26 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 695.5 | 0 | 0 | 0
PJ0003950 Total | [7 empty] | 7650.5 | 0 | 6955 | 6955
PJ0003948 | SR 11/12: REPAIR/REPLACE HEATING HOT WATER VALVES - FON - BLD 47 | MAY, TOM | CLOSED | 2011-09-23 | AD: JOC 11.022.046 STAPLES | U-UDOR | CLOSED | 13680.75 | 0 | 13680.75 | 13680.75
PJ0003948 | SR 11/12: REPAIR/REPLACE HEATING HOT WATER VALVES - FON - BLD 47 | MAY, TOM | CLOSED | 2011-09-23 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0003948 | SR 11/12: REPAIR/REPLACE HEATING HOT WATER VALVES - FON - BLD 47 | MAY, TOM | CLOSED | 2011-09-23 | CPE:REPAIR OR ASSIST IN REPLACEMENT OF HW VALVES TO FON | U-UDOR | CLOSED | 4927.0439 | 0 | 3678.475 | 3678.475
PJ0003948 | SR 11/12: REPAIR/REPLACE HEATING HOT WATER VALVES - FON - BLD 47 | MAY, TOM | CLOSED | 2011-09-23 | EO:ASSIST WITH HOT WATER VALVE REPAIR TO FON | U-UDOR | CLOSED | 1161.16 | 0 | 605.99 | 605.99
PJ0003948 | SR 11/12: REPAIR/REPLACE HEATING HOT WATER VALVES - FON - BLD 47 | MAY, TOM | CLOSED | 2011-09-23 | IN: REPAIR/REPLACE HEATING HOT WATER VALVES TO FON - BLD 47 | U-UDOR | CLOSED | 160.14 | 0 | 160.14 | 160.14
PJ0003948 | SR 11/12: REPAIR/REPLACE HEATING HOT WATER VALVES - FON - BLD 47 | MAY, TOM | CLOSED | 2011-09-23 | PL: ASSIST WITH SHUT-DOWN FOR HOT WATER VALVE REPLACEMENT- FON | U-UDOR | CLOSED | 242.1245 | 0 | 1007.695 | 1007.695
PJ0003948 Total | [7 empty] | 20171.2184 | 0 | 19133.05 | 19133.05
PJ0003947 | CONSULTIVE PROCESS / DISTRIBUTION SERVICES RELOCATION - BLDG 082 | LAMPMAN, GREG | CLOSED | 2011-09-23 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 0 | 0 | 0 | 0
PJ0003947 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003946 | SR 11/12: ADD HANDRAILS AT EXTERIOR STAIRS - BLD 51 | MAY, TOM | CLOSED | 2011-09-22 | AD: JOC 11.022.045 STAPLES | 051 | CLOSED | 8468.5 | 0 | 8468.5 | 8468.5
PJ0003946 | SR 11/12: ADD HANDRAILS AT EXTERIOR STAIRS - BLD 51 | MAY, TOM | CLOSED | 2011-09-22 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003946 | SR 11/12: ADD HANDRAILS AT EXTERIOR STAIRS - BLD 51 | MAY, TOM | CLOSED | 2011-09-22 | IN: SR 11/12: ADD HANDRAILS AT EXTERIOR STAIRS - BLD 51 | 051 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0003946 Total | [7 empty] | 8575.26 | 0 | 8575.26 | 8575.26
PJ0003945 | REMOVE WHITEBOARD AND OVERHEAD SHELVING - 43A-451/453 | BRENNAN, MICHAEL | CLOSED | 2011-09-23 | CA: RELOCATE OVERHEAD CABINETS AND WHITEBOARD | 043A | CLOSED | 388.6718 | 0 | 355.32 | 355.32
PJ0003945 | REMOVE WHITEBOARD AND OVERHEAD SHELVING - 43A-451/453 | BRENNAN, MICHAEL | CLOSED | 2011-09-23 | CP: PROJECT CONTINGENCY | 043A | CLOSED | 51.92 | 0 | 0 | 0
PJ0003945 | REMOVE WHITEBOARD AND OVERHEAD SHELVING - 43A-451/453 | BRENNAN, MICHAEL | CLOSED | 2011-09-23 | PA:TOUCH UP WALLS | 043A | CLOSED | 130.728 | 0 | 267.456 | 267.456
PJ0003945 Total | [7 empty] | 571.3198 | 0 | 622.776 | 622.776
PJ0003944 | TEST SOUNDPROOFING FOR ASBESTOS - BLDG 15-135 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2011-09-23 | AD: SAMPLE SOUNDPROOFING FOR ASBESTOS TESTING - BLDG 15-135 | 015 | CLOSED | 0 | 0 | 416.448 | 416.448
PJ0003944 | TEST SOUNDPROOFING FOR ASBESTOS - BLDG 15-135 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2011-09-23 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 0 | 0 | 0 | 0
PJ0003944 | TEST SOUNDPROOFING FOR ASBESTOS - BLDG 15-135 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2011-09-23 | EH&S: TEST SOUNDPROOFING FOR ASBESTOS - BLDG 15-135 | 015 | CLOSED | 0 | 0 | 246.048 | 246.048
PJ0003944 | TEST SOUNDPROOFING FOR ASBESTOS - BLDG 15-135 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2011-09-23 | IN: TEST SOUNDPROOFING FOR ASBESTOS - BLDG 15-135 | 015 | CLOSED | 0 | 0 | 64.056 | 64.056
PJ0003944 Total | [7 empty] | 0 | 0 | 726.552 | 726.552
PJ0003943 | REMOVE FURNITURE/PAINT WALLS - BLDG 70 RM 207 | MOLLAN, CHERYL L. | CLOSED | 2011-09-23 | CA:DISASSEMBLE OFFICE FURNITURE | 070 | CLOSED | 305.94 | 0 | 230.238 | 230.238
PJ0003943 | REMOVE FURNITURE/PAINT WALLS - BLDG 70 RM 207 | MOLLAN, CHERYL L. | CLOSED | 2011-09-23 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 114.92 | 0 | 0 | 0
PJ0003943 | REMOVE FURNITURE/PAINT WALLS - BLDG 70 RM 207 | MOLLAN, CHERYL L. | CLOSED | 2011-09-23 | MO:MOVE OFFICE FURNITURE TO ESURPLUS | 070 | CLOSED | 129.6 | 0 | 24.144 | 24.144
PJ0003943 | REMOVE FURNITURE/PAINT WALLS - BLDG 70 RM 207 | MOLLAN, CHERYL L. | CLOSED | 2011-09-23 | PA:PATCH HOLES IN WALL AND PAINT CAL POLY "CARLY WHITE". | 070 | CLOSED | 713.64 | 0 | 532.512 | 532.512
PJ0003943 Total | [7 empty] | 1264.1 | 0 | 786.894 | 786.894
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | AD: JL FASULO DRYWALL | 057 | CLOSED | 280 | 0 | 280 | 280
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | CA:ASSIST ENGR. SVCS. WITH FURNACE REPLACEMENT AT VET CLINIC | 057 | CLOSED | 5519.6207 | 0 | 4470.756 | 4470.756
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | CP: PROJECT CONTINGENCY | 057 | CLOSED | 0 | 0 | 0 | 0
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | EL:ASSIST ENGIN. SERVICES IN REPLACING VET CLINIC FURNACE | 057 | CLOSED | 1800.5678 | 0 | 699.09 | 699.09
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | ES:REPLACE VET CLINIC FURNACE | 057 | CLOSED | 9768.9923 | 0 | 12421.6872 | 12421.6872
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | IN: SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | 057 | CLOSED | 53.38 | 0 | 80.07 | 80.07
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | PA:PATCH AND PAINT FRONT ROOM IN VET CLINIC-FURNACE REPLACEMENT | 057 | CLOSED | 1531.6265 | 0 | 1102.46 | 1102.46
PJ0003942 | SR 11/12: REPLACE VET HOSPITAL FURNACE - BLD 57 | MAY, TOM | CLOSED | 2011-09-22 | PL:ASSIST ENGIN SERVICES IN REPLACING VET CLINIC FURNACE | 057 | CLOSED | 2679.6646 | 0 | 2701.23 | 2701.23
PJ0003942 Total | [7 empty] | 21633.8519 | 0 | 21755.2932 | 21755.2932
PJ0003941 | RE-ROOF LOWER ROOF OVER STUDY LOUNGE - TENAYA HALL | GALVEZ, CESAR | CLOSED | 2011-09-21 | AD: JOC 12.024.017 STAPLES | 110 | CLOSED | 41094.8801 | 0 | 41094.8801 | 41094.8801
PJ0003941 | RE-ROOF LOWER ROOF OVER STUDY LOUNGE - TENAYA HALL | GALVEZ, CESAR | CLOSED | 2011-09-21 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 2075.45 | 0 | 0 | 0
PJ0003941 | RE-ROOF LOWER ROOF OVER STUDY LOUNGE - TENAYA HALL | GALVEZ, CESAR | CLOSED | 2011-09-21 | IN: RE-ROOF LOWER ROOF OVER STUDY LOUNGE - TENAYA HALL | 110 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003941 Total | [7 empty] | 43298.4421 | 0 | 41222.9921 | 41222.9921
PJ0003940 | INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | BRENNAN, MICHAEL | CLOSED | 2011-09-20 | AD: ENGLEKIRK AND SABOL | 035 | CLOSED | 535 | 0 | 535 | 535
PJ0003940 | INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | BRENNAN, MICHAEL | CLOSED | 2011-09-20 | AD: JOC 11.022.044 STAPLES | 035 | CLOSED | 22735.5633 | 0 | 22735.5633 | 22735.5633
PJ0003940 | INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | BRENNAN, MICHAEL | CLOSED | 2011-09-20 | AD: SHIPPING CHARGES -PLANS TO ENGLEKIRK FOR SEISMIC PEER REVIEW | 035 | CLOSED | 0 | 0 | 11.028 | 11.028
PJ0003940 | INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | BRENNAN, MICHAEL | CLOSED | 2011-09-20 | AD: SHORELINE AWNING | 035 | CLOSED | 4922 | 0 | 4922 | 4922
PJ0003940 | INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | BRENNAN, MICHAEL | CLOSED | 2011-09-20 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 2832.07 | 0 | 0 | 0
PJ0003940 | INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | BRENNAN, MICHAEL | CLOSED | 2011-09-20 | IN: INSTALL AWNINGS AND SHADE SAILS - KEN LIB 35 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003940 Total | [7 empty] | 31152.7453 | 0 | 28331.7033 | 28331.7033
PJ0003939 | STUDENT APARTMENT MAINTENANCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2011-09-21 | AD: FLOOR CONNECTION | 055A | CLOSED | 0 | 0 | 2080.54 | 2080.54
PJ0003939 | STUDENT APARTMENT MAINTENANCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2011-09-21 | CA: REPAIR JAMB, MOLDING, WINDOW TRIM, DRAWERS, RR FLOORING | 055A | CLOSED | 0 | 0 | 1844.825 | 1844.825
PJ0003939 | STUDENT APARTMENT MAINTENANCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2011-09-21 | CP: PROJECT CONTINGENCY | 055A | CLOSED | 0 | 0 | 0 | 0
PJ0003939 | STUDENT APARTMENT MAINTENANCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2011-09-21 | EL: REPAIR CELING FAN BCEC TRAILER | 055A | CLOSED | 0 | 0 | 291.47 | 291.47
PJ0003939 | STUDENT APARTMENT MAINTENANCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2011-09-21 | PA: PATCH AND PAINT HOLE IN LIVING ROOM - BCEC TRAILER | 055A | CLOSED | 0 | 0 | 296.82 | 296.82
PJ0003939 | STUDENT APARTMENT MAINTENANCE - BCEC 55A (MAINT) | GALVEZ, CESAR | CLOSED | 2011-09-21 | PL: REPAIR VANITY SINK, TUB AND BOTH TOILETS | 055A | CLOSED | 0 | 0 | 1126.385 | 1126.385
PJ0003939 Total | [7 empty] | 0 | 0 | 5640.04 | 5640.04
PJ0003938 | PREPARE FOR CAME SECURITY INSTALLATION OF PANIC BUTTON- 001-407B | MAY, TOM | CLOSED | 2011-09-12 | ANTS: SUPPORT CAME SECURITY INSTALLATION OF PANIC BUTTON-01-407B | 001 | CLOSED | 48.048 | 0 | 24.024 | 24.024
PJ0003938 | PREPARE FOR CAME SECURITY INSTALLATION OF PANIC BUTTON- 001-407B | MAY, TOM | CLOSED | 2011-09-12 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 8.01 | 0 | 0 | 0
PJ0003938 | PREPARE FOR CAME SECURITY INSTALLATION OF PANIC BUTTON- 001-407B | MAY, TOM | CLOSED | 2011-09-12 | IN: SUPPORT CAME SECURITY INSTALLATION OF PANIC BUTTON- 01-407B | 001 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003938 Total | [7 empty] | 88.086 | 0 | 56.052 | 56.052
PJ0003937 | CAME SECURITY ALARMS - UPGRADE - DEXTER BLDG 34 | MAY, TOM | CLOSED | 2011-09-16 | ANTS: CAME SECURITY ALARMS - UPGRADE - DEXTER BLDG 34 | 034 | CLOSED | 144.144 | 0 | 36.036 | 36.036
PJ0003937 | CAME SECURITY ALARMS - UPGRADE - DEXTER BLDG 34 | MAY, TOM | CLOSED | 2011-09-16 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 17.62 | 0 | 0 | 0
PJ0003937 | CAME SECURITY ALARMS - UPGRADE - DEXTER BLDG 34 | MAY, TOM | CLOSED | 2011-09-16 | IN: CAME SECURITY ALARMS - UPGRADE - DEXTER BLDG 34 | 034 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003937 Total | [7 empty] | 193.792 | 0 | 68.064 | 68.064
PJ0003936 | CAME SECURITY ALARMS - UPGRADE - 35 SPECIAL COLLECTIONS | MAY, TOM | CLOSED | 2011-09-14 | ANTS: CAME SECURITY ALARMS - UPGRADE - 35 | 035 | CLOSED | 144.144 | 0 | 48.048 | 48.048
PJ0003936 | CAME SECURITY ALARMS - UPGRADE - 35 SPECIAL COLLECTIONS | MAY, TOM | CLOSED | 2011-09-14 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 17.62 | 0 | 0 | 0
PJ0003936 | CAME SECURITY ALARMS - UPGRADE - 35 SPECIAL COLLECTIONS | MAY, TOM | CLOSED | 2011-09-14 | IN: CAME SECURITY ALARMS - UPGRADE - 35 | 035 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003936 Total | [7 empty] | 193.792 | 0 | 80.076 | 80.076
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | CA: PULL OUT BLEACHERS FOR EVENT BEFORE 2:00PM. | GENERAL | CLOSED | 0 | 0 | 1033.78 | 1033.78
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | CU: SUPPORT FOR ACADEMIC DAY EVENTS(TRACKING) | GENERAL | CLOSED | 0 | 0 | 264.45 | 264.45
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | CU: SUPPORT FOR WOW ACADEMIC DAY - SEPT 13 & SEPT 14 | GENERAL | CLOSED | 0 | 0 | 182.46 | 182.46
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | CU: SUPPORT FOR WOW BLOCK PARTY - SEPT 18 | GENERAL | CLOSED | 0 | 0 | 474.396 | 474.396
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | EO: SUPPORT FOR OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 147.88 | 147.88
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | LA: SUPPORT FOR WOW WEEK BLOCK PARTY 2011 | P-H16 | CLOSED | 0 | 0 | 963.6715 | 963.6715
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | RE: SUPPORT FOR WOW | GENERAL | CLOSED | 0 | 0 | 141.012 | 141.012
PJ0003933 | 2011 WOW WEEK SUPPORT 9/12 - 9/16 | POPHAM, DONALD J. | CLOSED | 2011-09-12 | SUPPLY RENTAL: WOW SHOWCASE - SEPT 18 | GENERAL | CLOSED | 0 | 0 | 60 | 60
PJ0003933 Total | [7 empty] | 0 | 0 | 3267.6495 | 3267.6495
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: ASAP REPROGRAPHICS | 034 | CLOSED | 34.59 | 0 | 34.59 | 34.59
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: CAL POLY BUILDING PERMIT FEES | 034 | CLOSED | 2489.1 | 0 | 2489.1 | 2489.1
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: CAL POLY PLAN REVIEW FEES | 034 | CLOSED | 2215.3 | 0 | 2215.3 | 2215.3
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: ENGLEKIRK AND SABOL (NO OVERHEAD) | 034 | CLOSED | 1000 | 0 | 1000 | 1000
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: PARC ENVIRONMENTAL | 034 | CLOSED | 4301.4 | 0 | 4301.4 | 4301.4
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: PROJECT COORDINATION FEES (NO OVERHEAD) | 034 | CLOSED | 13000 | 0 | 13000 | 13000
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | AD: STATE FIRE MARSHAL FEES | 034 | CLOSED | 481.5 | 0 | 420 | 420
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 193.49 | 0 | 0 | 0
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | EH&S: SUBWAY PROJECT - TI BUILD-OUT - BLD 34 RM 111A (N/L) | 034 | CLOSED | 514.8 | 0 | 0 | 0
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | IN: (MAINT)PLAN REVIEW, PERMITS & OVERSIGHT -SUBWAY TI BUILD-OUT | 034 | CLOSED | 0 | 0 | 2161.89 | 2161.89
PJ0003932 | PLAN REVIEW, PERMITS & OVERSIGHT - SUBWAY TI BUILD-OUT - 34-111A | MOLLAN, CHERYL L. | CLOSED | 2011-09-09 | LO:CONSTRUCTION CORES | 034 | CLOSED | 352.176 | 0 | 29.022 | 29.022
PJ0003932 Total | [7 empty] | 24582.356 | 0 | 25651.302 | 25651.302
PJ0003931 | UPDATE CAGE WITH WIRE MESH WALLS -REC CTR 43 RM 188 (OLD RM 111) | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | AD: GRAINGER - DIRECT PAY PURCHASE BY PROJECT MANAGER | 043 | CLOSED | 3593.63 | 0 | 3505.91 | 3505.91
PJ0003931 | UPDATE CAGE WITH WIRE MESH WALLS -REC CTR 43 RM 188 (OLD RM 111) | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | CA: INSTALL CAGES | 043 | CLOSED | 12820.2236 | 0 | 15441.535 | 15441.535
PJ0003931 | UPDATE CAGE WITH WIRE MESH WALLS -REC CTR 43 RM 188 (OLD RM 111) | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 1936.92 | 0 | 0 | 0
PJ0003931 | UPDATE CAGE WITH WIRE MESH WALLS -REC CTR 43 RM 188 (OLD RM 111) | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | EL:INSTALL NEW KEYED SWITCH | 043 | CLOSED | 900.0012 | 0 | 769.848 | 769.848
PJ0003931 | UPDATE CAGE WITH WIRE MESH WALLS -REC CTR 43 RM 188 (OLD RM 111) | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | IN: UPDATE CAGE W/ WIRE MESH WALLS-REC CTR 43 RM 188(OLD RM 111) | 043 | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0003931 | UPDATE CAGE WITH WIRE MESH WALLS -REC CTR 43 RM 188 (OLD RM 111) | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | LO:REKEY CAGE DOORS | 043 | CLOSED | 1416.528 | 0 | 997.086 | 997.086
PJ0003931 Total | [7 empty] | 20795.4148 | 0 | 20778.435 | 20778.435
PJ0003930 | INSTALL 2-HOUR FIRE WALLS IN 6 LOCATIONS - NO. MTN. RESIDENCES | LAMPMAN, GREG | CLOSED | 2011-09-01 | AD: JOC 11.022.041 STAPLES | RESIDENCE | CLOSED | 84060.3128 | 0 | 84060.2914 | 84060.2914
PJ0003930 | INSTALL 2-HOUR FIRE WALLS IN 6 LOCATIONS - NO. MTN. RESIDENCES | LAMPMAN, GREG | CLOSED | 2011-09-01 | CA: PURCHASE DOORS FOR S. MTN. OVERFLOW ROOMS (MAT. ONLY) | RESIDENCE | CLOSED | 4429.344 | 0 | 4429.344 | 4429.344
PJ0003930 | INSTALL 2-HOUR FIRE WALLS IN 6 LOCATIONS - NO. MTN. RESIDENCES | LAMPMAN, GREG | CLOSED | 2011-09-01 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 4192.13 | 0 | 0 | 0
PJ0003930 | INSTALL 2-HOUR FIRE WALLS IN 6 LOCATIONS - NO. MTN. RESIDENCES | LAMPMAN, GREG | CLOSED | 2011-09-01 | IN: INSTALL 2 HOUR FIRE WALLS IN 6 LOCATIONS -NO. MTN. RESIDENCE | RESIDENCE | CLOSED | 1537.344 | 0 | 800.7 | 800.7
PJ0003930 | INSTALL 2-HOUR FIRE WALLS IN 6 LOCATIONS - NO. MTN. RESIDENCES | LAMPMAN, GREG | CLOSED | 2011-09-01 | LO: INSTALL LOCK HARDWARE IN 6 SOUTH MTN HALLS | RESIDENCE | CLOSED | 4236.4883 | 0 | 5104.668 | 5104.668
PJ0003930 | INSTALL 2-HOUR FIRE WALLS IN 6 LOCATIONS - NO. MTN. RESIDENCES | LAMPMAN, GREG | CLOSED | 2011-09-01 | PA: PAINT WALLS &DOOR FRAMES &APPLY CLEAR FINISH ON DOORS-NO MTN | RESIDENCE | CLOSED | 5234.208 | 0 | 4405.95 | 4405.95
PJ0003930 Total | [7 empty] | 103689.8271 | 0 | 98800.9534 | 98800.9534
PJ0003929 | CHANGE OUT LIGHT PANELS ON SCOREBOARD - SPANOS 61 | GALVEZ, CESAR | CLOSED | 2011-08-30 | AD: THE SIGN PLACE | 061 | CLOSED | 1589.6241 | 0 | 907.0925 | 907.0925
PJ0003929 | CHANGE OUT LIGHT PANELS ON SCOREBOARD - SPANOS 61 | GALVEZ, CESAR | CLOSED | 2011-08-30 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 158.96 | 0 | 0 | 0
PJ0003929 Total | [7 empty] | 1748.5841 | 0 | 907.0925 | 907.0925
PJ0003928 | COMMEMORATIVE BENCH - SCI NORTH BLD 53 (NO ESTIMATE) | MEAD, GEORGE | CLOSED | 2011-08-31 | CA: INSTALL PLAQUE ON MEMORIAL BENCH NEAR SCIENCE NORTH | GENERAL | CLOSED | 0 | 0 | 31.194 | 31.194
PJ0003928 | COMMEMORATIVE BENCH - SCI NORTH BLD 53 (NO ESTIMATE) | MEAD, GEORGE | CLOSED | 2011-08-31 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 0 | 0 | 0 | 0
PJ0003928 | COMMEMORATIVE BENCH - SCI NORTH BLD 53 (NO ESTIMATE) | MEAD, GEORGE | CLOSED | 2011-08-31 | EO: SUPPORT FOR MEMORIAL BENCH INSTALLATION NEAR SCIENCE NORTH | GENERAL | CLOSED | 0 | 0 | 88.728 | 88.728
PJ0003928 | COMMEMORATIVE BENCH - SCI NORTH BLD 53 (NO ESTIMATE) | MEAD, GEORGE | CLOSED | 2011-08-31 | LA: SUPPORT FOR MEMORIAL BENCH INSTALLATION NEAR SCIENCE NORTH | GENERAL | CLOSED | 0 | 0 | 77.928 | 77.928
PJ0003928 Total | [7 empty] | 0 | 0 | 197.85 | 197.85
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | AD: JL FASULO DRYWALL | 001 | CLOSED | 827.11 | 0 | 827.11 | 827.11
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | AD: RUSSCO | 001 | CLOSED | 2519.3899 | 0 | 2600.421 | 2600.421
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | CA: FRAME WALL INSTALL DOOR | 001 | CLOSED | 3421.8299 | 0 | 3311.79 | 3311.79
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 872.36 | 0 | 0 | 0
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | EL:INSTALL 4 OUTLETS FROM EXISTING J-BOX | 001 | CLOSED | 780.0024 | 0 | 526.368 | 526.368
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | IN: INSTALL WALL WITH DOOR - BLD 01 RM 317 | 001 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | LO:INSTALL OFFICE FUNCTION LOCK | 001 | CLOSED | 536.088 | 0 | 573.648 | 573.648
PJ0003927 | INSTALL WALL WITH DOOR - BLD 01 RM 317 | BRENNAN, MICHAEL | CLOSED | 2011-08-30 | PA:PAINT NEW WALL | 001 | CLOSED | 780.7213 | 0 | 969.636 | 969.636
PJ0003927 Total | [7 empty] | 9801.5575 | 0 | 8841.001 | 8841.001
PJ0003925 | COVER WALL INSULATION WITH PLYWOOD - LAB C - BLD 48H | MAY, TOM | CLOSED | 2011-08-29 | AD: TEMPLE BUILDERS | 048H | CLOSED | 2903.98 | 0 | 2903.98 | 2903.98
PJ0003925 | COVER WALL INSULATION WITH PLYWOOD - LAB C - BLD 48H | MAY, TOM | CLOSED | 2011-08-29 | CP: PROJECT CONTINGENCY | 048H | CLOSED | 901.9 | 0 | 0 | 0
PJ0003925 | COVER WALL INSULATION WITH PLYWOOD - LAB C - BLD 48H | MAY, TOM | CLOSED | 2011-08-29 | IN: INSTALL WALL TO COVER INSULATION IN LAB C - BLD 48H | 048H | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003925 | COVER WALL INSULATION WITH PLYWOOD - LAB C - BLD 48H | MAY, TOM | CLOSED | 2011-08-29 | PA:PAINT PLYWOOD WALLS AND SOUNDPROOFING IN LAB C AT OH | 048H | CLOSED | 6051.2249 | 0 | 4267.266 | 4267.266
PJ0003925 Total | [7 empty] | 9921.1609 | 0 | 7235.302 | 7235.302
PJ0003922 | DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | MOLLAN, CHERYL L. | CLOSED | 2011-08-22 | CP: PROJECT CONTINGENCY | 057 | CLOSED | 9.7 | 0 | 0 | 0
PJ0003922 | DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | MOLLAN, CHERYL L. | CLOSED | 2011-08-22 | EL:DISCONNECT ELECTRICAL TO AUTOCLAVE | 057 | CLOSED | 329.664 | 0 | 438.204 | 438.204
PJ0003922 | DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | MOLLAN, CHERYL L. | CLOSED | 2011-08-22 | ES: DISCONNECT REMAINING AUTOCLAVE FEEDS - VET CLINIC 057 | 057 | CLOSED | 109.263 | 0 | 179.76 | 179.76
PJ0003922 | DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | MOLLAN, CHERYL L. | CLOSED | 2011-08-22 | IN: DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | 057 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003922 | DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | MOLLAN, CHERYL L. | CLOSED | 2011-08-22 | MO:REMOVE AUTOCLAVE UNIT | 057 | CLOSED | 162 | 0 | 18.108 | 18.108
PJ0003922 | DISCONNECT AUTOCLAVE - VET CLINIC BLD 57 | MOLLAN, CHERYL L. | CLOSED | 2011-08-22 | PL:DISCONNECT PLUMBING TO AUTOCLAVE | 057 | CLOSED | 451.752 | 0 | 391.752 | 391.752
PJ0003922 Total | [7 empty] | 1126.435 | 0 | 1091.88 | 1091.88
PJ0003920 | OFFICE RELOCATION - BLD 70 RM 204 (NO ESTIMATE) | MAY, TOM | CLOSED | 2011-08-22 | CA:DISCONNECT FURNITURE AND WALL BRACKETS IN 70-204 | 070 | CLOSED | 0 | 0 | 197.358 | 197.358
PJ0003920 | OFFICE RELOCATION - BLD 70 RM 204 (NO ESTIMATE) | MAY, TOM | CLOSED | 2011-08-22 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0003920 | OFFICE RELOCATION - BLD 70 RM 204 (NO ESTIMATE) | MAY, TOM | CLOSED | 2011-08-22 | PA:PATCH AND PAINT 70-204 | 070 | CLOSED | 0 | 0 | 564.594 | 564.594
PJ0003920 Total | [7 empty] | 0 | 0 | 761.952 | 761.952
PJ0003919 | TI: PLAN CHECK APPLIED TECHNOLOGY ASSOC. TECH PARK 83 RM 2C | HOGAN, MIKE | CLOSED | 2011-08-19 | AD: SHIPPING CHARGES - PLANS TO HAYER (CHARGED DIRECT TO PJ CFS) | 083 | CLOSED | 0 | 0 | 60.07 | 60.07
PJ0003919 | TI: PLAN CHECK APPLIED TECHNOLOGY ASSOC. TECH PARK 83 RM 2C | HOGAN, MIKE | CLOSED | 2011-08-19 | AD: STATE FIRE MARSHALL REVIEW AND INSPECTION FEES | 083 | CLOSED | 2225.6 | 0 | 0 | 0
PJ0003919 | TI: PLAN CHECK APPLIED TECHNOLOGY ASSOC. TECH PARK 83 RM 2C | HOGAN, MIKE | CLOSED | 2011-08-19 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 540.86 | 0 | 0 | 0
PJ0003919 | TI: PLAN CHECK APPLIED TECHNOLOGY ASSOC. TECH PARK 83 RM 2C | HOGAN, MIKE | CLOSED | 2011-08-19 | IN: (MAINT) TI PLAN CHECK APPLIED TECH. - TECH PARK 83 RM 2C | 083 | CLOSED | 0 | 0 | 1441.26 | 1441.26
PJ0003919 | TI: PLAN CHECK APPLIED TECHNOLOGY ASSOC. TECH PARK 83 RM 2C | HOGAN, MIKE | CLOSED | 2011-08-19 | IN: CP BUILDING PERMIT FEES | 083 | CLOSED | 1683 | 0 | 1683 | 1683
PJ0003919 | TI: PLAN CHECK APPLIED TECHNOLOGY ASSOC. TECH PARK 83 RM 2C | HOGAN, MIKE | CLOSED | 2011-08-19 | IN: CP PLAN REVIEW FEES | 083 | CLOSED | 1500 | 0 | 1500 | 1500
PJ0003919 Total | [7 empty] | 5949.46 | 0 | 4684.33 | 4684.33
PJ0003918 | REPAIR FLOOD DAMAGE - TENAYA HALL 1ST & 2ND FLRS (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-08-22 | AD: FLOOR CONNECTION | 110 | CLOSED | 0 | 0 | 335.22 | 335.22
PJ0003918 | REPAIR FLOOD DAMAGE - TENAYA HALL 1ST & 2ND FLRS (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-08-22 | CA:TENAYA FLOOD REMEDIATION WORK | 110 | CLOSED | 0 | 0 | 2163.95 | 2163.95
PJ0003918 | REPAIR FLOOD DAMAGE - TENAYA HALL 1ST & 2ND FLRS (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-08-22 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 0 | 0 | 0 | 0
PJ0003918 Total | [7 empty] | 0 | 0 | 2499.17 | 2499.17
PJ0003914 | TI PLAN CHECK SERVICES FOR V LABORATORIES - BLDG 083 RM 1C-2 | HOGAN, MIKE | CLOSED | 2011-08-17 | AD: STATE FIRE MARSHAL REVIEW AND INSPECTION FEES | 083 | CLOSED | 1112.8 | 0 | 0 | 0
PJ0003914 | TI PLAN CHECK SERVICES FOR V LABORATORIES - BLDG 083 RM 1C-2 | HOGAN, MIKE | CLOSED | 2011-08-17 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 346.82 | 0 | 0 | 0
PJ0003914 | TI PLAN CHECK SERVICES FOR V LABORATORIES - BLDG 083 RM 1C-2 | HOGAN, MIKE | CLOSED | 2011-08-17 | IN: (MAINT) TI PLAN CHECK SVCS FOR V LABS - BLDG 083 RM 1C-2 | 083 | CLOSED | 0 | 0 | 1174.36 | 1174.36
PJ0003914 | TI PLAN CHECK SERVICES FOR V LABORATORIES - BLDG 083 RM 1C-2 | HOGAN, MIKE | CLOSED | 2011-08-17 | IN: BUILDING PERMIT FEES | 083 | CLOSED | 855.4 | 0 | 855.4 | 855.4
PJ0003914 | TI PLAN CHECK SERVICES FOR V LABORATORIES - BLDG 083 RM 1C-2 | HOGAN, MIKE | CLOSED | 2011-08-17 | IN: PLAN REVIEW FEES | 083 | CLOSED | 1500 | 0 | 1500 | 1500
PJ0003914 Total | [7 empty] | 3815.02 | 0 | 3529.76 | 3529.76
PJ0003913 | REATTACH STORE FRONT DOORS, EAST EXIT HALL BLDG. 47 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-08-16 | AD: CONTRACTOR'S GLASS COMPANY | 047 | CLOSED | 1450 | 0 | 1468.13 | 1468.13
PJ0003913 | REATTACH STORE FRONT DOORS, EAST EXIT HALL BLDG. 47 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-08-16 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0003913 Total | [7 empty] | 1450 | 0 | 1468.13 | 1468.13
PJ0003911 | HOOK UP POWER FOR FURNACE - BLD 41B RM 143 | ELLIOT, DENNIS K | CLOSED | 2011-08-12 | CP: PROJECT CONTINGENCY | 041B | CLOSED | 67.92 | 0 | 0 | 0
PJ0003911 | HOOK UP POWER FOR FURNACE - BLD 41B RM 143 | ELLIOT, DENNIS K | CLOSED | 2011-08-12 | EL: HOOK UP POWER FOR FURNACE | 041B | CLOSED | 614.833 | 0 | 307.224 | 307.224
PJ0003911 | HOOK UP POWER FOR FURNACE - BLD 41B RM 143 | ELLIOT, DENNIS K | CLOSED | 2011-08-12 | IN: HOOK UP POWER FOR FURNACE - BLD 41B RM 143 | 041B | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003911 Total | [7 empty] | 746.809 | 0 | 371.28 | 371.28
PJ0003910 | LIBRARY WINDOW TINTING - KEN LIB 35 | MAY, TOM | CLOSED | 2011-08-11 | AD: HEAT WAVE WINDOW TINTING | 035 | CLOSED | 13126.9312 | 0 | 13126.9312 | 13126.9312
PJ0003910 | LIBRARY WINDOW TINTING - KEN LIB 35 | MAY, TOM | CLOSED | 2011-08-11 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 317.35 | 0 | 0 | 0
PJ0003910 | LIBRARY WINDOW TINTING - KEN LIB 35 | MAY, TOM | CLOSED | 2011-08-11 | IN: LIBRARY WINDOW TINTING - KEN LIB 35 | 035 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003910 Total | [7 empty] | 13476.3092 | 0 | 13158.9592 | 13158.9592
PJ0003908 | MJ: INSTALL BIRD NETTING - PCV ALISO 171A COURTYARD (JOC, ONLY) | GRIFFIN, PATRICK E. | CLOSED | 2011-08-04 | CP: PROJECT CONTINGENCY | 171A | CLOSED | 0 | 0 | 0 | 0
PJ0003908 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | AD: SHORELINE AWNING (REPAIR TENT) - CREDIT CARD PAYMENT | 051 | CLOSED | 0 | 0 | 560 | 560
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | AD: CAME SECURITY (MAINT) | 051 | CLOSED | 0 | 0 | 1400 | 1400
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | AD: G&S APPLIANCE SERVICES, INC. | 051 | CLOSED | 0 | 0 | 730.19 | 730.19
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | AD: THE SIGN PLACE (MAINT) | 051 | CLOSED | 0 | 0 | 1336.13 | 1336.13
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | CA: FORM AND POUR CONCRETE SIGN WALL FOR UNIV. HOUSE ADDRESS | 051 | CLOSED | 0 | 0 | 1296.3784 | 1296.3784
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | CA: HANG TWO PICTURES IN THE DINING ROOM - 051 | 051 | CLOSED | 46.99 | 0 | 46.99 | 46.99
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | EL: REPAIR ELECTRIC GATE AT UNIVERSITY HOUSE - BLDG. 051 | 051 | CLOSED | 0 | 0 | 280.9 | 280.9
PJ0003907 | 11/12 MAINTENANCE NEEDS FOR THE UNIVERSITY HOUSE (MAINT) | BRENNAN, MICHAEL | CLOSED | 2011-08-05 | PL: MAINTENANCE NEEDS FOR UNIVERSITY HOUSE - 051 | 051 | CLOSED | 0 | 0 | 108.82 | 108.82
PJ0003907 Total | [7 empty] | 46.99 | 0 | 5759.4084 | 5759.4084
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR GREEN/GOLD VOLLEYBALL GAME-AUG 20 | 042 | CLOSED | 0 | 0 | 276.21 | 276.21
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL - NOV 11 | 042 | CLOSED | 0 | 0 | 610.98 | 610.98
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL GAME ON 11/5 AT 7PM | 042 | CLOSED | 0 | 0 | 694.518 | 694.518
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL V BAKERSFIELD - SEPT 18 | 042 | CLOSED | 0 | 0 | 748.086 | 748.086
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL V. CSU FULLERTON - OCT 22 | 042 | CLOSED | 0 | 0 | 724.056 | 724.056
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL V. PACIFIC - OCT 1 | 042 | CLOSED | 0 | 0 | 882.024 | 882.024
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL V. UCSB - OCT 12 | 042 | CLOSED | 0 | 0 | 473.904 | 473.904
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL V. UN DAVIS | 042 | CLOSED | 0 | 0 | 885.132 | 885.132
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VOLLEYBALL V.LONG BEACH ST - OCT 21 | 042 | CLOSED | 0 | 0 | 813.84 | 813.84
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR VWOMEN'S VOLLEYBALL GAME - OCT 13 | 042 | CLOSED | 0 | 0 | 635.241 | 635.241
PJ0003906 | 11/12 SUPPORT FOR WOMEN'S VOLLEYBALL | POPHAM, DONALD J. | CLOSED | 2011-08-04 | CU: SUPPORT FOR WOMEN'S SOCCER GAME - OCT 13 | 042 | CLOSED | 0 | 0 | 970.608 | 970.608
PJ0003906 Total | [7 empty] | 0 | 0 | 7714.599 | 7714.599
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SUPPORT FOR WOMEN'S SOCCER - 10/16 | 061 | CLOSED | 0 | 0 | 1045.5 | 1045.5
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SUPPORT FOR WOMEN'S SOCCER GAME-AUG 28 | 061 | CLOSED | 0 | 0 | 1242.606 | 1242.606
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SUPPORT FOR WOMEN'S SOCCER V. FRESNO ST - SEPT 23 | 061 | CLOSED | 0 | 0 | 1202.514 | 1202.514
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SUPPORT FOR WOMEN'S SOCCER V. UNIV OF NEVADA-SEPT 16 | 061 | CLOSED | 0 | 0 | 967.038 | 967.038
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SUPPORT FOR WOMEN'S SPCCER V.CSULB-OCT 2 | 061 | CLOSED | 0 | 0 | 802.332 | 802.332
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SUPPORT W. SOCCER V. CSU FULLERTON - SEPT 30 | 061 | CLOSED | 0 | 0 | 620.148 | 620.148
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA: LINING FOR SOCCER SPRING PRACTICES | 061 | CLOSED | 0 | 0 | 584.46 | 584.46
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA: STRIPING FOR WOMEN'S SOCCER PRACTICES 8/1-12/31 | 061 | CLOSED | 0 | 0 | 604.224 | 604.224
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA: SUPPORT FOR WOMEN'S SOCCER V FOOTHILL CC-APR 27 | 061 | CLOSED | 0 | 0 | 201.408 | 201.408
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA: SUPPORT FOR WOMEN'S SOCCER V. ST. MARYS - APR 15 | 061 | CLOSED | 0 | 0 | 260.136 | 260.136
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA: SUPPORT FOR WOMENS SOCCER GAME - APR 21 | 061 | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA: SUPPORT WOMEN'S SOCCER V CALIF. HEAT - MAY 12 | 061 | CLOSED | 0 | 0 | 160.248 | 160.248
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. CSU FULLERTON -FRIDAY SEPT 30 | 061 | CLOSED | 0 | 0 | 669.024 | 669.024
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. CSU LONG BEACH -SUNDAY OCT 2 | 061 | CLOSED | 0 | 0 | 323.202 | 323.202
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. FRESNO ST - FRIDAY SEPT 23 | 061 | CLOSED | 0 | 0 | 526.578 | 526.578
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. PEPPERDINE -SUNDAY SEPT 18 | 061 | CLOSED | 0 | 0 | 235.98 | 235.98
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. SANTA CLARA-AUG 28 | 061 | CLOSED | 0 | 0 | 297.72 | 297.72
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. UC DAVIS -SUNDAY OCT 16 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. UC RIVERSIDE - THURS OCT 13 | 061 | CLOSED | 0 | 0 | 811.824 | 811.824
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | LA:SUPPORT WOMEN'S SOCCER V. UNIV OF NEVADA - FRIDAY SEPT 16 | 061 | CLOSED | 0 | 0 | 537.096 | 537.096
PJ0003905 | 11/12 SUPPORT FOR WOMEN'S SOCCER | POPHAM, DONALD J. | CLOSED | 2011-08-01 | PL: PM RESTROOMS BEFORE WOMEN'S SOCCER GAMES AS NEEDED | 061 | CLOSED | 0 | 0 | 27.205 | 27.205
PJ0003905 Total | [7 empty] | 0 | 0 | 11275.099 | 11275.099
PJ0003904 | CLEAN DEAN'S COMPLEX EXTERIOR WINDOWS - BLDG 192 | LOOSLEY, SCOTT L. | CLOSED | 2011-08-02 | AD: COASTAL JANITORIAL | 192 | CLOSED | 353.1 | 0 | 353.1 | 353.1
PJ0003904 | CLEAN DEAN'S COMPLEX EXTERIOR WINDOWS - BLDG 192 | LOOSLEY, SCOTT L. | CLOSED | 2011-08-02 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 35.31 | 0 | 0 | 0
PJ0003904 Total | [7 empty] | 388.41 | 0 | 353.1 | 353.1
PJ0003903 | SR 11/12: DESIGN CHILLED WATER PROJECT - FISHER HALL 33 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-08-01 | AD: GOSS ENGINEERING (DESIGN) | 033 | CLOSED | 21270 | 0 | 21270 | 21270
PJ0003903 | SR 11/12: DESIGN CHILLED WATER PROJECT - FISHER HALL 33 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-08-01 | AD: HPS MECHANICAL | 033 | CLOSED | 124179.44 | 0 | 111112.31 | 111112.31
PJ0003903 | SR 11/12: DESIGN CHILLED WATER PROJECT - FISHER HALL 33 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-08-01 | AD: SIEMENS | 033 | CLOSED | 30961 | 0 | 30961 | 30961
PJ0003903 | SR 11/12: DESIGN CHILLED WATER PROJECT - FISHER HALL 33 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-08-01 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 12377.87 | 0 | 0 | 0
PJ0003903 Total | [7 empty] | 188788.31 | 0 | 163343.31 | 163343.31
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: CLEAN UP FOR SOAR - DEXTER LAWN | GENERAL | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: EXTRA SUPPORT FOR SOAR BUILDING 10: AUG 2- AUG 16 9(N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | CU: SPANOS THEATRE SUPPORT FOR SOAR - AUG 2 - AUG 16 | GENERAL | CLOSED | 0 | 0 | 1523.4 | 1523.4
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | EL: INSTALL ONE SPIDER BOX FOR SOAR AUG 2 - AUG 16 | GENERAL | CLOSED | 0 | 0 | 202.248 | 202.248
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | GR: SUPPORT FOR SOAR LUNCHES - DEXTER LAWN | GENERAL | CLOSED | 0 | 0 | 155.856 | 155.856
PJ0003902 | SUPPORT FOR SOAR - AUGUST 2011 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2011-08-01 | RE: SUPPORT FOR SOAR - AUG 2-16 | GENERAL | CLOSED | 0 | 0 | 718.08 | 718.08
PJ0003902 Total | [7 empty] | 0 | 0 | 2648.778 | 2648.778
PJ0003901 | 7/19 FACILITY INSPECTION (MAINTENANCE WALK-THRU) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-29 | CA:PAC FACILITY INSPECTION ITEMS FOR JULY 19TH | 006 | CLOSED | 0 | 0 | 1903.095 | 1903.095
PJ0003901 | 7/19 FACILITY INSPECTION (MAINTENANCE WALK-THRU) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-29 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003901 | 7/19 FACILITY INSPECTION (MAINTENANCE WALK-THRU) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-29 | ES:COMPLETE PAC FACILITY INSPECTION ITEMS-JULY 19TH | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003901 | 7/19 FACILITY INSPECTION (MAINTENANCE WALK-THRU) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-29 | LO:COMPLETE PAC FACILITY INSPECTION ITEMS - JULY 19TH | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003901 | 7/19 FACILITY INSPECTION (MAINTENANCE WALK-THRU) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-29 | PA:COMPLETE PAC FACILITY INSPECTION ITEMS - JULY 19TH | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003901 | 7/19 FACILITY INSPECTION (MAINTENANCE WALK-THRU) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-29 | PL:COMPLETE PAC FACILITY INSPECTION ITEMS - JULY 19TH | 006 | CLOSED | 0 | 0 | 54.41 | 54.41
PJ0003901 Total | [7 empty] | 0 | 0 | 1957.505 | 1957.505
PJ0003900 | INSTALL BOLLARDS AROUND HYDRANT - TECH PARK PARKING LOT BLD 83 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-28 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 59.02 | 0 | 0 | 0
PJ0003900 | INSTALL BOLLARDS AROUND HYDRANT - TECH PARK PARKING LOT BLD 83 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-28 | PA:PAINT HYDRANTS AT TECH PARK | 083 | CLOSED | 312.1698 | 0 | 356.82 | 356.82
PJ0003900 | INSTALL BOLLARDS AROUND HYDRANT - TECH PARK PARKING LOT BLD 83 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-28 | PL:REPAIR DAMAGED HYDRANT AT THE TECH PARK | 083 | CLOSED | 278.0753 | 0 | 228.522 | 228.522
PJ0003900 Total | [7 empty] | 649.2651 | 0 | 585.342 | 585.342
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | AD: COASTAL DEMO | 114A | CLOSED | 321 | 0 | 321 | 321
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | AD: G.F. GARCIA AND SONS | 114A | CLOSED | 5325.9464 | 0 | 5325.9464 | 5325.9464
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | AD: MAINO CONSTRUCTION (LOW-VALUE PUBLIC WORKS) | 114A | CLOSED | 4922 | 0 | 1931.6496 | 1931.6496
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | AD: RICK TEIXEIRA WELDING | 114A | CLOSED | 5008.9375 | 0 | 5008.9375 | 5008.9375
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | CA:MOVE AND REPLACE CABINET | 114A | CLOSED | 2127.9767 | 0 | 249.444 | 249.444
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | CP: PROJECT CONTINGENCY | 114A | CLOSED | 2551.2 | 0 | 0 | 0
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | ES:REPAIR HOT WATER LEAK AT YOSEMITE MAIN HALL LOUNGE | 114A | CLOSED | 6146.16 | 0 | 13267.9686 | 13267.9686
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | IN: REPAIR HEATING/HOT WATER PIPE UNDER SLAB-YOSEMITE T/0 LOUNGE | 114A | CLOSED | 128.112 | 0 | 96.084 | 96.084
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | LA:REMOVE LANDSCAPING AND IRRIGATION FOR PIPE REPAIR | 114A | CLOSED | 3070.272 | 0 | 740.8016 | 740.8016
PJ0003899 | REPAIR HEATING & HOT WATER PIPE UNDER SLAB - YOSEMITE T/0 LOUNGE | BRENNAN, MICHAEL | CLOSED | 2011-07-22 | PA:TOUCH UP PAINT AS NECESSARY AFTER PIPE REPAIR | 114A | CLOSED | 594.912 | 0 | 237.456 | 237.456
PJ0003899 Total | [7 empty] | 30196.5166 | 0 | 27179.2877 | 27179.2877
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | AD: CREDIT & ORIG INVFROM GRAINGER - MATERIALS TO BE USED BY JOC | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | AD: GRAINGER - MATERIALS TO BE USED BY JOC | 021 | CLOSED | 5554.3807 | 0 | 5554.37 | 5554.37
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | AD: INNOVATION COMMERCIAL FLOORING | 021 | CLOSED | 14515.7698 | 0 | 14515.7698 | 14515.7698
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | AD: JOC 11.023.022 STAPLES | 021 | CLOSED | 27578.2121 | 0 | 27578.2014 | 27578.2014
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | AD: MONTEREY LIGHTING | 021 | CLOSED | 5350 | 0 | 4265.8225 | 4265.8225
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | CA: DEMO, CONSTRUCTION PER PLAN (BLDG 21 - 105A/B, KTGY GALLERY) | 021 | CLOSED | 24881.9836 | 0 | 20269.479 | 20269.479
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 5002.96 | 0 | 0 | 0
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | EL: ELECTRICAL FOR KTGY GALLERY | 021 | CLOSED | 1688.028 | 0 | 1538.232 | 1538.232
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | IN: REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | 021 | CLOSED | 256.224 | 0 | 288.252 | 288.252
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | LO: SUPPLY AND INSTALL NEW DOOR HARDWARE FOR ROOM 21-105 | 021 | CLOSED | 1064.352 | 0 | 2417.796 | 2417.796
PJ0003898 | REMODEL ROOMS 105A AND 105B - KTGY GALLERY - BLD 21 | BRENNAN, MICHAEL | CLOSED | 2011-07-25 | PA: PAINTING FOR KTGY GALLERY 21-105 A & B | 021 | CLOSED | 9036.048 | 0 | 8532.684 | 8532.684
PJ0003898 Total | [7 empty] | 94927.9582 | 0 | 84960.6067 | 84960.6067
PJ0003897 | REMOVE WALL MOUNTED CUPBOARDS, PATCH AND PAINT WALL | MAY, TOM | CLOSED | 2011-07-25 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 18.85 | 0 | 0 | 0
PJ0003897 | REMOVE WALL MOUNTED CUPBOARDS, PATCH AND PAINT WALL | MAY, TOM | CLOSED | 2011-07-25 | PA:PAINT WALL AND END OF CABINET IN 11-114 | 011 | CLOSED | 132.3817 | 0 | 132.12 | 132.12
PJ0003897 Total | [7 empty] | 151.2317 | 0 | 132.12 | 132.12
PJ0003896 | PURCHASE AND INSTALL WHITEBOARD IN 035-204A | MAY, TOM | CLOSED | 2011-07-20 | CA:PURCHASE AND INSTALL 1-6' WHITE BOARD FOR 35-204A | 035 | CLOSED | 605.7452 | 0 | 919.2 | 919.2
PJ0003896 | PURCHASE AND INSTALL WHITEBOARD IN 035-204A | MAY, TOM | CLOSED | 2011-07-20 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 123.8 | 0 | 0 | 0
PJ0003896 | PURCHASE AND INSTALL WHITEBOARD IN 035-204A | MAY, TOM | CLOSED | 2011-07-20 | IN: PURCHASE AND INSTALL WHITEBOARD IN 035-204A | 035 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003896 | PURCHASE AND INSTALL WHITEBOARD IN 035-204A | MAY, TOM | CLOSED | 2011-07-20 | PA:PATCH AND PAINT 35-204A | 035 | CLOSED | 600.3396 | 0 | 268.656 | 268.656
PJ0003896 Total | [7 empty] | 1361.9128 | 0 | 1219.884 | 1219.884
PJ0003895 | INSTALL 1/2" PLYWOOD ON WALL BEFORE 8/5- BLD 21 RM 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-20 | AD: TEMPLE BUILDERS | 021 | CLOSED | 1021.315 | 0 | 1043.9776 | 1043.9776
PJ0003895 | INSTALL 1/2" PLYWOOD ON WALL BEFORE 8/5- BLD 21 RM 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-07-20 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 102.13 | 0 | 0 | 0
PJ0003895 Total | [7 empty] | 1123.445 | 0 | 1043.9776 | 1043.9776
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | AD: INNOVATION COMMERCIAL FLOORING | 001 | CLOSED | 6791.3221 | 0 | 6130.2761 | 6130.2761
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | CA: REPLACE 2 BROKEN/DAMAGED CEILING TILES - ADMIN 001-211 | 001 | CLOSED | 261.552 | 0 | 192.966 | 192.966
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | CA:FURNITURE REMOVAL FOR CARPET AND PAINT ADM 211 | 001 | CLOSED | 225.552 | 0 | 225.552 | 225.552
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 346.12 | 0 | 0 | 0
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | EL:ELECTRICAL FOR NEW FURNITURE LAYOUT IN ADM 211 | 001 | CLOSED | 1440.679 | 0 | 906.072 | 906.072
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | IN: NEW CARPET AND PAINT - BLD 1 RM 211 | 001 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | MO:MOVE FURNITURE AROUND IN OFFICE FOR CARPET ADM 211 | 001 | CLOSED | 64.8 | 0 | 24.144 | 24.144
PJ0003894 | NEW CARPET, ELECTRICAL, AND PAINT - BLD 1 RM 211 | GALVEZ, CESAR | CLOSED | 2011-07-22 | PA:PAINT ADM 211 FOR NEW FURNITURE LAYOUT | 001 | CLOSED | 1645.6124 | 0 | 1722.828 | 1722.828
PJ0003894 Total | [7 empty] | 10839.6935 | 0 | 9265.8941 | 9265.8941
PJ0003893 | NEW SEWER AND POTABLE WATER LINE IN EXTERIOR GROUNDS - BLDG 048 | MAY, TOM | CLOSED | 2011-07-22 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 599.6 | 0 | 0 | 0
PJ0003893 | NEW SEWER AND POTABLE WATER LINE IN EXTERIOR GROUNDS - BLDG 048 | MAY, TOM | CLOSED | 2011-07-22 | EO:ASSIST PL WITH NEW POTABLE WATER LINE AT OH | GENERAL | CLOSED | 3184.896 | 0 | 621.096 | 621.096
PJ0003893 | NEW SEWER AND POTABLE WATER LINE IN EXTERIOR GROUNDS - BLDG 048 | MAY, TOM | CLOSED | 2011-07-22 | IN: NEW SEWER & POTABLE WATER LINE - EXTERIOR GROUNDS - BLDG 048 | GENERAL | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003893 | NEW SEWER AND POTABLE WATER LINE IN EXTERIOR GROUNDS - BLDG 048 | MAY, TOM | CLOSED | 2011-07-22 | PL:INSTALL NEW POTABLE WATER AT OH | GENERAL | CLOSED | 3451.68 | 0 | 2775.2369 | 2775.2369
PJ0003893 Total | [7 empty] | 7300.232 | 0 | 3460.3889 | 3460.3889
PJ0003892 | FP 11/12: PEDESTRIAN PATHWAY TO CROSSWALK AT H2B PARKING LOT | GALVEZ, CESAR | CLOSED | 2011-07-21 | AD: JOC 11.022.026 STAPLES | P-H02 | CLOSED | 9190.05 | 0 | 9190.05 | 9190.05
PJ0003892 | FP 11/12: PEDESTRIAN PATHWAY TO CROSSWALK AT H2B PARKING LOT | GALVEZ, CESAR | CLOSED | 2011-07-21 | CP: PROJECT CONTINGENCY | P-H02 | CLOSED | 0 | 0 | 0 | 0
PJ0003892 | FP 11/12: PEDESTRIAN PATHWAY TO CROSSWALK AT H2B PARKING LOT | GALVEZ, CESAR | CLOSED | 2011-07-21 | EO: DEMO EXISTING PLANTER, CURB & GUTTER 8/30-9/1 | P-H02 | CLOSED | 1108.9078 | 0 | 1109.1 | 1109.1
PJ0003892 | FP 11/12: PEDESTRIAN PATHWAY TO CROSSWALK AT H2B PARKING LOT | GALVEZ, CESAR | CLOSED | 2011-07-21 | IN: FP 11/12: PEDESTRIAN PATHWAY TO CROSSWALK AT H2B PARKING LOT | P-H02 | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0003892 | FP 11/12: PEDESTRIAN PATHWAY TO CROSSWALK AT H2B PARKING LOT | GALVEZ, CESAR | CLOSED | 2011-07-21 | LA: INSTALL NEW IRRIGATION & FILL PLANTER | P-H02 | CLOSED | 292.219 | 0 | 292.23 | 292.23
PJ0003892 Total | [7 empty] | 10697.9368 | 0 | 10698.14 | 10698.14
PJ0003891 | ADD CENTER-DIVIDE HANDRAIL TO MAIN STAIRCASE - BLDG 35 | MAY, TOM | CLOSED | 2011-07-20 | AD: MAINO CONSTRUCTION (LOW-VALUE PUBLIC WORKS) | 035 | CLOSED | 5216.25 | 0 | 5216.25 | 5216.25
PJ0003891 | ADD CENTER-DIVIDE HANDRAIL TO MAIN STAIRCASE - BLDG 35 | MAY, TOM | CLOSED | 2011-07-20 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 586.88 | 0 | 0 | 0
PJ0003891 | ADD CENTER-DIVIDE HANDRAIL TO MAIN STAIRCASE - BLDG 35 | MAY, TOM | CLOSED | 2011-07-20 | IN: ADD CENTER-DIVIDE HANDRAIL TO MAIN STAIRCASE - BLDG 35 | 035 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003891 | ADD CENTER-DIVIDE HANDRAIL TO MAIN STAIRCASE - BLDG 35 | MAY, TOM | CLOSED | 2011-07-20 | PA: PAINT NEW HANDRAIL ON MAIN STAIRCASE - LIBRARY BLDG. 35 | 035 | CLOSED | 588.3396 | 0 | 474.912 | 474.912
PJ0003891 Total | [7 empty] | 6455.5256 | 0 | 5755.218 | 5755.218
PJ0003889 | REMOVE 2 DECOMMISSIONED STANDPIPES - CP PIER - BLD 228 (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-07-19 | AD: ALPHA FIRE | 228 | CLOSED | 0 | 0 | 0 | 0
PJ0003889 | REMOVE 2 DECOMMISSIONED STANDPIPES - CP PIER - BLD 228 (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-07-19 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 0 | 0 | 0 | 0
PJ0003889 | REMOVE 2 DECOMMISSIONED STANDPIPES - CP PIER - BLD 228 (NO ESTM) | MOLLAN, CHERYL L. | CLOSED | 2011-07-19 | IN: REMOVE 2 DECOMMISSIONED STANDPIPES - BLD 228 | 228 | CLOSED | 0 | 0 | 32.028 | 32.028
PJ0003889 Total | [7 empty] | 0 | 0 | 32.028 | 32.028
PJ0003888 | SUPPORT WORK FOR CAMPUS LOCK OUT / TAG OUT PROJECT (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-07-19 | CA: CREATE SIGNAGE FOR LOCK-OUT/TAG-OUT PROJECT | GENERAL | CLOSED | 0 | 0 | 234.95 | 234.95
PJ0003888 | SUPPORT WORK FOR CAMPUS LOCK OUT / TAG OUT PROJECT (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-07-19 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003888 | SUPPORT WORK FOR CAMPUS LOCK OUT / TAG OUT PROJECT (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-07-19 | CPE: SUPPORT WORK FOR CAMPUS LOCK OUT / TAG OUT PROJECT (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003888 | SUPPORT WORK FOR CAMPUS LOCK OUT / TAG OUT PROJECT (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-07-19 | ES: SUPPORT WORK FOR CAMPUS LOCK OUT / TAG OUT PROJECT | GENERAL | CLOSED | 0 | 0 | 234.135 | 234.135
PJ0003888 Total | [7 empty] | 0 | 0 | 469.085 | 469.085
PJ0003887 | REPLACE ENTRYWAY GLASS WITH TEMPERED GLASS - RESIDENCE HALLS | GRIFFIN, PATRICK E. | CLOSED | 2011-07-18 | AD: JOC 10.021.011 STAPLES | RESIDENCE | CLOSED | 15654.3461 | 0 | 15654.3461 | 15654.3461
PJ0003887 | REPLACE ENTRYWAY GLASS WITH TEMPERED GLASS - RESIDENCE HALLS | GRIFFIN, PATRICK E. | CLOSED | 2011-07-18 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 1565.43 | 0 | 0 | 0
PJ0003887 Total | [7 empty] | 17219.7761 | 0 | 15654.3461 | 15654.3461
PJ0003886 | REMOVE DECK & REPLACE WITH LANDING & STAIRS - BLD 117T BACK | GRIFFIN, PATRICK E. | CLOSED | 2011-07-14 | AD: TEMPLE BUILDERS | 117T | CLOSED | 992.6818 | 0 | 992.6818 | 992.6818
PJ0003886 | REMOVE DECK & REPLACE WITH LANDING & STAIRS - BLD 117T BACK | GRIFFIN, PATRICK E. | CLOSED | 2011-07-14 | CP: PROJECT CONTINGENCY | 117T | CLOSED | 99.27 | 0 | 0 | 0
PJ0003886 Total | [7 empty] | 1091.9518 | 0 | 992.6818 | 992.6818
PJ0003884 | REMODEL STUDY ROOMS AND ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | BRENNAN, MICHAEL | CLOSED | 2011-07-15 | AD: TEMPLE BUILDERS | 035 | CLOSED | 2051.725 | 0 | 2386.0679 | 2386.0679
PJ0003884 | REMODEL STUDY ROOMS AND ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | BRENNAN, MICHAEL | CLOSED | 2011-07-15 | CA:PURCHASE 8-8' WHITEBOARDS FOR 8 STUDY ROOMS-LIBRARY | 035 | CLOSED | 6349.8299 | 0 | 3889.392 | 3889.392
PJ0003884 | REMODEL STUDY ROOMS AND ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | BRENNAN, MICHAEL | CLOSED | 2011-07-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1593.06 | 0 | 0 | 0
PJ0003884 | REMODEL STUDY ROOMS AND ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | BRENNAN, MICHAEL | CLOSED | 2011-07-15 | EL:PLUGMOLD FOR 3 FLOORS + STUDY ROOMS IN LIBRARY | 035 | CLOSED | 27305.4641 | 0 | 31270.758 | 31270.758
PJ0003884 | REMODEL STUDY ROOMS AND ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | BRENNAN, MICHAEL | CLOSED | 2011-07-15 | IN: REMODEL STUDY RMS & ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003884 | REMODEL STUDY ROOMS AND ADD PLUG MOLD TO 3,4,5TH FLRS - BLDG 035 | BRENNAN, MICHAEL | CLOSED | 2011-07-15 | PA:PATCH N PAINT 8 STUDY ROOMS IN LIBRARY | 035 | CLOSED | 1705.6124 | 0 | 3916.65 | 3916.65
PJ0003884 Total | [7 empty] | 39133.8034 | 0 | 41590.9799 | 41590.9799
PJ0003883 | UPDATE LANDSCAPING IN LIBRARY COURTYARD - BLD 35 | MAY, TOM | CLOSED | 2011-07-15 | AD: JOC 11.022.018 STAPLES | 035 | CLOSED | 9182.5367 | 0 | 9182.5367 | 9182.5367
PJ0003883 | UPDATE LANDSCAPING IN LIBRARY COURTYARD - BLD 35 | MAY, TOM | CLOSED | 2011-07-15 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1158.43 | 0 | 0 | 0
PJ0003883 | UPDATE LANDSCAPING IN LIBRARY COURTYARD - BLD 35 | MAY, TOM | CLOSED | 2011-07-15 | IN: UPDATE LANDSCAPING IN LIBRARY COURTYARD - BLD 35 | 035 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003883 | UPDATE LANDSCAPING IN LIBRARY COURTYARD - BLD 35 | MAY, TOM | CLOSED | 2011-07-15 | LA:PREP FOR PAVER PROJECT IN LIBRARY COURTYARD | 035 | CLOSED | 6972.516 | 0 | 8122.026 | 8122.026
PJ0003883 Total | [7 empty] | 17441.5947 | 0 | 17432.6747 | 17432.6747
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | AD: OTIS ELEVATOR SUPPORT FOR 10/14 UCSB MEN'S SOCCER | 061 | CLOSED | 0 | 0 | 2181.59 | 2181.59
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SUPPROT FOR MEN'S SOCCER V. UCSB - OCT 14 AT 7PM | 061 | CLOSED | 0 | 0 | 241.17 | 241.17
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR M. SOCCER V. AKRON - SEPT 18 | 061 | CLOSED | 0 | 0 | 638.61 | 638.61
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR M. SOCCER V. W. VIRGINIA - SEPT 11 | 061 | CLOSED | 0 | 0 | 1040.022 | 1040.022
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER - OCT 12 | 061 | CLOSED | 0 | 0 | 1195.113 | 1195.113
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER EXHIBITION GAME - AUG 21 | 061 | CLOSED | 0 | 0 | 1739.988 | 1739.988
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER GAME - NOV 1 | 061 | CLOSED | 0 | 0 | 1169.514 | 1169.514
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER V. DENVER | 061 | CLOSED | 0 | 0 | 1095.93 | 1095.93
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER V. UC DAVIS - OCT 5 | 061 | CLOSED | 0 | 0 | 1367.835 | 1367.835
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER V. UC RIVERSIDE-OCT 9 | 061 | CLOSED | 0 | 0 | 1123.422 | 1123.422
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER V. UCSB - 10/14 | 061 | CLOSED | 0 | 0 | 2681.856 | 2681.856
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER V.SEATTLE - SEPT 4 | 061 | CLOSED | 0 | 0 | 1187.838 | 1187.838
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MEN'S SOCCER V.VILLANOVA - SEPT 9 | 061 | CLOSED | 0 | 0 | 1459.68 | 1459.68
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MENS SOCCER V. NEW MEXICO - SEPT 2 | 061 | CLOSED | 0 | 0 | 1988.814 | 1988.814
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR MLS SOCCER GAME - FEB 10 (CHARGED TO MO007) | 061 | CLOSED | 0 | 0 | 1277.22 | 1277.22
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR SOCCER V. CAL - AUG 13 | 061 | CLOSED | 0 | 0 | 1338.636 | 1338.636
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPRT FOR MEN'S SOCCER V. UNLV - AUG 27 | 061 | CLOSED | 0 | 0 | 912.3 | 912.3
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: CALLBACK FOR SCOREBOARD PROBLEM - AUG 27 | 061 | CLOSED | 0 | 0 | 290.616 | 290.616
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: SUPPORT MEN'S SOCCER V. UCSB - OCT 14 AT 7PM | 061 | CLOSED | 0 | 0 | 478.308 | 478.308
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | ES: MEN'S SOCCER V. UCSB - OCT 14 AT 7PM | 061 | CLOSED | 0 | 0 | 378.78 | 378.78
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: STRIPING FOR MEN'S SOCCER PRACTICES 2011/2012 | 061 | CLOSED | 0 | 0 | 565.26 | 565.26
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V CAL (EXHIBITION) AUG 13 | 061 | CLOSED | 0 | 0 | 922.806 | 922.806
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V CSU NORTHRIDGE - OCT 11 | 061 | CLOSED | 0 | 0 | 604.506 | 604.506
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V DENVER UNIV - SEPT 25 | 061 | CLOSED | 0 | 0 | 233.784 | 233.784
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V SEATTLE UNIV - SEPT 4 | 061 | CLOSED | 0 | 0 | 199.212 | 199.212
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UC DAVIS - OCT 5 | 061 | CLOSED | 0 | 0 | 253.266 | 253.266
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UC IRVINE - NOV 1 | 061 | CLOSED | 0 | 0 | 564.978 | 564.978
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UC RIVERSIDE - OCT 9 | 061 | CLOSED | 0 | 0 | 388.548 | 388.548
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UCSB - OCT 14 | 061 | CLOSED | 0 | 0 | 389.742 | 389.742
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UCSC (EXHIBITION) AUG 21 | 061 | CLOSED | 0 | 0 | 314.19 | 314.19
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UNIV OF NEW MEXICO SEPT 2 | 061 | CLOSED | 0 | 0 | 604.506 | 604.506
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V UNLV AUG 27 | 061 | CLOSED | 0 | 0 | 703.671 | 703.671
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V VILLANOVA - SEPT 9 | 061 | CLOSED | 0 | 0 | 701.916 | 701.916
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR M. SOCCER V W. VIRGINIA - SEPT 11 | 061 | CLOSED | 0 | 0 | 130.068 | 130.068
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR MEN'S SOCCER V. CERRITOS COLLEGE-APR 7 | 061 | CLOSED | 0 | 0 | 432.996 | 432.996
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR MEN'S SOCCER V. CSU MONTEREY BAY-APR 28 | 061 | CLOSED | 0 | 0 | 262.05 | 262.05
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR MLS SOCCER - FEB 10 | 061 | CLOSED | 0 | 0 | 390.204 | 390.204
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: PM RESTROOMS AT SPANOS STADIUM FOR SOCCER GAME - 2/10(MAINT) | 061 | CLOSED | 0 | 0 | 136.025 | 136.025
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: PM SPANOS STADIUM RESTROOM AS NEEDED FOR MEN SOCCER | 061 | CLOSED | 0 | 0 | 614.082 | 614.082
PJ0003882 | 11/12 MEN'S SOCCER EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: SUPPORT MEN'S SOCCER V. UCSB OCT 14 @ 7PM | 061 | CLOSED | 0 | 0 | 254.31 | 254.31
PJ0003882 Total | [7 empty] | 0 | 0 | 32453.362 | 32453.362
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | AD: OTIS ELEVATOR SUPPORT FOR 10/15 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 2057.76 | 2057.76
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | AD: OTIS ELEVATOR SUPPORT FOR FOOTBALL - 10/8 | 061 | CLOSED | 0 | 0 | 2181.59 | 2181.59
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | AD: OTIS ELEVATOR SUPPORT FOR NOV 12 FOOTBALL | 061 | CLOSED | 0 | 0 | 1981.25 | 1981.25
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | AD: OTIS ELEVATOR SUPPORT FOR OCT 29 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 1857.42 | 1857.42
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: CLEAN UP OF ROOF TRASH (EVENT RELATED) | 061 | CLOSED | 0 | 0 | 140.97 | 140.97
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: CONSTRUCT A 42" HIGH WOODEN GUARDRAIL FOR CAMERA PLTFM | 061 | CLOSED | 0 | 0 | 373.62 | 373.62
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: PRINT AND INSTALL 4 WHEELCHAIR SIGNS FOR SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 113.988 | 113.988
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SET OUT STANCHIONS PER UPD REQUEST | 061 | CLOSED | 0 | 0 | 930.402 | 930.402
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SUPPORT FOR FOOTBALL V. CEN OKLAHOMA - OCT 8 | 061 | CLOSED | 0 | 0 | 281.439 | 281.439
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SUPPORT FOR FOOTBALL V. EAST. WASHINGTON - NOV 12 | 061 | CLOSED | 0 | 0 | 376.488 | 376.488
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SUPPORT FOR FOOTBALL V. S. DAKOTA ST. - SEPT 17 | 061 | CLOSED | 0 | 0 | 331.476 | 331.476
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SUPPORT FOR FOOTBALL V. SOUTH DAKOTA - OCT 29 | 061 | CLOSED | 0 | 0 | 313.74 | 313.74
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CA: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT15 | 061 | CLOSED | 0 | 0 | 517.671 | 517.671
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CPE: SUPPORT FOR FOOTBALL V. CEN OKLAHOMA - OCT 8 | 061 | CLOSED | 0 | 0 | 382.14 | 382.14
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CPE: SUPPORT FOR FOOTBALL V. EAST. WASHINGTON - NOV 12 | 061 | CLOSED | 0 | 0 | 416.88 | 416.88
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CPE: SUPPORT FOR FOOTBALL V. S. DAKOTA ST. - SEPT 17 | 061 | CLOSED | 0 | 0 | 326.7101 | 326.7101
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CPE: SUPPORT FOR FOOTBALL V. SOUTH DAKOTA - OCT 29 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CPE: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT15 | 061 | CLOSED | 0 | 0 | 347.4 | 347.4
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: PREPARATION FOR FALL SEASON | 061 | CLOSED | 0 | 0 | 2335.488 | 2335.488
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR FOOTBALL EXHIBITION GAME-AUG 20 | 061 | CLOSED | 0 | 0 | 1285.224 | 1285.224
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR FOOTBALL V EASTERN WASH. - NOV 12 | 061 | CLOSED | 0 | 0 | 4126.836 | 4126.836
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR FOOTBALL V. CENT OKLAHOMA - OCT 8 | 061 | CLOSED | 0 | 0 | 4417.35 | 4417.35
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR FOOTBALL V. SOUTH DAKOTA - OCT 29 | 061 | CLOSED | 0 | 0 | 5169.99 | 5169.99
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR FOOTBALL V. SOUTH DAKOTA-SEPT 17 | 061 | CLOSED | 0 | 0 | 3685.692 | 3685.692
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT 15 | 061 | CLOSED | 0 | 0 | 5746.662 | 5746.662
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | CU: SUPPORT FOR GREEN & GOLD FOOTBALL GAME-APR 28 | 061 | CLOSED | 0 | 0 | 1404.708 | 1404.708
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: CALLBACK FOR POWER ISSUE AT O'NEILL LAWN | 061 | CLOSED | 0 | 0 | 253.104 | 253.104
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: INSTALL SPIDER BOX AT NORTH END CHASE LAWN BEFORE APR 28 | 115 | CLOSED | 0 | 0 | 202.248 | 202.248
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: INSTALL SPIDER BOX AT O'NEILL LAWN ON 10/8 | 061 | CLOSED | 0 | 0 | 269.664 | 269.664
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: INSTALL SPIDER BOX AT O'NEILL LAWN ON 9/14 | 061 | CLOSED | 0 | 0 | 202.248 | 202.248
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: STRAIGHTEN BENT FACE ON SOUTH DELAY OF GAME CLOCK | 061 | CLOSED | 0 | 0 | 471.912 | 471.912
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: SUPPORT FOR FOOTBALL V. CEN OKLAHOMA - OCT 8 | 061 | CLOSED | 0 | 0 | 472.5929 | 472.5929
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: SUPPORT FOR FOOTBALL V. EAST. WASHINGTON - NOV 12 | 061 | CLOSED | 0 | 0 | 1248.1438 | 1248.1438
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: SUPPORT FOR FOOTBALL V. S. DAKOTA ST. - SEPT 17 | 061 | CLOSED | 0 | 0 | 1198.1838 | 1198.1838
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: SUPPORT FOR FOOTBALL V. SOUTH DAKOTA - OCT 29 | 061 | CLOSED | 0 | 0 | 735.024 | 735.024
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EL: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT15 | 061 | CLOSED | 0 | 0 | 1494.1428 | 1494.1428
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EO: MOVE ENGR TRAILERS AT BLDG 13 | 061 | CLOSED | 0 | 0 | 88.728 | 88.728
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | EO: SUPPORT FOR FOOTBALL PARKING ADA ISSUES | 061 | CLOSED | 0 | 0 | 149.292 | 149.292
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | GR: SUPPROT FOR FOOTBALL EXHIBITION GAME | 061 | CLOSED | 0 | 0 | 433.278 | 433.278
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: FOOTBALL V. CENT OKLAHOMA - OCT 8 | 061 | CLOSED | 0 | 0 | 5796.453 | 5796.453
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: FOOTBALL V. EASTERN WASHINGTON - NOV 12 | 061 | CLOSED | 0 | 0 | 5231.088 | 5231.088
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: FOOTBALL V. SOUTH DAKOTA - OCT 29 | 061 | CLOSED | 0 | 0 | 5942.331 | 5942.331
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: FOOTBALL V. SOUTH DAKOTA ST - SEPT 17 | 061 | CLOSED | 0 | 0 | 7152.72 | 7152.72
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: FOOTBALL V. SOUTHERN UTAH - OCT 15 | 061 | CLOSED | 0 | 0 | 5643.909 | 5643.909
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SPRING FOOTBALL PRACTICE LINING | 061 | CLOSED | 0 | 0 | 1207.884 | 1207.884
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: STRIPING FOR FOOTBALL PRACTICES - 2011/2012 | 061 | CLOSED | 0 | 0 | 3169.002 | 3169.002
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | LA: SUPPORT FOR FOOTBALL GREEN/GOLD FOOTBALL GAME-APR 28 | 061 | CLOSED | 0 | 0 | 359.46 | 359.46
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | MC: SUPPORT FOR FOOTBALL PARKING - OCT 14 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: CHECK/REPLACE AREATORS ON SUITE LVL R.R. FAUCETS | 061 | CLOSED | 0 | 0 | 501.804 | 501.804
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: SUPPORT FOR FOOTBALL V. CEN OKLAHOMA - OCT 8 | 061 | CLOSED | 0 | 0 | 682.392 | 682.392
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: SUPPORT FOR FOOTBALL V. EAST. WASHINGTON - NOV 12 | 061 | CLOSED | 0 | 0 | 363.3 | 363.3
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: SUPPORT FOR FOOTBALL V. S. DAKOTA ST. - SEPT 17 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: SUPPORT FOR FOOTBALL V. SOUTH DAKOTA - OCT 29 | 061 | CLOSED | 0 | 0 | 290.64 | 290.64
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | PL: SUPPORT FOR FOOTBALL V. SOUTHERN UTAH - OCT15 | 061 | CLOSED | 0 | 0 | 145.32 | 145.32
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | RE: SUPPORT FOR FOOTBALL - OCT 29 | 061 | CLOSED | 0 | 0 | 423.036 | 423.036
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | RE: SUPPORT FOR FOOTBALL GAME - NOV 121 | 061 | CLOSED | 0 | 0 | 352.53 | 352.53
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | RE: SUPPORT FOR FOOTBALL GAME - OCT 15 | 061 | CLOSED | 0 | 0 | 587.55 | 587.55
PJ0003881 | 11/12 FOOTBALL SEASON SUPPORT | POPHAM, DONALD J. | CLOSED | 2011-07-14 | RE: SUPPORT FOR FOOTBALL GAME - OCT 8 | 061 | CLOSED | 0 | 0 | 188.016 | 188.016
PJ0003881 Total | [7 empty] | 0 | 0 | 86996.9304 | 86996.9304
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: (FP FUNDING WITH OH) DOVE SYSTEMS - PARTS INSTALLED BY JOC | 006 | CLOSED | 3649.2885 | 0 | 3756.2885 | 3756.2885
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: (FP FUNDING WITH OH) JOC 12.024.002.02 STAPLES | 006 | CLOSED | 108541.0675 | 0 | 95192.2611 | 95192.2611
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: ASAP REPROGRAPHICS | 006 | CLOSED | 130.54 | 0 | 130.54 | 130.54
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: BUEHLER AND BUEHLER | 006 | CLOSED | 27820 | 0 | 23463.6983 | 23463.6983
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: CC PURCHASES -VARIOUS VENDORS- TO BE INSTALLED BY CONTRACTOR | 006 | CLOSED | 524.71 | 0 | 524.7 | 524.7
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: JOC 12.024.002 STAPLES.00, .01, .03, .04, .05 | 006 | CLOSED | 732308.7062 | 0 | 732308.7062 | 732308.7062
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: JOC 13.027.003 PUB | 006 | CLOSED | 2034.2091 | 0 | 2034.2091 | 2034.2091
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: PACIFIC WEST SOUND COMPANY | 006 | CLOSED | 2381.9056 | 0 | 2381.9163 | 2381.9163
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: PRO SOUND | 006 | CLOSED | 787445.0144 | 0 | 788515.0144 | 788515.0144
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: THOMA ELECTRIC | 006 | CLOSED | 37450 | 0 | 17626.5808 | 17626.5808
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | AD: WLH BUILDING COMPANY | 006 | CLOSED | 1685.785 | 0 | 1685.785 | 1685.785
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | CP: (FP FUNDING WITH OH) PROJECT CONTINGENCY | 006 | CLOSED | 7631.17 | 0 | 0 | 0
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 31213.69 | 0 | 0 | 0
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | CU: CLEAN PAC PAVILION AFTER MOVE - 9/10/12 10:30 AM (ISH) (N/L) | 006 | CLOSED | 131.184 | 0 | 0 | 0
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | EL: INSTALL HIGH VOLTAGE PANEL & TRANSFORMER - PAC 06 | 006 | CLOSED | 18737.5656 | 0 | 14541.66 | 14541.66
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | IN: (PAC FUNDING) HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 06 | 006 | CLOSED | 2562.24 | 0 | 1665.456 | 1665.456
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | IN:(FP FUNDING WITH OH) HARMON HALL AUDIO & ACOUSTIC PROJECT-PAC | 006 | CLOSED | 1921.68 | 0 | 320.28 | 320.28
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | MO: MOVE BOXES FROM PAC PAVILION | 006 | CLOSED | 129.6 | 0 | 48.288 | 48.288
PJ0003880 | HARMAN HALL AUDIO & ACOUSTIC PROJECT - BLDG 006 | LAMPMAN, GREG | CLOSED | 2011-07-12 | PA: (FP FUNDING WITH OH) PAINTING FOR PAC AUDIO&ACOUSTIC PROJECT | 006 | CLOSED | 2342.164 | 0 | 1473.372 | 1473.372
PJ0003880 Total | [7 empty] | 1768640.5199 | 0 | 1685668.7557 | 1685668.7557
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | AD: J.L. FAULSO | 026 | CLOSED | 1554.6351 | 0 | 1521.54 | 1521.54
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | AD: PARC ENVIRONMENTAL | 026 | CLOSED | 3520.3 | 0 | 3520.3 | 3520.3
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | CA:REMODEL IN 26-212B | 026 | CLOSED | 2607.9767 | 0 | 2280.81 | 2280.81
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | CU: RESEAL FLOOR IN 26-212B | 026 | CLOSED | 286.2924 | 0 | 196.776 | 196.776
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | EL:DEMO ELECTRICAL IN WALLS TO BE REMOVED 26-212F | 026 | CLOSED | 1560.679 | 0 | 1192.476 | 1192.476
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | ES:MOVE T-STAT IN 26-212B | 026 | CLOSED | 675.6804 | 0 | 669.084 | 669.084
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | IN: REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | 026 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | LO: INSTALL A NEW LOCKSET ON THE MECHANICAL ROOM DOOR IN 26-212B | 026 | CLOSED | 0 | 0 | 977.874 | 977.874
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | PA: PATCH AND PAINT 26-212B | 026 | CLOSED | 2882.2916 | 0 | 1510.644 | 1510.644
PJ0003879 | REMODEL ROOM FOR FUTURE RESOURCE/STUDY LAB - BLD 26 RM 212B | MAY, TOM | CLOSED | 2011-07-07 | PL:REMOVE PLUMBING IN 26-212F | 026 | CLOSED | 1803.9493 | 0 | 1380.54 | 1380.54
PJ0003879 Total | [7 empty] | 14955.8605 | 0 | 13314.1 | 13314.1
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | AD: FLOOR CONNECTION | 035 | CLOSED | 13336.5121 | 0 | 13336.5228 | 13336.5228
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 3060.2 | 0 | 3060.2 | 3060.2
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | AD: SAN LUIS GLASS | 035 | CLOSED | 5323.25 | 0 | 5345.3348 | 5345.3348
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5136 | 0 | 5136 | 5136
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1474.05 | 0 | 0 | 0
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | EL:DISCONNECT OUTLET AND REROUTE LIGHT SWITCH IN 35-111C | 035 | CLOSED | 2577.9852 | 0 | 1613.004 | 1613.004
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | IN: REMODEL ROOM - KEN LIB 35 RM 111C | 035 | CLOSED | 160.14 | 0 | 128.112 | 128.112
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | LO:CYLINDERS AND DOOR CLOSURES IN 35-111C | 035 | CLOSED | 549.4381 | 0 | 845.412 | 845.412
PJ0003878 | REMODEL ROOM - KEN LIB 35 RM 111C | MAY, TOM | CLOSED | 2011-07-07 | PA:PATCH AND PAINT LIBRARY 111C | 035 | CLOSED | 1705.6124 | 0 | 2491.044 | 2491.044
PJ0003878 Total | [7 empty] | 33323.1879 | 0 | 31955.6296 | 31955.6296
PJ0003877 | FP 11/12: REPLACE THE FINISHES IN ADMIN ELEVATOR - BLDG 01 | JUDD, PERRY | CLOSED | 2011-07-07 | AD: OTIS ELEVATOR | 001 | CLOSED | 36918.72 | 0 | 30021.72 | 30021.72
PJ0003877 | FP 11/12: REPLACE THE FINISHES IN ADMIN ELEVATOR - BLDG 01 | JUDD, PERRY | CLOSED | 2011-07-07 | CA: VACUUM ASBESTOS DEBRIS FOR ELEVATOR FLOORING INSTALLER - 001 | 001 | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0003877 | FP 11/12: REPLACE THE FINISHES IN ADMIN ELEVATOR - BLDG 01 | JUDD, PERRY | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0003877 | FP 11/12: REPLACE THE FINISHES IN ADMIN ELEVATOR - BLDG 01 | JUDD, PERRY | CLOSED | 2011-07-07 | IN: FP 11/12: REPLACE THE FINISHES IN ADMIN ELEVATOR - BLDG 01 | 001 | CLOSED | 106.76 | 0 | 80.07 | 80.07
PJ0003877 Total | [7 empty] | 37025.48 | 0 | 30148.78 | 30148.78
PJ0003876 | HAZMAT ASSESSMENT FOR UU CHASE BANK SPACE - BLDG 065-103 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | AD: ASAP REPROGRAPHICS (DIRECT-PAY) | 065 | CLOSED | 0 | 0 | 30.26 | 30.26
PJ0003876 | HAZMAT ASSESSMENT FOR UU CHASE BANK SPACE - BLDG 065-103 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | AD: MCKENNA ENVIRONMENTAL | 065 | CLOSED | 2503.8 | 0 | 2487.1508 | 2487.1508
PJ0003876 | HAZMAT ASSESSMENT FOR UU CHASE BANK SPACE - BLDG 065-103 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | AD: PARC ENVIRONMENTAL | 065 | CLOSED | 963 | 0 | 963 | 963
PJ0003876 | HAZMAT ASSESSMENT FOR UU CHASE BANK SPACE - BLDG 065-103 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 353.09 | 0 | 0 | 0
PJ0003876 | HAZMAT ASSESSMENT FOR UU CHASE BANK SPACE - BLDG 065-103 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | IN: HAZMAT ASSESSMENT FOR UU CHASE BANK SPACE - BLDG 065-103 | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003876 Total | [7 empty] | 3883.946 | 0 | 3544.4668 | 3544.4668
PJ0003874 | SUBWAY PROJECT - DEMO FOR NEW CONSTRUCTION -BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | AD: JOC 11.022.016 STAPLES | 034 | CLOSED | 8653.9995 | 0 | 8601.2164 | 8601.2164
PJ0003874 | SUBWAY PROJECT - DEMO FOR NEW CONSTRUCTION -BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 650.39 | 0 | 0 | 0
PJ0003874 | SUBWAY PROJECT - DEMO FOR NEW CONSTRUCTION -BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | EH&S: SUBWAY PROJECT - DEMO & CONSTRUCTION -BLD 34 (N/L) | 034 | CLOSED | 92.7 | 0 | 67.2 | 67.2
PJ0003874 | SUBWAY PROJECT - DEMO FOR NEW CONSTRUCTION -BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | IN: SUBWAY PROJECT - DEMO & CONSTRUCTION -BLD 34 | 034 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003874 | SUBWAY PROJECT - DEMO FOR NEW CONSTRUCTION -BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-07-07 | LA: CLEAN PATIO IN FRONT OF SUBWAY RESTAURANT AREA - DEXTER 034 | 034 | CLOSED | 311.712 | 0 | 86.712 | 86.712
PJ0003874 Total | [7 empty] | 9772.8575 | 0 | 8819.1844 | 8819.1844
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | CA: PLASTER AND FILL IN HOLES - MENS 1ST FL. RESTROOM - UU 065 | 065 | CLOSED | 0 | 0 | 751.044 | 751.044
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | CPE: ISOLATE THE UU UTILIDOR RUN OUT VALVES | 065 | CLOSED | 0 | 0 | 634.434 | 634.434
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | CPE:PROVIDE/INSTALL PORTABLE HVAC UNIT IN CHASE BANK-CHEVRON III | 065 | CLOSED | 0 | 0 | 124.872 | 124.872
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | EL: ASSIST CENTRAL PLANT ISOLATE THE UU UTILIDOR RUN OUT VALVES | 065 | CLOSED | 0 | 0 | 134.832 | 134.832
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | EL: ASSIST CHEVRON WITH TESTING - PHASE III ENERGY PROJECT AT UU | 065 | CLOSED | 0 | 0 | 2225.04 | 2225.04
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | EL: CHANGE ALARMS TO TEST MODE FOR DUCT CLEANING AT UU - 065 | 065 | CLOSED | 0 | 0 | 471.912 | 471.912
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | ES: HVAC WATER SHUTDOWN/BUILDING DRAINAGE/CHEM FLUSH - UU 065 | 065 | CLOSED | 0 | 0 | 2876.274 | 2876.274
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | ES: MODIFY VENTILATION & VALIDATE AIR BALANCE-UU 1ST FL MEN'S RR | 065 | CLOSED | 0 | 0 | 2651.0316 | 2651.0316
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | ES: REVIEW/INSPECT BLDG. OPS TO DEVELOP COMMISSIONING PUNCHLIST | 065 | CLOSED | 2497.44 | 0 | 5525.586 | 5525.586
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | LO: INSTALL 110 CORE - UU 065 ADJACENT TO RM. 212 | 065 | CLOSED | 0 | 0 | 116.088 | 116.088
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | PA: TOUCH-UP PAINT FOR CHEVRON PHASE III PROJECT - UU BLDG. 65 | 065 | CLOSED | 0 | 0 | 8775.366 | 8775.366
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | PL: ASSESS HOT WATER PIPING CONNECTION - UU BLDG 65 RM 104 (N/L) | 065 | CLOSED | 0 | 0 | 40.008 | 40.008
PJ0003870 | MJ: UNIVERSITY UNION - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | PL: COORDINATION AND WATER SUPPLY FOR HVAC RESTART - UU 065 | 065 | CLOSED | 0 | 0 | 3032.154 | 3032.154
PJ0003870 Total | [7 empty] | 2497.44 | 0 | 27358.6416 | 27358.6416
PJ0003869 | MJ: HOUSING FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003869 | MJ: HOUSING FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | EL: ASSIST CHEVRON WITH RETROFIT AT DORMS (PHASE III ENERGY PJS) | RESIDENCE | CLOSED | 0 | 0 | 101.124 | 101.124
PJ0003869 | MJ: HOUSING FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | EL: REPAIR ELECTRICAL CONDUIT IN YOSEMITE T/6 3RD FLOOR RESTROOM | RESIDENCE | CLOSED | 0 | 0 | 134.832 | 134.832
PJ0003869 | MJ: HOUSING FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | IN: HOUSING FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | RESIDENCE | CLOSED | 0 | 0 | 128.112 | 128.112
PJ0003869 | MJ: HOUSING FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-07 | PL: SHUT DOWN WATER AT YOSEMITE TOWER 6 | RESIDENCE | CLOSED | 0 | 0 | 32.646 | 32.646
PJ0003869 Total | [7 empty] | 0 | 0 | 396.714 | 396.714
PJ0003867 | MJ: STATE FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-05 | CA: CUT TILE FOR CONTRACTOR FOR USE IN BLDG. 40 - CHEVRON III PJ | GENERAL | CLOSED | 0 | 0 | 56.388 | 56.388
PJ0003867 | MJ: STATE FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-05 | CA:STATE FAC-MATERIALS USED BY CHEVRON PHASE III PJS (MAT ONLY) | GENERAL | CLOSED | 0 | 0 | 49.2 | 49.2
PJ0003867 | MJ: STATE FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-05 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003867 | MJ: STATE FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-05 | LO: INSTALL ORANGE CONSTRUCTION CORE ON ENTRANCE TO 33-358 | GENERAL | CLOSED | 0 | 0 | 58.044 | 58.044
PJ0003867 | MJ: STATE FACILITIES - IN-HOUSE SUPPORT FOR CHEVRON PHASE III | UYTTEWAAL, JOHAN M | CLOSED | 2011-07-05 | PL: COORDINATION DURING FIXTURE INSTALLATION IN BLDGS 5 & 40 | GENERAL | CLOSED | 0 | 0 | 2272.464 | 2272.464
PJ0003867 Total | [7 empty] | 0 | 0 | 2436.096 | 2436.096
PJ0003866 | INSTALL GUTTER ON REAR SECTION OF STAGE CANOPY - UU PLAZA 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-28 | AD: QUAGLINO ROOFING | 065 | CLOSED | 3745 | 0 | 3398.32 | 3398.32
PJ0003866 | INSTALL GUTTER ON REAR SECTION OF STAGE CANOPY - UU PLAZA 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-28 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 375.9 | 0 | 0 | 0
PJ0003866 | INSTALL GUTTER ON REAR SECTION OF STAGE CANOPY - UU PLAZA 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-28 | IN: INSTALL GUTTER ON REAR SECTION OF STAGE CANOPY - UU PLAZA 65 | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003866 | INSTALL GUTTER ON REAR SECTION OF STAGE CANOPY - UU PLAZA 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-28 | LA: INSTALL SPLASH BLOCKS FOR UU GUTTER PROJECT | 065 | CLOSED | 1295.136 | 0 | 155.856 | 155.856
PJ0003866 Total | [7 empty] | 5544.148 | 0 | 3682.288 | 3682.288
PJ0003865 | CAMES SECURITY INSTALLATION - BLD 3 4TH FLOOR | ELLIOT, DENNIS K | CLOSED | 2011-06-27 | ANTS: PROGRAM PANIC BUTTON - BUSINESS 4TH FLOOR | 003 | CLOSED | 213.8136 | 0 | 48.048 | 48.048
PJ0003865 | CAMES SECURITY INSTALLATION - BLD 3 4TH FLOOR | ELLIOT, DENNIS K | CLOSED | 2011-06-27 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 88.08 | 0 | 0 | 0
PJ0003865 | CAMES SECURITY INSTALLATION - BLD 3 4TH FLOOR | ELLIOT, DENNIS K | CLOSED | 2011-06-27 | EL: PROVIDE POWER TO PANIC BUTTON SYSTEM FOR CAME SECURITY | 003 | CLOSED | 540.0012 | 0 | 525.6 | 525.6
PJ0003865 | CAMES SECURITY INSTALLATION - BLD 3 4TH FLOOR | ELLIOT, DENNIS K | CLOSED | 2011-06-27 | IN: CAMES SECURITY INSTALLATION - BLD 3 4TH FLOOR | 003 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0003865 Total | [7 empty] | 905.9508 | 0 | 605.676 | 605.676
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: (FP) AT&T - CABLE FOR NEW UPD OFFICES (DIRECT PAY) | 036 | CLOSED | 10000 | 0 | 10306.86 | 10306.86
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: (FP) JOC 11.023.027 STAPLES (FOR TELECOM CABLING) | 036 | CLOSED | 76237.48 | 0 | 76237.48 | 76237.48
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: CENTRAL COAST PROPANE | 036 | CLOSED | 939.5777 | 0 | 939.5777 | 939.5777
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: JOC 10.022.009 STAPLES | 036 | CLOSED | 68829.1731 | 0 | 68829.1731 | 68829.1731
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: JOC 11.023.042 STAPLES | 036 | CLOSED | 17621.1024 | 0 | 17621.1024 | 17621.1024
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: QUAGLINO ROOFING | 036 | CLOSED | 0 | 0 | 5082.5 | 5082.5
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: QUINN POWER SYSTEMS | 036 | CLOSED | 41748.3077 | 0 | 41942.9407 | 41942.9407
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: STATE FIRE MARSHAL FEES | 036 | CLOSED | 3750 | 0 | 8580 | 8580
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | CA: REMOVE CHAIN LINK FENCING & INSTALL FAUCET BACKING - BLDG 36 | 036 | CLOSED | 902.208 | 0 | 1513.416 | 1513.416
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 1781.52 | 0 | 0 | 0
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | EL: INSTALL OUTLET IN DISPATCH OFFICE, PER JOB WALK - UPD 036 | 036 | CLOSED | 2217.984 | 0 | 1525.248 | 1525.248
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | EO: LOCATE UTILITIES, TRENCHING, AND CONCRETE REMOVAL | 036 | CLOSED | 7499.4348 | 0 | 7136.28 | 7136.28
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | IN: SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | 036 | CLOSED | 512.448 | 0 | 192.168 | 192.168
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | LA: SUPPORT FOR UTILITY LINE INSTALL FOR NEW UPD OFFICES - 36 | 036 | CLOSED | 623.424 | 0 | 281.532 | 281.532
PJ0003863 | SP 11/12: SITE IMPROVEMENTS AND UTILITY UPGRADES - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | PL: UTILITY TRACING AND RELOCATION | 036 | CLOSED | 7930.368 | 0 | 8778.2681 | 8778.2681
PJ0003863 Total | [7 empty] | 240593.0277 | 0 | 248966.546 | 248966.546
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: BFGC DBA IBI GROUP ARCHITECTURE PLANNING | 036 | CLOSED | 21271.6642 | 0 | 24083.5049 | 24083.5049
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: JOC 10.022.003 STAPLES | 036 | CLOSED | 199488.5102 | 0 | 199489.3983 | 199489.3983
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | AD: MCKENNA ENVIRONMENTAL | 036 | CLOSED | 12593.9 | 0 | 12195.86 | 12195.86
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | CA: CORE 3" HOLES IN ACCESS FLOOR AT UPD AND INSTALL GROMMETS | 036 | CLOSED | 0 | 0 | 370.614 | 370.614
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 0 | 0 | 0 | 0
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | EL: ELECTRICAL AND FIRE ALARM CLEARANCE | 036 | CLOSED | 1652.3652 | 0 | 2160.756 | 2160.756
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | IN: SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | 036 | CLOSED | 994.1491 | 0 | 288.252 | 288.252
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | LO: NEW DOOR LOCKS | 036 | CLOSED | 588.264 | 0 | 1537.41 | 1537.41
PJ0003862 | SP 11/12: SHELL STRUCTURE REPAIR - BLDG 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-06-24 | PL: UTILITIES CLEARANCE FOR NEW UPD FACILITY - BLDG 36 | 036 | CLOSED | 261.168 | 0 | 304.866 | 304.866
PJ0003862 Total | [7 empty] | 236850.0207 | 0 | 240430.6612 | 240430.6612
PJ0003861 | FP 10/11: ADA WALKWAY THROUGH O'NEILL GREEN | LAMPMAN, GREG | CLOSED | 2011-06-24 | AD: JOC 10.022.006 STAPLES | GENERAL | CLOSED | 173411.59 | 0 | 173411.59 | 173411.59
PJ0003861 | FP 10/11: ADA WALKWAY THROUGH O'NEILL GREEN | LAMPMAN, GREG | CLOSED | 2011-06-24 | AD: WALLACE GROUP | GENERAL | CLOSED | 3335 | 0 | 3568.45 | 3568.45
PJ0003861 | FP 10/11: ADA WALKWAY THROUGH O'NEILL GREEN | LAMPMAN, GREG | CLOSED | 2011-06-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 11241.62 | 0 | 0 | 0
PJ0003861 | FP 10/11: ADA WALKWAY THROUGH O'NEILL GREEN | LAMPMAN, GREG | CLOSED | 2011-06-24 | IN: FP 10/11: ADA WALKWAY THROUGH O'NEILL GREEN | GENERAL | CLOSED | 1334.5 | 0 | 480.42 | 480.42
PJ0003861 | FP 10/11: ADA WALKWAY THROUGH O'NEILL GREEN | LAMPMAN, GREG | CLOSED | 2011-06-24 | LA: TRIM TREES, RE-LANDSCAPE AS NEEDED-O'NEILL GREEN ADA WALKWAY | GENERAL | CLOSED | 4461.15 | 0 | 17181.1916 | 17181.1916
PJ0003861 Total | [7 empty] | 193783.86 | 0 | 194641.6516 | 194641.6516
PJ0003860 | FP 10/11: ADA SIDEWALK AT CALIFORNIA BLVD. | LAMPMAN, GREG | CLOSED | 2011-06-24 | AD: JOC 10.022.005 STAPLES (PARTIAL - SEE PJ 3806 FOR REMAINDER) | GENERAL | CLOSED | 0 | 0 | 148383.78 | 148383.78
PJ0003860 | FP 10/11: ADA SIDEWALK AT CALIFORNIA BLVD. | LAMPMAN, GREG | CLOSED | 2011-06-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 150000 | 0 | 0 | 0
PJ0003860 | FP 10/11: ADA SIDEWALK AT CALIFORNIA BLVD. | LAMPMAN, GREG | CLOSED | 2011-06-24 | LA: LANDSCAPING FOR SIDEWALK ALONG CALIF BLVD - ROAD REBUILD PJ | GENERAL | CLOSED | 0 | 0 | 3509.4375 | 3509.4375
PJ0003860 Total | [7 empty] | 150000 | 0 | 151893.2175 | 151893.2175
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | AD: EARTH SYSTEMS | 018A | CLOSED | 5831.5 | 0 | 4040.855 | 4040.855
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | AD: ENGLEKIRK AND SABOL - SEISMIC PEER REVIEW | 018A | CLOSED | 1605 | 0 | 535 | 535
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | AD: JOC 10.022.007.00, 11.022.007.01 & .02 STAPLES | 018A | CLOSED | 143885.254 | 0 | 135787.3763 | 135787.3763
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | AD: QUARESMA DRYWALL | 018A | CLOSED | 1830.4383 | 0 | 1830.4383 | 1830.4383
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | CA: CONSTRUCT WALLS AND DOOR DRY STORAGE BUILDING 18A | 018A | CLOSED | 2327.76 | 0 | 18008.1832 | 18008.1832
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | CA: SUPPORT ELECTRIC SHOP - DAIRY DRY INGREDIENTS STORAGE BLDG. | 018A | CLOSED | 571.104 | 0 | 436.464 | 436.464
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | CP: (CPF FUNDING) PROJECT CONTINGENCY | 018A | CLOSED | 0 | 0 | 0 | 0
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | CP: PROJECT CONTINGENCY | 018A | CLOSED | 7815.22 | 0 | 0 | 0
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | EL: (CPF FUNDING) INSTALL NEW ELECTRICAL TO BUILDING 18S | 018A | CLOSED | 20402.0525 | 0 | 21232.9908 | 21232.9908
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | EL: INSTALL ELECTRICAL TO 18S NEW BUILDING | 018A | CLOSED | 4800.6862 | 0 | 7053.6816 | 7053.6816
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | EL:INSTALL ELECTRICAL IN NEW WALLS-DAIRY DRY INGREDIENTS STORAGE | 018A | CLOSED | 1588.32 | 0 | 1669.764 | 1669.764
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | EO: (CPF FUNDING) SUPPLY A NEW TRENCH FOR ELECTRICAL | 018A | CLOSED | 1938.3078 | 0 | 2499.024 | 2499.024
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | EO: SUPPLY A TRENCH FOR ELECTRICAL | 018A | CLOSED | 2470.56 | 0 | 1675.764 | 1675.764
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | IN: (CPF FUNDING) DRY INGREDIENTS STORAGE BUILDING - DAIRY | 018A | CLOSED | 285.0492 | 0 | 224.196 | 224.196
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | IN: DRY INGREDIENTS STORAGE BUILDING - DAIRY | 018A | CLOSED | 1281.12 | 0 | 800.7 | 800.7
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | LO: INSTALL CORE | 018A | CLOSED | 858.2958 | 0 | 29.022 | 29.022
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | LO: LOCKS FOR TWO NEW DOORS - DAIRY DRY INGREDIENTS STORAGE | 018A | CLOSED | 952.176 | 0 | 1567.242 | 1567.242
PJ0003859 | CONSTRUCT DRY INGREDIENTS STORAGE BUILDING - DAIRY | LAMPMAN, GREG | CLOSED | 2011-06-22 | PA: PAINT NEW WALLS - DAIRY DRY INGREDIENTS STORAGE | 018A | CLOSED | 1189.824 | 0 | 949.824 | 949.824
PJ0003859 Total | [7 empty] | 199632.6677 | 0 | 198340.5252 | 198340.5252
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: CLEANUP AT SPANOS THEATRE AFTER 1/7 EVENT | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: CUSTODIAL SUPPORT FOR ADV OF KING ARTHUR - JULY 9 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT-JULY 16 | 044 | CLOSED | 0 | 0 | 327.96 | 327.96
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: CUSTODIAL SUPPORT FOR SPILLER RECITAL - 1/6 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: PRESIDENT'S CABINET SUPPORT- APR 27 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SPANOS EVENT SUPPORT - SEPT 16 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SPANOS THEATRE SUPPORT FOR EVENT-SEPT 15 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SPANOS THEATRE SUPPORT FOR MAY 31 PERFORMANCE | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR 4/27 EVENT SPANOS THEATRE PRESIDENT'S CABINET | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR ALICE IN WONDERLAND - MAR 18 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR ALICE IN WONDERLAND-MAR 16 | 044 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR ARAB MUSIC CONCERT - MAR 10 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR CATA CONFERENCE - JUNE 24 | 044 | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR CORE DANCE EVENT MAR 24 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR CPA COLLECTIVE JAZZ - MAR 23 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR DEC 16 EVENT - ELVES & SHOEMAKER | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR JON MCCUCHEON - ,AR 17 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR KAHUMOKU PERFOORMANCE - MARCH 9 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR MOCK ROCK - APR 22 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR ORCHESIS IMMERSION EVENT 2/3-2/5 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR ORCHSIS EVENT - 1/27-1/29 | 044 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS EVENT-AXIS DANCE COM - OCT 15 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE - JUNE 18 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE - JUNE 25 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT (CORE) - OCT 22/23 | 044 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - 9/30 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - DEC 4 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - OCT 1 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - OCT 21 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - OCT 6 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 11 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 12 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 14 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 18 | 044 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 22 | 044 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 23 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 25 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 26 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 27 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 28 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 29 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 7 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT - SEPT 8 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT-JUNE 2 | 044 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT: OCT 29 (NO LABOR) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT:COME TOGETHER-OCT 23 (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE EVENT_-APR 8 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR SPANOS THEATRE FRIDAY EVENTS - MAR 30 | 044 | CLOSED | 0 | 0 | 291.936 | 291.936
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR STREET HEAT MAY 19 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR STREETCAR NAMED DESIRE PERF. - FEB 23-25 | 044 | CLOSED | 0 | 0 | 262.368 | 262.368
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR THEATRE EVENT - JUNE 10 | 044 | CLOSED | 0 | 0 | 109.476 | 109.476
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT FOR WALDEMAN EVENT - APR 15 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003858 | 11/12 CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS - BLD 44 | POPHAM, DONALD J. | CLOSED | 2011-06-21 | CU: SUPPORT MONTRAL GUITAR TRIO - APR 21 | 044 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003858 Total | [7 empty] | 0 | 0 | 3828.594 | 3828.594
PJ0003857 | SUPPLY ELECTRICAL & REMOVE FAN UNIT - BLD 21 | ELLIOT, DENNIS K | CLOSED | 2011-06-17 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 252.13 | 0 | 0 | 0
PJ0003857 | SUPPLY ELECTRICAL & REMOVE FAN UNIT - BLD 21 | ELLIOT, DENNIS K | CLOSED | 2011-06-17 | EL: SUPPLY ELECTRICAL TO NEW OIL COOLERS | 021 | CLOSED | 1680.679 | 0 | 2190.54 | 2190.54
PJ0003857 | SUPPLY ELECTRICAL & REMOVE FAN UNIT - BLD 21 | ELLIOT, DENNIS K | CLOSED | 2011-06-17 | ES: CAP OFF ABANDONED DUCT | 021 | CLOSED | 777.0725 | 0 | 340.422 | 340.422
PJ0003857 | SUPPLY ELECTRICAL & REMOVE FAN UNIT - BLD 21 | ELLIOT, DENNIS K | CLOSED | 2011-06-17 | IN: SUPPLY ELECTRICAL & REMOVE FAN UNIT - BLD 21 | 021 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003857 Total | [7 empty] | 2773.9374 | 0 | 2595.018 | 2595.018
PJ0003856 | REMOVE PARTIAL WALL & PAINT OFFICES - BLD 13 RM 260 | LAMPMAN, GREG | CLOSED | 2011-06-16 | AD: JOC 11.022.034 STAPLES | 013 | CLOSED | 5991.4008 | 0 | 5991.4008 | 5991.4008
PJ0003856 | REMOVE PARTIAL WALL & PAINT OFFICES - BLD 13 RM 260 | LAMPMAN, GREG | CLOSED | 2011-06-16 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 649.11 | 0 | 0 | 0
PJ0003856 | REMOVE PARTIAL WALL & PAINT OFFICES - BLD 13 RM 260 | LAMPMAN, GREG | CLOSED | 2011-06-16 | EL: REMOVE OUTLETS | 013 | CLOSED | 990.3401 | 0 | 760.032 | 760.032
PJ0003856 | REMOVE PARTIAL WALL & PAINT OFFICES - BLD 13 RM 260 | LAMPMAN, GREG | CLOSED | 2011-06-16 | IN: REMOVE PARTIAL WALL & PAINT OFFICES - BLD 13 RM 260 | 013 | CLOSED | 256.224 | 0 | 192.168 | 192.168
PJ0003856 | REMOVE PARTIAL WALL & PAINT OFFICES - BLD 13 RM 260 | LAMPMAN, GREG | CLOSED | 2011-06-16 | PA: PAINT CP1 IN ROOMS 260, 263, AND 263A | 013 | CLOSED | 1561.4426 | 0 | 1711.464 | 1711.464
PJ0003856 Total | [7 empty] | 9448.5175 | 0 | 8655.0648 | 8655.0648
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | AD: DA CRAGHEAD CONSTRUCTION | 057 | CLOSED | 5178.8 | 0 | 5178.7893 | 5178.7893
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | AD: G.F. GARCIA AND SONS, INC. | 057 | CLOSED | 2140 | 0 | 2140 | 2140
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | CP: PROJECT CONTINGENCY | 057 | CLOSED | 711.54 | 0 | 0 | 0
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | CPE:INSTALL COOLER AT VET CLINIC | 057 | CLOSED | 5183.4353 | 0 | 6211.572 | 6211.572
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | EL:INSTALL AND HOOK UP POWER FOR NEW COLD STORAGE AT VET | 057 | CLOSED | 4934.2226 | 0 | 3287.136 | 3287.136
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | EO: (MAINT) EXCAVATE FOR ELECTRICAL LINE AT VET CLINIC | 057 | CLOSED | 0 | 0 | 665.46 | 665.46
PJ0003855 | INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | MAY, TOM | CLOSED | 2011-06-16 | IN: INSTALLATION FOR WALK-IN REFRIGERATION UNIT - VET CLINIC 057 | 057 | CLOSED | 192.168 | 0 | 192.168 | 192.168
PJ0003855 Total | [7 empty] | 18340.1659 | 0 | 17675.1253 | 17675.1253
PJ0003854 | SR 11/12: OBTAIN PERMITS FOR PARKER RANCH BRIDGE SCOUR PROJECT | LAMPMAN, GREG | CLOSED | 2011-06-15 | AD: PERMIT FEES | 229 | CLOSED | 5000 | 0 | 4773.25 | 4773.25
PJ0003854 | SR 11/12: OBTAIN PERMITS FOR PARKER RANCH BRIDGE SCOUR PROJECT | LAMPMAN, GREG | CLOSED | 2011-06-15 | AD: SWCA | 229 | CLOSED | 17175 | 0 | 17175 | 17175
PJ0003854 | SR 11/12: OBTAIN PERMITS FOR PARKER RANCH BRIDGE SCOUR PROJECT | LAMPMAN, GREG | CLOSED | 2011-06-15 | CP: PROJECT CONTINGENCY | 229 | CLOSED | 0 | 0 | 0 | 0
PJ0003854 Total | [7 empty] | 22175 | 0 | 21948.25 | 21948.25
PJ0003852 | MJ:IN-HOUSE SUPPORT LOCATE UTILITIES FOR INTERCONNECTION PROJECT | NEEL, JOEL | CLOSED | 2011-06-10 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 0 | 0 | 0 | 0
PJ0003852 | MJ:IN-HOUSE SUPPORT LOCATE UTILITIES FOR INTERCONNECTION PROJECT | NEEL, JOEL | CLOSED | 2011-06-10 | EL: SUPPORT FOR PCV INTERCONNECTION PROJECT | 171 | CLOSED | 0 | 0 | 951.66 | 951.66
PJ0003852 | MJ:IN-HOUSE SUPPORT LOCATE UTILITIES FOR INTERCONNECTION PROJECT | NEEL, JOEL | CLOSED | 2011-06-10 | LA: SUPPORT FOR PCV INTERCONNECTION PROJECT | 171 | CLOSED | 0 | 0 | 1001.8433 | 1001.8433
PJ0003852 | MJ:IN-HOUSE SUPPORT LOCATE UTILITIES FOR INTERCONNECTION PROJECT | NEEL, JOEL | CLOSED | 2011-06-10 | PCV EL: SUPPORT FOR PCV INTERCONNECTION PROJECT | 171 | CLOSED | 0 | 0 | 35971.8145 | 35971.8145
PJ0003852 | MJ:IN-HOUSE SUPPORT LOCATE UTILITIES FOR INTERCONNECTION PROJECT | NEEL, JOEL | CLOSED | 2011-06-10 | PL: SUPPORT FOR PCV INTERCONNECTION PROJECT | 171 | CLOSED | 0 | 0 | 1164.102 | 1164.102
PJ0003852 Total | [7 empty] | 0 | 0 | 39089.4198 | 39089.4198
PJ0003851 | SERVICES FOR CATA FARM SHOW 6/21/11 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2011-06-08 | CA: SETUP CFOR CATA FARM SHOW ON MONDAY JUNE 20 | 009 | CLOSED | 0 | 0 | 898.08 | 898.08
PJ0003851 | SERVICES FOR CATA FARM SHOW 6/21/11 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2011-06-08 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0003851 | SERVICES FOR CATA FARM SHOW 6/21/11 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2011-06-08 | EL: INSTALL TEMP POER FOR CATA FARM SHOW -JUNE 20 | 009 | CLOSED | 0 | 0 | 390.444 | 390.444
PJ0003851 Total | [7 empty] | 0 | 0 | 1288.524 | 1288.524
PJ0003850 | INSTALLATION OF DONOR PAVERS - MUSTANG MEMORIAL | MAY, TOM | CLOSED | 2011-06-03 | CA:INSTALL 4 PAVERS IN THE STADIUM PLAZA | 061 | CLOSED | 678.8209 | 0 | 700.17 | 700.17
PJ0003850 | INSTALLATION OF DONOR PAVERS - MUSTANG MEMORIAL | MAY, TOM | CLOSED | 2011-06-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 62.67 | 0 | 0 | 0
PJ0003850 Total | [7 empty] | 741.4909 | 0 | 700.17 | 700.17
PJ0003847 | CHALKBOARD REMOVAL - BLD 20 RM 132 | MAY, TOM | CLOSED | 2011-05-31 | CA:PURCHASE AND INSTALL 2 CUSTOM WHITEBOARDS 20-132 | 020 | CLOSED | 2260.6718 | 0 | 2850.39 | 2850.39
PJ0003847 | CHALKBOARD REMOVAL - BLD 20 RM 132 | MAY, TOM | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 226.05 | 0 | 0 | 0
PJ0003847 Total | [7 empty] | 2486.7218 | 0 | 2850.39 | 2850.39
PJ0003844 | SR 11/12: CAMPUS WIDE ROAD RESTRIPING & FP 11/12:LOGO CROSSWALKS | GALVEZ, CESAR | CLOSED | 2011-05-31 | AD: (FP) JOC 11.022.036.01 STAPLES | STREETS | CLOSED | 27936.85 | 0 | 11588.54 | 11588.54
PJ0003844 | SR 11/12: CAMPUS WIDE ROAD RESTRIPING & FP 11/12:LOGO CROSSWALKS | GALVEZ, CESAR | CLOSED | 2011-05-31 | AD: (SR) JOC 11.022.036.00 & .02 STAPLES | STREETS | CLOSED | 49893.24 | 0 | 44376.12 | 44376.12
PJ0003844 | SR 11/12: CAMPUS WIDE ROAD RESTRIPING & FP 11/12:LOGO CROSSWALKS | GALVEZ, CESAR | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | STREETS | CLOSED | 0 | 0 | 0 | 0
PJ0003844 | SR 11/12: CAMPUS WIDE ROAD RESTRIPING & FP 11/12:LOGO CROSSWALKS | GALVEZ, CESAR | CLOSED | 2011-05-31 | IN: SR 11/12: ROAD RESTRIPING - CAMPUS WIDE | STREETS | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0003844 Total | [7 empty] | 77936.85 | 0 | 56071.42 | 56071.42
PJ0003843 | SR 11/12: REPLACE ROOF TILE UNDERLAYMENT - DEXTER BLDG 34 | GRIFFIN, PATRICK E. | CLOSED | 2011-05-31 | AD: JOC 11.022.004 STAPLES | 034 | CLOSED | 145020 | 0 | 145020 | 145020
PJ0003843 | SR 11/12: REPLACE ROOF TILE UNDERLAYMENT - DEXTER BLDG 34 | GRIFFIN, PATRICK E. | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0003843 | SR 11/12: REPLACE ROOF TILE UNDERLAYMENT - DEXTER BLDG 34 | GRIFFIN, PATRICK E. | CLOSED | 2011-05-31 | PA:PREP AND PAINT CHIMNEY AT DEXTER | 034 | CLOSED | 1633.04 | 0 | 693.93 | 693.93
PJ0003843 Total | [7 empty] | 146653.04 | 0 | 145713.93 | 145713.93
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | AD: EARTH SYSTEMS | U-UDOR | CLOSED | 675 | 0 | 339.5 | 339.5
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | AD: FERGUSON ENTERPRISES (PARTS TO BE USED BY JOC) | U-UDOR | CLOSED | 3000 | 0 | 2693.75 | 2693.75
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | AD: JOC 11.022.023 STAPLES | U-UDOR | CLOSED | 84391.73 | 0 | 84391.73 | 84391.73
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | CPE: REPAIR UTILIDOR VALVES AND LINES | U-UDOR | CLOSED | 6027.3517 | 0 | 4272.995 | 4272.995
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | ES: PURCHASE VAULTS AND LID (MATERIALS, ONLY) | U-UDOR | CLOSED | 0 | 0 | 3210.91 | 3210.91
PJ0003842 | SR 11/12: REPLACE UTILIDOR VALVES | MAY, TOM | CLOSED | 2011-05-31 | IN: SR 11/12: REPLACE UTILIDOR VALVES | U-UDOR | CLOSED | 213.52 | 0 | 213.52 | 213.52
PJ0003842 Total | [7 empty] | 94307.6017 | 0 | 95122.405 | 95122.405
PJ0003841 | SR 11/12: REPLACE SEPTIC TANK - SWINE UNIT BLDG 056 | BRENNAN, MICHAEL | CLOSED | 2011-05-31 | AD: AL'S SEPTIC | 056 | CLOSED | 12500 | 0 | 12500 | 12500
PJ0003841 | SR 11/12: REPLACE SEPTIC TANK - SWINE UNIT BLDG 056 | BRENNAN, MICHAEL | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | 056 | CLOSED | 0 | 0 | 0 | 0
PJ0003841 | SR 11/12: REPLACE SEPTIC TANK - SWINE UNIT BLDG 056 | BRENNAN, MICHAEL | CLOSED | 2011-05-31 | EL: PROVIDE ELECTRICAL FOR CONTROL PANEL FOR NEW SEPTIC TANK | 056 | CLOSED | 3500.5718 | 0 | 1721.83 | 1721.83
PJ0003841 | SR 11/12: REPLACE SEPTIC TANK - SWINE UNIT BLDG 056 | BRENNAN, MICHAEL | CLOSED | 2011-05-31 | PL: INSTALL NEW SEPTIC TANK AND LEACH FIELD SWINE UNIT | 056 | CLOSED | 1937.5401 | 0 | 1354.665 | 1354.665
PJ0003841 Total | [7 empty] | 17938.1119 | 0 | 15576.495 | 15576.495
PJ0003839 | SR 11/12: REPAIR/REPLACE CAMPUS EMERGENCY LIGHTS | JOHNSON, BEN | CLOSED | 2011-05-31 | AD: ELESCO | GENERAL | CLOSED | 6500 | 0 | 1575 | 1575
PJ0003839 | SR 11/12: REPAIR/REPLACE CAMPUS EMERGENCY LIGHTS | JOHNSON, BEN | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003839 | SR 11/12: REPAIR/REPLACE CAMPUS EMERGENCY LIGHTS | JOHNSON, BEN | CLOSED | 2011-05-31 | EL: GENERAL CAMPUS EMERGENCY LIGHTING - MATERIALS, ONLY | GENERAL | CLOSED | 26949.44 | 0 | 17583.49 | 17583.49
PJ0003839 Total | [7 empty] | 33449.44 | 0 | 19158.49 | 19158.49
PJ0003838 | SR 11/12: REPAIR HOT H2O PUMP & ECONOMIZER PUMPS - BLD 40 | ELLIOT, DENNIS K | CLOSED | 2011-05-31 | AD: R.F. MACDONALD CO. | 040 | CLOSED | 0 | 0 | 4049.93 | 4049.93
PJ0003838 | SR 11/12: REPAIR HOT H2O PUMP & ECONOMIZER PUMPS - BLD 40 | ELLIOT, DENNIS K | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0003838 | SR 11/12: REPAIR HOT H2O PUMP & ECONOMIZER PUMPS - BLD 40 | ELLIOT, DENNIS K | CLOSED | 2011-05-31 | CPE: REPAIR BLDG 40 PUMPS AND ASSOCIATED VALVE | 040 | CLOSED | 5537.2817 | 0 | 1696.37 | 1696.37
PJ0003838 | SR 11/12: REPAIR HOT H2O PUMP & ECONOMIZER PUMPS - BLD 40 | ELLIOT, DENNIS K | CLOSED | 2011-05-31 | PL: SUPPORT VALVE REPLACEMENT (N/L) | 040 | CLOSED | 2434.249 | 0 | 2215.16 | 2215.16
PJ0003838 Total | [7 empty] | 7971.5307 | 0 | 7961.46 | 7961.46
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | AD: JOC 11.023.033 STAPLES | 014 | CLOSED | 342570.1 | 0 | 342570.1 | 342570.1
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | AD: MCKENNA ENVIRONMENTAL | 014 | CLOSED | 1140 | 0 | 865 | 865
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | EL: REMOVE ELECTRICAL THAT IS NOT IN USE | 014 | CLOSED | 250.001 | 0 | 674.16 | 674.16
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | ES: TURN OFF MAKE UP AIR UNTILL ROOFING IS OVER. | 014 | CLOSED | 0 | 0 | 468.27 | 468.27
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | IN: SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | 014 | CLOSED | 213.52 | 0 | 160.14 | 160.14
PJ0003837 | SR 11/12: REPLACE ROOF - PILLING COMPUTER SCI. | LAMPMAN, GREG | CLOSED | 2011-05-31 | PL: INSTALL NEW ROOF DRAIN | 014 | CLOSED | 2253.6311 | 0 | 1082.045 | 1082.045
PJ0003837 Total | [7 empty] | 346427.2521 | 0 | 345819.715 | 345819.715
PJ0003834 | SR 11/12: LANDSLIDE SLOPE & RESTORE COURT BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-05-31 | AD: JOC 11.022.038 STAPLES | GENERAL | CLOSED | 157644.45 | 0 | 157644.45 | 157644.45
PJ0003834 | SR 11/12: LANDSLIDE SLOPE & RESTORE COURT BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-05-31 | AD: JOC 11.022.038.02 | GENERAL | CLOSED | 0 | 0 | 3855.43 | 3855.43
PJ0003834 | SR 11/12: LANDSLIDE SLOPE & RESTORE COURT BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003834 | SR 11/12: LANDSLIDE SLOPE & RESTORE COURT BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-05-31 | EL: HOOK UP LIGHT POLE | GENERAL | CLOSED | 1300.5658 | 0 | 273.5656 | 273.5656
PJ0003834 | SR 11/12: LANDSLIDE SLOPE & RESTORE COURT BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-05-31 | IN: SR 11/12: LANDSLIDE SLOPE & RESTORE COURT | GENERAL | CLOSED | 1601.4 | 0 | 880.77 | 880.77
PJ0003834 | SR 11/12: LANDSLIDE SLOPE & RESTORE COURT BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-05-31 | LA: RE-PLANT SLOPE NEXT TO SERVICE ROAD (N/L) | GENERAL | CLOSED | 4445.2397 | 0 | 166.67 | 166.67
PJ0003834 Total | [7 empty] | 164991.6555 | 0 | 162820.8856 | 162820.8856
PJ0003833 | FLOOD REMEDIATION AT CORPORATION ADMIN BLDG 15 (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2011-05-31 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 0 | 0 | 0 | 0
PJ0003833 | FLOOD REMEDIATION AT CORPORATION ADMIN BLDG 15 (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2011-05-31 | EL: FLOOD REMEDIATION SUPPORT - BLDG. 15 ROOF LEAKS | 015 | CLOSED | 0 | 0 | 528.528 | 528.528
PJ0003833 Total | [7 empty] | 0 | 0 | 528.528 | 528.528
PJ0003832 | PAC CONCESSIONS RENOVATIONS - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-05-25 | AD: FLOOR CONNECTION | 006 | CLOSED | 3218.7312 | 0 | 3218.7312 | 3218.7312
PJ0003832 | PAC CONCESSIONS RENOVATIONS - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-05-25 | AD: JOC 11.022.015 STAPLES | 006 | CLOSED | 2955.6717 | 0 | 2981.8225 | 2981.8225
PJ0003832 | PAC CONCESSIONS RENOVATIONS - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-05-25 | AD: JOC 11.023.019 STAPLES | 006 | CLOSED | 1017.1527 | 0 | 996.3947 | 996.3947
PJ0003832 | PAC CONCESSIONS RENOVATIONS - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-05-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 269.74 | 0 | 0 | 0
PJ0003832 | PAC CONCESSIONS RENOVATIONS - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-05-25 | IN: PAC CONCESSIONS RENOVATIONS - PAC 06 | 006 | CLOSED | 256.224 | 0 | 96.084 | 96.084
PJ0003832 | PAC CONCESSIONS RENOVATIONS - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-05-25 | PA: PAINTING FOR PAC CONCESSIONS RENOVATION PROJECT | 006 | CLOSED | 970.9405 | 0 | 118.728 | 118.728
PJ0003832 Total | [7 empty] | 8688.4601 | 0 | 7411.7604 | 7411.7604
PJ0003831 | INSTALL FIVE (5) 46" DISPLAYS INSIDE 3RD FLOOR RMS - BUSINESS 03 | MOLLAN, CHERYL L. | CLOSED | 2011-05-17 | AD: MORELAND THOMPSON, INC. | 003 | CLOSED | 1556.85 | 0 | 1556.85 | 1556.85
PJ0003831 | INSTALL FIVE (5) 46" DISPLAYS INSIDE 3RD FLOOR RMS - BUSINESS 03 | MOLLAN, CHERYL L. | CLOSED | 2011-05-17 | CA:INSTALL ELECTRONIC BILLBOARD MOUNTS AT BUSINESS BUILDING | 003 | CLOSED | 776.7798 | 0 | 506.088 | 506.088
PJ0003831 | INSTALL FIVE (5) 46" DISPLAYS INSIDE 3RD FLOOR RMS - BUSINESS 03 | MOLLAN, CHERYL L. | CLOSED | 2011-05-17 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 239.79 | 0 | 0 | 0
PJ0003831 | INSTALL FIVE (5) 46" DISPLAYS INSIDE 3RD FLOOR RMS - BUSINESS 03 | MOLLAN, CHERYL L. | CLOSED | 2011-05-17 | IN: INSTALLATION OF ELECTRONIC BILLBOARD - BLD 3 BREEZE WAY | 003 | CLOSED | 64.056 | 0 | 32.028 | 32.028
PJ0003831 Total | [7 empty] | 2637.4758 | 0 | 2094.966 | 2094.966
PJ0003829 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 114 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-24 | CA:SMART ROOM - SEE PRINT OUT- BLDG 38- ROOM 114 | 038 | CLOSED | 0 | 0 | 84.582 | 84.582
PJ0003829 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 114 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-24 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003829 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 114 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-24 | EL:SMART ROOM - SEE PLANS- BLDG 38- ROOM 114 | 038 | CLOSED | 0 | 0 | 1071.39 | 1071.39
PJ0003829 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 114 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-24 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 114 | 038 | CLOSED | 0 | 0 | 97.194 | 97.194
PJ0003829 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 114 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-24 | PA:SMART ROOM- BUILDING 38- ROOM 114 (N/L) | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003829 Total | [7 empty] | 0 | 0 | 1253.166 | 1253.166
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | ANTS: ASSIST CAME SECURITY AT UINVERSITY HOUSE | 051 | CLOSED | 0 | 0 | 23.82 | 23.82
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | CA: ASSIST ELECTRICIANS WITH SWITCH GEAR AT UH | 051 | CLOSED | 0 | 0 | 3154.2402 | 3154.2402
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 35000 | 0 | 0 | 0
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | EL: REPLACE SWITCH GEAR AT UNIVERSITY HOUSE | 051 | CLOSED | 0 | 0 | 28614.6551 | 28614.6551
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | LO: ASSIST ELECTRICIANS WITH SWITCH GEAR AT UH | 051 | CLOSED | 0 | 0 | 47.64 | 47.64
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | PA: PAINT NEW SWITCH GEAR AT UH | 051 | CLOSED | 0 | 0 | 190.64 | 190.64
PJ0003828 | SR 10/11: REPLACE SWITCH GEAR - BLD 51 | MAY, TOM | CLOSED | 2011-05-24 | PL: RELOCATE GAS LINE NEXT TO SWITCH GEAR - UH 051 | 051 | CLOSED | 0 | 0 | 264.9 | 264.9
PJ0003828 Total | [7 empty] | 35000 | 0 | 32295.8953 | 32295.8953
PJ0003827 | REPLACE GLASS, ENTRY DOORS, W/TEMPERED - ALL ASI BLDGS | GRIFFIN, PATRICK E. | CLOSED | 2011-05-23 | AD: JOC 10.021.009 | GENERAL | CLOSED | 10168.103 | 0 | 10048.9585 | 10048.9585
PJ0003827 | REPLACE GLASS, ENTRY DOORS, W/TEMPERED - ALL ASI BLDGS | GRIFFIN, PATRICK E. | CLOSED | 2011-05-23 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1016.81 | 0 | 0 | 0
PJ0003827 Total | [7 empty] | 11184.913 | 0 | 10048.9585 | 10048.9585
PJ0003824 | M&R ASI 11/12: BIKE PARKING CONCRETE PADS - SPORTS COMPLEX | GALVEZ, CESAR | CLOSED | 2011-05-17 | CA: FORM AND POUR 22'X7'X4" CONCRETE PAD FOR BIKE RACKS | 163 | CLOSED | 7015.9534 | 0 | 5677.95 | 5677.95
PJ0003824 | M&R ASI 11/12: BIKE PARKING CONCRETE PADS - SPORTS COMPLEX | GALVEZ, CESAR | CLOSED | 2011-05-17 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 933.85 | 0 | 0 | 0
PJ0003824 | M&R ASI 11/12: BIKE PARKING CONCRETE PADS - SPORTS COMPLEX | GALVEZ, CESAR | CLOSED | 2011-05-17 | EO: PREP AREA FOR A 22'X7'X4" CONCRETE PAD FOR BIKE RACKS | 163 | CLOSED | 1246.2968 | 0 | 1014.972 | 1014.972
PJ0003824 | M&R ASI 11/12: BIKE PARKING CONCRETE PADS - SPORTS COMPLEX | GALVEZ, CESAR | CLOSED | 2011-05-17 | IN: M&R UU 11/12: BIKE PARKING CONCRETE PADS - SPORTS COMPLEX | 163 | CLOSED | 142.8449 | 0 | 96.084 | 96.084
PJ0003824 | M&R ASI 11/12: BIKE PARKING CONCRETE PADS - SPORTS COMPLEX | GALVEZ, CESAR | CLOSED | 2011-05-17 | LA: CAP OFF AND MODIFY IRRIGATION FOR A 22'X7'X4" CONCRETE PAD | 163 | CLOSED | 933.9488 | 0 | 175.338 | 175.338
PJ0003824 Total | [7 empty] | 10272.8939 | 0 | 6964.344 | 6964.344
PJ0003822 | M&R ASI 11/12: CHUMASH FLOOR REFINISHING PM | MAY, TOM | CLOSED | 2011-05-17 | AD: MCWIL SPORT SURFACES, INC. | 065 | CLOSED | 6206 | 0 | 6205.9572 | 6205.9572
PJ0003822 | M&R ASI 11/12: CHUMASH FLOOR REFINISHING PM | MAY, TOM | CLOSED | 2011-05-17 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 627.01 | 0 | 0 | 0
PJ0003822 | M&R ASI 11/12: CHUMASH FLOOR REFINISHING PM | MAY, TOM | CLOSED | 2011-05-17 | IN: M&R UU 11/12: CHUMASH FLOOR REFINISHING PM | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003822 Total | [7 empty] | 6897.066 | 0 | 6270.0132 | 6270.0132
PJ0003821 | M&R ASI 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | MAY, TOM | CLOSED | 2011-05-16 | AD: FACT AUTOMATED ENTRANCES | 065 | CLOSED | 1190.91 | 0 | 1190.91 | 1190.91
PJ0003821 | M&R ASI 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | MAY, TOM | CLOSED | 2011-05-16 | AD: JOC 10.022.021 STAPLES | 065 | CLOSED | 142462.6034 | 0 | 142462.9351 | 142462.9351
PJ0003821 | M&R ASI 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | MAY, TOM | CLOSED | 2011-05-16 | AD: TEMPLE BUILDERS | 065 | CLOSED | 876.0625 | 0 | 876.0625 | 876.0625
PJ0003821 | M&R ASI 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | MAY, TOM | CLOSED | 2011-05-16 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 13392.29 | 0 | 0 | 0
PJ0003821 | M&R ASI 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | MAY, TOM | CLOSED | 2011-05-16 | EL: ELECTRICAL FOR NEW PIN SPOTTERS - UU BOWLING ALLEY | 065 | CLOSED | 12002.0465 | 0 | 17559.0322 | 17559.0322
PJ0003821 | M&R ASI 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | MAY, TOM | CLOSED | 2011-05-16 | IN: M&R UU 11/12: BOWLING CTR EQUIPMENT INSTALL - BLDG 65 RM 118 | 065 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003821 Total | [7 empty] | 170052.0244 | 0 | 162217.0518 | 162217.0518
PJ0003819 | RE-FINISH DOORS - SANTA LUCIA & TENAYA HALL - BLDGS 106 & 110 | MAY, TOM | CLOSED | 2011-05-16 | AD: JOC 10.021.024 STAPLES | RESIDENCE | CLOSED | 82364.2237 | 0 | 82364.2237 | 82364.2237
PJ0003819 | RE-FINISH DOORS - SANTA LUCIA & TENAYA HALL - BLDGS 106 & 110 | MAY, TOM | CLOSED | 2011-05-16 | CP: PROJECT CONTINGENCY | 106 | CLOSED | 0 | 0 | 0 | 0
PJ0003819 | RE-FINISH DOORS - SANTA LUCIA & TENAYA HALL - BLDGS 106 & 110 | MAY, TOM | CLOSED | 2011-05-16 | IN: REFINISH DOORS - SANTA LUCIA & TENAYA HALL - BLDGS 106 & 110 | RESIDENCE | CLOSED | 66.276 | 0 | 65.166 | 65.166
PJ0003819 Total | [7 empty] | 82430.4997 | 0 | 82429.3897 | 82429.3897
PJ0003817 | INSTALL CARPET - SANTA LUCIA & TENAYA HALL - BLGS 106 & 110 | MAY, TOM | CLOSED | 2011-05-16 | AD: INNOVATION COMMERCIAL FLOORING | RESIDENCE | CLOSED | 52880.1704 | 0 | 52528.3758 | 52528.3758
PJ0003817 | INSTALL CARPET - SANTA LUCIA & TENAYA HALL - BLGS 106 & 110 | MAY, TOM | CLOSED | 2011-05-16 | CP: PROJECT CONTINGENCY | 106 | CLOSED | 0 | 0 | 0 | 0
PJ0003817 | INSTALL CARPET - SANTA LUCIA & TENAYA HALL - BLGS 106 & 110 | MAY, TOM | CLOSED | 2011-05-16 | IN: INSTALL CARPET - SANTA LUCIA & TENAYA HALL - BLGS 106 & 110 | RESIDENCE | CLOSED | 66.276 | 0 | 65.166 | 65.166
PJ0003817 Total | [7 empty] | 52946.4464 | 0 | 52593.5418 | 52593.5418
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | AD: INNOVATION COMMERCIAL FLOORING | 110 | CLOSED | 2474.375 | 0 | 2474.375 | 2474.375
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | AD: JOC 10.021.027 STAPLES | 110 | CLOSED | 372992.0918 | 0 | 372992.0918 | 372992.0918
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | AD: MCKENNA ENVIRONMENTAL | 110 | CLOSED | 25319.9557 | 0 | 20993.6354 | 20993.6354
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | CA:INSTALL DOORSTOPS, PEEP HOLES AND NUMBERS IN TENAYA | 110 | CLOSED | 2311.8738 | 0 | 5002.404 | 5002.404
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | CP: PROJECT CONTINGENCY | 110 | CLOSED | 0 | 0 | 0 | 0
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | EL:FIRE ALARM BATTERIES-TENAYA | 110 | CLOSED | 63.444 | 0 | 99.138 | 99.138
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | ES: SHUT DOWON AIR HANDLERS AT TENAYA | 110 | CLOSED | 64.032 | 0 | 96.048 | 96.048
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | IN: INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | 110 | CLOSED | 66.276 | 0 | 65.166 | 65.166
PJ0003816 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - TENAYA 110 | MAY, TOM | CLOSED | 2011-05-16 | LO:INSTALL ORANGE CORES & CLOSURES IN TENAYA DORM | 110 | CLOSED | 1311.3158 | 0 | 2114.706 | 2114.706
PJ0003816 Total | [7 empty] | 404603.3641 | 0 | 403837.5642 | 403837.5642
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | AD: JOC 10.021.026 STAPLES | 106 | CLOSED | 488521.4042 | 0 | 488521.4042 | 488521.4042
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | CA:INSTALL DOORSTOPS, PEEP HOLES AND NUMBERS IN SANTA LUCIA | 106 | CLOSED | 4076.349 | 0 | 4201.062 | 4201.062
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | CP: PROJECT CONTINGENCY | 106 | CLOSED | 0 | 0 | 0 | 0
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | EL:FIRE ALARM BATTERIES-SANTA LUCIA | 106 | CLOSED | 63.444 | 0 | 194.028 | 194.028
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | ES: SHUT DOWN AIR HANDLERS AT SANTA LUCIA | 106 | CLOSED | 64.032 | 0 | 96.048 | 96.048
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | IN: CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | 106 | CLOSED | 132.552 | 0 | 65.166 | 65.166
PJ0003815 | INSTALL CABINETS, TELECOMM, ELECTRICAL & PAINT - SANTA LUCIA 106 | MAY, TOM | CLOSED | 2011-05-16 | LO:ORANGE CORES & CLOSURES IN SANTA LUCIA DORM | 106 | CLOSED | 1311.3158 | 0 | 1358.82 | 1358.82
PJ0003815 Total | [7 empty] | 494169.097 | 0 | 494436.5282 | 494436.5282
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | CA:PAC APR 2011 INSPECTION WORK | 006 | CLOSED | 0 | 0 | 277.74 | 277.74
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | CU:PAC MAINTENANCE INSPECTION APR 2011 (NO LABOR) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | ES:PAC MAINTENANCE INSPECTION APR 2011 (NO LABOR) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | LO:PAC MAINTENANCE INSPECTION - APR 2011 | 006 | CLOSED | 0 | 0 | 95.28 | 95.28
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | PA:PAC MAINTENANCE INSPECTION APR 2011 | 006 | CLOSED | 0 | 0 | 2066.995 | 2066.995
PJ0003812 | QUARTERLY INSPECTION 4-12-11 - PAC MAINTENANCE WALK-THRU | GRIFFIN, PATRICK E. | CLOSED | 2011-05-12 | PL:PAC MAINTENANCE INSPECTION APR 2011 | 006 | CLOSED | 0 | 0 | 158.94 | 158.94
PJ0003812 Total | [7 empty] | 0 | 0 | 2598.955 | 2598.955
PJ0003811 | REPLACE ENTRYWAY GLASS WITH TEMPERED GLASS -VG & DINING 112 & 19 | GRIFFIN, PATRICK E. | CLOSED | 2011-05-11 | AD: JOC 10.021.010 STAPLES | 112 | CLOSED | 4062.1159 | 0 | 4032.3271 | 4032.3271
PJ0003811 | REPLACE ENTRYWAY GLASS WITH TEMPERED GLASS -VG & DINING 112 & 19 | GRIFFIN, PATRICK E. | CLOSED | 2011-05-11 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 406.21 | 0 | 0 | 0
PJ0003811 Total | [7 empty] | 4468.3259 | 0 | 4032.3271 | 4032.3271
PJ0003810 | REVIEW PLANS FOR STRUCTURE IN POLY CANYON (TANZANIA) | HOGAN, MIKE | CLOSED | 2011-05-11 | AD: SEISMIC PEER REVIEW - ENGLEKIRK AND SABOL | 095 | CLOSED | 535 | 0 | 535 | 535
PJ0003810 | REVIEW PLANS FOR STRUCTURE IN POLY CANYON (TANZANIA) | HOGAN, MIKE | CLOSED | 2011-05-11 | CP: PROJECT CONTINGENCY | 095 | CLOSED | 0 | 0 | 0 | 0
PJ0003810 Total | [7 empty] | 535 | 0 | 535 | 535
PJ0003809 | INSTALL SMART ROOM EQUIPMENT - BLD 34 RM 145 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-10 | CA:SMART ROOM- BLDG. 34- ROOM 145 | 034 | CLOSED | 0 | 0 | 609.642 | 609.642
PJ0003809 | INSTALL SMART ROOM EQUIPMENT - BLD 34 RM 145 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-10 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0003809 | INSTALL SMART ROOM EQUIPMENT - BLD 34 RM 145 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-10 | EL:SMART ROOM- BLDG 34- ROOM 145 | 034 | CLOSED | 0 | 0 | 2003.214 | 2003.214
PJ0003809 | INSTALL SMART ROOM EQUIPMENT - BLD 34 RM 145 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-10 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 34 RM 145 | 034 | CLOSED | 0 | 0 | 97.194 | 97.194
PJ0003809 | INSTALL SMART ROOM EQUIPMENT - BLD 34 RM 145 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-05-10 | PA:SMART ROOM- BUILDING 34, ROOM 145 | 034 | CLOSED | 0 | 0 | 336.546 | 336.546
PJ0003809 Total | [7 empty] | 0 | 0 | 3046.596 | 3046.596
PJ0003808 | SR 11/12: RE-ROOF OVER HALLWAY 26 - BLD 47 F.O.N. | GRIFFIN, PATRICK E. | CLOSED | 2011-05-10 | AD: JOC 11.022.022 STAPLES | 047 | CLOSED | 65011.31 | 0 | 65011.31 | 65011.31
PJ0003808 | SR 11/12: RE-ROOF OVER HALLWAY 26 - BLD 47 F.O.N. | GRIFFIN, PATRICK E. | CLOSED | 2011-05-10 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0003808 Total | [7 empty] | 65011.31 | 0 | 65011.31 | 65011.31
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | AD: EARTH SYSTEMS PACIFIC | STREETS | CLOSED | 2000 | 0 | 653 | 653
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | AD: JOC 10.022.001 STAPLES | STREETS | CLOSED | 270762.06 | 0 | 188881.91 | 188881.91
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | AD: WALLACE GROUP | STREETS | CLOSED | 14780 | 0 | 10201.25 | 10201.25
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | EL: SUPPORT ROAD REBUILD PROJECT-CALIF BTWN STADIUM & POLY GROVE | STREETS | CLOSED | 449.44 | 0 | 365.17 | 365.17
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | IN: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | STREETS | CLOSED | 1067.6 | 0 | 160.14 | 160.14
PJ0003806 | SR 11/12: REBUILD ROAD, CALIFORNIA BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2011-05-10 | JOC 10.022.005 STAPLES (PARTIAL - SEE PJ 3860 FOR REMAINDER) | STREETS | CLOSED | 32820.72 | 0 | 110333.34 | 110333.34
PJ0003806 Total | [7 empty] | 321879.82 | 0 | 310594.81 | 310594.81
PJ0003805 | INSTALL WALL FOR ELECTRICAL CONDUIT - SPORTS COMPLEX (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-05-05 | CA:CONSTRUCT WALL AT SPORTS COMPLEX GROUNDS SHOP | 160F | CLOSED | 2777.66 | 0 | 2477.745 | 2477.745
PJ0003805 | INSTALL WALL FOR ELECTRICAL CONDUIT - SPORTS COMPLEX (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-05-05 | CP: PROJECT CONTINGENCY | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0003805 | INSTALL WALL FOR ELECTRICAL CONDUIT - SPORTS COMPLEX (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-05-05 | EL:INSTALL OUTLETS IN NEW WALL AT GROUNDS SHOP AT SPORTS COMPLEX | 160F | CLOSED | 1598.32 | 0 | 832.68 | 832.68
PJ0003805 | INSTALL WALL FOR ELECTRICAL CONDUIT - SPORTS COMPLEX (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-05-05 | IN: INSTALL WALL FOR ELECTRICAL CONDUIT - SPORTS COMPLEX | 160F | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0003805 Total | [7 empty] | 4482.74 | 0 | 3417.185 | 3417.185
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MID COAST FIRE - ASI PORTION | GENERAL | CLOSED | 581.8948 | 0 | 581.8874 | 581.8874
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MID COAST FIRE - CORP PORTION | GENERAL | CLOSED | 2445.1972 | 0 | 1163.7855 | 1163.7855
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MID COAST FIRE - HOUSING CERRO VISTA PORTION | GENERAL | CLOSED | 1600.1998 | 0 | 1600.1957 | 1600.1957
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MID COAST FIRE - HOUSING YOSEMITE PORTION | GENERAL | CLOSED | 579.2338 | 0 | 579.2338 | 579.2338
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MID COAST FIRE - STATE PORTION (SR) | GENERAL | CLOSED | 10550.41 | 0 | 10468.59 | 10468.59
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MIDCOAST - CORP. BUILDING 19 PORTION | GENERAL | CLOSED | 1280.7686 | 0 | 1280.7686 | 1280.7686
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | AD: MIDCOAST - STATE BUILDING 70 PORTION (SR) | GENERAL | CLOSED | 2591.42 | 0 | 2591.42 | 2591.42
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003802 | SR 10/11: CORRECT VARIOUS FIRE PROTECTION DEFICIENCIES - CAMPUS | ELLIOT, DENNIS K | CLOSED | 2011-05-04 | PL: (STATE) SUPPORT PLUMBING SHUTDOWN | GENERAL | CLOSED | 2635.85 | 0 | 2751.96 | 2751.96
PJ0003802 Total | [7 empty] | 22264.9742 | 0 | 21017.841 | 21017.841
PJ0003801 | SR 10/11: ADA COMPLIANCE - CHILD DEVELOPMENT RAMP - 038 | MOLLAN, CHERYL L. | CLOSED | 2011-05-04 | AD: JOC 10.020.059 STAPLES | 038 | CLOSED | 69364.96 | 0 | 69364.96 | 69364.96
PJ0003801 | SR 10/11: ADA COMPLIANCE - CHILD DEVELOPMENT RAMP - 038 | MOLLAN, CHERYL L. | CLOSED | 2011-05-04 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003801 | SR 10/11: ADA COMPLIANCE - CHILD DEVELOPMENT RAMP - 038 | MOLLAN, CHERYL L. | CLOSED | 2011-05-04 | IN: SR 10/11: ADA COMPLIANCE - CHILD DEVELOPMENT RAMP - 038 | 038 | CLOSED | 220.92 | 0 | 213.52 | 213.52
PJ0003801 | SR 10/11: ADA COMPLIANCE - CHILD DEVELOPMENT RAMP - 038 | MOLLAN, CHERYL L. | CLOSED | 2011-05-04 | LA:BLDG 38 -RELOCATE IRRIGATION-RELANDSCAPE AFTER RAMP CONSTRUCT | 038 | CLOSED | 8778.0064 | 0 | 6678.7725 | 6678.7725
PJ0003801 Total | [7 empty] | 78363.8864 | 0 | 76257.2525 | 76257.2525
PJ0003800 | SR 10/11: RE-ROOF FARM SHOP - 009 | LAMPMAN, GREG | CLOSED | 2011-05-04 | AD: JOC 10.021.021 STAPLES | 009 | CLOSED | 73642.65 | 0 | 73642.65 | 73642.65
PJ0003800 | SR 10/11: RE-ROOF FARM SHOP - 009 | LAMPMAN, GREG | CLOSED | 2011-05-04 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0003800 | SR 10/11: RE-ROOF FARM SHOP - 009 | LAMPMAN, GREG | CLOSED | 2011-05-04 | IN: SR 10/11: RE-ROOF FARM SHOP - 009 | 009 | CLOSED | 110.46 | 0 | 80.07 | 80.07
PJ0003800 Total | [7 empty] | 73753.11 | 0 | 73722.72 | 73722.72
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | AD: BUEHLER AND BUEHLER | 371 | CLOSED | 2675 | 0 | 2675 | 2675
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | AD: ENGLEKIRK AND SABOL | 371 | CLOSED | 1070 | 0 | 535 | 535
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | AD: GOLDEN STATE SEALING AND STRIPING | 371 | CLOSED | 626.485 | 0 | 929.3057 | 929.3057
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | AD: GOLDING CONCRETE SAWING | 371 | CLOSED | 952.3 | 0 | 952.3 | 952.3
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | AD: JOHN WRIGHT CONSTRUCTION | 371 | CLOSED | 1055.8867 | 0 | 1055.8867 | 1055.8867
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | CP: PROJECT CONTINGENCY | 371 | CLOSED | 377.66 | 0 | 0 | 0
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | EL:SHOP DOOR | 371 | CLOSED | 659.328 | 0 | 168.54 | 168.54
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | IN: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | 371 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | LO:SHOP DOOR | 371 | CLOSED | 654.132 | 0 | 572.088 | 572.088
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | PA:SHOP DOOR | 371 | CLOSED | 297.456 | 0 | 430.389 | 430.389
PJ0003799 | MJ: INSTALL SHOP DOOR LEADING INTO PARKING AREA - BLD 371 RM 108 | BRENNAN, MICHAEL | CLOSED | 2011-05-02 | PCV CA:SHOP DOOR | 371 | CLOSED | 4597.728 | 0 | 5993.746 | 5993.746
PJ0003799 Total | [7 empty] | 13094.0877 | 0 | 13440.3674 | 13440.3674
PJ0003798 | REMODEL CUSTOMER SERVICE AREA - EL CORRAL BOOKSTORE | MAY, TOM | CLOSED | 2011-05-02 | AD: TEMPLE BUILDERS | 065 | CLOSED | 855.1975 | 0 | 855.1975 | 855.1975
PJ0003798 | REMODEL CUSTOMER SERVICE AREA - EL CORRAL BOOKSTORE | MAY, TOM | CLOSED | 2011-05-02 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 10.44 | 0 | 0 | 0
PJ0003798 | REMODEL CUSTOMER SERVICE AREA - EL CORRAL BOOKSTORE | MAY, TOM | CLOSED | 2011-05-02 | EL: FINISH OUTLETS ON SLAT WALL IN BOOKSTORE - BLDG. 65 | 065 | CLOSED | 229.6694 | 0 | 221.964 | 221.964
PJ0003798 | REMODEL CUSTOMER SERVICE AREA - EL CORRAL BOOKSTORE | MAY, TOM | CLOSED | 2011-05-02 | IN: REMODEL CUSTOMER SERVICE AREA - EL CORRAL BOOKSTORE | 065 | CLOSED | 32.028 | 0 | 64.056 | 64.056
PJ0003798 | REMODEL CUSTOMER SERVICE AREA - EL CORRAL BOOKSTORE | MAY, TOM | CLOSED | 2011-05-02 | PA: PAINT AROUND WINDOWS AT BOOKSTORE | 065 | CLOSED | 578.799 | 0 | 593.64 | 593.64
PJ0003798 Total | [7 empty] | 1706.1339 | 0 | 1734.8575 | 1734.8575
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | AD: INNOVATION COMMERCIAL FLOORING | 014 | CLOSED | 4815 | 0 | 5578.1775 | 5578.1775
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | AD: MACDONALD COMPANY | 014 | CLOSED | 5193.6623 | 0 | 4976.6663 | 4976.6663
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | AD: QUARESMA DRYWALL | 014 | CLOSED | 4280 | 0 | 4222.22 | 4222.22
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | AD: SAN LUIS GLASS | 014 | CLOSED | 3694.0787 | 0 | 3694.0787 | 3694.0787
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 3210 | 0 | 2383.2752 | 2383.2752
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | CA:REMOVE RAISED FLOOR AND BUILD WALL IN 14-257 | 014 | CLOSED | 15699.2604 | 0 | 13888.2893 | 13888.2893
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 3441.64 | 0 | 0 | 0
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | EH&S: LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | 014 | CLOSED | 617.4 | 0 | 569.1 | 569.1
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | EL:PROVIDE ELECTRICAL AND LIGHTING FOR 14-257 PROJECT | 014 | CLOSED | 8821.6214 | 0 | 6103.2836 | 6103.2836
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | ES:INSTALL NEW REGISTERS IN 14-257 REMODEL | 014 | CLOSED | 780.8102 | 0 | 2140.482 | 2140.482
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | IN: LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | 014 | CLOSED | 265.104 | 0 | 257.334 | 257.334
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | LO:INSTALL NEW LOCKSET FOR 14-257 REMODEL | 014 | CLOSED | 1124.8022 | 0 | 2582.088 | 2582.088
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | MO: REMOVE SURPLUS FURNITURE FROM 14-257 | 014 | CLOSED | 126 | 0 | 68.184 | 68.184
PJ0003796 | LAB RENOVATION (DIVIDE INTO TWO) - BLD 14 RM 257 | MAY, TOM | CLOSED | 2011-05-02 | PA:PAINTING FOR 14-257 REMODEL | 014 | CLOSED | 4175.9534 | 0 | 3533.766 | 3533.766
PJ0003796 Total | [7 empty] | 56245.3328 | 0 | 49996.9446 | 49996.9446
PJ0003795 | M&R H/C 11/12: PAINT EXTERIOR STUCCO AREAS | GRIFFIN, PATRICK E. | CLOSED | 2011-04-29 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 2658.2 | 0 | 0 | 0
PJ0003795 | M&R H/C 11/12: PAINT EXTERIOR STUCCO AREAS | GRIFFIN, PATRICK E. | CLOSED | 2011-04-29 | IN: M&R H/C 11/12: PAINT EXTERIOR STUCCO AREAS | 027 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0003795 | M&R H/C 11/12: PAINT EXTERIOR STUCCO AREAS | GRIFFIN, PATRICK E. | CLOSED | 2011-04-29 | LA:TRIM LANDSCAPE AT HEALTH CENTER | 027 | CLOSED | 311.712 | 0 | 116.892 | 116.892
PJ0003795 | M&R H/C 11/12: PAINT EXTERIOR STUCCO AREAS | GRIFFIN, PATRICK E. | CLOSED | 2011-04-29 | PA:PAINT EXTERIOR AREAS AT HEALTH CENTER | 027 | CLOSED | 25691.04 | 0 | 18241.326 | 18241.326
PJ0003795 Total | [7 empty] | 28789.064 | 0 | 18390.246 | 18390.246
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | AD: COASTAL DEMO | 027 | CLOSED | 1047.53 | 0 | 523.23 | 523.23
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | AD: DIVISION OF STATE ARCHITECT | 027 | CLOSED | 1200 | 0 | 819.64 | 819.64
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | AD: JOC 13.027.021 PUB | 027 | CLOSED | 6487.2816 | 0 | 5869.3887 | 5869.3887
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | AD: MCKENNA ENVIRONMENTAL | 027 | CLOSED | 4492.93 | 0 | 2188.15 | 2188.15
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | AD: PARC ENVIRONMENTAL | 027 | CLOSED | 5271.9542 | 0 | 5348.93 | 5348.93
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | AD: VISALIA TILE | 027 | CLOSED | 2083.29 | 0 | 2083.29 | 2083.29
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | CA:REMOVE AND REINSTALL RESTROOM DISPENSERS DUE TO REMODEL | 027 | CLOSED | 4246.6753 | 0 | 1894.9477 | 1894.9477
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1084.43 | 0 | 0 | 0
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | CU:PROVIDE CUSTODIAL SUPPORT FOR ADA RESTROOM REMODEL | 027 | CLOSED | 131.184 | 0 | 32.796 | 32.796
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | EH&S: LAB CHARGES FOR SAMPLE ANALYIS (MATERIALS, ONLY) | 027 | CLOSED | 0 | 0 | 21.6 | 21.6
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | EH&S: LAB CHARGES PROCESSED THROUGH UTILITIES ACCOUNT(MAT, ONLY) | 027 | CLOSED | 0 | 0 | 71.4 | 71.4
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | EH&S: M&R H/C 11/12: DESIGN ADA COMPLIANT RESTROOM REMODEL (N/L) | 027 | CLOSED | 197.4 | 0 | 0 | 0
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | IN: M&R H/C 11/12: ADA COMPLIANT LOBBY RESTROOM REMODEL | 027 | CLOSED | 265.104 | 0 | 547.806 | 547.806
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | LA: PROVIDE CONSTRUCTION SUPPORT FOR RESTROOM REMODEL AT HC | 027 | CLOSED | 185.8583 | 0 | 177.456 | 177.456
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | PA:PAINT RESTROOM AFTER REMODEL- HC ROOM 129 | 027 | CLOSED | 593.64 | 0 | 695.64 | 695.64
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | PL: (FAC FUNDING)HEALTH CENTER RESTROOM 129- ADA UPGRADE | 027 | CLOSED | 3892.0561 | 0 | 1790.796 | 1790.796
PJ0003792 | M&R H/C 11/12: ADA COMPLIANT RESTROOM REMODEL | MOLLAN, CHERYL L. | CLOSED | 2011-04-29 | PL:REMOVE FIXTURES, REPLUMB AND INSTALL NEW FIXTURES | 027 | CLOSED | 9652.2664 | 0 | 9235.6938 | 9235.6938
PJ0003792 Total | [7 empty] | 40831.5999 | 0 | 31300.7642 | 31300.7642
PJ0003791 | STRUCTURAL EVALUATION - UU 65 EPICENTER BALCONY | LAMPMAN, GREG | CLOSED | 2011-03-08 | AD: BUEHLER AND BUEHLER | 065 | CLOSED | 3745 | 0 | 3745 | 3745
PJ0003791 | STRUCTURAL EVALUATION - UU 65 EPICENTER BALCONY | LAMPMAN, GREG | CLOSED | 2011-03-08 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 387.76 | 0 | 0 | 0
PJ0003791 | STRUCTURAL EVALUATION - UU 65 EPICENTER BALCONY | LAMPMAN, GREG | CLOSED | 2011-03-08 | IN: STRUCTURAL EVALUATION - UU 65 EPICENTER BALCONY | 065 | CLOSED | 128.112 | 0 | 32.028 | 32.028
PJ0003791 Total | [7 empty] | 4260.872 | 0 | 3777.028 | 3777.028
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | AD: FLOOR CONNECTION | RESIDENCE | CLOSED | 1500 | 0 | 200 | 200
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | AD: JOC 11.023.003 STAPLES | RESIDENCE | CLOSED | 6047.85 | 0 | 4926.4 | 4926.4
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | AD: MCKENNA ENVIRONMENTAL | RESIDENCE | CLOSED | 4000 | 0 | 2820.34 | 2820.34
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | AD: SAN LUIS GLASS | RESIDENCE | CLOSED | 4000 | 0 | 3572.39 | 3572.39
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | CA: FRAMING, DRYWALL AND FLOORING FOR VENDING AREA | 109 | CLOSED | 9421.042 | 0 | 7621.805 | 7621.805
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | EL:ROUGH AND FINISH ELEC FOR NEW VENDING AREA | RESIDENCE | CLOSED | 7001.7054 | 0 | 1538.8818 | 1538.8818
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | ES:HVAC WORK FOR NEW VENDING AREA | RESIDENCE | CLOSED | 7133.7918 | 0 | 888.36 | 888.36
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | IN: M&R HOUS 11/12: DESIGN VENDING AREA REMODEL-S. MTN SUMR 2012 | RESIDENCE | CLOSED | 106.76 | 0 | 106.76 | 106.76
PJ0003790 | M&R HOUS 11/12: DESIGN FOR VENDING AREA REMODEL-S. MTN SUMR 2012 | BRENNAN, MICHAEL | CLOSED | 2011-04-28 | LO:REKEY CYLINDER | RESIDENCE | CLOSED | 886.96 | 0 | 226.74 | 226.74
PJ0003790 Total | [7 empty] | 40098.1092 | 0 | 21901.6768 | 21901.6768
PJ0003789 | TI PERMIT FOR PLATINUM PERFORMANCE - BLD 83 LAB AREA 1C-1 | HOGAN, MIKE | CLOSED | 2011-04-25 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003789 | TI PERMIT FOR PLATINUM PERFORMANCE - BLD 83 LAB AREA 1C-1 | HOGAN, MIKE | CLOSED | 2011-04-25 | IN: BUILDING PERMIT FEES | 083 | CLOSED | 940.1 | 0 | 940.1 | 940.1
PJ0003789 | TI PERMIT FOR PLATINUM PERFORMANCE - BLD 83 LAB AREA 1C-1 | HOGAN, MIKE | CLOSED | 2011-04-25 | IN: PLAN REVIEW FEES | 083 | CLOSED | 1500 | 0 | 1500 | 1500
PJ0003789 | TI PERMIT FOR PLATINUM PERFORMANCE - BLD 83 LAB AREA 1C-1 | HOGAN, MIKE | CLOSED | 2011-04-25 | IN: STATE FIRE MARSHAL REVIEW AND INSPECTIONS | 083 | CLOSED | 1112 | 0 | 0 | 0
PJ0003789 | TI PERMIT FOR PLATINUM PERFORMANCE - BLD 83 LAB AREA 1C-1 | HOGAN, MIKE | CLOSED | 2011-04-25 | IN:(MAINT) TI PERMIT FOR PLATINUM PERFORMANCE - BLD 83 LAB 1C-1 | 083 | CLOSED | 0 | 0 | 1422.895 | 1422.895
PJ0003789 Total | [7 empty] | 3552.1 | 0 | 3862.995 | 3862.995
PJ0003788 | RESIDENTIAL PLAN REVIEW & INSPECTIONS- BELLA MONTANA 153F-611A | HOGAN, MIKE | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | 153 | CLOSED | 0 | 0 | 0 | 0
PJ0003788 | RESIDENTIAL PLAN REVIEW & INSPECTIONS- BELLA MONTANA 153F-611A | HOGAN, MIKE | CLOSED | 2011-04-27 | IN: (MAINT) PLAN REVIEW&INSPECTIONS- BELLA MONTANA 153F-611A | 153 | CLOSED | 0 | 0 | 414.225 | 414.225
PJ0003788 | RESIDENTIAL PLAN REVIEW & INSPECTIONS- BELLA MONTANA 153F-611A | HOGAN, MIKE | CLOSED | 2011-04-27 | IN: BUILDING PERMIT FEES | 153 | CLOSED | 278.35 | 0 | 278.35 | 278.35
PJ0003788 | RESIDENTIAL PLAN REVIEW & INSPECTIONS- BELLA MONTANA 153F-611A | HOGAN, MIKE | CLOSED | 2011-04-27 | IN: PLAN REVIEW FEES | 153 | CLOSED | 247.73 | 0 | 247.73 | 247.73
PJ0003788 | RESIDENTIAL PLAN REVIEW & INSPECTIONS- BELLA MONTANA 153F-611A | HOGAN, MIKE | CLOSED | 2011-04-27 | IN: STATE FIRE MARSHAL INSPECTION FEES (NO OVERHEAD) | 153 | CLOSED | 225 | 0 | 225 | 225
PJ0003788 Total | [7 empty] | 751.08 | 0 | 1165.305 | 1165.305
PJ0003787 | M&R HOUS 11/12: REDESIGN CSD KITCHEN CABINETS - SANTA LUCIA | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: ASAP REPROGRAPHICS - SHIPPING PLANS TO REA AND LUKER | 106 | CLOSED | 0 | 0 | 46.55 | 46.55
PJ0003787 | M&R HOUS 11/12: REDESIGN CSD KITCHEN CABINETS - SANTA LUCIA | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: REA AND LUKER, ARCHITECTS | 106 | CLOSED | 27928 | 0 | 21764.51 | 21764.51
PJ0003787 | M&R HOUS 11/12: REDESIGN CSD KITCHEN CABINETS - SANTA LUCIA | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | 106 | CLOSED | 0 | 0 | 0 | 0
PJ0003787 Total | [7 empty] | 27928 | 0 | 21811.06 | 21811.06
PJ0003785 | M&R HOUS 11/12: ROOF REPAIR - LEAKS AT WINDOW - CERRO VISTA 170 | MOLLAN, CHERYL L. | CLOSED | 2011-04-27 | AD: JOC 11.023.017 STAPLES | 170 | CLOSED | 94376.95 | 0 | 94376.95 | 94376.95
PJ0003785 | M&R HOUS 11/12: ROOF REPAIR - LEAKS AT WINDOW - CERRO VISTA 170 | MOLLAN, CHERYL L. | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 14188.57 | 0 | 0 | 0
PJ0003785 | M&R HOUS 11/12: ROOF REPAIR - LEAKS AT WINDOW - CERRO VISTA 170 | MOLLAN, CHERYL L. | CLOSED | 2011-04-27 | IN: ROOF REPAIR - LEAKS AT WINDOW - CERRO VISTA 170 | 170 | CLOSED | 213.52 | 0 | 133.45 | 133.45
PJ0003785 Total | [7 empty] | 108779.04 | 0 | 94510.4 | 94510.4
PJ0003783 | M&R HOUS 11/12: NEW SIDEWALK-NO. SIDE OF SHASTA TO VILLAGE DRIVE | LAMPMAN, GREG | CLOSED | 2011-04-27 | AD: JOC 11.022.029 STAPLES | RESIDENCE | CLOSED | 18446.6 | 0 | 18010.63 | 18010.63
PJ0003783 | M&R HOUS 11/12: NEW SIDEWALK-NO. SIDE OF SHASTA TO VILLAGE DRIVE | LAMPMAN, GREG | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 1748.31 | 0 | 0 | 0
PJ0003783 | M&R HOUS 11/12: NEW SIDEWALK-NO. SIDE OF SHASTA TO VILLAGE DRIVE | LAMPMAN, GREG | CLOSED | 2011-04-27 | IN: M&R HOUS 11/12: NEW SIDEWALK-N.SIDE OF SHASTA TO VILLAGE DR. | RESIDENCE | CLOSED | 320.28 | 0 | 160.14 | 160.14
PJ0003783 | M&R HOUS 11/12: NEW SIDEWALK-NO. SIDE OF SHASTA TO VILLAGE DRIVE | LAMPMAN, GREG | CLOSED | 2011-04-27 | LA: REPAIR LAWN AS NEEDED | RESIDENCE | CLOSED | 2980.9733 | 0 | 797.2375 | 797.2375
PJ0003783 | M&R HOUS 11/12: NEW SIDEWALK-NO. SIDE OF SHASTA TO VILLAGE DRIVE | LAMPMAN, GREG | CLOSED | 2011-04-27 | PL: REPAIR THREE ROOF DRAIN LINES - SHASTA BLDG. 100 | 100 | CLOSED | 426.46 | 0 | 460.07 | 460.07
PJ0003783 Total | [7 empty] | 23922.6233 | 0 | 19428.0775 | 19428.0775
PJ0003782 | M&R HOUS 11/12: REMOVE OLD SOLAR STORAGE TANKS - SOUTH MT | MAY, TOM | CLOSED | 2011-04-27 | AD: BOB'S CRANE SERVICE | RESIDENCE | CLOSED | 3950 | 0 | 3950 | 3950
PJ0003782 | M&R HOUS 11/12: REMOVE OLD SOLAR STORAGE TANKS - SOUTH MT | MAY, TOM | CLOSED | 2011-04-27 | CA:REMOVE ENCLOSURES FOR SOLAR TANKS AT RED BRICKS | RESIDENCE | CLOSED | 5081.5765 | 0 | 5471.365 | 5471.365
PJ0003782 | M&R HOUS 11/12: REMOVE OLD SOLAR STORAGE TANKS - SOUTH MT | MAY, TOM | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003782 | M&R HOUS 11/12: REMOVE OLD SOLAR STORAGE TANKS - SOUTH MT | MAY, TOM | CLOSED | 2011-04-27 | EL:DISCONNECT POWER FOR SOLAR TANK REMOVAL | RESIDENCE | CLOSED | 720.6181 | 0 | 196.63 | 196.63
PJ0003782 | M&R HOUS 11/12: REMOVE OLD SOLAR STORAGE TANKS - SOUTH MT | MAY, TOM | CLOSED | 2011-04-27 | EO:REMOVE BOLLARDS AND PATCH AC BEHIND RED BRICK DORMS | RESIDENCE | CLOSED | 1207.6637 | 0 | 591.52 | 591.52
PJ0003782 | M&R HOUS 11/12: REMOVE OLD SOLAR STORAGE TANKS - SOUTH MT | MAY, TOM | CLOSED | 2011-04-27 | SOLAR TANK REMOVAL PL REOVE ALL PIPING | RESIDENCE | CLOSED | 7292.1672 | 0 | 7610.455 | 7610.455
PJ0003782 Total | [7 empty] | 18252.0255 | 0 | 17819.97 | 17819.97
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: BUEHLER AND BUEHLER | 105 | CLOSED | 4800 | 0 | 3855 | 3855
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: COASTAL DEMO | 105 | CLOSED | 2230 | 0 | 2230 | 2230
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: ENGLEKIRK AND SABOL | 105 | CLOSED | 500 | 0 | 500 | 500
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: INNOVATION COMMERCIAL FLOORING | 105 | CLOSED | 1231.87 | 0 | 635.95 | 635.95
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: MORRO BAY CABINETS | 105 | CLOSED | 268.13 | 0 | 268.13 | 268.13
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: QUARESMA DRYWALL | 105 | CLOSED | 1500 | 0 | 1366.24 | 1366.24
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: SAN LUIS GLASS | 105 | CLOSED | 1592.82 | 0 | 1592.88 | 1592.88
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | AD: SANTA MARIA ACOUSTICAL | 105 | CLOSED | 1560 | 0 | 1608 | 1608
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | CA: TRINITY ROOM 100H REMODEL | 105 | CLOSED | 8561.1514 | 0 | 9521.97 | 9521.97
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | 105 | CLOSED | 0 | 0 | 0 | 0
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | EL: TRINITY ELEC FOR NEW OFFICE | 105 | CLOSED | 4500.5718 | 0 | 2945.9698 | 2945.9698
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | ES: TRINITY RM 100H REMODEL | 105 | CLOSED | 3315.8553 | 0 | 7041.03 | 7041.03
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | IN: M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | 105 | CLOSED | 213.52 | 0 | 186.83 | 186.83
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | LO: TRINITY RM 100H REMODEL | 105 | CLOSED | 1293.48 | 0 | 1098.045 | 1098.045
PJ0003781 | M&R HOUS 11/12: RENOVATE TECH IMPROVEMENT CENTER - TRINITY | BRENNAN, MICHAEL | CLOSED | 2011-04-27 | PA:TRINITY RM 100H REMODEL | 105 | CLOSED | 1387.28 | 0 | 2155.72 | 2155.72
PJ0003781 Total | [7 empty] | 32954.6785 | 0 | 35005.7648 | 35005.7648
PJ0003780 | M&R HOUS 11/12: REPLACE SHOWER VALVES ALL RESTROOMS NORTH MT | MAY, TOM | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003780 | M&R HOUS 11/12: REPLACE SHOWER VALVES ALL RESTROOMS NORTH MT | MAY, TOM | CLOSED | 2011-04-27 | PL: (MAINT - LABOR, ONLY) REPLACE SHOWER VALVES -RESIDENCE HALLS | RESIDENCE | CLOSED | 0 | 0 | 18762.9525 | 18762.9525
PJ0003780 | M&R HOUS 11/12: REPLACE SHOWER VALVES ALL RESTROOMS NORTH MT | MAY, TOM | CLOSED | 2011-04-27 | PL: (MATERIALS, ONLY) REPLACE SHOWER VALVES-RESIDENCE HALLS | RESIDENCE | CLOSED | 30000 | 0 | 29125.1669 | 29125.1669
PJ0003780 Total | [7 empty] | 30000 | 0 | 47888.1194 | 47888.1194
PJ0003779 | M&R HOUS 11/12: INSTALL PERMANENT BIRD NETTING CERRO VISTA | GRIFFIN, PATRICK E. | CLOSED | 2011-04-27 | AD: AVIARY MANAGEMENT PROFESSIONALS | 170 | CLOSED | 11800 | 0 | 11791.78 | 11791.78
PJ0003779 | M&R HOUS 11/12: INSTALL PERMANENT BIRD NETTING CERRO VISTA | GRIFFIN, PATRICK E. | CLOSED | 2011-04-27 | AD: JOC 10.022.012 STAPLES | 170 | CLOSED | 273226 | 0 | 273226 | 273226
PJ0003779 | M&R HOUS 11/12: INSTALL PERMANENT BIRD NETTING CERRO VISTA | GRIFFIN, PATRICK E. | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | 170 | CLOSED | 0 | 0 | 0 | 0
PJ0003779 | M&R HOUS 11/12: INSTALL PERMANENT BIRD NETTING CERRO VISTA | GRIFFIN, PATRICK E. | CLOSED | 2011-04-27 | PCV CA: INSTALL BIRD NETTING - CERRO VISTA - 170G | 170 | CLOSED | 6296.66 | 0 | 17127.855 | 17127.855
PJ0003779 Total | [7 empty] | 291322.66 | 0 | 302145.635 | 302145.635
PJ0003778 | M&R HOUS 11/12: REPLACE RESTROOM DROP CEILING - SM T0 | MAY, TOM | CLOSED | 2011-04-27 | AD: JOC 10.021.025 STAPLES | 113A | CLOSED | 29974.26 | 0 | 29974.26 | 29974.26
PJ0003778 | M&R HOUS 11/12: REPLACE RESTROOM DROP CEILING - SM T0 | MAY, TOM | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | 113A | CLOSED | 0 | 0 | 0 | 0
PJ0003778 Total | [7 empty] | 29974.26 | 0 | 29974.26 | 29974.26
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | AD: DAHL INSULATION | U-UDOR | CLOSED | 4000 | 0 | 2241.18 | 2241.18
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | AD: RICK TEIXEIRA WELDING | U-UDOR | CLOSED | 8000 | 0 | 7767.51 | 7767.51
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | CA: SUPPORT UTILIDOR WORK | U-UDOR | CLOSED | 547.9987 | 0 | 454.7132 | 454.7132
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | U-UDOR | CLOSED | 0 | 0 | 0 | 0
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | CPE: SUPPORT UTILIDOR VALVES REPLACEMENT | U-UDOR | CLOSED | 4216.9817 | 0 | 4022.59 | 4022.59
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | EO: EXCAVATION FOR UTILIDOR VALVES REPLACEMENT | U-UDOR | CLOSED | 1353.6954 | 0 | 1544.35 | 1544.35
PJ0003777 | M&R HOUS 11/12: REPLACE UTILIDOR CONNECTIONS - SOUTH MOUNTAIN | ELLIOT, DENNIS K | CLOSED | 2011-04-27 | LA: LANDSCAPE REPAIR AFTER UTILIDOR WORK | U-UDOR | CLOSED | 361.3911 | 0 | 259.76 | 259.76
PJ0003777 Total | [7 empty] | 18480.0669 | 0 | 16290.1032 | 16290.1032
PJ0003775 | M&R HOUS 11/12: CONSTRUCT WALK PATH - KLAMATH RD | LAMPMAN, GREG | CLOSED | 2011-04-27 | AD: JOC 11.022.028 STAPLES | RESIDENCE | CLOSED | 46651.22 | 0 | 46651.22 | 46651.22
PJ0003775 | M&R HOUS 11/12: CONSTRUCT WALK PATH - KLAMATH RD | LAMPMAN, GREG | CLOSED | 2011-04-27 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003775 | M&R HOUS 11/12: CONSTRUCT WALK PATH - KLAMATH RD | LAMPMAN, GREG | CLOSED | 2011-04-27 | IN: M&R HOUS 11/12: CONSTRUCT WALK PATH - KLAMATH RD | RESIDENCE | CLOSED | 213.52 | 0 | 133.45 | 133.45
PJ0003775 | M&R HOUS 11/12: CONSTRUCT WALK PATH - KLAMATH RD | LAMPMAN, GREG | CLOSED | 2011-04-27 | LA: CLAER LANDSCAPING FOR NEW DG WALK | RESIDENCE | CLOSED | 6022.4596 | 0 | 5240.5491 | 5240.5491
PJ0003775 Total | [7 empty] | 52887.1996 | 0 | 52025.2191 | 52025.2191
PJ0003773 | PROVIDE ELECTRICAL FOR EQUIPMENT - BLD 21 RM 13 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | AD: JOC 10.021.023 | 021 | CLOSED | 3523.7133 | 0 | 3349.6671 | 3349.6671
PJ0003773 | PROVIDE ELECTRICAL FOR EQUIPMENT - BLD 21 RM 13 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 819.41 | 0 | 0 | 0
PJ0003773 | PROVIDE ELECTRICAL FOR EQUIPMENT - BLD 21 RM 13 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | EL:PROVIDE ELECTRICAL SERVICE TO VIBRATION TEST AT ENG WEST 013 | 021 | CLOSED | 3834.8107 | 0 | 2458.032 | 2458.032
PJ0003773 | PROVIDE ELECTRICAL FOR EQUIPMENT - BLD 21 RM 13 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | IN: PROVIDE ELECTRICAL FOR EQUIPMENT - BLD 21 RM 13 | 021 | CLOSED | 265.104 | 0 | 128.112 | 128.112
PJ0003773 | PROVIDE ELECTRICAL FOR EQUIPMENT - BLD 21 RM 13 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | PL:PLUG DRAIN IN TRENCH AT ENG WEST 013 | 021 | CLOSED | 584.2948 | 0 | 130.584 | 130.584
PJ0003773 Total | [7 empty] | 9027.3328 | 0 | 6066.3951 | 6066.3951
PJ0003772 | CREATE A PHOTOGRAPHIC IMAGE WITH PHOTOSHOP - PAC 06(NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-21 | AD: CREATE A PHOTOGRAPHIC IMAGE WITH PHOTOSHOP - PAC 06 | 006 | CLOSED | 0 | 0 | 485.856 | 485.856
PJ0003772 | CREATE A PHOTOGRAPHIC IMAGE WITH PHOTOSHOP - PAC 06(NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003772 Total | [7 empty] | 0 | 0 | 485.856 | 485.856
PJ0003770 | M&R PARK 11/12: PARKING LOT REPAIR & TREE TRIMMING | GALVEZ, CESAR | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 454.55 | 0 | 0 | 0
PJ0003770 | M&R PARK 11/12: PARKING LOT REPAIR & TREE TRIMMING | GALVEZ, CESAR | CLOSED | 2011-04-21 | LA: SUPPORT M&R PARK 11/12: PARKING LOT REPAIR & TREE TRIMMING | GEN-PARK | CLOSED | 4545.5689 | 0 | 5354.466 | 5354.466
PJ0003770 Total | [7 empty] | 5000.1189 | 0 | 5354.466 | 5354.466
PJ0003769 | M&R PARK 11/12: PARKING STRUCTURE MAINT & STRIPING (130,371,372) | LAMPMAN, GREG | CLOSED | 2011-04-21 | AD: JOC 11.022.037 STAPLES | GEN-PARK | CLOSED | 13116.1456 | 0 | 13116.1456 | 13116.1456
PJ0003769 | M&R PARK 11/12: PARKING STRUCTURE MAINT & STRIPING (130,371,372) | LAMPMAN, GREG | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 1324.43 | 0 | 0 | 0
PJ0003769 | M&R PARK 11/12: PARKING STRUCTURE MAINT & STRIPING (130,371,372) | LAMPMAN, GREG | CLOSED | 2011-04-21 | IN: M&R PARK 11/12: PARKING STRUCTURE MAINT (130, 271, & 371) | GEN-PARK | CLOSED | 128.112 | 0 | 64.056 | 64.056
PJ0003769 Total | [7 empty] | 14568.6876 | 0 | 13180.2016 | 13180.2016
PJ0003768 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4A BRAE | GALVEZ, CESAR | CLOSED | 2011-04-21 | AD: JOC 10.021.030 STAPLES | P-H04 | CLOSED | 8403.3199 | 0 | 8403.3413 | 8403.3413
PJ0003768 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4A BRAE | GALVEZ, CESAR | CLOSED | 2011-04-21 | CA: NEW POLE, FABRICATE & MOUNT ACCESSIBLE SIGNS -BLDG 8 | P-H04 | CLOSED | 366.948 | 0 | 367.956 | 367.956
PJ0003768 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4A BRAE | GALVEZ, CESAR | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 0 | 0 | 0 | 0
PJ0003768 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4A BRAE | GALVEZ, CESAR | CLOSED | 2011-04-21 | IN: M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4A BRAE | P-H04 | CLOSED | 130.5637 | 0 | 128.112 | 128.112
PJ0003768 Total | [7 empty] | 8900.8316 | 0 | 8899.4093 | 8899.4093
PJ0003767 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4F CORP | GALVEZ, CESAR | CLOSED | 2011-04-21 | AD: JOC 10.021.029 STAPLES | P-H04 | CLOSED | 11478.4571 | 0 | 11610.891 | 11610.891
PJ0003767 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4F CORP | GALVEZ, CESAR | CLOSED | 2011-04-21 | CA: FABRICATE 3 SIGNS & INSTALL ONE POST - P-H4F LOT | P-H04 | CLOSED | 598.8625 | 0 | 475.596 | 475.596
PJ0003767 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4F CORP | GALVEZ, CESAR | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 423.18 | 0 | 0 | 0
PJ0003767 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4F CORP | GALVEZ, CESAR | CLOSED | 2011-04-21 | IN: M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-H4F CORP | P-H04 | CLOSED | 66.276 | 0 | 64.056 | 64.056
PJ0003767 Total | [7 empty] | 12566.7756 | 0 | 12150.543 | 12150.543
PJ0003766 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-C07 POLY GROVE | GALVEZ, CESAR | CLOSED | 2011-04-21 | AD: JOC 11.022.040 STAPLES | P-C07 | CLOSED | 5824.1384 | 0 | 5824.1384 | 5824.1384
PJ0003766 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-C07 POLY GROVE | GALVEZ, CESAR | CLOSED | 2011-04-21 | CA: ADD ACCESIBLE SIGNAGE WITH POST - LOT C7A | P-C07 | CLOSED | 1029.432 | 0 | 915.2764 | 915.2764
PJ0003766 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-C07 POLY GROVE | GALVEZ, CESAR | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | P-C07 | CLOSED | 627.3 | 0 | 0 | 0
PJ0003766 | M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-C07 POLY GROVE | GALVEZ, CESAR | CLOSED | 2011-04-21 | IN: M&R PARK 11/12: RESEAL, & RESTRIPE LOT P-C07 POLY GROVE | P-C07 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003766 Total | [7 empty] | 7608.9824 | 0 | 6867.5268 | 6867.5268
PJ0003765 | REPAVE UNEVEN TARMAC BETWN BRAE LABS&STORAGE BLDS -BLD 8A(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003765 | REPAVE UNEVEN TARMAC BETWN BRAE LABS&STORAGE BLDS -BLD 8A(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-04-21 | EO:PATCH ASPHALT BEHIND AG SHOPS | GENERAL | CLOSED | 0 | 0 | 384.17 | 384.17
PJ0003765 Total | [7 empty] | 0 | 0 | 384.17 | 384.17
PJ0003764 | M&R PARK 11/12: REPAIR ASPHALT, RESEAL, & RESTRIPE LOT P-H2B | GALVEZ, CESAR | CLOSED | 2011-04-20 | LA: INSPECT & APPROVE SMOOTH CUT ROOTS - H2B LOT (N/L) | P-H02 | CLOSED | 0 | 0 | 0 | 0
PJ0003764 | M&R PARK 11/12: REPAIR ASPHALT, RESEAL, & RESTRIPE LOT P-H2B | GALVEZ, CESAR | CLOSED | 2011-04-20 | AD: JOC 10.021.028 STAPLES | P-H02 | CLOSED | 16928.5556 | 0 | 16928.5556 | 16928.5556
PJ0003764 | M&R PARK 11/12: REPAIR ASPHALT, RESEAL, & RESTRIPE LOT P-H2B | GALVEZ, CESAR | CLOSED | 2011-04-20 | CP: PROJECT CONTINGENCY | P-H02 | CLOSED | 0 | 0 | 0 | 0
PJ0003764 | M&R PARK 11/12: REPAIR ASPHALT, RESEAL, & RESTRIPE LOT P-H2B | GALVEZ, CESAR | CLOSED | 2011-04-20 | IN: M&R PARK 11/12: REPAIR ASPHALT, RESEAL, & RESTRIPE LOT P-H2B | P-H02 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003764 Total | [7 empty] | 16992.6116 | 0 | 16992.6116 | 16992.6116
PJ0003761 | INSTALL RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | MOLLAN, CHERYL L. | CLOSED | 2011-04-19 | CP: PROJECT CONTINGENCY | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0003761 | INSTALL RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | MOLLAN, CHERYL L. | CLOSED | 2011-04-19 | EL: INSTALL ELECTRICAL TO NEW THERMOSTAT - SP COMPL GROUNDS SHOP | 160F | CLOSED | 600.002 | 0 | 473.7 | 473.7
PJ0003761 | INSTALL RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | MOLLAN, CHERYL L. | CLOSED | 2011-04-19 | EO:DIG TRENCH FOR NEW GAS PIPE | 160F | CLOSED | 2058.8 | 0 | 1603.82 | 1603.82
PJ0003761 | INSTALL RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | MOLLAN, CHERYL L. | CLOSED | 2011-04-19 | ES:SUPPLY AND INSTALL NEW RADIANT HEATERS | 160F | CLOSED | 5815.8553 | 0 | 7212.895 | 7212.895
PJ0003761 | INSTALL RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | MOLLAN, CHERYL L. | CLOSED | 2011-04-19 | IN: RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | 160F | CLOSED | 106.76 | 0 | 160.14 | 160.14
PJ0003761 | INSTALL RADIANT HEATER OVER OFFICE SPACE -SPRTS CMPLX GRND SHOP | MOLLAN, CHERYL L. | CLOSED | 2011-04-19 | PL:SUPPLY AND INSTALL NEW GAS PIPELINE FOR NEW HEATERS | 160F | CLOSED | 3957.9557 | 0 | 3410.175 | 3410.175
PJ0003761 Total | [7 empty] | 12539.373 | 0 | 12860.73 | 12860.73
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: EARTH SYSTEMS | 061 | CLOSED | 1200 | 0 | 1200 | 1200
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: ENGLEKIRK AND SABOL | 061 | CLOSED | 1250 | 0 | 1440 | 1440
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: HAYER CONSULTING | 061 | CLOSED | 1625 | 0 | 1625 | 1625
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: REA AND LUKER, ARCHITECTS | 061 | CLOSED | 26715 | 0 | 29221.89 | 29221.89
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: SHIPPING CHARGES (TO ENGLEKIRK AND HAYER) | 061 | CLOSED | 18.06 | 0 | 18.06 | 18.06
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: THE WALLACE GROUP | 061 | CLOSED | 3875 | 0 | 3875 | 3875
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | AD: UNJUSTIFIED - REA AND LUKER | 061 | CLOSED | 7475 | 0 | 0 | 0
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | EL: LOCATE UTILITIES FOR TOPO MAPPING | 061 | CLOSED | 196.63 | 0 | 196.63 | 196.63
PJ0003760 | FP 11/12: DESIGN/ENGINEERING, ONLY, FOR SOUTH SIDE ADA - 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-04-20 | IN: INSTALL PERMANENT BLEACHERS AT S.END-ZONE - SPANOS 061 | 061 | CLOSED | 533.8 | 0 | 533.8 | 533.8
PJ0003760 Total | [7 empty] | 42888.49 | 0 | 38110.38 | 38110.38
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | AD: MACDONALD COMPANY | 065 | CLOSED | 1358.3008 | 0 | 1355.0908 | 1355.0908
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | CA: INSTALL FIRE RATED SMOKE SEAL - UU 1ST FLOOR NEAR ELEVATOR | 065 | CLOSED | 232.776 | 0 | 81.684 | 81.684
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 190.77 | 0 | 0 | 0
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | EH&S: INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL(N/L) | 065 | CLOSED | 68.7 | 0 | 0 | 0
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | IN: INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | 065 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | LO:SUPPLY AND INSTALL NEW HARDWARE | 065 | CLOSED | 2268.264 | 0 | 1350.882 | 1350.882
PJ0003759 | INTERNAL STAIRWELL DOOR REPLACEMENT - UU 65 STAIRWELL | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | PA:PAINT METAL FIRE DOOR AND E FRAMEBLACK FOR UU LOWER STAIRWELL | 065 | CLOSED | 476.184 | 0 | 118.728 | 118.728
PJ0003759 Total | [7 empty] | 4659.0508 | 0 | 2970.4408 | 2970.4408
PJ0003758 | TEMPORARY REC CENTER FACILITY- BLD 19 RMS 102, 103, & 104E | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | AD: JOC 10.020.058 STAPLES | 019 | CLOSED | 5128.2104 | 0 | 5128.2104 | 5128.2104
PJ0003758 | TEMPORARY REC CENTER FACILITY- BLD 19 RMS 102, 103, & 104E | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 526.08 | 0 | 0 | 0
PJ0003758 | TEMPORARY REC CENTER FACILITY- BLD 19 RMS 102, 103, & 104E | MOLLAN, CHERYL L. | CLOSED | 2011-04-18 | IN: TEMPORARY REC CENTER FACILITY- BLD 19 RMS 102, 103, & 104E | 019 | CLOSED | 132.552 | 0 | 97.194 | 97.194
PJ0003758 Total | [7 empty] | 5786.8424 | 0 | 5225.4044 | 5225.4044
PJ0003756 | PAINT OUT EAST STAIRWELL IN ARCHITECTURE BLDG 5 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-14 | CA:FABRICATE AND INSTALL SIGNAGE AT ARCH. | 005 | CLOSED | 245.52 | 0 | 483.924 | 483.924
PJ0003756 | PAINT OUT EAST STAIRWELL IN ARCHITECTURE BLDG 5 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-14 | CA:FABRICATE SIGNS FOR ARCH STAIRWELL | 005 | CLOSED | 0 | 0 | 204.306 | 204.306
PJ0003756 | PAINT OUT EAST STAIRWELL IN ARCHITECTURE BLDG 5 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-14 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 542.09 | 0 | 0 | 0
PJ0003756 | PAINT OUT EAST STAIRWELL IN ARCHITECTURE BLDG 5 | GRIFFIN, PATRICK E. | CLOSED | 2011-04-14 | PA:PAINT OUT STAIRWELL AT ARCH | 005 | CLOSED | 5175.36 | 0 | 2422.968 | 2422.968
PJ0003756 Total | [7 empty] | 5962.97 | 0 | 3111.198 | 3111.198
PJ0003754 | INSTALL MEN'S BASKETBALL LOCKER ROOM DOORS - BLD 42(SEE PJ 3170) | MAY, TOM | CLOSED | 2011-04-13 | AD: MACDONALD COMPANY | 042 | CLOSED | 2539.1742 | 0 | 2524.6115 | 2524.6115
PJ0003754 | INSTALL MEN'S BASKETBALL LOCKER ROOM DOORS - BLD 42(SEE PJ 3170) | MAY, TOM | CLOSED | 2011-04-13 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 323.8 | 0 | 0 | 0
PJ0003754 | INSTALL MEN'S BASKETBALL LOCKER ROOM DOORS - BLD 42(SEE PJ 3170) | MAY, TOM | CLOSED | 2011-04-13 | IN: INSTALL MEN'S BASKETBALL LOCKER RM DOORS-BLD 42(SEE PJ 3170) | 042 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003754 | INSTALL MEN'S BASKETBALL LOCKER ROOM DOORS - BLD 42(SEE PJ 3170) | MAY, TOM | CLOSED | 2011-04-13 | LO:INSTALL (E) LOCKSET AND DOOR CLOSURES FOR BASKETBALL | 042 | CLOSED | 199.6714 | 0 | 202.29 | 202.29
PJ0003754 | INSTALL MEN'S BASKETBALL LOCKER ROOM DOORS - BLD 42(SEE PJ 3170) | MAY, TOM | CLOSED | 2011-04-13 | PA:PAINT BASKETBALL DOORS | 042 | CLOSED | 664.9615 | 0 | 237.456 | 237.456
PJ0003754 Total | [7 empty] | 3791.6631 | 0 | 3028.4135 | 3028.4135
PJ0003753 | CAME SECURITY LOCKS INSTALLATION - BLD 192 RMS 328, 329, & 330 | ELLIOT, DENNIS K | CLOSED | 2011-04-12 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 494.22 | 0 | 0 | 0
PJ0003753 | CAME SECURITY LOCKS INSTALLATION - BLD 192 RMS 328, 329, & 330 | ELLIOT, DENNIS K | CLOSED | 2011-04-12 | EL: INSTALL POWER TO CAME PANELS | 192 | CLOSED | 752.6275 | 0 | 401.64 | 401.64
PJ0003753 | CAME SECURITY LOCKS INSTALLATION - BLD 192 RMS 328, 329, & 330 | ELLIOT, DENNIS K | CLOSED | 2011-04-12 | IN:CAME SECURITY LOCKS INSTALLATION - BLD 192 RMS 328, 329, &330 | 192 | CLOSED | 132.552 | 0 | 33.138 | 33.138
PJ0003753 | CAME SECURITY LOCKS INSTALLATION - BLD 192 RMS 328, 329, & 330 | ELLIOT, DENNIS K | CLOSED | 2011-04-12 | LO: INSTALL STRIKERS TO THREE DOORS | 192 | CLOSED | 4057.344 | 0 | 2102.808 | 2102.808
PJ0003753 Total | [7 empty] | 5436.7435 | 0 | 2537.586 | 2537.586
PJ0003752 | SUPPORT FFA STATE FINALS - MAY 6TH & 7TH, 2011 | POPHAM, DONALD J. | CLOSED | 2011-04-13 | CA: MOVE OUT NORTH, SOUTH, & EAST BLEACHERS - MAY5 | GENERAL | CLOSED | 0 | 0 | 443.04 | 443.04
PJ0003752 | SUPPORT FFA STATE FINALS - MAY 6TH & 7TH, 2011 | POPHAM, DONALD J. | CLOSED | 2011-04-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003752 | SUPPORT FFA STATE FINALS - MAY 6TH & 7TH, 2011 | POPHAM, DONALD J. | CLOSED | 2011-04-13 | CU: SUPPORT FOR FFA STATE FINALS - MAY 7 | GENERAL | CLOSED | 0 | 0 | 655.92 | 655.92
PJ0003752 Total | [7 empty] | 0 | 0 | 1098.96 | 1098.96
PJ0003751 | REPAIR FENCE - POULTRY UNIT (UPD CASE # 11-0382) | GRIFFIN, PATRICK E. | CLOSED | 2011-04-11 | AD: TOWN AND COUNTRY FENCING | 150 | CLOSED | 2551.95 | 0 | 2618.1616 | 2618.1616
PJ0003751 | REPAIR FENCE - POULTRY UNIT (UPD CASE # 11-0382) | GRIFFIN, PATRICK E. | CLOSED | 2011-04-11 | CP: PROJECT CONTINGENCY | 150 | CLOSED | 0 | 0 | 0 | 0
PJ0003751 Total | [7 empty] | 2551.95 | 0 | 2618.1616 | 2618.1616
PJ0003749 | INSTALL SMART RM EQUIP-BLD 22 RMS 212, 220, 311, 312,313(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CA:SMART ROOM - SEE PLAN- BLDG. 22- RMS 212,220,311,312,313 | 022 | CLOSED | 0 | 0 | 1407.99 | 1407.99
PJ0003749 | INSTALL SMART RM EQUIP-BLD 22 RMS 212, 220, 311, 312,313(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 022 | CLOSED | 0 | 0 | 0 | 0
PJ0003749 | INSTALL SMART RM EQUIP-BLD 22 RMS 212, 220, 311, 312,313(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | EL:SMART ROOM - SEE PLAN- BLDG 22 RMS 212,220,311,312,313 | 022 | CLOSED | 0 | 0 | 16774.7904 | 16774.7904
PJ0003749 | INSTALL SMART RM EQUIP-BLD 22 RMS 212, 220, 311, 312,313(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | IN: INSTALL SMART RM EQUIP. - BLD 22 RMS 212, 220, 311, 312, 313 | 022 | CLOSED | 0 | 0 | 129.222 | 129.222
PJ0003749 | INSTALL SMART RM EQUIP-BLD 22 RMS 212, 220, 311, 312,313(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | PA:SMART ROOM PROJECT- BLDG. 22- ROOM 212,220,311,312,313 | 022 | CLOSED | 0 | 0 | 3434.292 | 3434.292
PJ0003749 Total | [7 empty] | 0 | 0 | 21746.2944 | 21746.2944
PJ0003748 | INSTALL SMART ROOM EQUIPMENT - BLD 20 RM 143 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CA:SMART ROOM- BLDG. 20 ROOM 143 | 020 | CLOSED | 0 | 0 | 310.134 | 310.134
PJ0003748 | INSTALL SMART ROOM EQUIPMENT - BLD 20 RM 143 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 0 | 0 | 0 | 0
PJ0003748 | INSTALL SMART ROOM EQUIPMENT - BLD 20 RM 143 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | EL:SMARTROOM BLDG 20, ROOM 143 | 020 | CLOSED | 0 | 0 | 2733.24 | 2733.24
PJ0003748 | INSTALL SMART ROOM EQUIPMENT - BLD 20 RM 143 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 20 RM 143 | 020 | CLOSED | 0 | 0 | 65.166 | 65.166
PJ0003748 | INSTALL SMART ROOM EQUIPMENT - BLD 20 RM 143 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | PA:SMART ROOM- BLDG 20 ROOM 143- PATCH AND PAINT AS NEEDED | 020 | CLOSED | 0 | 0 | 383.784 | 383.784
PJ0003748 Total | [7 empty] | 0 | 0 | 3492.324 | 3492.324
PJ0003747 | INSTALL SMART ROOM EQUIPMENT - BLD 14 RM 247 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CA:SMART ROOM- BLDG 14, ROOM 247 | 014 | CLOSED | 0 | 0 | 479.298 | 479.298
PJ0003747 | INSTALL SMART ROOM EQUIPMENT - BLD 14 RM 247 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0003747 | INSTALL SMART ROOM EQUIPMENT - BLD 14 RM 247 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | EL:SMART ROOM- BLDG 14, ROOM 247 | 014 | CLOSED | 0 | 0 | 2429.16 | 2429.16
PJ0003747 | INSTALL SMART ROOM EQUIPMENT - BLD 14 RM 247 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 14 RM 247 | 014 | CLOSED | 0 | 0 | 97.194 | 97.194
PJ0003747 | INSTALL SMART ROOM EQUIPMENT - BLD 14 RM 247 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | PA: SMART ROOM EQUIPMENT INSTALLATION BLDG 14, ROOM 247 | 014 | CLOSED | 0 | 0 | 671.832 | 671.832
PJ0003747 Total | [7 empty] | 0 | 0 | 3677.484 | 3677.484
PJ0003746 | INSTALL SMART ROOM EQUIPMENT - BLD 08 RM 121 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CA:SMART ROOM- BLDG 8, RM 121 | 008 | CLOSED | 0 | 0 | 676.656 | 676.656
PJ0003746 | INSTALL SMART ROOM EQUIPMENT - BLD 08 RM 121 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 008 | CLOSED | 0 | 0 | 0 | 0
PJ0003746 | INSTALL SMART ROOM EQUIPMENT - BLD 08 RM 121 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | EL:SMART ROOM - BLDG 8, RM 121 | 008 | CLOSED | 0 | 0 | 2845.7939 | 2845.7939
PJ0003746 | INSTALL SMART ROOM EQUIPMENT - BLD 08 RM 121 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 008 RM 121 | 008 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0003746 | INSTALL SMART ROOM EQUIPMENT - BLD 08 RM 121 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | PA: PAINTING FOR SMART ROOM PROJECT - BLDG 8, ROOM 121 | 008 | CLOSED | 0 | 0 | 435.636 | 435.636
PJ0003746 Total | [7 empty] | 0 | 0 | 4024.3619 | 4024.3619
PJ0003745 | INSTALL SMART ROOM EQUIPMENT - BLD 05 RM 226 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CA:CUT CEILING TILE FOR PROJECTOR, INSTALL SCREEN BOARD, SPEAKER | 005 | CLOSED | 0 | 0 | 157.35 | 157.35
PJ0003745 | INSTALL SMART ROOM EQUIPMENT - BLD 05 RM 226 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 0 | 0 | 0 | 0
PJ0003745 | INSTALL SMART ROOM EQUIPMENT - BLD 05 RM 226 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | EL:PROVIDE ELECTRICAL FOR SMART ROOM | 005 | CLOSED | 0 | 0 | 3080.028 | 3080.028
PJ0003745 | INSTALL SMART ROOM EQUIPMENT - BLD 05 RM 226 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 05 RM 226 | 005 | CLOSED | 0 | 0 | 97.194 | 97.194
PJ0003745 | INSTALL SMART ROOM EQUIPMENT - BLD 05 RM 226 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | PA:PAINT FRONT WALL WHERE SURFACE MOUNTED WAS REMOVED | 005 | CLOSED | 0 | 0 | 657.24 | 657.24
PJ0003745 Total | [7 empty] | 0 | 0 | 3991.812 | 3991.812
PJ0003744 | INSTALL ADDITIONAL SMART ROOM EQUIPMENT - BLD 38 RM 204 (NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CA:SMART ROOM UPGRADE- BLDG 38 RM 204 | 038 | CLOSED | 0 | 0 | 253.746 | 253.746
PJ0003744 | INSTALL ADDITIONAL SMART ROOM EQUIPMENT - BLD 38 RM 204 (NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003744 | INSTALL ADDITIONAL SMART ROOM EQUIPMENT - BLD 38 RM 204 (NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | EL:SMART ROOM UPGRADE- BLDG 38- RM 204 | 038 | CLOSED | 0 | 0 | 879.6144 | 879.6144
PJ0003744 | INSTALL ADDITIONAL SMART ROOM EQUIPMENT - BLD 38 RM 204 (NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | IN: INSTALL ADDITIONAL SMART ROOM EQUIPMENT - BLD 38 RM 204 | 038 | CLOSED | 0 | 0 | 65.166 | 65.166
PJ0003744 | INSTALL ADDITIONAL SMART ROOM EQUIPMENT - BLD 38 RM 204 (NO EST) | MOLLAN, CHERYL L. | CLOSED | 2011-04-08 | PA:SMART ROOM UPGRADE- BLDG 38- ROOM 204 | 038 | CLOSED | 0 | 0 | 900.696 | 900.696
PJ0003744 Total | [7 empty] | 0 | 0 | 2099.2224 | 2099.2224
PJ0003743 | SR 10/11: REPLACE ELECTRICAL DISTRIBUTION EQUIP. - BLD 71 | LAMPMAN, GREG | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 071 | CLOSED | 0 | 0 | 0 | 0
PJ0003743 | SR 10/11: REPLACE ELECTRICAL DISTRIBUTION EQUIP. - BLD 71 | LAMPMAN, GREG | CLOSED | 2011-04-08 | EL: (SR) MATERIALS ONLY - REPLACE ELECTRICAL DISTRIBUTION PANEL | 071 | CLOSED | 9000 | 0 | 14084.2932 | 14084.2932
PJ0003743 | SR 10/11: REPLACE ELECTRICAL DISTRIBUTION EQUIP. - BLD 71 | LAMPMAN, GREG | CLOSED | 2011-04-08 | EL:(MAINT)LABOR ONLY - ELECTRICAL DISTRIBUTION PANEL AT TRANSPO | 071 | CLOSED | 0 | 0 | 13135.84 | 13135.84
PJ0003743 | SR 10/11: REPLACE ELECTRICAL DISTRIBUTION EQUIP. - BLD 71 | LAMPMAN, GREG | CLOSED | 2011-04-08 | IN: (MAINT) REPLACE ELECTRICAL DISTRIBUTION EQUIP. - BLD 71 | 071 | CLOSED | 0 | 0 | 53.38 | 53.38
PJ0003743 Total | [7 empty] | 9000 | 0 | 27273.5132 | 27273.5132
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | AD: RF MACDONALD COMPANY | 035 | CLOSED | 1932.7303 | 0 | 1923.1859 | 1923.1859
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | AD: SAN LUIS GLASS | 035 | CLOSED | 634.3388 | 0 | 634.3495 | 634.3495
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | CA:INSTALL WHITE BOARD IN 35-409A | 035 | CLOSED | 55.38 | 0 | 56.388 | 56.388
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 232.63 | 0 | 0 | 0
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | IN: REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | 035 | CLOSED | 66.276 | 0 | 64.056 | 64.056
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | LO:ASSIST IN DOOR REPLACEMENT AT 35-409 (NO LABOR) | 035 | CLOSED | 490.9147 | 0 | 544.968 | 544.968
PJ0003742 | REPLACE ENTRY DOORS W/STORE FRONT DOORS - BLD 35 RM 409 | MAY, TOM | CLOSED | 2011-04-08 | PA:PAINT SIDE WALL AT ENTRANCE TO 35-409 | 035 | CLOSED | 786.9619 | 0 | 386.184 | 386.184
PJ0003742 Total | [7 empty] | 4199.2317 | 0 | 3609.1314 | 3609.1314
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | AD: BUEHLER AND BUEHLER | 034 | CLOSED | 5350 | 0 | 5350 | 5350
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | AD: ENGLEKIRK AND SABOL | 034 | CLOSED | 535 | 0 | 535 | 535
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | AD: JOC 13.029.051.00 (PARTIAL) MAINO | 034 | CLOSED | 0 | 0 | 2835.5 | 2835.5
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | AD: ON TRAC (SHIPPING CHARGES) | 034 | CLOSED | 0 | 0 | 37.2 | 37.2
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | CA:SUPPLY AND INSTALL CONCRETE TO MATCH EXISITNG SLAB | 034 | CLOSED | 9072.6516 | 0 | 4086.159 | 4086.159
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 2293.1 | 0 | 0 | 0
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | CU:PROVIDE CUSTIODIAL SUPPORT AFTER CONSTRUCTION | 034 | CLOSED | 131.184 | 0 | 114.786 | 114.786
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | EH&S: UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 (N/L) | 034 | CLOSED | 129.792 | 0 | 0 | 0
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | EL:INSTALL NEW ELECTRICAL FOR SUBWAY RESTAURANT | 034 | CLOSED | 57614.1884 | 0 | 52896.6595 | 52896.6595
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | EO:REMOVE CONCRETE AND DEBRIS TO PROVIDE SUPPORT FOR PLUMBERS | 034 | CLOSED | 3326.2627 | 0 | 2235.804 | 2235.804
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | ES:REMOVE PIPE- BALANCE NEW HVAC SYSTEM AFTER INSTALLATION | 034 | CLOSED | 4698.4282 | 0 | 2500.8166 | 2500.8166
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | IN: UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | 034 | CLOSED | 397.656 | 0 | 420.804 | 420.804
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | LO:CHANGE CORES FOR CONSTRUCTION | 034 | CLOSED | 348.672 | 0 | 748.176 | 748.176
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | MO: MOVE PALLETS FOR SUBWAY PROJECT - BDLG. 34 | 034 | CLOSED | 291.6 | 0 | 74.646 | 74.646
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | PA: PATCH/PAINT EXTERIOR WALL TO LEFT OF WALK-UP WINDOW - SUBWAY | 034 | CLOSED | 386.184 | 0 | 1161.762 | 1161.762
PJ0003739 | UTILITY UPGRADES FOR SUBWAY RESTAURANT - BLD 34 | MOLLAN, CHERYL L. | CLOSED | 2011-04-07 | PL:PLUMBING INSTALLATIONS IN DEXTER TO SUPPORT SUBWAY | 034 | CLOSED | 12350.6006 | 0 | 8045.364 | 8045.364
PJ0003739 Total | [7 empty] | 96925.3196 | 0 | 81042.6771 | 81042.6771
PJ0003737 | REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 | MOLLAN, CHERYL L. | CLOSED | 2011-04-06 | AD: JOC 10.020.057 STAPLES | 019 | CLOSED | 4697.7387 | 0 | 4697.7387 | 4697.7387
PJ0003737 | REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 | MOLLAN, CHERYL L. | CLOSED | 2011-04-06 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 696.7 | 0 | 0 | 0
PJ0003737 | REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 | MOLLAN, CHERYL L. | CLOSED | 2011-04-06 | EH&S: REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 (NO LABOR) | 019 | CLOSED | 189.792 | 0 | 73.2 | 73.2
PJ0003737 | REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 | MOLLAN, CHERYL L. | CLOSED | 2011-04-06 | IN: REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 | 019 | CLOSED | 265.104 | 0 | 195.498 | 195.498
PJ0003737 | REMOVE NON-WEIGHT BEARING WALL - BLD 19 RM 106 | MOLLAN, CHERYL L. | CLOSED | 2011-04-06 | PA:PAINT SOFFIT WHERE WALL HAS BEEN REMOVED- DINING 106 | 019 | CLOSED | 1814.4958 | 0 | 712.368 | 712.368
PJ0003737 Total | [7 empty] | 7663.8305 | 0 | 5678.8047 | 5678.8047
PJ0003735 | REPAIR ROLL UP DOOR - BCEC - 55A | GRIFFIN, PATRICK E. | CLOSED | 2011-04-06 | AD: HAMON OVERHEAD DOOR (CB-ZERODPT, OK) | 055A | CLOSED | 475 | 0 | 720.2 | 720.2
PJ0003735 | REPAIR ROLL UP DOOR - BCEC - 55A | GRIFFIN, PATRICK E. | CLOSED | 2011-04-06 | CA:REPAIR DAMAGED ROLL-UP DOOR TRIM AT BCEC | 055A | CLOSED | 220.5072 | 0 | 135.456 | 135.456
PJ0003735 | REPAIR ROLL UP DOOR - BCEC - 55A | GRIFFIN, PATRICK E. | CLOSED | 2011-04-06 | CP: PROJECT CONTINGENCY | 055A | CLOSED | 85.52 | 0 | 0 | 0
PJ0003735 | REPAIR ROLL UP DOOR - BCEC - 55A | GRIFFIN, PATRICK E. | CLOSED | 2011-04-06 | PA: PREP AND PAINT REPAIRED ROLL-UP DOOR TRIM AT BCEC | 055A | CLOSED | 126.384 | 0 | 150.384 | 150.384
PJ0003735 Total | [7 empty] | 907.4112 | 0 | 1006.04 | 1006.04
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | AD: ENGLEKIRK & SABOL - SEISMIC PEER REVIEW | 065 | CLOSED | 790 | 0 | 795.66 | 795.66
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | AD: MCKENNA ENVIRONMENTAL | 065 | CLOSED | 3418.65 | 0 | 3411.9946 | 3411.9946
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | AD: MORELAND THOMPSON, INC. | 065 | CLOSED | 2172.1 | 0 | 2270.326 | 2270.326
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | AD: PROJECT COORDINATION | 065 | CLOSED | 7447.2 | 0 | 7447.2 | 7447.2
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | AD: STATE FIRE MARSHAL REVIEW AND INSPECTION FEES | 065 | CLOSED | 481.5 | 0 | 0 | 0
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | EL:PROVIDE ELECTRICAL SUPPORT FOR CHASE TENANT IMPROVEMENT | 065 | CLOSED | 992.9894 | 0 | 483.852 | 483.852
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | IN: (MAINT) TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (SESLOC) | 065 | CLOSED | 0 | 0 | 1121.905 | 1121.905
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | IN: BUILDING PERMIT FEES | 065 | CLOSED | 1714.1 | 0 | 1714.1 | 1714.1
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | IN: PLAN REVIEW FEES | 065 | CLOSED | 1525.55 | 0 | 1525.55 | 1525.55
PJ0003734 | TENANT IMPROVEMENTS FOR CHASE BANK - UU 65 (FORMER SESLOC) | MOLLAN, CHERYL L. | CLOSED | 2011-03-25 | PL:CONSTRUCTION SUPPORT - KEEP WO OPEN DURING TI | 065 | CLOSED | 994.8058 | 0 | 261.168 | 261.168
PJ0003734 Total | [7 empty] | 19536.8952 | 0 | 19031.7556 | 19031.7556
PJ0003733 | REPAIR BIKE PATH CONCRETE AT POLE #136 ON HIGHLAND AVE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-24 | CA:REPAIR BROKEN CURB AND GUTTER ON HIGHLAND | GENERAL | CLOSED | 2076.4 | 0 | 2091.725 | 2091.725
PJ0003733 | REPAIR BIKE PATH CONCRETE AT POLE #136 ON HIGHLAND AVE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003733 | REPAIR BIKE PATH CONCRETE AT POLE #136 ON HIGHLAND AVE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-24 | EL: MARK THE LIGHT POLE LINES ON HIGHLAND | GENERAL | CLOSED | 0 | 0 | 52.87 | 52.87
PJ0003733 | REPAIR BIKE PATH CONCRETE AT POLE #136 ON HIGHLAND AVE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-24 | EL: REPLACE PULL BOX FOR STREET LIGHT ON HIGHLAND | GENERAL | CLOSED | 0 | 0 | 236.63 | 236.63
PJ0003733 | REPAIR BIKE PATH CONCRETE AT POLE #136 ON HIGHLAND AVE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-24 | EO:EXCAVATE FOR CURB AND GUTTER REPAIR ON HIGHLAND | GENERAL | CLOSED | 1451.7 | 0 | 1886.31 | 1886.31
PJ0003733 Total | [7 empty] | 3528.1 | 0 | 4267.535 | 4267.535
PJ0003732 | ANNUAL WON DOOR FIRE INSPECTIONS & SERVICE - PAC | GRIFFIN, PATRICK E. | CLOSED | 2011-03-23 | AD: WON DOOR | 006 | CLOSED | 810 | 0 | 810 | 810
PJ0003732 | ANNUAL WON DOOR FIRE INSPECTIONS & SERVICE - PAC | GRIFFIN, PATRICK E. | CLOSED | 2011-03-23 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003732 Total | [7 empty] | 810 | 0 | 810 | 810
PJ0003730 | FLOOD FROM RAIN WATER REMEDIATION - BLDS 192 RM 121 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-22 | CA:FLOOD REMEDIATION AT 192-121 AND 122 | 192 | CLOSED | 0 | 0 | 346.125 | 346.125
PJ0003730 | FLOOD FROM RAIN WATER REMEDIATION - BLDS 192 RM 121 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-22 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0003730 | FLOOD FROM RAIN WATER REMEDIATION - BLDS 192 RM 121 (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2011-03-22 | PA:TAPE, PATCH, MUD, PRIME AND PAINT AREAS AT 192 | 192 | CLOSED | 0 | 0 | 762.56 | 762.56
PJ0003730 Total | [7 empty] | 0 | 0 | 1108.685 | 1108.685
PJ0003728 | SP 10/11: OVERHEAD ELECTRICAL TO FIELD # 25 PUMP - 12 KV | LAMPMAN, GREG | CLOSED | 2011-03-21 | CP: PROJECT CONTINGENCY | 121V | CLOSED | 2188.09 | 0 | 0 | 0
PJ0003728 | SP 10/11: OVERHEAD ELECTRICAL TO FIELD # 25 PUMP - 12 KV | LAMPMAN, GREG | CLOSED | 2011-03-21 | EL: OVERHEAD ELECTRICAL TO FIELD # 25 PUMP - 12 KV | 121V | CLOSED | 21748.632 | 0 | 20931.48 | 20931.48
PJ0003728 | SP 10/11: OVERHEAD ELECTRICAL TO FIELD # 25 PUMP - 12 KV | LAMPMAN, GREG | CLOSED | 2011-03-21 | SP 10/11: OVERHEAD ELECTRICAL TO FIELD # 25 PUMP - 12 KV | 121V | CLOSED | 132.552 | 0 | 97.194 | 97.194
PJ0003728 Total | [7 empty] | 24069.274 | 0 | 21028.674 | 21028.674
PJ0003727 | MJ: NEW SIDEWALK - PALOMAR TO VILLAGE DR./KLAMATH RD. | LAMPMAN, GREG | CLOSED | 2011-03-21 | AD: JOC 10.020.061 STAPLES | GENERAL | CLOSED | 14398.89 | 0 | 14398.89 | 14398.89
PJ0003727 | MJ: NEW SIDEWALK - PALOMAR TO VILLAGE DR./KLAMATH RD. | LAMPMAN, GREG | CLOSED | 2011-03-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1842.1 | 0 | 0 | 0
PJ0003727 | MJ: NEW SIDEWALK - PALOMAR TO VILLAGE DR./KLAMATH RD. | LAMPMAN, GREG | CLOSED | 2011-03-21 | IN: NEW SIDEWALK - PALOMAR TO VILLAGE DR./KLAMATH RD. | GENERAL | CLOSED | 320.28 | 0 | 128.112 | 128.112
PJ0003727 | MJ: NEW SIDEWALK - PALOMAR TO VILLAGE DR./KLAMATH RD. | LAMPMAN, GREG | CLOSED | 2011-03-21 | LA: REPAIR LAWN AS NEEDED | GENERAL | CLOSED | 3701.9058 | 0 | 389.64 | 389.64
PJ0003727 Total | [7 empty] | 20263.1758 | 0 | 14916.642 | 14916.642
PJ0003726 | FP 10/11: CONSTRUCT GUARD RAIL NEXT TO CRANDALL WAY | LAMPMAN, GREG | CLOSED | 2011-03-21 | AD: JOC 10.021.007 STAPLES | GENERAL | CLOSED | 12128.26 | 0 | 11362.9 | 11362.9
PJ0003726 | FP 10/11: CONSTRUCT GUARD RAIL NEXT TO CRANDALL WAY | LAMPMAN, GREG | CLOSED | 2011-03-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003726 | FP 10/11: CONSTRUCT GUARD RAIL NEXT TO CRANDALL WAY | LAMPMAN, GREG | CLOSED | 2011-03-21 | EL: LOCATE ELECTRICAL UTILITIES FOR CRANDAL GUARD RAIL PROJECT | GENERAL | CLOSED | 105.74 | 0 | 79.305 | 79.305
PJ0003726 | FP 10/11: CONSTRUCT GUARD RAIL NEXT TO CRANDALL WAY | LAMPMAN, GREG | CLOSED | 2011-03-21 | IN: FP 10/11: CONSTRUCT GUARD RAIL NEXT TO CRANDALL WAY | GENERAL | CLOSED | 110.46 | 0 | 110.46 | 110.46
PJ0003726 Total | [7 empty] | 12344.46 | 0 | 11552.665 | 11552.665
PJ0003724 | REPAIR BRIZZIOLARI CREEK BRIDGE (MAINT) | LAMPMAN, GREG | CLOSED | 2011-03-18 | CA: REPAIR EXPOSED REBAR WITH CONCRETE PATCH - BRIZZOLAR BRIDGE | W-BRIZ | CLOSED | 0 | 0 | 140.97 | 140.97
PJ0003724 | REPAIR BRIZZIOLARI CREEK BRIDGE (MAINT) | LAMPMAN, GREG | CLOSED | 2011-03-18 | CP: PROJECT CONTINGENCY | W-BRIZ | CLOSED | 0 | 0 | 0 | 0
PJ0003724 Total | [7 empty] | 0 | 0 | 140.97 | 140.97
PJ0003723 | REPAIR COUNTERTOP AT CHIC-FIL-A SERVING LINE - BLDG 019-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-17 | AD: BACK TO PERFECTION, INC. | 019 | CLOSED | 1353.55 | 0 | 1251.0761 | 1251.0761
PJ0003723 | REPAIR COUNTERTOP AT CHIC-FIL-A SERVING LINE - BLDG 019-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-17 | AD: RINELL WELDING | 019 | CLOSED | 1765.5 | 0 | 1765.5 | 1765.5
PJ0003723 | REPAIR COUNTERTOP AT CHIC-FIL-A SERVING LINE - BLDG 019-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-17 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 311.91 | 0 | 0 | 0
PJ0003723 Total | [7 empty] | 3430.96 | 0 | 3016.5761 | 3016.5761
PJ0003720 | INSTALL FENCE/GATE FOR ELECT EQUIP YARD-SPORTS COMPLEX (MAINT) | MAY, TOM | CLOSED | 2011-03-15 | AD: THE FENCE FACTORY | 160F | CLOSED | 0 | 0 | 2922 | 2922
PJ0003720 | INSTALL FENCE/GATE FOR ELECT EQUIP YARD-SPORTS COMPLEX (MAINT) | MAY, TOM | CLOSED | 2011-03-15 | CP: PROJECT CONTINGENCY | 160F | CLOSED | 0 | 0 | 0 | 0
PJ0003720 Total | [7 empty] | 0 | 0 | 2922 | 2922
PJ0003719 | LAB CLEAN-UP - BLD 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2011-03-16 | CA: REMOVE CURTAINS AND CURTAIN TRACKS | 013 | CLOSED | 190.5072 | 0 | 127.032 | 127.032
PJ0003719 | LAB CLEAN-UP - BLD 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2011-03-16 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 243.7 | 0 | 0 | 0
PJ0003719 | LAB CLEAN-UP - BLD 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2011-03-16 | CU: CLEAN HVAC LAB AS PER EMAIL REQUEST | 013 | CLOSED | 459.144 | 0 | 564.3 | 564.3
PJ0003719 | LAB CLEAN-UP - BLD 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2011-03-16 | ES: PREP LAB FOR DEDICATION EVENT | 013 | CLOSED | 512.256 | 0 | 512.256 | 512.256
PJ0003719 | LAB CLEAN-UP - BLD 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2011-03-16 | PA: PREP LAB FOR DEDICATION EVENT AS PER EMAIL | 013 | CLOSED | 1275.072 | 0 | 1124.736 | 1124.736
PJ0003719 Total | [7 empty] | 2680.6792 | 0 | 2328.324 | 2328.324
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | AD: GRAINGER - CC PURCHASE - TO BE INSTALLED BY CONTRACTOR | 006 | CLOSED | 414.46 | 0 | 414.46 | 414.46
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | AD: JOC 11.023.015.00 | 006 | CLOSED | 115415.2718 | 0 | 115415.2718 | 115415.2718
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | AD: SERIES DESIGN | 006 | CLOSED | 20330 | 0 | 20330 | 20330
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | AD: SERIES USA, LLC | 006 | CLOSED | 552841.501 | 0 | 552841.501 | 552841.501
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 17376.29 | 0 | 0 | 0
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | CU: CLEAN SEATING AREA AT PAC AS NEEDED-SEAT REPLACEMENT PROJECT | 006 | CLOSED | 262.368 | 0 | 388.476 | 388.476
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | IN: REPLACE SEATING - PAC 06 | 006 | CLOSED | 1921.68 | 0 | 1409.232 | 1409.232
PJ0003718 | REPLACE SEATING - PAC 06 | LAMPMAN, GREG | CLOSED | 2011-03-15 | IN: REPLACE SEATS - PAC 06 | 006 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003718 Total | [7 empty] | 708689.6828 | 0 | 690927.0528 | 690927.0528
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | AD: CA DFG | GENERAL | OPEN | 0 | 0 | 2371.3875 | 2371.3875
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | AD: NORTH COAST ENGINEERING | GENERAL | OPEN | 11556 | 0 | 0 | 0
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | AD: ONTRAC SHIPPING | GENERAL | OPEN | 0 | 0 | 83.4065 | 83.4065
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | AD: POWER ENGINEERING SERVICES | GENERAL | OPEN | 83973.6 | 1634.6925 | 82338.9075 | 83973.6
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | AD: SWCA ENVIRONMENTAL SERVICES | GENERAL | OPEN | 37450 | 0 | 41944 | 41944
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 5622.74 | 0 | 0 | 0
PJ0003716 | SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | ELLIOT, DENNIS K | PUNCH_LIST | 2011-03-11 | SM: SP 15/16: CONSULTANT FOR SOLAR PV PROJECT | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0003716 Total | [7 empty] | 138602.34 | 1634.6925 | 126737.7015 | 128372.394
PJ0003714 | EVALUATE STRUCTURAL LOAD CAPACITY- BLD 19-103/103A/103B | MOLLAN, CHERYL L. | CLOSED | 2011-03-08 | AD: BUEHLER AND BUEHLER | 019 | CLOSED | 1070 | 0 | 1070 | 1070
PJ0003714 | EVALUATE STRUCTURAL LOAD CAPACITY- BLD 19-103/103A/103B | MOLLAN, CHERYL L. | CLOSED | 2011-03-08 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 107 | 0 | 0 | 0
PJ0003714 Total | [7 empty] | 1177 | 0 | 1070 | 1070
PJ0003712 | REPLACE DRINKING FOUNTAIN - BLD 53 1ST FLOOR BY RM 113 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-08 | CA: ASSIST PLUMBERS WITH DRINKING FOUNTAIN REPLACEMENT - BLD 53 | 053 | CLOSED | 0 | 0 | 756.731 | 756.731
PJ0003712 | REPLACE DRINKING FOUNTAIN - BLD 53 1ST FLOOR BY RM 113 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-08 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 0 | 0 | 0 | 0
PJ0003712 | REPLACE DRINKING FOUNTAIN - BLD 53 1ST FLOOR BY RM 113 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-08 | EL: RESET POWER FOR NEW DRINKING FOUNTAIN - BLD 53, NEAR RM. 113 | 053 | CLOSED | 0 | 0 | 414.405 | 414.405
PJ0003712 | REPLACE DRINKING FOUNTAIN - BLD 53 1ST FLOOR BY RM 113 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-08 | PA: PAINT WALLS AROUND NEW DRINKING FOUNTAIN - BLD 53, NEAR 113 | 053 | CLOSED | 0 | 0 | 905.54 | 905.54
PJ0003712 | REPLACE DRINKING FOUNTAIN - BLD 53 1ST FLOOR BY RM 113 (MAINT) | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-08 | PL: REPLACE DRINKING FOUNTAIN - BLD 53, NEAR ROOM 113 | 053 | CLOSED | 0 | 0 | 3017.73 | 3017.73
PJ0003712 Total | [7 empty] | 0 | 0 | 5094.406 | 5094.406
PJ0003711 | MJ: INSTALL A/C TO PROTECT SENSITIVE EQUIPMENT - BLD 52 RM D17 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-07 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 1740.21 | 0 | 0 | 0
PJ0003711 | MJ: INSTALL A/C TO PROTECT SENSITIVE EQUIPMENT - BLD 52 RM D17 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-07 | CPE:INSTALL AIR CONDITIONING | 052 | CLOSED | 13523.4982 | 0 | 8121.312 | 8121.312
PJ0003711 | MJ: INSTALL A/C TO PROTECT SENSITIVE EQUIPMENT - BLD 52 RM D17 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-07 | EL: AIR CONDITIONER POWER | 052 | CLOSED | 3686.304 | 0 | 915.396 | 915.396
PJ0003711 | MJ: INSTALL A/C TO PROTECT SENSITIVE EQUIPMENT - BLD 52 RM D17 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-03-07 | IN: INSTALL A/C TO PROTECT SENSITIVE EQUIPMENT - BLD 52 RM D17 | 052 | CLOSED | 192.168 | 0 | 160.14 | 160.14
PJ0003711 Total | [7 empty] | 19142.1802 | 0 | 9196.848 | 9196.848
PJ0003710 | HOOK-UP ELECTRICAL FOR 2 MACHINES - BLD 26 RMS 217 & 213 | LAMPMAN, GREG | CLOSED | 2011-03-04 | AD: JOC 10.021.034 STAPLES | 026 | CLOSED | 9662.9774 | 0 | 9662.9774 | 9662.9774
PJ0003710 | HOOK-UP ELECTRICAL FOR 2 MACHINES - BLD 26 RMS 217 & 213 | LAMPMAN, GREG | CLOSED | 2011-03-04 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 992.81 | 0 | 0 | 0
PJ0003710 | HOOK-UP ELECTRICAL FOR 2 MACHINES - BLD 26 RMS 217 & 213 | LAMPMAN, GREG | CLOSED | 2011-03-04 | IN: HOOK-UP ELECTRICAL FOR 2 MACHINES - BLD 26 RMS 217 & 213 | 026 | CLOSED | 265.104 | 0 | 98.304 | 98.304
PJ0003710 Total | [7 empty] | 10920.8914 | 0 | 9761.2814 | 9761.2814
PJ0003709 | VERIZON TO TRENCH A 75' CONDUIT RUN FROM FIBER VAULT- RADIO HILL | HOGAN, MIKE | CLOSED | 2011-03-07 | CP: PROJECT CONTINGENCY | 208U | CLOSED | 0 | 0 | 0 | 0
PJ0003709 | VERIZON TO TRENCH A 75' CONDUIT RUN FROM FIBER VAULT- RADIO HILL | HOGAN, MIKE | CLOSED | 2011-03-07 | IN: BUILDING PERMIT FEES (FEES HAVE BEEN WAIVED) | 208U | CLOSED | 108.4 | 0 | 0 | 0
PJ0003709 | VERIZON TO TRENCH A 75' CONDUIT RUN FROM FIBER VAULT- RADIO HILL | HOGAN, MIKE | CLOSED | 2011-03-07 | IN: PLAN REVIEW FEES (FEES HAVE BEEN WAIVED) | 208U | CLOSED | 96.48 | 0 | 0 | 0
PJ0003709 | VERIZON TO TRENCH A 75' CONDUIT RUN FROM FIBER VAULT- RADIO HILL | HOGAN, MIKE | CLOSED | 2011-03-07 | IN: VERIZON TO TRENCH 75' CONDUIT RUN-RADIO HILL (MAINT) | 208U | CLOSED | 0 | 0 | 110.46 | 110.46
PJ0003709 Total | [7 empty] | 204.88 | 0 | 110.46 | 110.46
PJ0003706 | DESIGN FOR 480V ELECTRICAL UPGRADE - 24-106 (SEE PJ 4081) | LAMPMAN, GREG | CLOSED | 2011-02-16 | AD: THOMA ELECTRIC | 024 | CLOSED | 21218.1 | 0 | 21218.1 | 21218.1
PJ0003706 | DESIGN FOR 480V ELECTRICAL UPGRADE - 24-106 (SEE PJ 4081) | LAMPMAN, GREG | CLOSED | 2011-02-16 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 2193.66 | 0 | 0 | 0
PJ0003706 | DESIGN FOR 480V ELECTRICAL UPGRADE - 24-106 (SEE PJ 4081) | LAMPMAN, GREG | CLOSED | 2011-02-16 | IN: 480V ELECTRICAL UPGRADE FOR NEW EQUIPMENT - BLDG 24-106 | 024 | CLOSED | 512.448 | 0 | 512.448 | 512.448
PJ0003706 Total | [7 empty] | 23924.208 | 0 | 21730.548 | 21730.548
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | CA:REMOVE SINK- FABRICATE NEW | 038 | CLOSED | 1817.2374 | 0 | 1418.196 | 1418.196
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 282.75 | 0 | 0 | 0
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | EL:DISCONNECT ELECTRICAL FROM OVEN AND EXISTING REFRIGERATOR. | 038 | CLOSED | 315.208 | 0 | 158.61 | 158.61
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | IN: COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | 038 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | MO:MOVE SINK AND COUNTER TO E-SURPLUS. | 038 | CLOSED | 72.135 | 0 | 24.144 | 24.144
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | PA:REPAIR SMALL HOLES IN WALL AND PAINT TO MATCH EXISTING. | 038 | CLOSED | 240.768 | 0 | 586.728 | 586.728
PJ0003705 | COPY/PRODUCTION ROOM MODIFICATION - BLD 38 RM 136A | MOLLAN, CHERYL L. | CLOSED | 2011-02-24 | PL:CAPP-OFF EXISTING PLUMBING FOR SINK REMOVAL. | 038 | CLOSED | 315.8138 | 0 | 477.672 | 477.672
PJ0003705 Total | [7 empty] | 3110.1882 | 0 | 2731.626 | 2731.626
PJ0003703 | INSTALL CONCRETE PAD AND BIKE RACKS AT # 52 AND UU. (MAINT) | GALVEZ, CESAR | CLOSED | 2011-02-16 | CA: FORM AND POUR 30'X7'X4" CONCRETE PAD FOR BIKE RACKS -BLDG 52 | GENERAL | CLOSED | 4500 | 0 | 4037.57 | 4037.57
PJ0003703 | INSTALL CONCRETE PAD AND BIKE RACKS AT # 52 AND UU. (MAINT) | GALVEZ, CESAR | CLOSED | 2011-02-16 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003703 | INSTALL CONCRETE PAD AND BIKE RACKS AT # 52 AND UU. (MAINT) | GALVEZ, CESAR | CLOSED | 2011-02-16 | EO: PREP AREA FOR A 30'X7'X4" CONCRETE BIKE PAD & RACKS -BLDG 52 | GENERAL | CLOSED | 344.84 | 0 | 1100.71 | 1100.71
PJ0003703 | INSTALL CONCRETE PAD AND BIKE RACKS AT # 52 AND UU. (MAINT) | GALVEZ, CESAR | CLOSED | 2011-02-16 | LA: CAP OFF AND MODIFY IRRIGATION FOR 30'X7'X4" CONCRETE PAD | GENERAL | CLOSED | 500 | 0 | 0 | 0
PJ0003703 Total | [7 empty] | 5344.84 | 0 | 5138.28 | 5138.28
PJ0003701 | INSTALLATION OF STERO DISH MACHINE - BLDG 112 RM 107 | MOLLAN, CHERYL L. | CLOSED | 2011-02-14 | AD: JOC 10.021.032 STAPLES | 112 | CLOSED | 10649.4639 | 0 | 10649.4639 | 10649.4639
PJ0003701 | INSTALLATION OF STERO DISH MACHINE - BLDG 112 RM 107 | MOLLAN, CHERYL L. | CLOSED | 2011-02-14 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 2052.42 | 0 | 0 | 0
PJ0003701 | INSTALLATION OF STERO DISH MACHINE - BLDG 112 RM 107 | MOLLAN, CHERYL L. | CLOSED | 2011-02-14 | EL:ELECTRICAL FOR NEW STERO DISH MACHINE AT VG | 112 | CLOSED | 2808.3948 | 0 | 1283.97 | 1283.97
PJ0003701 | INSTALLATION OF STERO DISH MACHINE - BLDG 112 RM 107 | MOLLAN, CHERYL L. | CLOSED | 2011-02-14 | IN: INSTALLATION OF STERO DISH MACHINE - BLDG 112 RM 107 | 112 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003701 | INSTALLATION OF STERO DISH MACHINE - BLDG 112 RM 107 | MOLLAN, CHERYL L. | CLOSED | 2011-02-14 | PL:HOOK UP OF NEW STERO DISH MACHINE AT VG | 112 | CLOSED | 7483.7338 | 0 | 5635.614 | 5635.614
PJ0003701 Total | [7 empty] | 23060.2885 | 0 | 17635.3239 | 17635.3239
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | AD: MAINO CONSTRUCTION (LOW-VALUE PUBLIC WORKS) | 061 | CLOSED | 13995.5 | 0 | 13995 | 13995
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | CA: REMOVE PICTURES FROM WALLS - 061 PRESIDENT'S SUITE | 061 | CLOSED | 138.45 | 0 | 369.2 | 369.2
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | EL:ELECTRICAL IN PRES SUITE AT SPANOS | 061 | CLOSED | 121.0723 | 0 | 495.93 | 495.93
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | IN: ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | 061 | CLOSED | 55.23 | 0 | 55.23 | 55.23
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | PA:TOUCH UP PAINTING AT PRES SUITE AT SPANOS | 061 | CLOSED | 218.7594 | 0 | 874.445 | 874.445
PJ0003700 | FP 10/11:ADA MODS & COUNTERTOP REPLACEMENT-PRESIDENTS BOX SPANOS | MAY, TOM | CLOSED | 2011-02-11 | PL:PLUMBING FOR SINK AT PRES SUITE AT SPANOS | 061 | CLOSED | 2805.916 | 0 | 1260.47 | 1260.47
PJ0003700 Total | [7 empty] | 17334.9277 | 0 | 17050.275 | 17050.275
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 627.75 | 0 | 0 | 0
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | EL: INSTALL POLE LIGHTS | 171 | CLOSED | 12121.6214 | 0 | 11869.104 | 11869.104
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | EO: MOVE STEEL TRENCHING PLATES - PCV | 171 | CLOSED | 533.376 | 0 | 2421.96 | 2421.96
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | IN: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | 171 | CLOSED | 662.76 | 0 | 325.83 | 325.83
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | LA: TRENCHING FOR LIGHTING AND WATER | 171 | CLOSED | 5744.16 | 0 | 4597.0158 | 4597.0158
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | PCV CA: CONCRETE WORK AND FENCE | 171 | CLOSED | 29874.5892 | 0 | 22558.4374 | 22558.4374
PJ0003699 | MJ: IN-HOUSE SUPPORT-FENCING/REPAIRS-PCV VOLLEY/BBALL CRTS - 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-02-10 | PCV PL: INSTALL DRINKING FOUNTAINS | 171 | CLOSED | 14750.6006 | 0 | 5427.198 | 5427.198
PJ0003699 Total | [7 empty] | 64314.8573 | 0 | 47199.5452 | 47199.5452
PJ0003698 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 135 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-02-10 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003698 | INSTALL SMART ROOM EQUIPMENT - BLD 38 RM 135 (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2011-02-10 | EL: LOW VOLTAGE CABLE PATHWAY FROM EXISTING BOB TO NEW SPEAKERS | 038 | CLOSED | 380.664 | 0 | 441.666 | 441.666
PJ0003698 Total | [7 empty] | 380.664 | 0 | 441.666 | 441.666
PJ0003697 | INSTALL ELECTRICAL BOX ABOVE CEILING GRID - BLD 83 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2011-02-10 | AD: ELECTRICRAFT | 083 | CLOSED | 334.91 | 0 | 330.0415 | 330.0415
PJ0003697 | INSTALL ELECTRICAL BOX ABOVE CEILING GRID - BLD 83 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2011-02-10 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 36.8 | 0 | 0 | 0
PJ0003697 | INSTALL ELECTRICAL BOX ABOVE CEILING GRID - BLD 83 RM 115 | MOLLAN, CHERYL L. | CLOSED | 2011-02-10 | IN: INSTALL ELECTRICAL BOX ABOVE CEILING GRID - BLD 83 RM 115 | 083 | CLOSED | 33.138 | 0 | 33.138 | 33.138
PJ0003697 Total | [7 empty] | 404.848 | 0 | 363.1795 | 363.1795
PJ0003695 | REPLACE AWNINGS FRONT & BACK - BLD 117T | MAY, TOM | CLOSED | 2011-01-19 | AD: SHORELINE AWNINGS | 117T | CLOSED | 1461.62 | 0 | 1461.62 | 1461.62
PJ0003695 | REPLACE AWNINGS FRONT & BACK - BLD 117T | MAY, TOM | CLOSED | 2011-01-19 | CP: PROJECT CONTINGENCY | 117T | CLOSED | 146.16 | 0 | 0 | 0
PJ0003695 Total | [7 empty] | 1607.78 | 0 | 1461.62 | 1461.62
PJ0003694 | SUPPORT FOR MLS GAME ON MARCH 4, 2011 | POPHAM, DONALD J. | CLOSED | 2011-02-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003694 | SUPPORT FOR MLS GAME ON MARCH 4, 2011 | POPHAM, DONALD J. | CLOSED | 2011-02-03 | CU: SUPPORT FOR MLS GAME ON MAR 4 AT 7PM | 061 | CLOSED | 0 | 0 | 1652.382 | 1652.382
PJ0003694 | SUPPORT FOR MLS GAME ON MARCH 4, 2011 | POPHAM, DONALD J. | CLOSED | 2011-02-03 | LA: SUPPORT FOR MLS SOCCER ON MAR 4 | 061 | CLOSED | 0 | 0 | 809.178 | 809.178
PJ0003694 Total | [7 empty] | 0 | 0 | 2461.56 | 2461.56
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | AD: JOC 10.022.042 STAPLES | 114G | CLOSED | 0 | 0 | 3367.6324 | 3367.6324
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | CA: CONCRETE REMOVAL FOR YOSEMITE CONDENSATE RECEIVER | 114G | CLOSED | 621.0144 | 0 | 1481.814 | 1481.814
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | CP: PROJECT CONTINGENCY | 114G | CLOSED | 0 | 0 | 0 | 0
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | EL: REMOVE STROBES & SMOKE DETECTORS IN YOSEMITE T6 | 114G | CLOSED | 0 | 0 | 132.175 | 132.175
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | EL: REPAIR ELECTRICAL CONDUIT IN YOSEMITE T/6 3RD FLOOR RESTROOM | 114G | CLOSED | 0 | 0 | 105.74 | 105.74
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | EL:INSTALL ELECTRICAL FOR TANK | 114G | CLOSED | 1884.1974 | 0 | 1069.992 | 1069.992
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | EO:EXCAVATION TO EXPOSE STEAM PIPE | 114G | CLOSED | 2085.48 | 0 | 1467.966 | 1467.966
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | ES: INSTALL CONDENSER RECEIVER TANK | 114G | CLOSED | 6386.7552 | 0 | 7273.6833 | 7273.6833
PJ0003693 | MJ: INSTALL CONDENSATE RECEIVER - YOSEMITE T6 (PART OF COGEN PJ) | LAMPMAN, GREG | CLOSED | 2011-02-02 | LO: CHANGE CORES TO ORANGE CONSTRUCTION CORES - YOSEMITE T6 | 114G | CLOSED | 0 | 0 | 47.64 | 47.64
PJ0003693 Total | [7 empty] | 10977.447 | 0 | 14946.6427 | 14946.6427
PJ0003692 | SR10/11:REPLACE GLASS IN DOORS & ADJACENT OPENINGS - CAMPUS WIDE | GRIFFIN, PATRICK E. | CLOSED | 2011-02-02 | AD: JOC 10.021.012 STAPLES | GENERAL | CLOSED | 58918.04 | 0 | 58918.04 | 58918.04
PJ0003692 | SR10/11:REPLACE GLASS IN DOORS & ADJACENT OPENINGS - CAMPUS WIDE | GRIFFIN, PATRICK E. | CLOSED | 2011-02-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003692 Total | [7 empty] | 58918.04 | 0 | 58918.04 | 58918.04
PJ0003691 | REPAIR KICKED-IN DOOR FRAME - SS BLD 61 MENS LOCKER RM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2011-02-01 | CA: REPAIR KICKED IN DOOR FRAME - SS BLD 61 MENS LOCKER RM | 061 | CLOSED | 0 | 0 | 163.475 | 163.475
PJ0003691 | REPAIR KICKED-IN DOOR FRAME - SS BLD 61 MENS LOCKER RM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2011-02-01 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003691 | REPAIR KICKED-IN DOOR FRAME - SS BLD 61 MENS LOCKER RM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2011-02-01 | LO: REPLACE LOCK - SPANOS BLD 61 MENS LOCKER RM | 061 | CLOSED | 0 | 0 | 23.82 | 23.82
PJ0003691 | REPAIR KICKED-IN DOOR FRAME - SS BLD 61 MENS LOCKER RM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2011-02-01 | PA: PAINT DOOR FRAME - SPANOS BLD 61 MENS LOCKER RM | 061 | CLOSED | 0 | 0 | 238.3 | 238.3
PJ0003691 Total | [7 empty] | 0 | 0 | 425.595 | 425.595
PJ0003690 | INSTALL NEW SIGNS IN TWO LOCATIONS - BLD 11 | LAMPMAN, GREG | CLOSED | 2011-02-01 | AD: SISTEK GRAPHIC ARTS | 011 | CLOSED | 4380.58 | 0 | 4363.5456 | 4363.5456
PJ0003690 | INSTALL NEW SIGNS IN TWO LOCATIONS - BLD 11 | LAMPMAN, GREG | CLOSED | 2011-02-01 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 444.69 | 0 | 0 | 0
PJ0003690 | INSTALL NEW SIGNS IN TWO LOCATIONS - BLD 11 | LAMPMAN, GREG | CLOSED | 2011-02-01 | IN: INSTALL NEW SIGNS IN TWO LOCATIONS - BLD 11 | 011 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003690 Total | [7 empty] | 4891.546 | 0 | 4429.8216 | 4429.8216
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | AD: (56.96% FR / 43.04% SP) ITS - NO OVERHEAD | 116 | CLOSED | 4283.8 | 0 | 4283.8 | 4283.8
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | AD: (FR) JOC 10.021.033 STAPLES | 116 | CLOSED | 13471.9848 | 0 | 11733.6628 | 11733.6628
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | AD: (FR) MECA | 116 | CLOSED | 5467.7 | 0 | 4040.855 | 4040.855
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | AD: (FR) RUSSCO | 116 | CLOSED | 7123.5999 | 0 | 7123.5892 | 7123.5892
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | CA: (SP) COMPLETE MISC ITEMS AT JESPERSEN | 116 | CLOSED | 281.94 | 0 | 225.552 | 225.552
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | CP: (FR) PROJECT CONTINGENCY | 116 | CLOSED | 1561.57 | 0 | 0 | 0
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | CP: (SP) PROJECT CONTINGENCY | 116 | CLOSED | 2226 | 0 | 0 | 0
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | EL: (SP) PROVIDE ELECTRICAL CIRCUITS FOR CALL CENTER MOVE | 116 | CLOSED | 8323.1758 | 0 | 1955.064 | 1955.064
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | ES: (SP) MOVE HEATER COIL IN JESPERSEN 109 (N/L) | 116 | CLOSED | 1205.7006 | 0 | 0 | 0
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | IN: (SP) UPD CALL CENTER - JESPERSEN BLD 116 | 116 | CLOSED | 256.224 | 0 | 32.028 | 32.028
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | LO: (SP) INSTALL NEW LOCKSET AT JESPERSEN | 116 | CLOSED | 1041.1726 | 0 | 1943.847 | 1943.847
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | MO: (SP) MOVE FURNITURE AT JESPERSEN | 116 | CLOSED | 64.8 | 0 | 229.368 | 229.368
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | PA: (SP)PAINT OUT ROOMS AND RESTROOM AT JESPERSEN | 116 | CLOSED | 3977.2183 | 0 | 3027.564 | 3027.564
PJ0003688 | SP 11/12: UPD CALL CENTER - JESPERSEN BLD 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-31 | PL: (FR) JESPERSEN ADA RESTROOM CONVERSION | 116 | CLOSED | 6797.04 | 0 | 7009.4573 | 7009.4573
PJ0003688 Total | [7 empty] | 56081.9259 | 0 | 41604.7873 | 41604.7873
PJ0003686 | INSTALL ACOUSTICAL/THEATRICAL CURTAINS IN LIBRARY - BLDG 35-216 | MAY, TOM | CLOSED | 2011-01-27 | AD: ALAN'S DRAPERIES | 035 | CLOSED | 8721.57 | 0 | 8721.57 | 8721.57
PJ0003686 | INSTALL ACOUSTICAL/THEATRICAL CURTAINS IN LIBRARY - BLDG 35-216 | MAY, TOM | CLOSED | 2011-01-27 | AD: TEMPLE BUILDERS | 035 | CLOSED | 1328.94 | 0 | 1328.94 | 1328.94
PJ0003686 | INSTALL ACOUSTICAL/THEATRICAL CURTAINS IN LIBRARY - BLDG 35-216 | MAY, TOM | CLOSED | 2011-01-27 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1023.26 | 0 | 0 | 0
PJ0003686 | INSTALL ACOUSTICAL/THEATRICAL CURTAINS IN LIBRARY - BLDG 35-216 | MAY, TOM | CLOSED | 2011-01-27 | IN: ACOUSTICAL/THEATRICAL CURTAINS IN LIBRARY - BLDG 35-216 | 035 | CLOSED | 32.028 | 0 | 32.028 | 32.028
PJ0003686 Total | [7 empty] | 11105.798 | 0 | 10082.538 | 10082.538
PJ0003685 | RECONFIGURE CHAIN LINK FENCE INSIDE / INSTALL NEW OUTSIDE-BLD 04 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-01-26 | CA: INSTALL CHAIN LINK FENCING | 004 | CLOSED | 3648.2286 | 0 | 4257.654 | 4257.654
PJ0003685 | RECONFIGURE CHAIN LINK FENCE INSIDE / INSTALL NEW OUTSIDE-BLD 04 | KUENTZEL, DOUGLAS A. | CLOSED | 2011-01-26 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 364.81 | 0 | 0 | 0
PJ0003685 Total | [7 empty] | 4013.0386 | 0 | 4257.654 | 4257.654
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (CPC FUNDING) JOC 10.021.019 | 082 | CLOSED | 4540.7269 | 0 | 4540.7269 | 4540.7269
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (CPC FUNDING) THOMA ELECTRIC | 082 | CLOSED | 7383 | 0 | 7383 | 7383
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (TRUST) CAME SECURITY | 082 | CLOSED | 755.6875 | 0 | 755.6875 | 755.6875
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (TRUST) JOC 12.024.021 STAPLES | 082 | CLOSED | 190060.6867 | 0 | 190060.6867 | 190060.6867
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | ANTS: (CPC FUNDING) PROGRAMMING - FIRE ALARM UPGRADES AT BLDG 82 | 082 | CLOSED | 96.096 | 0 | 84.084 | 84.084
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | CP: (CPC FUNDING) PROJECT CONTINGENCY | 082 | CLOSED | 459.2 | 0 | 0 | 0
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | CP: (TRUST) PROJECT CONTINGENCY | 082 | CLOSED | 3134.84 | 0 | 0 | 0
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | EL: (TRUST) (NO LABOR) | 082 | CLOSED | 269.664 | 0 | 1502.0448 | 1502.0448
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | IN: (CPC FUNDING) FIRE ALARM SYSTEM DESIGN - BLD 82 CORP WHRS | 082 | CLOSED | 265.104 | 0 | 130.332 | 130.332
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | IN: (TRUST) FIRE ALARM SYSTEM CONSTRUCTION - BLD 82 CORP WHRS | 082 | CLOSED | 512.448 | 0 | 480.42 | 480.42
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | PL: (CPC FUNDING) FLOW TEST ON HYDRANT NEAR CORP. WHSE. BLD. 82 | 082 | CLOSED | 663.576 | 0 | 768.528 | 768.528
PJ0003684 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 82 CORP WHSE | LAMPMAN, GREG | CLOSED | 2011-01-24 | PL: (TRUST) ASSIST CONTRACTOR WITH BLDG. 82 ALARM UPGRADE | 082 | CLOSED | 261.168 | 0 | 675.024 | 675.024
PJ0003684 Total | [7 empty] | 208402.1971 | 0 | 206380.5339 | 206380.5339
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (CPC FUNDING) JOC 10.021.020 STAPLES | 015 | CLOSED | 5045.2533 | 0 | 5045.2533 | 5045.2533
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (CPC FUNDING) THOMA ELECTRIC | 015 | CLOSED | 6794.5 | 0 | 6794.5 | 6794.5
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | AD: (TRUST) JOC 12.024.022 STAPLES | 015 | CLOSED | 91016.1367 | 0 | 91016.1367 | 91016.1367
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | ANTS: PROGRAMMING FOR FIRE ALARM UPGRADES AT BLDG 15 | 015 | CLOSED | 96.096 | 0 | 108.108 | 108.108
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | CP: (TRUST) PROJECT CONTINGENCY | 015 | CLOSED | 4666.05 | 0 | 0 | 0
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | CP:(CPC FUNDING) PROJECT CONTINGENCY | 015 | CLOSED | 1210.49 | 0 | 0 | 0
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | EL: SHUT DOWN ELECTRICAL PANEL AT BLDG. 15 SERVER ROOM | 015 | CLOSED | 269.664 | 0 | 131.5512 | 131.5512
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | IN: (CPC FUNDING) DESIGN FOR FIRE ALARM SYSTEM UPGRADES - BLD 15 | 015 | CLOSED | 265.104 | 0 | 130.332 | 130.332
PJ0003683 | FIRE ALARM SYSTEM/SPRINKLER UPGRADES - BLD 15 | LAMPMAN, GREG | CLOSED | 2011-01-24 | IN: (TRUST) CONSTRUCTION OF FIRE ALARM SYSTEM UPGRADES - BLD 15 | 015 | CLOSED | 512.448 | 0 | 576.504 | 576.504
PJ0003683 Total | [7 empty] | 109875.742 | 0 | 103802.3852 | 103802.3852
PJ0003681 | SPLIT ROOM INTO TWO - 192-101 | GALVEZ, CESAR | CLOSED | 2011-01-20 | AD: CAME SECURITY | 192 | CLOSED | 8640.25 | 0 | 8640.25 | 8640.25
PJ0003681 | SPLIT ROOM INTO TWO - 192-101 | GALVEZ, CESAR | CLOSED | 2011-01-20 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 1189.85 | 0 | 0 | 0
PJ0003681 | SPLIT ROOM INTO TWO - 192-101 | GALVEZ, CESAR | CLOSED | 2011-01-20 | EL:ASSIST WITH INSTALLATION OF CARD READER AT 192-101 | 192 | CLOSED | 1800.6802 | 0 | 273.036 | 273.036
PJ0003681 | SPLIT ROOM INTO TWO - 192-101 | GALVEZ, CESAR | CLOSED | 2011-01-20 | IN: SPLIT ROOM INTO TWO - 192-101 | 192 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003681 | SPLIT ROOM INTO TWO - 192-101 | GALVEZ, CESAR | CLOSED | 2011-01-20 | LO:ASSIST WITH INSTALLATION OF CARD READER AT 192-101 | 192 | CLOSED | 1393.867 | 0 | 991.674 | 991.674
PJ0003681 Total | [7 empty] | 13088.7031 | 0 | 9969.016 | 9969.016
PJ0003680 | INSTALL A/C IN ATL ROOM 11 | MAY, TOM | CLOSED | 2011-01-20 | CA: INSTALL GROUT TO N. WALL PENETRATIONS AT THE A/C UNIT - 007 | 007 | CLOSED | 142.776 | 0 | 116.136 | 116.136
PJ0003680 | INSTALL A/C IN ATL ROOM 11 | MAY, TOM | CLOSED | 2011-01-20 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 1423.39 | 0 | 0 | 0
PJ0003680 | INSTALL A/C IN ATL ROOM 11 | MAY, TOM | CLOSED | 2011-01-20 | CPE:ORDER AND INSTALL A/C IN ATL ROOM 11 | 007 | CLOSED | 13769.1274 | 0 | 14925.834 | 14925.834
PJ0003680 | INSTALL A/C IN ATL ROOM 11 | MAY, TOM | CLOSED | 2011-01-20 | EL:INSTALL ELECTRICAL TO NEW A/C UNIT IN ATL ROOM 11 | 007 | CLOSED | 2125.7374 | 0 | 2412.516 | 2412.516
PJ0003680 | INSTALL A/C IN ATL ROOM 11 | MAY, TOM | CLOSED | 2011-01-20 | IN: INSTALL A/C IN ATL ROOM 11 | 007 | CLOSED | 66.276 | 0 | 65.166 | 65.166
PJ0003680 Total | [7 empty] | 17527.3067 | 0 | 17519.652 | 17519.652
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | CA: HAND NEW DOOR AT ENG WEST RM. 122E | 021 | CLOSED | 464.1942 | 0 | 461.904 | 461.904
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | CA: HANG NEW DOOR AT ENG WEST RM. 122B | 021 | CLOSED | 464.1942 | 0 | 461.904 | 461.904
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | CA: HANG NEW DOOR AT ENG WEST RM. 122D | 021 | CLOSED | 464.1942 | 0 | 461.904 | 461.904
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | CA: HANG NEW DOORS AT 122A AND 122C ENG WEST | 021 | CLOSED | 928.3884 | 0 | 796.776 | 796.776
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | LO: RM 122B - KEYLESS (PUNCH TYPE) ENTRY SYSTEM | 021 | CLOSED | 1436.3522 | 0 | 990.612 | 990.612
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | LO: RM. 122D - KEYLESS (PUNCH TYPE) ENTRY SYSTEM | 021 | CLOSED | 1436.3522 | 0 | 1061.34 | 1061.34
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | LO: RM. 122E - KEYLESS (PUNCH TYPE) ENTRY SYSTEM | 021 | CLOSED | 1436.3522 | 0 | 1061.34 | 1061.34
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | LO: RM. 228 - KEYLESS (PUNCH TYPE) ENTRY SYSTEM | 021 | CLOSED | 1436.3622 | 0 | 1009.26 | 1009.26
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | LO: RMS 122A, 122C, & 229 - KEYLESS (PUNCH TYPE) ENTRY SYSTEM | 021 | CLOSED | 4075.1101 | 0 | 3080.724 | 3080.724
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | PA: SEAL AND FINISH NEW DOOR AT ENG WEST RM. 122B | 021 | CLOSED | 214.7405 | 0 | 88.092 | 88.092
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | PA: SEAL AND FINISH NEW DOOR AT ENG WEST RM. 122D | 021 | CLOSED | 214.7405 | 0 | 88.092 | 88.092
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | PA: SEAL AND FINISH NEW DOOR AT ENG WEST RM. 122E | 021 | CLOSED | 214.7405 | 0 | 88.092 | 88.092
PJ0003679 | KEYLESS (PUNCH TYPE) ENTRY SYSTEM TO 7 ROOMS - BLD 21 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-25 | PA: SEAL AND FINISH NEW DOORS AT ENG WEST RMS 122A, 122C | 021 | CLOSED | 214.7405 | 0 | 268.908 | 268.908
PJ0003679 Total | [7 empty] | 13000.4616 | 0 | 9918.948 | 9918.948
PJ0003677 | PREPARE OFFICE FOR NEW LIBRARIAN - KEN LIB 35 RM 409B | MAY, TOM | CLOSED | 2011-01-21 | AD: FLOOR CONNECTION | 035 | CLOSED | 1109.3653 | 0 | 1123.8959 | 1123.8959
PJ0003677 | PREPARE OFFICE FOR NEW LIBRARIAN - KEN LIB 35 RM 409B | MAY, TOM | CLOSED | 2011-01-21 | CA:INSTALL BLINDS IN 35-409B | 035 | CLOSED | 626.5002 | 0 | 669.828 | 669.828
PJ0003677 | PREPARE OFFICE FOR NEW LIBRARIAN - KEN LIB 35 RM 409B | MAY, TOM | CLOSED | 2011-01-21 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 258.96 | 0 | 0 | 0
PJ0003677 | PREPARE OFFICE FOR NEW LIBRARIAN - KEN LIB 35 RM 409B | MAY, TOM | CLOSED | 2011-01-21 | IN: PREPARE OFFICE FOR NEW LIBRARIAN - KEN LIB 35 RM 409B | 035 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003677 | PREPARE OFFICE FOR NEW LIBRARIAN - KEN LIB 35 RM 409B | MAY, TOM | CLOSED | 2011-01-21 | PA:PATCH AND PAINT 35-409B | 035 | CLOSED | 786.9619 | 0 | 627.324 | 627.324
PJ0003677 Total | [7 empty] | 2848.0634 | 0 | 2487.3239 | 2487.3239
PJ0003676 | RE-ROOF BUILDING SUMMER 2011 - CHILDREN'S CENTER 133 | LAMPMAN, GREG | CLOSED | 2011-01-19 | AD: JOC 10.021.006 STAPLES | 133 | CLOSED | 48724.8147 | 0 | 48724.8147 | 48724.8147
PJ0003676 | RE-ROOF BUILDING SUMMER 2011 - CHILDREN'S CENTER 133 | LAMPMAN, GREG | CLOSED | 2011-01-19 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 2188.02 | 0 | 0 | 0
PJ0003676 | RE-ROOF BUILDING SUMMER 2011 - CHILDREN'S CENTER 133 | LAMPMAN, GREG | CLOSED | 2011-01-19 | IN: RE-ROOF BUILDING SUMMER 2011 - CHILDREN'S CENTER 133 | 133 | CLOSED | 198.828 | 0 | 165.69 | 165.69
PJ0003676 Total | [7 empty] | 51111.6627 | 0 | 48890.5047 | 48890.5047
PJ0003675 | REPAIR ROOF LEAK ABOVE RM B608A - CERRO VISTA-CABRILLO | MOLLAN, CHERYL L. | CLOSED | 2011-01-19 | AD: QUAGLINO ROOFING | 170B | CLOSED | 13567.6 | 0 | 13567.6 | 13567.6
PJ0003675 | REPAIR ROOF LEAK ABOVE RM B608A - CERRO VISTA-CABRILLO | MOLLAN, CHERYL L. | CLOSED | 2011-01-19 | CP: PROJECT CONTINGENCY | 170B | CLOSED | 1224.21 | 0 | 0 | 0
PJ0003675 | REPAIR ROOF LEAK ABOVE RM B608A - CERRO VISTA-CABRILLO | MOLLAN, CHERYL L. | CLOSED | 2011-01-19 | IN: REPAIR ROOF LEAK ABOVE RM B608A - CERRO VISTA-CABRILLO | 170B | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003675 Total | [7 empty] | 14924.362 | 0 | 13700.152 | 13700.152
PJ0003671 | SR 10/11: REPAIR JESPERSON HALL ROOF - BLD 116 | GRIFFIN, PATRICK E | CLOSED | 2011-01-14 | AD: WICKS ROOFING | 116 | CLOSED | 25000 | 0 | 18497.73 | 18497.73
PJ0003671 | SR 10/11: REPAIR JESPERSON HALL ROOF - BLD 116 | GRIFFIN, PATRICK E | CLOSED | 2011-01-14 | CP: PROJECT CONTINGENCY | 116 | CLOSED | 0 | 0 | 0 | 0
PJ0003671 Total | [7 empty] | 25000 | 0 | 18497.73 | 18497.73
PJ0003670 | CLEANING OF ROOM BY 1/25/11-BLD 26A PRINTING PRESS RM A100 | LOOSLEY, SCOTT L. | CLOSED | 2011-01-12 | AD: COASTAL JANITORIAL | 026A | CLOSED | 321 | 0 | 321 | 321
PJ0003670 | CLEANING OF ROOM BY 1/25/11-BLD 26A PRINTING PRESS RM A100 | LOOSLEY, SCOTT L. | CLOSED | 2011-01-12 | CP: PROJECT CONTINGENCY | 026A | CLOSED | 0 | 0 | 0 | 0
PJ0003670 Total | [7 empty] | 321 | 0 | 321 | 321
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | AD: RENTAL OF ADDITIONAL CHAIRS-TAYLOR RENTALS | 061 | CLOSED | 0 | 0 | 1342.84 | 1342.84
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: DELIVER BOARDS AND STANCHIONS-2011 SPRING COMM-JUNE 10 | GENERAL | CLOSED | 0 | 0 | 230.75 | 230.75
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: HANG 6 BANNERS AT EDUCATION, BUSINESS, ENGR W-JUNE 10 | 003 | CLOSED | 0 | 0 | 343.39 | 343.39
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: PULL OUT BLEACHERS AT MOTT GYM ON FRI JUNE 10 | 042 | CLOSED | 0 | 0 | 369.2 | 369.2
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: SUPPORT FOR 2011 SPRING COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 6401.305 | 6401.305
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: UNBOLT BIKE RACKS IN FRONT OF KENNEDY LIBRARY - JUNE 9 | 035 | CLOSED | 0 | 0 | 92.3 | 92.3
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CU: SUPPORT FOR 2011 SPRING COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 9327.2167 | 9327.2167
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | EL: INSTALL ONE SPIDER BOX DEXTER LAWN EAST SIDE-JUNE 10 | GENERAL | CLOSED | 0 | 0 | 317.22 | 317.22
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | EL: SUPPORT FOR 2011 SPRING COMMENCEMENT-JUNE 11 | 061 | CLOSED | 0 | 0 | 681.06 | 681.06
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | ES: SUPPORT FOR 2011 SPRING COMMENCEMENT-JUNE 11 | 061 | CLOSED | 0 | 0 | 569.64 | 569.64
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | LA: SUPPORT FOR 2011 SPRING COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 8209.0682 | 8209.0682
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | MC: MOVE BIKE RACKS BY JUNE 10 FOR SPR COMMENCEMENT (N/L) | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | MO: SUPPORT FOR 2011 SPRING COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 942.265 | 942.265
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | PA: SUPPORT FOR 2011 SPRING COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 1116.43 | 1116.43
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | PERMIT: 40X80 CANOPY FOR ELECTRICAL ENGR POST COMMENCE - JUNE 9 | GENERAL | CLOSED | 0 | 0 | 41.4225 | 41.4225
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | PL: SUPPORT FOR 2011 SPRING COMMENCEMENT-JUNE 11 | GENERAL | CLOSED | 0 | 0 | 1757.68 | 1757.68
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | ROADS: SUPPORT FOR 2011 SPRING COMMENCEMENT-6/11 | 061 | CLOSED | 0 | 0 | 1388.5996 | 1388.5996
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: AGB POST COMMENCEMENT - 6/11 | GENERAL | CLOSED | 0 | 0 | 125 | 125
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: BMGE POST COMMENCEMENT - JUNE 10 | 061 | CLOSED | 0 | 0 | 51 | 51
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: CENG / SOC SCI POST COMMENCEMENT - 6/11 | 035 | CLOSED | 0 | 0 | 93 | 93
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: CSC POST COMMENCEMENT - JUNE 10 | 034 | CLOSED | 0 | 0 | 54 | 54
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: CSM POST COMMENCEMENT RECEP - 6/10 | 003 | CLOSED | 0 | 0 | 57 | 57
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: EE POST COMMENCMENT - JUNE 11 | 034 | CLOSED | 0 | 0 | 43 | 43
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: ENGLISH POST COMMENCEMENT-6/11 | 003 | CLOSED | 0 | 0 | 22 | 22
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: FSN POST COMMENCEMENT CEREMONY - JUNE 11 | 022 | CLOSED | 0 | 0 | 38 | 38
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: GRC POST COMMENCEMENT - 6/11 | 014 | CLOSED | 0 | 0 | 50 | 50
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: HISTORY POST COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 50.5 | 50.5
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: MATE POST COMMENCEMENT - JUNE 11 | 048 | CLOSED | 0 | 0 | 53 | 53
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: ME POST COMMENCEMENT - JUNE 11 | 061 | CLOSED | 0 | 0 | 55 | 55
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: OCOB POST COMMENCEMENT - 6/11 | GENERAL | CLOSED | 0 | 0 | 34 | 34
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: POL SCI POST COMMENCEMENT - JUNE11 | 061 | CLOSED | 0 | 0 | 11 | 11
PJ0003669 | 2011 SPRING COMMENCEMENT SUPPORT-JUNE 11 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | SUPPLY RENTAL: RPTA POST COMMENCEMENT - JUNE 11 | 034 | CLOSED | 0 | 0 | 40 | 40
PJ0003669 Total | [7 empty] | 0 | 0 | 33906.887 | 33906.887
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: SETUP OF STAGE AND CAL POLY BANNER - MOTT GYM APR 14 | GENERAL | CLOSED | 0 | 0 | 5226.378 | 5226.378
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CA: SUPPORT FOR 2011 CAL POLY OPEN HOUSE - APR 15 & 16 | GENERAL | CLOSED | 0 | 0 | 1254.14 | 1254.14
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CU: SETUP AND TAKEDOWN OF MATS AT MOTT GYM - 4/15-4/18 | GENERAL | CLOSED | 0 | 0 | 228.438 | 228.438
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | CU: SUPPORT FOR 2011 OPEN HOUSE - APRIL 15 & 16 | GENERAL | CLOSED | 0 | 0 | 2697.3432 | 2697.3432
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | EL: INSTALL SPIDER BOXES AT MOTT GYM FOR OPEN HOUSE EVENT-APR 15 | 042 | CLOSED | 0 | 0 | 343.655 | 343.655
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | EL: SUPPORT FOR 2011 OPEN HOUSE ON APRIL 15 & 16 | GENERAL | CLOSED | 0 | 0 | 1251.735 | 1251.735
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | ES: SUPPORT FOR 2011 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 426.88 | 426.88
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | ES: SUPPORT FOR 2011 OPEN HOUSE - APR 16 | GENERAL | CLOSED | 0 | 0 | 489.6 | 489.6
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | LA: (MAINT) SUPPORT FOR 2011 OPEN HOUSE - APRIL 15 & 16 | GENERAL | CLOSED | 0 | 0 | 6567.2697 | 6567.2697
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | LA: SETUP AND TAKE DOWN OF MATS & CHAIRS-MOTT GYM APR 14 | GENERAL | CLOSED | 0 | 0 | 423.864 | 423.864
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | MC: MOVE ASI STAGING, MATS, & CHAIRS TO MOTT GYM -APR 12 | GENERAL | CLOSED | 0 | 0 | 641.5925 | 641.5925
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | PA: PAINT STAGE RAILS FOR OPEN HOUSE EVENT @ MOTT GYM - APR 14 | 042 | CLOSED | 0 | 0 | 71.49 | 71.49
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | PERMIT: PERMIT PHASE FOR 2011 OPEN HOUSE APR 14, 15, & 16 | GENERAL | CLOSED | 0 | 0 | 55.23 | 55.23
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | PL: SUPPORT FOR 2011 OPEN HOUSE - APRIL 15 & 16 | GENERAL | CLOSED | 0 | 0 | 1152.305 | 1152.305
PJ0003668 | 2011 OPEN HOUSE SUPPORT - APRIL 15 & 16 (MAINT) | POPHAM, DONALD J. | CLOSED | 2011-01-11 | RE: SUPPORT FOR 2011 OPEN HOUSE - APRIL 15 & 16 (N/L) | GENERAL | CLOSED | 0 | 0 | 968.6144 | 968.6144
PJ0003668 Total | [7 empty] | 0 | 0 | 21798.5348 | 21798.5348
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: ALAN'S DRAPERIES | 051 | CLOSED | 3840 | 0 | 3840 | 3840
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: CAME SECURITY | 051 | CLOSED | 7200 | 0 | 3625 | 3625
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: KNECHT'S | 051 | CLOSED | 16689.82 | 0 | 17636.09 | 17636.09
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: SAN LUIS GLASS | 051 | CLOSED | 0 | 0 | 1460.51 | 1460.51
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: TED MULLER PLASTERING | 051 | CLOSED | 12160 | 0 | 8106 | 8106
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: TEMPLE BUILDERS CABINETRY | 051 | CLOSED | 8000 | 0 | 24118.51 | 24118.51
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: VISALIA TILE | 051 | CLOSED | 14000 | 0 | 13722 | 13722
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | AD: WAREHOUSE PARTS FOR UNIVERSITY HSE MODERNIZATION PROJECT | 051 | CLOSED | 0 | 0 | 434.3496 | 434.3496
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | ANTS: ASSIST WITH SECURITY SYSTEM AT UNIVERSITY HOUSE - BLG 51 | 051 | CLOSED | 0 | 0 | 71.46 | 71.46
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | CA: SUPPORT FOR THE MODERNIZATION OF THE UNIVERSITY HOUSE | 051 | CLOSED | 34532.7695 | 0 | 35415.9495 | 35415.9495
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | CU: PREPARE HOUSE FOR OCCUPANCY - UNIVERSITY HOUSE 051 | 051 | CLOSED | 546.6 | 0 | 2505.046 | 2505.046
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | EH&S: UNIVERSITY HOUSE MODERNIZATION PROJECTS | 051 | CLOSED | 0 | 0 | 426.08 | 426.08
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | EL: SUPPORT FOR THE MODERNIZATION OF THE UNIVERSITY HOUSE | 051 | CLOSED | 29502.1956 | 0 | 14751.211 | 14751.211
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | EO: SUPPORT FOR UNVERSITY HOUSE MODERNIZATION PROJECT | 051 | CLOSED | 1544.8 | 0 | 347.58 | 347.58
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | IN: FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | 051 | CLOSED | 497.07 | 0 | 469.455 | 469.455
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | ITS: DATA CONNECTIONS FOR UNIVERSITY HOUSE MODERNIZATION PROJECT | 051 | CLOSED | 4315.97 | 0 | 4315.97 | 4315.97
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | LA: SUPPORT FOR UNIVERSITY HOUSE MODERNIZATION PROJECT | 051 | CLOSED | 16468.2616 | 0 | 16695.295 | 16695.295
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | LO:CORES AND LOCKSETS FOR UNIVERSITY HOUSE | 051 | CLOSED | 2828.4232 | 0 | 3959.24 | 3959.24
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | PA:PAINT UNIVERSITY HOUSE AS NEEDED | 051 | CLOSED | 24623.342 | 0 | 25158.61 | 25158.61
PJ0003667 | FP 10/11: UNIVERSITY HOUSE MODERNIZATION PROJECTS | MAY, TOM | CLOSED | 2011-01-12 | PL: SUPPORT FOR THE MODERNIZATION OF THE UNIVERSITY HOUSE | 051 | CLOSED | 16706.4648 | 0 | 17139.38 | 17139.38
PJ0003667 Total | [7 empty] | 193455.7167 | 0 | 194197.7361 | 194197.7361
PJ0003666 | SR 10/11 & SR 11/12 : SECURE/REPAIR LANDSLIDE AREA BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-01-11 | AD: EARTH SYSTEMS | GENERAL | CLOSED | 10000 | 0 | 10234.79 | 10234.79
PJ0003666 | SR 10/11 & SR 11/12 : SECURE/REPAIR LANDSLIDE AREA BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-01-11 | AD: JOC 10.020.051 STAPLES | GENERAL | CLOSED | 13253.5 | 0 | 12447.22 | 12447.22
PJ0003666 | SR 10/11 & SR 11/12 : SECURE/REPAIR LANDSLIDE AREA BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-01-11 | CA: INSTALL SAFETY SIGNAGE FOR LANDSLIDE BEHIND SIERRA MADRE | 113 | CLOSED | 0 | 0 | 123.86 | 123.86
PJ0003666 | SR 10/11 & SR 11/12 : SECURE/REPAIR LANDSLIDE AREA BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-01-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003666 | SR 10/11 & SR 11/12 : SECURE/REPAIR LANDSLIDE AREA BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-01-11 | EL: TURN OFF POWER TO 1/2 OF VOLLEYBALL CT. BEHIND SIERRA MADRE | GENERAL | CLOSED | 0 | 0 | 79.305 | 79.305
PJ0003666 | SR 10/11 & SR 11/12 : SECURE/REPAIR LANDSLIDE AREA BEHIND SM 113 | LAMPMAN, GREG | CLOSED | 2011-01-11 | IN:SR 10/11: INVESTIGATE & SECURE LANDSLIDE AREA - BEHIND SM 113 | GENERAL | CLOSED | 110.46 | 0 | 108.61 | 108.61
PJ0003666 Total | [7 empty] | 23363.96 | 0 | 22993.785 | 22993.785
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | AD: APC CONTRACTORS | 116 | CLOSED | 10804.39 | 0 | 10804.39 | 10804.39
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | AD: FLOOR CONNECTION | 116 | CLOSED | 3143.21 | 0 | 4462.78 | 4462.78
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | AD: MECA | 116 | CLOSED | 7615 | 0 | 4743.2 | 4743.2
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | CA: (MAINT) COMPLETE MOLD REMEDIATION WORK AT JESPERSEN | 116 | CLOSED | 0 | 0 | 12032.7998 | 12032.7998
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | CA: MATERIAL CHARGES (NO LABOR) | 116 | CLOSED | 6675.5 | 0 | 6667.97 | 6667.97
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | CP: PROJECT CONTINGENCY | 116 | CLOSED | 0 | 0 | 0 | 0
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | EH&S: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | 116 | CLOSED | 108.16 | 0 | 432.64 | 432.64
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | EL: (MAINT) INSTALL NEW ELECTRICAL FEED TO JESPERSEN | 116 | CLOSED | 0 | 0 | 11798.4369 | 11798.4369
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | EL: MATERIAL CHARGES (NO LABOR) | 116 | CLOSED | 5842.05 | 0 | 5815.19 | 5815.19
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | ES: (MAINT) REMOVE HEATER COVER FOR CARPENTERS | 116 | CLOSED | 0 | 0 | 2269.8672 | 2269.8672
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | PA: (MAINT) PREP AND PAINT MOLD REMEDIATION AREAS AT JESPERSEN | 116 | CLOSED | 0 | 0 | 2194.175 | 2194.175
PJ0003663 | SR 10/11: WATER DAMAGE REPAIRS TO ROOMS 109 & 214 - JESP 116 | GRIFFIN, PATRICK E. | CLOSED | 2011-01-07 | PA: PAINTING FOR JESPERSON MOLD RENOVATION | 116 | CLOSED | 5306 | 0 | 4250.79 | 4250.79
PJ0003663 Total | [7 empty] | 39494.31 | 0 | 65472.239 | 65472.239
PJ0003662 | REPAIR ROOF (ESTIMATE ONLY) - JESPERSON BLD 116 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2011-01-07 | CP: PROJECT CONTINGENCY | 116 | CLOSED | 0 | 0 | 0 | 0
PJ0003662 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003660 | REMOVE SINK/CABINETS FROM PERCUSSION STUDIO -BLD 45-215 | MOLLAN, CHERYL L. | CLOSED | 2011-01-06 | CA: REMOVE CABINETS FROM PERCUSSION STUDIO -BLD 45-215 | 045 | CLOSED | 364.9542 | 0 | 297.414 | 297.414
PJ0003660 | REMOVE SINK/CABINETS FROM PERCUSSION STUDIO -BLD 45-215 | MOLLAN, CHERYL L. | CLOSED | 2011-01-06 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 51.5 | 0 | 0 | 0
PJ0003660 | REMOVE SINK/CABINETS FROM PERCUSSION STUDIO -BLD 45-215 | MOLLAN, CHERYL L. | CLOSED | 2011-01-06 | IN: REMOVE SINK/CABINETS FROM PERCUSSION STUDIO -BLD 45-215 | 045 | CLOSED | 49.707 | 0 | 49.707 | 49.707
PJ0003660 | REMOVE SINK/CABINETS FROM PERCUSSION STUDIO -BLD 45-215 | MOLLAN, CHERYL L. | CLOSED | 2011-01-06 | PL: REMOVE SINK FROM PERCUSSION STUDIO -BLD 45-215 | 045 | CLOSED | 218.7014 | 0 | 455.31 | 455.31
PJ0003660 Total | [7 empty] | 684.8626 | 0 | 802.431 | 802.431
PJ0003659 | REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | MAY, TOM | CLOSED | 2011-01-06 | CA:REMOVE WALL AT 14-112/113 AND CUT DOORWAY AT 112/111B | 014 | CLOSED | 4411.2516 | 0 | 4904.031 | 4904.031
PJ0003659 | REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | MAY, TOM | CLOSED | 2011-01-06 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 499.75 | 0 | 0 | 0
PJ0003659 | REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | MAY, TOM | CLOSED | 2011-01-06 | EL:DISCONNECT ELECTRICAL FROM WALL IN 14-112 | 014 | CLOSED | 291.208 | 0 | 666.162 | 666.162
PJ0003659 | REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | MAY, TOM | CLOSED | 2011-01-06 | IN: REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | 014 | CLOSED | 66.276 | 0 | 65.166 | 65.166
PJ0003659 | REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | MAY, TOM | CLOSED | 2011-01-06 | LO:INSTALL NEW LOCKSET FOR DOOR 14-112/111B | 014 | CLOSED | 490.9147 | 0 | 588.798 | 588.798
PJ0003659 | REMOVE WALL BETWEEN RM 112 & 113 - BLD 14 RM 112/113 | MAY, TOM | CLOSED | 2011-01-06 | PA:PATCH/PAINT FROM WALL REMOVAL 14-112/113 | 014 | CLOSED | 1049.4732 | 0 | 1893.156 | 1893.156
PJ0003659 Total | [7 empty] | 6808.8735 | 0 | 8117.313 | 8117.313
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | AD: MCKENNA ENVIRONMENTAL | 001 | CLOSED | 2878.3 | 0 | 2876.5773 | 2876.5773
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | AD: PARC ENVIRONMENTAL | 001 | CLOSED | 2937.15 | 0 | 2937.15 | 2937.15
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | AD: QUARESMA DRYWALL | 001 | CLOSED | 5323.25 | 0 | 1856.45 | 1856.45
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | AD: TEMPLE BUILDERS | 001 | CLOSED | 4815 | 0 | 2329.4114 | 2329.4114
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | CA:COVEBASE REPAIR IN ADM LOBBY | 001 | CLOSED | 4701.8532 | 0 | 667.266 | 667.266
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 3898.42 | 0 | 0 | 0
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | EH&S: ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 (N/L) | 001 | CLOSED | 1149.6 | 0 | 56.4 | 56.4
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | EL:REMODEL ADM LOBBY AND ROOM 200A | 001 | CLOSED | 5400.6862 | 0 | 179.916 | 179.916
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | ES: MOVE TSTAT IN ROOM ADJACENT TO ADM LOBBY | 001 | CLOSED | 5179.0264 | 0 | 1030.194 | 1030.194
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | IN: ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | 001 | CLOSED | 128.112 | 0 | 128.112 | 128.112
PJ0003658 | ENCLOSE ROOM IN 2ND FLOOR LOBBY AREA - BLDG 001-200 | MAY, TOM | CLOSED | 2011-01-06 | PA:PAINT LOBBY AND ADJACENT ROOM IN ADM | 001 | CLOSED | 2233.952 | 0 | 560.514 | 560.514
PJ0003658 Total | [7 empty] | 38645.3498 | 0 | 12621.9907 | 12621.9907
PJ0003656 | INSTALL 6 PORT NETWORK FCPLT & OUTLET - BLD 48 RM 101B&48M | MAY, TOM | CLOSED | 2010-12-21 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 268.25 | 0 | 0 | 0
PJ0003656 | INSTALL 6 PORT NETWORK FCPLT & OUTLET - BLD 48 RM 101B&48M | MAY, TOM | CLOSED | 2010-12-21 | EO:DIG TRENCH FOR DATA LINE AT OH | 048 | CLOSED | 556.128 | 0 | 504.204 | 504.204
PJ0003656 | INSTALL 6 PORT NETWORK FCPLT & OUTLET - BLD 48 RM 101B&48M | MAY, TOM | CLOSED | 2010-12-21 | IN: INSTALL 6 PORT NETWORK FCPLT & OUTLET - BLD 48 RM 101B&48M | 048 | CLOSED | 64.056 | 0 | 64.056 | 64.056
PJ0003656 Total | [7 empty] | 888.434 | 0 | 568.26 | 568.26
PJ0003652 | FP 10/11: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | LAMPMAN, GREG | CLOSED | 2011-01-05 | AD: JOC 11.022.002 STAPLES | 112 | CLOSED | 50764.6 | 0 | 50764.6 | 50764.6
PJ0003652 | FP 10/11: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | LAMPMAN, GREG | CLOSED | 2011-01-05 | AD: RENGEL AND COMPANY ARCHITECTS | 112 | CLOSED | 10125 | 0 | 10551.62 | 10551.62
PJ0003652 | FP 10/11: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | LAMPMAN, GREG | CLOSED | 2011-01-05 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 0 | 0 | 0 | 0
PJ0003652 | FP 10/11: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | LAMPMAN, GREG | CLOSED | 2011-01-05 | IN: FP 10/11REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLDG 112 | 112 | CLOSED | 266.9 | 0 | 320.28 | 320.28
PJ0003652 | FP 10/11: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | LAMPMAN, GREG | CLOSED | 2011-01-05 | IN: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | 112 | CLOSED | 110.46 | 0 | 81.92 | 81.92
PJ0003652 | FP 10/11: REPLACE RAMP AT VG ENTRANCE, ADA COMPLIANT -BLD VG 112 | LAMPMAN, GREG | CLOSED | 2011-01-05 | LA: REMODEL LANDSCAPING - VISTA GRANDE ADA ENTRANCE RAMP | 112 | CLOSED | 36066.9574 | 0 | 4030 | 4030
PJ0003652 Total | [7 empty] | 97333.9174 | 0 | 65748.42 | 65748.42
PJ0003646 | CUSTODIAL BREAK ROOM CONVERSION - CERRO VISTA 170D | MAY, TOM | CLOSED | 2010-12-28 | CA:REMODEL CUSTODIAL BREAK ROOM AT CERRO VISTA | 170D | CLOSED | 2755.3596 | 0 | 3313.356 | 3313.356
PJ0003646 | CUSTODIAL BREAK ROOM CONVERSION - CERRO VISTA 170D | MAY, TOM | CLOSED | 2010-12-28 | CP: PROJECT CONTINGENCY | 170D | CLOSED | 321.4 | 0 | 0 | 0
PJ0003646 | CUSTODIAL BREAK ROOM CONVERSION - CERRO VISTA 170D | MAY, TOM | CLOSED | 2010-12-28 | IN: CUSTODIAL BREAK ROOM CONVERSION - CERRO VISTA 170D | 170D | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003646 | CUSTODIAL BREAK ROOM CONVERSION - CERRO VISTA 170D | MAY, TOM | CLOSED | 2010-12-28 | PL:RECONFIGURE SPRINKLERS IN CUSTODIAL BREAK ROOM CV | 170D | CLOSED | 874.8058 | 0 | 743.28 | 743.28
PJ0003646 Total | [7 empty] | 4017.8414 | 0 | 4122.912 | 4122.912
PJ0003645 | FLOOD REMEDIATION FISHER SCI & SCIENCE N. BLDGS 033 & 053(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-12-22 | CA:FLOOD REMEDIATION AT SCIENCE NORTH AND FISHER SCIENCE | 033 | CLOSED | 0 | 0 | 3068.85 | 3068.85
PJ0003645 | FLOOD REMEDIATION FISHER SCI & SCIENCE N. BLDGS 033 & 053(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-12-22 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0003645 | FLOOD REMEDIATION FISHER SCI & SCIENCE N. BLDGS 033 & 053(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-12-22 | CU:FLOOD REMEDIATION AT FISHER SCIENCE AND SCIENCE NORTH (N/L) | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0003645 | FLOOD REMEDIATION FISHER SCI & SCIENCE N. BLDGS 033 & 053(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-12-22 | PA:FLOOD REMEDIATION AT FISHER SCIENCE AND SCIENCE NORTH | 033 | CLOSED | 0 | 0 | 1763.42 | 1763.42
PJ0003645 | FLOOD REMEDIATION FISHER SCI & SCIENCE N. BLDGS 033 & 053(MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-12-22 | PL:FLOOD REMEDIATION AT FISHER SCIENCE AND SCIENCE NORTH | 033 | CLOSED | 0 | 0 | 6642.485 | 6642.485
PJ0003645 Total | [7 empty] | 0 | 0 | 11474.755 | 11474.755
PJ0003643 | PROVIDE AIR LINE & ELECTRICAL FOR PRINTING PRESSES -BLD 26-217 | MAY, TOM | CLOSED | 2010-12-16 | AD: THOMA ELECTRIC | 026 | CLOSED | 9621.868 | 0 | 9620.2202 | 9620.2202
PJ0003643 | PROVIDE AIR LINE & ELECTRICAL FOR PRINTING PRESSES -BLD 26-217 | MAY, TOM | CLOSED | 2010-12-16 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0003643 | PROVIDE AIR LINE & ELECTRICAL FOR PRINTING PRESSES -BLD 26-217 | MAY, TOM | CLOSED | 2010-12-16 | IN: PROVIDE AIR & ELECTRICAL FOR PRINTING PRESSES - BLD 26-217 | 026 | CLOSED | 66.276 | 0 | 64.056 | 64.056
PJ0003643 | PROVIDE AIR LINE & ELECTRICAL FOR PRINTING PRESSES -BLD 26-217 | MAY, TOM | CLOSED | 2010-12-16 | PL:INSTALL AIRLINE TO EQUIP IN 26-217 | 026 | CLOSED | 3345.053 | 0 | 2714.316 | 2714.316
PJ0003643 Total | [7 empty] | 13033.197 | 0 | 12398.5922 | 12398.5922
PJ0003642 | INSTALL MISSING FIRE RATED DOOR - ADMIN 01 RM 303 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-12-16 | CA:INSTALL NEW FIRE RATED DOOR IN ADMIN 303 | 001 | CLOSED | 819.2 | 0 | 265.775 | 265.775
PJ0003642 | INSTALL MISSING FIRE RATED DOOR - ADMIN 01 RM 303 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-12-16 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0003642 | INSTALL MISSING FIRE RATED DOOR - ADMIN 01 RM 303 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-12-16 | LO:INSTALL LOCK HARDWARE IN NEW DOOR AT ADMIN 303 | 001 | CLOSED | 385.28 | 0 | 606.74 | 606.74
PJ0003642 | INSTALL MISSING FIRE RATED DOOR - ADMIN 01 RM 303 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-12-16 | PA:PREP, STAIN, AND FINISH NEW DOOR FOR ADMIN 303 | 001 | CLOSED | 421.28 | 0 | 190.64 | 190.64
PJ0003642 Total | [7 empty] | 1625.76 | 0 | 1063.155 | 1063.155
PJ0003641 | PHASE II - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FLOOR | LAMPMAN, GREG | CLOSED | 2010-12-14 | AD: JOC 10.020.044.02 AND .05 | 192 | CLOSED | 12111.8115 | 0 | 12111.8115 | 12111.8115
PJ0003641 | PHASE II - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FLOOR | LAMPMAN, GREG | CLOSED | 2010-12-14 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 742.62 | 0 | 0 | 0
PJ0003641 | PHASE II - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FLOOR | LAMPMAN, GREG | CLOSED | 2010-12-14 | IN: PHASE II - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FLOOR | 192 | CLOSED | 265.104 | 0 | 165.69 | 165.69
PJ0003641 | PHASE II - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FLOOR | LAMPMAN, GREG | CLOSED | 2010-12-14 | ITS: DATA WIRING FOR DEAN'S COMPLEX BUILD OUT - PHASE II | 192 | CLOSED | 1912.88 | 0 | 1797.74 | 1797.74
PJ0003641 | PHASE II - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FLOOR | LAMPMAN, GREG | CLOSED | 2010-12-14 | PA: PAINT ROOM | 192 | CLOSED | 931.92 | 0 | 915.072 | 915.072
PJ0003641 Total | [7 empty] | 15964.3355 | 0 | 14990.3135 | 14990.3135
PJ0003640 | FP 10/11:PURCHASE/INSTALL BLUE LIGHT PHONE-GRAND AVE PARK STRUCT | MAY, TOM | CLOSED | 2010-12-15 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 0 | 0 | 0 | 0
PJ0003640 | FP 10/11:PURCHASE/INSTALL BLUE LIGHT PHONE-GRAND AVE PARK STRUCT | MAY, TOM | CLOSED | 2010-12-15 | EL: PURCHASE & INSTALL BLUE LIGHT PHONE-GRAND AVE PARKING STRUCT | 130 | CLOSED | 4935.3466 | 0 | 4646.635 | 4646.635
PJ0003640 | FP 10/11:PURCHASE/INSTALL BLUE LIGHT PHONE-GRAND AVE PARK STRUCT | MAY, TOM | CLOSED | 2010-12-15 | IN:PURCHASE/INSTALL BLUE LIGHT PHONE-GRAND AVE PARK STRUCT | 130 | CLOSED | 55.23 | 0 | 54.305 | 54.305
PJ0003640 Total | [7 empty] | 4990.5766 | 0 | 4700.94 | 4700.94
PJ0003639 | LAIR SWIMMING POOL PLUMBING & ELECTRICAL CONNECTIONS 4-115 | MAY, TOM | CLOSED | 2010-12-03 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 0.2 | 0 | 0 | 0
PJ0003639 | LAIR SWIMMING POOL PLUMBING & ELECTRICAL CONNECTIONS 4-115 | MAY, TOM | CLOSED | 2010-12-03 | EL:INSTALL (1) EXTERIOR OUTLET OUTSIDE 04-115 | 004 | CLOSED | 762.4159 | 0 | 305.196 | 305.196
PJ0003639 | LAIR SWIMMING POOL PLUMBING & ELECTRICAL CONNECTIONS 4-115 | MAY, TOM | CLOSED | 2010-12-03 | IN: LAIR SWIMMING POOL PLUMBING & ELECTRICAL CONNECTIONS 4-115 | 004 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003639 | LAIR SWIMMING POOL PLUMBING & ELECTRICAL CONNECTIONS 4-115 | MAY, TOM | CLOSED | 2010-12-03 | PL: ASSIST WITH POOL FILL UP AT 04-115 | 004 | CLOSED | 82.6488 | 0 | 540.396 | 540.396
PJ0003639 Total | [7 empty] | 911.5407 | 0 | 911.868 | 911.868
PJ0003638 | SEAL OFF DOORS TO SOUND PROOF OFFICES - BLD 53-205, 210C/E/F/G | MAY, TOM | CLOSED | 2010-12-07 | CA:SOUNDPROOF TWO DOORS IN 53 | 053 | CLOSED | 1183.2288 | 0 | 1001.076 | 1001.076
PJ0003638 | SEAL OFF DOORS TO SOUND PROOF OFFICES - BLD 53-205, 210C/E/F/G | MAY, TOM | CLOSED | 2010-12-07 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 118.35 | 0 | 0 | 0
PJ0003638 Total | [7 empty] | 1301.5788 | 0 | 1001.076 | 1001.076
PJ0003637 | IN-HOUSE SUPPORT:T-MOBILE CELLULAR SITE ON WHEELS(COW) - R-1 LOT | MOLLAN, CHERYL L. | CLOSED | 2010-12-10 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 1068.09 | 0 | 0 | 0
PJ0003637 | IN-HOUSE SUPPORT:T-MOBILE CELLULAR SITE ON WHEELS(COW) - R-1 LOT | MOLLAN, CHERYL L. | CLOSED | 2010-12-10 | EL:SUPPLY AND INSTALL ELECTRICAL FOR T-MOBILE COW | P-R01 | CLOSED | 9880.7786 | 0 | 8106.1687 | 8106.1687
PJ0003637 | IN-HOUSE SUPPORT:T-MOBILE CELLULAR SITE ON WHEELS(COW) - R-1 LOT | MOLLAN, CHERYL L. | CLOSED | 2010-12-10 | EO:PROVIDE SUPPORT AS NEEDED TO ELECTRICIANS FOR NEW POLE | P-R01 | CLOSED | 610.8139 | 0 | 231.72 | 231.72
PJ0003637 | IN-HOUSE SUPPORT:T-MOBILE CELLULAR SITE ON WHEELS(COW) - R-1 LOT | MOLLAN, CHERYL L. | CLOSED | 2010-12-10 | IN: T-MOBILE CELLULAR SITE ON WHEELS(COW) - R-1 LOT | P-R01 | CLOSED | 132.552 | 0 | 231.966 | 231.966
PJ0003637 | IN-HOUSE SUPPORT:T-MOBILE CELLULAR SITE ON WHEELS(COW) - R-1 LOT | MOLLAN, CHERYL L. | CLOSED | 2010-12-10 | LO:PROVIDE LOCK FOR ELECTRICAL PANEL AT R-Q LOT FOR CELL TOWER | P-R01 | CLOSED | 57.168 | 0 | 123.168 | 123.168
PJ0003637 Total | [7 empty] | 11749.4026 | 0 | 8693.0227 | 8693.0227
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | AD: QUARESMA DRYWALL | 045 | CLOSED | 1881.06 | 0 | 1896.575 | 1896.575
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | AD: STAPLES CONSTRUCTION | 045 | CLOSED | 3275.3021 | 0 | 3177.9 | 3177.9
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | AD: VISALIA TILE | 045 | CLOSED | 787.52 | 0 | 787.52 | 787.52
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | CA: REPAIR FLOOR TILE & INSTALL COVEBASE - BLDG. 45 RM. 105 | 045 | CLOSED | 217.164 | 0 | 248.064 | 248.064
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 1.75 | 0 | 0 | 0
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | CU: CLEAN ALL SURFACES BLDG 45 ROOM 105 | 045 | CLOSED | 65.592 | 0 | 49.194 | 49.194
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | EL: ASSIST WITH ELECTRICAL SHUT-DOWN FOR WASHER/DRYER INSTALL | 045 | CLOSED | 134.832 | 0 | 67.416 | 67.416
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | ES:INSTALL VENT DUCTWORK FOR DRYERS | 045 | CLOSED | 814.9127 | 0 | 1004.7128 | 1004.7128
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | IN: INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | 045 | CLOSED | 128.112 | 0 | 192.168 | 192.168
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | PA:PAINT NEW CHASE WALL ROOM 105, MUSIC BLDG | 045 | CLOSED | 648.3396 | 0 | 851.25 | 851.25
PJ0003636 | INSTALL NEW WASHER AND DRYERS - BLDG 45-105 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | PL:INSTALL NEW HOT WATER HEATER AND RELOCATE PLUMBING | 045 | CLOSED | 5482.2994 | 0 | 4050.762 | 4050.762
PJ0003636 Total | [7 empty] | 13436.8837 | 0 | 12325.5618 | 12325.5618
PJ0003635 | MOUNT DINING PATIO TABLES AT LOWER UU PLAZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-12-07 | CA: INSTALL TABLES | 065 | CLOSED | 1036.08 | 0 | 200.136 | 200.136
PJ0003635 | MOUNT DINING PATIO TABLES AT LOWER UU PLAZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-12-07 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 116.86 | 0 | 0 | 0
PJ0003635 | MOUNT DINING PATIO TABLES AT LOWER UU PLAZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-12-07 | IN: MOUNT DINING PATIO TABLES AT LOWER UU PLAZA | 065 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003635 Total | [7 empty] | 1285.492 | 0 | 332.688 | 332.688
PJ0003634 | PROVIDE HEATING TO TECH ROOM - BLD 11 RM 301 | MAY, TOM | CLOSED | 2010-11-30 | AD: RICK TEIXEIRA WELDING | 011 | CLOSED | 749 | 0 | 749 | 749
PJ0003634 | PROVIDE HEATING TO TECH ROOM - BLD 11 RM 301 | MAY, TOM | CLOSED | 2010-11-30 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 463.61 | 0 | 0 | 0
PJ0003634 | PROVIDE HEATING TO TECH ROOM - BLD 11 RM 301 | MAY, TOM | CLOSED | 2010-11-30 | ES:INSTALL HEATING UNIT IN 11-301 | 011 | CLOSED | 3820.7842 | 0 | 2726.3429 | 2726.3429
PJ0003634 | PROVIDE HEATING TO TECH ROOM - BLD 11 RM 301 | MAY, TOM | CLOSED | 2010-11-30 | IN: PROVIDE HEATING TO TECH ROOM - BLD 11 RM 301 | 011 | CLOSED | 66.276 | 0 | 64.056 | 64.056
PJ0003634 Total | [7 empty] | 5099.6702 | 0 | 3539.3989 | 3539.3989
PJ0003633 | REMOVE X-RAY VIEWING BOX - BLD 27A RM 192 | GRIFFIN, PATRICK E | CLOSED | 2010-12-06 | CP: PROJECT CONTINGENCY | 027A | CLOSED | 60.5 | 0 | 0 | 0
PJ0003633 | REMOVE X-RAY VIEWING BOX - BLD 27A RM 192 | GRIFFIN, PATRICK E | CLOSED | 2010-12-06 | EL:REVIEW X-RAY VIEWING BOX IN HEALTH CENTER 192 | 027A | CLOSED | 63.444 | 0 | 95.166 | 95.166
PJ0003633 | REMOVE X-RAY VIEWING BOX - BLD 27A RM 192 | GRIFFIN, PATRICK E | CLOSED | 2010-12-06 | PA:PREP AND PAINT WALLS AND CEILING IN HEALTH CENTER 192 | 027A | CLOSED | 541.536 | 0 | 379.152 | 379.152
PJ0003633 Total | [7 empty] | 665.48 | 0 | 474.318 | 474.318
PJ0003632 | PEMIT: T-MOBILE CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | HOGAN, MIKE | CLOSED | 2010-12-06 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 0 | 0 | 0 | 0
PJ0003632 | PEMIT: T-MOBILE CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | HOGAN, MIKE | CLOSED | 2010-12-06 | IN: BUILDING PERMIT FEES | P-R01 | CLOSED | 201.1 | 0 | 201.1 | 201.1
PJ0003632 | PEMIT: T-MOBILE CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | HOGAN, MIKE | CLOSED | 2010-12-06 | IN: PLAN REVIEW FEES | P-R01 | CLOSED | 178.98 | 0 | 178.98 | 178.98
PJ0003632 | PEMIT: T-MOBILE CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | HOGAN, MIKE | CLOSED | 2010-12-06 | IN: STATE FIRE MARSHAL FEES | P-R01 | CLOSED | 160 | 0 | 0 | 0
PJ0003632 | PEMIT: T-MOBILE CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | HOGAN, MIKE | CLOSED | 2010-12-06 | IN:(MAINT) T-MOBILE CELLULAR SITE ON WHEELS (COW)R-1 PARKING LOT | P-R01 | CLOSED | 0 | 0 | 441.84 | 441.84
PJ0003632 Total | [7 empty] | 540.08 | 0 | 821.92 | 821.92
PJ0003631 | REMOVE CONCRETE RAMP FROM CULVERT-HIGHLAND NEAR CROPS (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-12-03 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003631 | REMOVE CONCRETE RAMP FROM CULVERT-HIGHLAND NEAR CROPS (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-12-03 | EO: REMOVE CONCRETE RAMPS UNDER HIGHLAND | GENERAL | CLOSED | 308.96 | 0 | 219.27 | 219.27
PJ0003631 Total | [7 empty] | 308.96 | 0 | 219.27 | 219.27
PJ0003630 | SR 11/12: FURNISH NEW LECTURE ROOM - BLD 38 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | AD: VIRCO (DIRECT-PAY) | 038 | CLOSED | 2000 | 0 | 1797.54 | 1797.54
PJ0003630 | SR 11/12: FURNISH NEW LECTURE ROOM - BLD 38 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003630 | SR 11/12: FURNISH NEW LECTURE ROOM - BLD 38 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | CU:CLEAN TAB ARM CHAIRS FOR ROOM 204, BLDG. 38 | 038 | CLOSED | 577.4829 | 0 | 54.66 | 54.66
PJ0003630 | SR 11/12: FURNISH NEW LECTURE ROOM - BLD 38 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | IN: FURNISH NEW LECTURE ROOM - BLD 38 RM 204 (N/L) | 038 | CLOSED | 53.38 | 0 | 0 | 0
PJ0003630 | SR 11/12: FURNISH NEW LECTURE ROOM - BLD 38 RM 204 | MOLLAN, CHERYL L. | CLOSED | 2010-12-02 | MO:MOVE TAB ARM CHAIRS AND TABLE FROM E-SURPLUS TO 38, RM 204 | 038 | CLOSED | 540 | 0 | 110.66 | 110.66
PJ0003630 Total | [7 empty] | 3170.8629 | 0 | 1962.86 | 1962.86
PJ0003627 | ELECT OUTLETS FOR NEW PRINTERS - BLD 26 RM 213A | MAY, TOM | CLOSED | 2010-11-30 | AD: THOMA ELECTRIC | 026 | CLOSED | 2937.15 | 0 | 1207.7625 | 1207.7625
PJ0003627 | ELECT OUTLETS FOR NEW PRINTERS - BLD 26 RM 213A | MAY, TOM | CLOSED | 2010-11-30 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 297.03 | 0 | 0 | 0
PJ0003627 | ELECT OUTLETS FOR NEW PRINTERS - BLD 26 RM 213A | MAY, TOM | CLOSED | 2010-11-30 | IN: ELECT OUTLETS FOR NEW PRINTERS - BLD 26 RM 213A | 026 | CLOSED | 33.138 | 0 | 66.276 | 66.276
PJ0003627 Total | [7 empty] | 3267.318 | 0 | 1274.0385 | 1274.0385
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: APC CONTRACTORS | 001 | CLOSED | 4584.6611 | 0 | 2341.16 | 2341.16
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: BKM FURNITURE | 001 | CLOSED | 31236.3709 | 0 | 30452.093 | 30452.093
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: INNOVATION FLOORING | 001 | CLOSED | 2551.95 | 0 | 2550.3664 | 2550.3664
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: J.L. FASULO DRYWALL | 001 | CLOSED | 8034.3411 | 0 | 5554.3593 | 5554.3593
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: MAINO CONSTRUCTION (LOW VALUE PUBLIC WORKS) | 001 | CLOSED | 2086.5 | 0 | 2086.5 | 2086.5
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: MCKENNA ENVIRONMENTAL | 001 | CLOSED | 729.74 | 0 | 729.74 | 729.74
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | AD: TEMPLE BUILDERS | 001 | CLOSED | 1868.541 | 0 | 1790.3775 | 1790.3775
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | CA:INSTALL COVEBASE AND HANG WHITEBOARD ADM 216/217 | 001 | CLOSED | 4352.7798 | 0 | 2713.866 | 2713.866
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 111.07 | 0 | 0 | 0
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | EH&S: SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (N/L) | 001 | CLOSED | 605.715 | 0 | 0 | 0
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | EL:ASSIST WITH REMODEL IN ADM 213A/215 | 001 | CLOSED | 2100.6802 | 0 | 3123.108 | 3123.108
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | ES:MOVE TSTAT IN ADM 215 | 001 | CLOSED | 1412.4767 | 0 | 798.924 | 798.924
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | IN: SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR | 001 | CLOSED | 512.448 | 0 | 160.14 | 160.14
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | LO: ASSIST IN REMODAL OF ADMIN 215 | 001 | CLOSED | 1974.8874 | 0 | 652.554 | 652.554
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | MO: MOVE FURNITURE IN ADM 215 | 001 | CLOSED | 259.2 | 0 | 108.648 | 108.648
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | PA: PAINT ADMIN 213A, 215, AND 217 - BLDG. 01 | 001 | CLOSED | 5349.12 | 0 | 2858.508 | 2858.508
PJ0003626 | SECOND FLOOR RENOVATION - ADMIN 2ND FLOOR (ACADEMIC AFFAIRS) | GONZALES, ALBERT M. | CLOSED | 2010-11-30 | PA: PROJECT SUPPORT FOR THE MOVING OF THREE OFFICES | 001 | CLOSED | 2942.2916 | 0 | 808.368 | 808.368
PJ0003626 Total | [7 empty] | 70712.7728 | 0 | 56728.7122 | 56728.7122
PJ0003625 | REMOVE SHELVES, PATCH & PAINT 1ST FLR SEE ATTCH MAP-BLD 35-111 | MAY, TOM | CLOSED | 2010-11-29 | CA:REMOVE SHELF BRACKETS IN SEVERAL LOCATIONS IN 35-111 | 035 | CLOSED | 126.8202 | 0 | 243.792 | 243.792
PJ0003625 | REMOVE SHELVES, PATCH & PAINT 1ST FLR SEE ATTCH MAP-BLD 35-111 | MAY, TOM | CLOSED | 2010-11-29 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 65.18 | 0 | 0 | 0
PJ0003625 | REMOVE SHELVES, PATCH & PAINT 1ST FLR SEE ATTCH MAP-BLD 35-111 | MAY, TOM | CLOSED | 2010-11-29 | PA:PATCH/PAINT SEVERAL LOCATIONS IN 35-111 FROM SHELF REMOVALS | 035 | CLOSED | 525.0226 | 0 | 586.728 | 586.728
PJ0003625 Total | [7 empty] | 717.0228 | 0 | 830.52 | 830.52
PJ0003623 | PAINT, CEILING TILES &LIGHTING - PERMIT, ONLY-BLD 21 RMS 21 & 18 | LAMPMAN, GREG | CLOSED | 2010-11-29 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0003623 | PAINT, CEILING TILES &LIGHTING - PERMIT, ONLY-BLD 21 RMS 21 & 18 | LAMPMAN, GREG | CLOSED | 2010-11-29 | IN: (MAINT)PAINT, NEW CEILING TILES & LIGHTING -BLD 21 RMS 21&18 | 021 | CLOSED | 0 | 0 | 160.14 | 160.14
PJ0003623 Total | [7 empty] | 0 | 0 | 160.14 | 160.14
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | AD: JOC 10.021.003 STAPLES | 036 | CLOSED | 25000.0043 | 0 | 24908.9687 | 24908.9687
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | AD: JOC 10.021.017 STAPLES | 036 | CLOSED | 38116.4816 | 0 | 37884.8908 | 37884.8908
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | AD: MECA | 036 | CLOSED | 5216.25 | 0 | 3265.7684 | 3265.7684
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | AD: REIMBURSE KINESIOLOGY FOR BOAT TRAILER MODS (DIRECT PAY) | 036 | CLOSED | 440.97 | 0 | 440.97 | 440.97
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | CA: INSTALL HARDWARE BLDG 42A | 042A | CLOSED | 1145.82 | 0 | 1096.83 | 1096.83
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 964.94 | 0 | 0 | 0
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | EL ELECTRICAL CLEARANCE AND | 036 | CLOSED | 8075.52 | 0 | 4754.424 | 4754.424
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | IN: HAZ MAT REMEDIATION AND TENNANT RELOCATION - BLD 36 | 036 | CLOSED | 384.336 | 0 | 256.224 | 256.224
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | LO: CHANGE CORES FOR UPD OFFICE RELOCATION - BLDG 36 | 036 | CLOSED | 528.672 | 0 | 114.774 | 114.774
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | MO: PROJECT SUPPORT BLDG 36 UPD RELOCATION | 036 | CLOSED | 630 | 0 | 212.34 | 212.34
PJ0003622 | SP 11/12: HAZ MAT REMEDIATION AND TENANT RELOCATION - BLD 36 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-29 | PL: CAP GAS PIPES | 036 | CLOSED | 6814.56 | 0 | 127.152 | 127.152
PJ0003622 Total | [7 empty] | 87317.5539 | 0 | 73062.3419 | 73062.3419
PJ0003621 | STATE FIRE MARSHAL INSPECTION CORRECTIONS - 001 5TH FLR (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | CA: INSTALL DRYWALL ON PLYWOOD STORAGE PARTITIONS | 001 | CLOSED | 0 | 0 | 6423.21 | 6423.21
PJ0003621 | STATE FIRE MARSHAL INSPECTION CORRECTIONS - 001 5TH FLR (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0003621 Total | [7 empty] | 0 | 0 | 6423.21 | 6423.21
PJ0003620 | DESIGN SERVICES FOR UU OFFICES, LOUNGE, TV LOUNGE& RM206 -BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2010-11-22 | AD: OMNI DESIGN | 065 | CLOSED | 15268.9 | 0 | 8335.3 | 8335.3
PJ0003620 | DESIGN SERVICES FOR UU OFFICES, LOUNGE, TV LOUNGE& RM206 -BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2010-11-22 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003620 Total | [7 empty] | 15268.9 | 0 | 8335.3 | 8335.3
PJ0003619 | ROOM REPAIR & PAINT - BLD 10 RM 138 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | CA:REMOVE CHALKBOARD AND WOODEN SLATS ETC. | 010 | CLOSED | 1990.4172 | 0 | 573.612 | 573.612
PJ0003619 | ROOM REPAIR & PAINT - BLD 10 RM 138 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 626.74 | 0 | 0 | 0
PJ0003619 | ROOM REPAIR & PAINT - BLD 10 RM 138 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | CU: STRIP/WAX FLOOR IN REMODELED WRITING LAB 10-138 | 010 | CLOSED | 150.5336 | 0 | 150.48 | 150.48
PJ0003619 | ROOM REPAIR & PAINT - BLD 10 RM 138 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | IN: ROOM REPAIR & PAINT - BLD 10 RM 138 DEC 13-17 | 010 | CLOSED | 66.276 | 0 | 33.138 | 33.138
PJ0003619 | ROOM REPAIR & PAINT - BLD 10 RM 138 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | LO:REPLACE EXISTING HANDELS WITH ADA COMPLIANT HANDELS | 010 | CLOSED | 2377.344 | 0 | 1506.312 | 1506.312
PJ0003619 | ROOM REPAIR & PAINT - BLD 10 RM 138 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | PA:PAINT WALLS WHERE CHALKBOARD AND WOODEN STRIPS WERE REMOVED | 010 | CLOSED | 1518.2412 | 0 | 1450.224 | 1450.224
PJ0003619 Total | [7 empty] | 6729.552 | 0 | 3713.766 | 3713.766
PJ0003618 | BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC (MAINT) | GALVEZ, CESAR | CLOSED | 2010-11-23 | CA: REPLACE CONCRETE FOR IRRIGATION VALVE PROJECT NEAR MUSIC | GENERAL | CLOSED | 0 | 0 | 684.65 | 684.65
PJ0003618 | BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC (MAINT) | GALVEZ, CESAR | CLOSED | 2010-11-23 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003618 | BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC (MAINT) | GALVEZ, CESAR | CLOSED | 2010-11-23 | EO: BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC | GENERAL | CLOSED | 0 | 0 | 617.92 | 617.92
PJ0003618 | BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC (MAINT) | GALVEZ, CESAR | CLOSED | 2010-11-23 | LA: BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC(N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003618 | BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC (MAINT) | GALVEZ, CESAR | CLOSED | 2010-11-23 | PL: BROKEN IRRIGATION VALVE - TAHOE NEXT TO MUSIC | GENERAL | CLOSED | 0 | 0 | 706.29 | 706.29
PJ0003618 Total | [7 empty] | 0 | 0 | 2008.86 | 2008.86
PJ0003616 | CUSTODIAL STORAGE IMPROVEMENTS - BLDG 50J RM 004 (NO ESTM) | MAY, TOM | CLOSED | 2010-11-22 | CA: | 050J | CLOSED | 0 | 0 | 46.15 | 46.15
PJ0003616 | CUSTODIAL STORAGE IMPROVEMENTS - BLDG 50J RM 004 (NO ESTM) | MAY, TOM | CLOSED | 2010-11-22 | CP: PROJECT CONTINGENCY | 050J | CLOSED | 0 | 0 | 0 | 0
PJ0003616 | CUSTODIAL STORAGE IMPROVEMENTS - BLDG 50J RM 004 (NO ESTM) | MAY, TOM | CLOSED | 2010-11-22 | EL:INSTALL OUTLETS (N/L) | 050J | CLOSED | 0 | 0 | 17.22 | 17.22
PJ0003616 | CUSTODIAL STORAGE IMPROVEMENTS - BLDG 50J RM 004 (NO ESTM) | MAY, TOM | CLOSED | 2010-11-22 | ES:RELOCATE VENT | 050J | CLOSED | 0 | 0 | 1794.62 | 1794.62
PJ0003616 Total | [7 empty] | 0 | 0 | 1857.99 | 1857.99
PJ0003615 | REPLACE ROTTEN DOOR -CHORRO CREEK RESTROOM BEHIND BARN (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2010-11-19 | CA: REPLACE ROTTEN DOOR - CHORRO CREEK RESTROOM BEHIND BARN | 126A | CLOSED | 0 | 0 | 1049.525 | 1049.525
PJ0003615 | REPLACE ROTTEN DOOR -CHORRO CREEK RESTROOM BEHIND BARN (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2010-11-19 | CP: PROJECT CONTINGENCY | 126A | CLOSED | 0 | 0 | 0 | 0
PJ0003615 | REPLACE ROTTEN DOOR -CHORRO CREEK RESTROOM BEHIND BARN (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2010-11-19 | LO: INSTALL LOCK ON NEW RESTROOM DOOR BEHIND BARN | 126A | CLOSED | 0 | 0 | 387.02 | 387.02
PJ0003615 | REPLACE ROTTEN DOOR -CHORRO CREEK RESTROOM BEHIND BARN (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2010-11-19 | PA:PAINT NEW DOORS AND JAMBS | 126A | CLOSED | 0 | 0 | 571.92 | 571.92
PJ0003615 Total | [7 empty] | 0 | 0 | 2008.465 | 2008.465
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | AD: QUARESMA DRYWALL | 045 | CLOSED | 1016.5 | 0 | 1024.2575 | 1024.2575
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | AD: SANTA MARIA ACOUSTICAL | 045 | CLOSED | 2102.9673 | 0 | 2102.9673 | 2102.9673
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | CA:INSTALL NEW DOOR IN EXISTING WALL, CONSTRUCT NEW WALL | 045 | CLOSED | 4224.6126 | 0 | 4929.6738 | 4929.6738
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 49.44 | 0 | 0 | 0
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | EH&S: RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104` (N/L) | 045 | CLOSED | 129.792 | 0 | 130.8 | 130.8
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | EL:DISCONNECT ELECTRICAL- INSTALL NEW - BLDG 45, 102-104 | 045 | CLOSED | 4779.6907 | 0 | 2452.818 | 2452.818
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | ES:ADD NEW DUCTWORK FOR SUPPLY/RETURN FOR DIVIDED OFFICES | 045 | CLOSED | 2233.08 | 0 | 2612.676 | 2612.676
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | IN: RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | 045 | CLOSED | 198.828 | 0 | 129.222 | 129.222
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | LO:SUPPLY AND INSTALL NEW LEVER HANDELS PER PLAN | 045 | CLOSED | 4582.1462 | 0 | 3430.728 | 3430.728
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | MO: MOVE OFFICE FURNITURE - BLDG. 45 RMS 102, 103, 104 | 045 | CLOSED | 388.8 | 0 | 253.512 | 253.512
PJ0003611 | RECONFIGURE OFFICE SPACE - 45 RMS 102, 103, 104 | MOLLAN, CHERYL L. | CLOSED | 2010-11-17 | PA:PATCH AND PAINT EXISTING AND PAINT NEW WALL- PAINT NEW DOOR | 045 | CLOSED | 3839.6645 | 0 | 2816.892 | 2816.892
PJ0003611 Total | [7 empty] | 23545.5213 | 0 | 19883.5466 | 19883.5466
PJ0003609 | WASH WINDOWS - BLD 124 RM 117 | LOOSLEY, SCOTT L. | CLOSED | 2010-10-27 | AD: COASTAL JANITORIAL | 124 | CLOSED | 518.95 | 0 | 518.95 | 518.95
PJ0003609 | WASH WINDOWS - BLD 124 RM 117 | LOOSLEY, SCOTT L. | CLOSED | 2010-10-27 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 51.9 | 0 | 0 | 0
PJ0003609 Total | [7 empty] | 570.85 | 0 | 518.95 | 518.95
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | AD: WAREHOUSE MATERIALS TO BE USED BY CONTRACTOR | GENERAL | CLOSED | 0 | 0 | 302.5868 | 302.5868
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | CA: 24 EA 12X12 CEILING TILE - BLG 2 (MATERIAL ONLY) (N/L) | GENERAL | CLOSED | 0 | 0 | 75.168 | 75.168
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2517.87 | 0 | 0 | 0
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | CPE: SUPPORT FOR CHEVRON PROJECT PHASE II - BLDS. 2 & 3 | GENERAL | CLOSED | 1280.64 | 0 | 73.44 | 73.44
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | EH&S: SUPPORT FOR CHEVRON ENERGY PROJECT PHASE II - BLDGS. 2 & 3 | GENERAL | CLOSED | 2238.336 | 0 | 324.48 | 324.48
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | EL: SUPPORT FOR CHEVRON PROJECT PHASE II - BLDS. 2 & 3 | GENERAL | CLOSED | 1268.88 | 0 | 1237.158 | 1237.158
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | ES: SUPPORT FOR CHEVRON PROJECT PHASE II - BLDS. 2 & 3 | GENERAL | CLOSED | 13024.3507 | 0 | 2810.808 | 2810.808
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | IN: SUPPORT FOR CHEVRON ENERGY PROJECT PHASE II - BLGS. 2 & 3 | GENERAL | CLOSED | 1060.416 | 0 | 1126.692 | 1126.692
PJ0003608 | MJ: FACILITIES SUPPORT-CHEVRON ENERGY PROJECT PHASE II -BLDS 2&3 | ELLIOT, DENNIS K | CLOSED | 2010-11-16 | PA: SUPPORT FOR CHEVRON PROJECT PHASE II - BLDS. 2 & 3 | GENERAL | CLOSED | 1143.84 | 0 | 1802.964 | 1802.964
PJ0003608 Total | [7 empty] | 22534.3327 | 0 | 7753.2968 | 7753.2968
PJ0003607 | FP 10/11: DESIGN WORK AT MEMORIAL PLAZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-16 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003607 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003606 | FACS SUPPORT TO BRIDGE GALLERY STUDENT PROJECT- 21-133A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | CA: INSTALL NAILER RAILS IN BRIDGE GALLERY 21-133A | 021 | CLOSED | 2272.446 | 0 | 957.456 | 957.456
PJ0003606 | FACS SUPPORT TO BRIDGE GALLERY STUDENT PROJECT- 21-133A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 330.95 | 0 | 0 | 0
PJ0003606 | FACS SUPPORT TO BRIDGE GALLERY STUDENT PROJECT- 21-133A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | IN: FACS SUPPORT TO BRIDGE GALLERY STUDENT PROJECT- 21-133A | 021 | CLOSED | 192.168 | 0 | 192.168 | 192.168
PJ0003606 | FACS SUPPORT TO BRIDGE GALLERY STUDENT PROJECT- 21-133A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | PA: PAINT EAST AND WEST WALLS | 021 | CLOSED | 1229.4732 | 0 | 588.48 | 588.48
PJ0003606 Total | [7 empty] | 4025.0372 | 0 | 1738.104 | 1738.104
PJ0003605 | T-MOBILE WIRELESS FACILITY INSTALLATION ON RADIO HILL -BLDG 208U | HOGAN, MIKE | CLOSED | 2010-11-15 | AD: ENGLEKIRK - SEISMIC PEER REVIEW | 208U | CLOSED | 500 | 0 | 500 | 500
PJ0003605 | T-MOBILE WIRELESS FACILITY INSTALLATION ON RADIO HILL -BLDG 208U | HOGAN, MIKE | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | 208U | CLOSED | 0 | 0 | 0 | 0
PJ0003605 | T-MOBILE WIRELESS FACILITY INSTALLATION ON RADIO HILL -BLDG 208U | HOGAN, MIKE | CLOSED | 2010-11-15 | IN: (MAINT) T-MOBILE POLE INSTALLATION ON RADIO HILL - BLDG 208U | 208U | CLOSED | 0 | 0 | 1021.755 | 1021.755
PJ0003605 | T-MOBILE WIRELESS FACILITY INSTALLATION ON RADIO HILL -BLDG 208U | HOGAN, MIKE | CLOSED | 2010-11-15 | IN: BUILDING PERMIT FEES | 208U | CLOSED | 863.1 | 0 | 863.1 | 863.1
PJ0003605 | T-MOBILE WIRELESS FACILITY INSTALLATION ON RADIO HILL -BLDG 208U | HOGAN, MIKE | CLOSED | 2010-11-15 | IN: PLAN REVIEW FEES | 208U | CLOSED | 786.16 | 0 | 786.16 | 786.16
PJ0003605 | T-MOBILE WIRELESS FACILITY INSTALLATION ON RADIO HILL -BLDG 208U | HOGAN, MIKE | CLOSED | 2010-11-15 | IN: STATE FIRE MARSHAL FEES | 208U | CLOSED | 320 | 0 | 0 | 0
PJ0003605 Total | [7 empty] | 2469.26 | 0 | 3171.015 | 3171.015
PJ0003604 | SP 10/11: DESIGN SERVICES FOR VIA CARTA BIKE/CART/PEDESTRIAN WAY | LAMPMAN, GREG | CLOSED | 2010-11-15 | AD: WALLACE GROUP | GENERAL | CLOSED | 49128 | 0 | 45240.67 | 45240.67
PJ0003604 | SP 10/11: DESIGN SERVICES FOR VIA CARTA BIKE/CART/PEDESTRIAN WAY | LAMPMAN, GREG | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003604 Total | [7 empty] | 49128 | 0 | 45240.67 | 45240.67
PJ0003603 | FP 10/11: REMEDIATE MISCELLANEOUS ADA ISSUES | LAMPMAN, GREG | CLOSED | 2010-11-15 | AD: WALLACE GROUP | GENERAL | CLOSED | 41800 | 0 | 42958.03 | 42958.03
PJ0003603 | FP 10/11: REMEDIATE MISCELLANEOUS ADA ISSUES | LAMPMAN, GREG | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003603 Total | [7 empty] | 41800 | 0 | 42958.03 | 42958.03
PJ0003602 | FP 10/11: DESIGN FOR PAVERS BETWEEN ARCH, EDUC, & ENG WEST | MOLLAN, CHERYL L. | CLOSED | 2010-11-15 | AD: BFGC - IB GROUP ARCHITECTURE PLANNING | GENERAL | CLOSED | 15000 | 0 | 7368.75 | 7368.75
PJ0003602 | FP 10/11: DESIGN FOR PAVERS BETWEEN ARCH, EDUC, & ENG WEST | MOLLAN, CHERYL L. | CLOSED | 2010-11-15 | AD: WALLACE GROUP | GENERAL | CLOSED | 4200 | 0 | 3510 | 3510
PJ0003602 | FP 10/11: DESIGN FOR PAVERS BETWEEN ARCH, EDUC, & ENG WEST | MOLLAN, CHERYL L. | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003602 Total | [7 empty] | 19200 | 0 | 10878.75 | 10878.75
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: COASTAL DEMO | 061 | CLOSED | 2400 | 0 | 2400 | 2400
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: EARTH SYSTEMS | 061 | CLOSED | 3000 | 0 | 1607.41 | 1607.41
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: ENGLEKIRK AND SABOL | 061 | CLOSED | 1017 | 0 | 1017 | 1017
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: HAYER CONSULTING | 061 | CLOSED | 1385 | 0 | 1385 | 1385
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: JOC 11.023.021 STAPLES | 061 | CLOSED | 126912.55 | 0 | 114507.83 | 114507.83
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: JOC 12.024.011 STAPLES | 061 | CLOSED | 31089.56 | 0 | 40264.99 | 40264.99
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: RENGEL & COMPANY, ARCHITECTS | 061 | CLOSED | 35060 | 0 | 35181.74 | 35181.74
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: SHIPPING CHARGES (TO ENGLEKIRK AND HAYER) | 061 | CLOSED | 0 | 0 | 31.59 | 31.59
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: WALLACE GROUP | 061 | CLOSED | 1400 | 0 | 1107.5 | 1107.5
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | CA: RELOCATE STOP SIGN | 061 | CLOSED | 0 | 0 | 291.03 | 291.03
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | CU: SET UP A-FRAME BARRICADES AT SPANOS TICKET WINDOW - 061 | 061 | CLOSED | 437.28 | 0 | 56.9785 | 56.9785
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | EL: RELOCATE STREET LIGHT CONDUIT - TICKET BOOTH ADA PROJECT 061 | 061 | CLOSED | 524.72 | 0 | 1210.98 | 1210.98
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | EO: BREAK UP CONCRETE FOOTING - SPANOS TICKET BOOTH PROJECT | 061 | CLOSED | 331.76 | 0 | 369.7 | 369.7
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | IN: FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | 061 | CLOSED | 213.52 | 0 | 1201.05 | 1201.05
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | LA: RELOCATE SPRINKLER FOR SPANOS TICKET BOOTH PROJECT | 061 | CLOSED | 294.82 | 0 | 64.94 | 64.94
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | LO: PROVIDE LOCKS FOR GATES AT SPANOS TICKET BOOTH - 061 | 061 | CLOSED | 150 | 0 | 359.185 | 359.185
PJ0003601 | FP 10/11: RENOVATE TICKET BOOTH FOR ADA COMPLIANCE | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | PA: PAINT STEEL FRAMEWORK AND PIPE RAILINGS - SPANOS TICKET LINE | 061 | CLOSED | 4207.6 | 0 | 1765.64 | 1765.64
PJ0003601 Total | [7 empty] | 208423.81 | 0 | 202822.5635 | 202822.5635
PJ0003600 | FP 10/11: ESTIMATING SERVICES AT SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | AD: DAVIS LANGDON ESTIMATING | 061 | CLOSED | 14000 | 0 | 13441.77 | 13441.77
PJ0003600 | FP 10/11: ESTIMATING SERVICES AT SPANOS STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-15 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003600 Total | [7 empty] | 14000 | 0 | 13441.77 | 13441.77
PJ0003599 | INSTALL FIBER OPTIC CABLE BETWEEN 13-105 & 41-116 | MAY, TOM | CLOSED | 2010-11-05 | AD: JOC 10.020.047 STAPLES | 013 | CLOSED | 10906.6705 | 0 | 10906.6705 | 10906.6705
PJ0003599 | INSTALL FIBER OPTIC CABLE BETWEEN 13-105 & 41-116 | MAY, TOM | CLOSED | 2010-11-05 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 1097.3 | 0 | 0 | 0
PJ0003599 | INSTALL FIBER OPTIC CABLE BETWEEN 13-105 & 41-116 | MAY, TOM | CLOSED | 2010-11-05 | IN: INSTALL FIBER OPTIC CABLE BETWEEN 13-105 & 41-116 | 013 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003599 Total | [7 empty] | 12070.2465 | 0 | 10972.9465 | 10972.9465
PJ0003598 | ENCLOSE DOORWAY BETWEEN 114A & 115B - BLD 14 | MAY, TOM | CLOSED | 2010-11-10 | CA:FILL IN DOORWAYS IN BLDG 14 | 014 | CLOSED | 658.3884 | 0 | 853.836 | 853.836
PJ0003598 | ENCLOSE DOORWAY BETWEEN 114A & 115B - BLD 14 | MAY, TOM | CLOSED | 2010-11-10 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 108.49 | 0 | 0 | 0
PJ0003598 | ENCLOSE DOORWAY BETWEEN 114A & 115B - BLD 14 | MAY, TOM | CLOSED | 2010-11-10 | IN: ENCLOSE DOORWAY BETWEEN 114A & 115B - BLD 14 | 014 | CLOSED | 33.138 | 0 | 16.569 | 16.569
PJ0003598 | ENCLOSE DOORWAY BETWEEN 114A & 115B - BLD 14 | MAY, TOM | CLOSED | 2010-11-10 | PA:PATCH AND PAINT TWO DOORWAYS IN 14 | 014 | CLOSED | 393.481 | 0 | 510.36 | 510.36
PJ0003598 Total | [7 empty] | 1193.4974 | 0 | 1380.765 | 1380.765
PJ0003594 | REPAIR SIDEWALK IN FRONT OF MOTT GYM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-11-05 | CA:REPAIR TWO LOCATIONS OF DAMAGED CONCRETE AT MOTT GYM | 042 | CLOSED | 0 | 0 | 3570.855 | 3570.855
PJ0003594 | REPAIR SIDEWALK IN FRONT OF MOTT GYM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-11-05 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003594 | REPAIR SIDEWALK IN FRONT OF MOTT GYM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-11-05 | EO:SAW CUT AND REMOVE TWO AREAS OF DAMAGED CONCRETE AT MOTT | 042 | CLOSED | 0 | 0 | 384.4 | 384.4
PJ0003594 Total | [7 empty] | 0 | 0 | 3955.255 | 3955.255
PJ0003593 | MOVE BIKE RACKS FROM UU LOWER PLAZA TO PERIMETER MALL | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | CA: UNBOLT BIKE RACKS | 065 | CLOSED | 185.523 | 0 | 27.69 | 27.69
PJ0003593 | MOVE BIKE RACKS FROM UU LOWER PLAZA TO PERIMETER MALL | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 37.44 | 0 | 0 | 0
PJ0003593 | MOVE BIKE RACKS FROM UU LOWER PLAZA TO PERIMETER MALL | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | MO: MOVE BIKE RACKS | 065 | CLOSED | 189 | 0 | 126 | 126
PJ0003593 Total | [7 empty] | 411.963 | 0 | 153.69 | 153.69
PJ0003592 | CREATE OFFICE FOR THE BOWLING CENTER MANAGER - UU 65 RM 117A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | CA: CONTRUCT WALL WITH GYP BD FINISH | 065 | CLOSED | 2124.6114 | 0 | 1748.256 | 1748.256
PJ0003592 | CREATE OFFICE FOR THE BOWLING CENTER MANAGER - UU 65 RM 117A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 365.28 | 0 | 0 | 0
PJ0003592 | CREATE OFFICE FOR THE BOWLING CENTER MANAGER - UU 65 RM 117A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | EL: ELECTRICAL ALTERATIONS FOR OFFICE 118C | 065 | CLOSED | 762.4159 | 0 | 445.44 | 445.44
PJ0003592 | CREATE OFFICE FOR THE BOWLING CENTER MANAGER - UU 65 RM 117A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | IN: CREATE OFFICE FOR THE BOWLING CENTER MANAGER - UU 65 RM 117A | 065 | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0003592 | CREATE OFFICE FOR THE BOWLING CENTER MANAGER - UU 65 RM 117A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-11-04 | PA: PAINT WALLS | 065 | CLOSED | 633.481 | 0 | 595.536 | 595.536
PJ0003592 Total | [7 empty] | 4018.3403 | 0 | 2888.646 | 2888.646
PJ0003590 | CHAIN LINK FENCE, GATES, DRIVEWAY - BLD 50J | LAMPMAN, GREG | CLOSED | 2010-11-03 | AD: JOC 10.020.035 STAPLES | 050J | CLOSED | 7072.15 | 0 | 7072.15 | 7072.15
PJ0003590 | CHAIN LINK FENCE, GATES, DRIVEWAY - BLD 50J | LAMPMAN, GREG | CLOSED | 2010-11-03 | CP: PROJECT CONTINGENCY | 050J | CLOSED | 0 | 0 | 0 | 0
PJ0003590 | CHAIN LINK FENCE, GATES, DRIVEWAY - BLD 50J | LAMPMAN, GREG | CLOSED | 2010-11-03 | IN: CHAIN LINK FENCE, GATES, DRIVEWAY - BLD 50J | 050J | CLOSED | 55.23 | 0 | 55.23 | 55.23
PJ0003590 Total | [7 empty] | 7127.38 | 0 | 7127.38 | 7127.38
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. CSU FULLERTON - APR 22 - 6PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. CSU FULLERTON - APR 23 - 1PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. CSU NORTHRIDGE - APR 15 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. CSU NORTHRIDGE - APR 16 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. CSU NORTHRIDGE - APR 17 - 1PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. LOYOLA - MAR 11 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. LOYOLA - MAR 12 - 2 GAMES (1 &4:30P) | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. MINNESOTA - MAR 25 - 6PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. MINNESOTA - MAR 26 - 4PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. MINNESOTA - MAR 27 - 10AM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. PEPPERDINE - MAR 29 - 6PM | 160 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UC DAVIS - MAY 13 - 6PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UC DAVIS - MAY 14 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UC DAVIS - MAY 15 - 1PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UC RIVERSIDE - APR 1 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UC RIVERSIDE - APR 2 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UC RIVERSIDE - APR 3 - 1PM | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UCLA - MAR 20 - 2PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. UCLA - MAR 21 - 6PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. VALPARAISO - MAR 4 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. VALPARAISO - MAR 5 - 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT BASEBALL V. VALPARAISO - MAR 6 - 1PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL PRACTICES TILL JUNE 30, 2011 | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. CSU FULLERTON - APR 21-23 | 160 | CLOSED | 0 | 0 | 1754.916 | 1754.916
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. FRESNO ST - APR 19 | 160 | CLOSED | 0 | 0 | 531.936 | 531.936
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. LOYOLA - MAR 11-13 | 160 | CLOSED | 0 | 0 | 1716.912 | 1716.912
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. MINNESOTA - MAR 25-27 | 160 | CLOSED | 0 | 0 | 1563.744 | 1563.744
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. PEPPERDINE - MAR 29 | 160 | CLOSED | 0 | 0 | 727.836 | 727.836
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. ST MARYS - MAY 3 | 160 | CLOSED | 0 | 0 | 618.612 | 618.612
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. UC DAVIS - MAY 13-15 | 160 | CLOSED | 0 | 0 | 1538.772 | 1538.772
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. UC RIVERSIDE - APR 1-3 (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. UC RIVERSIDE - APR 15-17 | 160 | CLOSED | 0 | 0 | 1759.644 | 1759.644
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. UCLA - MAR 19-21 | 160 | CLOSED | 0 | 0 | 585.336 | 585.336
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT BASEBALL V. VALPARAISO - MAR 4-6 | 160 | CLOSED | 0 | 0 | 3357.816 | 3357.816
PJ0003587 | 10/11 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT FOR BASEBALL ALUMNI GAME - FEB 12 | 160 | CLOSED | 0 | 0 | 416.772 | 416.772
PJ0003587 Total | [7 empty] | 0 | 0 | 15277.41 | 15277.41
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S SOFTBALL ALUMNI GAME - 11/6 | 161 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S SOFTBALL V CUESTA COLLEGE - 11/5 | 161 | CLOSED | 0 | 0 | 27.33 | 27.33
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL MUSTANG CLASSIC - MAR 25-27 | 161 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL MUSTANG CLASSIC - MAR 25-27 (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. CSULB - APR 22 | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. CSULB - APR 22 (2 GAMES) (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. NOTRE DAME - MAR 13 | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. NOTRE DAME - MAR 13 (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. PACIFIC - MAY 13 (2 GAMES) (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. PACIFIC - MAY 14 (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. UCSB - APR 10 (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT WMNS SOFTBALL V. UCSB - APR 9 (2 GAMES) (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT FOR WOMEN'S SOFTBALL PRACTICES - 2011 SEASON | 161 | CLOSED | 0 | 0 | 393.618 | 393.618
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA: SUPPORT WMN'S SOFTBALL V NOTRE DAME - MAR 13 @ 1&3 PM | 161 | CLOSED | 0 | 0 | 1087.026 | 1087.026
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA:SUPPORT WMN'S SOFTBALL MUSTANG CLASSIC-MAR 25,26,&27 | 161 | CLOSED | 0 | 0 | 4834.338 | 4834.338
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA:SUPPORT WMN'S SOFTBALL V CSU LONG BEACH ON APR 22 | 161 | CLOSED | 0 | 0 | 815.118 | 815.118
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA:SUPPORT WMN'S SOFTBALL V PACIFIC ON MAY 13 | 161 | CLOSED | 0 | 0 | 1011.018 | 1011.018
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | LA:SUPPORT WMN'S SOFTBALL V UCSB ON APR 9&10 | 161 | CLOSED | 0 | 0 | 1480.644 | 1480.644
PJ0003586 | 10/11 SUPPORT: WOMEN'S SOFTBALL - JANSSEN FIELD 161 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | SUPPLY RENTAL: ALUMNI GAME - 11/5 | 161 | CLOSED | 0 | 0 | 147.5 | 147.5
PJ0003586 Total | [7 empty] | 0 | 0 | 10015.232 | 10015.232
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL TOURNEY - MAR 8 | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. CAL - 3/17 @ 7PM | 042 | CLOSED | 0 | 0 | 300.96 | 300.96
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. CSU FULLERTON - 2/24 @ 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. CSULB - 2/26 @ 4PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. CSUN - 1/22 @ 4PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. LOYOLA - 11/19 @ 7PM | 042 | CLOSED | 0 | 0 | 526.68 | 526.68
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. PACIFIC - 1/06 @ 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. SAN FRANCISCO - 12/15 @ 5PM | 042 | CLOSED | 0 | 0 | 470.25 | 470.25
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. SANTA CLARA - 12/30 @ 4:30PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. UC DAVIS - 1/8 @ 4PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. UC IRVINE - 2/12 @ 4PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. UC RIVERSIDE - 1/19 @ 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003585 | 10/11 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WOMEN'S BBALL V. UCSB - 3/5 @ 4PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003585 Total | [7 empty] | 0 | 0 | 5981.58 | 5981.58
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CA: REMOVE CHAIRS FROM WEST BLEACHERS FOR UCSB BBALL-1/27 | 042 | CLOSED | 0 | 0 | 356.688 | 356.688
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL TOURNAMENT 2/19-7PM | 042 | CLOSED | 0 | 0 | 540.18 | 540.18
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V CSU EAST BAY (EXHIBITION) 11/6-7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V CSU MONTEREY BAY 11/18-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V CSU NORTHRIDGE 2/16-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V CSULB 12/30-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V FULLERTON 1/13-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V HAWAII 12/1-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V LOYOLA 11/24-7PM | 042 | CLOSED | 0 | 0 | 594.198 | 594.198
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V PACIFIC 2/5-7PM | 042 | CLOSED | 0 | 0 | 594.198 | 594.198
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V UC DAVIS 2/3-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V UC IRVINE 1/15-7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V UC IRVINE 2/12-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: MEN'S BBALL V UCSB 1/27-7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | EL: SUPPORT FOR MENS BBALL V. UCSB - THURS JAN 27 | 042 | CLOSED | 0 | 0 | 554.172 | 554.172
PJ0003584 | 10/11 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | PL: PM RESTROOMS AT MOTT FOR 1/27 BBALL GAME. (N/L) | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003584 Total | [7 empty] | 0 | 0 | 7379.556 | 7379.556
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING V. CAL BAPTIST - 12/17 @ TBA (1/3) | 042 | CLOSED | 0 | 0 | 225.72 | 225.72
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING V. CSU BAKERSFIELD - 1/28 @ 6:30PM | 042 | CLOSED | 0 | 0 | 319.77 | 319.77
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING V. MENLO - 12/17 @ TBA (2/3) | 042 | CLOSED | 0 | 0 | 150.48 | 150.48
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING V. SFSU - 2/13 @ 2:00PM | 042 | CLOSED | 0 | 0 | 300.96 | 300.96
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING V. SOUTHERN OREGON - 12/17 @ TBA (3/3) | 042 | CLOSED | 0 | 0 | 150.48 | 150.48
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING V. WYOMING - 1/14 @ 6:30PM | 042 | CLOSED | 0 | 0 | 413.82 | 413.82
PJ0003583 | 10/11 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2010-11-02 | CU: SUPPORT FOR WRESTLING-GREEN & GOLD - 11/6@2PM | 042 | CLOSED | 0 | 0 | 188.1 | 188.1
PJ0003583 Total | [7 empty] | 0 | 0 | 1749.33 | 1749.33
PJ0003582 | CONDITION REPORT: FAULTY ROOF TO WALL FLASHING - CERRO VISTA 170 | MOLLAN, CHERYL L. | CLOSED | 2010-11-01 | AD: ARCHITECTURAL ROOF DESIGN GROUP (ARDG) | RESIDENCE | CLOSED | 5000.003 | 0 | 5344.65 | 5344.65
PJ0003582 | CONDITION REPORT: FAULTY ROOF TO WALL FLASHING - CERRO VISTA 170 | MOLLAN, CHERYL L. | CLOSED | 2010-11-01 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003582 Total | [7 empty] | 5000.003 | 0 | 5344.65 | 5344.65
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | AD: FLOOR CONNECTION | 035 | CLOSED | 5582.9818 | 0 | 5582.9818 | 5582.9818
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5238.7093 | 0 | 5238.7093 | 5238.7093
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | CA:INSTALL WHITE BOARDS IN 35-301 | 035 | CLOSED | 1355.2086 | 0 | 1677.072 | 1677.072
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1157.51 | 0 | 0 | 0
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | EL:MEASURE, ODER AND INSTALL PLUGMOLD FOR 35-301 AND 401 | 035 | CLOSED | 5086.2161 | 0 | 5870.01 | 5870.01
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | IN: CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | 035 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0003581 | CARPET AND T-BAR CEILINGS - BLD 35 RM 301 & 401 | MAY, TOM | CLOSED | 2010-10-29 | PA:PAINT 301/401 LIBRARY | 035 | CLOSED | 525.0226 | 0 | 554.112 | 554.112
PJ0003581 Total | [7 empty] | 19078.2003 | 0 | 18989.1611 | 18989.1611
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | AD: CREDIT CUSTOMER FOR OVERHEAD ON GORDIAN DEDUCTIVE C.O. | RESIDENCE | CLOSED | 0 | 0 | -10.19 | -10.19
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | AD: JOC 11.022.011 STAPLES | RESIDENCE | CLOSED | 7350.0012 | 0 | 7350.0547 | 7350.0547
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | AD: PEAK RACKS (TO BE INSTALLED BY JOC) | RESIDENCE | CLOSED | 1927.9367 | 0 | 1927.926 | 1927.926
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | CA:INSTALL BIKE RACKS AND POUR CONCRETE FOR LIGHTING REPAIR - SM | RESIDENCE | CLOSED | 234.6756 | 0 | 1059.5722 | 1059.5722
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0.88 | 0 | 0 | 0
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | EL: REPAIR CONDUIT FOR OUTDOOR LIGHTING AT SIERRA MADRE - 113 | RESIDENCE | CLOSED | 299.664 | 0 | 715.824 | 715.824
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | EO:ASSIST WITH LANDSCAPING AT SIERRA MADRE | RESIDENCE | CLOSED | 3824.0436 | 0 | 2688.84 | 2688.84
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | IN: LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | RESIDENCE | CLOSED | 85.1945 | 0 | 96.084 | 96.084
PJ0003580 | LANDSCAPE BEAUTIFICATION & INSTALL TABLES - BLD 113 EXTERIOR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-22 | LA:INSTALL NEW LANDSCAPING AT SIERRA MADRE | RESIDENCE | CLOSED | 14386.1784 | 0 | 10562.346 | 10562.346
PJ0003580 Total | [7 empty] | 28108.574 | 0 | 24390.4569 | 24390.4569
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | CA: SUPPORT FOR 2010 FALL COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 8668.8325 | 8668.8325
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | CU: SUPPORT FOR 2010 FALL COMMENCEMENT-12/11 | GENERAL | CLOSED | 0 | 0 | 6113.25 | 6113.25
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | EL: SUPPORT FOR 2010 FALL COMMENCEMENT-12/11 | GENERAL | CLOSED | 0 | 0 | 485.12 | 485.12
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | IN: EVENTS PERMIT FOR 2010 FALL COMMENCEMENT | 061 | CLOSED | 0 | 0 | 55.23 | 55.23
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | LA: SUPPORT FOR 2010 FALL COMMENCEMENT - DEC 11, 2010 | GENERAL | CLOSED | 0 | 0 | 2219.1025 | 2219.1025
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | MC: SUPPORT FOR 2010 FALL COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 800.215 | 800.215
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | PA: TOUCH UP PAINT THE STAGE FOR COMMENCEMENT-12/10 | 042 | CLOSED | 0 | 0 | 469.63 | 469.63
PJ0003579 | SUPPORT FOR 2010 FALL COMMENCEMENT (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-10-28 | PL: SUPPORT FOR 2010 FALL COMMENCEMENT-DEC 11,2010 | GENERAL | CLOSED | 0 | 0 | 751.06 | 751.06
PJ0003579 Total | [7 empty] | 0 | 0 | 19562.44 | 19562.44
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | AD: BUS RENTAL - BREAKAWAY TOURS | GENERAL | CLOSED | 0 | 0 | 3391.9 | 3391.9
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | AD: BUS RENTAL - RIDE-ON | GENERAL | CLOSED | 0 | 0 | 2295.15 | 2295.15
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | CU: SUPPORT FOR PRESIDENT'S CANDIDATES INTERVIEWS-11/29-12/2 | GENERAL | CLOSED | 0 | 0 | 1015.74 | 1015.74
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | CU: SUPPORT FOR PRESIDENT'S SEARCH INTERVIEWS-NOV29-DEC 3 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | ES: SUPPORT FOR THE PRESIDENT INTERVIEWS-NOV 29-DEC 3 | GENERAL | CLOSED | 0 | 0 | 953.472 | 953.472
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | LA: SUPPORT FOR THE PRESIDENT'S SELECTION INTERVIEWS-NOV 29-DEC | GENERAL | CLOSED | 0 | 0 | 161.472 | 161.472
PJ0003578 | SP 10/11: SUPPORT FOR PRESIDENT SEARCH - NOV. 29, 2010 | POPHAM, DONALD J. | CLOSED | 2010-10-28 | PL: SUPPORT FOR PRESIDENT'S SELECTION INTERVIEWS-NOV29-DEC3 | GENERAL | CLOSED | 0 | 0 | 127.152 | 127.152
PJ0003578 Total | [7 empty] | 0 | 0 | 7944.886 | 7944.886
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | AD: MECA | 065 | CLOSED | 4836.4 | 0 | 4209.38 | 4209.38
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | AD: PROJECT MANAGEMENT FEES (NO OVERHEAD) | 065 | CLOSED | 1000 | 0 | 1000 | 1000
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 383.13 | 0 | 0 | 0
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | EH&S: SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | 065 | CLOSED | 72 | 0 | 809.436 | 809.436
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | EL:PROVIDE ELECTRICAL SUPPORT FOR CONTRACTOR ELEC DEMO | 065 | CLOSED | 380.664 | 0 | 602.718 | 602.718
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | ES:PROVIDE SUPPORT FOR CONTRACTOR | 065 | CLOSED | 256.128 | 0 | 64.032 | 64.032
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | IN: BUILDING PERMIT FEES (NO OVERHEAD) | 065 | CLOSED | 672.08 | 0 | 355.6 | 355.6
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | IN: PLAN REVEIW FEES (NO OVERHEAD) | 065 | CLOSED | 0 | 0 | 316.48 | 316.48
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | IN:(MAINT) SESLOC DEMOLITION TO PRE-TENANT CONDITIONS BLD65-103 | 065 | CLOSED | 0 | 0 | 220.92 | 220.92
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | LO:CHANGE SESLOC CORE TO ORANGE CORED KEY | 065 | CLOSED | 171.504 | 0 | 93.168 | 93.168
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | MO: ASSIST CONTRACTOR MOVING SAFE FROM STREET TO TRUCK | 065 | CLOSED | 63 | 0 | 5.682 | 5.682
PJ0003574 | SESLOC DEMOLITION TO PRE-TENANT CONDITIONS - BLD 65-103 | MOLLAN, CHERYL L. | CLOSED | 2010-10-22 | PL:DISCONNECT PLUMBING IN SINK FOR SINK DEMO | 065 | CLOSED | 381.456 | 0 | 127.152 | 127.152
PJ0003574 Total | [7 empty] | 8216.362 | 0 | 7804.568 | 7804.568
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 5335.02 | 0 | 5335.02 | 5335.02
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | AD: SAN LUIS GLASS | 035 | CLOSED | 2118.6 | 0 | 2118.6 | 2118.6
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 3523.4886 | 0 | 3531.0214 | 3531.0214
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | CA:HANG ELECTRIC SCREEN ON EAST WALL IN 35-511 | 035 | CLOSED | 677.0004 | 0 | 582.78 | 582.78
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | EL:SMART ROOM ELECTRICAL FOR 35-511 | 035 | CLOSED | 1318.548 | 0 | 1041.852 | 1041.852
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | IN: CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | 035 | CLOSED | 132.552 | 0 | 130.332 | 130.332
PJ0003572 | CONVERT EMPLOYEE LOUNGE INTO CONFERENCE ROOM - BLDG 35-511 | MAY, TOM | CLOSED | 2010-10-19 | PA:PAINT EAST WALL IN 35-511 | 035 | CLOSED | 651.948 | 0 | 651.948 | 651.948
PJ0003572 Total | [7 empty] | 13757.157 | 0 | 13391.5534 | 13391.5534
PJ0003571 | REPAINT RED EYEBROWS & SEAL EXT BLOCK WALLS (SEE TASKS) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2010-10-19 | AD: JOC 10.020.055 STAPLES | 006 | CLOSED | 86473.3447 | 0 | 84638.1556 | 84638.1556
PJ0003571 | REPAINT RED EYEBROWS & SEAL EXT BLOCK WALLS (SEE TASKS) - PAC 06 | GRIFFIN, PATRICK E. | CLOSED | 2010-10-19 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1667.97 | 0 | 0 | 0
PJ0003571 Total | [7 empty] | 88141.3147 | 0 | 84638.1556 | 84638.1556
PJ0003570 | INSTALL ADDITIONAL ACCESS CONTROL DOOR (CAME SECURITY) - 007-17 | GRIFFIN, PATRICK E. | CLOSED | 2010-10-19 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 59.15 | 0 | 0 | 0
PJ0003570 | INSTALL ADDITIONAL ACCESS CONTROL DOOR (CAME SECURITY) - 007-17 | GRIFFIN, PATRICK E. | CLOSED | 2010-10-19 | LO: | 007 | CLOSED | 591.504 | 0 | 461.286 | 461.286
PJ0003570 Total | [7 empty] | 650.654 | 0 | 461.286 | 461.286
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | AD: DIVISION OF STATE ARCHITECT | 045 | CLOSED | 400 | 0 | 0 | 0
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | AD: PURCHASE PARTS FOR VISALIA TILE | 045 | CLOSED | 0 | 0 | 31.47 | 31.47
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | AD: VISALIA TILE | 045 | CLOSED | 5715.65 | 0 | 5685.18 | 5685.18
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | CA: (MAINT) PUNCH LIST ITEMS FOR BLG. 45 ADA COMPLIANT RESTROOM | 045 | CLOSED | 0 | 0 | 801.86 | 801.86
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | CA:REMOVE PARTITIONS AND DISPENSERS- REINSTALL NEW | 045 | CLOSED | 8850.8055 | 0 | 10908.3928 | 10908.3928
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 0 | 0 | 0 | 0
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | CU:PROVIDE CUSTODIAL SUPPORT AFTER CONSTRUCTION | 045 | CLOSED | 188.0304 | 0 | 273.3 | 273.3
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | EH&S: ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | 045 | CLOSED | 1344.81 | 0 | 928.49 | 928.49
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | IN: ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 221 & 222 | 045 | CLOSED | 165.69 | 0 | 138.075 | 138.075
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | LO:CHANGE CORE TO ORANGE CONSTRUCTION AND BACK | 045 | CLOSED | 95.28 | 0 | 72.19 | 72.19
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | PA: REPAIR PLASTER AND PAINT WALLS IN RESTROOM | 045 | CLOSED | 2086.4 | 0 | 1487.5 | 1487.5
PJ0003568 | SR 10/11:ADA COMPLIANCE-MENS & WOMENS RESTRMS - BLD 45 109 & 110 | MOLLAN, CHERYL L. | CLOSED | 2010-10-14 | PL:REMOVE EXISTING NON COMPLIANT FIXTURES AND REPLACE WITH ADA | 045 | CLOSED | 10738.3964 | 0 | 10412.3443 | 10412.3443
PJ0003568 Total | [7 empty] | 29585.0623 | 0 | 30738.8021 | 30738.8021
PJ0003566 | INSTALL COMMERCIAL DISH MACHINE IN FOOD LAB -BLD 24 RM 103 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-11 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 482.61 | 0 | 0 | 0
PJ0003566 | INSTALL COMMERCIAL DISH MACHINE IN FOOD LAB -BLD 24 RM 103 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-11 | EL: CONNECT DISHWASHER | 024 | CLOSED | 1900.6921 | 0 | 1620.726 | 1620.726
PJ0003566 | INSTALL COMMERCIAL DISH MACHINE IN FOOD LAB -BLD 24 RM 103 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-10-11 | PL: CONNECT DISHWASHER | 024 | CLOSED | 2925.053 | 0 | 1121.868 | 1121.868
PJ0003566 Total | [7 empty] | 5308.3552 | 0 | 2742.594 | 2742.594
PJ0003565 | REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | CA:INSTALL 24"X30" WIRE GLASS AND METAL FRAME IN HALLWAY DOOR. | 010 | CLOSED | 1489.4028 | 0 | 1134.72 | 1134.72
PJ0003565 | REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 450.34 | 0 | 0 | 0
PJ0003565 | REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | IN: REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130/131 & 138 | 010 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003565 | REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | LO:INSTALL NEW ADA COMPLIANT HARDWARE | 010 | CLOSED | 1308.672 | 0 | 786.744 | 786.744
PJ0003565 | REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | MO:REMOVE OFFICE FURNITURE TO E-SURPLUS. | 010 | CLOSED | 252 | 0 | 45.456 | 45.456
PJ0003565 | REPAIR ROOMS & MODIFY DOORS TO MEET ADA-BLD 10-130 | MOLLAN, CHERYL L. | CLOSED | 2010-10-11 | PA:PAINT OFFICE | 010 | CLOSED | 1387.2715 | 0 | 1029.456 | 1029.456
PJ0003565 Total | [7 empty] | 4953.9623 | 0 | 3062.652 | 3062.652
PJ0003563 | ENCLOSE DOORWAYS TO SEPARATE CRAFT CTR/ROSE FLOAT-UU 65 RM111F&G | MOLLAN, CHERYL L. | CLOSED | 2010-10-07 | CA:REMOVE EXISTING DOORS AND JAMBS. FRAME AND DRYWALL | 065 | CLOSED | 3297.006 | 0 | 1915.446 | 1915.446
PJ0003563 | ENCLOSE DOORWAYS TO SEPARATE CRAFT CTR/ROSE FLOAT-UU 65 RM111F&G | MOLLAN, CHERYL L. | CLOSED | 2010-10-07 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 509.05 | 0 | 0 | 0
PJ0003563 | ENCLOSE DOORWAYS TO SEPARATE CRAFT CTR/ROSE FLOAT-UU 65 RM111F&G | MOLLAN, CHERYL L. | CLOSED | 2010-10-07 | IN:ENCLOSE DOORS TO SEPARATE CRAFT CTR/ROSE FLOAT-UU 65 RM111F&G | 065 | CLOSED | 66.276 | 0 | 33.138 | 33.138
PJ0003563 | ENCLOSE DOORWAYS TO SEPARATE CRAFT CTR/ROSE FLOAT-UU 65 RM111F&G | MOLLAN, CHERYL L. | CLOSED | 2010-10-07 | LO:REMOVE CORES FROM LOCKS | 065 | CLOSED | 114.336 | 0 | 28.584 | 28.584
PJ0003563 | ENCLOSE DOORWAYS TO SEPARATE CRAFT CTR/ROSE FLOAT-UU 65 RM111F&G | MOLLAN, CHERYL L. | CLOSED | 2010-10-07 | PA:TAPE, TEXTURE AND PAINT | 065 | CLOSED | 1612.608 | 0 | 1119.828 | 1119.828
PJ0003563 Total | [7 empty] | 5599.276 | 0 | 3096.996 | 3096.996
PJ0003562 | M&R HOUS 10/11: UPGRADE FIRE ALARM PANELS - YOS 114 & SM 113 | BRENNAN, MICHAEL | CLOSED | 2010-10-04 | AD: DEEP BLUE INTEGRATION | RESIDENCE | CLOSED | 2000 | 0 | 2406.97 | 2406.97
PJ0003562 | M&R HOUS 10/11: UPGRADE FIRE ALARM PANELS - YOS 114 & SM 113 | BRENNAN, MICHAEL | CLOSED | 2010-10-04 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003562 | M&R HOUS 10/11: UPGRADE FIRE ALARM PANELS - YOS 114 & SM 113 | BRENNAN, MICHAEL | CLOSED | 2010-10-04 | EL:INSTALL PANELS AND FIRE COMPONENTS | RESIDENCE | CLOSED | 147966 | 0 | 68500.4861 | 68500.4861
PJ0003562 Total | [7 empty] | 149966 | 0 | 70907.4561 | 70907.4561
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | AD: GF GARCIA AND SONS | 015 | CLOSED | 5336.09 | 0 | 5336.1007 | 5336.1007
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | AD: HARVEY PLUMBING | 015 | CLOSED | 642 | 0 | 642 | 642
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | AD: JOC 11.022.043 STAPLES | 015 | CLOSED | 22972.6753 | 0 | 22972.6753 | 22972.6753
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | AD: QUINN POWER SYSTEMS | 015 | CLOSED | 31303.6097 | 0 | 31303.6097 | 31303.6097
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | AD: TED MULLER PLASTERING | 015 | CLOSED | 1647.8 | 0 | 1647.8 | 1647.8
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | AD: TEMPLE BUILDERS | 015 | CLOSED | 3057.7925 | 0 | 3057.7925 | 3057.7925
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | CA:BOLTS FOR GENERATOR AT BUILDING 15 | 015 | CLOSED | 75.8706 | 0 | 307.044 | 307.044
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 2716.78 | 0 | 0 | 0
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | EL:ASSIST WITH SHUTDOWN FOR GENERATOR @ 15 | 015 | CLOSED | 369.2441 | 0 | 221.268 | 221.268
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | EO:LANDSCAPE WORK AT BUILDING 15 | 015 | CLOSED | 370.752 | 0 | 99.528 | 99.528
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | IN: INSTALL GENERATOR - BLD 15 RM 108 | 015 | CLOSED | 265.104 | 0 | 256.224 | 256.224
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | LA:LANDSCAPE PLANTINGS AROUND NEW GENERATOR ENCLOSURE AT 15 | 015 | CLOSED | 1651.776 | 0 | 331.194 | 331.194
PJ0003561 | INSTALL GENERATOR - BLD 15 RM 108 | MAY, TOM | CLOSED | 2010-10-01 | PL:ASSIST WITH GENERATOR INSTALLATION @ 15 | 015 | CLOSED | 212.3438 | 0 | 2597.22 | 2597.22
PJ0003561 Total | [7 empty] | 70621.838 | 0 | 68772.4562 | 68772.4562
PJ0003559 | REVIEW & REPAIR - POULTRY TRAILER (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-30 | AD: FLOOR CONNECTION (MAINT) | 150I-M014 | CLOSED | 0 | 0 | 640.57 | 640.57
PJ0003559 | REVIEW & REPAIR - POULTRY TRAILER (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-30 | CA: REPAIR HOLE IN FLOOR IN POULTRY TRAILER | 150I-M014 | CLOSED | 0 | 0 | 5853.945 | 5853.945
PJ0003559 | REVIEW & REPAIR - POULTRY TRAILER (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-30 | CP: PROJECT CONTINGENCY | 150I-M014 | CLOSED | 0 | 0 | 0 | 0
PJ0003559 | REVIEW & REPAIR - POULTRY TRAILER (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-30 | PA: PATCH, PREP, AND PAINT AS REQUIRED AT POULTRY TRAILER | 150I-M014 | CLOSED | 0 | 0 | 47.66 | 47.66
PJ0003559 Total | [7 empty] | 0 | 0 | 6542.175 | 6542.175
PJ0003557 | MAINTENANCE AND REPAIR WORK - ALUMNI HOUSE (MAINT) | MAY, TOM | CLOSED | 2010-09-23 | CA: MAINTENANCE REPAIR AT ALUMNI HOUSE | 028 | CLOSED | 0 | 0 | 2866.5528 | 2866.5528
PJ0003557 | MAINTENANCE AND REPAIR WORK - ALUMNI HOUSE (MAINT) | MAY, TOM | CLOSED | 2010-09-23 | CP: PROJECT CONTINGENCY | 028 | CLOSED | 0 | 0 | 0 | 0
PJ0003557 | MAINTENANCE AND REPAIR WORK - ALUMNI HOUSE (MAINT) | MAY, TOM | CLOSED | 2010-09-23 | LA: MAINTENANCE LANSCAPING AT ALUMNI HOUSE (N/L) | 028 | CLOSED | 0 | 0 | 0 | 0
PJ0003557 | MAINTENANCE AND REPAIR WORK - ALUMNI HOUSE (MAINT) | MAY, TOM | CLOSED | 2010-09-23 | PA: MAINTENANCE PAINTING AT ALUMNI HOUSE | 028 | CLOSED | 0 | 0 | 810.22 | 810.22
PJ0003557 Total | [7 empty] | 0 | 0 | 3676.7728 | 3676.7728
PJ0003556 | REPAIR DOOR TO FINISHER BARN - BLD 56B SWINE UNIT (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-09-23 | CA:REPLACE DOOR AND JAMB AT FINISH BARN | 056B | CLOSED | 0 | 0 | 910.95 | 910.95
PJ0003556 | REPAIR DOOR TO FINISHER BARN - BLD 56B SWINE UNIT (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-09-23 | CP: PROJECT CONTINGENCY | 056B | CLOSED | 0 | 0 | 0 | 0
PJ0003556 | REPAIR DOOR TO FINISHER BARN - BLD 56B SWINE UNIT (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-09-23 | LO:INSTALL LOCK HARDWARE AT FINISH BARN | 056B | CLOSED | 0 | 0 | 166.74 | 166.74
PJ0003556 | REPAIR DOOR TO FINISHER BARN - BLD 56B SWINE UNIT (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-09-23 | PA:PAINT NEW DOOR AND JAMB AT FINISH BARN | 056B | CLOSED | 0 | 0 | 238.3 | 238.3
PJ0003556 Total | [7 empty] | 0 | 0 | 1315.99 | 1315.99
PJ0003555 | FEASIBILITY OF PROPOSED SUBWAY PROJECT - DEXTER RMS 111A/111B | MOLLAN, CHERYL L. | CLOSED | 2010-09-20 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 145.69 | 0 | 0 | 0
PJ0003555 | FEASIBILITY OF PROPOSED SUBWAY PROJECT - DEXTER RMS 111A/111B | MOLLAN, CHERYL L. | CLOSED | 2010-09-20 | EL: DEXTER - EVALUATE EXISTING ELECTRICAL FOR PROPOSED SUBWAY | 034 | CLOSED | 727.7027 | 0 | 444.108 | 444.108
PJ0003555 | FEASIBILITY OF PROPOSED SUBWAY PROJECT - DEXTER RMS 111A/111B | MOLLAN, CHERYL L. | CLOSED | 2010-09-20 | PL:DEXTER - EVALUATE EXISTING PLUMBING FOR PROPOSED SUBWAY(N/L) | 034 | CLOSED | 729.2167 | 0 | 0 | 0
PJ0003555 Total | [7 empty] | 1602.6094 | 0 | 444.108 | 444.108
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | ANTS: PROGRAM ALARMS AT BLDG. 40 | 040 | CLOSED | 0 | 0 | 48.048 | 48.048
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | CA: CREATE 6 "SIDEWALK CLOSED" SIGNS FOR TES PROJECT | 040 | CLOSED | 0 | 0 | 240.03 | 240.03
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | CA: CREATE SIGNS FOR UNIVERSITY DRIVE CLOSURE - MON. 6/13/11 | 040 | CLOSED | 0 | 0 | 161.73 | 161.73
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 130000 | 0 | 0 | 0
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | CPE: TES PROJECT SUPPORT | 040 | CLOSED | 0 | 0 | 65531.3738 | 65531.3738
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | EH&S: OBSERVATION OF LEAD PAINT REMOVAL - TES PROJECT AT BLDG 40 | 040 | CLOSED | 0 | 0 | 343.5 | 343.5
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | EL: PROVIDE POWER TO SHOPS - TES PROJECT- BLDG. 040 | 040 | CLOSED | 0 | 0 | 2223.492 | 2223.492
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | EL: RUN TEMP POWER TO TRAILERS | 040 | CLOSED | 0 | 0 | 22396.47 | 22396.47
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | EO: REMOVE TRASH BETWEEN MUSTANG PRESS BLG & CEN. PLANT YARD | 040 | CLOSED | 0 | 0 | 85.23 | 85.23
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | KS: SUPPLY PADLOCKS FOR CONSTRUCTION GATES - TES PROJECT | 040 | CLOSED | 0 | 0 | 178.584 | 178.584
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | LA: REVEG CENTRAL PLANT PROJECT SITES - TES PROJECT | 040 | CLOSED | 0 | 0 | 8309.994 | 8309.994
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | LA: SUPPORT FOR TES TANKS AT BLDG. 40 | 040 | CLOSED | 0 | 0 | 8637.95 | 8637.95
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | LA: SUPPORT RETAINING WALL EXCAVATION FOR TES PROJECT | 040 | CLOSED | 0 | 0 | 2421.6758 | 2421.6758
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | LO: NEW CORES & REPAIR LOCKSET - BLDG 40 | 040 | CLOSED | 0 | 0 | 318.132 | 318.132
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | MO: ASSIST CENTRAL PLANT IN MOVING MATERIALS FOR TES PROJECT | 040 | CLOSED | 0 | 0 | 170.5178 | 170.5178
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | PL: ASSIST EH&S IN SAMPLING FOR TES PROJECT | 040 | CLOSED | 0 | 0 | 130.584 | 130.584
PJ0003554 | MJ: FACILITY SERVICES SUPPORT FOR TES - BLD 40 | NEEL, JOEL | CLOSED | 2010-09-20 | PL: SUPPORT FOR TES PROJECT | 040 | CLOSED | 0 | 0 | 12866.9054 | 12866.9054
PJ0003554 Total | [7 empty] | 130000 | 0 | 124064.217 | 124064.217
PJ0003553 | REMOVE/REPLACE SLIDING DOOR IN WAREHOUSE - 70 | LAMPMAN, GREG | CLOSED | 2010-09-17 | CA: REMOVE AND INSTALL NEW DOORS | 070 | CLOSED | 5215.2 | 0 | 3305.83 | 3305.83
PJ0003553 | REMOVE/REPLACE SLIDING DOOR IN WAREHOUSE - 70 | LAMPMAN, GREG | CLOSED | 2010-09-17 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0003553 | REMOVE/REPLACE SLIDING DOOR IN WAREHOUSE - 70 | LAMPMAN, GREG | CLOSED | 2010-09-17 | IN: REMOVE/REPLACE SLIDING DOOR IN WAREHOUSE - 70 | 070 | CLOSED | 110.46 | 0 | 27.615 | 27.615
PJ0003553 | REMOVE/REPLACE SLIDING DOOR IN WAREHOUSE - 70 | LAMPMAN, GREG | CLOSED | 2010-09-17 | PA: FINISH DRYWALL AND PAINT | 070 | CLOSED | 1624.5 | 0 | 255.97 | 255.97
PJ0003553 Total | [7 empty] | 6950.16 | 0 | 3589.415 | 3589.415
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | AD: BELFOR | 047 | CLOSED | 64083.17 | 0 | 64083.17 | 64083.17
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | CA:COMPLETE RECONSTRUCTION AFTER FLOOD AT FON 21 | 047 | CLOSED | 6176.5 | 0 | 6007.525 | 6007.525
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 0 | 0 | 0 | 0
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | CU:PROVIDE SUPPORT FOR FLOOD DAMAGE AT FON | 047 | CLOSED | 1284.51 | 0 | 1315.35 | 1315.35
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | ES:PROVIDE SUPPORT FOR FLOOD DAMAGE RECONSTRUCTION AT FON 21 | 047 | CLOSED | 1494.08 | 0 | 1651.77 | 1651.77
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | MO:PROVIDE MOVING SUPPORT FOR FLOOD AT FON 21 | 047 | CLOSED | 157.5 | 0 | 127.845 | 127.845
PJ0003551 | SR 10/11: FLOOD REMEDIATION-SEWER LINE BREAK 9-14-10 BLD 47 FON | GRIFFIN, PATRICK E | CLOSED | 2010-09-17 | PA:COMPLETE RECONSTRUCTION OF FLOOD DAMAGE AT FON 21 | 047 | CLOSED | 6330.18 | 0 | 6330.18 | 6330.18
PJ0003551 Total | [7 empty] | 79525.94 | 0 | 79515.84 | 79515.84
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | AD: JOC 10.020.038 STAPLES | GENERAL | CLOSED | 23274.06 | 0 | 23274.06 | 23274.06
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1000 | 0 | 0 | 0
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | EL: SUPPORT FOR WATERMAIN BREAK BEHIND SAGE RESTAURANT | GENERAL | CLOSED | 0 | 0 | 56.435 | 56.435
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | EO: SUPPORT FOR WATERMAIN BREAK BEHIND SAGE RESTAURANT | GENERAL | CLOSED | 1506.18 | 0 | 1472.765 | 1472.765
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | IN: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | GENERAL | CLOSED | 110.46 | 0 | 82.845 | 82.845
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | LA: SUPPORT FOR WATERMAIN BREAK BEHIND SAGE RESTAURANT | GENERAL | CLOSED | 570.96 | 0 | 202.345 | 202.345
PJ0003550 | SR 10/11: BROKEN WATERMAIN BEHIND SAGE RESTAURANT-EMERG. REPAIRS | LAMPMAN, GREG | CLOSED | 2010-09-17 | PL: SUPPORT FOR WATERMAIN BREAK BEHIND SAGE RESTAURANT | GENERAL | CLOSED | 3229.75 | 0 | 3366.0782 | 3366.0782
PJ0003550 Total | [7 empty] | 29691.41 | 0 | 28454.5282 | 28454.5282
PJ0003548 | WASH EXTERIOR & ATRIUM WINDOWS - KEN LIB 35 | LOOSLEY, SCOTT L. | CLOSED | 2010-08-12 | AD: COASTAL JANITORIAL | 035 | CLOSED | 5178.8 | 0 | 5178.8 | 5178.8
PJ0003548 | WASH EXTERIOR & ATRIUM WINDOWS - KEN LIB 35 | LOOSLEY, SCOTT L. | CLOSED | 2010-08-12 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 517.88 | 0 | 0 | 0
PJ0003548 Total | [7 empty] | 5696.68 | 0 | 5178.8 | 5178.8
PJ0003546 | PAC MAINTENANCE WALK-THRU AUGUST 2010 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-10 | CA:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 906.32 | 906.32
PJ0003546 | PAC MAINTENANCE WALK-THRU AUGUST 2010 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-10 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003546 | PAC MAINTENANCE WALK-THRU AUGUST 2010 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-10 | ES:REATTACH HVAC REGISTER AT PAC | 006 | CLOSED | 0 | 0 | 52.87 | 52.87
PJ0003546 | PAC MAINTENANCE WALK-THRU AUGUST 2010 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-10 | LO: RESECURE MAGNETIC HOLDBACK ON DOOR | 006 | CLOSED | 0 | 0 | 787.02 | 787.02
PJ0003546 | PAC MAINTENANCE WALK-THRU AUGUST 2010 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-10 | PA:COMPLETE PAINTING ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 428.94 | 428.94
PJ0003546 | PAC MAINTENANCE WALK-THRU AUGUST 2010 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E. | CLOSED | 2010-09-10 | PL: PAC MAINTENANCE WALK-THRU ITEMS | 006 | CLOSED | 0 | 0 | 158.94 | 158.94
PJ0003546 Total | [7 empty] | 0 | 0 | 2334.09 | 2334.09
PJ0003545 | HOIST THE GOLF ROBOT ONTO MEZZANINE - BLD 13 RM 205 | LAMPMAN, GREG | CLOSED | 2010-09-08 | AD: SUPERIOR CRANE AND TRANSPORT | 013 | CLOSED | 278.2 | 0 | 256.8 | 256.8
PJ0003545 | HOIST THE GOLF ROBOT ONTO MEZZANINE - BLD 13 RM 205 | LAMPMAN, GREG | CLOSED | 2010-09-08 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 27.82 | 0 | 0 | 0
PJ0003545 Total | [7 empty] | 306.02 | 0 | 256.8 | 256.8
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | CA: UNBOLT BIKE RACKS ON VIA CARTA BEFORE 9/17 | RESIDENCE | CLOSED | 0 | 0 | 264.65 | 264.65
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | LA: SET OUT BIKE RACKS AT PARKING LOT H-10 FOR BIKE NIGHT 9/17 | RESIDENCE | CLOSED | 0 | 0 | 537.876 | 537.876
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | LA: SUPPORT FOR WOW BLOCK PARTY - 9/19 | RESIDENCE | CLOSED | 0 | 0 | 351.1166 | 351.1166
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | LA: WOW WEEK MOVE IN SUPPORT | RESIDENCE | CLOSED | 0 | 0 | 9010.9 | 9010.9
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | MC: MOVE BIKE RACKS ON FRIDAY 9/17 TO PARKING H-10 | RESIDENCE | CLOSED | 0 | 0 | 28.41 | 28.41
PJ0003543 | 2010 WOW WEEK SUPPORT 9/15 - 9/19 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-09-02 | PERMIT: 40X100 CANOPY FOR WOW BLOCK PARTY ON 9/19 (N/L) | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003543 Total | [7 empty] | 0 | 0 | 10192.9526 | 10192.9526
PJ0003542 | PREP OFFICES FOR NEW STAFF - BLDG. 53 ROOMS 205, 210F, AND 210G | GRIFFIN, PATRICK E | CLOSED | 2010-08-31 | CA:COMPLETE ITEMS IN SCIENCE NORTH BY SEPT. 9TH. | 053 | CLOSED | 156.8202 | 0 | 302.43 | 302.43
PJ0003542 | PREP OFFICES FOR NEW STAFF - BLDG. 53 ROOMS 205, 210F, AND 210G | GRIFFIN, PATRICK E | CLOSED | 2010-08-31 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 349.58 | 0 | 0 | 0
PJ0003542 | PREP OFFICES FOR NEW STAFF - BLDG. 53 ROOMS 205, 210F, AND 210G | GRIFFIN, PATRICK E | CLOSED | 2010-08-31 | CU:STRIP AND WAX 210F AND 210G, SHAMPOO RUG IN 205 | 053 | CLOSED | 1082.8739 | 0 | 245.97 | 245.97
PJ0003542 | PREP OFFICES FOR NEW STAFF - BLDG. 53 ROOMS 205, 210F, AND 210G | GRIFFIN, PATRICK E | CLOSED | 2010-08-31 | PA: PREP AND PAINT ROOMS IN SCIENCE NORTH | 053 | CLOSED | 2255.9767 | 0 | 1462.638 | 1462.638
PJ0003542 Total | [7 empty] | 3845.2508 | 0 | 2011.038 | 2011.038
PJ0003540 | CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | MAY, TOM | CLOSED | 2010-08-27 | AD: FLOOR CONNECTION | 035 | CLOSED | 2904.5257 | 0 | 2927.8624 | 2927.8624
PJ0003540 | CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | MAY, TOM | CLOSED | 2010-08-27 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 5215.18 | 0 | 5215.18 | 5215.18
PJ0003540 | CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | MAY, TOM | CLOSED | 2010-08-27 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 605.87 | 0 | 0 | 0
PJ0003540 | CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | MAY, TOM | CLOSED | 2010-08-27 | EL:INSTALL LIGHT SWITCHING IN 35-216H/J | 035 | CLOSED | 507.552 | 0 | 978.69 | 978.69
PJ0003540 | CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | MAY, TOM | CLOSED | 2010-08-27 | IN: CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | 035 | CLOSED | 66.276 | 0 | 132.552 | 132.552
PJ0003540 | CARPET & ACOUSTIC TREATMENT - BLD 35 RMS 216 H&J | MAY, TOM | CLOSED | 2010-08-27 | PA:PAINT ROOMS 216 H & J IN LIBRARY | 035 | CLOSED | 1049.4732 | 0 | 920.988 | 920.988
PJ0003540 Total | [7 empty] | 10348.8769 | 0 | 10175.2724 | 10175.2724
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | AD: FLOOR CONNECTION | 035 | CLOSED | 5029 | 0 | 5101.546 | 5101.546
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | AD: J.L. FASULO DRYWALL | 035 | CLOSED | 5350 | 0 | 7374.44 | 7374.44
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | AD: SAN LUIS CUSTOM TINTS | 035 | CLOSED | 352.2012 | 0 | 351.5378 | 351.5378
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5350 | 0 | 1882.13 | 1882.13
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | BLDG. 35 ROOM 313 INSTALL NEW SINK AND FILTERED WATER SYSTEM | 035 | CLOSED | 127.152 | 0 | 722.916 | 722.916
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | CA:REMODEL JOB IN LIBRARY 312/313 | 035 | CLOSED | 6929.6688 | 0 | 10449.4492 | 10449.4492
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1603.86 | 0 | 0 | 0
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | EL:ELECTRICAL WORK IN 35-312/313 | 035 | CLOSED | 2749.0292 | 0 | 2738.556 | 2738.556
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | ES:RECONFIGURE HVAC IN 35-312/313 | 035 | CLOSED | 888.384 | 0 | 2852.292 | 2852.292
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | IN: REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | 035 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003539 | REMODEL ROOMS - BLD 35 RMS 312, 312A, & 312B | MAY, TOM | CLOSED | 2010-08-26 | PA:PAINT ROOMS 35-312/313 | 035 | CLOSED | 4175.9534 | 0 | 1384.641 | 1384.641
PJ0003539 Total | [7 empty] | 32687.8007 | 0 | 32990.06 | 32990.06
PJ0003538 | TI PERMIT FOR APPLIED BIOTECHNOLOGY INC. - BLD 83 LAB 1D | HOGAN, MIKE | CLOSED | 2010-08-27 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003538 | TI PERMIT FOR APPLIED BIOTECHNOLOGY INC. - BLD 83 LAB 1D | HOGAN, MIKE | CLOSED | 2010-08-27 | IN: (MAINT) TI PERMIT FOR APPLIED BIOTECH. - BLD 83 LAB 1D | 083 | CLOSED | 0 | 0 | 856.065 | 856.065
PJ0003538 | TI PERMIT FOR APPLIED BIOTECHNOLOGY INC. - BLD 83 LAB 1D | HOGAN, MIKE | CLOSED | 2010-08-27 | IN: BUILDING PERMIT FEES | 083 | CLOSED | 1125.1 | 0 | 1125.1 | 1125.1
PJ0003538 | TI PERMIT FOR APPLIED BIOTECHNOLOGY INC. - BLD 83 LAB 1D | HOGAN, MIKE | CLOSED | 2010-08-27 | IN: PLAN REVIEW FEES | 083 | CLOSED | 1001.34 | 0 | 1001.34 | 1001.34
PJ0003538 | TI PERMIT FOR APPLIED BIOTECHNOLOGY INC. - BLD 83 LAB 1D | HOGAN, MIKE | CLOSED | 2010-08-27 | IN: STATE FIRE MARSHAL FEES | 083 | CLOSED | 2080 | 0 | 0 | 0
PJ0003538 Total | [7 empty] | 4206.44 | 0 | 2982.505 | 2982.505
PJ0003537 | ADA REVIEW - SPANOS STADIUM (MAINT) | HUNTER, MARK A | CLOSED | 2010-08-27 | AD: SZS CONSULTING - ADA REVIEW (MAINT) SEE PO 2010200280 | 061 | CLOSED | 0 | 0 | 1920 | 1920
PJ0003537 | ADA REVIEW - SPANOS STADIUM (MAINT) | HUNTER, MARK A | CLOSED | 2010-08-27 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003537 Total | [7 empty] | 0 | 0 | 1920 | 1920
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 10/7- ASEE BROWNBAG LUNCH - 197-203 | 197 | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 8/30 - CLEAN UP OF DAC EXEC COMMITTEE MTG- (197-203) | 197 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 9/15-BMGE ADMITTED STUDENTS DAY (ATL-001&002) | 007 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 9/15-WOW WEEK FRESHMAN MTG - AERO (197-104) | 197 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 9/16-BME DEPT FALL RETREAT (197-203) | 197 | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 9/29 - SOC OF WOMEN ENGRS GEN MTG - 197-104 | 197 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: 9/29- SOCIETY OF CIVIL ENGRS MTG (ATL-001 & 002) | 007 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: ABBOT VASCULAR INTERVIEWS - 197-203 ON OCT 15, 2010 | 197 | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: MEDTRONIC INFO SESSION - 197-104 ON OCT 14, 2010 | 197 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: NORTHROP GRUMMAN EXEC MTG - 10/14 (197-104) | GENERAL | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: NORTHROP GRUMMAN RECRUITMENT - 10/12 - (ATL-001, 197-104) | GENERAL | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003536 | 10/11 COLLEGE OF ENGINEERING EVENT SUPPORT | POPHAM, DONALD J. | CLOSED | 2010-08-27 | CU: SBES: GUARANTEED WORKSHOP - 197-104 ON OCT 23, 2010 | GENERAL | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003536 Total | [7 empty] | 0 | 0 | 409.95 | 409.95
PJ0003535 | SUPPORT FOR CALLAHAN FUNERAL (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-23 | CA: CREATE SIGNS AND INSTALL FOR CALLAHAN FUNERAL - 8/27 | 006 | CLOSED | 0 | 0 | 168.625 | 168.625
PJ0003535 | SUPPORT FOR CALLAHAN FUNERAL (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-23 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003535 | SUPPORT FOR CALLAHAN FUNERAL (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-23 | CU: CUSTODIAL SUPPORT FOR CALLAHAN FUNERAL - 8/27 | 006 | CLOSED | 0 | 0 | 344.04 | 344.04
PJ0003535 | SUPPORT FOR CALLAHAN FUNERAL (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-23 | GR: SUPPORT FOR CALLAHAN FUNERAL - 8/27 | 006 | CLOSED | 0 | 0 | 201.84 | 201.84
PJ0003535 | SUPPORT FOR CALLAHAN FUNERAL (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-23 | MC: SUPPORT FOR CALLAHAN FUNERAL - 8/27 | 006 | CLOSED | 0 | 0 | 9.47 | 9.47
PJ0003535 | SUPPORT FOR CALLAHAN FUNERAL (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-23 | PL: PM RESTROOMS AT PAC & SPANOS THEATRE FOR FUNERAL-8/27 | 006 | CLOSED | 0 | 0 | 211.92 | 211.92
PJ0003535 Total | [7 empty] | 0 | 0 | 935.895 | 935.895
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CA: INSPECT/REPAIR SEATS AT SUITE 4 SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 161.525 | 161.525
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CA: REPAIR "LOOSE" SEATS AT SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 92.3 | 92.3
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CA: REPAIR BROKEN WINDOW AT SPANOS STADIUM SUITE 1 | 061 | CLOSED | 0 | 0 | 625.705 | 625.705
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CA: REPAIR SEATS AT WEST SIDE SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 1438.63 | 1438.63
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CA: REPLACE PLEXIGLAS PANEL AND FASTEN OTHER LOOSE PANELS | 061 | CLOSED | 0 | 0 | 1254.74 | 1254.74
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CA: TRIM NEW CP MAT FOR SOUTH ELEVATOR - SPANOS STAD | 061 | CLOSED | 0 | 0 | 46.15 | 46.15
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | EL: REPAIR 30 SEC CLOCK AT SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | EL: RESET BREAKER ON SCOREBOARD FOR CHUMASH PANEL. (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | LA: ASSIST WITH MOVING SEATS AT SPANOS STADIUM - 9/3 -(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | MC: MOVE CHAIRS FROM SPANOS STAD - CORP WAREHOUSE | 061 | CLOSED | 0 | 0 | 85.23 | 85.23
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | PA: PAINT THE RUSTED AREAS ON SUITES WALKWAY | 061 | CLOSED | 0 | 0 | 428.94 | 428.94
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | PCV ES: TACK WELD SOUTH GOAL POST AT SPANOS STADIUM. | 061 | CLOSED | 0 | 0 | 106.72 | 106.72
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | PL: PLEASE PM RESTROOMS (BOTH SIDES & SUITES) BEFORE SAT APR 30 | 061 | CLOSED | 0 | 0 | 317.88 | 317.88
PJ0003534 | 10/11 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-20 | PL: RECHECK STINKY DRAIN AT SUITE #4 DECK - SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 105.96 | 105.96
PJ0003534 Total | [7 empty] | 0 | 0 | 4822.39 | 4822.39
PJ0003532 | REPLACE OVERHEAD DOOR ON WEST SIDE OF BUILDING - BLD 70E (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-08-18 | AD: BRAD'S OVERHEAD DOOR (MAINT) | 070E | CLOSED | 2675 | 0 | 2675 | 2675
PJ0003532 | REPLACE OVERHEAD DOOR ON WEST SIDE OF BUILDING - BLD 70E (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-08-18 | CP: PROJECT CONTINGENCY | 070E | CLOSED | 0 | 0 | 0 | 0
PJ0003532 Total | [7 empty] | 2675 | 0 | 2675 | 2675
PJ0003530 | REPLACE EXTERIOR DOOR - BLD 116 2ND FLOOR HALLWAY(MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-08-18 | CA:REPLACE EXTERIOR DOOR AT JESPERSON | 116 | CLOSED | 0 | 0 | 633.575 | 633.575
PJ0003530 | REPLACE EXTERIOR DOOR - BLD 116 2ND FLOOR HALLWAY(MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-08-18 | CP: PROJECT CONTINGENCY | 116 | CLOSED | 0 | 0 | 0 | 0
PJ0003530 | REPLACE EXTERIOR DOOR - BLD 116 2ND FLOOR HALLWAY(MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-08-18 | LO: INSTALL LOCK HARDWARE ON NEW DOOR | 116 | CLOSED | 0 | 0 | 1362.02 | 1362.02
PJ0003530 | REPLACE EXTERIOR DOOR - BLD 116 2ND FLOOR HALLWAY(MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-08-18 | PA: PAINT NEW DOOR AT JESPERSON | 116 | CLOSED | 0 | 0 | 333.62 | 333.62
PJ0003530 Total | [7 empty] | 0 | 0 | 2329.215 | 2329.215
PJ0003528 | RENOVATE FOOD PREP AREA - 3 ACRE LAWN / BUS 03(MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-18 | CA: INSTALL NEW COUNTERTOP AND SPLASH GUARD AT O'NEILL LAWN | GENERAL | CLOSED | 0 | 0 | 447.15 | 447.15
PJ0003528 | RENOVATE FOOD PREP AREA - 3 ACRE LAWN / BUS 03(MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003528 | RENOVATE FOOD PREP AREA - 3 ACRE LAWN / BUS 03(MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-18 | LA: SMOOTH OUT DG AT BBQ AREA AT O'NEILL LAWN | GENERAL | CLOSED | 0 | 0 | 33.64 | 33.64
PJ0003528 Total | [7 empty] | 0 | 0 | 480.79 | 480.79
PJ0003526 | MEMORIAL BENCH - ALONG TRACK FENCE NEAR FOUNTAIN (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-08-16 | AD: QUICK CRETE | 042U | CLOSED | 0 | 0 | 1253.2589 | 1253.2589
PJ0003526 | MEMORIAL BENCH - ALONG TRACK FENCE NEAR FOUNTAIN (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-08-16 | CA: INSTALL PLAQUE ON MEMORIAL BENCH AT UPPER TRACK. | 042U | CLOSED | 0 | 0 | 55.38 | 55.38
PJ0003526 | MEMORIAL BENCH - ALONG TRACK FENCE NEAR FOUNTAIN (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-08-16 | CP: PROJECT CONTINGENCY | 042U | CLOSED | 0 | 0 | 0 | 0
PJ0003526 | MEMORIAL BENCH - ALONG TRACK FENCE NEAR FOUNTAIN (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-08-16 | LA: PLACE MEMORIAL BENCH NEAR TRACK | 042U | CLOSED | 0 | 0 | 46.308 | 46.308
PJ0003526 Total | [7 empty] | 0 | 0 | 1354.9469 | 1354.9469
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | AD: PURCHASE COLLEGE BANNER REPLACEMENT PART (NO LABOR) (MAINT) | 051 | CLOSED | 0 | 0 | 409.67 | 409.67
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | AD: RENTAL OF CANOPY HEATER (MATERIALS, ONLY) | 051 | CLOSED | 0 | 0 | 121.49 | 121.49
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: INSTALL ONE TABLE LEAF AT PRES. RESIDENT - DEC 21 | 051 | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: INSTALL TENT , CLOUDS, AND SOUTH WALL BEFORE SUNDAY SEPT 10 | 051 | CLOSED | 0 | 0 | 422.91 | 422.91
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: INSTALL TWO TABLE LEAVES AT UNIVERSITY HOUSE DINING TABLE | 051 | CLOSED | 0 | 0 | 46.99 | 46.99
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: PLEASE REMOVE THE SOUTH WALL AT UNIV HOUSE TENT BY 10/28 | 051 | CLOSED | 0 | 0 | 140.97 | 140.97
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: REMOVE TENT SIDES FOR EVENT ON SAT JUNE 11 | 051 | CLOSED | 0 | 0 | 148.431 | 148.431
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: REMOVE TWO LEAVES FROM DINNER TABLE ON THURS AM-10/20 | 051 | CLOSED | 0 | 0 | 93.98 | 93.98
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: SET UP TENT AT UNIVERSITY HOUSE ON APR 29 8:00AM | 051 | CLOSED | 0 | 0 | 369.2 | 369.2
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: SETUP ALL TENT SIDES AT UNIV HOUSE BY NOV 29 | 051 | CLOSED | 0 | 0 | 892.81 | 892.81
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: TENT SIDES FOR EVENTS ON MAY 17 & 18 AT PRES. RES. | 051 | CLOSED | 0 | 0 | 461.5 | 461.5
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | MC: MOVE FICUS TREES FROM PAC TO UH ON 12/3 (N/L) | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003523 | 10/11: UNIVERSITY HOUSE EVENT SUPPORT - BLD 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | MC: MOVE SOFA AND TWO CHAIRS FROM FAC SER-UNIV HOUSE | 051 | CLOSED | 0 | 0 | 14.205 | 14.205
PJ0003523 Total | [7 empty] | 0 | 0 | 3169.146 | 3169.146
PJ0003522 | 10/11: PRESIDENT'S SUITE EVENT SUPPORT - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | AD: PURCHASE OF NEW COLLEGE BANNER CONTAINER (MAINT) (N/L) | 061 | CLOSED | 0 | 0 | 20.04 | 20.04
PJ0003522 | 10/11: PRESIDENT'S SUITE EVENT SUPPORT - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CA: REMOVE PICS AT PRES SUITE ON MON. DEC 13 AT 9AM. | 061 | CLOSED | 0 | 0 | 230.75 | 230.75
PJ0003522 | 10/11: PRESIDENT'S SUITE EVENT SUPPORT - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003522 | 10/11: PRESIDENT'S SUITE EVENT SUPPORT - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-08-12 | EL: CHECK OUTLETS BEFORE FRIDAY SEPT 3. | 061 | CLOSED | 0 | 0 | 26.435 | 26.435
PJ0003522 Total | [7 empty] | 0 | 0 | 277.225 | 277.225
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | AD: JOC 10.020.041 STAPLES (TRUST FUND) | 083 | CLOSED | 400862.339 | 0 | 400862.3711 | 400862.3711
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | AD: OMNI DESIGN - CPC ACCOUNT | 083 | CLOSED | 20865 | 0 | 20865 | 20865
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | ANTS: PROGRAM AND TEST PULL STATIONS - TECH PARK LABS 1A & 1E | 083 | CLOSED | 114.336 | 0 | 662.328 | 662.328
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | CP: PROJECT CONTINGENCY - CPC ACCOUNT | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | CP: PROJECT CONTINGENCY - TRUST | 083 | CLOSED | 5750.02 | 0 | 0 | 0
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | IN: RENOVATE SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | 083 | CLOSED | 530.208 | 0 | 629.622 | 629.622
PJ0003519 | TENANT IMPROVEMENT SPACE FOR EDA - BLD 83 TECH PARK LABS 1A & 1E | KUENTZEL, DOUGLAS A. | CLOSED | 2010-08-06 | MO: MOVE OWNER'S PROJECT ELECTRIC TRANSFORMERS - TUES 4/19/11 | 083 | CLOSED | 189 | 0 | 22.728 | 22.728
PJ0003519 Total | [7 empty] | 428310.903 | 0 | 423042.0491 | 423042.0491
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | AD: CAME SECURITY (DIRECT PAY INVOICE) | 058 | CLOSED | 133.75 | 0 | 133.75 | 133.75
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | AD: GOSS ENGINEERING | 058 | CLOSED | 8453 | 0 | 8453 | 8453
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | AD: JOC 10.021.013 STAPLES | 058 | CLOSED | 54291.1901 | 0 | 54291.1901 | 54291.1901
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | AD: MCKENNA ENVIRONMENTAL | 058 | CLOSED | 782.17 | 0 | 782.17 | 782.17
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | AD: MECA | 058 | CLOSED | 5467.7 | 0 | 2658.415 | 2658.415
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | AD: QUAGLINO ROOFING (DIRECT-PAY INVOICE) | 058 | CLOSED | 0 | 0 | 262.15 | 262.15
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 2190.04 | 0 | 0 | 0
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | CPE: INSTALL DUCT WORK | 058 | CLOSED | 10944.4704 | 0 | 10655.664 | 10655.664
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | EL: REMODEL FOR NEW OFFICES | 058 | CLOSED | 10987.2348 | 0 | 11748.113 | 11748.113
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | IN: MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | 058 | CLOSED | 530.208 | 0 | 394.326 | 394.326
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | LO: INSTALL LOCKS IN NEW DOORS | 058 | CLOSED | 2972.8022 | 0 | 2309.718 | 2309.718
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | PA: PAINT NEW OFFICES | 058 | CLOSED | 6480.2278 | 0 | 4724.736 | 4724.736
PJ0003515 | MAKE SPACE USABLE FOR ANTS MOVE IN - BLD 58 RM 102 | LAMPMAN, GREG | CLOSED | 2010-07-29 | PL: INSTALL DRINKING FOUNTAIN | 058 | CLOSED | 1783.6277 | 0 | 1908.624 | 1908.624
PJ0003515 Total | [7 empty] | 105016.421 | 0 | 98321.8561 | 98321.8561
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | AD: BIG STEVE'S CHIMNEY SERVICE (MAINT) | 126 | CLOSED | 0 | 0 | 139 | 139
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | CA:COMPLETE MAINTENANCE AT CHORRO CREEK HOUSE | 126 | CLOSED | 0 | 0 | 1660.3 | 1660.3
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | CP: PROJECT CONTINGENCY | 126 | CLOSED | 0 | 0 | 0 | 0
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | EH&S: REPAIRS TO CHORRO CREEK RANCH HOUSE (N/L) | 126 | CLOSED | 0 | 0 | 0 | 0
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | EL: CHECK VOLTAGE AT CHORRO CREEK GARAGE | 126 | CLOSED | 0 | 0 | 1759.04 | 1759.04
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | ES: PM CHORRO CREEK HOUSE HEATING SYSTEM | 126 | CLOSED | 0 | 0 | 1646.88 | 1646.88
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | LA:TRIM BUSHES AWAY FROM CHORRO CREEK HOUSE (N/L) | 126 | CLOSED | 0 | 0 | 0 | 0
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | PA:PAINT EXTERIOR OF CHORRO CREEK HOUSE AND GARAGE | 126 | CLOSED | 0 | 0 | 6478.9 | 6478.9
PJ0003514 | MAINTENACNE AT CHORRO CREEK RANCH HOUSE (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2010-07-26 | PL:PM PLUMBING ITEMS AT CHORRO CREEK HOUSE | 126 | CLOSED | 0 | 0 | 537.4911 | 537.4911
PJ0003514 Total | [7 empty] | 0 | 0 | 12221.6111 | 12221.6111
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: COASTAL DEMO | 051 | CLOSED | 556.25 | 0 | 556.25 | 556.25
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: G & J TILE | 051 | CLOSED | 2140 | 0 | 2140 | 2140
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: HYDREX PEST CONTROL | 051 | CLOSED | 3220 | 0 | 3220 | 3220
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: JOC 10.021.008 STAPLES | 051 | CLOSED | 62957.67 | 0 | 63715.01 | 63715.01
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: MAINO CONSTRUCTION | 051 | CLOSED | 5000 | 0 | 4979.99 | 4979.99
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: QUAGLINO ROOFING | 051 | CLOSED | 13919 | 0 | 13961.98 | 13961.98
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: SAN LUIS GLASS | 051 | CLOSED | 4877.22 | 0 | 4880.47 | 4880.47
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: SHORELINE AWNINGS | 051 | CLOSED | 15033 | 0 | 16533 | 16533
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | AD: TED MULLER PLASTERING | 051 | CLOSED | 14280 | 0 | 14180 | 14180
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | CA:RENOVATION WORK ON THE UNIVERSITY HOUSE | 051 | CLOSED | 19237.092 | 0 | 34029.9025 | 34029.9025
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | EL:INSTALL NEW PANEL, SMOKE DET, MISC RENOVATION AT U. HOUSE | 051 | CLOSED | 16270.0756 | 0 | 7969.2163 | 7969.2163
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | EO:RENOVATION WORK AT UNIVERSITY HOUSE | 051 | CLOSED | 3089.6 | 0 | 1505.0625 | 1505.0625
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | IN: SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | 051 | CLOSED | 441.84 | 0 | 441.84 | 441.84
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | LA:RENOVATION AT UNIVERSITY HOUSE | 051 | CLOSED | 12691.2 | 0 | 11032.14 | 11032.14
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | PA:RENOVATION WORK AT UNIVERSITY HOUSE | 051 | CLOSED | 10232.602 | 0 | 20661.78 | 20661.78
PJ0003513 | SR 10/11: RENOVATE UNIVERSITY HOUSE - BLD 51 | MAY, TOM | CLOSED | 2010-07-26 | PL:RENOVATION WORK AT UNIVERSITY HOUSE | 051 | CLOSED | 4119.2 | 0 | 582.78 | 582.78
PJ0003513 Total | [7 empty] | 188064.7496 | 0 | 200389.4213 | 200389.4213
PJ0003512 | ROOF MAINTENANCE & REPAIRS - CORPORATION WHSE. BLDG. 82 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | AD: JOC 10.020.025 STAPLES | 082 | CLOSED | 41672.1344 | 0 | 41673.0118 | 41673.0118
PJ0003512 | ROOF MAINTENANCE & REPAIRS - CORPORATION WHSE. BLDG. 82 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 4167.21 | 0 | 0 | 0
PJ0003512 Total | [7 empty] | 45839.3444 | 0 | 41673.0118 | 41673.0118
PJ0003511 | ROOF REPLACEMENT- BLD 15 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | AD: MCGRAW-HILL - FOR TRACKING ONLY (MAINT) | 015 | CLOSED | 1454.67 | 0 | 1359.5 | 1359.5
PJ0003511 | ROOF REPLACEMENT- BLD 15 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | AD: QUAGLINO ROOFING | 015 | CLOSED | 111437.29 | 0 | 111437.29 | 111437.29
PJ0003511 | ROOF REPLACEMENT- BLD 15 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 11344.3 | 0 | 0 | 0
PJ0003511 | ROOF REPLACEMENT- BLD 15 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | EH&S: ROOF REPLACEMENT- BLD 15 | 015 | CLOSED | 129.792 | 0 | 237.696 | 237.696
PJ0003511 | ROOF REPLACEMENT- BLD 15 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-22 | IN: ROOF REPLACEMENT- BLD 15 | 015 | CLOSED | 265.104 | 0 | 497.07 | 497.07
PJ0003511 Total | [7 empty] | 124631.156 | 0 | 113531.556 | 113531.556
PJ0003509 | SR 10/11: REPLACE ALL SEVEN SKYLIGHTS - DAIRY 18 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-23 | AD: JOC 10.020.035 STAPLES | 018A | CLOSED | 42910.76 | 0 | 42910.76 | 42910.76
PJ0003509 | SR 10/11: REPLACE ALL SEVEN SKYLIGHTS - DAIRY 18 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-23 | CA: PURCHASE AND INSTALL GUTTERS AT DPTC - 18A | 018A | CLOSED | 2846 | 0 | 2100.175 | 2100.175
PJ0003509 | SR 10/11: REPLACE ALL SEVEN SKYLIGHTS - DAIRY 18 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-23 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 0 | 0 | 0 | 0
PJ0003509 Total | [7 empty] | 45756.76 | 0 | 45010.935 | 45010.935
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | AD: DIVISION OF STATE ARCHITECT (CHARGED TO PROJECT CFS) | 065 | CLOSED | 500 | 0 | 400 | 400
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | AD: JOC 10.020.030 | 065 | CLOSED | 49088.925 | 0 | 48517.0635 | 48517.0635
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | AD: MECA | 065 | CLOSED | 4725.4624 | 0 | 3576.475 | 3576.475
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 4467.28 | 0 | 0 | 0
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | EL: RELOCATE GAMES POWER/BILLIARDS LIGHTING; REMOVE SOUND SYSTEM | 065 | CLOSED | 6086.64 | 0 | 6601.5415 | 6601.5415
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | IN: EXPAND BACKSTAGE PIZZA | 065 | CLOSED | 397.656 | 0 | 364.518 | 364.518
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | LO: CORES AT BACKSTAGE PIZZA | 065 | CLOSED | 643.008 | 0 | 141.168 | 141.168
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | PA: PAINT WALL IN BACKSTAGE PIZZA | 065 | CLOSED | 1743.84 | 0 | 949.74 | 949.74
PJ0003507 | EXPAND BACKSTAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-21 | PL: CAP PIPES | 065 | CLOSED | 127.152 | 0 | 127.152 | 127.152
PJ0003507 Total | [7 empty] | 67779.9634 | 0 | 60677.658 | 60677.658
PJ0003506 | REPLACE ADVERTISMENT PANEL/REPAIR DONOR PLAQUE - SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2010-07-20 | AD: FLUORESCO | 061 | CLOSED | 3497.83 | 0 | 3610.3833 | 3610.3833
PJ0003506 | REPLACE ADVERTISMENT PANEL/REPAIR DONOR PLAQUE - SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2010-07-20 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 160.65 | 0 | 0 | 0
PJ0003506 Total | [7 empty] | 3658.48 | 0 | 3610.3833 | 3610.3833
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | AD: REPUBLIC ELEVATOR FOR SEPT 11 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 2321.86 | 2321.86
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | AD: REPUBLIC ELEVATOR FOR SEPT 4 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 1547.9 | 1547.9
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | AD: REPUBLIC ELEVATOR SUPPORT FOR 10/23 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 1934.88 | 1934.88
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | AD: REPUBLIC ELEVATOR SUPPORT FOR 10/30 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 1736.67 | 1736.67
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | AD: REPUBLIC ELEVATOR SUPPORT FOR 11/13 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 2267.61 | 2267.61
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: DELIVER BOARDS & STANCHIONS FOR NOV 13 FOOTBALL GAME. | 061 | CLOSED | 0 | 0 | 110.76 | 110.76
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: DELIVER BOARDS & STANCHIONS FOR OCT 23 FOOTBALL GAME. | 061 | CLOSED | 0 | 0 | 304.59 | 304.59
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: DELIVER BOARDS & STANCHIONS FOR OCT 30 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 664.56 | 664.56
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: DELIVER BOARDS AND STANCHIONS FOR SEPT 11 FOOTBALL. | 061 | CLOSED | 0 | 0 | 276.9 | 276.9
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: DELIVER STANCHIONS FOR FOOTBALL GAME BEFORE SEP 4. | 061 | CLOSED | 0 | 0 | 498.42 | 498.42
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: REMOVE 4 SEATS BY 10/27 IN EVENING - SPANOS STADIUM 61 | 061 | CLOSED | 0 | 0 | 387.66 | 387.66
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: REPAIR BROKEN CHAIR AT SPANOS STADIUM. | 061 | CLOSED | 0 | 0 | 787.524 | 787.524
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: SUPPORT FOR FOOTBALL V. ST FRANCIS UNIC - 10/30 | 061 | CLOSED | 0 | 0 | 254.064 | 254.064
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: SUPPORT FOR FOOTBALL V. UC DAVIS - 11/13 | 061 | CLOSED | 0 | 0 | 254.064 | 254.064
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: SUPPORT FOR FOOTBALL V. UNIV OF NORTH DAKOTA - OCT 23 | 061 | CLOSED | 0 | 0 | 269.943 | 269.943
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CPE: SUPPORT FOR FOOTBALL V. MONTANA - 9/11 | 061 | CLOSED | 0 | 0 | 367.2 | 367.2
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CPE: SUPPORT FOR FOOTBALL V. ST FRANCIS UNIC - 10/30 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CPE: SUPPORT FOR FOOTBALL V. UC DAVIS - 11/13 | 061 | CLOSED | 0 | 0 | 367.2 | 367.2
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CPE: SUPPORT FOR FOOTBALL V. UNIV NORTH DAKOTA - 10/23 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR FOOTBALL V. HUMBOLDT ST - SEPT 4 | 061 | CLOSED | 0 | 0 | 3216.51 | 3216.51
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR FOOTBALL V. ST FRANCIS UNIV(HOMECOMING) - OCT 30 | 061 | CLOSED | 0 | 0 | 4026.78 | 4026.78
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR FOOTBALL V. UC DAVIS - NOV 13 | 061 | CLOSED | 0 | 0 | 4100.58 | 4100.58
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR FOOTBALL V. UNIC OF MONTANA - SEPT 11 | 061 | CLOSED | 0 | 0 | 3500.1 | 3500.1
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR FOOTBALL V. UNIV OF NORTH DAKOTA - OCT 23 | 061 | CLOSED | 0 | 0 | 3950.1 | 3950.1
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR SPRING FOOTBALL GAME- APRIL 30 | 061 | CLOSED | 0 | 0 | 1203.84 | 1203.84
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: INSTALL SPIDER BOX AT CHASE HALL BEFORE SAT 10/30 - 11AM | 115 | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: INSTALL SPIDER BOX FOR EVENT BEFORE OCT 30 AT O'NEILL | 003 | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: INSTALL SPIDER BOX FOR EVENT ON OCT 23 AT O'NEILL LAWN. | 061 | CLOSED | 0 | 0 | 136.212 | 136.212
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: SUPPORT FOR FOOTBALL V. HUMBOLDT ST - SEPT 4 | 061 | CLOSED | 0 | 0 | 690.1258 | 690.1258
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: SUPPORT FOR FOOTBALL V. ST FRANCIS UNIV - 10/30 | 061 | CLOSED | 0 | 0 | 622.278 | 622.278
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: SUPPORT FOR FOOTBALL V. UC DAVIS - 11/13 | 061 | CLOSED | 0 | 0 | 705.6354 | 705.6354
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: SUPPORT FOR FOOTBALL V. UNIV OF MONTANA - SEPT 11 | 061 | CLOSED | 0 | 0 | 938.994 | 938.994
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: SUPPORT FOR FOOTBALL V. UNIV OF NORTH DAKOTA - OCT 23 | 061 | CLOSED | 0 | 0 | 604.542 | 604.542
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: FIELD PREP MATERIALS FOR 10/11 FOOTBALL SEASON | 061 | CLOSED | 0 | 0 | 5673.396 | 5673.396
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: FOOTBALL STRIPING FOR PRACTICES BEGINNING AUG 9 | 061 | CLOSED | 0 | 0 | 6917.916 | 6917.916
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: STRIPING FOR WOMEN'S SOCCER PRACTICE BEGINNING 8/9 | 061 | CLOSED | 0 | 0 | 1194.22 | 1194.22
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOOTBALL V HUMBOLDT ST - SEPT 4 | 061 | CLOSED | 0 | 0 | 7788.288 | 7788.288
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOOTBALL V ST FRANCIS UNIV. (HOMECOMING) - OCT 30 | 061 | CLOSED | 0 | 0 | 6389.4 | 6389.4
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOOTBALL V UC DAVIS - NOV 13 | 061 | CLOSED | 0 | 0 | 5121.816 | 5121.816
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOOTBALL V UNIV OF MONTANA - SEPT 11 | 061 | CLOSED | 0 | 0 | 9046.173 | 9046.173
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOOTBALL V UNIV OF NORTH DAKOTA - OCT 23 | 061 | CLOSED | 0 | 0 | 9285.168 | 9285.168
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR 2011 SPRING FOOTBALL PRACTICES(NOT GAME) (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR FOOTBALL GREEN AND GOLD GAME - AUG 21 | 061 | CLOSED | 0 | 0 | 2271.696 | 2271.696
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR SPRING FOOTBALL GAME APR 30 SPANOS STAD | 061 | CLOSED | 0 | 0 | 1284.684 | 1284.684
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PERMIT: 20X40 CANOPY - 1960 MEMORIAL REUNION-MEMORIAL PLAZA | 061 | CLOSED | 0 | 0 | 49.707 | 49.707
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR FOOTBALL V. HUMBOLDT ST - SEPT 4 | 061 | CLOSED | 0 | 0 | 127.152 | 127.152
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR FOOTBALL V. ST FRANCIS UNIV - 10/30 | 061 | CLOSED | 0 | 0 | 328.158 | 328.158
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR FOOTBALL V. UC DAVIS - 11/13 | 061 | CLOSED | 0 | 0 | 291.696 | 291.696
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR FOOTBALL V. UNIV OF MONTANA - SEPT 11 | 061 | CLOSED | 0 | 0 | 491.772 | 491.772
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR FOOTBALL V. UNIV OF NORTH DAKOTA - OCT 23 | 061 | CLOSED | 0 | 0 | 736.728 | 736.728
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | RE: SUPPORT FOR FOOTBALL V. MONTANA - 9/11 | 003 | CLOSED | 0 | 0 | 566.436 | 566.436
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | RE: SUPPORT FOR FOOTBALL V. ST FRANCIS UNIV - 10/30 | 003 | CLOSED | 0 | 0 | 413.934 | 413.934
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | RE: SUPPORT FOR FOOTBALL V. UC DAVIS - 11/13 (N/L) | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | RE: SUPPORT FOR FOOTBALL V. UNIV OF NORTH DAKOTA-10/23 | 003 | CLOSED | 0 | 0 | 348.576 | 348.576
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | SUPPLY RENTAL: FOOTBALL TAILGATE BBQ - 10/22 | 003 | CLOSED | 0 | 0 | 75 | 75
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | SUPPLY RENTAL: FOOTBALL TAILGATE BBQ - 10/28 | 003 | CLOSED | 0 | 0 | 75 | 75
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | SUPPLY RENTAL: FOOTBALL TAILGATE BBQ - 11/12 | 003 | CLOSED | 0 | 0 | 75 | 75
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | SUPPLY RENTAL: FOOTBALL TAILGATE BBQ - 9/10 | 003 | CLOSED | 0 | 0 | 75 | 75
PJ0003504 | 10/11 FOOTBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | SUPPLY RENTAL: FOOTBALL TAILGATE BBQ - 9/4 | 003 | CLOSED | 0 | 0 | 75 | 75
PJ0003504 Total | [7 empty] | 0 | 0 | 97034.9162 | 97034.9162
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. AZUSA PACIFIC-AUG 18 (N/L) | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. CSU BAKERSFIELD - OCT 31 | 163 | CLOSED | 0 | 0 | 978.12 | 978.12
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. CSU NORTHRIDGE - OCT 10 | 163 | CLOSED | 0 | 0 | 1241.46 | 1241.46
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. NORTH CAROLINA - SEPT 10 | 163 | CLOSED | 0 | 0 | 2193.048 | 2193.048
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. PACIFIC - OCT 15 | 163 | CLOSED | 0 | 0 | 1730.52 | 1730.52
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. SAN JOSE ST - SEPT 3 | 163 | CLOSED | 0 | 0 | 1448.37 | 1448.37
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. SEATTLE UNIV. - OCT 17 | 163 | CLOSED | 0 | 0 | 1147.41 | 1147.41
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. UC IRVINE - OCT 8 | 163 | CLOSED | 0 | 0 | 1655.28 | 1655.28
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. UCSB - OCT 29 | 163 | CLOSED | 0 | 0 | 1222.65 | 1222.65
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR W. SOCCER V. WEBER ST - SEPT 19 | 163 | CLOSED | 0 | 0 | 977.634 | 977.634
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT WOMEN'S SOCCER V USC-APRIL 15 AT 6PM | 061 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: STRIPING FOR WOMEN'S SOCCER PRATICE | 061 | CLOSED | 0 | 0 | 80.736 | 80.736
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. PACIFIC - OCT 15 | 163 | CLOSED | 0 | 0 | 704.076 | 704.076
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. AZUSA PACIFIC-AUG 18 | 061 | CLOSED | 0 | 0 | 611.46 | 611.46
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. CSU BAKERSFIELD - OCT 31. | 163 | CLOSED | 0 | 0 | 266.271 | 266.271
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. CSU NORTHRIDGE - OCT 10 | 163 | CLOSED | 0 | 0 | 486.234 | 486.234
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. NORTH CAROLINA - SEPT 10 | 061 | CLOSED | 0 | 0 | 826.392 | 826.392
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. SAN JOSE ST - SEPT 3 | 061 | CLOSED | 0 | 0 | 546.18 | 546.18
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. SEATTLE UNIV - OCT 17 | 163 | CLOSED | 0 | 0 | 555.696 | 555.696
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. UC IRVINE - OCT 8 | 061 | CLOSED | 0 | 0 | 607.641 | 607.641
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. UCSB - OCT 29 | 163 | CLOSED | 0 | 0 | 283.182 | 283.182
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR W. SOCCER V. WEBER STATE - SEPT 19 (N/L) | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0003503 | 10/11 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT WOMEN'S SOCCER V. USC - APRIL 15 AT 6PM | 061 | CLOSED | 0 | 0 | 459.504 | 459.504
PJ0003503 Total | [7 empty] | 0 | 0 | 18071.058 | 18071.058
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | AD: REPUBLIC ELEV SUPPORT FOR MENS SOCCER V UCSB-10/27 | 061 | CLOSED | 0 | 0 | 1986.79 | 1986.79
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CA: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 27 | 061 | CLOSED | 0 | 0 | 238.728 | 238.728
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 0 | 0 | 0 | 0
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CPE: CHECK AC UNITS AT SPANOS STADIUM SUITES BEFORE 8/25 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: GAME PREP FOR SOCCER SEASON ON AUG 21 | 163 | CLOSED | 0 | 0 | 2448.51 | 2448.51
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V CAL ST BAKERSFIELD - SEPT 29 | 163 | CLOSED | 0 | 0 | 1635.984 | 1635.984
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V CSU FULLERTON - NOV 3 | 163 | CLOSED | 0 | 0 | 1504.8 | 1504.8
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V CSU NORTHRIDGE - OCT 6 | 163 | CLOSED | 0 | 0 | 1635.984 | 1635.984
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V LOYOLA - SEPT 23 | 163 | CLOSED | 0 | 0 | 1316.7 | 1316.7
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V MEXICAN NATL TEAM - AUG25 | 163 | CLOSED | 0 | 0 | 1786.95 | 1786.95
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V UC DAVIS- OCT 24 | 163 | CLOSED | 0 | 0 | 1354.32 | 1354.32
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V UC IRVINE - OCTOBER 16 | 163 | CLOSED | 0 | 0 | 1889.676 | 1889.676
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V UC SANTA BARBARA - OCT 27 | 163 | CLOSED | 0 | 0 | 2706.228 | 2706.228
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V UC SANTA CRUZ - AUG28 | 163 | CLOSED | 0 | 0 | 1391.94 | 1391.94
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR M. SOCCER V UCLA - SEPT 17 | 163 | CLOSED | 0 | 0 | 2169.414 | 2169.414
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR MEN'S SOCCER V FRESNO FUEGO-APR 2 5PM | 061 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT MEN'S SOCCER V. STANDFORD-APR 23 AT 7PM | 061 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT MEN'S SOCCER V. USF - APRIL 30 AT 7PM | 061 | CLOSED | 0 | 0 | 752.4 | 752.4
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | EL: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 27 (TELEVISED) | 061 | CLOSED | 0 | 0 | 626.94 | 626.94
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | ES: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 27 7PM-10'ISH | 061 | CLOSED | 0 | 0 | 239.148 | 239.148
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: MEN'S SOCCER V FRESNO FUEGO - APRIL 2 AT 5PM | 061 | CLOSED | 0 | 0 | 439.926 | 439.926
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: STRIPING FOR MENS SOCCER PRACTICES - SC#4 | 061 | CLOSED | 0 | 0 | 161.472 | 161.472
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V CAL ST BAKERSFIELD - SEPT 29 | 163 | CLOSED | 0 | 0 | 653.646 | 653.646
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V CSU FULLERTON - NOV 3 | 163 | CLOSED | 0 | 0 | 520.056 | 520.056
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V CSU NORTHRIDGE - OCT 6 | 163 | CLOSED | 0 | 0 | 415.56 | 415.56
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V LOYOLA - SEPT 23 | 163 | CLOSED | 0 | 0 | 508.782 | 508.782
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V UC DAVIS - OCT 24 | 163 | CLOSED | 0 | 0 | 378.768 | 378.768
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V UC IRVINE - OCT 16 | 163 | CLOSED | 0 | 0 | 100.92 | 100.92
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V UC SANTA CRUZ - AUG28 | 163 | CLOSED | 0 | 0 | 786.024 | 786.024
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V UCLA - SEPT 17 | 163 | CLOSED | 0 | 0 | 1138.668 | 1138.668
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR M. SOCCER V UCSB - OCT 27 | 163 | CLOSED | 0 | 0 | 740.928 | 740.928
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT FOR MEN'S SOCCER VS MEXICAN NATIONAL TEAM - 8/25/10 | 061 | CLOSED | 0 | 0 | 625.158 | 625.158
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT MEN'S SOCCER V STANFORD-APR 23 AT 7PM | 061 | CLOSED | 0 | 0 | 349.068 | 349.068
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | LA: SUPPORT MEN'S SOCCER V. USF - APRIL 30 AT 7PM | 061 | CLOSED | 0 | 0 | 840.636 | 840.636
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR MEN'S SOCCER V MEXICAN NATL TEAM - 8/25 | 061 | CLOSED | 0 | 0 | 105.96 | 105.96
PJ0003502 | 10/11 MEN'S SOCCER (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | PL: SUPPORT FOR MEN'S SOCCER V. UCSB - OCT 27 | 061 | CLOSED | 0 | 0 | 274.08 | 274.08
PJ0003502 Total | [7 empty] | 0 | 0 | 31848.598 | 31848.598
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. CSU BAKERSFIELD - SEPT 19 | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. CSU FULLERTON - OCT 1 | 042 | CLOSED | 0 | 0 | 357.39 | 357.39
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. CSU LONG BEACH - OCT 2 | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. CSU NORTHRIDGE - OCT 22 | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. UC DAVIS - NOV 13 | 042 | CLOSED | 0 | 0 | 620.73 | 620.73
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. UC IRVINE - OCT 23 | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. UC RIVERSIDE - OCT 8 | 042 | CLOSED | 0 | 0 | 526.68 | 526.68
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. UC SANTA BARBARA - OCT 9 | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003501 | 10/11 WOMEN'S VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2010-07-19 | CU: SUPPORT FOR VOLLEYBALL V. UNIV OF PACIFIC - NOV 12 | 042 | CLOSED | 0 | 0 | 592.515 | 592.515
PJ0003501 Total | [7 empty] | 0 | 0 | 4805.955 | 4805.955
PJ0003500 | INSTALL 3 DOORS W/WINDOWS - ADMIN RMS 216 & 217 | MAY, TOM | CLOSED | 2010-07-13 | CA:INSTALL (3) NEW DOORS ADM 216/217 | 001 | CLOSED | 3889.4028 | 0 | 3732.024 | 3732.024
PJ0003500 | INSTALL 3 DOORS W/WINDOWS - ADMIN RMS 216 & 217 | MAY, TOM | CLOSED | 2010-07-13 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 559.04 | 0 | 0 | 0
PJ0003500 | INSTALL 3 DOORS W/WINDOWS - ADMIN RMS 216 & 217 | MAY, TOM | CLOSED | 2010-07-13 | IN: INSTALL 3 DOORS W/WINDOWS - ADMIN RMS 216 & 217 (N/L) | 001 | CLOSED | 66.276 | 0 | 0 | 0
PJ0003500 | INSTALL 3 DOORS W/WINDOWS - ADMIN RMS 216 & 217 | MAY, TOM | CLOSED | 2010-07-13 | LO:INSTALL LOCKSETS IN (3) NEW DOORS ADM 216/217 | 001 | CLOSED | 1177.344 | 0 | 216.888 | 216.888
PJ0003500 | INSTALL 3 DOORS W/WINDOWS - ADMIN RMS 216 & 217 | MAY, TOM | CLOSED | 2010-07-13 | PA:STAIN (3) NEW DOORS ADM 216/217 | 001 | CLOSED | 457.536 | 0 | 556.74 | 556.74
PJ0003500 Total | [7 empty] | 6149.5988 | 0 | 4505.652 | 4505.652
PJ0003499 | REMOVE SINK, COUNTER, PVC LINES, PATCH/PAINT-BLD13 RM124(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2010-07-13 | CA: REMOVE SINK & CABNETRY; INSTALL FLOOR TILE & COVEBASE 13-124 | 013 | CLOSED | 0 | 0 | 611.094 | 611.094
PJ0003499 | REMOVE SINK, COUNTER, PVC LINES, PATCH/PAINT-BLD13 RM124(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2010-07-13 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0003499 | REMOVE SINK, COUNTER, PVC LINES, PATCH/PAINT-BLD13 RM124(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2010-07-13 | PA: REPAIR HOLES, FINISH, AND PAINT WALL - BLDG. 13 RM. 124 | 013 | CLOSED | 0 | 0 | 341.568 | 341.568
PJ0003499 | REMOVE SINK, COUNTER, PVC LINES, PATCH/PAINT-BLD13 RM124(NO EST) | MOLLAN, CHERYL L. | CLOSED | 2010-07-13 | PL: CAP OFF WATER, AIR, AND GAS SUPPLY BLDG. 13 RM. 124 | 013 | CLOSED | 0 | 0 | 317.88 | 317.88
PJ0003499 Total | [7 empty] | 0 | 0 | 1270.542 | 1270.542
PJ0003498 | MJ: INSTALL 4 ELECTRICAL METERS - PCV ALISO AND ESTRELLA | ELLIOT, DENNIS K | CLOSED | 2010-07-14 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 0 | 0 | 0 | 0
PJ0003498 | MJ: INSTALL 4 ELECTRICAL METERS - PCV ALISO AND ESTRELLA | ELLIOT, DENNIS K | CLOSED | 2010-07-14 | EL: ASSIST WITH INSTALLATION OF POWER METERS AT PCV | 171 | CLOSED | 507.552 | 0 | 579.576 | 579.576
PJ0003498 | MJ: INSTALL 4 ELECTRICAL METERS - PCV ALISO AND ESTRELLA | ELLIOT, DENNIS K | CLOSED | 2010-07-14 | PCV EL: INSTALL 4 POWER METERS IN PCV ALISO AND ESTRELLA | 171 | CLOSED | 14441.7721 | 0 | 21346.29 | 21346.29
PJ0003498 Total | [7 empty] | 14949.3241 | 0 | 21925.866 | 21925.866
PJ0003497 | SR 10/11: ANNUAL ROAD STRIPING - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2010-07-13 | AD: JOC 10.020.026 STAPLES | GENERAL | CLOSED | 31384.12 | 0 | 31384.12 | 31384.12
PJ0003497 | SR 10/11: ANNUAL ROAD STRIPING - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2010-07-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003497 | SR 10/11: ANNUAL ROAD STRIPING - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2010-07-13 | IN: SR 10/11: ANNUAL ROAD STRIPING - CAMPUS WIDE | GENERAL | CLOSED | 55.23 | 0 | 55.23 | 55.23
PJ0003497 Total | [7 empty] | 31439.35 | 0 | 31439.35 | 31439.35
PJ0003496 | DISASSEMBLE AND REMOVE FURNITURE - BLD 3 RM 455 | MOLLAN, CHERYL L. | CLOSED | 2010-07-12 | CA:DISASSEMBLE OFFICE FURNITURE TO BE REMOVED BY MOVERS | 003 | CLOSED | 304.59 | 0 | 542.643 | 542.643
PJ0003496 | DISASSEMBLE AND REMOVE FURNITURE - BLD 3 RM 455 | MOLLAN, CHERYL L. | CLOSED | 2010-07-12 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 5.55 | 0 | 0 | 0
PJ0003496 | DISASSEMBLE AND REMOVE FURNITURE - BLD 3 RM 455 | MOLLAN, CHERYL L. | CLOSED | 2010-07-12 | CU: REFINISH FLOORS IN BUSINESS BLDG. ROOMS 455/454A | 003 | CLOSED | 286.776 | 0 | 295.164 | 295.164
PJ0003496 | DISASSEMBLE AND REMOVE FURNITURE - BLD 3 RM 455 | MOLLAN, CHERYL L. | CLOSED | 2010-07-12 | MO:REMOVE OFFICE FURNITURE TO E-SURPLUS (NO LABOR) | 003 | CLOSED | 378 | 0 | 0 | 0
PJ0003496 Total | [7 empty] | 974.916 | 0 | 837.807 | 837.807
PJ0003495 | REPLACEMENT OF EXISTING WELL AND WELL WORKS - FIELD 25, WELL #1 | LAMPMAN, GREG | CLOSED | 2010-07-12 | AD: JOC 10.020.029 STAPLES | GENERAL | CLOSED | 87599.3913 | 0 | 87599.3913 | 87599.3913
PJ0003495 | REPLACEMENT OF EXISTING WELL AND WELL WORKS - FIELD 25, WELL #1 | LAMPMAN, GREG | CLOSED | 2010-07-12 | CA: POUR CONCRETE DEADMAN FOR POWER LINE AT FIELD 25 WELL # 1 | GENERAL | CLOSED | 581.52 | 0 | 769.926 | 769.926
PJ0003495 | REPLACEMENT OF EXISTING WELL AND WELL WORKS - FIELD 25, WELL #1 | LAMPMAN, GREG | CLOSED | 2010-07-12 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 4114.9 | 0 | 0 | 0
PJ0003495 | REPLACEMENT OF EXISTING WELL AND WELL WORKS - FIELD 25, WELL #1 | LAMPMAN, GREG | CLOSED | 2010-07-12 | EL: INSTALL NEW PANEL AND HOOK UP PUMP | GENERAL | CLOSED | 5910.8107 | 0 | 5012.196 | 5012.196
PJ0003495 | REPLACEMENT OF EXISTING WELL AND WELL WORKS - FIELD 25, WELL #1 | LAMPMAN, GREG | CLOSED | 2010-07-12 | IN: REPLACEMENT OF EXISTING WELL & WELL WORKS - FIELD 25, WELL#1 | GENERAL | CLOSED | 331.38 | 0 | 130.332 | 130.332
PJ0003495 Total | [7 empty] | 98538.002 | 0 | 93511.8453 | 93511.8453
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: COLE FARMS TRUCKING | 160E | CLOSED | 916.562 | 0 | 570.845 | 570.845
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: EARTH SYSTEMS - BOLT TENSION TEST/FOUNDATION RECOMMENDATIONS | 160E | CLOSED | 2386.5387 | 0 | 2386.5387 | 2386.5387
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: ENGLEKIRK AND SABOL -SEISMIC PEER REVIEW | 160E | CLOSED | 1105.31 | 0 | 1105.31 | 1105.31
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: JOC 11.022.014 STAPLES | 160E | CLOSED | 139441.6082 | 0 | 139441.6082 | 139441.6082
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: JOC 12.024.010 STAPLES | 160E | CLOSED | 32635.2461 | 0 | 32635.2461 | 32635.2461
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: OMNI (TRUST FUND) | 160E | CLOSED | 1142.76 | 0 | 1142.76 | 1142.76
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: OMNI DESIGN (CPC FUNDING) | 160E | CLOSED | 15301 | 0 | 14953.25 | 14953.25
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: QUAGLINO ROOFING (SPLIT FUNDING) | 160E | CLOSED | 408.74 | 0 | 2086.5 | 2086.5
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: SHIPPING CHARGES (TO ENGLEKIRK) | 160E | CLOSED | 0 | 0 | 9.9 | 9.9
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | AD: WCN SPORTS EQUIPMENT | 160E | CLOSED | 49582.516 | 0 | 49123.486 | 49123.486
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | CA: BATTING CAGE GUTTER, FLOOR PREP, ES SUPPORT | 160E | CLOSED | 1027.0781 | 0 | 398.868 | 398.868
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | CP: PROJECT CONTINGENCY (CPC FUNDING) | 160E | CLOSED | 353.1 | 0 | 0 | 0
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | CP: PROJECT CONTINGENCY (TRUST FUND) | 160E | CLOSED | 78.43 | 0 | 0 | 0
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | EL: ELECTRICAL FOR BATTING CAGES - BAGGETT STADIUM | 160E | CLOSED | 16753.332 | 0 | 16687.566 | 16687.566
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | EO: PAVING REMOVAL | 160E | CLOSED | 99.528 | 0 | 621.096 | 621.096
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | ES: INSTALL HEAT EXHAUST VENTILATION | 160E | CLOSED | 2783.7456 | 0 | 3128.004 | 3128.004
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | IN: RENOVATE BATTING CAGES - BAGGETT STADIUM | 160E | CLOSED | 896.784 | 0 | 896.784 | 896.784
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | LA: CLEAN UP AND DISPOSE OF DEBRIS FROM OLD BATTING CAGES | 160E | CLOSED | 935.136 | 0 | 845.244 | 845.244
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | LO: PROVIDE ORANGE CORE PADLOCK FOR BATTING CAGE PROJECT | 160E | CLOSED | 60 | 0 | 92.511 | 92.511
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | PA: PAINTING FOR BAGGETT STADIUM BATTING CAGE RENOVATIONS | 160E | CLOSED | 1189.824 | 0 | 474.912 | 474.912
PJ0003494 | RENOVATE BATTING CAGES - BAGGETT STADIUM | KUENTZEL, DOUGLAS A. | CLOSED | 2010-07-09 | PL: CAP WATER PIPE | 160E | CLOSED | 0 | 0 | 130.584 | 130.584
PJ0003494 Total | [7 empty] | 267097.2387 | 0 | 266731.013 | 266731.013
PJ0003491 | INSTALL LOW PILE CARPET, DIRECTOR'S OFF., HIGH TRAFFIC-BLD 9 RM1 | LAMPMAN, GREG | CLOSED | 2010-07-01 | AD: FLOOR CONNECTION | 009 | CLOSED | 1451.776 | 0 | 1451.776 | 1451.776
PJ0003491 | INSTALL LOW PILE CARPET, DIRECTOR'S OFF., HIGH TRAFFIC-BLD 9 RM1 | LAMPMAN, GREG | CLOSED | 2010-07-01 | CA: REMOVE BASE AND CUT BOTTOM OF DOORS | 009 | CLOSED | 221.52 | 0 | 143.01 | 143.01
PJ0003491 | INSTALL LOW PILE CARPET, DIRECTOR'S OFF., HIGH TRAFFIC-BLD 9 RM1 | LAMPMAN, GREG | CLOSED | 2010-07-01 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 195.77 | 0 | 0 | 0
PJ0003491 | INSTALL LOW PILE CARPET, DIRECTOR'S OFF., HIGH TRAFFIC-BLD 9 RM1 | LAMPMAN, GREG | CLOSED | 2010-07-01 | CU: STRIP TILE FLOOR | 009 | CLOSED | 218.577 | 0 | 163.98 | 163.98
PJ0003491 | INSTALL LOW PILE CARPET, DIRECTOR'S OFF., HIGH TRAFFIC-BLD 9 RM1 | LAMPMAN, GREG | CLOSED | 2010-07-01 | IN:INSTALL LOW PILE HIGH-TRAFFIC CARPET-DIRECTOR'S OFF-BLD 9 RM1 | 009 | CLOSED | 66.276 | 0 | 132.552 | 132.552
PJ0003491 Total | [7 empty] | 2153.919 | 0 | 1891.318 | 1891.318
PJ0003486 | INSTALL CEILING PROJECTOR MOUNT & ELECTRICAL - BLD 4 RM 115 | MAY, TOM | CLOSED | 2010-06-24 | CA:INSTALL PROJECTOR MOUNT IN 04-115 | 004 | CLOSED | 126.8202 | 0 | 56.916 | 56.916
PJ0003486 | INSTALL CEILING PROJECTOR MOUNT & ELECTRICAL - BLD 4 RM 115 | MAY, TOM | CLOSED | 2010-06-24 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 46.61 | 0 | 0 | 0
PJ0003486 | INSTALL CEILING PROJECTOR MOUNT & ELECTRICAL - BLD 4 RM 115 | MAY, TOM | CLOSED | 2010-06-24 | EL:RUN ELECTRICAL TO CEILING PROJECTOR IN 04-115 | 004 | CLOSED | 339.208 | 0 | 397.338 | 397.338
PJ0003486 Total | [7 empty] | 512.6382 | 0 | 454.254 | 454.254
PJ0003485 | INSTALL POWER DROPS AND REPAIR FLOOR TILE - BLD 20 RM 132 | MAY, TOM | CLOSED | 2010-06-23 | CA:FLOOR TILE REPAIR/NAIL REMOVAL 20-132 | 020 | CLOSED | 254.1942 | 0 | 572.532 | 572.532
PJ0003485 | INSTALL POWER DROPS AND REPAIR FLOOR TILE - BLD 20 RM 132 | MAY, TOM | CLOSED | 2010-06-23 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 295.68 | 0 | 0 | 0
PJ0003485 | INSTALL POWER DROPS AND REPAIR FLOOR TILE - BLD 20 RM 132 | MAY, TOM | CLOSED | 2010-06-23 | EL:INSTALL (8) POWER DROPS ON (E) OVERHEAD RACEWAY 20-132 | 020 | CLOSED | 2570.208 | 0 | 2900.7922 | 2900.7922
PJ0003485 | INSTALL POWER DROPS AND REPAIR FLOOR TILE - BLD 20 RM 132 | MAY, TOM | CLOSED | 2010-06-23 | IN: INSTALL POWER DROPS AND REPAIR FLOOR TILE - BLD 20 RM 132 | 020 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0003485 Total | [7 empty] | 3252.6342 | 0 | 3539.6002 | 3539.6002
PJ0003484 | REPAIR WALL, ADD CHAIR RAIL, HANG BB & PHOTOS - 01-413 (NO EST) | MAY, TOM | CLOSED | 2010-06-22 | CA: INSTALL CHAIR RAIL, HANG BULLETIN BOARD/PICTURE -NEAR 01-413 | 001 | CLOSED | 0 | 0 | 410.838 | 410.838
PJ0003484 | REPAIR WALL, ADD CHAIR RAIL, HANG BB & PHOTOS - 01-413 (NO EST) | MAY, TOM | CLOSED | 2010-06-22 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0003484 Total | [7 empty] | 0 | 0 | 410.838 | 410.838
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | AD: BELFOR | 003 | CLOSED | 24136.89 | 0 | 24136.89 | 24136.89
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | AD: R.F. KOEBER INTERIOR CONTRACTORS | 003 | CLOSED | 5524 | 0 | 5524 | 5524
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | CA: PROVIDE SUPPORT FOR WATER LEAK AT BUSINESS | 003 | CLOSED | 619.2 | 0 | 770.125 | 770.125
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | EL: SR 10/11: REPAIR WATER DAMAGE - BUS 03 | 003 | CLOSED | 3356.58 | 0 | 1334.1948 | 1334.1948
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | ES: REPAIR LEAKING DIA-ELECTRIC COUPLING AT BUSINESS 2ND FLOOR | 003 | CLOSED | 2851.2 | 0 | 2138.705 | 2138.705
PJ0003483 | SR 10/11: REPAIR WATER DAMAGE - BUS 03 | GRIFFIN, PATRICK E | CLOSED | 2010-06-25 | PA:PATCH AND PAINT ROOMS AT BUSINESS FROM FLOOD | 003 | CLOSED | 2156.4 | 0 | 1262.99 | 1262.99
PJ0003483 Total | [7 empty] | 38644.27 | 0 | 35166.9048 | 35166.9048
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | AD: BOB'S CRANE | GENERAL | CLOSED | 0 | 0 | 588.5 | 588.5
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | AD: ENERNOC-COGENT ENGERY (SP PORTION, ONLY) | GENERAL | CLOSED | 92821.8473 | 0 | 93849.0473 | 93849.0473
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | AD: SIEMENS (SP PORTION) | GENERAL | CLOSED | 3625.3526 | 0 | 3625.3526 | 3625.3526
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | CP: PROJECT CONTINGENCY | GENERAL | OPEN | 14001.17 | 0 | 0 | 0
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | EL:SUPPORT FOR MBCX PROJECT | GENERAL | CLOSED | 888.216 | 0 | 944.16 | 944.16
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | ES/CPE: BTU METER COMMISTIONING - SUPPORT MBCX PROJECT | GENERAL | CLOSED | 44870.16 | 0 | 72911.468 | 72911.468
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | ES/CPE:INSTALL BTU METERS (2 AT ENG 3, 1 AT BUSINESS) | GENERAL | CLOSED | 16033.308 | 0 | 17627.964 | 17627.964
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | ES: PURCHASE FLOW METERS (MATERIALS, ONLY) | GENERAL | CLOSED | 16914.204 | 0 | 16914.204 | 16914.204
PJ0003476 | SP 10/11: SUPPORT FOR MBCX PROJECT - BLDS. 02, 03, 41, 192, &197 | ELLIOT, DENNIS K | CONST_COMP | 2010-06-18 | SM: SP 10/11: SUPPORT FOR MBCX PJ - BLDS. 02, 03, 41, 192, &197 | GENERAL | OPEN | 0 | 0 | 0 | 0
PJ0003476 Total | [7 empty] | 189154.2579 | 0 | 206460.6959 | 206460.6959
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | AD: PEAK BIKE RACKS (NO OVERHEAD) | 065 | CLOSED | 4872 | 0 | 4849.6 | 4849.6
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | AD: QUICKCETE (NO OVERHEAD) | 065 | CLOSED | 11894.26 | 0 | 11626.05 | 11626.05
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | AD: SISTEK GRAPHIC ARTS (NO OVERHEAD) | 065 | CLOSED | 1563.6 | 0 | 1521.94 | 1521.94
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | CA:INSTALL SIGN AND BIKE RACKS | 065 | CLOSED | 5888.2 | 0 | 5079.75 | 5079.75
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | EL: PROJECT SUPPORT FOR PEDESTRIAL MALL - UU PLAZA EXPANSION | 065 | CLOSED | 105.74 | 0 | 30.32 | 30.32
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | EO: EXCAVATE BACK FLOW DEVICE. | 065 | CLOSED | 772.4 | 0 | 347.58 | 347.58
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | LA: PLANTING INSTALLATIONS | 065 | CLOSED | 9855.2 | 0 | 10595.18 | 10595.18
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | MO: MOVE BIKE RACKS FROM FACILITIES YARD TO S. PERIMITER PLAZA | 065 | CLOSED | 52.5 | 0 | 42.615 | 42.615
PJ0003475 | SP 10/11: UU PLAZA SO. PERIMETER SUPPORT - THE AVENUE TO REC CTR | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | PL: REPLACE BACKFLOW DEVICE | 065 | CLOSED | 3816.7 | 0 | 1939.0789 | 1939.0789
PJ0003475 Total | [7 empty] | 38820.6 | 0 | 36032.1139 | 36032.1139
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: ASAP REPROGRAPHICS (DIRECT-PAY INVOICE) | RESIDENCE | CLOSED | 77.2 | 0 | 77.2 | 77.2
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: DIVISION OF STATE ARCHITECT | RESIDENCE | CLOSED | 1600 | 0 | 1600 | 1600
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: EARTH SYSTEMS | RESIDENCE | CLOSED | 9095 | 0 | 8843.55 | 8843.55
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: JOC 10.022.013 STAPLES | RESIDENCE | CLOSED | 262976.2433 | 0 | 262976.2433 | 262976.2433
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: JOC 11.022.048.02 STAPLES | RESIDENCE | CLOSED | 30137.2241 | 0 | 30137.2241 | 30137.2241
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: JOC 11.023.011 STAPLES | RESIDENCE | CLOSED | 197980.1419 | 0 | 197980.1419 | 197980.1419
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: OMNI DESIGN | RESIDENCE | CLOSED | 38007.47 | 0 | 38007.47 | 38007.47
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | AD: WALLACE GROUP (PO IN PS WITHOUT CFS CLASS P3474) | RESIDENCE | CLOSED | 2889 | 0 | 2717.8214 | 2717.8214
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 50553.48 | 0 | 0 | 0
PJ0003474 | MJ: NEW WAREHOUSE WEST OF PARKING 371 PCV | BRENNAN, MICHAEL | CLOSED | 2010-06-18 | PA:PAINT PCV WAREHOUSE | RESIDENCE | CLOSED | 4761.84 | 0 | 6048.354 | 6048.354
PJ0003474 Total | [7 empty] | 598077.5993 | 0 | 548388.0047 | 548388.0047
PJ0003473 | SERVICES FOR ASCE CANOE COMPETITION 6/16-6/18 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-06-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003473 | SERVICES FOR ASCE CANOE COMPETITION 6/16-6/18 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-06-18 | CU: CUSTODIAL SUPPORT FOR ASCE CANOE COMPETITION 6/16-6/18 | GENERAL | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003473 | SERVICES FOR ASCE CANOE COMPETITION 6/16-6/18 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-06-18 | LA: LANDSCAPE SUPPORT FOR ASCE CANOE COMPETION 6/16/6/18 | GENERAL | CLOSED | 0 | 0 | 80.736 | 80.736
PJ0003473 Total | [7 empty] | 0 | 0 | 113.532 | 113.532
PJ0003472 | REPAIR CEILINGS - BLD 19 RMS 100 & 105A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | AD: JOC 10.020.008 STAPLES | 019 | CLOSED | 15038.7644 | 0 | 15038.7644 | 15038.7644
PJ0003472 | REPAIR CEILINGS - BLD 19 RMS 100 & 105A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 955.91 | 0 | 0 | 0
PJ0003472 | REPAIR CEILINGS - BLD 19 RMS 100 & 105A | KUENTZEL, DOUGLAS A. | CLOSED | 2010-06-18 | IN: REPAIR CEILINGS - BLD 19 RMS 100 & 105A | 019 | CLOSED | 397.656 | 0 | 331.38 | 331.38
PJ0003472 Total | [7 empty] | 16392.3304 | 0 | 15370.1444 | 15370.1444
PJ0003471 | SR 10/11: RE-ROOF ELECTRIC SHOP | GRIFFIN, PATRICK E | CLOSED | 2010-06-16 | AD: JOC 10.020.020 STAPLES | 070B | CLOSED | 74257.44 | 0 | 74257.44 | 74257.44
PJ0003471 | SR 10/11: RE-ROOF ELECTRIC SHOP | GRIFFIN, PATRICK E | CLOSED | 2010-06-16 | CA:ELECTRIC SHOP RE-ROOF SUPPORT | 070B | CLOSED | 638.225 | 0 | 384.74 | 384.74
PJ0003471 | SR 10/11: RE-ROOF ELECTRIC SHOP | GRIFFIN, PATRICK E | CLOSED | 2010-06-16 | CP: PROJECT CONTINGENCY | 070B | CLOSED | 0 | 0 | 0 | 0
PJ0003471 | SR 10/11: RE-ROOF ELECTRIC SHOP | GRIFFIN, PATRICK E | CLOSED | 2010-06-16 | EH&S: SR 10/11: RE-ROOF ELECTRIC SHOP | 070B | CLOSED | 1241.52 | 0 | 1178.26 | 1178.26
PJ0003471 | SR 10/11: RE-ROOF ELECTRIC SHOP | GRIFFIN, PATRICK E | CLOSED | 2010-06-16 | EL:PROVIDE SUPPORT FOR ELECTRIC SHOP RE-ROOF | 070B | CLOSED | 12156.33 | 0 | 12455.1786 | 12455.1786
PJ0003471 Total | [7 empty] | 88293.515 | 0 | 88275.6186 | 88275.6186
PJ0003468 | SR 10/11: FIRE ALARM UPGRADES - PHASE 3 - GENERAL CAMPUS | MOLLAN, CHERYL L. | CLOSED | 2010-06-16 | AD: ALPHA FIRE | GENERAL | CLOSED | 1200 | 0 | 1200 | 1200
PJ0003468 | SR 10/11: FIRE ALARM UPGRADES - PHASE 3 - GENERAL CAMPUS | MOLLAN, CHERYL L. | CLOSED | 2010-06-16 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1071.96 | 0 | 0 | 0
PJ0003468 | SR 10/11: FIRE ALARM UPGRADES - PHASE 3 - GENERAL CAMPUS | MOLLAN, CHERYL L. | CLOSED | 2010-06-16 | EL:UPGRADE SIMPLEX PANEL TO NOTIFIER (CAMPUS VARIOUS) | GENERAL | CLOSED | 22719.7001 | 0 | 23585.2856 | 23585.2856
PJ0003468 Total | [7 empty] | 24991.6601 | 0 | 24785.2856 | 24785.2856
PJ0003465 | SR 10/11: RE-ROOF BOAT SHED - BLDG 53A | LAMPMAN, GREG | CLOSED | 2010-06-14 | AD: JOC 10.020.015 STAPLES | 053A | CLOSED | 33830.05 | 0 | 33830.05 | 33830.05
PJ0003465 | SR 10/11: RE-ROOF BOAT SHED - BLDG 53A | LAMPMAN, GREG | CLOSED | 2010-06-14 | CP: PROJECT CONTINGENCY | 053A | CLOSED | 0 | 0 | 0 | 0
PJ0003465 | SR 10/11: RE-ROOF BOAT SHED - BLDG 53A | LAMPMAN, GREG | CLOSED | 2010-06-14 | IN: SR 10/11: RE-ROOF BOAT SHED - BLDG 53A | 053A | CLOSED | 110.46 | 0 | 110.46 | 110.46
PJ0003465 Total | [7 empty] | 33940.51 | 0 | 33940.51 | 33940.51
PJ0003464 | SR 10/11 & SR 11/12: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | LAMPMAN, GREG | CLOSED | 2010-06-14 | AD: JOC 10.021.005 STAPLES | GENERAL | CLOSED | 33477.83 | 0 | 33477.83 | 33477.83
PJ0003464 | SR 10/11 & SR 11/12: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | LAMPMAN, GREG | CLOSED | 2010-06-14 | AD: JOC 11.023.010.00 | GENERAL | CLOSED | 59066.66 | 0 | 59066.66 | 59066.66
PJ0003464 | SR 10/11 & SR 11/12: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | LAMPMAN, GREG | CLOSED | 2010-06-14 | AD: OMNI DESIGN | GENERAL | CLOSED | 22500 | 0 | 22500 | 22500
PJ0003464 | SR 10/11 & SR 11/12: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | LAMPMAN, GREG | CLOSED | 2010-06-14 | AD: THE MORRO GROUP (SWCA) | GENERAL | CLOSED | 11300.51 | 0 | 4909.98 | 4909.98
PJ0003464 | SR 10/11 & SR 11/12: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | LAMPMAN, GREG | CLOSED | 2010-06-14 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003464 | SR 10/11 & SR 11/12: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | LAMPMAN, GREG | CLOSED | 2010-06-14 | IN: SR 10/11: GILARDI ROAD BRIDGE REPAIR CONSTRUCTION | GENERAL | CLOSED | 13807.5 | 0 | 640.56 | 640.56
PJ0003464 Total | [7 empty] | 140152.5 | 0 | 120595.03 | 120595.03
PJ0003463 | SR 10/11: ENV. HORT. RESIDENCE - REPLACE ROOF - BLDG 48 | MOLLAN, CHERYL L. | CLOSED | 2010-06-14 | AD: JOC 10.020.004 STAPLES | 048 | CLOSED | 10321.51 | 0 | 10321.51 | 10321.51
PJ0003463 | SR 10/11: ENV. HORT. RESIDENCE - REPLACE ROOF - BLDG 48 | MOLLAN, CHERYL L. | CLOSED | 2010-06-14 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 204.17 | 0 | 0 | 0
PJ0003463 | SR 10/11: ENV. HORT. RESIDENCE - REPLACE ROOF - BLDG 48 | MOLLAN, CHERYL L. | CLOSED | 2010-06-14 | EH&S: SR 10/11: ENV. HORT. RES. - REPLACE ROOF - BLDG 48 (N/L) | 048 | CLOSED | 216.32 | 0 | 0 | 0
PJ0003463 | SR 10/11: ENV. HORT. RESIDENCE - REPLACE ROOF - BLDG 48 | MOLLAN, CHERYL L. | CLOSED | 2010-06-14 | IN: SR 10/11: ENV. HORT. RESIDENCE - REPLACE ROOF - BLDG 48 | 048 | CLOSED | 165.69 | 0 | 138.075 | 138.075
PJ0003463 | SR 10/11: ENV. HORT. RESIDENCE - REPLACE ROOF - BLDG 48 | MOLLAN, CHERYL L. | CLOSED | 2010-06-14 | PA:PAINT EXPOSED WOOD ON EXTERIOR OF BUILDING | 048 | CLOSED | 481.28 | 0 | 929.4178 | 929.4178
PJ0003463 Total | [7 empty] | 11388.97 | 0 | 11389.0028 | 11389.0028
PJ0003461 | REPAIR/PAINT/CLEAN 54 CHAIRS - ALUMNI HOUSE BLD 28 CONF. RM | POPHAM, DONALD J. | CLOSED | 2010-06-03 | CA: REPAIR/REPLACE GLIDES ON CHAIRS IN ALUMNI CONF ROOM | 028 | CLOSED | 221.52 | 0 | 149.25 | 149.25
PJ0003461 | REPAIR/PAINT/CLEAN 54 CHAIRS - ALUMNI HOUSE BLD 28 CONF. RM | POPHAM, DONALD J. | CLOSED | 2010-06-03 | CP: PROJECT CONTINGENCY | 028 | CLOSED | 100.14 | 0 | 0 | 0
PJ0003461 | REPAIR/PAINT/CLEAN 54 CHAIRS - ALUMNI HOUSE BLD 28 CONF. RM | POPHAM, DONALD J. | CLOSED | 2010-06-03 | CU: CLEAN ALUMNI ASSOC CONF CHAIRS | 028 | CLOSED | 262.368 | 0 | 98.388 | 98.388
PJ0003461 | REPAIR/PAINT/CLEAN 54 CHAIRS - ALUMNI HOUSE BLD 28 CONF. RM | POPHAM, DONALD J. | CLOSED | 2010-06-03 | PA: REFINISH ALUMNI HOUSE CONF CHAIRS. | 028 | CLOSED | 517.536 | 0 | 285.96 | 285.96
PJ0003461 Total | [7 empty] | 1101.564 | 0 | 533.598 | 533.598
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | CA: RAMP CONSTRUCTION FOR PRESIDENTIAL EVENT - O'NEILL GREEN | GENERAL | CLOSED | 1256.223 | 0 | 4232.844 | 4232.844
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 100.22 | 0 | 0 | 0
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | CU: SUPPORT FOR BAKER DINNER ON 6/19/10 - O'NEILL GREEN | GENERAL | CLOSED | 196.776 | 0 | 489.06 | 489.06
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | EL: BAKER DINNER | GENERAL | CLOSED | 1164.1974 | 0 | 348.942 | 348.942
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | EO: BUILD RAMP FOR PRESIDENTIAL EVENT - O'NEILL GREEN | GENERAL | CLOSED | 861.504 | 0 | 1042.74 | 1042.74
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | IN:DINNER EVENT FOR PRES BAKER ON 6/19/10-O'NEILL GREEN (N/L) | GENERAL | CLOSED | 132.552 | 0 | 0 | 0
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | LA: SUPPORT FOR BAKER DINNER ON 6/19/10 | GENERAL | CLOSED | 1291.776 | 0 | 2139.1554 | 2139.1554
PJ0003460 | SP 09/10:DINNER EVENT FOR PRESIDENT BAKER 6/19/10 -O'NEILL GREEN | MAY, TOM | CLOSED | 2010-06-02 | MO: MOVE STAGING FOR PRESIDENTIAL EVENT - O'NEILL GREEN | GENERAL | CLOSED | 189 | 0 | 153.414 | 153.414
PJ0003460 Total | [7 empty] | 5192.2484 | 0 | 8406.1554 | 8406.1554
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | AD: INNOVATION COMMERCIAL FLOORING | RESIDENCE | CLOSED | 41303.3696 | 0 | 41303.3696 | 41303.3696
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | AD: JOC 09.019.019 STAPLES | RESIDENCE | CLOSED | 65448.9789 | 0 | 65448.9789 | 65448.9789
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | AD: THOMA ELECTRIC | RESIDENCE | CLOSED | 6687.5 | 0 | 6687.5 | 6687.5
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | CA:NUMBERS, DOORSTOPS AND NEW DOORS FOR FREMONT/SEQ | RESIDENCE | CLOSED | 4824.3414 | 0 | 8256.48 | 8256.48
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | CA:REPLACE HALL DOORS AT FREMONT AND SEQUOIA | RESIDENCE | CLOSED | 13762.08 | 0 | 20838.12 | 20838.12
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 12393.92 | 0 | 0 | 0
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | EL:MOVE SMOKE ALARM IN HALLWAYS AT FREMONT AND SEQUOIA | RESIDENCE | CLOSED | 627.552 | 0 | 331.62 | 331.62
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | IN: REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | RESIDENCE | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | LO:CORRIDOR DOORS FREMONT AND SEQUOIA | RESIDENCE | CLOSED | 262.4011 | 0 | 2766.936 | 2766.936
PJ0003459 | REFINISH INTERIOR DOORS & REPLACE CARPET - FREMONT & SEQUOIA | MAY, TOM | CLOSED | 2010-06-02 | PA:PREP AND PAINT WALLS AND JAMBS AT FREMONT AND SEQUOIA | RESIDENCE | CLOSED | 5151.36 | 0 | 6233.928 | 6233.928
PJ0003459 Total | [7 empty] | 150594.055 | 0 | 151999.4845 | 151999.4845
PJ0003456 | TI PERMIT FOR COUTO SOLUTIONS - BLD 83 TECH PARK LAB SPACE 2B | HOGAN, MIKE | CLOSED | 2010-05-27 | AD: ENGLEKIRK AND SABOL - SEISMIC PEER REVIEW FEES | 083 | CLOSED | 1037.5 | 0 | 1037 | 1037
PJ0003456 | TI PERMIT FOR COUTO SOLUTIONS - BLD 83 TECH PARK LAB SPACE 2B | HOGAN, MIKE | CLOSED | 2010-05-27 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003456 | TI PERMIT FOR COUTO SOLUTIONS - BLD 83 TECH PARK LAB SPACE 2B | HOGAN, MIKE | CLOSED | 2010-05-27 | IN: (MAINT) TI PERMIT, COUTO SOLUTIONS - BLD 83 TECH PARK LAB 2B | 083 | CLOSED | 0 | 0 | 1104.6 | 1104.6
PJ0003456 | TI PERMIT FOR COUTO SOLUTIONS - BLD 83 TECH PARK LAB SPACE 2B | HOGAN, MIKE | CLOSED | 2010-05-27 | IN: BUILDING PERMIT FEES | 083 | CLOSED | 1683.1 | 0 | 1683.1 | 1683.1
PJ0003456 | TI PERMIT FOR COUTO SOLUTIONS - BLD 83 TECH PARK LAB SPACE 2B | HOGAN, MIKE | CLOSED | 2010-05-27 | IN: PLAN REVIEW FEES | 083 | CLOSED | 1497.96 | 0 | 1497.96 | 1497.96
PJ0003456 | TI PERMIT FOR COUTO SOLUTIONS - BLD 83 TECH PARK LAB SPACE 2B | HOGAN, MIKE | CLOSED | 2010-05-27 | IN: STATE FIRE MARSHAL INSPECTION FEES | 083 | CLOSED | 2225.6 | 0 | 0 | 0
PJ0003456 Total | [7 empty] | 6444.16 | 0 | 5322.66 | 5322.66
PJ0003455 | SERVICES FOR CATA FARM SHOW 6/22&23/10 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-26 | CA: INSTALL 142 SHEETS OF 3/4" PLYWOOD BY 6/21 | 009 | CLOSED | 0 | 0 | 674.16 | 674.16
PJ0003455 | SERVICES FOR CATA FARM SHOW 6/22&23/10 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-26 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0003455 | SERVICES FOR CATA FARM SHOW 6/22&23/10 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-26 | EL: SUPPLY POWER FOR CATA FARM SHOW 6/21 | 009 | CLOSED | 0 | 0 | 570.996 | 570.996
PJ0003455 | SERVICES FOR CATA FARM SHOW 6/22&23/10 FARM SHOP 09 (NO ESTMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-26 | SUPPLY RENTAL: CATA FARM SHOW - 6/18 - 6/22 | 009 | CLOSED | 0 | 0 | 15 | 15
PJ0003455 Total | [7 empty] | 0 | 0 | 1260.156 | 1260.156
PJ0003454 | MODIFY DOOR BETWEEN RM 117/116 TO OPEN TO THE RIGHT - BLDG 01 | GRIFFIN, PATRICK E | CLOSED | 2010-05-26 | CA:INSTALL NEW POCKET DOOR AND ACOUSTICAL PANELS AT ADMIN 117 | 001 | CLOSED | 4764.6402 | 0 | 4201.638 | 4201.638
PJ0003454 | MODIFY DOOR BETWEEN RM 117/116 TO OPEN TO THE RIGHT - BLDG 01 | GRIFFIN, PATRICK E | CLOSED | 2010-05-26 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 658.73 | 0 | 0 | 0
PJ0003454 | MODIFY DOOR BETWEEN RM 117/116 TO OPEN TO THE RIGHT - BLDG 01 | GRIFFIN, PATRICK E | CLOSED | 2010-05-26 | IN: MODIFY DOOR BETWN 117&116 TO OPEN TO THE RIGHT BLDG 01(N/L) | 001 | CLOSED | 66.276 | 0 | 0 | 0
PJ0003454 | MODIFY DOOR BETWEEN RM 117/116 TO OPEN TO THE RIGHT - BLDG 01 | GRIFFIN, PATRICK E | CLOSED | 2010-05-26 | LO:INSTALL NEW POCKET DOOR PULL AND PRIVACY LATCH AT ADMIN 117 | 001 | CLOSED | 376.6579 | 0 | 423.504 | 423.504
PJ0003454 | MODIFY DOOR BETWEEN RM 117/116 TO OPEN TO THE RIGHT - BLDG 01 | GRIFFIN, PATRICK E | CLOSED | 2010-05-26 | PA:TAPE, MUD, PRIME AND PAINT NEW POCKET DOOR AT ADMIN 117 | 001 | CLOSED | 1379.4732 | 0 | 1532.058 | 1532.058
PJ0003454 Total | [7 empty] | 7245.7773 | 0 | 6157.2 | 6157.2
PJ0003451 | SP 10/11: SPEAKER REPLACEMENT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-26 | AD: BOB'S CRANE SERVICE | 061 | CLOSED | 1070 | 0 | 1070 | 1070
PJ0003451 | SP 10/11: SPEAKER REPLACEMENT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-26 | AD: GRAND PERFORMANCE | 061 | CLOSED | 27017.5 | 0 | 27017.5 | 27017.5
PJ0003451 | SP 10/11: SPEAKER REPLACEMENT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-26 | AD: THE MORRO GROUP (SWCA) | 061 | CLOSED | 4173 | 0 | 3485.2575 | 3485.2575
PJ0003451 | SP 10/11: SPEAKER REPLACEMENT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-26 | AD: UNITED RENTAL | 061 | CLOSED | 2038.9706 | 0 | 1905.5844 | 1905.5844
PJ0003451 | SP 10/11: SPEAKER REPLACEMENT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-26 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 1463.99 | 0 | 0 | 0
PJ0003451 | SP 10/11: SPEAKER REPLACEMENT - SPANOS STADIUM 061 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-26 | EL: SUPPORT FOR SPEAKER REPLACEMENT AT SPANOS STADIUM | 061 | CLOSED | 1268.88 | 0 | 1300.602 | 1300.602
PJ0003451 Total | [7 empty] | 37032.3406 | 0 | 34778.9439 | 34778.9439
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: CENTRAL COAST SPECIALTY - DIRECT PAY PURCHASE | 065 | CLOSED | 320 | 0 | 342.4 | 342.4
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: JOC 09.019.020 STAPLES | 065 | CLOSED | 176767.7129 | 0 | 176767.7129 | 176767.7129
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: JOC 10.020.033 STAPLES | 065 | CLOSED | 15611.1716 | 0 | 24264.0369 | 24264.0369
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: MECA | 065 | CLOSED | 13501.26 | 0 | 11862.555 | 11862.555
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: MORELAND THOMPSON | 065 | CLOSED | 2765.95 | 0 | 2765.95 | 2765.95
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: SUPPLY ADA RESTROOM SIGNS FOR UPGRADE PROJECT | 065 | CLOSED | 0 | 0 | 134.508 | 134.508
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CA: INSTALL ADA COMPLIANT SIGNAGE - BLGS 65 RESTROOMS | 065 | CLOSED | 169.164 | 0 | 169.164 | 169.164
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CA: SUPPLY SOAP DISPENSERS (MATERIALS, ONLY) | 065 | CLOSED | 443.04 | 0 | 3.8976 | 3.8976
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 1154.07 | 0 | 0 | 0
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | EL: ROUGH/FINISH WORK FOR UU RESTROOM | 065 | CLOSED | 32387.6429 | 0 | 26146.6993 | 26146.6993
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | ES: HVAC MODIFICATIONS FOR UU RESTROOM UPGRADES | 065 | CLOSED | 1174.9872 | 0 | 4216.4605 | 4216.4605
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | IN: SR 10/11: UU RESTROOM UPGRADES - BLDG 065 | 065 | CLOSED | 662.76 | 0 | 563.346 | 563.346
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | LO: CHANGE CORES FOR UU RESTROOM; REMOVE/REINSTALL LOCK & HANDLE | 065 | CLOSED | 943.008 | 0 | 225.288 | 225.288
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | LO: INSTALL NEW PUSH PAD AND CLOSURE - 2ND FL. UU RESTROOMS | 065 | CLOSED | 6571.68 | 0 | 9633.636 | 9633.636
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | PA: PAINT RR CEILING & DOORS & VARNISH DOOR TO LACTATION STATION | 065 | CLOSED | 4367.809 | 0 | 1264.02 | 1264.02
PJ0003450 | M&R ASI 10/11: UU RESTROOM UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | PL: ROUGH/FINISH WORK FOR UU RESTROOM | 065 | CLOSED | 49834.1016 | 0 | 47748.012 | 47748.012
PJ0003450 Total | [7 empty] | 306674.3571 | 0 | 306107.6862 | 306107.6862
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: JOC 10.020.016 STAPLES | 065 | CLOSED | 51403.5276 | 0 | 51403.5276 | 51403.5276
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: JOC 10.021.031 STAPLES | 065 | CLOSED | 53060.0374 | 0 | 53060.0481 | 53060.0481
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: RAT SOUND SYSTEMS (PURCHASED BY ASI) | 065 | CLOSED | 0 | 0 | 106859.9584 | 106859.9584
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: THOMA ELECTRIC | 065 | CLOSED | 3896.0305 | 0 | 3809.2 | 3809.2
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | EL:ELECTRICAL SUPPORT | 065 | CLOSED | 761.328 | 0 | 134.832 | 134.832
PJ0003449 | M&R ASI 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | IN:M&R UU 10/11: CHUMASH AUDITORIUM ACOUSTIC UPGRADES - BLDG 065 | 065 | CLOSED | 463.932 | 0 | 390.996 | 390.996
PJ0003449 Total | [7 empty] | 109584.8555 | 0 | 215658.5621 | 215658.5621
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: FLOOR CONNECTION | 065 | CLOSED | 10954.7991 | 0 | 10954.7991 | 10954.7991
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: JOC 09-019.031 STAPLES | 065 | CLOSED | 177812.9852 | 0 | 177812.9852 | 177812.9852
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | AD: JOC 10-020.034 STAPLES | 065 | CLOSED | 14854.703 | 0 | 22640.9325 | 22640.9325
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CA: OPEN CEILING AT ELECTRICAL BOX - UU CONFERENCE ROOM | 065 | CLOSED | 281.52 | 0 | 167.832 | 167.832
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 82.53 | 0 | 0 | 0
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | EL: LIGHTING/SMART ROOM WORK FOR CONFERENCE ROOMS | 065 | CLOSED | 18697.1414 | 0 | 16804.278 | 16804.278
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | ES: REMOVE AND REINSTALL GRILLS IN CONFERENCE ROOMS | 065 | CLOSED | 8099.569 | 0 | 2833.4431 | 2833.4431
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | IN: SR 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | 065 | CLOSED | 397.656 | 0 | 364.518 | 364.518
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | LO: CHANGE LEVER AND CORES FOR UU CONFERENCE ROOMS | 065 | CLOSED | 1543.008 | 0 | 1051.776 | 1051.776
PJ0003448 | M&R ASI 10/11: CONFERENCE ROOM RENOVATION - BLDG 065 | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | PA: PAINT CONFERENCE ROOM CEILINGS AND WALLS AND VARNISH DOOR | 065 | CLOSED | 6111.649 | 0 | 4618.752 | 4618.752
PJ0003448 Total | [7 empty] | 238835.5607 | 0 | 237249.3159 | 237249.3159
PJ0003447 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 252A (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CA:INSTALL BRACKETS FOR PROJECTOR SCREEN/ INSTALL SPEAKERS | 034 | CLOSED | 0 | 0 | 526.11 | 526.11
PJ0003447 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 252A (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0003447 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 252A (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | EL:SMART ROOM ELECTRICAL | 034 | CLOSED | 0 | 0 | 2447.55 | 2447.55
PJ0003447 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 252A (NO ESTIMATE) | MOLLAN, CHERYL L. | CLOSED | 2010-05-24 | IN: INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 252A | 034 | CLOSED | 0 | 0 | 318.636 | 318.636
PJ0003447 Total | [7 empty] | 0 | 0 | 3292.296 | 3292.296
PJ0003446 | RENOVATE THE AVENUE FOOD COURT BEVERAGE ISLAND - BLDG 19-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-24 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 1193.16 | 0 | 0 | 0
PJ0003446 | RENOVATE THE AVENUE FOOD COURT BEVERAGE ISLAND - BLDG 19-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-24 | EL: DISCONNECT AND PROVIDE ELECTRICAL CLEARANCE - 019 - 100 | 019 | CLOSED | 5675.52 | 0 | 2752.362 | 2752.362
PJ0003446 | RENOVATE THE AVENUE FOOD COURT BEVERAGE ISLAND - BLDG 19-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-24 | IN: RENOVATE THE AVENUE FOOD COURT BEVERAGE ISLAND - BLDG 19-100 | 019 | CLOSED | 397.656 | 0 | 364.518 | 364.518
PJ0003446 | RENOVATE THE AVENUE FOOD COURT BEVERAGE ISLAND - BLDG 19-100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-24 | PL: PLUMBING SUPPORT FOR AVENUE REMODEL | 019 | CLOSED | 4414.56 | 0 | 4827.0573 | 4827.0573
PJ0003446 Total | [7 empty] | 11680.896 | 0 | 7943.9373 | 7943.9373
PJ0003445 | RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | MAY, TOM | CLOSED | 2010-05-24 | AD: SAN LUIS CUSTOM TINTS | 035 | CLOSED | 155.5245 | 0 | 155.2249 | 155.2249
PJ0003445 | RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | MAY, TOM | CLOSED | 2010-05-24 | AD: SAN LUIS GLASS | 035 | CLOSED | 3349.1 | 0 | 3349.1 | 3349.1
PJ0003445 | RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | MAY, TOM | CLOSED | 2010-05-24 | CA:TEMPORARY WALL FOR PONY PRINTS | 035 | CLOSED | 221.52 | 0 | 200.214 | 200.214
PJ0003445 | RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | MAY, TOM | CLOSED | 2010-05-24 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 330.32 | 0 | 0 | 0
PJ0003445 | RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | MAY, TOM | CLOSED | 2010-05-24 | EL:RECONFIGURE ELECTRICAL IN PONY PRINTS AREA | 035 | CLOSED | 1164.1974 | 0 | 627.912 | 627.912
PJ0003445 | RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | MAY, TOM | CLOSED | 2010-05-24 | IN: RECONFIGURE AREA FOR PONY PRINTS - BLDG 35-114 | 035 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003445 Total | [7 empty] | 5286.9379 | 0 | 4398.7269 | 4398.7269
PJ0003443 | MJ: IN-HOUSE SUPPORT FOR GRAND TO TAHOE PEDESTRIAN WAY EXPANSION | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-20 | CA: INSTALL FLEXIBLE BOLLARDS FOR PEDESTRIAN EXPANSION-UU PLAZA | GENERAL | CLOSED | 0 | 0 | 257.118 | 257.118
PJ0003443 | MJ: IN-HOUSE SUPPORT FOR GRAND TO TAHOE PEDESTRIAN WAY EXPANSION | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003443 Total | [7 empty] | 0 | 0 | 257.118 | 257.118
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | AD: BUEHLER AND BUEHLER | 056 | CLOSED | 7918 | 0 | 7918 | 7918
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | AD: EARTH SYSTEMS | 056 | CLOSED | 235.4 | 0 | 235.4 | 235.4
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | AD: ENGLEKIRK AND SABOL | 056 | CLOSED | 776.82 | 0 | 776.82 | 776.82
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | AD: MAINO CONSTRUCTION - LOW VALUE PUBLIC WORKS | 056 | CLOSED | 10347.4885 | 0 | 10347.1354 | 10347.1354
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | CA:INSTALL PAD AND BOLLARDS FOR PROPANE TANK AT SWINE | 056 | CLOSED | 1033.8 | 0 | 1046.6364 | 1046.6364
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | CP: PROJECT CONTINGENCY | 056 | CLOSED | 997.73 | 0 | 0 | 0
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | EL:CONNECT ELECTRICAL TO MODULAR FARROWING BARN AT SWINE UNIT | 056 | CLOSED | 13920.3108 | 0 | 17872.704 | 17872.704
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | EO:DIG TRENCHES FOR WATER/ELECTRICAL HOOK UP AT SWINE UNIT | 056 | CLOSED | 4765.4606 | 0 | 6249.888 | 6249.888
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | IN: SUPPORT FOR MODULAR FARROWING BARN | 056 | CLOSED | 397.656 | 0 | 463.932 | 463.932
PJ0003442 | INSTALLATION SUPPORT FOR MODULAR FARROWING BARN -BLDG 56 | MAY, TOM | CLOSED | 2010-05-19 | PL:HOOK UP WATER AND SEWER TO MODULAR FARROWING BARN AT SWINE | 056 | CLOSED | 6740.4946 | 0 | 8091.18 | 8091.18
PJ0003442 Total | [7 empty] | 47133.1605 | 0 | 53001.6958 | 53001.6958
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | AD: BOB'S CRANE (DIRECT-PAY INVOICE) | 052 | CLOSED | 0 | 0 | 550 | 550
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | AD: FLUID RESOURCE MGT (ASSIST PLUMBERS WITH HYDRANT FLOW TESTS) | 052 | CLOSED | 0 | 0 | 174.58 | 174.58
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | AD: GREENVALE TREE COMPANY | 052 | CLOSED | 0 | 0 | 1353.55 | 1353.55
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | AD: RESTROOM DISPENSERS & RECEPTACLES - CENTER FOR SCI | 180 | CLOSED | 0 | 0 | 7581.3895 | 7581.3895
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | ANTS: FIRE ALARM WORK AT CENTER FOR SCIENCE | 180 | CLOSED | 0 | 0 | 2162.16 | 2162.16
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: ASSIST IN INSTALLATION OF GILBANE TRAILER - CTR. FOR SCI. | GENERAL | CLOSED | 0 | 0 | 505.44 | 505.44
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: ASSIST WITH MOLD REMEDIATION - BLDG. 20 | 020 | CLOSED | 0 | 0 | 462.696 | 462.696
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: ASSIST WITH STICKERS FOR CTR. FOR SCI. WAYFINDING SIGNS | 052 | CLOSED | 0 | 0 | 236.382 | 236.382
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: BENCH DONATED BY PAUL BONDERSON 8/20/13@9:30 AM -CTR FOR SCI | 180 | CLOSED | 0 | 0 | 660.864 | 660.864
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: CONSTRUCTION SIGNS FOR REC. CTR. AT S. PERIMETER | GENERAL | CLOSED | 0 | 0 | 181.752 | 181.752
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: CUT HOLE IN NE CORNER OF ROOM 52-D17 | 052 | CLOSED | 0 | 0 | 1451.715 | 1451.715
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: DISASSEMBLE AND MOVE DRAFTING TABLE FROM 52-C20 TO 26-110H | 052 | CLOSED | 0 | 0 | 219.144 | 219.144
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: INSTALL 8 BOLLARD AT CENTER FOR SCIENCE - BLDG 180 | 180 | CLOSED | 0 | 0 | 1438.9137 | 1438.9137
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: INSTALL CLOCKS IN VARIOUS ROOMS - CTR FOR SCIENCE, BLDG 180 | 180 | CLOSED | 0 | 0 | 3064.818 | 3064.818
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: INSTALL NEW DONOR PLAQUE - CTR. FOR SCI. S. PLAZA, BLDG. 180 | 180 | CLOSED | 0 | 0 | 786.918 | 786.918
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: INSTALL TOWEL DISPENSERS - CENTER FOR SCIENCE - BLDG. 180 | 180 | CLOSED | 0 | 0 | 325.6882 | 325.6882
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: MANUFACTURE VINYL LETTER SIGNS FOR CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 1583.406 | 1583.406
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: PROVIDE SIGN POST TO BE INSTALLED BY GILBANE(MATERIALS ONLY) | 052 | CLOSED | 0 | 0 | 44.4 | 44.4
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: REINSTALL EVACUATION SIGNAGE - CENTER FOR SCIENCE 180 | 180 | CLOSED | 0 | 0 | 1406.244 | 1406.244
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: RELOCATE COUNTER - 52-A05 TO 52-D17 &ADD CYLINDER RESTRAINTS | 052 | CLOSED | 0 | 0 | 2759.508 | 2759.508
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CA: VINYL LETTERS FOR CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 170.34 | 170.34
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 345000 | 0 | 0 | 0
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CPE: (MAINT) REVIEW WORK INSTALLATIONS FOR CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 1213.46 | 1213.46
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CPE: ASSIST IN AIR HANDLER EQUIP START-UP - CTR FOR SCI 11/27/12 | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CPE: PROVIDE CHEMICALLY-TREATED HOT WATER - CTR FOR SCI | 052 | CLOSED | 0 | 0 | 2063.394 | 2063.394
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | CPE: START UP & COMMISSIONING OF HVAC SYSTEMS IN IT BUILDING 20B | 180 | CLOSED | 0 | 0 | 824.256 | 824.256
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: ADD 20 AMP DEDICATED LINE FOR ULTRA FREEZER - BLD 33 RM 390A | 033 | CLOSED | 0 | 0 | 130.308 | 130.308
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: ASSIST PLUMBERS WITH COMPRESSOR INSTALLATION 52-F5 | 052 | CLOSED | 0 | 0 | 3233.4 | 3233.4
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: ASSIST WITH BASEMENT FLOOD - BLG 52 CTR FOR SCI | 052 | CLOSED | 0 | 0 | 28889.9986 | 28889.9986
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: ASSIST WITH POWER OUTAGE AT CENTER FOR SCI. 8/3/12 AT 2:30PM | 052 | CLOSED | 0 | 0 | 401.22 | 401.22
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: DISCONNECT POWER - OLD SCIENCE 52-A05 | 052 | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: ELECTRICAL SUPPORT TO COMPLETE IT BUILDING 20B | 180 | CLOSED | 0 | 0 | 8036.316 | 8036.316
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: LOCATE UTILITIES FOR CONTSTRUCTION FENCING - CTR. FOR SCI. | GENERAL | CLOSED | 0 | 0 | 253.776 | 253.776
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: MARK UNDERGROUND UTILITIES AT OLD "COTTAGES" SITE | 052 | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: ORDER REPLACEMENT TRANSFORMER - CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 15310.908 | 15310.908
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: POWER FOR MAIN RECIEVER FOR ATOMIC CLOCKS - CTR FOR SCIENCE | 180 | CLOSED | 0 | 0 | 474.24 | 474.24
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: PROVIDE QUADPLEX OUTLET - RMS 105, 267, & 369 - CTR FOR SCI | 180 | CLOSED | 0 | 0 | 2997.456 | 2997.456
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: PROVIDE SCADA METERING/CONNECTION FOR CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: PROVIDE TEMPORARY METERING FOR CONTRACTOR - CENTER FOR SCI | 052 | CLOSED | 0 | 0 | 3410.49 | 3410.49
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: REFRESH UTILITY MARKINGS FOR CTR. FOR SCI. DEMO | 052 | CLOSED | 0 | 0 | 539.274 | 539.274
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: RELOCATE FIRE ALARM USER CONTROL PANEL - CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 1138.0423 | 1138.0423
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: RELOCATE SCADA FIBERS ONTO CAMPUS ETHERNET - CTR. FOR SCI. | 052 | CLOSED | 0 | 0 | 317.22 | 317.22
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: REPAIR EXTERIOR LIGHT CONDUIT BY STAIRS FROM EE TO VIA CARTA | GENERAL | CLOSED | 0 | 0 | 103.566 | 103.566
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: REPAIR LIGHT POLE ON VIA CARTA - DAMAGED BY CONTRACTOR | 052 | CLOSED | 0 | 0 | 2068.812 | 2068.812
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: REPLACE/RELOCATE FIRE ALARM CONTROL PANEL - CTR. FOR SCIENCE | 052 | CLOSED | 0 | 0 | 6093.2141 | 6093.2141
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: STREET LIGHT CONDUIT DAMAGED BY CONTRACTOR - CTR FOR SCI | 052 | CLOSED | 0 | 0 | 2199.408 | 2199.408
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: SUPPORT FOR CTR FOR SCI UNDERGROUND UTILITY MARKING | 052 | CLOSED | 0 | 0 | 13981.321 | 13981.321
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: TEMP POWER - CTR. FOR SCI. CONSTRUCTION AND GILBANE OFFICES | GENERAL | CLOSED | 0 | 0 | 33555.942 | 33555.942
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: TEMP POWER FOR TELECOM BLDG. 20B | 020B | CLOSED | 0 | 0 | 9793.632 | 9793.632
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: TURN OFF POWER TO (2) THERMAL OVENS - 52-A07 AND A10A | 052 | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EL: VALIDATE CABLING FOR 12KL LINE ON VIA CARTA - CTR. FOR SCI. | GENERAL | CLOSED | 0 | 0 | 576.324 | 576.324
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EO: EXCAVATE FOR VIA CARTE BOLLARD INSTALLATION | 180 | CLOSED | 0 | 0 | 945.516 | 945.516
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | EO: REPAIR POTHOLE AT BIOSCIENCE LOADING DOCK - BLDG. 53A | STREETS | CLOSED | 0 | 0 | 524.208 | 524.208
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | ES: ETHERNET-CAPABLE EMS CONTROL CABINETS - OLD SCI. 52 | 052 | CLOSED | 0 | 0 | 11200.752 | 11200.752
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | ES: MARK UNDERGROUND UTILITIES AT OLD "COTTAGES" SITE(N/L) | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | ES: REPAIR HOT WATER GAUGE BROKEN BY CLEAN-UP CREW - BLDG 20 | 020 | CLOSED | 0 | 0 | 315.606 | 315.606
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | ES: RESEARCH AND ORDER AIR COMPRESSOR EQUIP FOR CENTER FOR SCI. | 052 | CLOSED | 0 | 0 | 16728.924 | 16728.924
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | ES: SUPPORT FOR CENTER FOR SCIENCE | 180 | CLOSED | 0 | 0 | 3077.544 | 3077.544
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LA: IDENTIFY IRRIGATION ON HILL BETWEEN BLDG 20 & VIA CARTA | GENERAL | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LA: LANDSCAPING SUPPORT FOR CENTER FOR SCIENCE | 052 | CLOSED | 0 | 0 | 22101.5413 | 22101.5413
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LA: LOCATE IRRIGATION LINES FOR CONSTRUCTION FENCING-CTR FOR SCI | GENERAL | CLOSED | 0 | 0 | 3158.952 | 3158.952
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LO: INSTALL PERMANENT CORE LOCKS IN LABS & OFFICES - CTR FOR SCI | 180 | CLOSED | 0 | 0 | 22429.518 | 22429.518
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LO: LOCKS FOR NEW TELECOM BLDG - 020B | 052 | CLOSED | 0 | 0 | 129.168 | 129.168
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LO: MAKE LOCK MODIFICATIONS TO SCIENCE 052-D-1 | 052 | CLOSED | 0 | 0 | 597.72 | 597.72
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | LO:CHANGE EXT. LOCKS TO GREEN KEY CORE-N. SECTION CTR FOR SCI 52 | 052 | CLOSED | 0 | 0 | 1464.264 | 1464.264
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: ASSIST CHEMISTRY DEPT. IN CTR.FOR SCIENCE MOVE - SUMMER 2010 | 052 | CLOSED | 0 | 0 | 267.054 | 267.054
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: GROUP II SUPPORT FOR CENTER FOR SCIENCE - BLDG. 180 | 180 | CLOSED | 0 | 0 | 2707.146 | 2707.146
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: MOVE (2) FILE CABINETS FROM CTR FOR SCI CONSTRUCTION TRAILER | 052 | CLOSED | 0 | 0 | 28.41 | 28.41
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: MOVE SHELVES & CABINIET FROM 70-103A TO CTR FOR SCI. TRAILER | GENERAL | CLOSED | 0 | 0 | 22.728 | 22.728
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: MOVE TAB-ARMS FROM 52-A04, A11, A12 TO BLGS. 14, 21, & 36 | GENERAL | CLOSED | 0 | 0 | 68.184 | 68.184
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: MOVE TABLES TO OWNER'S TRAILER - CTR FOR SCI | 052 | CLOSED | 0 | 0 | 22.728 | 22.728
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO: PICK UP SURPLUS TAMPON DISPENSERS - CENTER FOR SCIENCE | 180 | CLOSED | 0 | 0 | 24.144 | 24.144
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO:MOVE REMAINING LOOSE FURNITURE FROM BLDG 52 NORTH-CTR FOR SCI | 052 | CLOSED | 0 | 0 | 673.317 | 673.317
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | MO:RELOCATE FURNITURE FROM ROOM 52-C21 | 052 | CLOSED | 0 | 0 | 22.728 | 22.728
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PA: STRIPE PARKING SPACES FOR CENTER FOR SCIENCE (N/L) | 180 | CLOSED | 0 | 0 | 0 | 0
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: ASSIST W/SEWER LINE REPAIR FOR CTR. FOR SCI. - ENGLISH LAWN | 052 | CLOSED | 0 | 0 | 681.456 | 681.456
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: ASSIST WITH BASEMENT FLOOD - BLG 52 CTR FOR SCI | 052 | CLOSED | 0 | 0 | 802.164 | 802.164
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: CONNECT PHISICS WING TO E-WING AIR COMPRESSOR - CTR FOR SCI. | 052 | CLOSED | 0 | 0 | 7603.824 | 7603.824
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: FINAL PLUMBING CONNECTION FOR ICEMAKERS - CTR. FOR SCI. | 180 | CLOSED | 0 | 0 | 7011.1094 | 7011.1094
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: INSTALL AIR COMPRESSOR IN BASEMENT OF F-WING, OLD SCI. 52 | 052 | CLOSED | 0 | 0 | 9837.6847 | 9837.6847
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: INSTALL SAFETY SHOWERS FOR REC. CTR. RELOCATION - 033 | 052 | CLOSED | 0 | 0 | 364.62 | 364.62
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: ISOLATE EXISTING WATER SERVICE AT BLDG 52, NORTH & SOUTH | 052 | CLOSED | 0 | 0 | 2625.264 | 2625.264
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: LOCATE UTILITIES FOR CONSTRUCTION FENCING - CTR. FOR SCI. | GENERAL | CLOSED | 0 | 0 | 984.996 | 984.996
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: MARK UNDERGROUND UTILITIES AT OLD "COTTAGES" SITE | 052 | CLOSED | 0 | 0 | 190.728 | 190.728
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: MOCK WATER SHUTDOWN - CTR FOR SCI | 052 | CLOSED | 0 | 0 | 1731.168 | 1731.168
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: REFRESH UTILITY MARKINGS FOR CTR. FOR SCI. DEMO | 052 | CLOSED | 0 | 0 | 63.576 | 63.576
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: SEWER/WATER HOOKUPS FOR CTR. FOR SCI. ADMIN. TRAILER 180T-A | GENERAL | CLOSED | 0 | 0 | 1548.684 | 1548.684
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: SHUT DOWN WATER AND GAS LINES - CTR. FOR SCI. | 052 | CLOSED | 0 | 0 | 27664.3795 | 27664.3795
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: SUPPORT AUTOCLAVE INSTALLATION - CTR FOR SCI RMS 466B & 534A | 180 | CLOSED | 0 | 0 | 5264.6312 | 5264.6312
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | PL: TEST HYDRANTS, PER STATE FIRE MARSHAL - CTR. FOR SCI. | 052 | CLOSED | 0 | 0 | 261.168 | 261.168
PJ0003441 | MJ: IN-HOUSE SUPPORT FOR CENTER FOR SCIENCE - BLDG 180 | JUDD, PERRY | CLOSED | 2010-05-19 | RE: MOVE DUMPSTER -BLDG 53A LOADING DOCK TO PHYSICS LOADING DOCK | 052 | CLOSED | 0 | 0 | 7924.17 | 7924.17
PJ0003441 Total | [7 empty] | 345000 | 0 | 326450.2555 | 326450.2555
PJ0003439 | M&R ASI 10/11: RENOVATE BASKETBALL COURTS BEHIND MOTT - BLDG 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-18 | AD: BOB'S CRANE | GENERAL | CLOSED | 535 | 0 | 535 | 535
PJ0003439 | M&R ASI 10/11: RENOVATE BASKETBALL COURTS BEHIND MOTT - BLDG 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-18 | AD: JOC 10.020.007 STAPLES | GENERAL | CLOSED | 34257.3875 | 0 | 34257.3768 | 34257.3768
PJ0003439 | M&R ASI 10/11: RENOVATE BASKETBALL COURTS BEHIND MOTT - BLDG 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-18 | CA: INSTALL BREAK-AWAY BOLLARDS BEHIND MOTT GYM | GENERAL | CLOSED | 406.14 | 0 | 146.364 | 146.364
PJ0003439 | M&R ASI 10/11: RENOVATE BASKETBALL COURTS BEHIND MOTT - BLDG 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-18 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2005.58 | 0 | 0 | 0
PJ0003439 | M&R ASI 10/11: RENOVATE BASKETBALL COURTS BEHIND MOTT - BLDG 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-18 | EO: RELOCATE SHIPPING CONTAINERS | GENERAL | CLOSED | 139.032 | 0 | 46.344 | 46.344
PJ0003439 | M&R ASI 10/11: RENOVATE BASKETBALL COURTS BEHIND MOTT - BLDG 42 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-18 | IN: RENOVATE OUTDOOR BASKETBALL COURTS BEHIND MOTT GYM - BLDG 42 | GENERAL | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0003439 Total | [7 empty] | 37475.6915 | 0 | 35084.4988 | 35084.4988
PJ0003438 | SR 09/10: ORDER & INSTALL NEW RADIO REPEATER SYSTEM- BLDG 70-107 | GRIFFIN, PATRICK E | CLOSED | 2010-05-18 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0003438 | SR 09/10: ORDER & INSTALL NEW RADIO REPEATER SYSTEM- BLDG 70-107 | GRIFFIN, PATRICK E | CLOSED | 2010-05-18 | ITS: NEW RADIO REPEATER SYSTEM FOR FAC. SERV FRONT OFFICE(MAINT) | 070 | CLOSED | 4167.95 | 0 | 4171.66 | 4171.66
PJ0003438 Total | [7 empty] | 4167.95 | 0 | 4171.66 | 4171.66
PJ0003436 | FACS SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 211.13 | 0 | 0 | 0
PJ0003436 | FACS SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | 042 | CLOSED | 1316.7594 | 0 | 1709.748 | 1709.748
PJ0003436 | FACS SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | POPHAM, DONALD J. | CLOSED | 2010-05-17 | EL: SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | 042 | CLOSED | 364.1686 | 0 | 363.84 | 363.84
PJ0003436 | FACS SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | POPHAM, DONALD J. | CLOSED | 2010-05-17 | IN: FACS SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | 042 | CLOSED | 66.276 | 0 | 99.414 | 99.414
PJ0003436 | FACS SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | POPHAM, DONALD J. | CLOSED | 2010-05-17 | PL: SUPPORT FOR WRESTLING FUND RAISER 5/22 - BLDG 42 | 042 | CLOSED | 364.9262 | 0 | 364.62 | 364.62
PJ0003436 Total | [7 empty] | 2323.2602 | 0 | 2537.622 | 2537.622
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | AD: JOC 10.020.044.00, .01, .03, .04, 06 STAPLES | 192 | CLOSED | 248110.7868 | 0 | 251454.066 | 251454.066
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 18846.6 | 0 | 0 | 0
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | EL: ALARM WORK AT ENGINEERING IV 3RD FLOOR | 192 | CLOSED | 253.776 | 0 | 244.908 | 244.908
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | ES: TEST VAV VALVES FOR COMMISSIONING | 192 | CLOSED | 512.256 | 0 | 384.192 | 384.192
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | IN: SP 10/11: PROJECT COMPLETION OF 3RD FLOOR - BLDG 192 | 192 | CLOSED | 2120.832 | 0 | 957.672 | 957.672
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | ITS: DATA WIRING FOR DEAN'S COMPLEX BUILD OUT - PHASE I | 192 | CLOSED | 8447.36 | 0 | 8489.73 | 8489.73
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | LO: INSTALL LOCKS AS PER DRAWINGS | 192 | CLOSED | 10127.1509 | 0 | 6797.316 | 6797.316
PJ0003435 | SP 10/11: PHASE I - BUILD OUT OF DEAN'S COMPLEX - BLD 192 3RD FL | LAMPMAN, GREG | CLOSED | 2010-05-17 | PA:PAINT AS PER PLANS | 192 | CLOSED | 17648.1269 | 0 | 7312.602 | 7312.602
PJ0003435 Total | [7 empty] | 306066.8886 | 0 | 275640.486 | 275640.486
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY JUNE 3 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SATURDAY JUNE 25 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUNDAY JUNE 26 (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURSDAY 10/7/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - 10/8/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - 9/25/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - APR 1(MIDSUMMER STU MAT) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI 10/15/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI APR 15 CENG EVENT | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI APR 15 MECH ENG EVENT | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI APR 15 SHIPWRECK | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI FEB 4(ORCHESIS)8P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI JAN 28(ORCHESIS)8P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI JAN 7 SPILLER RECITAL | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAR 11(JUST JAZZ) 7P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAR 12(JUST JAZZ) 8P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAR 18(MARK NIZER MAT) 11A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAR 4(FALSETTOS) 8A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAY 13(SMASH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAY 20(SMASH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRI MAY 27(DANCE CONC) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 10/22/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 10/23/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 11/12/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 11/19/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 12/3/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 12/3/2010 - 11AM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - FRIDAY 12/3/2010-9AM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - MON APR 11(FORUM) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - MON JAN10 (VERITAS FORUM)7P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT 10/16/2010 N/L | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT 10/9/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT APR 16 (MEXICO DE NOCHE | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT APR 2(MOSE ALLISION) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT APR 3(TENT EVENT) (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT APR 30(CLA DEAN DINNER) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT APR 9(MESA MTGS) (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT APR9(MESA AFTERNOON) | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT FEB 24(FALSETTOS) 8A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT FEB 25(FALSETTOS) 8A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT FEB 26(FALSETTOS) 8A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT FEB 5(MENTORING) 8A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT FEB 5(ORCHESIS)8P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT JAN 29(ORCHESIS)8P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAR 19(DOOLITTLE EVENT) 3P | 044 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAR 19(MELINDA D.) 11A | 044 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAR 26(CORE DANCE) 7P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAR 5(FALSETTOS) | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAR 5(MESA REGIONALS) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAR 8 (THETA CHI EVENT) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAY 14(SMASH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SAT MAY 21(SMASH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SATURDAY 11/13/2010 | 044 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SATURDAY 11/20/2010 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SATURDAY 12/04/2010 BEFORE 11AM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN 10/17/2010 | 044 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN APR 10(FORUM) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN DEC 12 AFTER 4PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN DEC. 12 BEFORE 11AM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN JAN 30(ORCHESIS)2P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN JUNE 5 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - SUN MAY 22(GROUNDLINGS) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURS APR 21(LAVAY SMITH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURS FEB 3(ORCHESIS)8P | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURS MAR 3(FALSETTOS) 8A | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURS MAY 12(SMASH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURS MAY 19(SMASH) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURS MAY 26(DANCE CONC) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURSDAY 10/21/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURSDAY 11/11/2010 | 044 | CLOSED | 0 | 0 | 188.1 | 188.1
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - THURSDAY 11/18/2010 | 044 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - TUES APR 12(FORUM) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - TUES APR 19(REAL FOOD COLL) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - TUES MAR 22 - 11A (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - TUES MAR 22(PUSS IN BOOTS)9:30A | 044 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - TUES MAY 17(FORESTRY SOC) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - TUES MAY 24(PIANO RECITAL) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - WED APR 20(GREEK UNIVERSSE) | 044 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - WED DEC 9 AFTER 11PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - WED MAY 18(STRIDE) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE - WEDNESDAY 10/20/2010 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE-FRI APR 1(INTRA FRAT COUNCIL) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE-FRI JAN 14(GUITAR MASTERS) | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP AT SPANOS THEATRE-SAT 12/4/2010 B/T MAT & EVE PERF | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP SPANOS THEATRE - SUNDAY 12/05/2010 AFTER 4PM PERF. | 044 | CLOSED | 0 | 0 | 27.33 | 27.33
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEAN UP SPANOS THEATRE - SUNDAY 12/05/2010 BEFORE 11AM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CLEANUP OF SPANOS THEATRE JUNE 20-23 (CATA) | 044 | CLOSED | 0 | 0 | 229.572 | 229.572
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N AUG 2 BY 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JULY 14 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JULY 16 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JULY 17 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JULY 18 NOON | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU:CLEAN UP AT SPANOS THEATRE-SUN MARCH 6-DRAMA STRIKE 12-3(N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003434 | 10/11 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2010-05-17 | CU:CUSTODIAL SUPPORT AT SPANOS THEATRE - JULY 27 | 044 | CLOSED | 0 | 0 | 196.776 | 196.776
PJ0003434 Total | [7 empty] | 0 | 0 | 6110.676 | 6110.676
PJ0003433 | MJ:INSTALL ADDITIONAL EXTERIOR LIGHTING N. SIDE OF HEALTH CENTER | MAY, TOM | CLOSED | 2010-05-13 | CA: POUR CONCRETE BASES FOR EXTERIOR LIGHTING - N. SIDE BLDG 27 | GENERAL | CLOSED | 0 | 0 | 2114.202 | 2114.202
PJ0003433 | MJ:INSTALL ADDITIONAL EXTERIOR LIGHTING N. SIDE OF HEALTH CENTER | MAY, TOM | CLOSED | 2010-05-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003433 | MJ:INSTALL ADDITIONAL EXTERIOR LIGHTING N. SIDE OF HEALTH CENTER | MAY, TOM | CLOSED | 2010-05-13 | EL: INSTALL ADDITIONAL EXTERIOR LIGHTING N. SIDE BLDG 27 | GENERAL | CLOSED | 0 | 0 | 17228.5389 | 17228.5389
PJ0003433 | MJ:INSTALL ADDITIONAL EXTERIOR LIGHTING N. SIDE OF HEALTH CENTER | MAY, TOM | CLOSED | 2010-05-13 | EO: ASSIST ELECTRICIANS WITH POLE LIGHTS - N. SIDE BLDG 27 | GENERAL | CLOSED | 0 | 0 | 2565.732 | 2565.732
PJ0003433 Total | [7 empty] | 0 | 0 | 21908.4729 | 21908.4729
PJ0003432 | INSTALL SMART ROOM AUDIO-VISUAL EQUIPMENT - BLD 27 RM 153 | MOLLAN, CHERYL L. | CLOSED | 2010-05-12 | CA:INSTALL PROJECTOR BRACKET, SPEAKER MOUNT, SCREEN MOUNT | 027 | CLOSED | 1764.6114 | 0 | 1024.53 | 1024.53
PJ0003432 | INSTALL SMART ROOM AUDIO-VISUAL EQUIPMENT - BLD 27 RM 153 | MOLLAN, CHERYL L. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 512.98 | 0 | 0 | 0
PJ0003432 | INSTALL SMART ROOM AUDIO-VISUAL EQUIPMENT - BLD 27 RM 153 | MOLLAN, CHERYL L. | CLOSED | 2010-05-12 | EL:INSTALL NEW ELECTRICAL FOR SMARTROOM HEALTH CENTER, ROOM 153 | 027 | CLOSED | 2183.108 | 0 | 2584.71 | 2584.71
PJ0003432 | INSTALL SMART ROOM AUDIO-VISUAL EQUIPMENT - BLD 27 RM 153 | MOLLAN, CHERYL L. | CLOSED | 2010-05-12 | IN: INSTALL SMART ROOM AUDIO-VISUAL EQUIPMENT - BLD 27 RM 153 | 027 | CLOSED | 132.552 | 0 | 231.966 | 231.966
PJ0003432 | INSTALL SMART ROOM AUDIO-VISUAL EQUIPMENT - BLD 27 RM 153 | MOLLAN, CHERYL L. | CLOSED | 2010-05-12 | PA:VARNISH BACKER BOARD FOR PROJECTOR SCREEN, TOUCH UP WALLS | 027 | CLOSED | 1049.4732 | 0 | 753.756 | 753.756
PJ0003432 Total | [7 empty] | 5642.7246 | 0 | 4594.962 | 4594.962
PJ0003430 | SUPPORT FOR PRESIDENT SELECTION EVENT - MAY 23 - 28 | POPHAM, DONALD J. | CLOSED | 2010-05-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003430 | SUPPORT FOR PRESIDENT SELECTION EVENT - MAY 23 - 28 | POPHAM, DONALD J. | CLOSED | 2010-05-13 | CU: PREPARATION OF AREAS FOR CANDIDATE INTERVIEWS-5/24-5/28 | GENERAL | CLOSED | 0 | 0 | 1644.156 | 1644.156
PJ0003430 | SUPPORT FOR PRESIDENT SELECTION EVENT - MAY 23 - 28 | POPHAM, DONALD J. | CLOSED | 2010-05-13 | ES: CHECK HVAC SYSTEMS AT FOLLOWING AREAS - 5/24-5/28 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003430 | SUPPORT FOR PRESIDENT SELECTION EVENT - MAY 23 - 28 | POPHAM, DONALD J. | CLOSED | 2010-05-13 | LA: SUPPORT FOR CANDIDATE OPEN FORUMS - 5/22-5/25 | GENERAL | CLOSED | 0 | 0 | 246.018 | 246.018
PJ0003430 | SUPPORT FOR PRESIDENT SELECTION EVENT - MAY 23 - 28 | POPHAM, DONALD J. | CLOSED | 2010-05-13 | PL: PM RESTROOMS FOR CANDIDATE INTERVIEWS | GENERAL | CLOSED | 0 | 0 | 890.064 | 890.064
PJ0003430 Total | [7 empty] | 0 | 0 | 2780.238 | 2780.238
PJ0003429 | RELAY FOR LIFE - DEXTER LAWN - SAT MAY 15, 2010 BY 7 AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-05-13 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003429 | RELAY FOR LIFE - DEXTER LAWN - SAT MAY 15, 2010 BY 7 AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-05-13 | CU: OPEN MATH AND SCIENCE BUILDING FOR RELAY FOR LIFE-5/16 | GENERAL | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003429 | RELAY FOR LIFE - DEXTER LAWN - SAT MAY 15, 2010 BY 7 AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-05-13 | EL: SUPPLY ONE SPIDER BOX FOR RELAY FOR LIFE - 5/14 | GENERAL | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0003429 | RELAY FOR LIFE - DEXTER LAWN - SAT MAY 15, 2010 BY 7 AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2010-05-13 | LA: INSTALL QUICK COUPLERS ON DEXTER LAWN - 5/14 | GENERAL | CLOSED | 0 | 0 | 40.368 | 40.368
PJ0003429 Total | [7 empty] | 0 | 0 | 248.172 | 248.172
PJ0003428 | M&R PARK 10/11: RESEAL & STRIPE KLAMATH PARKING LOT R-1 | POPHAM, DONALD J. | CLOSED | 2010-05-12 | AD: JOC 10.020.019 STAPLES | P-R01 | CLOSED | 51017.5572 | 0 | 55115.0259 | 55115.0259
PJ0003428 | M&R PARK 10/11: RESEAL & STRIPE KLAMATH PARKING LOT R-1 | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 5101.76 | 0 | 0 | 0
PJ0003428 Total | [7 empty] | 56119.3172 | 0 | 55115.0259 | 55115.0259
PJ0003426 | M&R PARK 10/11: RESEAL & STRIPE PARKING LOT C-2C | POPHAM, DONALD J. | CLOSED | 2010-05-12 | AD: JOC 10.020.028 STAPLES | P-C02 | CLOSED | 8726.92 | 0 | 9512.7601 | 9512.7601
PJ0003426 | M&R PARK 10/11: RESEAL & STRIPE PARKING LOT C-2C | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | P-C02 | CLOSED | 872.69 | 0 | 0 | 0
PJ0003426 Total | [7 empty] | 9599.61 | 0 | 9512.7601 | 9512.7601
PJ0003425 | M&R PARK 10/11: RESTRIPE SOUTH SPANOS PARKING LOT C-3B | POPHAM, DONALD J. | CLOSED | 2010-05-12 | AD: JOC 10.020.027 STAPLES | P-C03 | CLOSED | 4363.46 | 0 | 6214.3032 | 6214.3032
PJ0003425 | M&R PARK 10/11: RESTRIPE SOUTH SPANOS PARKING LOT C-3B | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | P-C03 | CLOSED | 436.35 | 0 | 0 | 0
PJ0003425 Total | [7 empty] | 4799.81 | 0 | 6214.3032 | 6214.3032
PJ0003424 | M&R PARK 10/11: ANNUAL PARKING STRUCTURE MAINT - 130, 271, & 371 | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CA: INSTALL HANDRAIL NEAR N. ELEVATOR, 4TH FLOOR - 130 | GEN-PARK | CLOSED | 1566.8202 | 0 | 1336.026 | 1336.026
PJ0003424 | M&R PARK 10/11: ANNUAL PARKING STRUCTURE MAINT - 130, 271, & 371 | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 1492.41 | 0 | 0 | 0
PJ0003424 | M&R PARK 10/11: ANNUAL PARKING STRUCTURE MAINT - 130, 271, & 371 | POPHAM, DONALD J. | CLOSED | 2010-05-12 | LA: CLEAN UP OF GREASE SPOTS AT PARKING STRUCTURES | GEN-PARK | CLOSED | 4630.2096 | 0 | 484.416 | 484.416
PJ0003424 Total | [7 empty] | 7689.4398 | 0 | 1820.442 | 1820.442
PJ0003423 | M&R PARK 10/11: TREE MAINT. & REMOVAL - PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2010-05-12 | AD: GREENVALE TREE COMPANY | GEN-PARK | CLOSED | 9630 | 0 | 9389.25 | 9389.25
PJ0003423 | M&R PARK 10/11: TREE MAINT. & REMOVAL - PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 1805.7 | 0 | 0 | 0
PJ0003423 | M&R PARK 10/11: TREE MAINT. & REMOVAL - PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2010-05-12 | LA: 2010/2011 PARKING LOT TREE TRIMMING WORK - GREENVALE (N/L) | GEN-PARK | CLOSED | 8426.82 | 0 | 11340 | 11340
PJ0003423 Total | [7 empty] | 19862.52 | 0 | 20729.25 | 20729.25
PJ0003422 | M&R PARK 10/11: RESEAL & STRIPE GROUNDS H-4C | POPHAM, DONALD J. | CLOSED | 2010-05-12 | AD: JOC 10.020.018 STAPLES | P-H04 | CLOSED | 6545.19 | 0 | 6625.5256 | 6625.5256
PJ0003422 | M&R PARK 10/11: RESEAL & STRIPE GROUNDS H-4C | POPHAM, DONALD J. | CLOSED | 2010-05-12 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 697.04 | 0 | 0 | 0
PJ0003422 | M&R PARK 10/11: RESEAL & STRIPE GROUNDS H-4C | POPHAM, DONALD J. | CLOSED | 2010-05-12 | EO: PATCH POTHOLES IN PARKING LOTS H4C AND C3. | P-H04 | CLOSED | 425.4379 | 0 | 461.28 | 461.28
PJ0003422 Total | [7 empty] | 7667.6679 | 0 | 7086.8056 | 7086.8056
PJ0003421 | INSTALL CUSTOMER SERVICE WALK UP WINDOW/COUNTER-BACK STAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-11 | AD: JOC 10.020.005 STAPLES | 065 | CLOSED | 7153.8274 | 0 | 7143.8764 | 7143.8764
PJ0003421 | INSTALL CUSTOMER SERVICE WALK UP WINDOW/COUNTER-BACK STAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-11 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003421 | INSTALL CUSTOMER SERVICE WALK UP WINDOW/COUNTER-BACK STAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-11 | EL: ADD RECEPTACLE FOR CASH REGISTER - BACKSTAGE PIZZA | 065 | CLOSED | 224.292 | 0 | 224.292 | 224.292
PJ0003421 | INSTALL CUSTOMER SERVICE WALK UP WINDOW/COUNTER-BACK STAGE PIZZA | KUENTZEL, DOUGLAS A. | CLOSED | 2010-05-11 | IN:INSTALL CUSTOMER SVC. WALK UP WINDOW/COUNTER-BACK STAGE PIZZA | 065 | CLOSED | 397.656 | 0 | 66.276 | 66.276
PJ0003421 Total | [7 empty] | 7775.7754 | 0 | 7434.4444 | 7434.4444
PJ0003420 | MAKE STORAGE ROOM INTO AN OFFICE - KEN LIB 35 RM 104A | MAY, TOM | CLOSED | 2010-05-11 | AD: FLOOR CONNECTION | 035 | CLOSED | 1355.155 | 0 | 1349.912 | 1349.912
PJ0003420 | MAKE STORAGE ROOM INTO AN OFFICE - KEN LIB 35 RM 104A | MAY, TOM | CLOSED | 2010-05-11 | CA:REMOVE SHELVING BRACKETS IN 35-104A | 035 | CLOSED | 63.687 | 0 | 63.516 | 63.516
PJ0003420 | MAKE STORAGE ROOM INTO AN OFFICE - KEN LIB 35 RM 104A | MAY, TOM | CLOSED | 2010-05-11 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 134.07 | 0 | 0 | 0
PJ0003420 | MAKE STORAGE ROOM INTO AN OFFICE - KEN LIB 35 RM 104A | MAY, TOM | CLOSED | 2010-05-11 | IN: MAKE STORAGE ROOM INTO AN OFFICE - KEN LIB 35 RM 104A | 035 | CLOSED | 66.276 | 0 | 99.414 | 99.414
PJ0003420 | MAKE STORAGE ROOM INTO AN OFFICE - KEN LIB 35 RM 104A | MAY, TOM | CLOSED | 2010-05-11 | PA:PATCH AND PAINT 35-104A | 035 | CLOSED | 585.0226 | 0 | 446.712 | 446.712
PJ0003420 Total | [7 empty] | 2204.2106 | 0 | 1959.554 | 1959.554
PJ0003419 | PAC MAINTENANCE WALK-THRU MAY 2010 - PAC (NO EST) | GRIFFIN, PATRICK E | CLOSED | 2010-05-06 | CA:PAC MAINTENANCE FOR SPRING QTR | 006 | CLOSED | 0 | 0 | 761.475 | 761.475
PJ0003419 | PAC MAINTENANCE WALK-THRU MAY 2010 - PAC (NO EST) | GRIFFIN, PATRICK E | CLOSED | 2010-05-06 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003419 | PAC MAINTENANCE WALK-THRU MAY 2010 - PAC (NO EST) | GRIFFIN, PATRICK E | CLOSED | 2010-05-06 | CU:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 13.665 | 13.665
PJ0003419 | PAC MAINTENANCE WALK-THRU MAY 2010 - PAC (NO EST) | GRIFFIN, PATRICK E | CLOSED | 2010-05-06 | EL:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 53.32 | 53.32
PJ0003419 | PAC MAINTENANCE WALK-THRU MAY 2010 - PAC (NO EST) | GRIFFIN, PATRICK E | CLOSED | 2010-05-06 | LO:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 47.64 | 47.64
PJ0003419 | PAC MAINTENANCE WALK-THRU MAY 2010 - PAC (NO EST) | GRIFFIN, PATRICK E | CLOSED | 2010-05-06 | PA:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 1382.14 | 1382.14
PJ0003419 Total | [7 empty] | 0 | 0 | 2258.24 | 2258.24
PJ0003418 | RENOVATE OLD WELDING SHOP - BLD 70D (MAINT) | MAY, TOM | CLOSED | 2010-05-06 | CA:CLOSE OUT WALL FOR STORAGE AT WELDING SHOP | 070D | CLOSED | 1338.4 | 0 | 2327.1 | 2327.1
PJ0003418 | RENOVATE OLD WELDING SHOP - BLD 70D (MAINT) | MAY, TOM | CLOSED | 2010-05-06 | CP: PROJECT CONTINGENCY | 070D | CLOSED | 465.65 | 0 | 0 | 0
PJ0003418 | RENOVATE OLD WELDING SHOP - BLD 70D (MAINT) | MAY, TOM | CLOSED | 2010-05-06 | LO: INSTALL LOCK SET AT OLD WELDING SHOP - BLDG. 070D | 070D | CLOSED | 195.28 | 0 | 235.28 | 235.28
PJ0003418 | RENOVATE OLD WELDING SHOP - BLD 70D (MAINT) | MAY, TOM | CLOSED | 2010-05-06 | PA:PAINT WELDING SHOP | 070D | CLOSED | 1074.561 | 0 | 1286.82 | 1286.82
PJ0003418 Total | [7 empty] | 3073.891 | 0 | 3849.2 | 3849.2
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | AD: CREDIT CARD PURCHASE - CHAIR FROM STAPLES | 035 | CLOSED | 0 | 0 | 217.58 | 217.58
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | AD: FLOOR CONNECTION | 035 | CLOSED | 1051.6709 | 0 | 1051.6816 | 1051.6816
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | AD: RUSSCO | 035 | CLOSED | 1750.6698 | 0 | 1720.4958 | 1720.4958
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | AD: SAN LUIS GLASS | 035 | CLOSED | 1367.888 | 0 | 1367.8773 | 1367.8773
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | CA:REMOVE CARPET IN LIBRARY 207/SIGNAGE FOR 207 | 035 | CLOSED | 2142.8568 | 0 | 2510.5082 | 2510.5082
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 145.53 | 0 | 0 | 0
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | EH&S: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 205 | 035 | CLOSED | 484.896 | 0 | 397.368 | 397.368
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | MO: MOVE BOXES FROM OFFICE 207 TO BONDERSON 212 | 035 | CLOSED | 31.5 | 0 | 45.456 | 45.456
PJ0003416 | SP 10/11: PAINT & CARPET OFFICE & SOUNDPROOF - BLD 35 RM 207 | MAY, TOM | CLOSED | 2010-05-06 | PA:PAINT WALL IN 35-207 | 035 | CLOSED | 525.0226 | 0 | 182.58 | 182.58
PJ0003416 Total | [7 empty] | 7500.0341 | 0 | 7493.5469 | 7493.5469
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | AD: JOC 10.020.037 STAPLES | 058 | CLOSED | 109882.6656 | 0 | 109882.6656 | 109882.6656
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | AD: QUAGLINO ROOFING | 058 | CLOSED | 204.37 | 0 | 204.37 | 204.37
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | AD: WAREHOUSE PARTS TO BE USED BY JOC (CHECK OUT TO PM) | 058 | CLOSED | 600 | 0 | 61.0134 | 61.0134
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 6034.9 | 0 | 0 | 0
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | CPES: INSTALL HVAC UNIT AND RELATED EQUIPMENT | 058 | CLOSED | 24165.1906 | 0 | 17019.9089 | 17019.9089
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | EH&S: CONSTRUCTION OF NEW OFFICES - BLD 58 RM 107 | 058 | CLOSED | 1297.92 | 0 | 1244.1 | 1244.1
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | EL: PANEL REPLACEMENT BLD 58 | 058 | CLOSED | 0 | 0 | 678.948 | 678.948
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | EL: SUPPLY ELECTRICAL | 058 | CLOSED | 24345.5564 | 0 | 22467.5409 | 22467.5409
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | IN: CONSTRUCTION OF NEW OFFICES - BLD 58 RM 107 | 058 | CLOSED | 397.656 | 0 | 662.76 | 662.76
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | LO: INSTALL LOCKS AS PER PLANS | 058 | CLOSED | 3550.176 | 0 | 3069.708 | 3069.708
PJ0003415 | CONSTRUCTION OF NEW OFFICES FOR PURCHASING - BLD 58 RM 107 | LAMPMAN, GREG | CLOSED | 2010-05-06 | PA: PAINT INTERIOR OF REMODEL | 058 | CLOSED | 5849.4 | 0 | 5661.384 | 5661.384
PJ0003415 Total | [7 empty] | 176327.8346 | 0 | 160952.3988 | 160952.3988
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: DEEP BLUE INTEGRATION, INC. | 027 | CLOSED | 2765.95 | 0 | 2765.95 | 2765.95
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: EMPIRE CONSTRUCTION | 027 | CLOSED | 749.5457 | 0 | 735.8176 | 735.8176
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: FLOOR CONNECTION | 027 | CLOSED | 2247 | 0 | 2980.6455 | 2980.6455
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: GRAND PERFORMANCE | 027 | CLOSED | 314.2376 | 0 | 335.98 | 335.98
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: JOC 10.020.011 STAPLES | 027 | CLOSED | 36766.5161 | 0 | 46281.1594 | 46281.1594
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: MCKENNA ENVIRONMENTAL | 027 | CLOSED | 3210 | 0 | 3235.252 | 3235.252
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: PURCHASE LIGHT FIXTURE TO BE INSTALLED BY SUBCONTRACTOR | 027 | CLOSED | 0 | 0 | 215.148 | 215.148
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | CA: DISASSEMBLE RECEPTION DESK - X-RAY LAB 27-178 | 027 | CLOSED | 55.38 | 0 | 225.5929 | 225.5929
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 2597.6 | 0 | 0 | 0
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | EH&S: M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | 027 | CLOSED | 180 | 0 | 250.5 | 250.5
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | EL:REMODEL X-RAY ROOM- RELOCATE AND INSTALL NEW ELECTRICAL | 027 | CLOSED | 14392.4588 | 0 | 1307.658 | 1307.658
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | ES:RELOCATE EXISTING DUCTWORK AS NEEDED | 027 | CLOSED | 3184.8317 | 0 | 2077.422 | 2077.422
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | IN: M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | 027 | CLOSED | 265.104 | 0 | 387.666 | 387.666
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | LO: SECURE DOOR TO 27-178E (DAMAGED BY SUBCONTRACTOR) | 027 | CLOSED | 0 | 0 | 267.066 | 267.066
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | LO:SUPPLY AND INSTALL LOCKS IN NEW DOORS | 027 | CLOSED | 2891.0731 | 0 | 3308.46 | 3308.46
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | MO:PROVIDE MOVING SUPPORT AS NEEDED | 027 | CLOSED | 189 | 0 | 102.276 | 102.276
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | PA:PAINT NEW WALLS, DOORS, AND CHAIR RAIL FOR X-RAY REMODEL | 027 | CLOSED | 6657.4111 | 0 | 4099.62 | 4099.62
PJ0003412 | M&R H/C 11/12: REMODEL X-RAY AREA - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | PL:DISCONNECT PLUMBING AND REMOVE FOR X-RAY REMODEL | 027 | CLOSED | 1578.4334 | 0 | 1140.0244 | 1140.0244
PJ0003412 Total | [7 empty] | 78044.5416 | 0 | 69716.2378 | 69716.2378
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: FLOOR CONNECTION | 027 | CLOSED | 535 | 0 | 535 | 535
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | AD: JOC 10.020.017 STAPLES | 027 | CLOSED | 10763.451 | 0 | 10763.451 | 10763.451
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | CA: ADDITIONAL WORK: DRILL HOLE FOR GROMMIT IN COUNTERTOP | 027 | CLOSED | 110.76 | 0 | 193.83 | 193.83
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1204.17 | 0 | 0 | 0
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | EH&S: M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | 027 | CLOSED | 259.584 | 0 | 259.584 | 259.584
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | EL PROVIDE EL;ECTRICAL SUPPORT | 027 | CLOSED | 735.3886 | 0 | 1352.856 | 1352.856
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | IN: M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | 027 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | LO:REMOVE CORES FROM CUPBOARDS AT HEALTH CENTER, ROOM 180 | 027 | CLOSED | 114.336 | 0 | 57.168 | 57.168
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | PA:VARNISH TRIM AND VENEER | 027 | CLOSED | 343.152 | 0 | 959.796 | 959.796
PJ0003411 | M&R H/C 10/11: REMODEL URGENT CARE - HC 27 | MOLLAN, CHERYL L. | CLOSED | 2010-05-05 | PL:DISCONNECT PLUMBING / RECONNECT | 027 | CLOSED | 1423.6265 | 0 | 1430.46 | 1430.46
PJ0003411 Total | [7 empty] | 15555.744 | 0 | 15618.421 | 15618.421
PJ0003410 | INSTALL SMART ROOM - BLD 10 RM 100 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-04-30 | CA: SMART ROOM MODIFICATIONS | 010 | CLOSED | 0 | 0 | 1091.67 | 1091.67
PJ0003410 | INSTALL SMART ROOM - BLD 10 RM 100 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-04-30 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0003410 | INSTALL SMART ROOM - BLD 10 RM 100 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-04-30 | EL:INSTALL SMART ROOM ELECTRICAL | 010 | CLOSED | 0 | 0 | 1950.438 | 1950.438
PJ0003410 | INSTALL SMART ROOM - BLD 10 RM 100 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-04-30 | IN: INSTALL SMART ROOM - BLD 10 RM 100 | 010 | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0003410 | INSTALL SMART ROOM - BLD 10 RM 100 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-04-30 | PA. PATCH AND PAINT | 010 | CLOSED | 0 | 0 | 871.488 | 871.488
PJ0003410 Total | [7 empty] | 0 | 0 | 3946.734 | 3946.734
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | ANTS: PROGRAMMING AND TESTING OF ALARM POINTS AT NEW MEATS LAB | 155 | CLOSED | 0 | 0 | 396.396 | 396.396
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CA: (V62611) PROVIDE & INSTALL TOWEL & SOAP DISPENSERS - BLD155 | 155 | CLOSED | 0 | 0 | 786.266 | 786.266
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CA: ASSIST ELECTRICIANS WITH POWER POLE INSTALLATION - MEATS CTR | 155 | CLOSED | 1043.04 | 0 | 387.54 | 387.54
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CA: FABRICATE & INSTALL (2) "MAIN ELECTRIC ROOM" SIGNS- BLDG 155 | 155 | CLOSED | 0 | 0 | 120.576 | 120.576
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 48956.96 | 0 | 0 | 0
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CPE: (MAINT) REVIEW WORK INSTALLATIONS FOR MEAT PROCESSING CTR. | 155 | CLOSED | 0 | 0 | 12667.6075 | 12667.6075
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CPE: REFRIGERATION INSPECTION - MEATS PROCESSING | 155 | CLOSED | 0 | 0 | 2214.864 | 2214.864
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | CPE: TOOLS AND PARTS FOR MEATS PROCESSING CENTER - 155 | 155 | CLOSED | 0 | 0 | 473.382 | 473.382
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | EL: INSTALL UTILITY POLES/SUPPORT TO PULL POWER FROM OLD POULTRY | 155 | CLOSED | 0 | 0 | 49484.16 | 49484.16
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | EL: MARK UTILITIES FOR MEATS PROCESSING CENTER PROJECT | 155 | CLOSED | 0 | 0 | 1506.348 | 1506.348
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | EL: PROVIDE THE METERING/SCADA TO THE MAIN SWITCH BOARD FOR MPC | 155 | CLOSED | 0 | 0 | 1892.688 | 1892.688
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | EO: SUPPORT METERS/SIGNAGE INSTALLATION FOR UPD AT NEW MEATS LAB | 155 | CLOSED | 0 | 0 | 199.056 | 199.056
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | ES: BOILER AT MEATS PROCESSING LAB | 155 | CLOSED | 0 | 0 | 2950.074 | 2950.074
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | LO: ORDER & INSTALL 20 CORES FOR VARIOUS LOCATIONS AT BLDG 154 | 155 | CLOSED | 0 | 0 | 3535.08 | 3535.08
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | LO: SUPPLY 2 ORANGE-CORE PADLOCKS FOR NEW MEAT PROCESS CTR | 155 | CLOSED | 0 | 0 | 184.584 | 184.584
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: ASSIST WITH GAS SHUTDOWN @ POULTRY ON THURSDAY, MARCH 31ST | 155 | CLOSED | 0 | 0 | 381.456 | 381.456
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: FLOW TEST AT MEAT PROCESSING CENTER - FRM | 155 | CLOSED | 0 | 0 | 349.668 | 349.668
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: INSTALL PLUMBING FOR TWO SINKS - MEATS PROCESSING CTR. | 155 | CLOSED | 0 | 0 | 3824.376 | 3824.376
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: INSTALL WATER METER ON HYDRANT AT POULTRY SCIENCE | 155 | CLOSED | 0 | 0 | 254.304 | 254.304
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: MARK UTILITIES FOR MEATS PROCESSING CENTER PROJECT | 155 | CLOSED | 0 | 0 | 32.646 | 32.646
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: MARK WATER LINE ON STENNER CREEK ROAD, ACROSS FROM POULTRY | 155 | CLOSED | 0 | 0 | 1145.298 | 1145.298
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: ORDER/INSTALL DOMESTIC HOT WATER BOOSTER PUMP- MEATS LAB 155 | 155 | CLOSED | 0 | 0 | 97.938 | 97.938
PJ0003408 | MJ: TRADES SUPPORT SERVICES - NEW MEAT PROCESSING CENTER (155) | QUEEN, BARBARA | CLOSED | 2010-04-30 | PL: PERFORM STATIC PRESSURE READING AT POULTRY CTR FIRE HYDRANT | 155 | CLOSED | 0 | 0 | 1554.984 | 1554.984
PJ0003408 Total | [7 empty] | 50000 | 0 | 84439.2915 | 84439.2915
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | AD: AIR POLLUTION CONTROL DISTRICT FEES | RESIDENCE | CLOSED | 235.4 | 0 | 235.4 | 235.4
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | AD: JOC 08.018.039 MAINO | RESIDENCE | CLOSED | 115365.1209 | 0 | 111620.1423 | 111620.1423
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | AD: JOC 09.019.028 STAPLES | RESIDENCE | CLOSED | 230827.034 | 0 | 230174.6978 | 230174.6978
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | AD: MAINO (LOW-VALUE PUBLIC WORKS) | RESIDENCE | CLOSED | 0 | 0 | 3738.1199 | 3738.1199
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | AD: MECA | RESIDENCE | CLOSED | 4526.1 | 0 | 4510.05 | 4510.05
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | AD: THOMA ELECTRIC | RESIDENCE | CLOSED | 5350 | 0 | 5122.09 | 5122.09
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 802.74 | 0 | 0 | 0
PJ0003407 | FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | MAY, TOM | CLOSED | 2010-04-29 | IN: FREMONT & SEQUOIA CLOSET REMODEL & FURNITURE | RESIDENCE | CLOSED | 265.104 | 0 | 231.966 | 231.966
PJ0003407 Total | [7 empty] | 357371.4989 | 0 | 355632.466 | 355632.466
PJ0003404 | M&R HOUS 10/11: SIERRA MADRE - REPLACE SEWER LINES | MAY, TOM | CLOSED | 2010-04-29 | AD: JOC 10.020.022 STAPLES | 113 | CLOSED | 88049.02 | 0 | 88049.02 | 88049.02
PJ0003404 | M&R HOUS 10/11: SIERRA MADRE - REPLACE SEWER LINES | MAY, TOM | CLOSED | 2010-04-29 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 0 | 0 | 0 | 0
PJ0003404 | M&R HOUS 10/11: SIERRA MADRE - REPLACE SEWER LINES | MAY, TOM | CLOSED | 2010-04-29 | EL:ASSIST WITH SIERRA MADRE SEWER PROJECT | 113 | CLOSED | 1206.73 | 0 | 1464.5024 | 1464.5024
PJ0003404 | M&R HOUS 10/11: SIERRA MADRE - REPLACE SEWER LINES | MAY, TOM | CLOSED | 2010-04-29 | IN: M&R HOUSING 10/11: SIERRA MADRE - REPLACE SEWER LINES | 113 | CLOSED | 165.69 | 0 | 193.305 | 193.305
PJ0003404 | M&R HOUS 10/11: SIERRA MADRE - REPLACE SEWER LINES | MAY, TOM | CLOSED | 2010-04-29 | LA:ASSIST WITH SIERRA MADRE PROJECT | 113 | CLOSED | 9536.8 | 0 | 9355.34 | 9355.34
PJ0003404 | M&R HOUS 10/11: SIERRA MADRE - REPLACE SEWER LINES | MAY, TOM | CLOSED | 2010-04-29 | PL:ASSIST WITH SIERRA MADRE SEWER PROJECT | 113 | CLOSED | 423.84 | 0 | 791.26 | 791.26
PJ0003404 Total | [7 empty] | 99382.08 | 0 | 99853.4274 | 99853.4274
PJ0003403 | M&R HOUS 10/11: SIERRA MADRE - PICNIC & VOLLEYBALL REPAIR | MAY, TOM | CLOSED | 2010-04-29 | CA:CORE 2 HOLES IN RETAINING WALL FOR DRAINAGE-S/M-BACK VB COURT | 113 | CLOSED | 2289.425 | 0 | 2864.735 | 2864.735
PJ0003403 | M&R HOUS 10/11: SIERRA MADRE - PICNIC & VOLLEYBALL REPAIR | MAY, TOM | CLOSED | 2010-04-29 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 0 | 0 | 0 | 0
PJ0003403 | M&R HOUS 10/11: SIERRA MADRE - PICNIC & VOLLEYBALL REPAIR | MAY, TOM | CLOSED | 2010-04-29 | EO: SIERRA MADRE VOLLEYBALL COURTS PROJECT | 113 | CLOSED | 0 | 0 | 3855.708 | 3855.708
PJ0003403 Total | [7 empty] | 2289.425 | 0 | 6720.443 | 6720.443
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | AD: JOC 09.019.030 STAPLES | 114 | CLOSED | 277437.66 | 0 | 277437.66 | 277437.66
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | AD: VISALIA TILE | 114 | CLOSED | 4248.99 | 0 | 4248.99 | 4248.99
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | AD: WAREHOUSE PARTS TO BE INSTALLED BY JOC | 114 | CLOSED | 0 | 0 | 119.0366 | 119.0366
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | CA: PURCHASE AND INSTALL 5 ACCESS PANELS FOR YOSEMITE T3 | 114 | CLOSED | 1615.9 | 0 | 1486.356 | 1486.356
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 0 | 0 | 0 | 0
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | EL:ASSIST IN YOS T3 RESTROOM REMODEL | 114 | CLOSED | 5299.24 | 0 | 5530.622 | 5530.622
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | ES:INSTALL (5) NEW REGISTERS IN (5) RESTROOMS IN YOS T3 | 114 | CLOSED | 960.4 | 0 | 762.35 | 762.35
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | IN: M&R HOUSING 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | 114 | CLOSED | 441.84 | 0 | 414.225 | 414.225
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | LO:INSTALL ORANGE CORES AND INSTALL DEAD BOLTS-YOS T3 | 114 | CLOSED | 588.2 | 0 | 716.28 | 716.28
PJ0003402 | M&R HOUS 10/11: YOSEMITE T3 RESTROOM REMODEL CONTINUED | MAY, TOM | CLOSED | 2010-04-29 | PL: REMOVE OLD/PROVIDE NEW FIXTURES FOR YOSEMITE TOWER 3 RESTRMS | 114 | CLOSED | 18572.84 | 0 | 18328.29 | 18328.29
PJ0003402 Total | [7 empty] | 309165.07 | 0 | 309043.8096 | 309043.8096
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | AD: BOB'S CRANE | 108 | CLOSED | 800 | 0 | 1850 | 1850
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | AD: JOC 09.019.022 STAPLES | 108 | CLOSED | 272851.53 | 0 | 272851.53 | 272851.53
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | AD: THOMA ELECTRIC | 108 | CLOSED | 5000 | 0 | 4505 | 4505
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | CA:REMOVE TANK ENCLOSURES FREMONT SEQUOIA | 108 | CLOSED | 19234.724 | 0 | 4694.1925 | 4694.1925
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | CP: PROJECT CONTINGENCY | 108 | CLOSED | 0 | 0 | 0 | 0
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | EL:ASSIST PL WITH CIRC. PUMP REMOVAL FREMONT/SEQUOIA | 108 | CLOSED | 422.96 | 0 | 79.305 | 79.305
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | EO:REMOVE (4) BOLLARDS BEHIND FREMONT/SEQUOIA | 108 | CLOSED | 708.677 | 0 | 193.1 | 193.1
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | ES:REGISTERS FOR DORMS | 108 | CLOSED | 25300.98 | 0 | 35344.2 | 35344.2
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | IN: M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | 108 | CLOSED | 441.84 | 0 | 441.84 | 441.84
PJ0003401 | M&R HOUS 10/11: SEQUOIA - REPLACE ROOF & REMOVE SOLAR PANEL | MAY, TOM | CLOSED | 2010-04-29 | PL:REMOVE PIPES FROM TOWERS FREMONT/SEQUOIA | 108 | CLOSED | 3646.0836 | 0 | 2667.66 | 2667.66
PJ0003401 Total | [7 empty] | 328406.7946 | 0 | 322626.8275 | 322626.8275
PJ0003400 | DESIGN PAINT SHOP RECONFIGURATION FOR CUSTODIAL-BLDG 70E (MAINT) | LAMPMAN, GREG | CLOSED | 2010-04-29 | CP: PROJECT CONTINGENCY | 070E | CLOSED | 0 | 0 | 0 | 0
PJ0003400 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | AD: COASTAL JANITORIAL - POWERWASHING BLDG 25 STAIRS | 052 | CLOSED | 0 | 0 | 615.25 | 615.25
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | CA: CENTER FOR SCIENCE GROUNDBREAKIUNG SUPPORT-5/1 | 052 | CLOSED | 0 | 0 | 443.04 | 443.04
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | CA: SET UP BANNER FOR CTS DEDICATION - 5/1 | 052 | CLOSED | 0 | 0 | 1068.264 | 1068.264
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | LA: LANDSCAPE SERVICES SUPPORT FOR CTS GROUNDBREAKING | 052 | CLOSED | 0 | 0 | 1291.776 | 1291.776
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | PA: PAINT STEPS TO BLDG 25 FOR CTR FOR SCI GROUNDBREAKING - 5/1 | 052 | CLOSED | 0 | 0 | 714.9 | 714.9
PJ0003398 | FACS SUPPORT FOR CENTER FOR SCI. GROUND BREAKING EVENT - BLDG 52 | POPHAM, DONALD J. | CLOSED | 2010-04-27 | SUPPLY RENTAL: CENTER FOR SCIENCE LUNCHEON - 4/30 | 052 | CLOSED | 0 | 0 | 108 | 108
PJ0003398 Total | [7 empty] | 0 | 0 | 4241.23 | 4241.23
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | AD: EARTH SYSTEMS - SPECIAL WELDING INSPECTION | 083 | CLOSED | 3488.2 | 0 | 799.29 | 799.29
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | AD: ENGLEKIRK & SABOL - SEISMIC PEER REVIEW | 083 | CLOSED | 720 | 0 | 720 | 720
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | AD: STATE FIRE MARSHAL PLAN CHECK AND INSPECTION | 083 | CLOSED | 2080 | 0 | 0 | 0
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | IN: CAL POLY BUILDING PERMIT FEES | 083 | CLOSED | 1466.1 | 0 | 1466.1 | 1466.1
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | IN: CAL POLY PLAN REVIEW FEES | 083 | CLOSED | 1304.93 | 0 | 1304.83 | 1304.83
PJ0003397 | TI PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK LAB SPACE 2A | HOGAN, MIKE | CLOSED | 2010-04-26 | IN: PERMIT FOR APPLIED TECHNOLOGY - BLD 83 TECH PARK (MAINT) | 083 | CLOSED | 0 | 0 | 1684.515 | 1684.515
PJ0003397 Total | [7 empty] | 9059.23 | 0 | 5974.735 | 5974.735
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | CA: 2010 BAKER FORUM SUPPORT: APRIL 30 - MAY 3 | GENERAL | CLOSED | 0 | 0 | 184.6 | 184.6
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | CU: CUSTODIAL PAC/SPANOS THEATRE SUPPORT BAKER FORUM- 5/2 & 5/3 | GENERAL | CLOSED | 0 | 0 | 658.35 | 658.35
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | CU: CUSTODIAL SUPPORT FOR 2010 BAKER FORUM | GENERAL | CLOSED | 0 | 0 | 1055.04 | 1055.04
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | CU: PRE-BAKER FORUM CLEAN UP OF ATL AND BONDERSON | GENERAL | CLOSED | 0 | 0 | 1316.7 | 1316.7
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | EL: CHECK LIGHTS IN ATL, BONDERSON, UH, & PAC - BAKER FORUM | GENERAL | CLOSED | 0 | 0 | 1082.0364 | 1082.0364
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | MC:SUPPORT FOR BAKER FORUM - 5/3 AND 4 | GENERAL | CLOSED | 0 | 0 | 56.82 | 56.82
PJ0003396 | SUPPORT FOR BAKER FORUM / APRIL 30- MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2010-04-22 | PL: 2010 BAKER FORUM SUPPORT: APRIL 30 - MAY 3 | GENERAL | CLOSED | 0 | 0 | 317.88 | 317.88
PJ0003396 Total | [7 empty] | 0 | 0 | 4671.4264 | 4671.4264
PJ0003395 | MOUNT TACKBOARDS & TV & CHANGE LIGHTS - DEXTER BLDG 34 RM 210 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | CA:INSTALL TACKBOARDS AT DEXTER 210 | 034 | CLOSED | 3152.7156 | 0 | 3526.23 | 3526.23
PJ0003395 | MOUNT TACKBOARDS & TV & CHANGE LIGHTS - DEXTER BLDG 34 RM 210 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 262.21 | 0 | 0 | 0
PJ0003395 | MOUNT TACKBOARDS & TV & CHANGE LIGHTS - DEXTER BLDG 34 RM 210 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | EL: INSTALL NEW CIRCUIT AT DEXTER 210 | 034 | CLOSED | 1545.558 | 0 | 670.182 | 670.182
PJ0003395 | MOUNT TACKBOARDS & TV & CHANGE LIGHTS - DEXTER BLDG 34 RM 210 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | PA: PREP AND PAINT SCREEN BOARDS FOR DEXTER 210 | 034 | CLOSED | 207.576 | 0 | 721.56 | 721.56
PJ0003395 Total | [7 empty] | 5168.0596 | 0 | 4917.972 | 4917.972
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | AD: INNOVATION COMMERCIAL FLOORING | 014 | CLOSED | 3837.555 | 0 | 3873.4 | 3873.4
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 2140 | 0 | 1369.5893 | 1369.5893
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | CA:REMOVE RAISED FLOOR 14-255 | 014 | CLOSED | 8596.0344 | 0 | 6128.1604 | 6128.1604
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 145.55 | 0 | 0 | 0
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | EL:INSTALL T-BAR LIGHTS AND OUTLETS IN RACEWAY 14-255 | 014 | CLOSED | 7086.428 | 0 | 4942.404 | 4942.404
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | ES:INSTALL NEW REGISTERS IN 14-255 | 014 | CLOSED | 827.8138 | 0 | 692.688 | 692.688
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | IN: UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | 014 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003394 | UPGRADE FLOORS, WIRING, LIGHTING AND BLINDS - BLD 14 RM 255 | MAY, TOM | CLOSED | 2010-04-16 | PA:PATCH/PAINT 14-255 | 014 | CLOSED | 1694.4958 | 0 | 2369.688 | 2369.688
PJ0003394 Total | [7 empty] | 24460.429 | 0 | 19508.4817 | 19508.4817
PJ0003392 | INSTALL 2ND CABLE LINE FROM SATELLITE DISH THRU ATTIC - 03-409 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | AD: AHERN RENTALS (HIGH LIFT) | 003 | CLOSED | 825 | 0 | 883.79 | 883.79
PJ0003392 | INSTALL 2ND CABLE LINE FROM SATELLITE DISH THRU ATTIC - 03-409 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 151.66 | 0 | 0 | 0
PJ0003392 | INSTALL 2ND CABLE LINE FROM SATELLITE DISH THRU ATTIC - 03-409 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | EL:RUN NEW CABLE FOR SATELLITE DISH 03-409B | 003 | CLOSED | 567.552 | 0 | 380.664 | 380.664
PJ0003392 | INSTALL 2ND CABLE LINE FROM SATELLITE DISH THRU ATTIC - 03-409 | GRIFFIN, PATRICK E | CLOSED | 2010-04-21 | IN:INSTALL 2ND CABLE LINE FROM SATELLITE DISH THRU ATTIC 03-409 | 003 | CLOSED | 66.276 | 0 | 33.138 | 33.138
PJ0003392 Total | [7 empty] | 1610.488 | 0 | 1297.592 | 1297.592
PJ0003391 | UPGRADE GOSS PRESS - BLD 26A | MAY, TOM | CLOSED | 2010-04-15 | AD: CREDIT CARD PURCHASE - GRAYLIFT FORKLIFT RENTAL | 026A | CLOSED | 0 | 0 | 1067.33 | 1067.33
PJ0003391 | UPGRADE GOSS PRESS - BLD 26A | MAY, TOM | CLOSED | 2010-04-15 | AD: UNITED RENTAL | 026A | CLOSED | 1605 | 0 | 781.7741 | 781.7741
PJ0003391 | UPGRADE GOSS PRESS - BLD 26A | MAY, TOM | CLOSED | 2010-04-15 | CP: PROJECT CONTINGENCY | 026A | CLOSED | 1816.68 | 0 | 0 | 0
PJ0003391 | UPGRADE GOSS PRESS - BLD 26A | MAY, TOM | CLOSED | 2010-04-15 | EL:ASSIST IN GOSS PRESS UPGRADE-26A | 026A | CLOSED | 14910.8107 | 0 | 16299.294 | 16299.294
PJ0003391 | UPGRADE GOSS PRESS - BLD 26A | MAY, TOM | CLOSED | 2010-04-15 | IN: UPGRADE GOSS PRESS - BLD 26A | 026A | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003391 | UPGRADE GOSS PRESS - BLD 26A | MAY, TOM | CLOSED | 2010-04-15 | PL:ASSIST IN GOSS PRESS ADDITION 26A | 026A | CLOSED | 1518.4334 | 0 | 835.4616 | 835.4616
PJ0003391 Total | [7 empty] | 19983.4762 | 0 | 19116.4117 | 19116.4117
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 2140 | 0 | 2985.3 | 2985.3
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | CA:REMOVE A WALL BETWEEN 248/249 IN 14 | 014 | CLOSED | 6790.0572 | 0 | 5942.7224 | 5942.7224
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 1380.1 | 0 | 0 | 0
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | EL:RELOCATE ELECTRICAL IN WALL 14-248/249 | 014 | CLOSED | 1236.1974 | 0 | 3482.6201 | 3482.6201
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | ES:INSTALL NEW REGISTERS 14-248 | 014 | CLOSED | 293.9069 | 0 | 603.726 | 603.726
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | IN: COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | 014 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | LO:INSTALL (3) SETS OF PANIC HARDWARE 14-249 | 014 | CLOSED | 1908.672 | 0 | 2854.272 | 2854.272
PJ0003390 | COMBINE LECTURE RMS INTO ONE SPACE - BLD 14 RM 248/249 | MAY, TOM | CLOSED | 2010-04-14 | PA: PATCH AND PAINT IN 14-248/249 | 014 | CLOSED | 2338.9464 | 0 | 914.52 | 914.52
PJ0003390 Total | [7 empty] | 16220.4319 | 0 | 16915.7125 | 16915.7125
PJ0003389 | REMODEL TO CREATE 30 SEAT TEACHING LAB - BLD 20 RM B136 | MAY, TOM | CLOSED | 2010-04-09 | CA:REMOVE WALL IN 20-136 NEW TASK: INSTALL WHITEBOARD | 020 | CLOSED | 1644.6114 | 0 | 876.147 | 876.147
PJ0003389 | REMODEL TO CREATE 30 SEAT TEACHING LAB - BLD 20 RM B136 | MAY, TOM | CLOSED | 2010-04-09 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 226.39 | 0 | 0 | 0
PJ0003389 | REMODEL TO CREATE 30 SEAT TEACHING LAB - BLD 20 RM B136 | MAY, TOM | CLOSED | 2010-04-09 | EL:REMOVE OUTLET FROM WALL IN 20-136 | 020 | CLOSED | 63.444 | 0 | 73.836 | 73.836
PJ0003389 | REMODEL TO CREATE 30 SEAT TEACHING LAB - BLD 20 RM B136 | MAY, TOM | CLOSED | 2010-04-09 | PA:PATCH AND PAINT ATTACHMENT POINTS IN 20-136 | 020 | CLOSED | 457.536 | 0 | 629.112 | 629.112
PJ0003389 Total | [7 empty] | 2391.9814 | 0 | 1579.095 | 1579.095
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | AD: BKM FURNITURE | 035 | CLOSED | 19089.5276 | 0 | 19089.5276 | 19089.5276
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | AD: FLOOR CONNECTION | 035 | CLOSED | 5652.2643 | 0 | 6094.1315 | 6094.1315
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5770.6598 | 0 | 5485.6011 | 5485.6011
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | CA:BUILD A WALL IN 35-202 TO DIVIDE INTO TWO ROOMS | 035 | CLOSED | 7686.4602 | 0 | 8788.332 | 8788.332
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | CU: CLEAN LEDGE ABOVE WINDOWS - KENNEDY LIBRARY RMS 202A & 202B | 035 | CLOSED | 131.184 | 0 | 65.592 | 65.592
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | EL:INSTALL NEW ELECTRICAL IN NEW WALL IN 25-202 | 035 | CLOSED | 16399.1947 | 0 | 15981.9802 | 15981.9802
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | IN: SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | 035 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | LO: CHANGE FUNCTION OF DOOR TO CLASSROOM IN LIBRARY 35-202B | 035 | CLOSED | 114.336 | 0 | 57.168 | 57.168
PJ0003388 | SP 09/10: DIVIDE INTO TWO ROOMS, RENOVATE - BLDG 35 RM 202 | MAY, TOM | CLOSED | 2010-04-08 | PA:TAPE, MUD AND PAINT ROOMS 35-202A/B | 035 | CLOSED | 2527.68 | 0 | 2717.304 | 2717.304
PJ0003388 Total | [7 empty] | 57503.8586 | 0 | 58412.1884 | 58412.1884
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | AD: BKM (FURNITURE AND RAISED FLOORING) | 035 | CLOSED | 31145.0999 | 0 | 24740.5614 | 24740.5614
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | AD: EC WEST | 035 | CLOSED | 25088.5575 | 0 | 25088.5575 | 25088.5575
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | AD: FLOOR CONNECTION | 035 | CLOSED | 4735.285 | 0 | 4805.4342 | 4805.4342
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5330.74 | 0 | 5330.74 | 5330.74
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | CA:REMOVE BUILT IN CABINETS IN 35-111H | 035 | CLOSED | 2350.4172 | 0 | 1472.541 | 1472.541
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | EL:PROVIDE ELECT FOR NEW POWER FLOOR IN 35-111H | 035 | CLOSED | 15752.4787 | 0 | 19826.616 | 19826.616
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | IN: SP 09/10: RENOVATE FLOOR, CEILING, PAINT, FURNITURE 35-111H | 035 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003387 | SP 09/10: RENOVATE - FLOOR, CEILING, PAINT, FURNITURE - 35-111H | MAY, TOM | CLOSED | 2010-04-08 | PA:PAINT 35-111H AFTER CABINET DEMO | 035 | CLOSED | 1732.608 | 0 | 512.4 | 512.4
PJ0003387 Total | [7 empty] | 86267.7383 | 0 | 81909.4021 | 81909.4021
PJ0003386 | REPLACE 4 WINDOWS, INSTALL WINDOWS IN 3 DOORS-LIB 35 104,111,114 | MAY, TOM | CLOSED | 2010-04-07 | AD: SAN LUIS GLASS | 035 | CLOSED | 1168.8145 | 0 | 1168.8038 | 1168.8038
PJ0003386 | REPLACE 4 WINDOWS, INSTALL WINDOWS IN 3 DOORS-LIB 35 104,111,114 | MAY, TOM | CLOSED | 2010-04-07 | CA:INSTALL WINDOWS IN DOORS IN THE LIBRARY | 035 | CLOSED | 1123.5216 | 0 | 1309.818 | 1309.818
PJ0003386 | REPLACE 4 WINDOWS, INSTALL WINDOWS IN 3 DOORS-LIB 35 104,111,114 | MAY, TOM | CLOSED | 2010-04-07 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 229.25 | 0 | 0 | 0
PJ0003386 Total | [7 empty] | 2521.5861 | 0 | 2478.6218 | 2478.6218
PJ0003385 | SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | AD: BUEHLER AND BUEHLER | 006 | CLOSED | 2300 | 0 | 2300 | 2300
PJ0003385 | SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | AD: EARTH SYSTEMS | 006 | CLOSED | 8083 | 0 | 7020.25 | 7020.25
PJ0003385 | SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | AD: JOC 10.020.013.00 STAPLES | 006 | CLOSED | 246855.24 | 0 | 253765.9 | 253765.9
PJ0003385 | SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 20000 | 0 | 0 | 0
PJ0003385 | SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | IN: SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | 006 | CLOSED | 441.84 | 0 | 165.69 | 165.69
PJ0003385 | SR 10/11: REPAIR PAC RETAINING WALL - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | LA: REPAIR PLANTER DAMMAGE | 006 | CLOSED | 1038.24 | 0 | 67.28 | 67.28
PJ0003385 Total | [7 empty] | 278718.32 | 0 | 263319.12 | 263319.12
PJ0003384 | SR 10/11: REBUILD ROAD BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2010-04-06 | AD: EARTH SYSTEMS PACIFIC | GENERAL | CLOSED | 2650 | 0 | 2207 | 2207
PJ0003384 | SR 10/11: REBUILD ROAD BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2010-04-06 | AD: JOC 10.020.023 STAPLES | GENERAL | CLOSED | 83387.49 | 0 | 83387.49 | 83387.49
PJ0003384 | SR 10/11: REBUILD ROAD BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2010-04-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003384 | SR 10/11: REBUILD ROAD BETWEEN STADIUM & POLY GROVE | LAMPMAN, GREG | CLOSED | 2010-04-06 | IN: SR 10/11: REBUILD ROAD BETWEEN STADIUM & POLY GROVE | GENERAL | CLOSED | 165.69 | 0 | 165.69 | 165.69
PJ0003384 Total | [7 empty] | 86203.18 | 0 | 85760.18 | 85760.18
PJ0003383 | REMOVE KEY REQUIREMENT FROM BACK STAGE ELEVATOR - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | AD: REPUBLIC ELEVATOR | 006 | CLOSED | 569.0795 | 0 | 569.0795 | 569.0795
PJ0003383 | REMOVE KEY REQUIREMENT FROM BACK STAGE ELEVATOR - BLDG 006 | LAMPMAN, GREG | CLOSED | 2010-04-06 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 56.91 | 0 | 0 | 0
PJ0003383 Total | [7 empty] | 625.9895 | 0 | 569.0795 | 569.0795
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | AD: JOC 10.020.043 STAPLES | 006 | CLOSED | 29599.8059 | 0 | 29599.8059 | 29599.8059
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | AD: KIRKEGAARD (CHARGES TO Z93070) | 006 | CLOSED | 1605 | 0 | 1284 | 1284
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 3180.56 | 0 | 0 | 0
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | EL: INSTALL POWER FOR CURTAIN SYSTEM | 006 | CLOSED | 1128.216 | 0 | 697.884 | 697.884
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | ES:REMOVE DUCT FROM GRILL | 006 | CLOSED | 128.064 | 0 | 96.048 | 96.048
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | IN: MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX -PAC 201B | 006 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | MO: MOVE PLYWOOD AND SHORING LUMBER | 006 | CLOSED | 157.5 | 0 | 74.028 | 74.028
PJ0003382 | MOTORIZED VELOUR ACOUSTIC CURTAIN, PRESIDENT'S BOX - PAC 201B | LAMPMAN, GREG | CLOSED | 2010-04-05 | PA: PATCH AND PAINT AS NEEDED (N/L) | 006 | CLOSED | 463.152 | 0 | 0 | 0
PJ0003382 Total | [7 empty] | 36394.8499 | 0 | 31884.3179 | 31884.3179
PJ0003381 | INSTALL RECEPTACLE FOR VIDEO PROJECTOR - PAC RM 302 | LAMPMAN, GREG | CLOSED | 2010-04-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 556.89 | 0 | 0 | 0
PJ0003381 | INSTALL RECEPTACLE FOR VIDEO PROJECTOR - PAC RM 302 | LAMPMAN, GREG | CLOSED | 2010-04-05 | EL: INSTALL ELECTRICAL FOR PROJECTOR FAN | 006 | CLOSED | 373.776 | 0 | 715.26 | 715.26
PJ0003381 | INSTALL RECEPTACLE FOR VIDEO PROJECTOR - PAC RM 302 | LAMPMAN, GREG | CLOSED | 2010-04-05 | ES: INSTALL EX-FAN FOR PROJECTOR | 006 | CLOSED | 4679.2339 | 0 | 4095.288 | 4095.288
PJ0003381 | INSTALL RECEPTACLE FOR VIDEO PROJECTOR - PAC RM 302 | LAMPMAN, GREG | CLOSED | 2010-04-05 | IN: INSTALL RECEPTACLE FOR VIDEO PROJECTOR - PAC RM 302 | 006 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003381 Total | [7 empty] | 5676.1759 | 0 | 4876.824 | 4876.824
PJ0003380 | STEEL COVER BLD WITH SLAB FOR EQUIPMENT - VINEYARD C71 | LAMPMAN, GREG | CLOSED | 2010-04-01 | AD: EARTH SYSTEMS | GENERAL | CLOSED | 2675 | 0 | 1378.16 | 1378.16
PJ0003380 | STEEL COVER BLD WITH SLAB FOR EQUIPMENT - VINEYARD C71 | LAMPMAN, GREG | CLOSED | 2010-04-01 | AD: ENGLEKIRK AND SABOL | GENERAL | CLOSED | 588.5 | 0 | 588.5 | 588.5
PJ0003380 | STEEL COVER BLD WITH SLAB FOR EQUIPMENT - VINEYARD C71 | LAMPMAN, GREG | CLOSED | 2010-04-01 | AD: JOC 09.019.016 STAPLES | GENERAL | CLOSED | 47106.4932 | 0 | 47106.4932 | 47106.4932
PJ0003380 | STEEL COVER BLD WITH SLAB FOR EQUIPMENT - VINEYARD C71 | LAMPMAN, GREG | CLOSED | 2010-04-01 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 4409.53 | 0 | 0 | 0
PJ0003380 | STEEL COVER BLD WITH SLAB FOR EQUIPMENT - VINEYARD C71 | LAMPMAN, GREG | CLOSED | 2010-04-01 | IN: STEEL COVER BLD WITH SLAB FOR EQUIPMENT - VINEYARD C71 | GENERAL | CLOSED | 198.828 | 0 | 132.552 | 132.552
PJ0003380 Total | [7 empty] | 54978.3512 | 0 | 49205.7052 | 49205.7052
PJ0003378 | CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | MAY, TOM | CLOSED | 2010-03-26 | CA:CONCRETE PAD FOR MILES CAR AT 81 | 081 | CLOSED | 2826.6402 | 0 | 3659.3688 | 3659.3688
PJ0003378 | CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | MAY, TOM | CLOSED | 2010-03-26 | CP: PROJECT CONTINGENCY | 081 | CLOSED | 590.25 | 0 | 0 | 0
PJ0003378 | CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | MAY, TOM | CLOSED | 2010-03-26 | EL:RUN ELECTRICAL AND INSTALL A CHARGING MONUMENT AT 81 | 081 | CLOSED | 2106.6133 | 0 | 784.65 | 784.65
PJ0003378 | CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | MAY, TOM | CLOSED | 2010-03-26 | EO:EXCAVATE FOR CONCRETE PAD FOR MILES CAR AT 81 | 081 | CLOSED | 741.504 | 0 | 996.396 | 996.396
PJ0003378 | CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | MAY, TOM | CLOSED | 2010-03-26 | IN: CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | 081 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003378 | CHARGING STATION/PARKING FOR ELECTRIC VEHICLE - BLD 81 | MAY, TOM | CLOSED | 2010-03-26 | LA:ASSIST WITH CHARGING PAD FOR MILES CAR AT 81 | 081 | CLOSED | 161.472 | 0 | 643.608 | 643.608
PJ0003378 Total | [7 empty] | 6492.7555 | 0 | 6150.2988 | 6150.2988
PJ0003376 | MOVE, REPAIR, PATCH & PAINT -BLD 27 RMS 136, 136A, 138, 139 | MOLLAN, CHERYL L. | CLOSED | 2010-03-24 | CA:RELOCATE MAGAZINE RACK; REPAIR COUNTER EDGE; REMOVE L-BRACKET | 027 | CLOSED | 166.14 | 0 | 359.97 | 359.97
PJ0003376 | MOVE, REPAIR, PATCH & PAINT -BLD 27 RMS 136, 136A, 138, 139 | MOLLAN, CHERYL L. | CLOSED | 2010-03-24 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 34.35 | 0 | 0 | 0
PJ0003376 | MOVE, REPAIR, PATCH & PAINT -BLD 27 RMS 136, 136A, 138, 139 | MOLLAN, CHERYL L. | CLOSED | 2010-03-24 | MO:MOVE FILING CABINETS TO E-SURPLUS OR ADJACENT ROOM | 027 | CLOSED | 63 | 0 | 5.682 | 5.682
PJ0003376 | MOVE, REPAIR, PATCH & PAINT -BLD 27 RMS 136, 136A, 138, 139 | MOLLAN, CHERYL L. | CLOSED | 2010-03-24 | PA: PATCH AND PAINT SMALL HOLES IN WALL | 027 | CLOSED | 114.384 | 0 | 171.576 | 171.576
PJ0003376 Total | [7 empty] | 377.874 | 0 | 537.228 | 537.228
PJ0003373 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 150 & 151 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-03-19 | CA:INSTALL SPEAKERS AND CEILING MOUNT | 034 | CLOSED | 0 | 0 | 1226.952 | 1226.952
PJ0003373 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 150 & 151 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-03-19 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0003373 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 150 & 151 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-03-19 | EL: INSTALL ELECTRICAL FOR SMART ROOM EQ. | 034 | CLOSED | 0 | 0 | 4067.892 | 4067.892
PJ0003373 | INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 150 & 151 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2010-03-19 | IN: INSTALL SMART ROOM EQUIPMENT- BLD 34 RM 150 & 151 | 034 | CLOSED | 0 | 0 | 99.414 | 99.414
PJ0003373 Total | [7 empty] | 0 | 0 | 5394.258 | 5394.258
PJ0003372 | INSTALL SMART ROOM EQUIPMENT - BLD 27 RM 11 | LAMPMAN, GREG | CLOSED | 2010-03-19 | CA:INSTALL SPEAKERS AND PLYWOOD | 027 | CLOSED | 2004.6114 | 0 | 2048.922 | 2048.922
PJ0003372 | INSTALL SMART ROOM EQUIPMENT - BLD 27 RM 11 | LAMPMAN, GREG | CLOSED | 2010-03-19 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 599.53 | 0 | 0 | 0
PJ0003372 | INSTALL SMART ROOM EQUIPMENT - BLD 27 RM 11 | LAMPMAN, GREG | CLOSED | 2010-03-19 | EL:INSTALL SMART ROOM ELECTRICAL | 027 | CLOSED | 2568.3948 | 0 | 218.526 | 218.526
PJ0003372 | INSTALL SMART ROOM EQUIPMENT - BLD 27 RM 11 | LAMPMAN, GREG | CLOSED | 2010-03-19 | IN: INSTALL SMART ROOM EQUIPMENT - BLD 27 RM 11 | 027 | CLOSED | 132.552 | 0 | 165.69 | 165.69
PJ0003372 | INSTALL SMART ROOM EQUIPMENT - BLD 27 RM 11 | LAMPMAN, GREG | CLOSED | 2010-03-19 | PA:FINISH PLYWOOD | 027 | CLOSED | 1289.4732 | 0 | 542.508 | 542.508
PJ0003372 Total | [7 empty] | 6594.5614 | 0 | 2975.646 | 2975.646
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | AD: FLOOR CONNECTION | 021 | CLOSED | 3942.95 | 0 | 4173.3531 | 4173.3531
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | AD: GRAINGER PURCHASE | 021 | CLOSED | 0 | 0 | 1330.176 | 1330.176
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | AD: JOC 010.020.002 STAPLES | 021 | CLOSED | 11876.4436 | 0 | 12801.2874 | 12801.2874
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | CA:REMOVE CABINETRY AND HOMOSOTE PANELS; FUR-IN EAST DOORWAY | 021 | CLOSED | 9441.6516 | 0 | 5536.068 | 5536.068
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 1499.28 | 0 | 0 | 0
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | CU:CLEAN COB WEBS/DIRT FROM WINDOWS EAST SIDE, BLDG 21-232 (N/L) | 021 | CLOSED | 262.368 | 0 | 0 | 0
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | EL:REMOVE EXISTING FIXTURES / INSTALL NEW IN NEW DROP-DOWN CEILI | 021 | CLOSED | 5484.3733 | 0 | 4091.76 | 4091.76
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | ES:REMOVE DUCT WORK / INCREASE AIR CIRCULATION IN BLDG. 21 RM232 | 021 | CLOSED | 752.256 | 0 | 2648.8507 | 2648.8507
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | IN: RENOVATE SCARAB LAB - BLDG 21 RM 232 | 021 | CLOSED | 132.552 | 0 | 198.828 | 198.828
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | LO:INSTALL CONSTRUCTION CORE IN NORTH DOOR; REMOVE CORE | 021 | CLOSED | 1309.092 | 0 | 1127.988 | 1127.988
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | MO:REMOVE ALL TABLES AND CHAIRS TO BE E-SURPLUSED | 021 | CLOSED | 126 | 0 | 68.184 | 68.184
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | PA:PAINT ROOM IN COLORS DETERMINED BY CLIENT & VARNISH NEW DOOR | 021 | CLOSED | 4380.288 | 0 | 1229.784 | 1229.784
PJ0003371 | RENOVATE SCARAB LAB - BLDG 21 RM 232 | MOLLAN, CHERYL L. | CLOSED | 2010-03-18 | PL:DISCONNECT AND CAP-OFF SINK | 021 | CLOSED | 314.304 | 0 | 620.184 | 620.184
PJ0003371 Total | [7 empty] | 39521.5585 | 0 | 33826.4632 | 33826.4632
PJ0003369 | SR 09/10: RE-ROOF BALANCE OF BUILDING - ENG. 13 | LAMPMAN, GREG | CLOSED | 2010-03-18 | AD: JOC 09.019.012 STAPLES | 013 | CLOSED | 230680.56 | 0 | 230834.3 | 230834.3
PJ0003369 | SR 09/10: RE-ROOF BALANCE OF BUILDING - ENG. 13 | LAMPMAN, GREG | CLOSED | 2010-03-18 | AD: JOC 10.020.014 STAPLES | 013 | CLOSED | 104445.38 | 0 | 104445.38 | 104445.38
PJ0003369 | SR 09/10: RE-ROOF BALANCE OF BUILDING - ENG. 13 | LAMPMAN, GREG | CLOSED | 2010-03-18 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0003369 | SR 09/10: RE-ROOF BALANCE OF BUILDING - ENG. 13 | LAMPMAN, GREG | CLOSED | 2010-03-18 | EL: REPAIR PHOTOCELL ON ENGINEERING 13 ROOF | 013 | CLOSED | 155.74 | 0 | 149.675 | 149.675
PJ0003369 | SR 09/10: RE-ROOF BALANCE OF BUILDING - ENG. 13 | LAMPMAN, GREG | CLOSED | 2010-03-18 | IN: SR 09/10: RE-ROOF BALANCE OF BUILDING - ENG. 13 | 013 | CLOSED | 165.69 | 0 | 82.845 | 82.845
PJ0003369 Total | [7 empty] | 335447.37 | 0 | 335512.2 | 335512.2
PJ0003367 | MODIFY ROOF ACCESS LADDER & HATCH -BLD 46 OLD NATATORIUM (MAINT) | MAY, TOM | CLOSED | 2010-03-17 | CA:INSTALL ROOF LADDER AT NATATORIUM | 046 | CLOSED | 0 | 0 | 1802.16 | 1802.16
PJ0003367 | MODIFY ROOF ACCESS LADDER & HATCH -BLD 46 OLD NATATORIUM (MAINT) | MAY, TOM | CLOSED | 2010-03-17 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 0 | 0 | 0 | 0
PJ0003367 Total | [7 empty] | 0 | 0 | 1802.16 | 1802.16
PJ0003366 | MJ: IN-HOUSE SUPPORT FOR CHEVRON LIGHTING RETROFIT- 005 AND 034 | ELLIOT, DENNIS K | CLOSED | 2010-03-17 | CA:(CB TO THOMA-TRACKING ONLY) REPAIR DAMAGE TO LAMINATE DESKTOP | 005 | CLOSED | 0 | 0 | 792.696 | 792.696
PJ0003366 | MJ: IN-HOUSE SUPPORT FOR CHEVRON LIGHTING RETROFIT- 005 AND 034 | ELLIOT, DENNIS K | CLOSED | 2010-03-17 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1519.5 | 0 | 0 | 0
PJ0003366 | MJ: IN-HOUSE SUPPORT FOR CHEVRON LIGHTING RETROFIT- 005 AND 034 | ELLIOT, DENNIS K | CLOSED | 2010-03-17 | EL: CONTRACTOR SUPPORT FOR LIGHTING RETROFIT - BLDGS 05, 34 | GENERAL | CLOSED | 5075.52 | 0 | 2305.1048 | 2305.1048
PJ0003366 | MJ: IN-HOUSE SUPPORT FOR CHEVRON LIGHTING RETROFIT- 005 AND 034 | ELLIOT, DENNIS K | CLOSED | 2010-03-17 | MO: MOVE STORED MATERIALS IN 34-134 TO SW CORNER OF ROOM | GENERAL | CLOSED | 0 | 0 | 62.502 | 62.502
PJ0003366 Total | [7 empty] | 6595.02 | 0 | 3160.3028 | 3160.3028
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | AD: BKM | 070 | CLOSED | 10711.81 | 0 | 10711.81 | 10711.81
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | AD: HON | 070 | CLOSED | 1140.05 | 0 | 1134.8 | 1134.8
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | CA.INSTALL WHITE BOARDS | 070 | CLOSED | 1576.8 | 0 | 280.26 | 280.26
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 1050.87 | 0 | 0 | 0
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | CU: CLEAN BLUE CHAIRS | 070 | CLOSED | 437.28 | 0 | 407.55 | 407.55
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | EL: MOVE ELECTRICAL | 070 | CLOSED | 317.22 | 0 | 114.16 | 114.16
PJ0003365 | CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | LAMPMAN, GREG | CLOSED | 2010-03-17 | IN: CREATE CONFERENCE/TRAINING SPACE IN ANNEX - BLD 70 RM 109 | 070 | CLOSED | 55.23 | 0 | 27.615 | 27.615
PJ0003365 Total | [7 empty] | 15289.26 | 0 | 12676.195 | 12676.195
PJ0003362 | REMOVE BOOKCASE, PATCH & PAINT - KEN LIB 35 RM 101 | MAY, TOM | CLOSED | 2010-03-10 | CA:REMOVE AND DISPOSE OF SHELVING 35-101 | 035 | CLOSED | 55.38 | 0 | 27.69 | 27.69
PJ0003362 | REMOVE BOOKCASE, PATCH & PAINT - KEN LIB 35 RM 101 | MAY, TOM | CLOSED | 2010-03-10 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 32.61 | 0 | 0 | 0
PJ0003362 | REMOVE BOOKCASE, PATCH & PAINT - KEN LIB 35 RM 101 | MAY, TOM | CLOSED | 2010-03-10 | PA:PATCH AND PAINT CONCRETE WALL AT MAIN DESK LIBRARY | 035 | CLOSED | 270.768 | 0 | 488.748 | 488.748
PJ0003362 Total | [7 empty] | 358.758 | 0 | 516.438 | 516.438
PJ0003361 | MJ:CHEVRON LIGHTING RETROFIT- 002, 003, 018, 018A, 025, 040, 202 | ELLIOT, DENNIS K | CLOSED | 2010-03-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1341.35 | 0 | 0 | 0
PJ0003361 | MJ:CHEVRON LIGHTING RETROFIT- 002, 003, 018, 018A, 025, 040, 202 | ELLIOT, DENNIS K | CLOSED | 2010-03-10 | EL: SUPPORT FOR LIGHTING RETROFIT - BLDGS 2,3,18,24,25,40,202 | GENERAL | CLOSED | 25463.3575 | 0 | 20393.694 | 20393.694
PJ0003361 Total | [7 empty] | 26804.7075 | 0 | 20393.694 | 20393.694
PJ0003360 | REPLACE EXTERIOR DOOR, IT CAN'T BE REPAIRED - BLD 19 RM 105E | GRIFFIN, PATRICK E | CLOSED | 2010-03-09 | CA:REPLACE DOOR AT DINING COMPLEX | 019 | CLOSED | 1115.04 | 0 | 1013.232 | 1013.232
PJ0003360 | REPLACE EXTERIOR DOOR, IT CAN'T BE REPAIRED - BLD 19 RM 105E | GRIFFIN, PATRICK E | CLOSED | 2010-03-09 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 361.04 | 0 | 0 | 0
PJ0003360 | REPLACE EXTERIOR DOOR, IT CAN'T BE REPAIRED - BLD 19 RM 105E | GRIFFIN, PATRICK E | CLOSED | 2010-03-09 | LO:INSTALL LOCK HARDWARE ON DOOR AT DINING COMPLEX | 019 | CLOSED | 1999.008 | 0 | 1653.408 | 1653.408
PJ0003360 | REPLACE EXTERIOR DOOR, IT CAN'T BE REPAIRED - BLD 19 RM 105E | GRIFFIN, PATRICK E | CLOSED | 2010-03-09 | PA:PAINT NEW DOOR AND EXISTING JAMB AT DINING COMPLEX | 019 | CLOSED | 496.344 | 0 | 114.384 | 114.384
PJ0003360 Total | [7 empty] | 3971.432 | 0 | 2781.024 | 2781.024
PJ0003358 | M&R PARK 09/10: TREE MAINTENANCE ALL PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2010-03-09 | CP: PROJECT CONTINGENCY | GEN-PARK | CLOSED | 1361.82 | 0 | 0 | 0
PJ0003358 | M&R PARK 09/10: TREE MAINTENANCE ALL PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2010-03-09 | LA: PARKING LOT TREE MAINTENANCE | GEN-PARK | CLOSED | 4630.2096 | 0 | 7806.111 | 7806.111
PJ0003358 Total | [7 empty] | 5992.0296 | 0 | 7806.111 | 7806.111
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | AD: G&J TILE - FUNDED BY FACILITY SERVICES | 019 | CLOSED | 0 | 0 | 1276.5 | 1276.5
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | AD: JOC 09.019.014 STAPLES | 019 | CLOSED | 75150.9899 | 0 | 75150.6689 | 75150.6689
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | AD: MID-COAST FIRE PROTECTION | 019 | CLOSED | 2434.25 | 0 | 2434.25 | 2434.25
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 1868.54 | 0 | 0 | 0
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | EL: EQUIPMENT AND LIGHTING POWER CONNECTIONS RELOCATIONS | 019 | CLOSED | 14813.28 | 0 | 6727.23 | 6727.23
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | IN: RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | 019 | CLOSED | 1060.416 | 0 | 994.14 | 994.14
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | PA: CEILING PAINT | 019 | CLOSED | 2287.68 | 0 | 292.8 | 292.8
PJ0003357 | RENOVATE CHICK-FIL-A - BLDG 19 RM 100 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-03-08 | PL: PLUMBING FOR CHIC-FIL-A | 019 | CLOSED | 12429.12 | 0 | 3990.108 | 3990.108
PJ0003357 Total | [7 empty] | 110044.2759 | 0 | 90865.6969 | 90865.6969
PJ0003355 | INSTALL 3 PROJECTION SCREENS - BLD 21-105B & 05-105 | MAY, TOM | CLOSED | 2010-02-24 | CA:INSTALL 3 SCREENS IN 05, 21 | GENERAL | CLOSED | 1233.597 | 0 | 2257.56 | 2257.56
PJ0003355 | INSTALL 3 PROJECTION SCREENS - BLD 21-105B & 05-105 | MAY, TOM | CLOSED | 2010-02-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 232.29 | 0 | 0 | 0
PJ0003355 | INSTALL 3 PROJECTION SCREENS - BLD 21-105B & 05-105 | MAY, TOM | CLOSED | 2010-02-24 | EL:INSTALL POWER TO 3 SCREENS IN 05, 21 | GENERAL | CLOSED | 1022.9894 | 0 | 2175.708 | 2175.708
PJ0003355 | INSTALL 3 PROJECTION SCREENS - BLD 21-105B & 05-105 | MAY, TOM | CLOSED | 2010-02-24 | IN: INSTALL 3 PROJECTION SCREENS - BLD 21-105B & 05-105 | GENERAL | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003355 Total | [7 empty] | 2555.1524 | 0 | 4499.544 | 4499.544
PJ0003354 | M&R H/C 09/10:WIDEN TURN AREA AND PARKING FOR AMBULANCE - BLD 27 | LAMPMAN, GREG | CLOSED | 2010-02-25 | AD: GOLDEN STATE SEALING AND STRIPING | 027 | CLOSED | 374.5 | 0 | 374.5 | 374.5
PJ0003354 | M&R H/C 09/10:WIDEN TURN AREA AND PARKING FOR AMBULANCE - BLD 27 | LAMPMAN, GREG | CLOSED | 2010-02-25 | AD: TOSTE GRADING AND PAVING | 027 | CLOSED | 2461 | 0 | 2461 | 2461
PJ0003354 | M&R H/C 09/10:WIDEN TURN AREA AND PARKING FOR AMBULANCE - BLD 27 | LAMPMAN, GREG | CLOSED | 2010-02-25 | CA:MOVE ADA PARKING FOR AMBULANCE PARKING | 027 | CLOSED | 5538.12 | 0 | 3328.656 | 3328.656
PJ0003354 | M&R H/C 09/10:WIDEN TURN AREA AND PARKING FOR AMBULANCE - BLD 27 | LAMPMAN, GREG | CLOSED | 2010-02-25 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 569.92 | 0 | 0 | 0
PJ0003354 | M&R H/C 09/10:WIDEN TURN AREA AND PARKING FOR AMBULANCE - BLD 27 | LAMPMAN, GREG | CLOSED | 2010-02-25 | EO:DEMO (E) ADA PARKING AND PATCH AC. | 027 | CLOSED | 6932.016 | 0 | 3009.672 | 3009.672
PJ0003354 | M&R H/C 09/10:WIDEN TURN AREA AND PARKING FOR AMBULANCE - BLD 27 | LAMPMAN, GREG | CLOSED | 2010-02-25 | IN:M&R H/C 09/10 WIDEN TURN AREA & PARKING FOR AMBULANCE-BLD 27 | 027 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003354 Total | [7 empty] | 16008.108 | 0 | 9306.38 | 9306.38
PJ0003353 | MAINTENANCE ITEM PUNCH LIST FOR 1-19-2010 - PAC (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2010-02-23 | CA: COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 1384.5 | 1384.5
PJ0003353 | MAINTENANCE ITEM PUNCH LIST FOR 1-19-2010 - PAC (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2010-02-23 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003353 | MAINTENANCE ITEM PUNCH LIST FOR 1-19-2010 - PAC (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2010-02-23 | ES:COMPLETE MAINTENANCE ITEMS AT PAC (N/L) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003353 | MAINTENANCE ITEM PUNCH LIST FOR 1-19-2010 - PAC (NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2010-02-23 | LO:COMPLETE PAC MAINTENANCE ITEMS | 006 | CLOSED | 0 | 0 | 190.56 | 190.56
PJ0003353 Total | [7 empty] | 0 | 0 | 1575.06 | 1575.06
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | CA: SETUP OF STAGE AND CAL POLY BANNER - MOTT GYM | GENERAL | CLOSED | 3322.8 | 0 | 4805.07 | 4805.07
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 20.77 | 0 | 0 | 0
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | CU: (MAINT) CUSTODIAL SUPPORT FOR 2010 OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 3639.285 | 3639.285
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | EL: SUPPORT FOR OPEN HOUSE - APRIL 16 & 17 | GENERAL | CLOSED | 0 | 0 | 1660.692 | 1660.692
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | IN: (MAINT) 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE - PERMITS | GENERAL | CLOSED | 0 | 0 | 55.23 | 55.23
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | LA: (MAINT) LANDSCAPING SUPPORT FOR OPEN HOUSE | GENERAL | CLOSED | 0 | 0 | 5675.9333 | 5675.9333
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | LA:SETUP AND TAKE DOWN OF CHAIRS AT MOTT GYM | GENERAL | CLOSED | 1614.72 | 0 | 959.1 | 959.1
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | MO:MOVE ASI STAGING TO MOTT GYM - 4/14 | GENERAL | CLOSED | 472.5 | 0 | 335.238 | 335.238
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | PL: SUPPORT FOR 2010 OPEN HOUSE - APRIL 16 & 17 | GENERAL | CLOSED | 0 | 0 | 2363.52 | 2363.52
PJ0003350 | 2010 STUDENT LIFE & LEADERSHIP OPEN HOUSE | POPHAM, DONALD J. | CLOSED | 2010-02-22 | RE: OPEN HOUSE SUPPORT - APRIL 16 &17 (N/L) | GENERAL | CLOSED | 0 | 0 | 125.7992 | 125.7992
PJ0003350 Total | [7 empty] | 5430.79 | 0 | 19619.8675 | 19619.8675
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: 3C ENGINEERING (FAC SERV) | 013 | CLOSED | 17762 | 0 | 17762 | 17762
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: ALPHA FIRE | 013 | CLOSED | 214 | 0 | 214 | 214
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: BOB'S CRANE | 013 | CLOSED | 955.5742 | 0 | 882.75 | 882.75
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: DAHL INSULATION (FAC SERV) | 013 | CLOSED | 11342 | 0 | 11342 | 11342
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: QUAGLINO ROOFING (FAC SERV) | 013 | CLOSED | 0 | 0 | 3105.14 | 3105.14
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: SIEMENS (FAC SERV) | 013 | CLOSED | 19313.5 | 0 | 17937.48 | 17937.48
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | AD: WRIGHT CONSTRUCTION (SPLIT - CPC/FAC SERV) | 013 | CLOSED | 15996.5 | 0 | 15996.5 | 15996.5
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | CP: PROJECT CONTINGENCY (CPC) | 013 | CLOSED | 17742.65 | 0 | 0 | 0
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | CP: PROJECT CONTINGENCY (FAC SERV) | 013 | CLOSED | 2719.78 | 0 | 0 | 0
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | EL: PROVIDE POWER FOR HVAC EQUIPMENT (CFS CHANGED 5/26/11) | 013 | CLOSED | 17763.3188 | 0 | 18098.19 | 18098.19
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | ES: INSTALL HVAC EQUIPMENT AND CONTROLS | 013 | CLOSED | 142844.6736 | 0 | 174715.9456 | 174715.9456
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | IN: CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | 013 | CLOSED | 265.104 | 0 | 463.932 | 463.932
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | ITS: INSTALL ETHERNET PORT | 013 | CLOSED | 449.4 | 0 | 379.85 | 379.85
PJ0003349 | CONSTRUCTION OF HVAC TEACHING LABORATORY - BLDG 13 RM 124 | ELLIOT, DENNIS K | CLOSED | 2010-02-22 | PL: PROVIDE NATURAL GAS AND WATER FOR HVAC EQUIPMENT | 013 | CLOSED | 6841.7338 | 0 | 9803.885 | 9803.885
PJ0003349 Total | [7 empty] | 254210.2344 | 0 | 270701.6727 | 270701.6727
PJ0003348 | SUPPORT FOR FFA STATE FINALS - MOTT GYM MAIN GYM -MAY 1ST, 2010 | POPHAM, DONALD J. | CLOSED | 2010-02-22 | CA: PULL OUT AND RETRACT MOTT GYM BLEACHERS FOR FFA-4/30 | 042 | CLOSED | 0 | 0 | 553.8 | 553.8
PJ0003348 | SUPPORT FOR FFA STATE FINALS - MOTT GYM MAIN GYM -MAY 1ST, 2010 | POPHAM, DONALD J. | CLOSED | 2010-02-22 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003348 | SUPPORT FOR FFA STATE FINALS - MOTT GYM MAIN GYM -MAY 1ST, 2010 | POPHAM, DONALD J. | CLOSED | 2010-02-22 | CU: SUPPORT FOR FFA STATE FINALS - 5/1 | 042 | CLOSED | 0 | 0 | 677.16 | 677.16
PJ0003348 Total | [7 empty] | 0 | 0 | 1230.96 | 1230.96
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | AD: EARTH SYSTEMS | 127V | CLOSED | 590.3725 | 0 | 590.3725 | 590.3725
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | AD: ENGLEKIRK AND SABOL | 127V | CLOSED | 535 | 0 | 535 | 535
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | AD: JOC 10.020.039 STAPLES | 127V | CLOSED | 13529.0693 | 0 | 13529.0693 | 13529.0693
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | AD: SHIPPING CHARGES - PLANS FOR SEISMIC PEER REVIEW | 127V | CLOSED | 0 | 0 | 18.41 | 18.41
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | AD: SLO COUNTY AIR POLLUTION CONTROL DISTRICT | 127V | CLOSED | 385 | 0 | 385 | 385
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | CP: PROJECT CONTINGENCY | 127V | CLOSED | 2393.31 | 0 | 0 | 0
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | EL: DRILL CAISSONS AND ASSEMBLE WIND TOWER - ESCUELA RANCH | 127V | CLOSED | 6690.624 | 0 | 6479.232 | 6479.232
PJ0003346 | CONSTRUCT FOUNDATION FOR WIND TURBINE & ASSEMBLE TOWER - ESCUELA | ELLIOT, DENNIS K | CLOSED | 2010-02-18 | IN: SUPPORT FOR WIND TOWER - ESCUELA RANCH | 127V | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003346 Total | [7 empty] | 24255.9278 | 0 | 21669.6358 | 21669.6358
PJ0003343 | PURCHASE/INSTALL LOCKERS FOR HALL BY RM 201 - KEN LIB 35 | MAY, TOM | CLOSED | 2010-02-10 | AD: SCHOOL OUTFITTERS | 035 | CLOSED | 3412.5296 | 0 | 3412.4761 | 3412.4761
PJ0003343 | PURCHASE/INSTALL LOCKERS FOR HALL BY RM 201 - KEN LIB 35 | MAY, TOM | CLOSED | 2010-02-10 | CA:INSTALL LOCKERS IN HALLWAY ON 2ND FLOOR LIBRARY | 035 | CLOSED | 1076.223 | 0 | 749.301 | 749.301
PJ0003343 | PURCHASE/INSTALL LOCKERS FOR HALL BY RM 201 - KEN LIB 35 | MAY, TOM | CLOSED | 2010-02-10 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 163.43 | 0 | 0 | 0
PJ0003343 | PURCHASE/INSTALL LOCKERS FOR HALL BY RM 201 - KEN LIB 35 | MAY, TOM | CLOSED | 2010-02-10 | IN: PURCHASE/INSTALL LOCKERS FOR HALL BY RM 201 - KEN LIB 35 | 035 | CLOSED | 33.138 | 0 | 33.138 | 33.138
PJ0003343 | PURCHASE/INSTALL LOCKERS FOR HALL BY RM 201 - KEN LIB 35 | MAY, TOM | CLOSED | 2010-02-10 | PA: PATCH AND PAINT CUBICLE BEHIND JULIAN'S - 35 LIBRARY | 035 | CLOSED | 288.768 | 0 | 386.352 | 386.352
PJ0003343 Total | [7 empty] | 4974.0886 | 0 | 4581.2671 | 4581.2671
PJ0003341 | SR 09/10: TREE MAINTENANCE PROGRAM - CAMPUS WIDE | LOOSLEY, SCOTT L. | CLOSED | 2010-02-09 | AD: GREENVALE TREE COMPANY | GENERAL | CLOSED | 35000 | 0 | 41985 | 41985
PJ0003341 | SR 09/10: TREE MAINTENANCE PROGRAM - CAMPUS WIDE | LOOSLEY, SCOTT L. | CLOSED | 2010-02-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003341 | SR 09/10: TREE MAINTENANCE PROGRAM - CAMPUS WIDE | LOOSLEY, SCOTT L. | CLOSED | 2010-02-09 | EO: 09/10 TREE MAINTENANCE PROGRAM SUPPORT | GENERAL | CLOSED | 1107.6216 | 0 | 1583.42 | 1583.42
PJ0003341 | SR 09/10: TREE MAINTENANCE PROGRAM - CAMPUS WIDE | LOOSLEY, SCOTT L. | CLOSED | 2010-02-09 | LA: 09/10 TREE MAINTENANCE PROGRAM | GENERAL | CLOSED | 13890.6288 | 0 | 563.495 | 563.495
PJ0003341 Total | [7 empty] | 49998.2504 | 0 | 44131.915 | 44131.915
PJ0003339 | ELECTRICAL OUTLETS, AC POWER, & REMOVE SHEETROCK -BLD 20 RM 150 | MAY, TOM | CLOSED | 2010-02-02 | CA:RELOCATE WHITE BOARDS AND REMOVE SHEETROCK 20-150 | 020 | CLOSED | 1270.4172 | 0 | 533.094 | 533.094
PJ0003339 | ELECTRICAL OUTLETS, AC POWER, & REMOVE SHEETROCK -BLD 20 RM 150 | MAY, TOM | CLOSED | 2010-02-02 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 579.95 | 0 | 0 | 0
PJ0003339 | ELECTRICAL OUTLETS, AC POWER, & REMOVE SHEETROCK -BLD 20 RM 150 | MAY, TOM | CLOSED | 2010-02-02 | EL:INSTALL OUTLETS ON CABLE TRAY IN ROOM 150, BLDG 20 | 020 | CLOSED | 4005.312 | 0 | 8452.626 | 8452.626
PJ0003339 | ELECTRICAL OUTLETS, AC POWER, & REMOVE SHEETROCK -BLD 20 RM 150 | MAY, TOM | CLOSED | 2010-02-02 | IN:ELECTRICAL OUTLETS, AC POWER, REMOVE SHEETROCK -BLD 20 RM 150 | 020 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003339 | ELECTRICAL OUTLETS, AC POWER, & REMOVE SHEETROCK -BLD 20 RM 150 | MAY, TOM | CLOSED | 2010-02-02 | PA: (MAINT) MAINTENANCE PAINTING IN E.E. ROOM 150 | 020 | CLOSED | 0 | 0 | 4074.93 | 4074.93
PJ0003339 | ELECTRICAL OUTLETS, AC POWER, & REMOVE SHEETROCK -BLD 20 RM 150 | MAY, TOM | CLOSED | 2010-02-02 | PA:PAINT 20-150 | 020 | CLOSED | 457.536 | 0 | 343.152 | 343.152
PJ0003339 Total | [7 empty] | 6379.4912 | 0 | 13470.078 | 13470.078
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | AD: SAN LUIS GLASS | 035 | CLOSED | 1926 | 0 | 1917.4935 | 1917.4935
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | AD: SANTA MARIAL ACOUSTIAL | 035 | CLOSED | 4601 | 0 | 4601.0107 | 4601.0107
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | CA:ASSIST WITH A/C UNIT IN 35-114B/C | 035 | CLOSED | 1316.223 | 0 | 3524.4388 | 3524.4388
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 481.12 | 0 | 0 | 0
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | EL:PROVIDE AND HOOK UP ELECT FOR NEW A/C AT 35-114B | 035 | CLOSED | 3390.8107 | 0 | 3421.752 | 3421.752
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | EO: EXCAVATE FOR CONCRETE SLAB - N. SIDE OF LIBRARY 35 | 035 | CLOSED | 370.752 | 0 | 486.612 | 486.612
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | ES:DESIGN AND INSTALL A/C UNITS IN 35-114B | 035 | CLOSED | 30413.3645 | 0 | 27014.0698 | 27014.0698
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | IN: DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | 035 | CLOSED | 265.104 | 0 | 265.104 | 265.104
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | LA: SPRINKER RENOVATION FOR CONCRETE SLAB - N. SIDE LIBRARY 35 | 035 | CLOSED | 221.472 | 0 | 161.472 | 161.472
PJ0003338 | DESIGN/INSTALL A/C SYSTEM - BLD 35 RM 114B / 114F | MAY, TOM | CLOSED | 2010-02-03 | LO:EXCHANGE DOORS IN 114B AND ADD CLOSURES | 035 | CLOSED | 2176.3238 | 0 | 3794.112 | 3794.112
PJ0003338 Total | [7 empty] | 45162.17 | 0 | 45186.0647 | 45186.0647
PJ0003337 | BUILD WALL TO ENCLOSE RM & INSTALL T-BAR CEILING-BLD 35 RM 114C | MAY, TOM | CLOSED | 2010-02-03 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 5243 | 0 | 5243 | 5243
PJ0003337 | BUILD WALL TO ENCLOSE RM & INSTALL T-BAR CEILING-BLD 35 RM 114C | MAY, TOM | CLOSED | 2010-02-03 | CA: BUILD STEEL STUD AND SHEETROCK WALL - 035 RM 114C | 035 | CLOSED | 1785.0114 | 0 | 2165.394 | 2165.394
PJ0003337 | BUILD WALL TO ENCLOSE RM & INSTALL T-BAR CEILING-BLD 35 RM 114C | MAY, TOM | CLOSED | 2010-02-03 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 442.61 | 0 | 0 | 0
PJ0003337 | BUILD WALL TO ENCLOSE RM & INSTALL T-BAR CEILING-BLD 35 RM 114C | MAY, TOM | CLOSED | 2010-02-03 | EL: INSTALL PLUG STRIPS IN ROOM 114 | 035 | CLOSED | 1255.104 | 0 | 4880.718 | 4880.718
PJ0003337 | BUILD WALL TO ENCLOSE RM & INSTALL T-BAR CEILING-BLD 35 RM 114C | MAY, TOM | CLOSED | 2010-02-03 | IN:BUILD WALL TO ENCLOSE RM/INSTALL T-BAR CEILING-BLD 35 RM 114C | 035 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003337 | BUILD WALL TO ENCLOSE RM & INSTALL T-BAR CEILING-BLD 35 RM 114C | MAY, TOM | CLOSED | 2010-02-03 | PA:TAPE AND PAINT WALL ABOVE STOREFRONT 35-114C | 035 | CLOSED | 850.884 | 0 | 1079.652 | 1079.652
PJ0003337 Total | [7 empty] | 9642.8854 | 0 | 13435.04 | 13435.04
PJ0003336 | REMOVE CLOSETS, INSTALL UPPER CABINETS- RES 108 & 109 | MAY, TOM | CLOSED | 2010-02-03 | AD: JOC 08.018.038 MAINO | RESIDENCE | CLOSED | 392061.1075 | 0 | 392061.1075 | 392061.1075
PJ0003336 | REMOVE CLOSETS, INSTALL UPPER CABINETS- RES 108 & 109 | MAY, TOM | CLOSED | 2010-02-03 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003336 | REMOVE CLOSETS, INSTALL UPPER CABINETS- RES 108 & 109 | MAY, TOM | CLOSED | 2010-02-03 | EH&S: REMOVE CLOSETS, INSTALL UPPER CABINETS- RES 108 & 109 | RESIDENCE | CLOSED | 1898.2896 | 0 | 5361.552 | 5361.552
PJ0003336 | REMOVE CLOSETS, INSTALL UPPER CABINETS- RES 108 & 109 | MAY, TOM | CLOSED | 2010-02-03 | IN: REMOVE CLOSETS, INSTALL UPPER CABINETS- RES 108 & 109 | RESIDENCE | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003336 Total | [7 empty] | 394091.9491 | 0 | 397555.2115 | 397555.2115
PJ0003335 | MULTIYEAR SVC AGREEMENT-SDP FOR PCV COGEN(SETC NOTIFICATION ONLY | ELLIOT, DENNIS K | CLOSED | 2010-02-02 | CP: PROJECT CONTINGENCY | 271 | CLOSED | 0 | 0 | 0 | 0
PJ0003335 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003333 | INSTALLATION OF LIFT - RM / LAB 4 - BLD 8A BRAE/ITRC | LAMPMAN, GREG | CLOSED | 2010-01-28 | AD: ENGLEKIRK AND SABOL - SEISMIC PEER REVIEW | 008A | CLOSED | 642 | 0 | 535 | 535
PJ0003333 | INSTALLATION OF LIFT - RM / LAB 4 - BLD 8A BRAE/ITRC | LAMPMAN, GREG | CLOSED | 2010-01-28 | AD: JOC 10.020.052 STAPLES | 008A | CLOSED | 16013.2241 | 0 | 16013.2241 | 16013.2241
PJ0003333 | INSTALLATION OF LIFT - RM / LAB 4 - BLD 8A BRAE/ITRC | LAMPMAN, GREG | CLOSED | 2010-01-28 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 1690.85 | 0 | 0 | 0
PJ0003333 | INSTALLATION OF LIFT - RM / LAB 4 - BLD 8A BRAE/ITRC | LAMPMAN, GREG | CLOSED | 2010-01-28 | IN: INSTALLATION OF LIFT - RM / LAB 4 - BLD 8A BRAE/ITRC | 008A | CLOSED | 463.932 | 0 | 259.554 | 259.554
PJ0003333 | INSTALLATION OF LIFT - RM / LAB 4 - BLD 8A BRAE/ITRC | LAMPMAN, GREG | CLOSED | 2010-01-28 | PL: REMOVE SINK TO MAKE ROOM FOR RAILING - 08A LAB 4 | 008A | CLOSED | 130.584 | 0 | 1206.864 | 1206.864
PJ0003333 Total | [7 empty] | 18940.5901 | 0 | 18014.6421 | 18014.6421
PJ0003332 | REPLACE ROOF, MOISTURE REMEDIATION - HILLCREST 81 RM 18 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-01-27 | AD: QUAGLINO ROOFING | 081 | CLOSED | 5000 | 0 | 3700 | 3700
PJ0003332 | REPLACE ROOF, MOISTURE REMEDIATION - HILLCREST 81 RM 18 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-01-27 | CA: COMPLETE MOISTURE REMEDIATION AT HILLCREST | 081 | CLOSED | 3942 | 0 | 2351.0745 | 2351.0745
PJ0003332 | REPLACE ROOF, MOISTURE REMEDIATION - HILLCREST 81 RM 18 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2010-01-27 | CP: PROJECT CONTINGENCY | 081 | CLOSED | 0 | 0 | 0 | 0
PJ0003332 Total | [7 empty] | 8942 | 0 | 6051.0745 | 6051.0745
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | AD: FURNITURE INSTALLATION TEAM | 001 | CLOSED | 2058.68 | 0 | 2058.68 | 2058.68
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | AD: J.L. FASULO DRYWALL | 001 | CLOSED | 2691.05 | 0 | 2691.05 | 2691.05
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | CA:REMOVE CABINETS IN ADM 301 | 001 | CLOSED | 5980.0074 | 0 | 8493.385 | 8493.385
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1118.69 | 0 | 0 | 0
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | EL:ELECTRICAL NEEDS TO MAKE ADM 301 INTO CONFERENCE ROOM | 001 | CLOSED | 2628.3948 | 0 | 2584.572 | 2584.572
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | IN: RENOVATE OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | 001 | CLOSED | 198.828 | 0 | 231.966 | 231.966
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | PA:PATCH AND PAINT ADM 301 | 001 | CLOSED | 2218.9464 | 0 | 1655.808 | 1655.808
PJ0003330 | CONVERT OFFICE TO CONFERENCE ROOM - BLD 01 RM 301 | MAY, TOM | CLOSED | 2010-01-25 | PL:INSTALL SINK IN SMALL CABINET IN ADM 301 | 001 | CLOSED | 3773.2392 | 0 | 3455.604 | 3455.604
PJ0003330 Total | [7 empty] | 20667.8358 | 0 | 21171.065 | 21171.065
PJ0003329 | MOVE BLACKBOARD 2 FT TO THE RIGHT -BLD 25 RM 306 | MAY, TOM | CLOSED | 2010-01-22 | CA:MOVE BLACKBOARD IN ROOM 25-306 | 025 | CLOSED | 110.76 | 0 | 27.69 | 27.69
PJ0003329 | MOVE BLACKBOARD 2 FT TO THE RIGHT -BLD 25 RM 306 | MAY, TOM | CLOSED | 2010-01-22 | CP: PROJECT CONTINGENCY | 025 | CLOSED | 33.95 | 0 | 0 | 0
PJ0003329 | MOVE BLACKBOARD 2 FT TO THE RIGHT -BLD 25 RM 306 | MAY, TOM | CLOSED | 2010-01-22 | PA:PATCH/PAINT AFTER BLACKBOARD RELOCATION IN 25-306 | 025 | CLOSED | 228.768 | 0 | 57.192 | 57.192
PJ0003329 Total | [7 empty] | 373.478 | 0 | 84.882 | 84.882
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | AD: AIR POLLUTION CONTROL DISTRICT FEES | 092T-M030 | CLOSED | 495 | 0 | 495 | 495
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | AD: WILLIAM-SCOTSMAN | 092T-M030 | CLOSED | 8254 | 0 | 8279.18 | 8279.18
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | CA:DISMANTLE AND REBUILD DECK FOR TRAILER REMOVAL 92T | 092T-M030 | CLOSED | 4889.444 | 0 | 3083.365 | 3083.365
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | CP: PROJECT CONTINGENCY | 092T-M030 | CLOSED | 0 | 0 | 0 | 0
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | EL:DISCONNECT TRAILER 92T AT POLY GROVE | 092T-M030 | CLOSED | 606.4189 | 0 | 475.83 | 475.83
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | EO:REMOVE DECKING AND GRADE AREA AT 92T TRAILER SITE | 092T-M030 | CLOSED | 1017.92 | 0 | 376 | 376
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | IN: SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | 092T-M030 | CLOSED | 55.23 | 0 | 55.23 | 55.23
PJ0003327 | SR 09/10: REMOVE TRAILERS FROM POLY GROVE/SPRING 2010 | MAY, TOM | CLOSED | 2010-01-21 | LO: REMOVE LOCKS AND INSTALL ORANGE CORES - POLY GROVE TRAILER | 092T-M030 | CLOSED | 95.28 | 0 | 238.2 | 238.2
PJ0003327 Total | [7 empty] | 15413.2929 | 0 | 13002.805 | 13002.805
PJ0003326 | KITCHEN REMODEL - CHILDREN CTR 133 RM 112 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-01-20 | AD: JOC 09.019.004 STAPLES | 133 | CLOSED | 19151.2131 | 0 | 19151.2131 | 19151.2131
PJ0003326 | KITCHEN REMODEL - CHILDREN CTR 133 RM 112 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-01-20 | CA: REMOVE CABINET DOORS | 133 | CLOSED | 1076.223 | 0 | 55.38 | 55.38
PJ0003326 | KITCHEN REMODEL - CHILDREN CTR 133 RM 112 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-01-20 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 2437.26 | 0 | 0 | 0
PJ0003326 | KITCHEN REMODEL - CHILDREN CTR 133 RM 112 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-01-20 | IN: KITCHEN REMODEL - CHILDREN CTR 133 RM 112 | 133 | CLOSED | 265.104 | 0 | 265.104 | 265.104
PJ0003326 | KITCHEN REMODEL - CHILDREN CTR 133 RM 112 | KUENTZEL, DOUGLAS A. | CLOSED | 2010-01-20 | PA: JULY 14 WED | 133 | CLOSED | 3879.9612 | 0 | 2710.86 | 2710.86
PJ0003326 Total | [7 empty] | 26809.7613 | 0 | 22182.5571 | 22182.5571
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | AD: SAN LUIS GLASS | 035 | CLOSED | 387.34 | 0 | 387.34 | 387.34
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 4747.59 | 0 | 4747.59 | 4747.59
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | CA:CUT IN NEW DOORWAY BETWEEN 114B/C | 035 | CLOSED | 568.3884 | 0 | 600.468 | 600.468
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 793.68 | 0 | 0 | 0
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | EL:REROUTE ELECTRICAL FOR NEW DOORWAY IN LIBRARY | 035 | CLOSED | 1112.9894 | 0 | 2467.05 | 2467.05
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | IN: CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | 035 | CLOSED | 198.828 | 0 | 198.828 | 198.828
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | LO: INSTALL DOOR BETWEEN 114B AND 114C AND EXCHANGE CORE | 035 | CLOSED | 776.016 | 0 | 784.848 | 784.848
PJ0003323 | CUT IN DOORWAY BETWEEN 114B AND 114C - BLD 35 | MAY, TOM | CLOSED | 2010-01-14 | PA:PATCH/PAINT FOR NEW DOORWAY IN 114B/C | 035 | CLOSED | 825.0226 | 0 | 857.88 | 857.88
PJ0003323 Total | [7 empty] | 9409.8544 | 0 | 10044.004 | 10044.004
PJ0003322 | ASSIST WITH RUSSCO FURNITURE INSTALLATION - BLD 35 RM 114F & 216 | MAY, TOM | CLOSED | 2010-01-13 | AD: RUSSCO | 035 | CLOSED | 2374.4905 | 0 | 2374.4905 | 2374.4905
PJ0003322 | ASSIST WITH RUSSCO FURNITURE INSTALLATION - BLD 35 RM 114F & 216 | MAY, TOM | CLOSED | 2010-01-13 | AD: RUSSCO - JULIAN'S (CHARGE TO CORPORATION) | 035 | CLOSED | 329.5279 | 0 | 329.5279 | 329.5279
PJ0003322 | ASSIST WITH RUSSCO FURNITURE INSTALLATION - BLD 35 RM 114F & 216 | MAY, TOM | CLOSED | 2010-01-13 | AD: RUSSCO PARTS PURCHASE | 035 | CLOSED | 72.744 | 0 | 72.744 | 72.744
PJ0003322 | ASSIST WITH RUSSCO FURNITURE INSTALLATION - BLD 35 RM 114F & 216 | MAY, TOM | CLOSED | 2010-01-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 65.63 | 0 | 0 | 0
PJ0003322 | ASSIST WITH RUSSCO FURNITURE INSTALLATION - BLD 35 RM 114F & 216 | MAY, TOM | CLOSED | 2010-01-13 | CU: CLEAN WINDOWS IN BLD 35 RM 114F & 216 | 035 | CLOSED | 32.796 | 0 | 16.398 | 16.398
PJ0003322 | ASSIST WITH RUSSCO FURNITURE INSTALLATION - BLD 35 RM 114F & 216 | MAY, TOM | CLOSED | 2010-01-13 | IN: ASSIST W/ INSTALL OF RUSSCO - BLD 35 RM 114F & 216 | 035 | CLOSED | 66.276 | 0 | 99.414 | 99.414
PJ0003322 Total | [7 empty] | 2941.4644 | 0 | 2892.5744 | 2892.5744
PJ0003320 | INSTALL SOUND PROOF PANELS - BLD 001 RM 412 | MAY, TOM | CLOSED | 2010-01-12 | CA:INSTALL SOUND PANEL IN DOORWAY IN ADM 413 | 001 | CLOSED | 350.1942 | 0 | 235.434 | 235.434
PJ0003320 | INSTALL SOUND PROOF PANELS - BLD 001 RM 412 | MAY, TOM | CLOSED | 2010-01-12 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 40.73 | 0 | 0 | 0
PJ0003320 Total | [7 empty] | 390.9242 | 0 | 235.434 | 235.434
PJ0003319 | INSTALL CARPET & WINDOW BLINDS - BLD 35 RM 104B | MAY, TOM | CLOSED | 2010-01-11 | AD: FLOOR CONNECTION | 035 | CLOSED | 1073.1886 | 0 | 1079.3946 | 1079.3946
PJ0003319 | INSTALL CARPET & WINDOW BLINDS - BLD 35 RM 104B | MAY, TOM | CLOSED | 2010-01-11 | CA:INSTALL WINDOW BLINDS IN 35-104B | 035 | CLOSED | 524.76 | 0 | 824.28 | 824.28
PJ0003319 | INSTALL CARPET & WINDOW BLINDS - BLD 35 RM 104B | MAY, TOM | CLOSED | 2010-01-11 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 159.79 | 0 | 0 | 0
PJ0003319 Total | [7 empty] | 1757.7386 | 0 | 1903.6746 | 1903.6746
PJ0003318 | SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | LAMPMAN, GREG | CLOSED | 2010-01-11 | AD: JOC 09.019. STAPLES | GENERAL | CLOSED | 224869.6378 | 0 | 236877.9803 | 236877.9803
PJ0003318 | SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | LAMPMAN, GREG | CLOSED | 2010-01-11 | AD: SISTEK GRAPHIC ARTS | GENERAL | CLOSED | 10451.1394 | 0 | 10431.3872 | 10431.3872
PJ0003318 | SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | LAMPMAN, GREG | CLOSED | 2010-01-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 9331.08 | 0 | 0 | 0
PJ0003318 | SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | LAMPMAN, GREG | CLOSED | 2010-01-11 | IN: SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | GENERAL | CLOSED | 530.208 | 0 | 563.346 | 563.346
PJ0003318 | SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | LAMPMAN, GREG | CLOSED | 2010-01-11 | LA: REPAIR LANDSCAPING/IRRIGATION AS NEEDED FOR WAYFINDING PROJ. | GENERAL | CLOSED | 766.992 | 0 | 40.368 | 40.368
PJ0003318 | SP 09/10: CONSTRUCTION OF WAYFINDING SIGNS | LAMPMAN, GREG | CLOSED | 2010-01-11 | PA: TOUCH UP EXTERIOR WALLS, AS NEEDED, FOR WAYFINDING PROJECT | GENERAL | CLOSED | 517.536 | 0 | 143.82 | 143.82
PJ0003318 Total | [7 empty] | 246466.5932 | 0 | 248056.9015 | 248056.9015
PJ0003317 | MJ: SUPPORT FIRE SPRINKLER SIGNS AT HOUSING APTS BLDG 171 & 170 | BRENNAN, MICHAEL | CLOSED | 2010-01-07 | AD: SYSTEK GRAPHIC ARTS | 171 | CLOSED | 12498.3383 | 0 | 12498.3383 | 12498.3383
PJ0003317 | MJ: SUPPORT FIRE SPRINKLER SIGNS AT HOUSING APTS BLDG 171 & 170 | BRENNAN, MICHAEL | CLOSED | 2010-01-07 | CA:INSTALL SIGNAGE AT PCV AND CERRO VISTA | 171 | CLOSED | 14712.0404 | 0 | 4734.6 | 4734.6
PJ0003317 | MJ: SUPPORT FIRE SPRINKLER SIGNS AT HOUSING APTS BLDG 171 & 170 | BRENNAN, MICHAEL | CLOSED | 2010-01-07 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 2548.47 | 0 | 0 | 0
PJ0003317 | MJ: SUPPORT FIRE SPRINKLER SIGNS AT HOUSING APTS BLDG 171 & 170 | BRENNAN, MICHAEL | CLOSED | 2010-01-07 | IN: INSTALL FIRE SPRINKLER SIGNS AT HOUSING APTS BLDG 171 & 170 | 171 | CLOSED | 265.104 | 0 | 256.224 | 256.224
PJ0003317 Total | [7 empty] | 30023.9527 | 0 | 17489.1623 | 17489.1623
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: 2010 SPRING COMMENCMENT SUPPORT | GENERAL | CLOSED | 0 | 0 | 8043.103 | 8043.103
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: DELIVER BOARDS AND STANCHIONS FOR COMMENCEMENT 6/11 | GENERAL | CLOSED | 0 | 0 | 110.76 | 110.76
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: HANG OCOB BANNERS ON FRIDAY JUNE 11 | GENERAL | CLOSED | 0 | 0 | 300.96 | 300.96
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: INSTALL SIGNAGE FOR SPRING COMMENCEMENT AT SPANOS STAD | GENERAL | CLOSED | 0 | 0 | 473.296 | 473.296
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: PULL OUT NORTH, SOUTH, & EAST BLEACHERS ON FRI JUN 11 | 042 | CLOSED | 0 | 0 | 678.405 | 678.405
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: SET UP WEST SIDE OF TENT AT UNIV HOUSE ON FRI JUNE 11 | GENERAL | CLOSED | 0 | 0 | 101.53 | 101.53
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CA: UNBOLT BIKE RACKS FOR COMMENCEMENT & PLACE SIGNS- BLDG 35 | GENERAL | CLOSED | 0 | 0 | 249.21 | 249.21
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CU: SUPPORT FOR 2010 SPRING COMMENCEMENT-JUNE 12 | GENERAL | CLOSED | 0 | 0 | 7499.196 | 7499.196
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | CU: UNLOCK FRONT DOOR&RESTROOMS FOR COMMENCEMENT- LIB RESERVE RM | GENERAL | CLOSED | 0 | 0 | 37.62 | 37.62
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | EL: SUPPORT FOR 2010 SPRING COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 1089.696 | 1089.696
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | ES: SUPPORT FOR 2010 SPRING COMMENCEMENT (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | GR: 2010 SPRING COMMENCEMENT SUPPORT | GENERAL | CLOSED | 0 | 0 | 9685.5118 | 9685.5118
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | IN: PERMIT FOR TENT/CANOPIES AT SPANOS STADIUM (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | LA: TEMPORARILY REMOVE BIKE RACKS BY 6/10 - BLDG 35 | GENERAL | CLOSED | 0 | 0 | 499.872 | 499.872
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | MC: 2010 SPRING COMMENCMENET SUPPORT | GENERAL | CLOSED | 0 | 0 | 685.628 | 685.628
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | PA: PAINT SHOP SUPPORT FOR 2010 SPRING COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 171.576 | 171.576
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | PCV: REPAIR/WELD BROKEN BENCH AT SOUTH SIDE OF SPANOS STADIIUM | 061 | CLOSED | 0 | 0 | 404.964 | 404.964
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | PL: SUPPORT FOR 2010 SPRING COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 4133.664 | 4133.664
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: AGRIBUSINESS POST COMMENCEMENT - JUNE 12 | GENERAL | CLOSED | 0 | 0 | 190.6 | 190.6
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: BIO & GENERAL ENGINEERING COMMENCEMENT 6/12 | GENERAL | CLOSED | 0 | 0 | 69 | 69
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: COB POST COMMENCEMENT - 6/12 | GENERAL | CLOSED | 0 | 0 | 47 | 47
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: COMPUTER SCIENCE POST COMMENCEMENT - 6/12 | GENERAL | CLOSED | 0 | 0 | 71 | 71
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: ELECTRICAL ENGR POST COMMENCEMENT - JUNE 12 | GENERAL | CLOSED | 0 | 0 | 43 | 43
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: ENGLISH POST COMMENCEMENT - JUNE 12` | GENERAL | CLOSED | 0 | 0 | 37 | 37
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: FSN POST COMMENCMENT-6/11 | GENERAL | CLOSED | 0 | 0 | 60 | 60
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: HCS POST COMMENCEMENT - 6/11 | GENERAL | CLOSED | 0 | 0 | 39 | 39
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: HISTORY POST COMMENCEMENT-6/12 | GENERAL | CLOSED | 0 | 0 | 51 | 51
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: MECHANICAL ENGINEERING COMMENCEMENT 6/10-6/12 | GENERAL | CLOSED | 0 | 0 | 92 | 92
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: MECHANICAL ENGR POST COMMENECMENT-6/12 | GENERAL | CLOSED | 0 | 0 | 60 | 60
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: POLITICAL SCIENCE POST COMMENCEMENT - 6/12 | GENERAL | CLOSED | 0 | 0 | 57 | 57
PJ0003315 | SUPPORT FOR 2010 SPRING COMMENCEMENT - SAT JUNE 12TH | POPHAM, DONALD J. | CLOSED | 2010-01-04 | SUPPLY RENTAL: SOCIAL SCIENCE POST COMMENCEMENT - 6/12 | GENERAL | CLOSED | 0 | 0 | 52 | 52
PJ0003315 Total | [7 empty] | 0 | 0 | 35033.5918 | 35033.5918
PJ0003312 | DESIGN SAFETY NETTING BTW SOCCER FIELD & BBALL CRTS - SP CMPLX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-17 | AD: BUEHLER AND BUEHLER | 163 | CLOSED | 2675 | 0 | 2675 | 2675
PJ0003312 | DESIGN SAFETY NETTING BTW SOCCER FIELD & BBALL CRTS - SP CMPLX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-17 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 267.5 | 0 | 0 | 0
PJ0003312 Total | [7 empty] | 2942.5 | 0 | 2675 | 2675
PJ0003310 | INSTALL CARD READER ACCESS TO ROOM- BLDG 192 RM 130 | GRIFFIN, PATRICK E | CLOSED | 2009-12-17 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 416.91 | 0 | 0 | 0
PJ0003310 | INSTALL CARD READER ACCESS TO ROOM- BLDG 192 RM 130 | GRIFFIN, PATRICK E | CLOSED | 2009-12-17 | EL: PROVIDE CONDUIT RUNS FOR NEW CARD READER AT ENG IV | 192 | CLOSED | 1404.1974 | 0 | 888.216 | 888.216
PJ0003310 | INSTALL CARD READER ACCESS TO ROOM- BLDG 192 RM 130 | GRIFFIN, PATRICK E | CLOSED | 2009-12-17 | LO: INSTALL ELECTRONIC PANIC HARDWARE AT ENG IV 130 | 192 | CLOSED | 2764.812 | 0 | 3108.876 | 3108.876
PJ0003310 Total | [7 empty] | 4585.9194 | 0 | 3997.092 | 3997.092
PJ0003309 | MJ: PLANT AREA ALONG DRUMM FENCE - GROUNDS BLDG 171 - PCV | MAY, TOM | CLOSED | 2009-12-17 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 4071.95 | 0 | 0 | 0
PJ0003309 | MJ: PLANT AREA ALONG DRUMM FENCE - GROUNDS BLDG 171 - PCV | MAY, TOM | CLOSED | 2009-12-17 | LA:DRUMM RESERVOIR LANDSCAPE PROJECT- PCV | 171 | CLOSED | 45781.2576 | 0 | 55123.4629 | 55123.4629
PJ0003309 | MJ: PLANT AREA ALONG DRUMM FENCE - GROUNDS BLDG 171 - PCV | MAY, TOM | CLOSED | 2009-12-17 | PCV EL: ASSIST WITH PLANTINGS AT PCV | 171 | CLOSED | 761.328 | 0 | 808.002 | 808.002
PJ0003309 Total | [7 empty] | 50614.5356 | 0 | 55931.4649 | 55931.4649
PJ0003308 | SP 09/10: INSTALL HEATING SYS, LANDSCAPE SHOP - PCV | STEWART, GLENN S | CLOSED | 2009-12-11 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 534.8 | 0 | 0 | 0
PJ0003308 | SP 09/10: INSTALL HEATING SYS, LANDSCAPE SHOP - PCV | STEWART, GLENN S | CLOSED | 2009-12-11 | PCV EL: PROVIDE ELECTRICAL FOR HEATING SYSTEM | 171 | CLOSED | 1064.9894 | 0 | 570.996 | 570.996
PJ0003308 | SP 09/10: INSTALL HEATING SYS, LANDSCAPE SHOP - PCV | STEWART, GLENN S | CLOSED | 2009-12-11 | PCV ES: INSTALL HEATING SYSTEM | 171 | CLOSED | 1454.447 | 0 | 9590.0767 | 9590.0767
PJ0003308 Total | [7 empty] | 3054.2365 | 0 | 10161.0727 | 10161.0727
PJ0003307 | ADA COMPLIANCE FOR RESTROOMS - LIB 35 (MAINT) | MAY, TOM | CLOSED | 2009-12-10 | CA: ADA COMPLIANCE MODIFICATIONS FOR LIBRARY RESTROOMS | 035 | CLOSED | 0 | 0 | 3813.2794 | 3813.2794
PJ0003307 | ADA COMPLIANCE FOR RESTROOMS - LIB 35 (MAINT) | MAY, TOM | CLOSED | 2009-12-10 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0003307 | ADA COMPLIANCE FOR RESTROOMS - LIB 35 (MAINT) | MAY, TOM | CLOSED | 2009-12-10 | PA: PAINT RESTROOMS - LIBRARY 2ND THRU 5TH FLOORS - ADA PROJECT | 035 | CLOSED | 0 | 0 | 1668.1 | 1668.1
PJ0003307 | ADA COMPLIANCE FOR RESTROOMS - LIB 35 (MAINT) | MAY, TOM | CLOSED | 2009-12-10 | PL: ADA COMPLIANCE UPGRADES - LIBRARY RESTROOMS | 035 | CLOSED | 0 | 0 | 1370.01 | 1370.01
PJ0003307 Total | [7 empty] | 0 | 0 | 6851.3894 | 6851.3894
PJ0003305 | INSTALL ICE MACHINE - JANSSEN FIELD | RIVERA, MARIO L | CLOSED | 2009-11-02 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 81.06 | 0 | 0 | 0
PJ0003305 | INSTALL ICE MACHINE - JANSSEN FIELD | RIVERA, MARIO L | CLOSED | 2009-11-02 | EL:INSTALL ELECTRICAL FOR ICE MACHINE | 160A | CLOSED | 497.22 | 0 | 243.714 | 243.714
PJ0003305 | INSTALL ICE MACHINE - JANSSEN FIELD | RIVERA, MARIO L | CLOSED | 2009-11-02 | IN: INSTALL ICE MACHINE - JANSSEN FIELD | 160A | CLOSED | 66.276 | 0 | 265.104 | 265.104
PJ0003305 | INSTALL ICE MACHINE - JANSSEN FIELD | RIVERA, MARIO L | CLOSED | 2009-11-02 | PL: PROVIDE SUPPLY WATER TO ICE MACHINE | 160A | CLOSED | 247.152 | 0 | 349.668 | 349.668
PJ0003305 Total | [7 empty] | 891.708 | 0 | 858.486 | 858.486
PJ0003301 | RETROFIT WINDOWS TO MATCH 13-203 - BLD 13 RM 103 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-12-07 | AD: SAN LUIS GLASS AND WINDOW | 013 | CLOSED | 2486 | 0 | 2618.62 | 2618.62
PJ0003301 | RETROFIT WINDOWS TO MATCH 13-203 - BLD 13 RM 103 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-12-07 | CA:PROVIDE SUPPORT FOR REPLACEMENT WINDOWS AT ENG 13 | 013 | CLOSED | 184.6 | 0 | 323.05 | 323.05
PJ0003301 | RETROFIT WINDOWS TO MATCH 13-203 - BLD 13 RM 103 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-12-07 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0003301 Total | [7 empty] | 2670.6 | 0 | 2941.67 | 2941.67
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | AD: JOC 10.020.006 STAPLES | 133 | CLOSED | 83487.8521 | 0 | 82294.8556 | 82294.8556
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | AD: SLO CO APCD - NESHAP 10-DAY NOTICE FEES | 133 | CLOSED | 385 | 0 | 385 | 385
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 1050.44 | 0 | 0 | 0
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | EL: SUPPORT CHILDREN'S CTR. ROOF EXTENSION PROJECT | 133 | CLOSED | 934.44 | 0 | 384.498 | 384.498
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | IN: CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | 133 | CLOSED | 662.76 | 0 | 662.76 | 662.76
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | LO: INSTALL PADLOCK ON TRANSFORMER GATE AT CHILDREN'S CTR - 133 | 133 | CLOSED | 88.584 | 0 | 28.584 | 28.584
PJ0003299 | CHILDREN CENTER ROOF EXTENSION - BLD 133 BACK PATIO | KUENTZEL, DOUGLAS A. | CLOSED | 2009-12-03 | PA: PAINT ROOF EXTENSION AREA | 133 | CLOSED | 5463.36 | 0 | 872.43 | 872.43
PJ0003299 Total | [7 empty] | 92072.4361 | 0 | 84628.1276 | 84628.1276
PJ0003298 | FLUID MECH LAB, WATER TURBINE EXPERIMENT - ENGR 4 192 | MAY, TOM | CLOSED | 2009-12-04 | CA: INSTALL UNISTRUT AND ANCHORING FOR PIPING | 192 | CLOSED | 568.3884 | 0 | 387.66 | 387.66
PJ0003298 | FLUID MECH LAB, WATER TURBINE EXPERIMENT - ENGR 4 192 | MAY, TOM | CLOSED | 2009-12-04 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 197.89 | 0 | 0 | 0
PJ0003298 | FLUID MECH LAB, WATER TURBINE EXPERIMENT - ENGR 4 192 | MAY, TOM | CLOSED | 2009-12-04 | EL: CONNECTION FOR WATER TURBINE LAB | 192 | CLOSED | 642.4159 | 0 | 3053.496 | 3053.496
PJ0003298 | FLUID MECH LAB, WATER TURBINE EXPERIMENT - ENGR 4 192 | MAY, TOM | CLOSED | 2009-12-04 | IN: FLUID MECH LAB, WATER TURBINE EXPERIMENT - ENGR 4 192 (N/L) | 192 | CLOSED | 99.414 | 0 | 0 | 0
PJ0003298 | FLUID MECH LAB, WATER TURBINE EXPERIMENT - ENGR 4 192 | MAY, TOM | CLOSED | 2009-12-04 | PL: CONNECTION FOR WATER TURBINE | 192 | CLOSED | 1114.8058 | 0 | 564.696 | 564.696
PJ0003298 Total | [7 empty] | 2622.9141 | 0 | 4005.852 | 4005.852
PJ0003297 | INSTALL EXTERIOR DOOR CONTROL - LIB 35 | MAY, TOM | CLOSED | 2009-12-03 | AD: CAME SECURITY | 035 | CLOSED | 12545.75 | 0 | 12545.75 | 12545.75
PJ0003297 | INSTALL EXTERIOR DOOR CONTROL - LIB 35 | MAY, TOM | CLOSED | 2009-12-03 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1310.49 | 0 | 0 | 0
PJ0003297 | INSTALL EXTERIOR DOOR CONTROL - LIB 35 | MAY, TOM | CLOSED | 2009-12-03 | EL:ASSIST WITH DOOR ACCESS IN LIBRARY 114 | 035 | CLOSED | 1797.641 | 0 | 939.798 | 939.798
PJ0003297 | INSTALL EXTERIOR DOOR CONTROL - LIB 35 | MAY, TOM | CLOSED | 2009-12-03 | IN: INSTALL EXTERIOR DOOR CONTROL - LIB 35 | 035 | CLOSED | 198.828 | 0 | 132.552 | 132.552
PJ0003297 | INSTALL EXTERIOR DOOR CONTROL - LIB 35 | MAY, TOM | CLOSED | 2009-12-03 | JOC 11.022.020 STAPLES | 035 | CLOSED | 15242.1072 | 0 | 15242.1072 | 15242.1072
PJ0003297 | INSTALL EXTERIOR DOOR CONTROL - LIB 35 | MAY, TOM | CLOSED | 2009-12-03 | LO: REMOVE EXTERIOR DOOR HANDLES 35-114 | 035 | CLOSED | 2605.9632 | 0 | 5397.858 | 5397.858
PJ0003297 Total | [7 empty] | 33700.7794 | 0 | 34258.0652 | 34258.0652
PJ0003295 | REPAIR DOOR AND JAMB - BLDG 65 RM 109 | MOLLAN, CHERYL L. | CLOSED | 2009-12-03 | AD: JOC 08.018.005 MAINO | 065 | CLOSED | 2908.5489 | 0 | 2908.5596 | 2908.5596
PJ0003295 | REPAIR DOOR AND JAMB - BLDG 65 RM 109 | MOLLAN, CHERYL L. | CLOSED | 2009-12-03 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 540.18 | 0 | 0 | 0
PJ0003295 | REPAIR DOOR AND JAMB - BLDG 65 RM 109 | MOLLAN, CHERYL L. | CLOSED | 2009-12-03 | LO:INSTALL CORES IN DOORS | 065 | CLOSED | 811.68 | 0 | 171.504 | 171.504
PJ0003295 | REPAIR DOOR AND JAMB - BLDG 65 RM 109 | MOLLAN, CHERYL L. | CLOSED | 2009-12-03 | PA:SPRAY VARNISH DOORS AND PAINT DOOR JAMBS | 065 | CLOSED | 1681.8103 | 0 | 720.9 | 720.9
PJ0003295 Total | [7 empty] | 5942.2192 | 0 | 3800.9636 | 3800.9636
PJ0003289 | REPLACE SQUARE CURB WITH ROUNDED - BLD 133 PLAY YARD | MOLLAN, CHERYL L. | CLOSED | 2009-11-19 | CA:SAW CUT AND REFORM CONCRETE CURB | 133 | CLOSED | 5784.7056 | 0 | 5871.942 | 5871.942
PJ0003289 | REPLACE SQUARE CURB WITH ROUNDED - BLD 133 PLAY YARD | MOLLAN, CHERYL L. | CLOSED | 2009-11-19 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 443.53 | 0 | 0 | 0
PJ0003289 | REPLACE SQUARE CURB WITH ROUNDED - BLD 133 PLAY YARD | MOLLAN, CHERYL L. | CLOSED | 2009-11-19 | IN: REPLACE SQUARE CURB WITH ROUNDED - BLD 133 PLAY YARD | 133 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003289 | REPLACE SQUARE CURB WITH ROUNDED - BLD 133 PLAY YARD | MOLLAN, CHERYL L. | CLOSED | 2009-11-19 | LA: CAP OFF SPRINKLER HEAD FOR CURB MODIFICATION - 133 PLAY YARD | 133 | CLOSED | 201.84 | 0 | 80.736 | 80.736
PJ0003289 Total | [7 empty] | 6496.3516 | 0 | 6018.954 | 6018.954
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | AD: BELFOR | 170B | CLOSED | 83341.3584 | 0 | 83341.3584 | 83341.3584
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | AD: FLOOR CONNECTION | 170B | CLOSED | 7376.7084 | 0 | 7378.0352 | 7378.0352
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | AD: JOC 08.018.034 MAINO | 170B | CLOSED | 62850.7086 | 0 | 62850.7086 | 62850.7086
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | AD: MORRO BAY CABINETS | 170B | CLOSED | 2263.05 | 0 | 2263.05 | 2263.05
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | AD: SANTA MARIA ACOUSTICAL | 170B | CLOSED | 1947.4 | 0 | 1947.4 | 1947.4
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | AD: TED MULLER PLASTERING | 170B | CLOSED | 2279.1 | 0 | 2279.1 | 2279.1
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | CP: PROJECT CONTINGENCY | 170B | CLOSED | 0 | 0 | 0 | 0
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | EL: ELECTRICAL AS NEEDED C.V.-CABRILLO 203, 204, 303, 304&MECH | 170B | CLOSED | 1808.154 | 0 | 1810.506 | 1810.506
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | ES: REPAIR EMS - WATER DAMAGE CAUSED BY FIRE SPRINKLERS | 170B | CLOSED | 192.096 | 0 | 192.096 | 192.096
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | IN: WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM | 170B | CLOSED | 347.949 | 0 | 347.949 | 347.949
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | PA: PAINT AS NEEDED C.V.-CABRILLO 203, 204, 303, 304,& MECH RM | 170B | CLOSED | 8780.028 | 0 | 8545.02 | 8545.02
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | PCV CA: REPAIR MISCELLANOUS FLOOD DAMAGE - CV BLG. B CABRILLO | 170B | CLOSED | 589.8 | 0 | 583.8 | 583.8
PJ0003288 | WATER DAMAGE - C.V. 170B-203, 204, 303, 304, & MECH RM (NO EST.) | MAY, TOM | CLOSED | 2009-11-20 | PL: PLUMBING AS NEEDED C.V.-CABRILLO 203, 204, 303, 304&MECH | 170B | CLOSED | 909.048 | 0 | 907.248 | 907.248
PJ0003288 Total | [7 empty] | 172685.4004 | 0 | 172446.2712 | 172446.2712
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | CA: SUPPORT FOR 2009 FALL COMMENCEMENT | 042 | CLOSED | 0 | 0 | 9445.685 | 9445.685
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | CU: SETUP SUPPORT FOR 2009 FALL COMMENCEMENT - 12/12 | 042 | CLOSED | 0 | 0 | 820.4308 | 820.4308
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | CU: SUPPORT FOR 2009 FALL COMMENCEMENT - MOTT GYM | 042 | CLOSED | 0 | 0 | 4727.535 | 4727.535
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | EL: SUPPORT FOR 2009 FALL COMMENCEMENT | 042 | CLOSED | 0 | 0 | 422.96 | 422.96
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | IN: BUILDING PERMIT FOR FALL COMMENCEMENT 2009 | 042 | CLOSED | 0 | 0 | 110.46 | 110.46
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | LA: SUPPORT FOR 2009 FALL COMMENCEMENT | 042 | CLOSED | 0 | 0 | 1589.385 | 1589.385
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | LS: INSTALL CONST. CORE FOR HOOP CONTROL - MOTT GYM 12/10 | 042 | CLOSED | 0 | 0 | 47.64 | 47.64
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | MC: 2009 FALL COMMENCEMENT SUPPORT | 042 | CLOSED | 0 | 0 | 550.09 | 550.09
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | PA: SUPPORT FOR 2009 FALL COMMENCEMENT -MOTT GYM DEC 12 | 042 | CLOSED | 0 | 0 | 71.49 | 71.49
PJ0003286 | PROVIDE SERVICES FOR "FALL COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-11-13 | PL: SUPPORT FOR 2009 FALL COMMENCEMENT | 042 | CLOSED | 0 | 0 | 1466.29 | 1466.29
PJ0003286 Total | [7 empty] | 0 | 0 | 19251.9658 | 19251.9658
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | AD: BELFOR | 170E | CLOSED | 56190.7504 | 0 | 56190.7504 | 56190.7504
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | AD: BELFOR INVOICE PAID FROM 204600 (MAINT) | 170E | CLOSED | 0 | 0 | -52514.72 | -52514.72
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | AD: FLOOR CONNECTION | 170E | CLOSED | 6497.9602 | 0 | 6498.3561 | 6498.3561
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | AD: JOC 08.018.037 MAINO | 170E | CLOSED | 48671.0472 | 0 | 48671.0472 | 48671.0472
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | AD: MORRO BAY CABINETS | 170E | CLOSED | 3381.2 | 0 | 3381.2 | 3381.2
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | AD: REIMBURSE 204600 FOR BELFOR INVOICE 0710-9-12270-01F | 170E | CLOSED | 0 | 0 | 52514.72 | 52514.72
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | CP: PROJECT CONTINGENCY | 170E | CLOSED | 0 | 0 | 0 | 0
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | IN: REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 | 170E | CLOSED | 613.053 | 0 | 463.932 | 463.932
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | PCV CA: REPAIR CERRO VISTA "E" APTS, AS NEEDED. WATER DAMAGE | 170E | CLOSED | 635.58 | 0 | 612.72 | 612.72
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | PCV EL: ELECTRICAL AS NEEDED-"E" APTS CERRO VISTA-WATER DAMAGE | 170E | CLOSED | 816.522 | 0 | 780.8831 | 780.8831
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | PCV PA: PAINT AFTER WATER DAMAGE IN CERRO VISTA "E" | 170E | CLOSED | 9136.422 | 0 | 9086.592 | 9086.592
PJ0003285 | REPAIR WATER DAMAGE - C.V. BISHOP E207, E208, E307 (NO EST) | MAY, TOM | CLOSED | 2009-11-13 | PCV PL:PLUMBING AS NEEDED IN "E" APTS CERRO VISTA-WATER DAMAGE | 170E | CLOSED | 36.348 | 0 | 35.592 | 35.592
PJ0003285 Total | [7 empty] | 125978.8828 | 0 | 125721.0728 | 125721.0728
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. CSU BAKERSFIELD - 1/30 AT 7PM | 042 | CLOSED | 0 | 0 | 733.59 | 733.59
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. CSU FULLERTON - 2/24 AT 7PM | 042 | CLOSED | 0 | 0 | 545.49 | 545.49
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. CSU LONG BEACH - 2/11 AT 7PM | 042 | CLOSED | 0 | 0 | 412.848 | 412.848
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. CSU NORTHRIDGE - 1/23 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. MONTANA ST. - 12/21 AT 7PM | 042 | CLOSED | 0 | 0 | 489.06 | 489.06
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. PEPPERDINE - 12/5 AT 7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. SEATTLE UNIV - 12/3 AT 7PM | 042 | CLOSED | 0 | 0 | 432.144 | 432.144
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. UC DAVIS - 1/9 AT 7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. UC IRVINE - 3/6 AT 7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. UC RIVERSIDE - 1/20 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. UCSB - 2/27 AT 7PM | 042 | CLOSED | 0 | 0 | 464.454 | 464.454
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR MEN'S BBALL V. UNIV OF PACIFIC - 1/7 AT 7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | EL: SUPPORT FOR TELEVISED MEN'S BASKETBALL GAME-2/24 | 042 | CLOSED | 0 | 0 | 554.172 | 554.172
PJ0003284 | 09/10 SUPPORT: MEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | IN: TENT PERMIT FOR 40X80 TENT BEHIND MOTT GYM. | 042 | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0003284 Total | [7 empty] | 0 | 0 | 6824.976 | 6824.976
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBAL V. NEW MEXICO ST - 11/15 @ 2PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBAL V. PEPPERDINE - 11/21 @ 2PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBAL V. SAN DIEGO - 12/5 @ 2PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL THANKSGIVING TOURNEY - 11/28&29 | 042 | CLOSED | 0 | 0 | 1410.75 | 1410.75
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. CSU FULLERTON - 1/14 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. CSU NORTHRIDGE - 2/20 AT 4PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. CSULB - 1/16 AT 4PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. SEATTLE - 12/29 AT 2PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. UC DAVIS - 2/6 AT 2PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. UC IRVINE - 1/2 AT 4PM | 042 | CLOSED | 0 | 0 | 371.376 | 371.376
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. UC RIVERSIDE - 2/13 AT 4PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WOMEN'S BBALL V. UNIV OF PACIFIC - 2/4 AT 7PM | 042 | CLOSED | 0 | 0 | 505.458 | 505.458
PJ0003283 | 09/10 SUPPORT: WOMEN'S BASKETBALL - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT WOMEN'S BBALL V. UCSB 1/28 AT 7:00 PM | 042 | CLOSED | 0 | 0 | 432.144 | 432.144
PJ0003283 Total | [7 empty] | 0 | 0 | 7008.408 | 7008.408
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WRESTLING V. ARIZONA ST. UNIV ON FEB 5 - 6:30 PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WRESTLING V. BOISE ST. UNIV ON JAN 24 - 2PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WRESTLING V. N DAKOTA ST - JAN 10 @ 2PM | 042 | CLOSED | 0 | 0 | 489.06 | 489.06
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WRESTLING V. OREGON ST. UNIV ON FEB 6 - 7:00 PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WRESTLING V. STANFORD UNIV ON JAN 22 AT 6:30PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0003282 | 09/10 SUPPORT: MEN'S WRESTLING - MOTT GYM 42 | POPHAM, DONALD J. | CLOSED | 2009-11-12 | CU: SUPPORT FOR WRESTLING V. UC DAVIS ON FEB 12 - 6:30 PM | 042 | CLOSED | 0 | 0 | 516.06 | 516.06
PJ0003282 Total | [7 empty] | 0 | 0 | 2980.17 | 2980.17
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. CSU FULLERTON APR 17 12 & 2 | 161 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. CSU FULLERTON APR 18 12PM | 161 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. CSU NORTHRIDGE-MAY 1 | 161 | CLOSED | 0 | 0 | 56.43 | 56.43
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. CSU NORTHRIDGE-MAY 2 | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. IOWA STATE - 3/13 - 2PM | 161 | CLOSED | 0 | 0 | 37.62 | 37.62
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. IOWA STATE-3/12 | 161 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. SAC STATE - 3/12 - 2PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. SAC STATE - 3/13 - 11AM | 161 | CLOSED | 0 | 0 | 56.43 | 56.43
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. UC DAVIS -MAY 8 | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. UC DAVIS -MAY 9 | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. UC RIVERSIDE APR 2 12 & 2 | 161 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. UC RIVERSIDE APR 3 12PM | 161 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | CU: SUPPORT FOR SOFTBALL V. UCLA MAR 23 1PM & 3PM | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR ALUMNI SOFTBALL GAME ON 11/7 | 161 | CLOSED | 0 | 0 | 566.97 | 566.97
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR SOFTBALL - MUSTANG CLASSIC -3/12 AND 3/13 | 161 | CLOSED | 0 | 0 | 3115.668 | 3115.668
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR SOFTBALL V. CSU FULLERTON APR 17 & 18 | 161 | CLOSED | 0 | 0 | 634.182 | 634.182
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR SOFTBALL V. CSU NORTHRIDGE-MAY 1 & 2 | 161 | CLOSED | 0 | 0 | 1296.018 | 1296.018
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR SOFTBALL V. UC DAVIS -MAY 8 & 9 | 161 | CLOSED | 0 | 0 | 1275.018 | 1275.018
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR SOFTBALL V. UC RIVERSIDE APR 2 AND 3 | 161 | CLOSED | 0 | 0 | 873.912 | 873.912
PJ0003279 | 09/10 SUPPORT: SOFTBALL - JANSSEN STADIUM 161 | POPHAM, DONALD J. | CLOSED | 2009-11-05 | LA: SUPPORT FOR SOFTBALL V. UCLA MAR 23 1PM & 3PM | 161 | CLOSED | 0 | 0 | 451.2 | 451.2
PJ0003279 Total | [7 empty] | 0 | 0 | 8773.398 | 8773.398
PJ0003278 | SUPPORT: WOMENS SOCCER PLAYOFF - 11/5 & 11/8/09 | POPHAM, DONALD J. | CLOSED | 2009-11-02 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003278 | SUPPORT: WOMENS SOCCER PLAYOFF - 11/5 & 11/8/09 | POPHAM, DONALD J. | CLOSED | 2009-11-02 | CU: SUPPORT FOR WOMEN'S SOCCER ON 11/5 & 11/8 AT 1PM | 061 | CLOSED | 0 | 0 | 1595.682 | 1595.682
PJ0003278 | SUPPORT: WOMENS SOCCER PLAYOFF - 11/5 & 11/8/09 | POPHAM, DONALD J. | CLOSED | 2009-11-02 | LA: LANDSCAPE SUPPORT FOR WOMNEN'S SOCCER ON 11/5 & 11/8 | 061 | CLOSED | 0 | 0 | 606.429 | 606.429
PJ0003278 Total | [7 empty] | 0 | 0 | 2202.111 | 2202.111
PJ0003277 | PROVIDE ELECT & INSTALL 8 TO 9 FLAT SCREEN MONITORS - PAC LOBBY | LAMPMAN, GREG | CLOSED | 2009-10-29 | CA: INSTALL 10 FLAT SCREEN T.V. | 006 | CLOSED | 6217.8918 | 0 | 1151.844 | 1151.844
PJ0003277 | PROVIDE ELECT & INSTALL 8 TO 9 FLAT SCREEN MONITORS - PAC LOBBY | LAMPMAN, GREG | CLOSED | 2009-10-29 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 4122.55 | 0 | 0 | 0
PJ0003277 | PROVIDE ELECT & INSTALL 8 TO 9 FLAT SCREEN MONITORS - PAC LOBBY | LAMPMAN, GREG | CLOSED | 2009-10-29 | EL: INSTALL ELECTRICAL TO 10 FLAT SCREEN T.V. | 006 | CLOSED | 23886.4858 | 0 | 4788.996 | 4788.996
PJ0003277 | PROVIDE ELECT & INSTALL 8 TO 9 FLAT SCREEN MONITORS - PAC LOBBY | LAMPMAN, GREG | CLOSED | 2009-10-29 | IN:PROVIDE ELECT/INSTALL 8 TO 9 FLAT SCREEN MONITORS - PAC LOBBY | 006 | CLOSED | 265.104 | 0 | 497.07 | 497.07
PJ0003277 | PROVIDE ELECT & INSTALL 8 TO 9 FLAT SCREEN MONITORS - PAC LOBBY | LAMPMAN, GREG | CLOSED | 2009-10-29 | PA: PATCH AND PAINT | 006 | CLOSED | 10855.8758 | 0 | 531.3232 | 531.3232
PJ0003277 Total | [7 empty] | 45347.9074 | 0 | 6969.2332 | 6969.2332
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | CA: INSTALL CONCRETE FOR BENCHES IN THE BREESWAY BLDG 21 BY ELEV | 021 | CLOSED | 1366.08 | 0 | 2423.8344 | 2423.8344
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 1472.02 | 0 | 0 | 0
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | EL: ELECTRICAL FOR E.W. PATIO REMODEL | 021 | CLOSED | 978.036 | 0 | 2491.1228 | 2491.1228
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | EO: REMOVE AND REPLACE SOME COMCRETE APPROACHES TO THE PLAZA ARE | 021 | CLOSED | 1088.772 | 0 | 1027.776 | 1027.776
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | LA: LANDSCAPE WORK ASSOCIATED WITH EW PATIO REVAMP | 021 | CLOSED | 1836.72 | 0 | 2035.7971 | 2035.7971
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | MO: MOVE PALLETS OF BRICK FROM E.W. PATIO TO GROUNDS SHOP | 021 | CLOSED | 157.5 | 0 | 45.456 | 45.456
PJ0003275 | MJ: LANDSCAPE PATIO & ELEVATOR AREA - ENG WEST 21 | MAY, TOM | CLOSED | 2009-10-26 | PL: DRAINAGE FOR E.W. PATIO REMODEL | 021 | CLOSED | 1490.064 | 0 | 1663.488 | 1663.488
PJ0003275 Total | [7 empty] | 8389.192 | 0 | 9687.4743 | 9687.4743
PJ0003274 | MJ: ADA PATH OF TRAVEL - EW 21- JOC ONLY (PJ3275 FOR IN-HSE)) | MAY, TOM | CLOSED | 2009-10-26 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0003274 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003272 | INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2009-10-23 | AD: COIN SECURITY SYTSTEMS | 070 | CLOSED | 10937.5935 | 0 | 11125.2287 | 11125.2287
PJ0003272 | INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2009-10-23 | AD: ITS CHARGES (MAINT) | 070 | CLOSED | 0 | 0 | 355 | 355
PJ0003272 | INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2009-10-23 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 1467.2 | 0 | 0 | 0
PJ0003272 | INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2009-10-23 | EL:PROVIDE ELECTRICAL CIRCUIT FOR NEW KEY BOX AT FAC PLANNING | 070 | CLOSED | 1195.104 | 0 | 539.274 | 539.274
PJ0003272 | INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2009-10-23 | IN: INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | 070 | CLOSED | 132.552 | 0 | 33.138 | 33.138
PJ0003272 | INSTALL KEY BOX FOR PLANNING - BLD 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2009-10-23 | LO:INSTALL KEY SYSTEMS KEY BOX AT FAC PLANNING | 070 | CLOSED | 2406.72 | 0 | 228.672 | 228.672
PJ0003272 Total | [7 empty] | 16139.1695 | 0 | 12281.3127 | 12281.3127
PJ0003271 | MJ: PROVIDE IN-HOUSE SUPPORT FOR SIMPSON STRONG TIE CONSTRUCTION | JUDD, PERRY | CLOSED | 2009-10-23 | ANTS: FIRE ALARM WORK - SIMPSON STRONG-TIE CONSTRUCTION PROJECT | 187 | CLOSED | 0 | 0 | 457.344 | 457.344
PJ0003271 | MJ: PROVIDE IN-HOUSE SUPPORT FOR SIMPSON STRONG TIE CONSTRUCTION | JUDD, PERRY | CLOSED | 2009-10-23 | CP: PROJECT CONTINGENCY | 187 | CLOSED | 20000 | 0 | 0 | 0
PJ0003271 | MJ: PROVIDE IN-HOUSE SUPPORT FOR SIMPSON STRONG TIE CONSTRUCTION | JUDD, PERRY | CLOSED | 2009-10-23 | EL: CONTRACTOR SUPPORT FOR SIMPSON STRONG-TIE CONSTRUCTION | 187 | CLOSED | 0 | 0 | 1074.144 | 1074.144
PJ0003271 | MJ: PROVIDE IN-HOUSE SUPPORT FOR SIMPSON STRONG TIE CONSTRUCTION | JUDD, PERRY | CLOSED | 2009-10-23 | LA: PREP PLANTERS FOR RIBBON-CUTTING CEREMONY - SIMPSON BLDG. | 187 | CLOSED | 0 | 0 | 121.104 | 121.104
PJ0003271 | MJ: PROVIDE IN-HOUSE SUPPORT FOR SIMPSON STRONG TIE CONSTRUCTION | JUDD, PERRY | CLOSED | 2009-10-23 | LO: REPLACE CONSTRUCTION CORES - SIMPSON STRONG-TIE BLDG. | 187 | CLOSED | 0 | 0 | 1016.016 | 1016.016
PJ0003271 | MJ: PROVIDE IN-HOUSE SUPPORT FOR SIMPSON STRONG TIE CONSTRUCTION | JUDD, PERRY | CLOSED | 2009-10-23 | PL: CONTRACTOR SUPPORT FOR SIMPSON STRONG-TIE CONSTRUCTION | 187 | CLOSED | 0 | 0 | 4420.962 | 4420.962
PJ0003271 Total | [7 empty] | 20000 | 0 | 7089.57 | 7089.57
PJ0003268 | M&R PARK 09/10: PARKING STRUCTURE MAINT - 130, 271 & 371 | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING AND STRIPING | GENERAL | CLOSED | 5291.15 | 0 | 5291.15 | 5291.15
PJ0003268 | M&R PARK 09/10: PARKING STRUCTURE MAINT - 130, 271 & 371 | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003268 Total | [7 empty] | 5291.15 | 0 | 5291.15 | 5291.15
PJ0003267 | M&R PARK 09/10: RESTRIPE H-14A & H-14B N VIA CARTA PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING AND STRIPING | P-H14 | CLOSED | 2963.9 | 0 | 2963.9 | 2963.9
PJ0003267 | M&R PARK 09/10: RESTRIPE H-14A & H-14B N VIA CARTA PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GREENVALE TREE COMPANY | P-H14 | CLOSED | 2744.55 | 0 | 2744.55 | 2744.55
PJ0003267 | M&R PARK 09/10: RESTRIPE H-14A & H-14B N VIA CARTA PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H14 | CLOSED | 274.46 | 0 | 0 | 0
PJ0003267 Total | [7 empty] | 5982.91 | 0 | 5708.45 | 5708.45
PJ0003265 | M&R PARK 09/10: RESTRIPE H-13 N VIA CARTA PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING & STRIPING | P-H13 | CLOSED | 588.5 | 0 | 588.5 | 588.5
PJ0003265 | M&R PARK 09/10: RESTRIPE H-13 N VIA CARTA PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H13 | CLOSED | 0 | 0 | 0 | 0
PJ0003265 Total | [7 empty] | 588.5 | 0 | 588.5 | 588.5
PJ0003264 | M&R PARK 09/10: RESTRIPE H-12 AERO HANGER PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING AND STRIPING | P-H12 | CLOSED | 3070.9 | 0 | 3070.9 | 3070.9
PJ0003264 | M&R PARK 09/10: RESTRIPE H-12 AERO HANGER PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H12 | CLOSED | 0 | 0 | 0 | 0
PJ0003264 Total | [7 empty] | 3070.9 | 0 | 3070.9 | 3070.9
PJ0003263 | M&R PARK 09/10: RESTRIPE H-11 AG CIRCLE PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING AND STRIPING | P-H11 | CLOSED | 3680.8 | 0 | 3573.8 | 3573.8
PJ0003263 | M&R PARK 09/10: RESTRIPE H-11 AG CIRCLE PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H11 | CLOSED | 238.61 | 0 | 0 | 0
PJ0003263 Total | [7 empty] | 3919.41 | 0 | 3573.8 | 3573.8
PJ0003262 | M&R PARK 09/10: RESTRIPE H-10 MATH & SCI PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: DIRECT PAY TO GOLDEN STATE SEALING AND STRIPING | P-H10 | CLOSED | 3226.05 | 0 | 3226.05 | 3226.05
PJ0003262 | M&R PARK 09/10: RESTRIPE H-10 MATH & SCI PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H10 | CLOSED | 0 | 0 | 0 | 0
PJ0003262 Total | [7 empty] | 3226.05 | 0 | 3226.05 | 3226.05
PJ0003261 | M&R PARK 09/10: SEAL COAT & RESTRIPE H-4B PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING AND STRIPING | P-H04 | CLOSED | 4857.8 | 0 | 4857.8 | 4857.8
PJ0003261 | M&R PARK 09/10: SEAL COAT & RESTRIPE H-4B PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H04 | CLOSED | 0 | 0 | 0 | 0
PJ0003261 Total | [7 empty] | 4857.8 | 0 | 4857.8 | 4857.8
PJ0003260 | M&R PARK 09/10: SEAL COAT & RESTRIPE H-2C PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: GOLDEN STATE SEALING AND STRIPING | P-H02 | CLOSED | 1594.3 | 0 | 1594.3 | 1594.3
PJ0003260 | M&R PARK 09/10: SEAL COAT & RESTRIPE H-2C PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H02 | CLOSED | 159.43 | 0 | 0 | 0
PJ0003260 Total | [7 empty] | 1753.73 | 0 | 1594.3 | 1594.3
PJ0003259 | M&R PARK 09/10: RESTRIPE G-1/R-2 GRAND AVE. PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: DIRECT PAY TO GOLDEN STATE SEALING AND STRIPING | P-G01 | CLOSED | 0 | 0 | 3728.95 | 3728.95
PJ0003259 | M&R PARK 09/10: RESTRIPE G-1/R-2 GRAND AVE. PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: JOC 09.019.002.00 STAPLES | P-G01 | CLOSED | 5275.1 | 0 | 4513.6559 | 4513.6559
PJ0003259 | M&R PARK 09/10: RESTRIPE G-1/R-2 GRAND AVE. PARKING LOT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-G01 | CLOSED | 3224.9 | 0 | 0 | 0
PJ0003259 Total | [7 empty] | 8500 | 0 | 8242.6059 | 8242.6059
PJ0003256 | M&R PARK 09/10: H12 VIA CARTA REMOVE FICUS & REPAIR ASPHALT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | AD: JOC 09.019.002.02 STAPLES | P-H12 | CLOSED | 18090.7896 | 0 | 18090.8003 | 18090.8003
PJ0003256 | M&R PARK 09/10: H12 VIA CARTA REMOVE FICUS & REPAIR ASPHALT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | CP: PROJECT CONTINGENCY | P-H12 | CLOSED | 2303.3 | 0 | 0 | 0
PJ0003256 | M&R PARK 09/10: H12 VIA CARTA REMOVE FICUS & REPAIR ASPHALT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | EO: REMOVAL OF TWO FICUS TREE ROOT BALL IN PARKING LOT H-12 | P-H12 | CLOSED | 1700.8248 | 0 | 631.842 | 631.842
PJ0003256 | M&R PARK 09/10: H12 VIA CARTA REMOVE FICUS & REPAIR ASPHALT | POPHAM, DONALD J. | CLOSED | 2009-10-22 | LA:REMOVAL OF 2 FICUS TREES AT PARKING LOT H-12 | P-H12 | CLOSED | 3241.1467 | 0 | 1546.656 | 1546.656
PJ0003256 Total | [7 empty] | 25336.0611 | 0 | 20269.2983 | 20269.2983
PJ0003254 | REPLACE CARPET & INSTALL ACOUSTIC WALL PANELS - 35-112B | MAY, TOM | CLOSED | 2009-10-21 | AD: FLOOR CONNECTION | 035 | CLOSED | 1584.67 | 0 | 1593.7222 | 1593.7222
PJ0003254 | REPLACE CARPET & INSTALL ACOUSTIC WALL PANELS - 35-112B | MAY, TOM | CLOSED | 2009-10-21 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 6866.19 | 0 | 6866.19 | 6866.19
PJ0003254 | REPLACE CARPET & INSTALL ACOUSTIC WALL PANELS - 35-112B | MAY, TOM | CLOSED | 2009-10-21 | CA:SIGN FOR PEACE CORPS 33-290A | 035 | CLOSED | 390.435 | 0 | 746.958 | 746.958
PJ0003254 | REPLACE CARPET & INSTALL ACOUSTIC WALL PANELS - 35-112B | MAY, TOM | CLOSED | 2009-10-21 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 8.67 | 0 | 0 | 0
PJ0003254 | REPLACE CARPET & INSTALL ACOUSTIC WALL PANELS - 35-112B | MAY, TOM | CLOSED | 2009-10-21 | PA: PAINT ONE WALL IN 35-112B | 035 | CLOSED | 228.768 | 0 | 229.176 | 229.176
PJ0003254 Total | [7 empty] | 9078.733 | 0 | 9436.0462 | 9436.0462
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | CA: ANCHOR 20X20 TENTS - PAC PLAZA 10/31 | GENERAL | CLOSED | 0 | 0 | 270.222 | 270.222
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | CU: SUPPORT FOR THE HANDS ON HEALTH EVENT - 10/30 & 10/31 | GENERAL | CLOSED | 0 | 0 | 319.77 | 319.77
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | EL: SUPPLY SPIDER BOXES AT PAC PLAZA & MOTT LAWN-10/30&31 | GENERAL | CLOSED | 0 | 0 | 475.83 | 475.83
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | LA: SUPPORT FOR HANDS N HEALTH EVENT - 10/30 & 10/31 | GENERAL | CLOSED | 0 | 0 | 486.234 | 486.234
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | SUPPLY RENTAL: HANDS ON HEALTH - PAC PLAZA - 10/30 | GENERAL | CLOSED | 0 | 0 | 136.5 | 136.5
PJ0003253 | SUPPORT: 09 HANDS ON HEALTH - PAC/PAC PLAZA/MOTT LAWN -OCT 30-31 | POPHAM, DONALD J. | CLOSED | 2009-10-21 | SUPPLY RENTAL: HANDS ON HEALTH MOTT LAWN-10/29 | GENERAL | CLOSED | 0 | 0 | 255 | 255
PJ0003253 Total | [7 empty] | 0 | 0 | 1943.556 | 1943.556
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | AD: DUCHARME PERFORMANCE SEATING | 061 | CLOSED | 298.5086 | 0 | 878.5877 | 878.5877
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | AD: JOC 09.019.027 STAPLES | 061 | CLOSED | 191528.9728 | 0 | 191528.9621 | 191528.9621
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | AD: JOC 10.020.042 STAPLES | 061 | CLOSED | 1610.778 | 0 | 1610.778 | 1610.778
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | AD: PURCHSE SEAT END-POSTS - STEVE RINELL WELDING | 061 | CLOSED | 535 | 0 | 500 | 500
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | CA: SUPPORT FOR ADA COMPLIANCE SPANOS STADIUM | 061 | CLOSED | 1407.6 | 0 | 1798.032 | 1798.032
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 9065.41 | 0 | 0 | 0
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | CU: POST-CONSTRUCTION CLEANUP FOR ADA COMPLIANCE PROJECT AT 061 | 061 | CLOSED | 2087.76 | 0 | 1832.724 | 1832.724
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | EL: SUPPORT ADA COMPLIANCE PROJECT AT SPANOS PLAZA/SUITES | 061 | CLOSED | 1568.88 | 0 | 921.894 | 921.894
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | IN: ADA COMPLIANCE FOR MEMORIAL PLAZA & SUITES- BLDG 61 | 061 | CLOSED | 795.312 | 0 | 629.622 | 629.622
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | LO: DOOR HARDWARE COORDINATION | 061 | CLOSED | 943.008 | 0 | 923.928 | 923.928
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | PA: SUPPORT FOR ADA COMPLIANCE SPANOS STADIUM | 061 | CLOSED | 4631.52 | 0 | 1629.156 | 1629.156
PJ0003252 | SP 09/10: ADA COMPLIANCE FOR SPANOS SUITES - BLDG 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-10-20 | PL: RESTROOM REMODEL | 061 | CLOSED | 14972.16 | 0 | 5870.874 | 5870.874
PJ0003252 Total | [7 empty] | 229444.9094 | 0 | 208124.5578 | 208124.5578
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | AD: (SR) ALPHA FIRE | 058 | CLOSED | 750 | 0 | 750 | 750
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | AD: (SR) BKM OFFICE FURNITURE | 058 | CLOSED | 7578.07 | 0 | 7551.27 | 7551.27
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | AD: (SR) QUAGLINO ROOFING | 058 | CLOSED | 825 | 0 | 825 | 825
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | AD: (SR) SANTA MARIA ACOUSTICAL | 058 | CLOSED | 5189 | 0 | 5189 | 5189
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | ANTS: (SR) PROGRAM ALARMS FOR NEW ENGR. SVCS SHOP/OFFICE | 058 | CLOSED | 714.5 | 0 | 83.37 | 83.37
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | CA: (MAINT - LABOR ONLY) REMODEL & FRAME NEW WALLS FOR ENGR SHOP | 058 | CLOSED | 0 | 0 | 35858.55 | 35858.55
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | CA: (SR) MATERIALS FOR ENGR. SVCS. SHOP/OFFICE (N/L) | 058 | CLOSED | 39751.93 | 0 | 14214.1882 | 14214.1882
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | CP: PROJECT CONTINGENCY (SPECIAL REPAIRS) | 058 | CLOSED | 3377.46 | 0 | 0 | 0
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | CU: (MAINT - LABOR ONLY) | 058 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | EH&S: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 | 058 | CLOSED | 0 | 0 | 676 | 676
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | EL: (MAINT - LABOR ONLY) WIRING FOR NEW ENGR. SVCS. SHOP-BLG. 58 | 058 | CLOSED | 0 | 0 | 14913.9818 | 14913.9818
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | EL: (SR) MATERIALS FOR ENGR. SVCS. SHOP/OFFICE (N/L) | 058 | CLOSED | 10000 | 0 | 5435.1103 | 5435.1103
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | EO: EXCAVATE FOR PLUMBING | 058 | CLOSED | 0 | 0 | 849.64 | 849.64
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | ES: (MAINT - LABOR ONLY) PROVIDE HVAC FOR NEW OFFICES | 058 | CLOSED | 0 | 0 | 38544.93 | 38544.93
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | ES: (SR) MATERIALS FOR ENGR. SVCS. SHOP/OFFICE (N.L) | 058 | CLOSED | 15000 | 0 | 13076.7136 | 13076.7136
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | IN: IN-HOUSE WORK FOR ENGRS SVCS SHOP/OFFICE - BLDG 58 (MAINT) | 058 | CLOSED | 0 | 0 | 769.585 | 769.585
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | ITS: (SR) INSTALL CABLING AND 3-PORT FACEPLATE | 058 | CLOSED | 0 | 0 | 7640 | 7640
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | LA: (MAINT - LABOR ONLY) TRIM PLANTS -EAST SIDE OF BLG. 85 (N/L) | 058 | CLOSED | 0 | 0 | 0 | 0
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | LO: (MAINT - LABOR ONLY) | 058 | CLOSED | 0 | 0 | 833.7 | 833.7
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | LO: (SR) MATERIALS FOR ENGR. SVCS. SHOP/OFFICE - (N/L) | 058 | CLOSED | 600 | 0 | 9333.9 | 9333.9
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | PA: (MAINT - LABOR ONLY) PAINT CEILING AND WALLS | 058 | CLOSED | 0 | 0 | 12153.84 | 12153.84
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | PA: (SR) MATERIALS FOR ENGR. SVCS. SHOP/OFFICE | 058 | CLOSED | 4200 | 0 | 3405.56 | 3405.56
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | PL: (MAINT - LABOR ONLY) PLUMBING FOR NEW ENGR SVCS SHOP-BLG. 58 | 058 | CLOSED | 0 | 0 | 16380.16 | 16380.16
PJ0003250 | SR 09/10: IN-HOUSE WORK FOR ENGR SVCS SHOP-BLDG 58 (MAINT LABOR) | LAMPMAN, GREG | CLOSED | 2009-10-14 | PL: (SR) MATERIALS FOR ENGR. SVCS. SHOP/OFFICE (N/L) | 058 | CLOSED | 8300 | 0 | 8255.75 | 8255.75
PJ0003250 Total | [7 empty] | 96285.96 | 0 | 196849.5689 | 196849.5689
PJ0003249 | 09/10 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: PURCHASE OF WOODPECKER DETERRENT (MAINT) | 061 | CLOSED | 0 | 0 | 1201.48 | 1201.48
PJ0003249 | 09/10 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: HANG PICTURES IN PRESIDENTIAL SUITE - SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 1171.235 | 1171.235
PJ0003249 | 09/10 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: INSTALL SECURITY DEVICES FOR SLIDING DOORS SPANOS SUITES | 061 | CLOSED | 0 | 0 | 539.225 | 539.225
PJ0003249 | 09/10 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: SPANOS STADIUM SUITES MAINTENANCE WORK | 061 | CLOSED | 0 | 0 | 92.3 | 92.3
PJ0003249 | 09/10 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003249 | 09/10 MAINTENANCE WORK TRACKING - SPANOS STADIUM (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | PL: CHECK ON PLUGGED SINK AT SPANOS STAD SUITE 7 | 061 | CLOSED | 0 | 0 | 79.47 | 79.47
PJ0003249 Total | [7 empty] | 0 | 0 | 3083.71 | 3083.71
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: DAKTRONICS | 061 | CLOSED | 10700 | 0 | 13248.098 | 13248.098
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: QUINN RENTALS | 061 | CLOSED | 0 | 0 | 3529.4913 | 3529.4913
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: RICK TIEXIERA WELDING | 061 | CLOSED | 1605 | 0 | 1070 | 1070
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | EL: INSTALL LIGHTS AND SUPPLY POWER TO LIGHTS ON SCOREBOARD | 061 | CLOSED | 2783.108 | 0 | 2217.228 | 2217.228
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | ES: ASSIST WITH INSTALLATION OF SCOREBOARD LIGHT BAR - SPANOS 61 | 061 | CLOSED | 582.4159 | 0 | 396.525 | 396.525
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | IN:INSTALL LIGHT BAR ON SPANOS SCOREBRD-61 STADIM (NO EST) | 061 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0003248 | INSTALL LIGHT BAR ON SPANOS SCOREBOARD - SPANOS STADIUM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | PA: PAINT SCOREBOARD LIGHT ARMS | 061 | CLOSED | 607.3426 | 0 | 373.38 | 373.38
PJ0003248 Total | [7 empty] | 16410.4185 | 0 | 20900.9983 | 20900.9983
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: COASTAL JANITORIAL (MAINT) | 051 | CLOSED | 0 | 0 | 807.5 | 807.5
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: PURCHASE OF LIGHTS FOR UNIVERSITY HOUSE (MAINT) | 051 | CLOSED | 0 | 0 | 358.88 | 358.88
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: RAYNE WATER CONDITIONING | 051 | CLOSED | 0 | 0 | 233.7 | 233.7
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: STANLEY STEEMER (MAINT) | 051 | CLOSED | 0 | 0 | 443 | 443
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | AD: WINDOW WASHING AT UNIV. HOUSE - 12/8 (LEAVE PO OPEN) (MAINT) | 051 | CLOSED | 0 | 0 | 145 | 145
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: INSTALL TENT SIDES AT UH 51 FOR NOV EVENTS BEFORE 11/6 | 051 | CLOSED | 0 | 0 | 501.15 | 501.15
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: PLEASE CHECK UH TENT TOP BEFORE LUNCHEON ON 4/23 - 12PM | 051 | CLOSED | 0 | 0 | 230.75 | 230.75
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: PULL DOWN TENT SIDES ON MONDAY MAY 17 IN MORING | 051 | CLOSED | 0 | 0 | 103.63 | 103.63
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: SETUP TENT SIDES AT UH-51 ON FRIDAY MAY 7 - CONFIRMED | 051 | CLOSED | 0 | 0 | 323.05 | 323.05
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: SETUP TENT TOP AT UNIVERISITY HOUSE BEFORE APR 15 | 051 | CLOSED | 0 | 0 | 738.4 | 738.4
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CA: TAKE DOWN CANOPY AND TENT SIDES BEFORE 12/29 | 051 | CLOSED | 0 | 0 | 1015.3 | 1015.3
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CU: CLEAN UP AFTER APRIL 30 EVENT AT UNIV HOUSE | 051 | CLOSED | 0 | 0 | 62.7 | 62.7
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CU: CLEAN UP AFTER WINE AND VIT. DINNER AT UH 51 ON 11/18 | 051 | CLOSED | 0 | 0 | 114.786 | 114.786
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CU: CUSTODIAL SUPPORT FOR CP FDN DINNER - 11/6 & 11/7 | 051 | CLOSED | 225.6365 | 0 | 211.248 | 211.248
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | CU: SUPPORT FOR CPAA BOARD OF DIRECTORS RETREAT 1/30/10 - UH 051 | 051 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | EL: REPAIR GFI AT UNIVERISTY HOUSE | 051 | CLOSED | 0 | 0 | 258.83 | 258.83
PJ0003247 | 09/10 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-10-12 | LA: PREPARATION FOR DINNER AT UNIVERSITY HOUSE ON 12/11 | 051 | CLOSED | 0 | 0 | 1000.31 | 1000.31
PJ0003247 Total | [7 empty] | 225.6365 | 0 | 6630.224 | 6630.224
PJ0003246 | TILE ETCHING FOR PLAZA - BLDG 192 | MOLLAN, CHERYL L. | CLOSED | 2009-10-07 | AD: JOC 09.019.008 STAPLES | 192 | CLOSED | 16022.6294 | 0 | 16022.6294 | 16022.6294
PJ0003246 | TILE ETCHING FOR PLAZA - BLDG 192 | MOLLAN, CHERYL L. | CLOSED | 2009-10-07 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 1653.9 | 0 | 0 | 0
PJ0003246 | TILE ETCHING FOR PLAZA - BLDG 192 | MOLLAN, CHERYL L. | CLOSED | 2009-10-07 | IN: TILE ETCHING FOR PLAZA - BLDG 192 | 192 | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0003246 Total | [7 empty] | 17809.0814 | 0 | 16122.0434 | 16122.0434
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | AD: MACDONALD COMPANY | 053 | CLOSED | 877.4 | 0 | 937.0525 | 937.0525
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | AD: SAN LUIS GLASS | 053 | CLOSED | 1285.07 | 0 | 1285.07 | 1285.07
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | CA:CUT OUT FOR NEW SERVICE WINDOW IN 53-219 AND INSTALL BLINDS | 053 | CLOSED | 1812.7014 | 0 | 1995.198 | 1995.198
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | CP: PROJECT CONTINGENCY | 053 | CLOSED | 84.58 | 0 | 0 | 0
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | CU: CLEAN AND WAX FLOOR - BLDG. 53 ROOM 219 | 053 | CLOSED | 131.184 | 0 | 131.184 | 131.184
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | EH&S: ASBESTOS SAMPLING IN 53-219 | 053 | CLOSED | 304.896 | 0 | 306.684 | 306.684
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | EL: REMOVE HALLWAY OUTLET - OUTSIDE 53-219 | 053 | CLOSED | 63.444 | 0 | 98.946 | 98.946
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | IN: INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | 053 | CLOSED | 66.276 | 0 | 132.552 | 132.552
PJ0003245 | INSTALL A CASHIER TYPE WINDOW IN HALLWAY - BLD 53-219 | MAY, TOM | CLOSED | 2009-10-02 | PA:PATCH AND PAINT FOR SERVICE WINDOW REMODEL 53-219 | 053 | CLOSED | 754.9344 | 0 | 751.308 | 751.308
PJ0003245 Total | [7 empty] | 5380.4858 | 0 | 5637.9945 | 5637.9945
PJ0003240 | RECONFIGURE PARKING SPACES IN ALLEY BEHIND SEQUOIA - 108 | GRIFFIN, PATRICK E | CLOSED | 2009-09-23 | AD: GOLDEN STATE SEALING AND STRIPING | 108 | CLOSED | 625.95 | 0 | 625.95 | 625.95
PJ0003240 | RECONFIGURE PARKING SPACES IN ALLEY BEHIND SEQUOIA - 108 | GRIFFIN, PATRICK E | CLOSED | 2009-09-23 | CA: MOVE SIGNAGE PER PLAN AT SEQUOIA | 108 | CLOSED | 883.8 | 0 | 314.19 | 314.19
PJ0003240 | RECONFIGURE PARKING SPACES IN ALLEY BEHIND SEQUOIA - 108 | GRIFFIN, PATRICK E | CLOSED | 2009-09-23 | CP: PROJECT CONTINGENCY | 108 | CLOSED | 150.98 | 0 | 0 | 0
PJ0003240 Total | [7 empty] | 1660.73 | 0 | 940.14 | 940.14
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CU: SUPPORT FOR VOLLEYBALL GAMES - SEPT 25 & 26 | 042 | CLOSED | 0 | 0 | 940.014 | 940.014
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CU: SUPPORT FOR VOLLEYBALL PISMO BEACH INVITATIONAL-9/19 | 042 | CLOSED | 0 | 0 | 2608.254 | 2608.254
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CU: SUPPORT FOR VOLLEYBALL V. CS NORTHRIDGE-11/20 AT 7PM | 042 | CLOSED | 0 | 0 | 486.162 | 486.162
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CU: SUPPORT FOR VOLLEYBALL V. CSULB & CSU FULLERTON - 10/30 & 31 | 042 | CLOSED | 0 | 0 | 959.31 | 959.31
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CU: SUPPORT FOR VOLLEYBALL V. UCSB ON 11/7 AT 7PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0003239 | 09/10 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2009-09-21 | CU:SUPPORT FOR VOLLEYBALL ON OCT 16 & 17 | 042 | CLOSED | 0 | 0 | 1077.948 | 1077.948
PJ0003239 Total | [7 empty] | 0 | 0 | 6635.988 | 6635.988
PJ0003238 | MULTIYEAR SERVICE AGREEMENT RENEWAL-SIEMENS TECH SUPPORT(NO EST) | ELLIOT, DENNIS K | CLOSED | 2009-09-16 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003238 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | AD: G&J TILE | 034 | CLOSED | 4990 | 0 | 9528.82 | 9528.82
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | CA: DEMO TILE, RELOCATE PARTITIONS AND DISPENSERS 34-136 & 139 | 034 | CLOSED | 9812.131 | 0 | 10735.998 | 10735.998
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 3701.86 | 0 | 0 | 0
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | CU: PROVIDE CONSTUCTION SUPPORT FOR RESTROOM REMODELS, BLG. 34 | 034 | CLOSED | 117.2457 | 0 | 188.1 | 188.1
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | IN: SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | 034 | CLOSED | 110.46 | 0 | 220.92 | 220.92
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | LO: CHANGE CORES TO ORANGE CONSTRUCTION CORES, 34-136&139 | 034 | CLOSED | 95.28 | 0 | 23.82 | 23.82
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | PA: PAINT RESTROOMS 34-136 & 139 | 034 | CLOSED | 2969.7412 | 0 | 3123.88 | 3123.88
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | PL: (MAINT) ADDITIONAL PLUMBING WORK FOR ADA RESTROOM UPGRADES | 034 | CLOSED | 0 | 0 | 17621.765 | 17621.765
PJ0003237 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 34 | MOLLAN, CHERYL L. | CLOSED | 2009-09-15 | PL: REMOVE & REPLACE FIXTURES, RECONFIGURE PLUMBING. 34-136&139 | 034 | CLOSED | 6824.8836 | 0 | 4799.99 | 4799.99
PJ0003237 Total | [7 empty] | 28621.6015 | 0 | 46243.293 | 46243.293
PJ0003236 | EVALUATE KEY BOX LOCATION, ESTIMATE ONLY - GENERAL (MAINT) | GRIFFIN, PATRICK E. | CLOSED | 2009-09-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003236 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003235 | 2009 WOW WEEK SUPPORT 9/14 - 9/19 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-09-11 | CA: INSTALL BANNER AT MOTT GYM - 9/11 | GENERAL | CLOSED | 221.52 | 0 | 129.024 | 129.024
PJ0003235 | 2009 WOW WEEK SUPPORT 9/14 - 9/19 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-09-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003235 | 2009 WOW WEEK SUPPORT 9/14 - 9/19 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-09-11 | CU: CUSTODIAL SUPPORT FOR WOW BLOCK PARTY - 9/19 | GENERAL | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003235 | 2009 WOW WEEK SUPPORT 9/14 - 9/19 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-09-11 | EL: DELIVER GENERATOR TO LOWER SPORTS COMPLEX FIELDS-9/16 | GENERAL | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0003235 | 2009 WOW WEEK SUPPORT 9/14 - 9/19 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-09-11 | EL: PROVIDE SPIDER BOXES FOR WOW WEEK - 9/14-9/20 | GENERAL | CLOSED | 0 | 0 | 553.7922 | 553.7922
PJ0003235 | 2009 WOW WEEK SUPPORT 9/14 - 9/19 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-09-11 | LA: WOW SUPPORT FOR BLOCK PARTY - 9/2 | GENERAL | CLOSED | 0 | 0 | 40.368 | 40.368
PJ0003235 Total | [7 empty] | 221.52 | 0 | 948.4602 | 948.4602
PJ0003233 | INSTALL NEW INTERIOR SIGNAGE - PAC 06 | MAY, TOM | CLOSED | 2009-09-01 | AD: SISTEK GRAPHIC ARTS | 006 | CLOSED | 5726.64 | 0 | 5702.7897 | 5702.7897
PJ0003233 | INSTALL NEW INTERIOR SIGNAGE - PAC 06 | MAY, TOM | CLOSED | 2009-09-01 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003233 Total | [7 empty] | 5726.64 | 0 | 5702.7897 | 5702.7897
PJ0003232 | HANG CORK BOARD AND PATCH/PAINT ROOMS- HC 27-140/141/145/147 | GRIFFIN, PATRICK E | CLOSED | 2009-08-31 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 18.96 | 0 | 0 | 0
PJ0003232 | HANG CORK BOARD AND PATCH/PAINT ROOMS- HC 27-140/141/145/147 | GRIFFIN, PATRICK E | CLOSED | 2009-08-31 | PA: COMPLETE SPOT PAINTING AT HEALTH CENTER 2/26 | 027 | CLOSED | 189.576 | 0 | 162.18 | 162.18
PJ0003232 Total | [7 empty] | 208.536 | 0 | 162.18 | 162.18
PJ0003231 | REFURBISH / UPGRADE ROOM - AG ERHART 10 RM 102 | MAY, TOM | CLOSED | 2009-08-31 | CA:REMOVE WINDOWS FOR MOVE IN 10-102 | 010 | CLOSED | 508.3884 | 0 | 55.38 | 55.38
PJ0003231 | REFURBISH / UPGRADE ROOM - AG ERHART 10 RM 102 | MAY, TOM | CLOSED | 2009-08-31 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 131.08 | 0 | 0 | 0
PJ0003231 | REFURBISH / UPGRADE ROOM - AG ERHART 10 RM 102 | MAY, TOM | CLOSED | 2009-08-31 | EL: OUTLETS FOR EQUIPMENT IN 10-102 | 010 | CLOSED | 676.4947 | 0 | 355.092 | 355.092
PJ0003231 | REFURBISH / UPGRADE ROOM - AG ERHART 10 RM 102 | MAY, TOM | CLOSED | 2009-08-31 | MO:SWAP TABLES IN 10-102 | 010 | CLOSED | 126 | 0 | 22.728 | 22.728
PJ0003231 Total | [7 empty] | 1441.9631 | 0 | 433.2 | 433.2
PJ0003230 | MJ: FURNISH/INSTALL ACOUSTICAL BAFFLES-EDES JOC (TRACKING, ONLY) | JUDD, PERRY | CLOSED | 2009-08-28 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 0 | 0 | 0 | 0
PJ0003230 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003229 | PERMANENT SUPPORT FOR AJAX BOILER - SIERRA MADRE 113 T3 (MAINT) | GARCIA, ANTHONY | CLOSED | 2009-08-26 | CA: INSTALL CONCRETE PAD IN FRONT OF AJAX | 113D | CLOSED | 0 | 0 | 23.075 | 23.075
PJ0003229 | PERMANENT SUPPORT FOR AJAX BOILER - SIERRA MADRE 113 T3 (MAINT) | GARCIA, ANTHONY | CLOSED | 2009-08-26 | CP: PROJECT CONTINGENCY | 113D | CLOSED | 0 | 0 | 0 | 0
PJ0003229 | PERMANENT SUPPORT FOR AJAX BOILER - SIERRA MADRE 113 T3 (MAINT) | GARCIA, ANTHONY | CLOSED | 2009-08-26 | EO: REMOVE ASPHALT IN FRONT OF AJAX | 113D | CLOSED | 0 | 0 | 308.96 | 308.96
PJ0003229 Total | [7 empty] | 0 | 0 | 332.035 | 332.035
PJ0003227 | PREP SPACE FOR SEVERAL DEPARTMENTS - BLDG 58 | LAMPMAN, GREG | CLOSED | 2009-08-24 | CA: INSTALL NEW DOOR | 058 | CLOSED | 748.3884 | 0 | 500.016 | 500.016
PJ0003227 | PREP SPACE FOR SEVERAL DEPARTMENTS - BLDG 58 | LAMPMAN, GREG | CLOSED | 2009-08-24 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 221.4 | 0 | 0 | 0
PJ0003227 | PREP SPACE FOR SEVERAL DEPARTMENTS - BLDG 58 | LAMPMAN, GREG | CLOSED | 2009-08-24 | CU: CLEAN FLOOR AND DUST WALLS | 058 | CLOSED | 584.736 | 0 | 227.9357 | 227.9357
PJ0003227 | PREP SPACE FOR SEVERAL DEPARTMENTS - BLDG 58 | LAMPMAN, GREG | CLOSED | 2009-08-24 | LO: INSTALL USED LOCK SET | 058 | CLOSED | 250.9147 | 0 | 85.752 | 85.752
PJ0003227 | PREP SPACE FOR SEVERAL DEPARTMENTS - BLDG 58 | LAMPMAN, GREG | CLOSED | 2009-08-24 | MO: REMOVE TRASH FROM ROOM 103 | 058 | CLOSED | 630 | 0 | 221.598 | 221.598
PJ0003227 Total | [7 empty] | 2435.4391 | 0 | 1035.3017 | 1035.3017
PJ0003225 | INSTALL CONDUIT, 3 LIGHT POLES,& SIGN LIGHTING - PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2009-08-21 | AD: JOC 08.018.027 MAINO | 228 | CLOSED | 66828.2731 | 0 | 66828.2731 | 66828.2731
PJ0003225 | INSTALL CONDUIT, 3 LIGHT POLES,& SIGN LIGHTING - PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2009-08-21 | AD: THOMA ELECTRIC | 228 | CLOSED | 11267.4424 | 0 | 11267.1 | 11267.1
PJ0003225 | INSTALL CONDUIT, 3 LIGHT POLES,& SIGN LIGHTING - PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2009-08-21 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 2449.62 | 0 | 0 | 0
PJ0003225 | INSTALL CONDUIT, 3 LIGHT POLES,& SIGN LIGHTING - PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2009-08-21 | EL:CONFIRM WORKING ORDER OF ELECTRICAL AT CP PIER LANDSIDE | 228 | CLOSED | 317.22 | 0 | 63.444 | 63.444
PJ0003225 | INSTALL CONDUIT, 3 LIGHT POLES,& SIGN LIGHTING - PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2009-08-21 | IN: INSTALL CONDUIT, 3 LIGHT POLES,& SIGN LIGHTING - PIER 228 | 228 | CLOSED | 331.38 | 0 | 397.656 | 397.656
PJ0003225 Total | [7 empty] | 81193.9355 | 0 | 78556.4731 | 78556.4731
PJ0003223 | INSTALL RETRACTABLE DOOR WITH WINDOW - BLD 11 RM 262 | POPHAM, DONALD J. | CLOSED | 2009-08-19 | CA: INSTALL WINDOW IN DOOR AT 11-262 | 011 | CLOSED | 276.8202 | 0 | 55.38 | 55.38
PJ0003223 | INSTALL RETRACTABLE DOOR WITH WINDOW - BLD 11 RM 262 | POPHAM, DONALD J. | CLOSED | 2009-08-19 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 34.26 | 0 | 0 | 0
PJ0003223 | INSTALL RETRACTABLE DOOR WITH WINDOW - BLD 11 RM 262 | POPHAM, DONALD J. | CLOSED | 2009-08-19 | LO: RECONNECT DOOR CLOSER AT 11-261 | 011 | CLOSED | 65.7432 | 0 | 114.336 | 114.336
PJ0003223 Total | [7 empty] | 376.8234 | 0 | 169.716 | 169.716
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | AD: AIR POLLUTION CONTROL DISTRICT FEES (NO OVERHEAD) | 026 | CLOSED | 385 | 0 | 385 | 385
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | CA:DEMO WALL BETWEEN 26- 207/207A | 026 | CLOSED | 3941.8488 | 0 | 4198.6237 | 4198.6237
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 399.19 | 0 | 0 | 0
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | EH&S:SAMPLES FOR WALL REMOVAL 26-207 | 026 | CLOSED | 194.688 | 0 | 502.896 | 502.896
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | EL:REMOVE ELECTRICAL IN WALL TO BE DEMO'D IN 26-207 | 026 | CLOSED | 3219.6028 | 0 | 2851.7599 | 2851.7599
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | ES: SHUT DOWN AIR HANDLER FOR 26-207 DEMO | 026 | CLOSED | 256.128 | 0 | 320.16 | 320.16
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | IN: REMOVE WALL BETWEEN 26-207 & 26-207A/ INSTALL SMART RM EQUIP | 026 | CLOSED | 132.552 | 0 | 115.983 | 115.983
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | LO:ORANGE CORES FOR PROJECT IN 26-207 | 026 | CLOSED | 114.336 | 0 | 142.92 | 142.92
PJ0003218 | REMOVE WALL BETWEEN 26-207&207A; INSTALL SMART ROOM EQUIP IN 207 | MAY, TOM | CLOSED | 2009-07-30 | PA:PATCH AND PAINT 26-207 | 026 | CLOSED | 525.0226 | 0 | 800.688 | 800.688
PJ0003218 Total | [7 empty] | 9168.3681 | 0 | 9318.0306 | 9318.0306
PJ0003217 | COMPLETE MAINTENANCE WALK LIST OF 7/14/09 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2009-08-06 | CA: PAC MAINTENANCE WALK-THRU, JULY 2009 | 006 | CLOSED | 1257.6 | 0 | 2034.475 | 2034.475
PJ0003217 | COMPLETE MAINTENANCE WALK LIST OF 7/14/09 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2009-08-06 | CA: REPAIR UPPER ACOUSTIC CURTAIN PULLEY AT PAC | 006 | CLOSED | 0 | 0 | 230.75 | 230.75
PJ0003217 | COMPLETE MAINTENANCE WALK LIST OF 7/14/09 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2009-08-06 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003217 | COMPLETE MAINTENANCE WALK LIST OF 7/14/09 - PAC (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2009-08-06 | LO: PAC MAINTENANCE WALK-THRU, JULY 2009 | 006 | CLOSED | 781.12 | 0 | 190.56 | 190.56
PJ0003217 Total | [7 empty] | 2038.72 | 0 | 2455.785 | 2455.785
PJ0003216 | SR 09/10: HAZMAT REMOVAL & FIRE SPRINKLER -WELDING 58-101 | LAMPMAN, GREG | CLOSED | 2009-08-06 | AD: JOC 08.018.017 MAINO | 058 | CLOSED | 82717.06 | 0 | 82717.06 | 82717.06
PJ0003216 | SR 09/10: HAZMAT REMOVAL & FIRE SPRINKLER -WELDING 58-101 | LAMPMAN, GREG | CLOSED | 2009-08-06 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 0 | 0 | 0 | 0
PJ0003216 | SR 09/10: HAZMAT REMOVAL & FIRE SPRINKLER -WELDING 58-101 | LAMPMAN, GREG | CLOSED | 2009-08-06 | IN: SR 09/10: HAZMAT REMOVAL & FIRE SPRINKLER -WELDING 58-101 | 058 | CLOSED | 110.46 | 0 | 110.46 | 110.46
PJ0003216 Total | [7 empty] | 82827.52 | 0 | 82827.52 | 82827.52
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR ALUMNI BASEBALL GAME - 2/13 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL CAMP - 8/1 | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CAL - 3/19 | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CAL - 3/20 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CAL - 3/21 AT 1PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CSU BAKERSFIELD - MAY 28 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CSU BAKERSFIELD - MAY 29 AT (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CSU BAKERSFIELD - MAY 30 AT 1PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CSU LONG BEACH - 5/1 @ 6PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. CSU LONG BEACH - 5/2 @ 1PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. FRESNO ST - 3/23 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. HOUSTON - 3/12 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. HOUSTON - 3/13 | 160 | CLOSED | 0 | 0 | 37.62 | 37.62
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. HOUSTON - 3/14 | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. LONG BEACH STATE - APRIL 30 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. LOYOLA - MAY 25 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. N. ILLINOIS - 3/9 | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. N. ILLINOIS-3/10 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. PACIFIC - MAY 21 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. PACIFIC - MAY 22 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. PACIFIC - MAY 23 AT 1PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. PEPPERDINE - MAY 18 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UC IRVINE - MAY 7 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UC IRVINE - MAY 8 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UC IRVINE - MAY 9 AT 1PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UCSB-4/10 AT 6PM | 160 | CLOSED | 0 | 0 | 16.398 | 16.398
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UCSB-4/11 AT 1PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UCSB-4/9 AT 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UNIV OF SF ON FEB 26 @ 6PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UNIV OF SF ON FEB 27 @ 1PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. UNIV OF SF ON FEB 28 @ 1PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. USC - 2/19 | 160 | CLOSED | 0 | 0 | 37.62 | 37.62
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. USC - 2/20 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | CU: SUPPORT FOR BASEBALL V. USC - 2/21 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. CALIF - MAR 19, 20, & 21 | 160 | CLOSED | 0 | 0 | 1845.168 | 1845.168
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. CSU BAKERSFIELD - MAY 28, 29, 30 | 160 | CLOSED | 0 | 0 | 1686.606 | 1686.606
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. CSU LONG BEACH - APR 30, MAY 1, & 2 | 160 | CLOSED | 0 | 0 | 1651.632 | 1651.632
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. FRESNO ST - MAR 23 | 160 | CLOSED | 0 | 0 | 448.23 | 448.23
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. HOUSTON - MAR 12, 13, & 14 | 160 | CLOSED | 0 | 0 | 1396.332 | 1396.332
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. LOYOLA - MAY 25 | 160 | CLOSED | 0 | 0 | 544.968 | 544.968
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. N. ILLINOIS - MAR 9 & 10 | 160 | CLOSED | 0 | 0 | 1341.72 | 1341.72
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. PACIFIC - MAY 21, 22, & 23 | 160 | CLOSED | 0 | 0 | 1626.054 | 1626.054
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. PEPPERDINE - MAY 18 | 160 | CLOSED | 0 | 0 | 496.296 | 496.296
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. UC IRVINE - MAY 7, 8, & 9 | 160 | CLOSED | 0 | 0 | 1107.93 | 1107.93
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT BASEBALL V. UCSB - APR 9, 10, & 11 | 160 | CLOSED | 0 | 0 | 1887.294 | 1887.294
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT FOR ALUMNI BASEBALL GAME ON 2/13 | 160 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT FOR BASEBALL CAMP 8/1 | 160 | CLOSED | 0 | 0 | 83.706 | 83.706
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT FOR BASEBALL V. UNIV OF SF - FEB26, 27, & 28. | 160 | CLOSED | 0 | 0 | 1620.72 | 1620.72
PJ0003215 | 09/10 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-08-05 | LA: SUPPORT FOR BASEBALL V. USC ON 2/19, 2/20, & 2/21 | 160 | CLOSED | 0 | 0 | 1719.579 | 1719.579
PJ0003215 Total | [7 empty] | 0 | 0 | 18987.135 | 18987.135
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: CUSTODIAL SUPPORT FOR WOMENS SOCCER PLAYOFF-11/5 | 061 | CLOSED | 0 | 0 | 1277.136 | 1277.136
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: WMNS SOCCR V. CAL BAPTIST- 8/22 SPRTS COMPLX (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: WOMEN'S SOCCER V. CSU LONG BEACH - OCT 18 @ 1PM | 061 | CLOSED | 0 | 0 | 1223.586 | 1223.586
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: WOMEN'S SOCCER V. SEATTLE UNIV - 9/4 AT 7PM | 061 | CLOSED | 0 | 0 | 897.084 | 897.084
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: WOMEN'S SOCCER V. STANFORD ON 8/28 @ 7PM | 061 | CLOSED | 0 | 0 | 916.38 | 916.38
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: WOMEN'S SOCCER V. UC DAVIS - 10/15 AT 7PM | 061 | CLOSED | 0 | 0 | 1203.84 | 1203.84
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: WOMEN'S SOCCER V. UNIV ARIZONA - 9/27 AT 11AM | 061 | CLOSED | 0 | 0 | 1104.48 | 1104.48
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU:WOMEN'S SOCCER V. CSU FULLERTON ON 10/11 AT 1PM | 061 | CLOSED | 0 | 0 | 1418.202 | 1418.202
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU:WOMEN'S SOCCER V. CSU RIVERSIDE ON 10/09 AT 1PM | 061 | CLOSED | 0 | 0 | 774.576 | 774.576
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: GROUNDS SUPPORT FOR WOMEN'S SOCCER APRIL 25 | 061 | CLOSED | 0 | 0 | 222.024 | 222.024
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: LANDSCAPE SUPPORT FOR WOMEN'S SOCCER PRACTICES | 061 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR WMN'S SOCCR V. WESTMONT- 8/15 @ 7PM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR WOMEN'S PLAYOFF SOCCER GAME - NOV 5 (WO 156531) | 061 | CLOSED | 0 | 0 | 173.655 | 173.655
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. CAL BAPTIST 8/22 SPORTS COMPLEX (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. CSU LONG BEACH - OCT 18 @ 1PM | 061 | CLOSED | 0 | 0 | 80.736 | 80.736
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. SEATTLE UNIV - 9/4 AT 7PM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. STANFORD 8/28 @ 7PM | 061 | CLOSED | 0 | 0 | 606.732 | 606.732
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. UC DAVIS - 10/15 AT 7PM | 061 | CLOSED | 0 | 0 | 121.104 | 121.104
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. UC RIVERSIDE - 10/9 @ 7PM | 061 | CLOSED | 0 | 0 | 540.543 | 540.543
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: WOMEN'S SOCCER V. UNIV ARIZONA - 9/27 AT 11AM | 061 | CLOSED | 0 | 0 | 156.192 | 156.192
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA:WOMEN'S SOCCER V. CSU FULLERTON ON 10/11 AT 1PM | 061 | CLOSED | 0 | 0 | 277.848 | 277.848
PJ0003213 | 09/10 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | PL: SERVICE RESTROOM BEFORE WOMEN'S SOCCER GAMES (MAINT) | 061 | CLOSED | 0 | 0 | 238.41 | 238.41
PJ0003213 Total | [7 empty] | 0 | 0 | 11474.736 | 11474.736
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER ON 11/11 AT 7PM | 061 | CLOSED | 0 | 0 | 2243.106 | 2243.106
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. FULLERTON - 10/14 @ 7PM | 061 | CLOSED | 0 | 0 | 1034.064 | 1034.064
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. NORTHRIDGE - 10/24 @ 11AM | 061 | CLOSED | 0 | 0 | 1748.34 | 1748.34
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. SAN JOSE STATE - 9/20 AT 1PM | 061 | CLOSED | 0 | 0 | 1128.6 | 1128.6
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. SANTA CLARA & FRESNO-4/17 | 061 | CLOSED | 0 | 0 | 526.68 | 526.68
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. UC DAVIS - 10/4 AT 1PM | 061 | CLOSED | 0 | 0 | 1089.036 | 1089.036
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. UC RIVERSIDE - 10/28 @ 7PM | 061 | CLOSED | 0 | 0 | 1354.32 | 1354.32
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. UCSB - 11/4 AT 7PM | 061 | CLOSED | 0 | 0 | 1859.76 | 1859.76
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V. UNIV NEW MEXICO-4/11 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MEN'S SOCCER V.SAC STATE ON 9/18 AT 7PM | 061 | CLOSED | 0 | 0 | 1214.424 | 1214.424
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MENS SOCCER V SAN DIEGO ST-8/26 SPORTS CMPLX | 061 | CLOSED | 0 | 0 | 1296.432 | 1296.432
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | CU: SUPPORT FOR MENS SOCCER V. UNLV - 9/1 AT 7PM | 061 | CLOSED | 0 | 0 | 1107.36 | 1107.36
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | EL: SUOOCER SUPPORT FOR UCSB SOCCER GAME - 11/4 AT 7PM | 061 | CLOSED | 0 | 0 | 434.748 | 434.748
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: LANDSCAPE SUPPORT FOR MEN'S SOCCER V. SAN DIEGO ST-8/26 | 061 | CLOSED | 0 | 0 | 554.484 | 554.484
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER GAME ON 11/11 AT 7PM | 061 | CLOSED | 0 | 0 | 1633.536 | 1633.536
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER PRACTICES | 061 | CLOSED | 0 | 0 | 645.888 | 645.888
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER PRACTICES - 09/10 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. FULLERTON - 10/14 @ 7PM | 061 | CLOSED | 0 | 0 | 144.258 | 144.258
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. SAC STATE 9/18 7PM | 061 | CLOSED | 0 | 0 | 994.41 | 994.41
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. SAN JOSE ST - 9/20 AT 1PM | 061 | CLOSED | 0 | 0 | 277.848 | 277.848
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. SANTA CLARA & FRESNO FUEGO-(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. UC DAVIS - OCT 1 AT 1PM | 061 | CLOSED | 0 | 0 | 389.436 | 389.436
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. UC RIVERSIDE - 10/28 @ 7PM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. UCSB - 11/4 AT 7PM | 061 | CLOSED | 0 | 0 | 704.076 | 704.076
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MEN'S SOCCER V. UNIV NEW MEXICO-4/11 | 061 | CLOSED | 0 | 0 | 608.49 | 608.49
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT FOR MENS SOCCER V. UNLV ON 9/1 - SPANOS STADIUM | 061 | CLOSED | 0 | 0 | 383.496 | 383.496
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | LA: SUPPORT MEN'S SOCCER V. CSU NORTHRIDGE - 10/24 AT 11AM | 061 | CLOSED | 0 | 0 | 751.596 | 751.596
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | PL: PM RESTRM AT SPANOS STADIUM FOR MEN'S SOCCER GAMES (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003212 | 09/10 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-08-04 | PL: SUPPORT FOR MEN'S SOCCER V. UCSB - 11/4 AT 7PM | 061 | CLOSED | 0 | 0 | 255.234 | 255.234
PJ0003212 Total | [7 empty] | 0 | 0 | 22379.622 | 22379.622
PJ0003211 | REFURBISH PAC MONUMENT SIGN ADJACENT TO FRONT DRIVEWAY | MAY, TOM | CLOSED | 2009-08-03 | AD: SIGNCRAFT | 006 | CLOSED | 1314.0242 | 0 | 1313.8423 | 1313.8423
PJ0003211 | REFURBISH PAC MONUMENT SIGN ADJACENT TO FRONT DRIVEWAY | MAY, TOM | CLOSED | 2009-08-03 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 174.58 | 0 | 0 | 0
PJ0003211 Total | [7 empty] | 1488.6042 | 0 | 1313.8423 | 1313.8423
PJ0003210 | 2009 SOAR SUPPORT (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-29 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003210 | 2009 SOAR SUPPORT (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-29 | CU: SWING SHIFT CUSTODIAL SUPPORT FOR 2009 SOAR 7/29 - 8/21 | GENERAL | CLOSED | 0 | 0 | 2486.263 | 2486.263
PJ0003210 | 2009 SOAR SUPPORT (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-29 | LA: LANDSCAPE SUPPORT FOR SOAR EVENT FROM 7/29 - 8/21 | GENERAL | CLOSED | 0 | 0 | 222.024 | 222.024
PJ0003210 | 2009 SOAR SUPPORT (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-29 | RECYCLE: SUPPORT FOR SOAR EVENT - 7/29-8/21 (NO LABOR) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003210 Total | [7 empty] | 0 | 0 | 2708.287 | 2708.287
PJ0003208 | SUPPORT FOR CONF. & EVENT PLANNING -DEXTER LAWN 8-5-09 | POPHAM, DONALD J. | CLOSED | 2009-07-28 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0003208 | SUPPORT FOR CONF. & EVENT PLANNING -DEXTER LAWN 8-5-09 | POPHAM, DONALD J. | CLOSED | 2009-07-28 | EL: INSTALL ONE DISTRIBUTION BOX AT DEXTER LAWN ON 8/5 | 034 | CLOSED | 0 | 0 | 253.776 | 253.776
PJ0003208 Total | [7 empty] | 0 | 0 | 253.776 | 253.776
PJ0003207 | INSTALL DRINKING FOUNTAIN - BLDG 52-E46 & D17 (MAINT) | RIVERA, MARIO L | CLOSED | 2009-07-27 | CA: REPAIR WALLS AFTER DRINKING FOUNTAIN INSTALL, 52 NEAR E46 | 052 | CLOSED | 0 | 0 | 824.09 | 824.09
PJ0003207 | INSTALL DRINKING FOUNTAIN - BLDG 52-E46 & D17 (MAINT) | RIVERA, MARIO L | CLOSED | 2009-07-27 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0003207 | INSTALL DRINKING FOUNTAIN - BLDG 52-E46 & D17 (MAINT) | RIVERA, MARIO L | CLOSED | 2009-07-27 | PA: PAINT WALLS AFTER DRINKING FOUNTAIN INSTALL - 52, NEAR E46 | 052 | CLOSED | 0 | 0 | 667.24 | 667.24
PJ0003207 | INSTALL DRINKING FOUNTAIN - BLDG 52-E46 & D17 (MAINT) | RIVERA, MARIO L | CLOSED | 2009-07-27 | PL: INSTALL NEW DRINKING FOUNTAIN OLD SCI 52, NEAR ROOM E46 | 052 | CLOSED | 0 | 0 | 2354.32 | 2354.32
PJ0003207 Total | [7 empty] | 0 | 0 | 3845.65 | 3845.65
PJ0003206 | AT&T CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2009-07-24 | CP: PROJECT CONTINGENCY | P-R01 | CLOSED | 630.9 | 0 | 0 | 0
PJ0003206 | AT&T CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2009-07-24 | EL:INSTALL POLE AND POWER FOR CELL ON WHEELS | P-R01 | CLOSED | 8878.0873 | 0 | 6079.542 | 6079.542
PJ0003206 | AT&T CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2009-07-24 | EO:REMOVE ASPHALT AND PROVIDE CONST. SUPPORT | P-R01 | CLOSED | 556.128 | 0 | 278.064 | 278.064
PJ0003206 | AT&T CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2009-07-24 | IN: CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | P-R01 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003206 | AT&T CELLULAR SITE ON WHEELS (COW) - R-1 PARKING LOT | MOLLAN, CHERYL L. | CLOSED | 2009-07-24 | LO: 3 PADLOCKS W/2359 CORE FOR ELECTRICAL PANELS - R-1 LOT | P-R01 | CLOSED | 325.752 | 0 | 55.584 | 55.584
PJ0003206 Total | [7 empty] | 10523.4193 | 0 | 6545.742 | 6545.742
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | AD: REBULIC ELEVATOR FOR 10/17 FOOTBALL GAME. | 061 | CLOSED | 0 | 0 | 1547.9 | 1547.9
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | AD: REPUBLIC ELEVATOR SUPPORT FOR 10/3 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 1547.9 | 1547.9
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: DELIVER A FRAMES & STANCHIONS FOR OCT 3 FOOTBALL GAME | 061 | CLOSED | 443.04 | 0 | 941.46 | 941.46
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: DELIVER A FRAMES AND STANCHIONS FOR NOV. 14 FOOTBALL | 061 | CLOSED | 443.04 | 0 | 996.84 | 996.84
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: DELIVER A FRAMES AND STANCHIONS FOR OCT 17 FOOTBALL | 061 | CLOSED | 443.04 | 0 | 609.18 | 609.18
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: DELIVER A-FRAMES AND STANCHIONS FOR OCT 24 FOOTBALL | 061 | CLOSED | 443.04 | 0 | 581.49 | 581.49
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: DELIVER A-FRAMES FOR FOOTBALL ON 9/12 | 061 | CLOSED | 221.52 | 0 | 803.01 | 803.01
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: SUPPORT FOR 10/3 HOME FOOTBALL GAME: 5PM - 9PM | 061 | CLOSED | 0 | 0 | 266.16 | 266.16
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CA: SUPPORT FOR FOOTBALL GAME ON 9/11 | 061 | CLOSED | 332.28 | 0 | 810.7892 | 810.7892
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: 09/10 FOOTBALL V. SAC STATE - SEPT 12 2009 | 061 | CLOSED | 1311.84 | 0 | 4147.455 | 4147.455
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: 09/10 FOOTBAL V. SOUTH UTAH (HOMECOMING) OCT 17, 2009 | 061 | CLOSED | 1311.84 | 0 | 4910.562 | 4910.562
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: 09/10 FOOTBALL V. SOUTH DAKOTA STATE - OCT 3, 2009 | 061 | CLOSED | 1311.84 | 0 | 3836.0788 | 3836.0788
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: FOOTBALL V. DIXIE STATE - OCT 24 AT 6PM | 061 | CLOSED | 1311.84 | 0 | 3896.586 | 3896.586
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: FOOTBALL V. SOUTH DAKOTA - 11/14 AT 6PM | 061 | CLOSED | 1311.84 | 0 | 3836.628 | 3836.628
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: PREP WEST SIDE SPANOS STADIUM FOR GREEN GOLD GAME | 061 | CLOSED | 0 | 0 | 376.2 | 376.2
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: SUITES SUPPORT FOR SPRING RECRUITING AT SPANOS SUITES | 061 | CLOSED | 0 | 0 | 524.736 | 524.736
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: SUPPORT FOR FOOTBALL GREEN AND GOLD GAME - 4/24 | 061 | CLOSED | 0 | 0 | 1388.988 | 1388.988
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: SUPPORT FOR FOOTBALL SCRIMMAGE - 4/10 (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | CU: SUPPORT FOR FOOTBALL SCRIMMAGE ON 8/29 | 061 | CLOSED | 1311.84 | 0 | 324.108 | 324.108
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: 09/10 FOOTBALL V. SAC STATE - SEPT 12 2009 - 4PM | 061 | CLOSED | 380.664 | 0 | 362.0782 | 362.0782
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: 09/10 FOOTBAL V. SOUTH UTAH (HOMECOMING) OCT 17, 2009 | 061 | CLOSED | 380.664 | 0 | 555.1159 | 555.1159
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: 09/10 FOOTBALL V. SOUTH DAKOTA STATE - OCT 3, 2009 | 061 | CLOSED | 380.664 | 0 | 975.3367 | 975.3367
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: FOOTBALL V. DIXIE STATE - OCT 24 AT 6PM | 061 | CLOSED | 380.664 | 0 | 617.28 | 617.28
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: FOOTBALL V. SOUTH DAKOTA - 11/14 AT 6PM | 061 | CLOSED | 380.664 | 0 | 875.4533 | 875.4533
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: INSTALL ONE SPIDER BOX AT O'NEILL LAWN FOR BBQ - 10/17 | 061 | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: INSTALL ONE SPIDER BOX FOR FANFEST ON 10/24 BY 1:00PM | 115 | CLOSED | 0 | 0 | 236.04 | 236.04
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: PROVIDE ONE SPIDER BOX FOR FANFEST ON NOV. 14 BY 1:00 PM | 115 | CLOSED | 0 | 0 | 222.054 | 222.054
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: PROVIDE SPIDER BOX FOR FANFEST - 10/3 BEFORE 1PM | 115 | CLOSED | 0 | 0 | 476.064 | 476.064
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | EL: PROVIDE TWO SPIDER BOXES FOR FANFEST - 10/17 BY 1:00PM | 115 | CLOSED | 0 | 0 | 190.332 | 190.332
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | ES: 09/10 FOOTBALL V. SAC STATE - SEPT 12/2009 | 061 | CLOSED | 384.192 | 0 | 505.488 | 505.488
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | ES: 09/10 FOOTBAL V. SOUTH UTAH (HOMECOMING) OCT 17, 2009 | 061 | CLOSED | 384.192 | 0 | 0 | 0
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | ES: 09/10 FOOTBALL V. SOUTH DAKOTA STATE - OCT 3, 2009 | 061 | CLOSED | 384.192 | 0 | 403.92 | 403.92
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | ES: FOOTBALL V. DIXIE STATE - OCT 24 AT 6PM | 061 | CLOSED | 384.192 | 0 | 881.28 | 881.28
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | ES: FOOTBALL V. SOUTH DAKOTA - 11/14 AT 6PM | 061 | CLOSED | 384.192 | 0 | 440.64 | 440.64
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | GR: TEMP. LINE SPORTS COMP FIELD 1 BEFORE JUNE 21 | 162 | CLOSED | 0 | 0 | 161.472 | 161.472
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: 09/10 FOOTBALL V. SAC STATE - SEPT 12/2009 | 061 | CLOSED | 1614.72 | 0 | 8309.694 | 8309.694
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: 09/10 FOOTBAL V. SOUTH UTAH (HOMECOMING) OCT 17, 2009 | 061 | CLOSED | 1614.72 | 0 | 5203.422 | 5203.422
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: 09/10 FOOTBALL V. SOUTH DAKOTA STATE - OCT 3, 2009 | 061 | CLOSED | 1614.72 | 0 | 5709.768 | 5709.768
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: FOOTBALL V. DIXIE STATE - OCT 24 AT 6PM | 061 | CLOSED | 1614.72 | 0 | 5169.528 | 5169.528
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: FOOTBALL V. SOUTH DAKOTA - 11/14 AT 6PM | 061 | CLOSED | 1614.72 | 0 | 7758.21 | 7758.21
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: LINING AND DYING FIELDS FOR 09/10 FOOTBALL SEASON | 061 | CLOSED | 1614.72 | 0 | 3316.344 | 3316.344
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: REPAIR RUTS FROM HARVEY'S WINE TASTING VEHICLES - 10/17 | 061 | CLOSED | 0 | 0 | 40.368 | 40.368
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: SUPPORT FOOTBALL - GREEN AND GOLD FOOTBALL GAME-4/24 | 061 | CLOSED | 0 | 0 | 1130.352 | 1130.352
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | LA: SUPPORT FOR MEN'S FOOTBALL SCRIMMAGE - 8/29 | 061 | CLOSED | 1614.72 | 0 | 854.274 | 854.274
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | PL: 09/10 FOOTBALL V. SAC STATE - SEPT 12 2009 - 4PM | 061 | CLOSED | 381.456 | 0 | 373.038 | 373.038
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | PL: 09/10 FOOTBALL V. SOUTH DAKOTA STATE - OCT 3, 2009 | 061 | CLOSED | 381.456 | 0 | 291.696 | 291.696
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | PL: FOOTBAL V. SOUTH UTAH (HOMECOMING) OCT 17, 2009 | 061 | CLOSED | 381.456 | 0 | 218.772 | 218.772
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | PL: FOOTBALL V. DIXIE STATE - OCT 24 AT 6PM | 061 | CLOSED | 381.456 | 0 | 291.696 | 291.696
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | PL: FOOTBALL V. SOUTH DAKOTA - 11/14 AT 6PM | 061 | CLOSED | 381.456 | 0 | 0 | 0
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | PL: PLUMBING PRE - FOOTBALL RESTROOM PREVENTIVE MAINT | 061 | CLOSED | 529.8 | 0 | 423.84 | 423.84
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | RE: SUPPORT FOR BOOSTER TAILGATE AT O'NELL | 061 | CLOSED | 0 | 0 | 1620.372 | 1620.372
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | RE: SUPPORT FOR THE PUBLIC TAILGATE IN H-12 | 061 | CLOSED | 0 | 0 | 740.724 | 740.724
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | SUPPLY RENTAL: FOOTBALL BBQ - 9/4 | 003 | CLOSED | 0 | 0 | 50 | 50
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | SUPPLY RENTAL: HOME TEAM BBQ 4/24/10 | 061 | CLOSED | 0 | 0 | 55 | 55
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 10/17 | 061 | CLOSED | 0 | 0 | 75 | 75
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 10/24 | 061 | CLOSED | 0 | 0 | 75 | 75
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 10/3 | 061 | CLOSED | 0 | 0 | 75 | 75
PJ0003205 | 09/10 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2009-07-24 | SUPPLY RENTAL: MUSTANG CORRAL BBQ - 11/14 | 061 | CLOSED | 0 | 0 | 75 | 75
PJ0003205 Total | [7 empty] | 27761.4 | 0 | 80264.3331 | 80264.3331
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | AD: CREDIT CARD PURCHASE - AMSCO | 026 | CLOSED | 79.82 | 0 | 79.82 | 79.82
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | AD: G&J TILE | 026 | CLOSED | 4990 | 0 | 5285.48 | 5285.48
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | CA: DEMO TILE, RELOCATE PARTITIONS AND DISPENSERS 26-117 & 119 | 026 | CLOSED | 7542.9755 | 0 | 5186.8602 | 5186.8602
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | CU:PROVIDE CONSTRUCTION SUPPORT FOR RESTROOM REMODELS 26-117&119 | 026 | CLOSED | 117.2457 | 0 | 95.655 | 95.655
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | IN: SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | 026 | CLOSED | 110.46 | 0 | 331.38 | 331.38
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | LO: CHANGE CORES TO ORANGE CONSTRUCTION CORES AT 26 - 117 & 119 | 026 | CLOSED | 95.28 | 0 | 95.28 | 95.28
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | PA: PAINT RESTROOMS, 026 - 117 & 119 | 026 | CLOSED | 2969.7412 | 0 | 3101.09 | 3101.09
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | PL: (MAINT) ADDITIONAL PLUMBING WORK FOR ADA RESTROOM UPGRADES | 026 | CLOSED | 0 | 0 | 7255.2 | 7255.2
PJ0003198 | SR 09/10: RENOVATE RESTROOMS ADA COMPLIANCE - BLG. 26 | MOLLAN, CHERYL L. | CLOSED | 2009-07-20 | PL: REMOVE & REPLACE FIXTURES, RECONFIGURE PLUMBING 26 - 117&119 | 026 | CLOSED | 8924.8836 | 0 | 1243.46 | 1243.46
PJ0003198 Total | [7 empty] | 24830.406 | 0 | 22674.2252 | 22674.2252
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | CA:ASSIST IN DEMO OF TRAILER AT WAREHOUSE | 082 | CLOSED | 3478.787 | 0 | 784.55 | 784.55
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 0 | 0 | 0 | 0
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | EL:ASSIST IN DEMO OF TRAILER AT WAREHOUSE | 082 | CLOSED | 422.96 | 0 | 845.92 | 845.92
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | EO:ASSIST WITH TRAILER DEMO AT WAREHOUSE | 082 | CLOSED | 3089.6 | 0 | 2664.78 | 2664.78
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | ES: EVACUATE A/C UNITS AT TRAILER TO BE DEMOLISED | 082 | CLOSED | 213.44 | 0 | 248.2 | 248.2
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | IN: SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | 082 | CLOSED | 220.92 | 0 | 220.92 | 220.92
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | LO:ASSIST IN DEMO OF TRAILER AT WAREHOUSE | 082 | CLOSED | 142.92 | 0 | 142.92 | 142.92
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | MO:MOVE OUT RELATED TO TRAILER DEMO AT WAREHOUSE | 082 | CLOSED | 420 | 0 | 42.615 | 42.615
PJ0003194 | SR 09/10: AG TRAILER REMOVAL - FOUNDATION WAREHOUSE 82 | MAY, TOM | CLOSED | 2009-07-20 | PL:ASSIST IN TRAILER DEMO AT WAREHOUSE | 082 | CLOSED | 423.84 | 0 | 317.88 | 317.88
PJ0003194 Total | [7 empty] | 8412.467 | 0 | 5267.785 | 5267.785
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | AD: AIR POLLUTION CONTROL DISTRICT FEES (MAINT) | 056 | CLOSED | 385 | 0 | 385 | 385
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | CA:DEMO SWINE BUILDINGS | 056 | CLOSED | 27960 | 0 | 9068.2474 | 9068.2474
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | CP: PROJECT CONTINGENCY | 056 | CLOSED | 0 | 0 | 0 | 0
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | EL:ASSIST IN DEMO OF SWINE BUILDINGS | 056 | CLOSED | 1791.84 | 0 | 52.87 | 52.87
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | EO:ASSIST IN DEMO OF SWINE BUILDINGS | 056 | CLOSED | 6579.2 | 0 | 4932.5 | 4932.5
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | IN: SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | 056 | CLOSED | 220.92 | 0 | 220.92 | 220.92
PJ0003191 | SR 09/10: REMOVE NURSERY / GROWER BUILDING - SWINE UNIT 56 | MAY, TOM | CLOSED | 2009-07-20 | PL:ASSIST IN DEMO OF SWINE BUILDINGS | 056 | CLOSED | 1786.16 | 0 | 1207.63 | 1207.63
PJ0003191 Total | [7 empty] | 38723.12 | 0 | 15867.1674 | 15867.1674
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | AD: G&J TILE | 048 | CLOSED | 4557.6 | 0 | 6632.41 | 6632.41
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | CA:REPAIR WATER DAMAGE AT SHOWER ENV. HORT. UNIT 48 | 048 | CLOSED | 8538 | 0 | 5807.6224 | 5807.6224
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 0 | 0 | 0 | 0
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | EL:DISCONNECT ELECTRICAL / REINSTALL FIXTURE AFTER CONSTRUCTION | 048 | CLOSED | 211.48 | 0 | 337.367 | 337.367
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | IN: SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | 048 | CLOSED | 220.92 | 0 | 165.69 | 165.69
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | PA:FINISH COAT AND PAINT RESTROOMS TO MATCH EXISTING. | 048 | CLOSED | 2787.68 | 0 | 3026.41 | 3026.41
PJ0003190 | SR 10/11: REPAIR WATER DAMAGE - ENV HORT 48 STUDENT RES | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | PL:RELOCATE PLUMBING AS NEEDED. | 048 | CLOSED | 8657.6 | 0 | 990.0474 | 990.0474
PJ0003190 Total | [7 empty] | 24973.28 | 0 | 16959.5468 | 16959.5468
PJ0003183 | SR 09/10: REPLACE ROOF& EQUIPMENT WELL - ENG 13 | LAMPMAN, GREG | CLOSED | 2009-07-17 | AD: JOC 08.018.016 MAINO | 013 | CLOSED | 184277.73 | 0 | 184277.73 | 184277.73
PJ0003183 | SR 09/10: REPLACE ROOF& EQUIPMENT WELL - ENG 13 | LAMPMAN, GREG | CLOSED | 2009-07-17 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0003183 | SR 09/10: REPLACE ROOF& EQUIPMENT WELL - ENG 13 | LAMPMAN, GREG | CLOSED | 2009-07-17 | IN: SR 09/10: REPLACE ROOF& EQUIPMENT WELL - ENG 13 | 013 | CLOSED | 110.46 | 0 | 82.845 | 82.845
PJ0003183 Total | [7 empty] | 184388.19 | 0 | 184360.575 | 184360.575
PJ0003179 | SR 09/10: REPLACE GUTTERS - BLD 8A AG ENGR | KUENTZEL, DOUGLAS A. | CLOSED | 2009-07-17 | AD: JOC 09.019.006 STAPLES | 008A | CLOSED | 28883.46 | 0 | 28883.46 | 28883.46
PJ0003179 | SR 09/10: REPLACE GUTTERS - BLD 8A AG ENGR | KUENTZEL, DOUGLAS A. | CLOSED | 2009-07-17 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 0 | 0 | 0 | 0
PJ0003179 Total | [7 empty] | 28883.46 | 0 | 28883.46 | 28883.46
PJ0003178 | MJ: IN-HOUSE SUPPORT FOR SWIMMING POOL COVER - 171A PCV POOL | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | CP: PROJECT CONTINGENCY | 171A | CLOSED | 1417.45 | 0 | 0 | 0
PJ0003178 | MJ: IN-HOUSE SUPPORT FOR SWIMMING POOL COVER - 171A PCV POOL | MOLLAN, CHERYL L. | CLOSED | 2009-07-17 | IN: IN-HOUSE SUPPORT FOR SWIMMING POOL COVER - 171A PCV | 171A | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0003178 Total | [7 empty] | 1550.002 | 0 | 99.414 | 99.414
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU CUSTODIAL SUPPORT FOR SPANOS THEATRE SHOW -7/12/09 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT AT SPANOS THEATRE-7/28-9/1 (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR BELIEVE IN DANCE PERF - 7/26 | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER EVENT - 7/17(N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER EVENT - 8/15 (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER SHOW-7/11 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 15 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 17 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 2 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 23 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 24 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 25 BY 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 3 BY 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N APR 3 BY 6PM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 24 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 25 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 26 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 27 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 4 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 5 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N FEB 6 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JAN 29 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JAN 30 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JAN 31 BY 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JUNE 26 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JUNE 3 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JUNE 4 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JUNE 5 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N JUNE 6 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 13 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 17 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 19 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 20 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 21 BY 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 26 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 27 BY 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 27 BY 6PM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 4 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 5 BY 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 6 BY 6PM | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAR 9 BY 5PM | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 12 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 13 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 14 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 15 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 20 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 22 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 23 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 27 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT 0N MAY 28 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT-7/19 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT-8/15 (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENT-8/22 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE EVENTS-8/29 & 8/30 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATRE SHOW-7/18 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT SPANOS THEATER - 7/10 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SPANOS THEATRE EVENT SUPPORT ON OCT 24 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR PERFORMANCE AT SPANOS THEATRE - 9/18 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT - OCT 23 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON DEC 18 BEFORE 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON DEC 19 BEFORE 5PM (N/L) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON DEC 5 AT 12 & 5 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 11 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 12 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 13 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 14 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 19 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 20 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON NOV 21 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON OCT 1 BEFORE 5PM | 044 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON OCT 16 BEFORE 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON OCT 17 BEFORE 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON OCT 18 BEFORE 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENT ON SEPT 26 - 7PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENTS ON DEC 6 BEFORE 12PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE EVENTS ON OCT 25 BEFORE 12 AND 5 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE ON OCT 15 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE PERFORMANCE - 10/2 BY 5PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPANOS THEATRE SUPPORT ON 9/22 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: SUPPORT FOR SPNAOS THEATRE EVENT ON OCT 10 BEFORE 6PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU:: SUPPORT FOR SPANOS THEATRE EVENT ON DEC 4 BEFORE 5PM | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003175 | 09/10 EXTRA CLEANING, 044 THEATRE (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CUSTODIAL SUPPORT FOR SMILE AND NOD PERFORMANCE | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003175 Total | [7 empty] | 0 | 0 | 5198.166 | 5198.166
PJ0003174 | CAFES EVENT AT UNIVERSITY HOUSE - FRI JULY 17, 2009 | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CA: INSTALL TENT CANOPY AT UNIVERSITY HOUSE BEFORE 7/16 - 6PM | 051 | CLOSED | 1270.4172 | 0 | 664.56 | 664.56
PJ0003174 | CAFES EVENT AT UNIVERSITY HOUSE - FRI JULY 17, 2009 | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 140.06 | 0 | 0 | 0
PJ0003174 | CAFES EVENT AT UNIVERSITY HOUSE - FRI JULY 17, 2009 | POPHAM, DONALD J. | CLOSED | 2009-07-15 | CU: CUSTODIAL SUPPORT FOR CAFES EVENTS - 7/16 | 051 | CLOSED | 37.7154 | 0 | 32.796 | 32.796
PJ0003174 | CAFES EVENT AT UNIVERSITY HOUSE - FRI JULY 17, 2009 | POPHAM, DONALD J. | CLOSED | 2009-07-15 | LA: LANDSCAPE SERVICES SUPPORT FOR CAFES EVENT-7/16 | 051 | CLOSED | 92.4427 | 0 | 40.368 | 40.368
PJ0003174 Total | [7 empty] | 1540.6353 | 0 | 737.724 | 737.724
PJ0003172 | ONE DAY FOOTBALL CAMP - SAT 7/11/09 - SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2009-07-09 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003172 | ONE DAY FOOTBALL CAMP - SAT 7/11/09 - SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2009-07-09 | CU: CLEAN RESTROOMS AT CRANDALL GYM 7/11/09 | 061 | CLOSED | 0 | 0 | 37.62 | 37.62
PJ0003172 | ONE DAY FOOTBALL CAMP - SAT 7/11/09 - SPANOS STADIUM | POPHAM, DONALD J. | CLOSED | 2009-07-09 | LA: LINE SPANOS STADIUM FOR FOOTBALL CAMP ON 7/11 | 061 | CLOSED | 0 | 0 | 403.68 | 403.68
PJ0003172 Total | [7 empty] | 0 | 0 | 441.3 | 441.3
PJ0003170 | NEW DOOR W/ CP LOGO - MOTT BLD 42 INSIDE RM 124 (SEE PJ 3754) | MOLLAN, CHERYL L. | CLOSED | 2009-07-07 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 505.95 | 0 | 0 | 0
PJ0003170 | NEW DOOR W/ CP LOGO - MOTT BLD 42 INSIDE RM 124 (SEE PJ 3754) | MOLLAN, CHERYL L. | CLOSED | 2009-07-07 | IN: NEW DOOR W/ CP LOGO - MOTT BLD 42 INSIDE RM 124 | 042 | CLOSED | 66.276 | 0 | 33.138 | 33.138
PJ0003170 | NEW DOOR W/ CP LOGO - MOTT BLD 42 INSIDE RM 124 (SEE PJ 3754) | MOLLAN, CHERYL L. | CLOSED | 2009-07-07 | LO:PURCHASE AND INSTALL NEW KEY PAD AND CLOSURE (NO LABOR) | 042 | CLOSED | 1837.344 | 0 | 1122.156 | 1122.156
PJ0003170 Total | [7 empty] | 2409.57 | 0 | 1155.294 | 1155.294
PJ0003169 | SR 09/10: ROOF PROJECT - BLD 40 | LAMPMAN, GREG | CLOSED | 2009-06-26 | AD: JOC 08.018.008 MAINO | 040 | CLOSED | 201146.9 | 0 | 201146.9 | 201146.9
PJ0003169 | SR 09/10: ROOF PROJECT - BLD 40 | LAMPMAN, GREG | CLOSED | 2009-06-26 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0003169 | SR 09/10: ROOF PROJECT - BLD 40 | LAMPMAN, GREG | CLOSED | 2009-06-26 | IN: SR 09/10: ROOF PROJECT - BLD 40 | 040 | CLOSED | 276.15 | 0 | 110.46 | 110.46
PJ0003169 Total | [7 empty] | 201423.05 | 0 | 201257.36 | 201257.36
PJ0003168 | SR 09/10 ROAD STRIPING - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2009-06-26 | AD: JOC 08.018.009 MAINO | GENERAL | CLOSED | 42831.57 | 0 | 42831.57 | 42831.57
PJ0003168 | SR 09/10 ROAD STRIPING - CAMPUS WIDE | LAMPMAN, GREG | CLOSED | 2009-06-26 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003168 Total | [7 empty] | 42831.57 | 0 | 42831.57 | 42831.57
PJ0003167 | SR 09/10: ROOF REPAIR - FOOD PROC. BLD 24 | LAMPMAN, GREG | CLOSED | 2009-06-26 | AD: JOC 08.018.007 MAINO | 024 | CLOSED | 386899.26 | 0 | 386899.26 | 386899.26
PJ0003167 | SR 09/10: ROOF REPAIR - FOOD PROC. BLD 24 | LAMPMAN, GREG | CLOSED | 2009-06-26 | AD: QUAGLINO ROOFING | 024 | CLOSED | 975 | 0 | 975 | 975
PJ0003167 | SR 09/10: ROOF REPAIR - FOOD PROC. BLD 24 | LAMPMAN, GREG | CLOSED | 2009-06-26 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 0 | 0 | 0 | 0
PJ0003167 | SR 09/10: ROOF REPAIR - FOOD PROC. BLD 24 | LAMPMAN, GREG | CLOSED | 2009-06-26 | IN: SR 09/10: ROOF REPAIR - FOOD PROC. BLD 24 | 024 | CLOSED | 110.46 | 0 | 110.46 | 110.46
PJ0003167 Total | [7 empty] | 387984.72 | 0 | 387984.72 | 387984.72
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | AD: QUINN POWER SYSTEMS - PURCHASE GENERATOR | 150 | CLOSED | 90384.42 | 0 | 90384.42 | 90384.42
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | CA: EXTEND (E) PAD | 150 | CLOSED | 7233.3395 | 0 | 2975.695 | 2975.695
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | CP: PROJECT CONTINGENCY | 150 | CLOSED | 0 | 0 | 0 | 0
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | EL: INSTALL GENERATOR | 150 | CLOSED | 27558.3936 | 0 | 30441.305 | 30441.305
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | EO: DITCH FOR MOVING THE GAS LINE | 150 | CLOSED | 617.92 | 0 | 2355.82 | 2355.82
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | IN: SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | 150 | CLOSED | 110.46 | 0 | 82.845 | 82.845
PJ0003166 | SR 09/10: REPLACE BACK-UP GENERATOR - POULTRY CENTER 150 | LAMPMAN, GREG | CLOSED | 2009-06-25 | PL: MOVE GAS LINE | 150 | CLOSED | 1472.183 | 0 | 2895.4215 | 2895.4215
PJ0003166 Total | [7 empty] | 127376.7161 | 0 | 129135.5065 | 129135.5065
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | AD: HARVEY PLUMBING | 160F | CLOSED | 5136 | 0 | 5136 | 5136
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | AD: JOC 10.020.010 STAPLES | 160F | CLOSED | 143590.897 | 0 | 143539.002 | 143539.002
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | AD: MOTION INDUSTRIES | 160F | CLOSED | 20538.543 | 0 | 20443.2381 | 20443.2381
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | AD: PURCHASE METER PARTS TO BE INSTALLED BY FARM OPS | 160F | CLOSED | 716.45 | 0 | 1321.69 | 1321.69
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | CA: INSTALL TEMP POWER PROTECTION ON SPORTS COMPLEX RD. | 160F | CLOSED | 1213.8 | 0 | 3696.0552 | 3696.0552
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | CP: PROJECT CONTINGENCY | 160F | CLOSED | 5173.65 | 0 | 0 | 0
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | EL: SUPPORT FOR VFD INSTALLATION AT SPORTS COMPLEX | 160F | CLOSED | 23247.72 | 0 | 27859.7899 | 27859.7899
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | EO: EXCAVATE EXISTING CONDUITS, PER ELECTRICIANS - SPORT COMPLEX | 160F | CLOSED | 4487.52 | 0 | 4948.5 | 4948.5
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | IN: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | 160F | CLOSED | 662.76 | 0 | 596.484 | 596.484
PJ0003165 | MJ: INSTALL VFD DRIVES ON IRRIGATION PUMPS - SPORTS COMPLEX 160 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-26 | PA: PAINT ELECTRICAL CORD COVER ON PATHWAY NEAR JANSSEN | 160F | CLOSED | 148.728 | 0 | 118.728 | 118.728
PJ0003165 Total | [7 empty] | 204916.068 | 0 | 207659.4872 | 207659.4872
PJ0003164 | REMOVE CLOSET WALLS TO CREATE LARGER SHARED OFFICE-BLD 34 RM 214 | MAY, TOM | CLOSED | 2009-06-22 | CA:FLOOR TILE REPAIR IN 34-214 | 034 | CLOSED | 254.1942 | 0 | 816.0422 | 816.0422
PJ0003164 | REMOVE CLOSET WALLS TO CREATE LARGER SHARED OFFICE-BLD 34 RM 214 | MAY, TOM | CLOSED | 2009-06-22 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 118.28 | 0 | 0 | 0
PJ0003164 | REMOVE CLOSET WALLS TO CREATE LARGER SHARED OFFICE-BLD 34 RM 214 | MAY, TOM | CLOSED | 2009-06-22 | EL:DISCONNECT ELECTRICAL IN 34-214A | 034 | CLOSED | 190.332 | 0 | 158.61 | 158.61
PJ0003164 | REMOVE CLOSET WALLS TO CREATE LARGER SHARED OFFICE-BLD 34 RM 214 | MAY, TOM | CLOSED | 2009-06-22 | IN: REMOVE CLOSET WALLS TO CREATE LARGER OFFICE-BLD 34 RM 214 | 034 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003164 | REMOVE CLOSET WALLS TO CREATE LARGER SHARED OFFICE-BLD 34 RM 214 | MAY, TOM | CLOSED | 2009-06-22 | MO:MOVE STEEL TO METAL BIN FROM 34-214 | 034 | CLOSED | 28.35 | 0 | 22.728 | 22.728
PJ0003164 | REMOVE CLOSET WALLS TO CREATE LARGER SHARED OFFICE-BLD 34 RM 214 | MAY, TOM | CLOSED | 2009-06-22 | PA:PATCH AND PAINT 34-214 | 034 | CLOSED | 1372.608 | 0 | 2925.624 | 2925.624
PJ0003164 Total | [7 empty] | 2030.0402 | 0 | 3989.2802 | 3989.2802
PJ0003161 | SR 09/10: GROUND WATER REMEDIATION - FARM SHOP | LAMPMAN, GREG | CLOSED | 2009-06-12 | AD: EARTH SYSTEMS | 009 | CLOSED | 60347.5 | 0 | 57024.38 | 57024.38
PJ0003161 | SR 09/10: GROUND WATER REMEDIATION - FARM SHOP | LAMPMAN, GREG | CLOSED | 2009-06-12 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0003161 | SR 09/10: GROUND WATER REMEDIATION - FARM SHOP | LAMPMAN, GREG | CLOSED | 2009-06-12 | EL: SUPPLY POWER FOR REMEDIATION EQUIPMENT | 009 | CLOSED | 685.3466 | 0 | 1680.9075 | 1680.9075
PJ0003161 Total | [7 empty] | 61032.8466 | 0 | 58705.2875 | 58705.2875
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | CA: CONSTRUCT WALKWAY IN GRASS AREA ALONG POLYVIEW DR. | 065 | CLOSED | 0 | 0 | 208.548 | 208.548
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | CA: CREATE AND INSTALL SIGNS FOR BUS STOPS AT UU AND MOTT | 065 | CLOSED | 443.04 | 0 | 769.464 | 769.464
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | CA: INSTALL WAYFINDING SIGNS AT UU PLAZA AND CHUMASH EXIT SIGNS | 065 | CLOSED | 221.52 | 0 | 475.314 | 475.314
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 19056.75 | 0 | 0 | 0
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL: DETERMINE IF FAN FOR B OF A ATM IS OPERATIONAL | 065 | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL: INSTALL TEMPORARY SMOKE DETECTORS AT EL CORRAL - UU 65 | 065 | CLOSED | 0 | 0 | 95.166 | 95.166
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL: MARK ELECTRICAL UNDERGROUND UTILITIES AT UU PLAZA | 065 | CLOSED | 0 | 0 | 63.444 | 63.444
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL: PURCHASE STOCK PARTS FOR UU PROJECT (SEE ATTACHMENTS) | 065 | CLOSED | 0 | 0 | 5553.204 | 5553.204
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL: REPAIR WIRING AT STAGE - UU PLAZA 65 | 065 | CLOSED | 0 | 0 | 104.166 | 104.166
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL: SUPPLY TEMP ELECTRICAL POWER AT AERO HANGER FOR MAINO | 004 | CLOSED | 0 | 0 | 146.166 | 146.166
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EL:ASSIST LANDSCAPERS W/ IRRIGATION CONTROLLER MODS @ THE AVENUE | 065 | CLOSED | 0 | 0 | 485.442 | 485.442
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EO: ASSIST PLUMBERS TO REMOVE VALVE AT PLANTER IN UU PLAZA (N/L) | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EO: MOVE CONCRETE PLANTERS AND TABLES OUT OF UU PLAZA | 065 | CLOSED | 0 | 0 | 1598.868 | 1598.868
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | EO: SAW CUT CURB AT SANDWICH PLANT - UU 65 | 065 | CLOSED | 0 | 0 | 674.61 | 674.61
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | ES: MAINT. ON HVAC UNIT AT UU -DUST CLOGGING INTAKE FILTERS(N/L) | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | ES: PROVIDE POWER TO HVAC SYSTEM AT UU - 65 | 065 | CLOSED | 0 | 0 | 96.048 | 96.048
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | LA: MARK AND REMOVE UNDERGROUND IRRIGATION AT UU PLAZA | 065 | CLOSED | 0 | 0 | 2515.037 | 2515.037
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | LA: MODIFY PLANTING AT TAHOE RD. AND S. PERIMETER | 065 | CLOSED | 0 | 0 | 153.24 | 153.24
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | LA: REMOVE PLANTS FROM RED HAND PLANTER AT UU | 065 | CLOSED | 0 | 0 | 1554.168 | 1554.168
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | LA: TURN OFF IRRIGATION ON BLG 52 LAWN-9/18/09 TO 9/24/09 (N/L) | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | LO: ADD PULL HANDLE TO DOOR AT EL CORRAL BOOKSTORE | 065 | CLOSED | 57.168 | 0 | 407.688 | 407.688
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | LO: REPLACE LOCKS ON LIGHTING CONTROL PANELS - UU PLAZA | 065 | CLOSED | 0 | 0 | 213.168 | 213.168
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | PL: IRRIGATION CORRECTIONS FOR UU PLAZA | 065 | CLOSED | 0 | 0 | 2614.92 | 2614.92
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | PL: REMOVE DOUBLE CHECK VALVE AT PLANTER IN UU PLAZA. | 065 | CLOSED | 0 | 0 | 437.544 | 437.544
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | PL:MARK UNDERGROUND GAS, WATER, SEWER, STORM DRAINS AT UU PLAZA | 065 | CLOSED | 0 | 0 | 6631.6104 | 6631.6104
PJ0003160 | MJ: UU PLAZA CONSTRUCTION - IN-HOUSE SUPPORT - BLDG 65 | QUEEN, BARBARA | CLOSED | 2009-06-11 | WAREHOUSE SUPPLIES - GENERAL USE FOR UU PLAZA PROJECT | 065 | CLOSED | 0 | 0 | 62.784 | 62.784
PJ0003160 Total | [7 empty] | 19778.478 | 0 | 24987.4874 | 24987.4874
PJ0003159 | SMART ROOM SET-UP - BLD 21 ARCE RM 228 & 229 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2009-06-09 | CA: INSTALL SMARTROOM EQUIPMENT - BLD 21, RMS 228 & 229 | 021 | CLOSED | 0 | 0 | 641.1 | 641.1
PJ0003159 | SMART ROOM SET-UP - BLD 21 ARCE RM 228 & 229 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2009-06-09 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0003159 | SMART ROOM SET-UP - BLD 21 ARCE RM 228 & 229 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2009-06-09 | EL: INSTALL ELECTRICAL FOR SMARTROOMS - BLG. 21, RMS. 228 & 229 | 021 | CLOSED | 0 | 0 | 1168.3776 | 1168.3776
PJ0003159 | SMART ROOM SET-UP - BLD 21 ARCE RM 228 & 229 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2009-06-09 | IN: SMART ROOM SET-UP - BLD 21 ARCE RM 228 & 229 | 021 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0003159 Total | [7 empty] | 132.552 | 0 | 1875.7536 | 1875.7536
PJ0003157 | MOVE SODA FOUNTAIN TO NEW LOCATION - EINSTEIN BRO 171B | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-08 | CP: PROJECT CONTINGENCY | 171B | CLOSED | 779.93 | 0 | 0 | 0
PJ0003157 | MOVE SODA FOUNTAIN TO NEW LOCATION - EINSTEIN BRO 171B | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-08 | IN: RELOCATE SODA FOUNTAIN - EINSTEIN'S BAGELS 171B | 171B | CLOSED | 265.104 | 0 | 33.138 | 33.138
PJ0003157 | MOVE SODA FOUNTAIN TO NEW LOCATION - EINSTEIN BRO 171B | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-08 | PCV CA: RELOCATE DRINKS COUNTER | 171B | CLOSED | 2265.6258 | 0 | 2706.684 | 2706.684
PJ0003157 | MOVE SODA FOUNTAIN TO NEW LOCATION - EINSTEIN BRO 171B | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-08 | PCV EL: INSTALL NEW CIRCUITS | 171B | CLOSED | 2808.3948 | 0 | 2007.684 | 2007.684
PJ0003157 | MOVE SODA FOUNTAIN TO NEW LOCATION - EINSTEIN BRO 171B | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-08 | PCV ES: FABRICATE BACK SPLASH | 171B | CLOSED | 1034.447 | 0 | 625.08 | 625.08
PJ0003157 | MOVE SODA FOUNTAIN TO NEW LOCATION - EINSTEIN BRO 171B | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-08 | PCV PL: INSTALL SODA DRAINLINE TO FLOOR SINK. | 171B | CLOSED | 1114.8058 | 0 | 1074.204 | 1074.204
PJ0003157 Total | [7 empty] | 8268.3074 | 0 | 6446.79 | 6446.79
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | AD: AIR POLLUTION CONTROL DISTRICT FEES | GENERAL | CLOSED | 365 | 0 | 365 | 365
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | AD: COSTS FOR PARKING SIGNS (CB-ZERODPT - SEE TASK LIST) | GENERAL | CLOSED | 0 | 0 | 1498.54 | 1498.54
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | AD: JOC 08.018.001 MAINO | GENERAL | CLOSED | 318443.6844 | 0 | 318443.6844 | 318443.6844
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | CA: CREATE AND INSTALL SIGN FOR SPORTS COMPLEX PARKING EXPANSION | GENERAL | CLOSED | 170.76 | 0 | 47.568 | 47.568
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 27143.93 | 0 | 0 | 0
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | EL: PROVIDE POWER FOR NEW BASKETBALL COURTS - SPORTS COMPLEX | GENERAL | CLOSED | 4950.8107 | 0 | 5206.272 | 5206.272
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | EO: SPORTS COMPLEX BASKETBALL COURTS EXCAVATION | GENERAL | CLOSED | 1275.8503 | 0 | 14208.3068 | 14208.3068
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | IN: PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | GENERAL | CLOSED | 795.312 | 0 | 231.966 | 231.966
PJ0003156 | PARKING LOT EXPANSION W/ PATHS FOR STADIUM - SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-10 | PL: INSTALL WATER SUPPLY SOURCE FOR BASKETBALL COURTS | GENERAL | CLOSED | 4596.8669 | 0 | 612.132 | 612.132
PJ0003156 Total | [7 empty] | 357742.2143 | 0 | 340613.4692 | 340613.4692
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | AD: DIRECT PAY PURCHASE - SIGNS FOR BUS STOPS | GENERAL | CLOSED | 1250.604 | 0 | 1250.604 | 1250.604
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | AD: JOC 08.017.019 MAINO | GENERAL | CLOSED | 283970.6491 | 0 | 283970.6491 | 283970.6491
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | AD: JOC 08.018.021 MAINO | GENERAL | CLOSED | 91009.1496 | 0 | 91009.1389 | 91009.1389
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | CA: CREATE (3) TEMPORARY BUS STOP LOCATION SIGNS | GENERAL | CLOSED | 230.76 | 0 | 124.68 | 124.68
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | CA: CREATE TRAFFIC SIGNS FOR BUS STOP PROJECT | GENERAL | CLOSED | 55.38 | 0 | 457.764 | 457.764
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 14079.34 | 0 | 0 | 0
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | EL: MOVE LIGHT POLES, CONNECT SIGNS, INSTALL LIGHT IN ISLAND | GENERAL | CLOSED | 10095.9374 | 0 | 18928.6222 | 18928.6222
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | EO: SUPPLY TRENCHING AS NEEDED | GENERAL | CLOSED | 370.752 | 0 | 1276.308 | 1276.308
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | IN:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | GENERAL | CLOSED | 994.14 | 0 | 927.864 | 927.864
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | LA: (USE WO165161) LANDSCAPING FOR S. PERIMETER BUS STOP PROJECT | GENERAL | CLOSED | 11634.96 | 0 | 16017.4861 | 16017.4861
PJ0003155 | SP 09/10:CONSTRUCT 4 BUS STOPS/CLOSE S.PERIMETER-GRAND TO CUESTA | LAMPMAN, GREG | CLOSED | 2009-06-09 | PL: SUPPLY PLUMBING AS NEEDED | GENERAL | CLOSED | 729.2167 | 0 | 4496.2154 | 4496.2154
PJ0003155 Total | [7 empty] | 414420.8889 | 0 | 418459.3317 | 418459.3317
PJ0003154 | SP 09/10: PURCHASE & INSTALL BIKE RACKS (NO PADS) - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2009-06-09 | AD: DERO (BIKE RACKS) | GENERAL | CLOSED | 4117.3065 | 0 | 3803.5183 | 3803.5183
PJ0003154 | SP 09/10: PURCHASE & INSTALL BIKE RACKS (NO PADS) - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2009-06-09 | AD: PEAK RACKS, INC. | GENERAL | CLOSED | 40459.91 | 0 | 40278.438 | 40278.438
PJ0003154 | SP 09/10: PURCHASE & INSTALL BIKE RACKS (NO PADS) - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2009-06-09 | CA:PROVIDE INSTALLATION SUPPORT FOR BIKE RACKS | GENERAL | CLOSED | 3013.2258 | 0 | 3495.588 | 3495.588
PJ0003154 | SP 09/10: PURCHASE & INSTALL BIKE RACKS (NO PADS) - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2009-06-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 294.42 | 0 | 0 | 0
PJ0003154 | SP 09/10: PURCHASE & INSTALL BIKE RACKS (NO PADS) - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2009-06-09 | EO:GRADE AND REPLACE BARK WITH DG | GENERAL | CLOSED | 523.44 | 0 | 370.752 | 370.752
PJ0003154 | SP 09/10: PURCHASE & INSTALL BIKE RACKS (NO PADS) - CAMPUS WIDE | MOLLAN, CHERYL L. | CLOSED | 2009-06-09 | MO:MOVE BIKE RACKS FROM STORAGE YARD TO CAMPUS LOCATIONS | GENERAL | CLOSED | 1591.695 | 0 | 568.2 | 568.2
PJ0003154 Total | [7 empty] | 49999.9973 | 0 | 48516.4963 | 48516.4963
PJ0003153 | SP 09/10: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | MAY, TOM | CLOSED | 2009-06-09 | AD: CPC LOSS PREVENTION DEPARTMENT | 001 | CLOSED | 24634.0108 | 0 | 26171.2905 | 26171.2905
PJ0003153 | SP 09/10: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | MAY, TOM | CLOSED | 2009-06-09 | AD: EXPENDITURE TRANSFER (MAINT - FOR TRACKING, ONLY) | 001 | CLOSED | -34995.02 | 0 | -26072.32 | -26072.32
PJ0003153 | SP 09/10: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | MAY, TOM | CLOSED | 2009-06-09 | CA:INSTALL CAMERA BASES IN ADM | 001 | CLOSED | 3068.8344 | 0 | 2476.4954 | 2476.4954
PJ0003153 | SP 09/10: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | MAY, TOM | CLOSED | 2009-06-09 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 2814.48 | 0 | 0 | 0
PJ0003153 | SP 09/10: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | MAY, TOM | CLOSED | 2009-06-09 | IN: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | 001 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003153 | SP 09/10: INSTALL CAMERAS FOR SECURITY - ADMIN BLD 01 | MAY, TOM | CLOSED | 2009-06-09 | LO: REPLACE DEADBOLT ON ELECTRICAL CLOSET - ADMIN 4TH FLOOR | 001 | CLOSED | 234.336 | 0 | 702.696 | 702.696
PJ0003153 Total | [7 empty] | -4110.8068 | 0 | 3410.7139 | 3410.7139
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | AD: ENGLEKIRK AND SABOL - SEISMIC PEER REVIEW | GENERAL | CLOSED | 572.45 | 0 | 535 | 535
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | AD: JOC 08.018.003 MAINO | GENERAL | CLOSED | 179870.4133 | 0 | 179870.4133 | 179870.4133
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | CA: CREATE AND INSTALL PARKING SIGNS AT SPORTS COMPLEX | GENERAL | CLOSED | 572.28 | 0 | 520.59 | 520.59
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 23874.48 | 0 | 0 | 0
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | EL: BASKETBALL COURT LIGHTING | GENERAL | CLOSED | 63638.5134 | 0 | 73566.738 | 73566.738
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | IN: ACCESSIBILITY COMPLIANCE OF BASKETBALL COURTS | GENERAL | CLOSED | 530.208 | 0 | 430.794 | 430.794
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | LO:CORES AND PADLOCKS AT THE ASI BASKETBALL COURT | GENERAL | CLOSED | 1593.3158 | 0 | 114.336 | 114.336
PJ0003149 | EQUIPMENT, FINISHES, FENCES, STORAGE BLG - SP COMPLEX BBALL CRTS | KUENTZEL, DOUGLAS A. | CLOSED | 2009-06-02 | PA: EQUIPMENT CLEARANCE MARKING | GENERAL | CLOSED | 1954.8226 | 0 | 228.768 | 228.768
PJ0003149 Total | [7 empty] | 272606.4831 | 0 | 255266.6393 | 255266.6393
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | AD: J.L. FASULO DRYWALL | 046 | CLOSED | 3135.1 | 0 | 3135.1 | 3135.1
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | AD: RUSSCO | 046 | CLOSED | 770.4 | 0 | 577.8 | 577.8
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | CA:BUILD CONFERENCE ROOM IN BLDG 46 | 046 | CLOSED | 3711.945 | 0 | 5456.382 | 5456.382
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 1677.45 | 0 | 0 | 0
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | EL:ELECTRICAL FOR NEW CONFERENCE ROOM IN 46 | 046 | CLOSED | 4710.8107 | 0 | 2904.0487 | 2904.0487
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | ES:EXTEND (E) HVAC TO NEW ROOM IN BLDG 46 | 046 | CLOSED | 2368.8941 | 0 | 4599.48 | 4599.48
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | IN: ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | 046 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | LO:NEW LOCKSET FOR NEW CONFERENCE ROOM IN 46 | 046 | CLOSED | 550.9147 | 0 | 911.928 | 911.928
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | MO: MOVE RUSSCO PANELS FROM BLG. 46 TO BLG. 20 RM. 126 | 046 | CLOSED | 94.5 | 0 | 56.82 | 56.82
PJ0003146 | ENCLOSE CONFERENCE AREA FOR PRIVACY- BLD 46 CONFERENCE RM | MAY, TOM | CLOSED | 2009-05-22 | PA:PAINT NEW CONFERENCE ROOM IN 46 | 046 | CLOSED | 2338.9464 | 0 | 950.304 | 950.304
PJ0003146 Total | [7 empty] | 19491.5129 | 0 | 18724.4147 | 18724.4147
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | CA:REMOVE WALL ITEMS IN 10-202 *ADDITIONAL WORK* | 010 | CLOSED | 374.1942 | 0 | 392.598 | 392.598
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 172.4 | 0 | 0 | 0
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | CU:STRIP AND WAX FLOOR IN 10-202 | 010 | CLOSED | 285.6365 | 0 | 524.736 | 524.736
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | EL:REMOVE WIREMOLD IN 10-202 - ADDITIONAL WORK | 010 | CLOSED | 218.2474 | 0 | 489.24 | 489.24
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | IN: MINOR RENOVATIONS - BLD 10 RM 202 | 010 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | MO:MOVE OUT FURNITURE IN 10-202 | 010 | CLOSED | 72.135 | 0 | 73.866 | 73.866
PJ0003145 | MINOR RENOVATIONS - BLD 10 RM 202 | MAY, TOM | CLOSED | 2009-05-28 | PA:PAINT ROOM 10-202 | 010 | CLOSED | 2098.9464 | 0 | 1195.4948 | 1195.4948
PJ0003145 Total | [7 empty] | 3354.1114 | 0 | 2742.2108 | 2742.2108
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | AD: SLO APCD - TRACKING OF PERMIT COSTS (MAINT) | GENERAL | CLOSED | 0 | 0 | 265 | 265
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | AD: SLO APCD NOTIFICATION OF DEMO AND RENOVATION (OVERHEAD ONLY) | GENERAL | CLOSED | 535 | 0 | 25.55 | 25.55
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | AD: WILLIAMS SCOTSMAN | GENERAL | CLOSED | 1597.51 | 0 | 1262.6 | 1262.6
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | CA:REMOVE AWNING AND DECK AT 52T | GENERAL | CLOSED | 10163.3376 | 0 | 5363.4065 | 5363.4065
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 877.85 | 0 | 0 | 0
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | EL:DISCONNECT POWER TO 52T TRAILER FOR REMOVAL | GENERAL | CLOSED | 291.208 | 0 | 95.166 | 95.166
PJ0003143 | SP 08/09: REMOVE TRAILER 52T INCLUDING PORCH & DECK | MAY, TOM | CLOSED | 2009-05-21 | ES: WELDING ASSISTANCE WITH AWNING AT TRAILER 52T | GENERAL | CLOSED | 512.256 | 0 | 220.32 | 220.32
PJ0003143 Total | [7 empty] | 13977.1616 | 0 | 7232.0425 | 7232.0425
PJ0003142 | INSTALL NEW PAINT BOOTH AT PAINT SHOP - BLDG 70E | GRIFFIN, PATRICK E | CLOSED | 2009-05-18 | CA: POUR CONCRETE PAD FOR SPRAY BOOTH | 070E | CLOSED | 4509.7 | 0 | 9152.74 | 9152.74
PJ0003142 | INSTALL NEW PAINT BOOTH AT PAINT SHOP - BLDG 70E | GRIFFIN, PATRICK E | CLOSED | 2009-05-18 | CP: PROJECT CONTINGENCY | 070E | CLOSED | 555.66 | 0 | 0 | 0
PJ0003142 | INSTALL NEW PAINT BOOTH AT PAINT SHOP - BLDG 70E | GRIFFIN, PATRICK E | CLOSED | 2009-05-18 | EL: PROVIDE ELECTRICAL SERVICES FOR NEW SPRAY BOOTH | 070E | CLOSED | 472.96 | 0 | 2136.618 | 2136.618
PJ0003142 | INSTALL NEW PAINT BOOTH AT PAINT SHOP - BLDG 70E | GRIFFIN, PATRICK E | CLOSED | 2009-05-18 | EO: SAW CUT AND EXCAVATE AREA FOR NEW PAD AT PAINT SHOP | 070E | CLOSED | 463.44 | 0 | 270.34 | 270.34
PJ0003142 | INSTALL NEW PAINT BOOTH AT PAINT SHOP - BLDG 70E | GRIFFIN, PATRICK E | CLOSED | 2009-05-18 | IN: INSTALL NEW PAINT BOOTH AT PAINT SHOP - BLDG 70E | 070E | CLOSED | 110.46 | 0 | 55.23 | 55.23
PJ0003142 Total | [7 empty] | 6112.22 | 0 | 11614.928 | 11614.928
PJ0003141 | EXTEND WIRE BASKET - BLDG 35 LIBRARY - 1ST FLOOR HALLWAY | MAY, TOM | CLOSED | 2009-05-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 19.21 | 0 | 0 | 0
PJ0003141 | EXTEND WIRE BASKET - BLDG 35 LIBRARY - 1ST FLOOR HALLWAY | MAY, TOM | CLOSED | 2009-05-13 | ES:REMOVE A SECTION OF DUCT IN LIBRARY | 035 | CLOSED | 192.096 | 0 | 81.396 | 81.396
PJ0003141 Total | [7 empty] | 211.306 | 0 | 81.396 | 81.396
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | AD: RUSSCO | 070 | CLOSED | 0 | 0 | 457.37 | 457.37
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | CA: DETACH & REMOUNT FURNITURE 70-103B & 103F (SEE TASKS) | 070 | CLOSED | 184.6 | 0 | 307.3575 | 307.3575
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 225.2 | 0 | 0 | 0
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | CU: SHAMPOO CARPET ON OR BY THURSDAY 5/21/09 70-103B & 103F | 070 | CLOSED | 437.28 | 0 | 163.98 | 163.98
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | LO: CHANGE CORE IN FACILITY SERVICES ROOM 103 TO 57A-2 | 070 | CLOSED | 47.64 | 0 | 53.82 | 53.82
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | MO: MOVE OFFICE FURNITURE FROM OFFICE (SEE TASK) | 070 | CLOSED | 105 | 0 | 37.88 | 37.88
PJ0003140 | PREP OFFICE FOR FURNITURE MOVE FROM 70-103F TO 103B (MAINT) | GALVEZ, CESAR | CLOSED | 2009-05-14 | PA: PAINT OFFICES BY THURSDAY 5/21/09 - 70-103B & 103F | 070 | CLOSED | 1525.12 | 0 | 1048.52 | 1048.52
PJ0003140 Total | [7 empty] | 2524.84 | 0 | 2068.9275 | 2068.9275
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | AD: MACDONALD COMPANY | 010 | CLOSED | 1284 | 0 | 876.0732 | 876.0732
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | CA:DEMO DESKS IN 10-215 | 010 | CLOSED | 3302.8632 | 0 | 2695.1208 | 2695.1208
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 984.17 | 0 | 0 | 0
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | CU:STRIP AND WAX FLOOR IN 10-215 | 010 | CLOSED | 196.776 | 0 | 491.94 | 491.94
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | EL:RECONFIGURE ELECTRIC RACEWAYS IN 10-215 | 010 | CLOSED | 3493.2266 | 0 | 1339.2378 | 1339.2378
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | IN: FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | 010 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | MO:MOVE OUT EXCESS FURNITURE FROM 10-215 | 010 | CLOSED | 126 | 0 | 85.23 | 85.23
PJ0003139 | FURNITURE AND POWER MODIFICATIONS FOR COMPUTER LAB 10-215 | MAY, TOM | CLOSED | 2009-05-04 | PA:PAINT ROOM 10-215 | 010 | CLOSED | 1372.608 | 0 | 2037.228 | 2037.228
PJ0003139 Total | [7 empty] | 10825.9198 | 0 | 7591.1058 | 7591.1058
PJ0003134 | RE-CORE DORMITORY AREAS | GRIFFIN, PATRICK E. | CLOSED | 2009-05-06 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 26008.99 | 0 | 0 | 0
PJ0003134 | RE-CORE DORMITORY AREAS | GRIFFIN, PATRICK E. | CLOSED | 2009-05-06 | LO: RE-CORE ROOMS IN HOUSING FROM 07 TO NEW SERIES | RESIDENCE | CLOSED | 260089.848 | 0 | 236031.5478 | 236031.5478
PJ0003134 Total | [7 empty] | 286098.838 | 0 | 236031.5478 | 236031.5478
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | AD: JOC 08.018.019 MAINO | 061 | CLOSED | 91371.3767 | 0 | 91371.3874 | 91371.3874
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | CA: (MAINT)INSTALL SIDEWALK & FENCE AT NORTH END OF STADIUM - 61 | 061 | CLOSED | 3346 | 0 | 7274.9456 | 7274.9456
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | CA: INSTALL ADA COMPLIANT UPGRADES AT SPANOS | 061 | CLOSED | 0 | 0 | 490.956 | 490.956
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | CP: PROJECT CONTINGENCY | 061 | CLOSED | -1598.38 | 0 | 0 | 0
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | EO: (MAINT) SIDEWALK PREPARATION FOR SPANOS ADA UPGRADES | 061 | CLOSED | 0 | 0 | 733.78 | 733.78
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | IN: ADA UPGRADES - SPANOS STADIUM 61 | 061 | CLOSED | 0 | 0 | 430.794 | 430.794
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | LO: ADJUST DOOR CLOSERS AT SPANOS | 061 | CLOSED | 0 | 0 | 1057.608 | 1057.608
PJ0003132 | SP 09/10: ADA UPGRADES - SPANOS STADIUM 61 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-29 | PL: COORDINATE WITH CONTRACTOR | 061 | CLOSED | 0 | 0 | 401.082 | 401.082
PJ0003132 Total | [7 empty] | 93118.9967 | 0 | 101760.553 | 101760.553
PJ0003131 | INSTALL WINDOW THAT OPENS - BLD 35 RM 206 | MAY, TOM | CLOSED | 2009-04-28 | AD: SAN LUIS GLASS | 035 | CLOSED | 1016.5 | 0 | 1029.3507 | 1029.3507
PJ0003131 | INSTALL WINDOW THAT OPENS - BLD 35 RM 206 | MAY, TOM | CLOSED | 2009-04-28 | CA:INSTALL ANCHORS FOR SHELVES IN LIBRARY | 035 | CLOSED | 1107.6 | 0 | 2211.666 | 2211.666
PJ0003131 | INSTALL WINDOW THAT OPENS - BLD 35 RM 206 | MAY, TOM | CLOSED | 2009-04-28 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 184.81 | 0 | 0 | 0
PJ0003131 | INSTALL WINDOW THAT OPENS - BLD 35 RM 206 | MAY, TOM | CLOSED | 2009-04-28 | EL: DISCONNECT POWER TO DESK UNIT IN 35-114B | 035 | CLOSED | 63.444 | 0 | 95.166 | 95.166
PJ0003131 Total | [7 empty] | 2372.354 | 0 | 3336.1827 | 3336.1827
PJ0003130 | STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | LAMPMAN, GREG | CLOSED | 2009-04-28 | CA: REMOVE GREEN HOUSE | GENERAL | CLOSED | 1926.8202 | 0 | 368.6342 | 368.6342
PJ0003130 | STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | LAMPMAN, GREG | CLOSED | 2009-04-28 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1391.46 | 0 | 0 | 0
PJ0003130 | STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | LAMPMAN, GREG | CLOSED | 2009-04-28 | EL: INSTALL ELECTRICAL FOR NEW GREEN HOUSE STRUCTURE | GENERAL | CLOSED | 6781.6214 | 0 | 1417.398 | 1417.398
PJ0003130 | STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | LAMPMAN, GREG | CLOSED | 2009-04-28 | EO: LEVEL SITE FOR GREEN HOUSE | GENERAL | CLOSED | 1853.76 | 0 | 3705.444 | 3705.444
PJ0003130 | STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | LAMPMAN, GREG | CLOSED | 2009-04-28 | IN: STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | GENERAL | CLOSED | 397.656 | 0 | 265.104 | 265.104
PJ0003130 | STRUCTURE, POWER, WATER TO GROW ALGAE - NEAR H1 PARKING LOT | LAMPMAN, GREG | CLOSED | 2009-04-28 | PL: INSTALL NEW WATER LINE | GENERAL | CLOSED | 2470.2473 | 0 | 2791.128 | 2791.128
PJ0003130 Total | [7 empty] | 14821.5649 | 0 | 8547.7082 | 8547.7082
PJ0003126 | REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | MAY, TOM | CLOSED | 2009-04-21 | AD: JOC 08.017.020 MAINO | 035 | CLOSED | 21481.7159 | 0 | 21481.7266 | 21481.7266
PJ0003126 | REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | MAY, TOM | CLOSED | 2009-04-21 | AD: RUSSCO | 035 | CLOSED | 1715.8092 | 0 | 1763.4884 | 1763.4884
PJ0003126 | REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | MAY, TOM | CLOSED | 2009-04-21 | CA:DEMO SERVICE COUNTER IN 35-111 | 035 | CLOSED | 1270.4172 | 0 | 195.7488 | 195.7488
PJ0003126 | REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | MAY, TOM | CLOSED | 2009-04-21 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 799.19 | 0 | 0 | 0
PJ0003126 | REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | MAY, TOM | CLOSED | 2009-04-21 | EL:DISCONNECT POWER TO SERVICE COUNTER 35-111 | 035 | CLOSED | 582.4159 | 0 | 2866.68 | 2866.68
PJ0003126 | REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | MAY, TOM | CLOSED | 2009-04-21 | IN: REFERENCE DOOR; STORE-FRONT WINDOW&DOOR BLD 35-111 | 035 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003126 Total | [7 empty] | 25982.1002 | 0 | 26440.1958 | 26440.1958
PJ0003125 | VPSA OFFICE REMODEL COMPLETION - ADMIN 01-209 LOBBY & 209B | MAY, TOM | CLOSED | 2009-04-24 | CA:INSTALL PAINTING AND MIRROR IN ADM 209 | 001 | CLOSED | 63.687 | 0 | 92.538 | 92.538
PJ0003125 | VPSA OFFICE REMODEL COMPLETION - ADMIN 01-209 LOBBY & 209B | MAY, TOM | CLOSED | 2009-04-24 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 52.5 | 0 | 0 | 0
PJ0003125 Total | [7 empty] | 116.187 | 0 | 92.538 | 92.538
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | AD: FLOOR CONNECTION | 035 | CLOSED | 15540.0059 | 0 | 15557.0296 | 15557.0296
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | AD: HAMON OVERHEAD DOOR | 035 | CLOSED | 2247 | 0 | 2034.391 | 2034.391
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | AD: JOC 08.017.21.00 MAINO | 035 | CLOSED | 17712.1915 | 0 | 17712.1915 | 17712.1915
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | CA:REMODEL PROJECT IN 35-114 | 035 | CLOSED | 5011.2516 | 0 | 5675.9748 | 5675.9748
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 700.39 | 0 | 0 | 0
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | CU:CONSTRUCTION CARPET CLEANING 35-114B | 035 | CLOSED | 262.368 | 0 | 344.358 | 344.358
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | EH&S:MONITORING FOR CARPET REMOVAL IN 35-206 | 035 | CLOSED | 616.512 | 0 | 606.48 | 606.48
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | EL:ELECTRICAL WORK IN 35-114 | 035 | CLOSED | 7261.6214 | 0 | 7264.41 | 7264.41
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | IN: RELOCATION/EXPANSION - POLYCONNECT LAB | 035 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | LO:INSTALL NEW DOOR HARDWARE IN 35-114B | 035 | CLOSED | 682.4011 | 0 | 2185.776 | 2185.776
PJ0003124 | RELOCATION/EXPANSION - POLYCONNECT LAB | MAY, TOM | CLOSED | 2009-04-21 | PA:PAINT 35-114 B/C | 035 | CLOSED | 4175.9534 | 0 | 5312.88 | 5312.88
PJ0003124 Total | [7 empty] | 54342.247 | 0 | 56826.0429 | 56826.0429
PJ0003122 | INSTALL (2) NEW 220V CIRCUITS IN EACH BLDG: 001, 002, 011, 047. | LAMPMAN, GREG | CLOSED | 2009-04-23 | AD: JOC 08.017.024 MAINO | GENERAL | CLOSED | 7954.8187 | 0 | 7954.8187 | 7954.8187
PJ0003122 | INSTALL (2) NEW 220V CIRCUITS IN EACH BLDG: 001, 002, 011, 047. | LAMPMAN, GREG | CLOSED | 2009-04-23 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 701.73 | 0 | 0 | 0
PJ0003122 | INSTALL (2) NEW 220V CIRCUITS IN EACH BLDG: 001, 002, 011, 047. | LAMPMAN, GREG | CLOSED | 2009-04-23 | EL: BLG 11 - ASSIST THOMA ELECTRIC | GENERAL | CLOSED | 126.888 | 0 | 63.444 | 63.444
PJ0003122 | INSTALL (2) NEW 220V CIRCUITS IN EACH BLDG: 001, 002, 011, 047. | LAMPMAN, GREG | CLOSED | 2009-04-23 | IN: INSTALL (2)NEW 220V CIRCUITS IN EACH BLDG:001, 002, 011, 047 | GENERAL | CLOSED | 331.38 | 0 | 33.138 | 33.138
PJ0003122 Total | [7 empty] | 9114.8167 | 0 | 8051.4007 | 8051.4007
PJ0003121 | ASSIST CAMPUS DINING REINSTALL 13 VENDING MISERS (TRACKING ONLY) | ELLIOT, DENNIS K | CLOSED | 2009-04-23 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 0 | 0 | 0 | 0
PJ0003121 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0003119 | RELAY FOR LIFE - DEXTER LAWN-SAT MAY 16, 2009 BY 7:30AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-04-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003119 | RELAY FOR LIFE - DEXTER LAWN-SAT MAY 16, 2009 BY 7:30AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-04-22 | EL: INSTALL ONE SPIDER BOX FOR RELAY FOR LIFE EVENT ON 5/16-5/17 | GENERAL | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0003119 | RELAY FOR LIFE - DEXTER LAWN-SAT MAY 16, 2009 BY 7:30AM (NO EST) | POPHAM, DONALD J. | CLOSED | 2009-04-22 | LA: TURN OFF WATER FOR REALY FOR LIFE EVENT 5/16 & 5/17 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003119 Total | [7 empty] | 0 | 0 | 158.61 | 158.61
PJ0003118 | FFA STATE FINALS SUPPORT - MAY 2009 | POPHAM, DONALD J. | CLOSED | 2009-04-22 | CA: PULL OUT EAST SIDE BLEACHERSFOR FFA STATE FINALS - 5/1 | GENERAL | CLOSED | 443.04 | 0 | 470.73 | 470.73
PJ0003118 | FFA STATE FINALS SUPPORT - MAY 2009 | POPHAM, DONALD J. | CLOSED | 2009-04-22 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0003118 | FFA STATE FINALS SUPPORT - MAY 2009 | POPHAM, DONALD J. | CLOSED | 2009-04-22 | CU: CUSTODIAL SUPPORT FOR FFA STATE FINALS | GENERAL | CLOSED | 0 | 0 | 376.2 | 376.2
PJ0003118 Total | [7 empty] | 443.04 | 0 | 846.93 | 846.93
PJ0003117 | RE-PIN EXT. DOORS -SO MT,YOS,SM&ALL NO MT RMS-ISSUE KEYS(NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003117 | RE-PIN EXT. DOORS -SO MT,YOS,SM&ALL NO MT RMS-ISSUE KEYS(NO EST) | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | LO: RE-PIN EXTERIOR DOORS | RESIDENCE | CLOSED | 0 | 0 | 4840.24 | 4840.24
PJ0003117 Total | [7 empty] | 0 | 0 | 4840.24 | 4840.24
PJ0003116 | INSTALL ONITY SWIPE CARD LOCKS, ALL EXTERIOR S.M., YOS., SO MT | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | AD: JOC 08.017.023 MAINO | RESIDENCE | CLOSED | 15231.85 | 0 | 15231.85 | 15231.85
PJ0003116 | INSTALL ONITY SWIPE CARD LOCKS, ALL EXTERIOR S.M., YOS., SO MT | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | CA:CARPENTRY SERVICES FOR ONITY PROJECT | RESIDENCE | CLOSED | 763.4 | 0 | 463.53 | 463.53
PJ0003116 | INSTALL ONITY SWIPE CARD LOCKS, ALL EXTERIOR S.M., YOS., SO MT | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 10371.21 | 0 | 0 | 0
PJ0003116 | INSTALL ONITY SWIPE CARD LOCKS, ALL EXTERIOR S.M., YOS., SO MT | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | EL:PROVIDE NEW CIRUITS AND WIRE RUNS FOR ONITY LOCKSETS AT DRF | RESIDENCE | CLOSED | 11251.04 | 0 | 8807.06 | 8807.06
PJ0003116 | INSTALL ONITY SWIPE CARD LOCKS, ALL EXTERIOR S.M., YOS., SO MT | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | LO:INSTALL NEW ONITY ELECTRIFIED DOOR ACCESS SYSTEMS IN DRF | RESIDENCE | CLOSED | 77229.2 | 0 | 77650.5875 | 77650.5875
PJ0003116 | INSTALL ONITY SWIPE CARD LOCKS, ALL EXTERIOR S.M., YOS., SO MT | GRIFFIN, PATRICK E. | CLOSED | 2009-04-21 | PA-TOUCH UP PAINTING | RESIDENCE | CLOSED | 0 | 0 | 95.32 | 95.32
PJ0003116 Total | [7 empty] | 114846.7 | 0 | 102248.3475 | 102248.3475
PJ0003114 | ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | MAY, TOM | CLOSED | 2009-04-15 | CA:SUPPORT FOR BLUE LIGHT ON GRAND AVE | GENERAL | CLOSED | 1126.08 | 0 | 2243.361 | 2243.361
PJ0003114 | ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | MAY, TOM | CLOSED | 2009-04-15 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2162.09 | 0 | 0 | 0
PJ0003114 | ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | MAY, TOM | CLOSED | 2009-04-15 | EL:BLUE LIGHT ON GRAND AVE | GENERAL | CLOSED | 6806.64 | 0 | 4487.91 | 4487.91
PJ0003114 | ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | MAY, TOM | CLOSED | 2009-04-15 | EO:(CHARGEBACK)EXCAVATE FOR BLUE LIGHT ON GRAND | GENERAL | CLOSED | 12322.56 | 0 | 17442.4775 | 17442.4775
PJ0003114 | ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | MAY, TOM | CLOSED | 2009-04-15 | IN: ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | GENERAL | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003114 | ADD CODE BLUE PHONE, HARDWIRE, NEAR G-1 PARKING LOT | MAY, TOM | CLOSED | 2009-04-15 | LA:(CHARGEBACK) SUPPORT FOR BLUE LIGHT ON GRAND AVE | GENERAL | CLOSED | 724.416 | 0 | 302.76 | 302.76
PJ0003114 Total | [7 empty] | 23274.338 | 0 | 24609.0605 | 24609.0605
PJ0003113 | REPLACE ENTRY CARPET, ALL DORM RMS - TRINITY 105 & MUIR 107 | MAY, TOM | CLOSED | 2009-04-16 | AD: INNOVATION FLOORING | RESIDENCE | CLOSED | 74804.0424 | 0 | 73049.1782 | 73049.1782
PJ0003113 | REPLACE ENTRY CARPET, ALL DORM RMS - TRINITY 105 & MUIR 107 | MAY, TOM | CLOSED | 2009-04-16 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 4661.39 | 0 | 0 | 0
PJ0003113 Total | [7 empty] | 79465.4324 | 0 | 73049.1782 | 73049.1782
PJ0003112 | TELECOM ACCESS HATCH, 24"X24" MINIMUM, SW CORNER-BLD 24 RM 103A | MAY, TOM | CLOSED | 2009-04-13 | CA:INSTALL HATCH IN 24-103A | 024 | CLOSED | 494.1942 | 0 | 578.412 | 578.412
PJ0003112 | TELECOM ACCESS HATCH, 24"X24" MINIMUM, SW CORNER-BLD 24 RM 103A | MAY, TOM | CLOSED | 2009-04-13 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 49.41 | 0 | 0 | 0
PJ0003112 Total | [7 empty] | 543.6042 | 0 | 578.412 | 578.412
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | AD: SANTA MARIA ACOUSTICAL | 024 | CLOSED | 6108.844 | 0 | 2568 | 2568
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | CA: REMOVE CABINETS | 024 | CLOSED | 3087.6546 | 0 | 1520.616 | 1520.616
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 3100.63 | 0 | 0 | 0
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | EL REMOVE AND INSTALL ELECTRICAL | 024 | CLOSED | 10873.1874 | 0 | 2556.3486 | 2556.3486
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | ES: INSTALL NEW DUCTS IN ROOM | 024 | CLOSED | 3898.4285 | 0 | 3811.04 | 3811.04
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | IN: MODIFY ROOM - BLD 024 RM 104B | 024 | CLOSED | 331.38 | 0 | 298.242 | 298.242
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | LO: INSTALL NEW KEY PAD LOCK SET | 024 | CLOSED | 1348.1443 | 0 | 901.1238 | 901.1238
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | PA: PAINT WALLS 24-104B | 024 | CLOSED | 4152.251 | 0 | 5264.105 | 5264.105
PJ0003111 | MODIFY ROOM - BLD 024 RM 104B | LAMPMAN, GREG | CLOSED | 2009-04-13 | PL: DEMO ISLAND PLUMBING | 024 | CLOSED | 2402.0611 | 0 | 1702.071 | 1702.071
PJ0003111 Total | [7 empty] | 35302.581 | 0 | 18621.5464 | 18621.5464
PJ0003110 | INSTALL MASTS FOR WEBCAMS - 42, 44, 43A, 82, TENNIS SHED | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-10 | AD: CREDIT CARD PURCHASE (WILL-BURT) | GENERAL | CLOSED | 3000 | 0 | 2814.6 | 2814.6
PJ0003110 | INSTALL MASTS FOR WEBCAMS - 42, 44, 43A, 82, TENNIS SHED | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-10 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 799.04 | 0 | 0 | 0
PJ0003110 | INSTALL MASTS FOR WEBCAMS - 42, 44, 43A, 82, TENNIS SHED | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-10 | EL: INSTALL CONDUIT AND POWER FOR WEBCAM MOUNTING | GENERAL | CLOSED | 2295.4054 | 0 | 1917.396 | 1917.396
PJ0003110 | INSTALL MASTS FOR WEBCAMS - 42, 44, 43A, 82, TENNIS SHED | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-10 | EL: INSTALL WEBCAMS ON TENNIS SHED AND BLDGS 43A AND 19 | GENERAL | CLOSED | 3810.8107 | 0 | 2412.006 | 2412.006
PJ0003110 | INSTALL MASTS FOR WEBCAMS - 42, 44, 43A, 82, TENNIS SHED | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-10 | IN: INSTALL MASTS FOR WEBCAMS - 42, 44, 43A, 82, TENNIS SHED | GENERAL | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0003110 Total | [7 empty] | 10037.8081 | 0 | 7243.416 | 7243.416
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | AD: CREDIT CARD PURCHASE FROM DYSON AIRBLADE | 065 | CLOSED | 2098.5 | 0 | 2725.956 | 2725.956
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | AD: G&J TILE | 065 | CLOSED | 3351.24 | 0 | 3552.4 | 3552.4
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | AD: JOC 08.018.005 MAINO | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | CA:REMOVE TILE FOR PLUMBING ACCESS, RELOCATE DISPENSER | 065 | CLOSED | 563.04 | 0 | 3382.3422 | 3382.3422
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 108.32 | 0 | 0 | 0
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | CU:PROVIDE CUSTIODIAL SUPPORT AFTER CONSTRUCTION | 065 | CLOSED | 131.184 | 0 | 75.24 | 75.24
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | EL:INSTALL NEW ELECTRICAL DYSON AIRBLADE HANDRYERS | 065 | CLOSED | 1550.1186 | 0 | 1402.326 | 1402.326
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | IN: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | 065 | CLOSED | 132.552 | 0 | 149.121 | 149.121
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | LO: | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | PA:PAINT RESTROOMS AS NEEDED AFTER DISPENSER RELOCATION | 065 | CLOSED | 3103.969 | 0 | 400.866 | 400.866
PJ0003109 | M&R ASI 09/10: DOWNSTAIRS RESTROOM - DSA COMPLIANCE - BLD 65 | MOLLAN, CHERYL L. | CLOSED | 2009-04-10 | PL: UU RESTROOM REMODEL | 065 | CLOSED | 7615.3003 | 0 | 7395.0204 | 7395.0204
PJ0003109 Total | [7 empty] | 18654.2239 | 0 | 19083.2716 | 19083.2716
PJ0003102 | CUSTOM CABINETS, COUNTERS, STORAGE, ELECTRICAL - CANYON POST 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-09 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 440.26 | 0 | 0 | 0
PJ0003102 | CUSTOM CABINETS, COUNTERS, STORAGE, ELECTRICAL - CANYON POST 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-09 | PCV CA: INSTALL SHELVES AND DRAWERS - CANYON POST | 171A | CLOSED | 3859.2228 | 0 | 4105.194 | 4105.194
PJ0003102 | CUSTOM CABINETS, COUNTERS, STORAGE, ELECTRICAL - CANYON POST 171 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-09 | PCV EL: RELOCATE AND INSTALL WALL OUTLETS - CANYON POST | 171A | CLOSED | 411.208 | 0 | 158.61 | 158.61
PJ0003102 Total | [7 empty] | 4710.6908 | 0 | 4263.804 | 4263.804
PJ0003100 | WORK IN SCIENCE BLDG FOR CTR FOR SCI RELOCATION-052 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-04-08 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0003100 | WORK IN SCIENCE BLDG FOR CTR FOR SCI RELOCATION-052 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-04-08 | EL: DISCONNECT ELECTRICAL AND BENCHTOPS, 52-B11 & E30 | 052 | CLOSED | 0 | 0 | 729.608 | 729.608
PJ0003100 | WORK IN SCIENCE BLDG FOR CTR FOR SCI RELOCATION-052 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-04-08 | ES: E48 - REMOVE HVAC EQUIP FOR CENTER FOR SCI. RELOCATION - 052 | 052 | CLOSED | 0 | 0 | 969.108 | 969.108
PJ0003100 | WORK IN SCIENCE BLDG FOR CTR FOR SCI RELOCATION-052 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-04-08 | PL: E46/E47/E48 PLUMBING FOR SCI. RELOCATION - 052 | 052 | CLOSED | 0 | 0 | 51960.7164 | 51960.7164
PJ0003100 Total | [7 empty] | 0 | 0 | 53659.4324 | 53659.4324
PJ0003098 | SUPPORT LEED-EB FOR ANNOUNCEMENT - FOE 25 (MAINT) APRIL 9 @ NOON | POPHAM, DONALD J. | CLOSED | 2009-04-06 | AD: PURCHASE OF 10X10 POP UP TENTS FOR RAIN (N/L) | 025 | CLOSED | 0 | 0 | 171.83 | 171.83
PJ0003098 | SUPPORT LEED-EB FOR ANNOUNCEMENT - FOE 25 (MAINT) APRIL 9 @ NOON | POPHAM, DONALD J. | CLOSED | 2009-04-06 | CP: PROJECT CONTINGENCY | 025 | CLOSED | 0 | 0 | 0 | 0
PJ0003098 | SUPPORT LEED-EB FOR ANNOUNCEMENT - FOE 25 (MAINT) APRIL 9 @ NOON | POPHAM, DONALD J. | CLOSED | 2009-04-06 | CU: CUSTODIAL SUPPORT FOR FOE LEED DEDICATION EVENT - 4/9 | 025 | CLOSED | 0 | 0 | 27.33 | 27.33
PJ0003098 | SUPPORT LEED-EB FOR ANNOUNCEMENT - FOE 25 (MAINT) APRIL 9 @ NOON | POPHAM, DONALD J. | CLOSED | 2009-04-06 | LA: LANDSCAPE SUPPORT FOR FOE LEED DEDICATION - 4/9 | 025 | CLOSED | 0 | 0 | 201.84 | 201.84
PJ0003098 Total | [7 empty] | 0 | 0 | 401 | 401
PJ0003095 | MISC WIRING & ELECTRICAL REPAIRS-BLDG 004-HANGAR SHOP (NO EST.) | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-01 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 338.31 | 0 | 0 | 0
PJ0003095 | MISC WIRING & ELECTRICAL REPAIRS-BLDG 004-HANGAR SHOP (NO EST.) | KUENTZEL, DOUGLAS A. | CLOSED | 2009-04-01 | EL: MISC WIRING AND REPAIRS | 004 | CLOSED | 3383.108 | 0 | 4292.034 | 4292.034
PJ0003095 Total | [7 empty] | 3721.418 | 0 | 4292.034 | 4292.034
PJ0003094 | INSTALL CARPET - BLD 34 RM 210 | POPHAM, DONALD J. | CLOSED | 2009-03-25 | AD: INNOVATION FLOORING | 034 | CLOSED | 3457.1914 | 0 | 3478.3239 | 3478.3239
PJ0003094 | INSTALL CARPET - BLD 34 RM 210 | POPHAM, DONALD J. | CLOSED | 2009-03-25 | CA: REMOVE COVEBASE FOR CARPET INSTALLATION. 034-210 | 034 | CLOSED | 190.5072 | 0 | 417.4769 | 417.4769
PJ0003094 | INSTALL CARPET - BLD 34 RM 210 | POPHAM, DONALD J. | CLOSED | 2009-03-25 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 364.78 | 0 | 0 | 0
PJ0003094 Total | [7 empty] | 4012.4786 | 0 | 3895.8008 | 3895.8008
PJ0003092 | SERVICES FOR CATA FARM SHOW 6/23/09 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-03-26 | CA: SUPPORT FOR CATA FARM SHOW ON JUNE 23 | 009 | CLOSED | 886.08 | 0 | 595.764 | 595.764
PJ0003092 | SERVICES FOR CATA FARM SHOW 6/23/09 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-03-26 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0003092 | SERVICES FOR CATA FARM SHOW 6/23/09 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-03-26 | EL: INSTALL POWER FOR CATA FARM SHOW ON JUNE 22 | 009 | CLOSED | 0 | 0 | 793.05 | 793.05
PJ0003092 | SERVICES FOR CATA FARM SHOW 6/23/09 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-03-26 | SUPPLY RENTAL: CATA FARM SHOW - 6/19 - 6/24 | 009 | CLOSED | 0 | 0 | 52.5 | 52.5
PJ0003092 Total | [7 empty] | 886.08 | 0 | 1441.314 | 1441.314
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | AD: BUEHLER AND BUEHLER | 027 | CLOSED | 3103 | 0 | 2814.1 | 2814.1
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | AD: JOC 08.017.027 MAINO | 027 | CLOSED | 8954.2201 | 0 | 8954.2201 | 8954.2201
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 1696.24 | 0 | 0 | 0
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | CU: CLEAN RM 196 AND WAX FLOOR IN RM 180A-HEALTH CENTER | 027 | CLOSED | 131.184 | 0 | 163.98 | 163.98
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | EL:COMPLETE ELECTRICAL WORK AT HEALTH CENTER 196 | 027 | CLOSED | 1490.1186 | 0 | 671.622 | 671.622
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | IN: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | 027 | CLOSED | 265.104 | 0 | 265.104 | 265.104
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | LO: COMPLETE LOCK HARDWARE INSTALLATION AT HEALTH CENTER | 027 | CLOSED | 1357.717 | 0 | 1372.1064 | 1372.1064
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | PA: PREP AND PAINT ROOMS IN HEALTH CENTER 196 AND 180A | 027 | CLOSED | 2636.9993 | 0 | 2295.108 | 2295.108
PJ0003091 | M&R H/C 09/10: ENGINEER & CONSTRUCT DOOR RM 196 TO LOBBY- BLD 27 | GRIFFIN, PATRICK E. | CLOSED | 2009-03-26 | PL:REMOVE CAST SUMP AND CAP OF SUPPLY LINES AT HEALTH CENTER | 027 | CLOSED | 467.4029 | 0 | 699.336 | 699.336
PJ0003091 Total | [7 empty] | 20101.9858 | 0 | 17235.5765 | 17235.5765
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | AD: FLOOR CONNECTION | 027 | CLOSED | 845.8029 | 0 | 1508.1115 | 1508.1115
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | AD: JOC 08.018.006 MAINO | 027 | CLOSED | 1906.8363 | 0 | 1906.8363 | 1906.8363
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | CA: FINISH ENDWALL AND SECURE SHELVING - HEALTH CTR. 135 | 027 | CLOSED | 553.8 | 0 | 394.032 | 394.032
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | CA:INSTALL NEW WALL AND DOORS | 027 | CLOSED | 3956.187 | 0 | 3956.19 | 3956.19
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | CP: PROJECT CONTINGENCY (N/L) | 027 | CLOSED | 122.97 | 0 | 0 | 0
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | EL:DISCONNECT ELECTRICAL IN WALL, CEILING, & RECEPTION DESK | 027 | CLOSED | 2059.5739 | 0 | 1517.0645 | 1517.0645
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | IN: M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | 027 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | LO:BLDG. 27, ROOM 116 REMOVE CORE / INSTALL NEW CORES IN NEW DRS | 027 | CLOSED | 2971.68 | 0 | 781.764 | 781.764
PJ0003090 | M&R H/C 09/10: REMODEL COUNSELING AREA - BLD 27 RM 135 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | PA:PATCH AND PAINT TO MATCH EXISTING IN BLDG. 27, RM 135 | 027 | CLOSED | 3711.8167 | 0 | 2801.436 | 2801.436
PJ0003090 Total | [7 empty] | 16261.2188 | 0 | 12997.9863 | 12997.9863
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | AD: FLOOR CONNECTION | 027 | CLOSED | 374.5 | 0 | 378.9191 | 378.9191
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | CA:UNSCREW SHELVES (114)& REMOVE CARPET AND COUNTER(154) BLDG27 | 027 | CLOSED | 2032.446 | 0 | 553.614 | 553.614
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | CP: PROJECT CONTINGENCY (N/L) | 027 | CLOSED | 518.43 | 0 | 0 | 0
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | EH&S: HAZ MAT REVIEW (MAINT) (NO LABOR) | 027 | CLOSED | 0 | 0 | 0 | 0
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | EL:DISCONNECT ELECTRICAL | 027 | CLOSED | 63.444 | 0 | 126.888 | 126.888
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | IN: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | 027 | CLOSED | 66.276 | 0 | 49.707 | 49.707
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | MO:ADD WORK:MOVE DESK IN BLDG 27 | 027 | CLOSED | 126 | 0 | 153.414 | 153.414
PJ0003088 | M&R H/C 09/10: CONVERT RM 154 FROM STORAGE TO OFFICE - BLD 27 | MOLLAN, CHERYL L. | CLOSED | 2009-03-26 | PA:PAINT ROOMS IN BLDG 27, ROOM 154, 114 | 027 | CLOSED | 2455.8245 | 0 | 1794.96 | 1794.96
PJ0003088 Total | [7 empty] | 5636.9205 | 0 | 3057.5021 | 3057.5021
PJ0003087 | WORK IN FISHER SCI BLDG FOR CTR FOR SCI RELOCATION-033 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-19 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0003087 | WORK IN FISHER SCI BLDG FOR CTR FOR SCI RELOCATION-033 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-19 | EH&S:WORK IN FISHER SCI BLDG FOR CENTER FOR SCI RELOCATION (N/L) | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0003087 | WORK IN FISHER SCI BLDG FOR CTR FOR SCI RELOCATION-033 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-19 | PL: INSTALL SAFETY SHOWERS FOR CTR FOR SCI. RELOCATION - 033 | 033 | CLOSED | 0 | 0 | 24207 | 24207
PJ0003087 Total | [7 empty] | 0 | 0 | 24207 | 24207
PJ0003086 | SUPPLY WATER AND INSTALL HOSE BIB - NEW METAL BLDG 18M | LAMPMAN, GREG | CLOSED | 2009-03-26 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 221.45 | 0 | 0 | 0
PJ0003086 | SUPPLY WATER AND INSTALL HOSE BIB - NEW METAL BLDG 18M | LAMPMAN, GREG | CLOSED | 2009-03-26 | EO: TRENCH FOR WATER SUPPLY AT NEW METAL BLDG 18M (N/L) | GENERAL | CLOSED | 741.504 | 0 | 0 | 0
PJ0003086 | SUPPLY WATER AND INSTALL HOSE BIB - NEW METAL BLDG 18M | LAMPMAN, GREG | CLOSED | 2009-03-26 | IN: SUPPLY WTER AND INSTLL HOSE BIB -NEW METAL BLG 18M (N/L) | GENERAL | CLOSED | 66.276 | 0 | 0 | 0
PJ0003086 | SUPPLY WATER AND INSTALL HOSE BIB - NEW METAL BLDG 18M | LAMPMAN, GREG | CLOSED | 2009-03-26 | PL: SUPPLY WATER AND INSTALL HOSE BIB - NEW METAL BLGD 18M | GENERAL | CLOSED | 1406.6196 | 0 | 1124.256 | 1124.256
PJ0003086 Total | [7 empty] | 2435.8496 | 0 | 1124.256 | 1124.256
PJ0003085 | MOVE & SET UP FURNITURE FROM PCV TO DORMS SUMMER 2009 | MAY, TOM | CLOSED | 2009-03-24 | AD: JOC 08.017.005 MAINO | RESIDENCE | CLOSED | 320089.8259 | 0 | 320089.8259 | 320089.8259
PJ0003085 | MOVE & SET UP FURNITURE FROM PCV TO DORMS SUMMER 2009 | MAY, TOM | CLOSED | 2009-03-24 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 24880.71 | 0 | 0 | 0
PJ0003085 | MOVE & SET UP FURNITURE FROM PCV TO DORMS SUMMER 2009 | MAY, TOM | CLOSED | 2009-03-24 | IN: MOVE & SET UP FURNITURE FROM PCV TO DORMS THIS SUMMER | RESIDENCE | CLOSED | 265.104 | 0 | 265.104 | 265.104
PJ0003085 Total | [7 empty] | 345235.6399 | 0 | 320354.9299 | 320354.9299
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | AD: INNOVATION FLOORING | 014 | CLOSED | 2206.3935 | 0 | 2307.5085 | 2307.5085
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 2285.52 | 0 | 2330.46 | 2330.46
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | CA:OFFICE REMODEL IN 14-102A/B - ADDITIONAL WORK | 014 | CLOSED | 14412.9204 | 0 | 18767.5957 | 18767.5957
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 1195.96 | 0 | 0 | 0
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | CU: CLEAN WINDOWS IN 14-102 | 014 | CLOSED | 72.1512 | 0 | 75.24 | 75.24
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | EL:REMODEL IN 14-102 | 014 | CLOSED | 872.9894 | 0 | 3396.9682 | 3396.9682
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | ES:RELOCATE THERMOSTAT 14-102A/B REMODEL | 014 | CLOSED | 587.8138 | 0 | 584.52 | 584.52
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | IN: RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | 014 | CLOSED | 265.104 | 0 | 281.673 | 281.673
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | LO:INSTALL NEW LOCKSETS 14-102A/B | 014 | CLOSED | 1964.8022 | 0 | 1348.4844 | 1348.4844
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | MO: MOVE FURNITURE OUT OF 14-102A/B - ADDITIONAL WORK | 014 | CLOSED | 94.5 | 0 | 102.276 | 102.276
PJ0003083 | RENOVATE/FURNISH RM & INSTALL SERVICE WINDOW - BLD 14-102 | MAY, TOM | CLOSED | 2009-03-19 | PA:PAINT OFFICE REMODEL 14-102A/B | 014 | CLOSED | 5487.9379 | 0 | 1823.4 | 1823.4
PJ0003083 Total | [7 empty] | 29446.0925 | 0 | 31018.1258 | 31018.1258
PJ0003081 | WORK IN GRAPHIC ARTS BLG FOR CTR FOR SCI RELOCATION-026 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-13 | CA:DEMO WALL - RM 110; FUR OUT PLUMBING WALL FOR DRAIN - RM 123 | 026 | CLOSED | 0 | 0 | 4425.0594 | 4425.0594
PJ0003081 | WORK IN GRAPHIC ARTS BLG FOR CTR FOR SCI RELOCATION-026 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-13 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 0 | 0 | 109.5228 | 109.5228
PJ0003081 | WORK IN GRAPHIC ARTS BLG FOR CTR FOR SCI RELOCATION-026 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-13 | EH&S: WORK IN GRAPHIC ARTS BLG FOR CENTER FOR SCI. RELOCATION | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0003081 | WORK IN GRAPHIC ARTS BLG FOR CTR FOR SCI RELOCATION-026 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-13 | PA: PAINT ROOM 26-110H - DUNN EDWARDS DE6205, STUCCO TAN | 026 | CLOSED | 0 | 0 | 1626.204 | 1626.204
PJ0003081 | WORK IN GRAPHIC ARTS BLG FOR CTR FOR SCI RELOCATION-026 (NO EST) | QUEEN, BARBARA | CLOSED | 2009-03-13 | PL:SAFETY SHOWER AND SINKS - RMS 110, 110M, & 123 - BLG. 26 | 026 | CLOSED | 0 | 0 | 26518.2445 | 26518.2445
PJ0003081 Total | [7 empty] | 0 | 0 | 32679.0307 | 32679.0307
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | CA: CORE HOLE IN WALL AT MOTT GYM FOR TICKET OFFICE COMM ACCESS | 043 | CLOSED | 0 | 0 | 166.14 | 166.14
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | CA: PLACE A-FRAMES/BACKBOARDS AT SPECIFIED LOCATIONS - REC. CTR. | 043 | CLOSED | 0 | 0 | 505.32 | 505.32
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | CA: RELOCATE COUNTERTOP TO TEMPORARY TICKET OFFICE TRAILER | 043 | CLOSED | 0 | 0 | 2560.86 | 2560.86
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | CA: SIGNAGE FOR TEMP WALKWAY CLOSURE AT REC. CENTER | 043 | CLOSED | 0 | 0 | 818.622 | 818.622
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | CA:CREATE CONCRETE LANDINGS AT REC CENTER | 043 | CLOSED | 33.4968 | 0 | 33.8238 | 33.8238
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 10500 | 0 | 0 | 0
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | EL: DISCONNECT POWER AT FRONT DESK -REC CNTR 43 MON AUG 24TH | 043 | CLOSED | 126.888 | 0 | 126.888 | 126.888
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | EL: INSTALL ELECTRICAL AT TICKET OFFICE TRAILER - MOTT GYM 42 | 043 | CLOSED | 0 | 0 | 4227.384 | 4227.384
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | EL: PROVIDE ELECTRICAL FOR 3 TURNSTILES - BLD 43 MAIN GYM | 043 | CLOSED | 158.61 | 0 | 158.61 | 158.61
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | EL: TEMP POWER AT ADMIN TRAILER AND GYM - 43 | 043 | CLOSED | 11744.337 | 0 | 19275.1955 | 19275.1955
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | LO: INSTALL LOCK AND PULL ON EXT. 2ND FLOOR EXIT DOOR - 43-204 | 043 | CLOSED | 0 | 0 | 1439.148 | 1439.148
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | LO: INSTALL NEW LOCK HARDWARE ON TEMPORARY TICKET BOOTH TRAILER | 043 | CLOSED | 0 | 0 | 601.812 | 601.812
PJ0003078 | MJ: FACILITIES SUPPORT FOR REC CTR GYM TEMPORARY MODS - BLDG 43 | JUDD, PERRY | CLOSED | 2009-03-12 | MO: MOVE BOXES AND FURNITURE TO TEMP. TICKET OFFICE TRAILER | 043 | CLOSED | 0 | 0 | 45.456 | 45.456
PJ0003078 Total | [7 empty] | 22563.3318 | 0 | 29959.2593 | 29959.2593
PJ0003077 | LABORATORY SAFETY UPGRADES - BLD 20-130 | MAY, TOM | CLOSED | 2009-03-05 | CA:FLOOR WORK IN 20-130 | 020 | CLOSED | 2205.6258 | 0 | 3265.7981 | 3265.7981
PJ0003077 | LABORATORY SAFETY UPGRADES - BLD 20-130 | MAY, TOM | CLOSED | 2009-03-05 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 1631.82 | 0 | 0 | 0
PJ0003077 | LABORATORY SAFETY UPGRADES - BLD 20-130 | MAY, TOM | CLOSED | 2009-03-05 | EL:INSTALL (6) CIRCUITS IN 20-130 | 020 | CLOSED | 2189.544 | 0 | 2117.652 | 2117.652
PJ0003077 | LABORATORY SAFETY UPGRADES - BLD 20-130 | MAY, TOM | CLOSED | 2009-03-05 | IN: LABORATORY SAFETY UPGRADES - BLD 20-130 | 020 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003077 | LABORATORY SAFETY UPGRADES - BLD 20-130 | MAY, TOM | CLOSED | 2009-03-05 | PL:INSTALL SINKS AND EYE WASH IN 20-130 | 020 | CLOSED | 11593.7338 | 0 | 8677.109 | 8677.109
PJ0003077 Total | [7 empty] | 17753.2756 | 0 | 14193.1111 | 14193.1111
PJ0003076 | M&R HOUS 09/10: SO MT DORMS-CONCRETE BIKE PADS | GRIFFIN, PATRICK E | CLOSED | 2009-03-06 | CA:POUR NEW BIKE PADS AT SOUTH MTN HALLS | RESIDENCE | CLOSED | 40084.222 | 0 | 43144.312 | 43144.312
PJ0003076 | M&R HOUS 09/10: SO MT DORMS-CONCRETE BIKE PADS | GRIFFIN, PATRICK E | CLOSED | 2009-03-06 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 2280.46 | 0 | 0 | 0
PJ0003076 | M&R HOUS 09/10: SO MT DORMS-CONCRETE BIKE PADS | GRIFFIN, PATRICK E | CLOSED | 2009-03-06 | EO:EXCAVATE FOR NEW BIKE PADS AT SOUTH MTN HALLS | RESIDENCE | CLOSED | 7113.2628 | 0 | 6319.53 | 6319.53
PJ0003076 | M&R HOUS 09/10: SO MT DORMS-CONCRETE BIKE PADS | GRIFFIN, PATRICK E | CLOSED | 2009-03-06 | LA:REMOVE LANDSCAPING FOR NEW BIKE RACKS | RESIDENCE | CLOSED | 1303.32 | 0 | 685.0694 | 685.0694
PJ0003076 Total | [7 empty] | 50781.2648 | 0 | 50148.9114 | 50148.9114
PJ0003074 | M&R HOUS 09/10: SIERRA MADRE-RENOVATE VOLLEYBALL COURT | MEAD, GEORGE | CLOSED | 2009-03-06 | AD: GREENVALE TREE COMPANY | 113 | CLOSED | 0 | 0 | 8495 | 8495
PJ0003074 | M&R HOUS 09/10: SIERRA MADRE-RENOVATE VOLLEYBALL COURT | MEAD, GEORGE | CLOSED | 2009-03-06 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 14000 | 0 | 0 | 0
PJ0003074 | M&R HOUS 09/10: SIERRA MADRE-RENOVATE VOLLEYBALL COURT | MEAD, GEORGE | CLOSED | 2009-03-06 | EO: INSTALL SAND AT SIERRA MADRE VOLLEYBALL COURTS | 113 | CLOSED | 0 | 0 | 2212.71 | 2212.71
PJ0003074 Total | [7 empty] | 14000 | 0 | 10707.71 | 10707.71
PJ0003072 | M&R HOUS 09/10: YOSEMITE T2 STORAGE TANK REPLACEMENT | RIVERA, MARIO L | CLOSED | 2009-03-06 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 1859.8 | 0 | 0 | 0
PJ0003072 | M&R HOUS 09/10: YOSEMITE T2 STORAGE TANK REPLACEMENT | RIVERA, MARIO L | CLOSED | 2009-03-06 | PL: REPLACE DOMESTIC HOT WATER TANK AT YOSEMITE TOWER 2 | 114 | CLOSED | 18598 | 0 | 17056.7519 | 17056.7519
PJ0003072 Total | [7 empty] | 20457.8 | 0 | 17056.7519 | 17056.7519
PJ0003070 | M&R HOUS 09/10: MUIR/TRINITY REFINISH RESIDENT RM ENTRY DOORS | MAY, TOM | CLOSED | 2009-03-06 | AD: JOC 08.017.015 MAINO | RESIDENCE | CLOSED | 58486.43 | 0 | 58486.43 | 58486.43
PJ0003070 | M&R HOUS 09/10: MUIR/TRINITY REFINISH RESIDENT RM ENTRY DOORS | MAY, TOM | CLOSED | 2009-03-06 | CA: FABRICATE AND INSTALL VINYL ROOM NUMBERS AT MUIR AND TRINITY | RESIDENCE | CLOSED | 1946 | 0 | 3949.6865 | 3949.6865
PJ0003070 | M&R HOUS 09/10: MUIR/TRINITY REFINISH RESIDENT RM ENTRY DOORS | MAY, TOM | CLOSED | 2009-03-06 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 1827.32 | 0 | 0 | 0
PJ0003070 Total | [7 empty] | 62259.75 | 0 | 62436.1165 | 62436.1165
PJ0003069 | M&R HOUS 09/10: CERRO VISTA REPAIR STUCCO CEILINGS | MAY, TOM | CLOSED | 2009-03-06 | AD: JOC 08.018.035 MAINO | RESIDENCE | CLOSED | 19433.09 | 0 | 19433.09 | 19433.09
PJ0003069 | M&R HOUS 09/10: CERRO VISTA REPAIR STUCCO CEILINGS | MAY, TOM | CLOSED | 2009-03-06 | AD: JOC 09.019.021 STAPLES | RESIDENCE | CLOSED | 53496.91 | 0 | 53496.91 | 53496.91
PJ0003069 | M&R HOUS 09/10: CERRO VISTA REPAIR STUCCO CEILINGS | MAY, TOM | CLOSED | 2009-03-06 | AD: TED MULLER PLASTERING | RESIDENCE | CLOSED | 2070 | 0 | 2070 | 2070
PJ0003069 | M&R HOUS 09/10: CERRO VISTA REPAIR STUCCO CEILINGS | MAY, TOM | CLOSED | 2009-03-06 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003069 Total | [7 empty] | 75000 | 0 | 75000 | 75000
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | AD:JOC 08.017.007 MAINO | 114 | CLOSED | 281886.98 | 0 | 281886.96 | 281886.96
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 3282.35 | 0 | 0 | 0
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | EL:LIGHTS AND OUTLETS FOR YOS TOWER 9 | 114 | CLOSED | 5572.2 | 0 | 5219.5643 | 5219.5643
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | ES:PURCHASE AND INSTALL REGISTERS IN YOS TOWER 9 | 114 | CLOSED | 433.5584 | 0 | 934.02 | 934.02
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | IN: M&R HOUS 09/10:YOSEMITE T0 RESTROOM RENOVATIONS | 114 | CLOSED | 220.92 | 0 | 331.38 | 331.38
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | LO:PURCHASE AND INSTALL LOCKS IN YOS TOWER 9 | 114 | CLOSED | 718.1912 | 0 | 690.87 | 690.87
PJ0003068 | M&R HOUS 09/10:YOSEMITE T9 RESTROOM RENOVATIONS | MAY, TOM | CLOSED | 2009-03-06 | PL: PROVIDE FIXTURES FOR YOSEMITE RESTRMS,TO BE INSTALLED BY JOC | 114 | CLOSED | 15000 | 0 | 15631.3335 | 15631.3335
PJ0003068 Total | [7 empty] | 307114.1996 | 0 | 304694.1278 | 304694.1278
PJ0003067 | INSTALL KEY TRACK BOX IN GROUNDS SHOP - BLD 70 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-03-05 | CA: INSTALL NEW MOUNTING SURFACE FOR KEY BOX | 070C | CLOSED | 519.2 | 0 | 138.195 | 138.195
PJ0003067 | INSTALL KEY TRACK BOX IN GROUNDS SHOP - BLD 70 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-03-05 | CP: PROJECT CONTINGENCY | 070C | CLOSED | 0 | 0 | 0 | 0
PJ0003067 | INSTALL KEY TRACK BOX IN GROUNDS SHOP - BLD 70 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-03-05 | EL: ADD NEW CIRCUIT FOR GROUNDS KEY BOX | 070C | CLOSED | 759.44 | 0 | 185.045 | 185.045
PJ0003067 | INSTALL KEY TRACK BOX IN GROUNDS SHOP - BLD 70 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-03-05 | IN: INSPECT NEW CIRCUIT INSTALLATION AT GROUNDS SHOP(N/L) | 070C | CLOSED | 55.23 | 0 | 0 | 0
PJ0003067 | INSTALL KEY TRACK BOX IN GROUNDS SHOP - BLD 70 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-03-05 | LO: PROGRAM AND INSTALL KEY RINGS FOR GROUNDS KEY BOX | 070C | CLOSED | 14859.9 | 0 | 9055.07 | 9055.07
PJ0003067 Total | [7 empty] | 16193.77 | 0 | 9378.31 | 9378.31
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | AD: EARTH SYSTEMS | GENERAL | CLOSED | 520.02 | 0 | 261.615 | 261.615
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | AD: JOC 08.018.002 MAINO | GENERAL | CLOSED | 225677.0277 | 0 | 225677.0277 | 225677.0277
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | CA: CONCRETE FOR LIGHT POLE BASES-SPORTS COMPL BASKETBALL COURTS | GENERAL | CLOSED | 2686.08 | 0 | 8627.46 | 8627.46
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | CA: VERIFY MEASUREMENTS OF BASKETBALL HOOPS - SPORTS COMPLEX | GENERAL | CLOSED | 110.76 | 0 | 135.096 | 135.096
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 20412.72 | 0 | 0 | 0
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | EL: UNDERGROUND CONDUIT COURT LIGHTING | GENERAL | CLOSED | 7366.2161 | 0 | 19075.3044 | 19075.3044
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | EO: ASSIST IN BASKETBALL COURTS AT SPORTS COMPLEX | GENERAL | CLOSED | 4252.5254 | 0 | 1992.5292 | 1992.5292
PJ0003065 | GRADING, PAVING, UTILITIES FOR BASKETBALL CRTS AT SPORTS COMPLEX | KUENTZEL, DOUGLAS A. | CLOSED | 2009-03-03 | IN: GRADING, PAVING, UTIL FOR BASKETBALL COURTS AT SPTS COMPLEX | GENERAL | CLOSED | 0 | 0 | 828.45 | 828.45
PJ0003065 Total | [7 empty] | 261025.3492 | 0 | 256597.4823 | 256597.4823
PJ0003064 | INSTALL CUSTOMER SUPPLIED SCREEN & PROJ. - BLD 14 RM 238B | MAY, TOM | CLOSED | 2009-03-03 | CA:INSTALL SCREEN IN T-BAR CEILING AT EAST END OF ROOM | 014 | CLOSED | 628.3884 | 0 | 1055.997 | 1055.997
PJ0003064 | INSTALL CUSTOMER SUPPLIED SCREEN & PROJ. - BLD 14 RM 238B | MAY, TOM | CLOSED | 2009-03-03 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 112.48 | 0 | 0 | 0
PJ0003064 | INSTALL CUSTOMER SUPPLIED SCREEN & PROJ. - BLD 14 RM 238B | MAY, TOM | CLOSED | 2009-03-03 | EL:INSTALL SWITCH AND ELEC FOR SCREEN 14-238F | 014 | CLOSED | 496.4947 | 0 | 289.008 | 289.008
PJ0003064 Total | [7 empty] | 1237.3631 | 0 | 1345.005 | 1345.005
PJ0003063 | LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | LAMPMAN, GREG | CLOSED | 2009-03-03 | AD: JOC 08.017.017 MAINO | 192 | CLOSED | 56040.8755 | 0 | 56040.8755 | 56040.8755
PJ0003063 | LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | LAMPMAN, GREG | CLOSED | 2009-03-03 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 6357.21 | 0 | 0 | 0
PJ0003063 | LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | LAMPMAN, GREG | CLOSED | 2009-03-03 | CU: CLEAN FLOOR AND SEAL | 192 | CLOSED | 1668.5104 | 0 | 752.4 | 752.4
PJ0003063 | LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | LAMPMAN, GREG | CLOSED | 2009-03-03 | IN: LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | 192 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0003063 | LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | LAMPMAN, GREG | CLOSED | 2009-03-03 | LO: CHANGE CORE TO CONSTRUCTION CORE BLG. 192 RM. 130 | 192 | CLOSED | 57.168 | 0 | 114.336 | 114.336
PJ0003063 | LIGHT & POWER PER PLANS W/ MODIFICATIONS -BLD 192 RM 130 | LAMPMAN, GREG | CLOSED | 2009-03-03 | PA: PAINT WALLS | 192 | CLOSED | 7759.9224 | 0 | 2437.32 | 2437.32
PJ0003063 Total | [7 empty] | 72016.2383 | 0 | 59411.2075 | 59411.2075
PJ0003062 | CONSTRUCT DONOR PLAQUE DISPLAY - BLD 154 FEED MILL RM | MAY, TOM | CLOSED | 2009-03-02 | CA:INSTALL PLAQUE AT ANC | 154 | CLOSED | 2332.446 | 0 | 2918.676 | 2918.676
PJ0003062 | CONSTRUCT DONOR PLAQUE DISPLAY - BLD 154 FEED MILL RM | MAY, TOM | CLOSED | 2009-03-02 | CP: PROJECT CONTINGENCY | 154 | CLOSED | 12.94 | 0 | 0 | 0
PJ0003062 | CONSTRUCT DONOR PLAQUE DISPLAY - BLD 154 FEED MILL RM | MAY, TOM | CLOSED | 2009-03-02 | EL: MOVE ELECTRICAL CONDUIT AT ANC | 154 | CLOSED | 220.332 | 0 | 563.022 | 563.022
PJ0003062 Total | [7 empty] | 2565.718 | 0 | 3481.698 | 3481.698
PJ0003061 | NEW/UPGRADE ALARM PANELS BLDS 15-BASE, 65-M108, 82 COM CLOSET | PAHLOW, BOB | CLOSED | 2009-03-02 | ANTS:PROVIDE PROGRAMMING SERVICES FOR PANEL CHANGE OUTS | GENERAL | CLOSED | 343.008 | 0 | 285.84 | 285.84
PJ0003061 | NEW/UPGRADE ALARM PANELS BLDS 15-BASE, 65-M108, 82 COM CLOSET | PAHLOW, BOB | CLOSED | 2009-03-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 179.39 | 0 | 0 | 0
PJ0003061 | NEW/UPGRADE ALARM PANELS BLDS 15-BASE, 65-M108, 82 COM CLOSET | PAHLOW, BOB | CLOSED | 2009-03-02 | IN: ALARM PANELS BLDS 15-BASE, 65-M108, 82 COM (NO LABOR) | GENERAL | CLOSED | 397.656 | 0 | 0 | 0
PJ0003061 Total | [7 empty] | 920.054 | 0 | 285.84 | 285.84
PJ0003060 | INSTALL DOOR ACCESS CONTROL AND ALARM SYSTEM -BLDG 197 | GRIFFIN, PATRICK E | CLOSED | 2009-03-02 | CA:CORE HOLES IN FLOOR AT BONDERSON | 197 | CLOSED | 1584.6114 | 0 | 1523.1948 | 1523.1948
PJ0003060 | INSTALL DOOR ACCESS CONTROL AND ALARM SYSTEM -BLDG 197 | GRIFFIN, PATRICK E | CLOSED | 2009-03-02 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 1398.39 | 0 | 0 | 0
PJ0003060 | INSTALL DOOR ACCESS CONTROL AND ALARM SYSTEM -BLDG 197 | GRIFFIN, PATRICK E | CLOSED | 2009-03-02 | EL: PHASE I -INSTALL CONDUIT FOR CAMES DOOR ACCESS | 197 | CLOSED | 3270.8107 | 0 | 9004.422 | 9004.422
PJ0003060 | INSTALL DOOR ACCESS CONTROL AND ALARM SYSTEM -BLDG 197 | GRIFFIN, PATRICK E | CLOSED | 2009-03-02 | EL: PHASE II-ELECTRICAL SERVICES FOR MEDIA SYSTEMS AT BONDERSON | 197 | CLOSED | 5855.52 | 0 | 2949.954 | 2949.954
PJ0003060 | INSTALL DOOR ACCESS CONTROL AND ALARM SYSTEM -BLDG 197 | GRIFFIN, PATRICK E | CLOSED | 2009-03-02 | IN: PHASE II - DOOR ACCESS CONTROL & ALARM SYSTEM -BLDG 197 | 197 | CLOSED | 265.104 | 0 | 265.104 | 265.104
PJ0003060 | INSTALL DOOR ACCESS CONTROL AND ALARM SYSTEM -BLDG 197 | GRIFFIN, PATRICK E | CLOSED | 2009-03-02 | LO:INSTALL DOOR HARDWARE FOR BONDERSON DOOR ACCESS | 197 | CLOSED | 2742.8678 | 0 | 1429.2 | 1429.2
PJ0003060 Total | [7 empty] | 15117.304 | 0 | 15171.8748 | 15171.8748
PJ0003059 | SR 08/09: REPLACE LIGHTING CONTROLLER-PAC 06-124(ENC BY 6/30/09) | VELARDE, DENIS L | CLOSED | 2009-02-27 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 63.204 | 63.204
PJ0003059 | SR 08/09: REPLACE LIGHTING CONTROLLER-PAC 06-124(ENC BY 6/30/09) | VELARDE, DENIS L | CLOSED | 2009-02-27 | EL: LIGHTING CONTROLLER AT PAC | 006 | CLOSED | 978.095 | 0 | 5052.73 | 5052.73
PJ0003059 Total | [7 empty] | 978.095 | 0 | 5115.934 | 5115.934
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 0 | 0 | 0 | 0
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | CU: CUSTODIAL SUPPORT FOR THE PRESIDENTS CABINET-5/3&4 | GENERAL | CLOSED | 0 | 0 | 2689.65 | 2689.65
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | ES: CHECK THE HVAC AT THE KECK LAB ON 3/13 BEFOR 8:00AM (N/L) | 007 | CLOSED | 0 | 0 | 0 | 0
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | GR: BLOW AND PREP AREA FOR PRES. CABINET MEETING - 3/13 | 007 | CLOSED | 0 | 0 | 67.28 | 67.28
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | LA: LANDSCAPE SERVICES SUPPORT FOR CABINET MTG - MAY 3&4 | GENERAL | CLOSED | 0 | 0 | 812.36 | 812.36
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | MO: MOVE FLOWER CART FROM UH51 TO PAINT SHOP | GENERAL | CLOSED | 0 | 0 | 4.735 | 4.735
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | MO: PRESIDENT'S CABINET WORK MAY1 - MAY 4 | GENERAL | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | PA: PRESIDENTS CABINET PREPARATION WORK - 5/3 | 006 | CLOSED | 0 | 0 | 1628.095 | 1628.095
PJ0003058 | SUPPORT FOR PRESIDENTS CABINET EXEC MEET-MAR 13 & MAY 3 (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-02-26 | PL: PM BATHROOMS AT ATL BEFORE CABINET MEETING | 007 | CLOSED | 0 | 0 | 105.96 | 105.96
PJ0003058 Total | [7 empty] | 0 | 0 | 5362.74 | 5362.74
PJ0003057 | SP 08/09: SECURITY EQUIP IN PRESIDENT'S OFFICE -BLD 01 4TH FLOOR | MAY, TOM | CLOSED | 2009-02-24 | CA: CREATE AND INSTALL SIGNS FOR ADMIN STAIRWELLS | 001 | CLOSED | 226.14 | 0 | 384.006 | 384.006
PJ0003057 | SP 08/09: SECURITY EQUIP IN PRESIDENT'S OFFICE -BLD 01 4TH FLOOR | MAY, TOM | CLOSED | 2009-02-24 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 319.47 | 0 | 0 | 0
PJ0003057 | SP 08/09: SECURITY EQUIP IN PRESIDENT'S OFFICE -BLD 01 4TH FLOOR | MAY, TOM | CLOSED | 2009-02-24 | LO:INSTALL SECURITY LOCKS IN ADM | 001 | CLOSED | 5455.717 | 0 | 3937.902 | 3937.902
PJ0003057 Total | [7 empty] | 6001.327 | 0 | 4321.908 | 4321.908
PJ0003054 | SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | POPHAM, DONALD J. | CLOSED | 2009-02-11 | AD: AL'S SEPTIC PUMPING SERVICE | 129 | CLOSED | 4900 | 0 | 5800 | 5800
PJ0003054 | SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | POPHAM, DONALD J. | CLOSED | 2009-02-11 | CP: PROJECT CONTINGENCY | 129 | CLOSED | 1281.13 | 0 | 0 | 0
PJ0003054 | SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | POPHAM, DONALD J. | CLOSED | 2009-02-11 | EO:ASSIST WITH LEACH FIELD INSTALL (N/L) | 129 | CLOSED | 1544.8 | 0 | 0 | 0
PJ0003054 | SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | POPHAM, DONALD J. | CLOSED | 2009-02-11 | IN: SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | 129 | CLOSED | 331.38 | 0 | 82.845 | 82.845
PJ0003054 | SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | POPHAM, DONALD J. | CLOSED | 2009-02-11 | LA: LANDSCAPE SUPPORT FOR AVILA HOUSE LEACH FIELD INSTALL | 129 | CLOSED | 0 | 0 | 33.64 | 33.64
PJ0003054 | SR 08/09: REPLACE LEACH FIELD AT AVILA HOUSE | POPHAM, DONALD J. | CLOSED | 2009-02-11 | PL: SUPPORT FOR LEACH FIELD INSTALL | 129 | CLOSED | 4430.7224 | 0 | 1907.28 | 1907.28
PJ0003054 Total | [7 empty] | 12488.0324 | 0 | 7823.765 | 7823.765
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | AD: CREDIT CARD PURCHASES FROM QUICK CRETE PRODUCTS | 228 | CLOSED | 0 | 0 | 8120.052 | 8120.052
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | AD: JOC 07.015.037 MAINO | GENERAL | CLOSED | 100871.0721 | 0 | 108430.7719 | 108430.7719
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | AD: JOC 08-018.027.01 MAINO | 228 | CLOSED | 14501.282 | 0 | 14511.982 | 14511.982
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | AD: JOC 08.017.025 MAINO | 228 | CLOSED | 251054.1321 | 0 | 251054.1321 | 251054.1321
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | AD: SYSTEK GRAPHIC ARTS | 228 | CLOSED | 1663.0047 | 0 | 1663.0047 | 1663.0047
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | CA: MAKE SIGNAGE FOR AVILA PIER CLOSURE | GENERAL | CLOSED | 5449.2228 | 0 | 273.654 | 273.654
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 17611.11 | 0 | 0 | 0
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | EL:REMOVE LIGHT POST ON EAST SIDE | GENERAL | CLOSED | 4093.2266 | 0 | 253.776 | 253.776
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | EL:REMOVE LIGHT POST ON WEST SIDE OF LOT AT PIER | 228 | CLOSED | 620.664 | 0 | 1027.8955 | 1027.8955
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | IN: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | 228 | CLOSED | 265.104 | 0 | 430.794 | 430.794
PJ0003053 | SP 08/09: UPGRADE LANDSIDE DEV. TO MEET CCC REQS - CALPOLY PIER | MOLLAN, CHERYL L. | CLOSED | 2009-02-11 | PL: 90 ANGLE ON WATER SUPPLY & BACKFLOW CONNECTION AT PIER | 228 | CLOSED | 1511.52 | 0 | 1080.792 | 1080.792
PJ0003053 Total | [7 empty] | 397640.3383 | 0 | 386846.8542 | 386846.8542
PJ0003051 | SR 08/09:INSTALL 4' GRN VINYL CHAIN LINK FENCE N. SIDEWLK G1 LOT | POPHAM, DONALD J. | CLOSED | 2009-02-09 | CA: INSTALL GREEN VINYL CHAIN LINK FENCE AT NORTHSIDE G-1 | GENERAL | CLOSED | 7176.043 | 0 | 7491.7985 | 7491.7985
PJ0003051 | SR 08/09:INSTALL 4' GRN VINYL CHAIN LINK FENCE N. SIDEWLK G1 LOT | POPHAM, DONALD J. | CLOSED | 2009-02-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 778.86 | 0 | 0 | 0
PJ0003051 | SR 08/09:INSTALL 4' GRN VINYL CHAIN LINK FENCE N. SIDEWLK G1 LOT | POPHAM, DONALD J. | CLOSED | 2009-02-09 | IN: SR 08/09:INSTALL 4' VINYL CHAIN LINK FENCE N. SIDEWLK G1 LOT | GENERAL | CLOSED | 276.15 | 0 | 82.845 | 82.845
PJ0003051 | SR 08/09:INSTALL 4' GRN VINYL CHAIN LINK FENCE N. SIDEWLK G1 LOT | POPHAM, DONALD J. | CLOSED | 2009-02-09 | LA:SUPPORT FOR INSTALL OF GREEN VINYL FENCE IN G-1(N/L) | GENERAL | CLOSED | 336.4 | 0 | 0 | 0
PJ0003051 Total | [7 empty] | 8567.453 | 0 | 7574.6435 | 7574.6435
PJ0003050 | RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | MAY, TOM | CLOSED | 2009-02-06 | CA:CABINET WORK IN 20-131 | 020 | CLOSED | 5540.8344 | 0 | 9721.7225 | 9721.7225
PJ0003050 | RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | MAY, TOM | CLOSED | 2009-02-06 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 3481.42 | 0 | 0 | 0
PJ0003050 | RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | MAY, TOM | CLOSED | 2009-02-06 | EL:INSTALL OVERHEAD ELECTRICAL IN 20-131 | 020 | CLOSED | 12421.6214 | 0 | 2089.452 | 2089.452
PJ0003050 | RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | MAY, TOM | CLOSED | 2009-02-06 | IN: ESTIMATE ASAP TO RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | 020 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0003050 | RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | MAY, TOM | CLOSED | 2009-02-06 | PA:PATCH AND PAINT 20-131 | 020 | CLOSED | 2983.969 | 0 | 1774.584 | 1774.584
PJ0003050 | RECONFIGURE / UPGRADE LAB - BLD 20 RM 131 | MAY, TOM | CLOSED | 2009-02-06 | PL:INSTALL SINKS AND EYE WASH STATION IN 20-131 | 020 | CLOSED | 8046.6686 | 0 | 8473.833 | 8473.833
PJ0003050 Total | [7 empty] | 32607.0654 | 0 | 22192.1435 | 22192.1435
PJ0003048 | SP 08/09: ASSESS ADA ACCESS TO STAGE (CONSULTANT) - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-02-05 | AD: SALLY SWANSON ARCHITECTS | 006 | CLOSED | 5136 | 0 | 5136 | 5136
PJ0003048 | SP 08/09: ASSESS ADA ACCESS TO STAGE (CONSULTANT) - PAC 06 | KUENTZEL, DOUGLAS A. | CLOSED | 2009-02-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 513.6 | 0 | 0 | 0
PJ0003048 Total | [7 empty] | 5649.6 | 0 | 5136 | 5136
PJ0003047 | FACILITIES SUPPORT - MAJOR LEAGUE SOCCER 2/13 & 2/15 (NO EST.) | POPHAM, DONALD J. | CLOSED | 2009-02-05 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0003047 | FACILITIES SUPPORT - MAJOR LEAGUE SOCCER 2/13 & 2/15 (NO EST.) | POPHAM, DONALD J. | CLOSED | 2009-02-05 | CU: PREP SPANOS STADIUM FOR MLS GAME ON 2/13/2009 | 061 | CLOSED | 0 | 0 | 432.63 | 432.63
PJ0003047 | FACILITIES SUPPORT - MAJOR LEAGUE SOCCER 2/13 & 2/15 (NO EST.) | POPHAM, DONALD J. | CLOSED | 2009-02-05 | CU: SUPPORT FOR MLS GAME ON 2/13 AT SPANOS STADIUM AT 7PM | 061 | CLOSED | 0 | 0 | 1316.7 | 1316.7
PJ0003047 | FACILITIES SUPPORT - MAJOR LEAGUE SOCCER 2/13 & 2/15 (NO EST.) | POPHAM, DONALD J. | CLOSED | 2009-02-05 | CU: SUPPORT FOR MLS GAME ON 2/15 AT SPANOS STADIUM AT 1PM | 061 | CLOSED | 0 | 0 | 1692.9 | 1692.9
PJ0003047 | FACILITIES SUPPORT - MAJOR LEAGUE SOCCER 2/13 & 2/15 (NO EST.) | POPHAM, DONALD J. | CLOSED | 2009-02-05 | LA: LANDSCAPE SERVICES PREP FOR MLS GAMES ON 2/13 & 2/15 | 061 | CLOSED | 0 | 0 | 1236.921 | 1236.921
PJ0003047 | FACILITIES SUPPORT - MAJOR LEAGUE SOCCER 2/13 & 2/15 (NO EST.) | POPHAM, DONALD J. | CLOSED | 2009-02-05 | PL: PM WEST SIDE RESTRMS, SPANOS STADIUM FOR SOCCER GAMES(MAINT) | 061 | CLOSED | 0 | 0 | 105.96 | 105.96
PJ0003047 Total | [7 empty] | 0 | 0 | 4785.111 | 4785.111
PJ0003045 | SUMMER 2009 SMART ROOM UPGRADES, BLD 10 RM 220 & 227 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | CA: SMARTROOM UPGRADES IN BLG. 10 ROOMS 220 & 227 | 010 | CLOSED | 898.08 | 0 | 335.016 | 335.016
PJ0003045 | SUMMER 2009 SMART ROOM UPGRADES, BLD 10 RM 220 & 227 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0003045 | SUMMER 2009 SMART ROOM UPGRADES, BLD 10 RM 220 & 227 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | EL: SMARTROOM UPGRADES IN BLG. 10 ROOMS 220 & 227 | 010 | CLOSED | 0 | 0 | 2026.194 | 2026.194
PJ0003045 | SUMMER 2009 SMART ROOM UPGRADES, BLD 10 RM 220 & 227 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | IN: SUMMER 2009 SMART ROOM UPGRADES, BLD 10 RM 220 & 227 | 010 | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0003045 Total | [7 empty] | 1030.632 | 0 | 2460.624 | 2460.624
PJ0003044 | SUMMER 2009 SMARTROOM UPGRADES, BLDGS 2, 5, 22, 26, 53 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | CA: SMARTROOM UPGRADES IN VARIOUS ROOMS IN SEVERAL BLGS. | GENERAL | CLOSED | 2436.72 | 0 | 4689.3554 | 4689.3554
PJ0003044 | SUMMER 2009 SMARTROOM UPGRADES, BLDGS 2, 5, 22, 26, 53 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003044 | SUMMER 2009 SMARTROOM UPGRADES, BLDGS 2, 5, 22, 26, 53 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | EL: SMARTROOM UPGRADES FOR VARIOUS ROOMS IN SEVERAL BLGS. | GENERAL | CLOSED | 0 | 0 | 23991.9923 | 23991.9923
PJ0003044 | SUMMER 2009 SMARTROOM UPGRADES, BLDGS 2, 5, 22, 26, 53 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | IN: SUMMER 2009 SMARTROOM UPGRADES, BLDGS 2, 5, 22, 26, 53 | GENERAL | CLOSED | 265.104 | 0 | 132.552 | 132.552
PJ0003044 | SUMMER 2009 SMARTROOM UPGRADES, BLDGS 2, 5, 22, 26, 53 (NO EST) | LAMPMAN, GREG | CLOSED | 2009-02-02 | PA: PAINT ROOMS IN SERVERAL BLGS. FOR SMARTROOM UPGRADES | GENERAL | CLOSED | 0 | 0 | 690.72 | 690.72
PJ0003044 Total | [7 empty] | 2701.824 | 0 | 29504.6197 | 29504.6197
PJ0003043 | ROOM PREP FOR NEW PROFESSOR - BLD 47 RM 25N | POPHAM, DONALD J. | CLOSED | 2009-01-27 | CA:DISCONNECT SHELVING FROM WALL - 047 - 25N | 047 | CLOSED | 126.8202 | 0 | 206.478 | 206.478
PJ0003043 | ROOM PREP FOR NEW PROFESSOR - BLD 47 RM 25N | POPHAM, DONALD J. | CLOSED | 2009-01-27 | CP: PROJECT CONTINGENCY | 047 | CLOSED | 15.86 | 0 | 0 | 0
PJ0003043 | ROOM PREP FOR NEW PROFESSOR - BLD 47 RM 25N | POPHAM, DONALD J. | CLOSED | 2009-01-27 | CU: STRIP AND WAX OFFICE FLOOR AT 047-25N | 047 | CLOSED | 0 | 0 | 150.315 | 150.315
PJ0003043 | ROOM PREP FOR NEW PROFESSOR - BLD 47 RM 25N | POPHAM, DONALD J. | CLOSED | 2009-01-27 | MO:MOVE OFFICE FURNITURE FOR PAINTING - 47-25N - 3/27/2009 | 047 | CLOSED | 31.5 | 0 | 22.728 | 22.728
PJ0003043 | ROOM PREP FOR NEW PROFESSOR - BLD 47 RM 25N | POPHAM, DONALD J. | CLOSED | 2009-01-27 | PA: PAINT OFFICE - FON 47-25N (MAINT) | 047 | CLOSED | 0 | 0 | 381.28 | 381.28
PJ0003043 Total | [7 empty] | 174.1802 | 0 | 760.801 | 760.801
PJ0003041 | REMOVE CARPET - BLD 20 RM 119 | MAY, TOM | CLOSED | 2009-01-22 | CA:REMOVE CARPET IN 20-119 | 020 | CLOSED | 1046.223 | 0 | 1309.2972 | 1309.2972
PJ0003041 | REMOVE CARPET - BLD 20 RM 119 | MAY, TOM | CLOSED | 2009-01-22 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 88.88 | 0 | 0 | 0
PJ0003041 | REMOVE CARPET - BLD 20 RM 119 | MAY, TOM | CLOSED | 2009-01-22 | MO:MOVE OUT CABINETS FOR CARPET REMOVAL 20-119 | 020 | CLOSED | 15.75 | 0 | 22.728 | 22.728
PJ0003041 Total | [7 empty] | 1150.853 | 0 | 1332.0252 | 1332.0252
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | CA: OPEN HOUSE SUPPORT - INSTALL CP BANNER & BARRICADES | GENERAL | CLOSED | 1476.8 | 0 | 1015.3 | 1015.3
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | CU: CUSTODIAL SUPPORT FOR OPEN HOUSE EVENT ON 4/18 | GENERAL | CLOSED | 0 | 0 | 2993.925 | 2993.925
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | EL: ELCTRICIAN SUPPORT FOR OPEN HOUSE EVENT ON 4/18 | GENERAL | CLOSED | 0 | 0 | 1284.735 | 1284.735
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | IN:PERMIT FOR TENT/STAGE INSTALL AT DEXTER LAWN-2009 OPEN HOUSE | 034 | CLOSED | 0 | 0 | 41.4225 | 41.4225
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | LA: OPEN HOUSE SUPPORT APR 16-18 | GENERAL | CLOSED | 0 | 0 | 6186.4382 | 6186.4382
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | MC: MOVE FLAGS AND BANNERS TO REC CENTER FRI APR 15 | GENERAL | CLOSED | 0 | 0 | 9.47 | 9.47
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | PL: PLUMBING SUPPORT FOR OPEN HOUSE ON APRIL 18 | GENERAL | CLOSED | 0 | 0 | 1168.568 | 1168.568
PJ0003038 | 2009 STUDENT LIFE & LEADERSHIP OPEN HOUSE 4/18 - (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-22 | SUPPLY RENTAL: TRASH & RECYCLE CANS OPEN HOUSE APR 16 | GENERAL | CLOSED | 0 | 0 | 60 | 60
PJ0003038 Total | [7 empty] | 1476.8 | 0 | 12759.8587 | 12759.8587
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | AD: AIR POLLUTION CONTROL DISTRICT - 10 DAY NESHAPS NOTIFICATION | 038 | CLOSED | 385 | 0 | 385 | 385
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | AD: EARTH SYSTEMS - WELDING INSPECTIONS | 038 | CLOSED | 326 | 0 | 326 | 326
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | AD: ENGLEKIRK AND SABOL | 038 | CLOSED | 500 | 0 | 500 | 500
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | AD: FENCE FACTORY | 038 | CLOSED | 795 | 0 | 817.11 | 817.11
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | AD: JOC 10.020.003 STAPLES | 038 | CLOSED | 69503.02 | 0 | 69503.02 | 69503.02
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | CA: INSTALL LEAF GRATE ON GUTTERS - BLD 38 CHILDREN'S CTR PATIO | 038 | CLOSED | 516.0521 | 0 | 645.415 | 645.415
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | EH&S: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 (N/L) | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | EL:DISCONNECT ELECTRICAL - INSTALL NEW LIGHTING | 038 | CLOSED | 732.0993 | 0 | 685.62 | 685.62
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | IN: SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | 038 | CLOSED | 110.46 | 0 | 109.535 | 109.535
PJ0003037 | SR 10/11: REPLACE FLAT ROOF ON UPPER PATIO - BLD 38-125 | MOLLAN, CHERYL L. | CLOSED | 2009-01-21 | PA:PAINT STUCCO REPAIR ON BUILDING AND CONDUIT FOR PATIO COVER | 038 | CLOSED | 581.28 | 0 | 566.76 | 566.76
PJ0003037 Total | [7 empty] | 73448.9114 | 0 | 73538.46 | 73538.46
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | CA: SPRING COMMENCEMENT SETUP 6/8-6/16 | GENERAL | CLOSED | 2215.2 | 0 | 7497.136 | 7497.136
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | CA:INSTALL BANNER AND STAGE RAMP AT REC CENTER-6/12 | GENERAL | CLOSED | 664.56 | 0 | 416.898 | 416.898
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | CU: CUSTODIAL SUPPORT FOR 2009 SPRING COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 13504.4727 | 13504.4727
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | CU: CUSTODIAL SUPPORT FOR COSAM AND CAED POST COMMENCEMENT | 043 | CLOSED | 0 | 0 | 601.92 | 601.92
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | CU: REPAIR/REPLACE WHEEL ON COMMENCEMENT STAGING STAIRS | GENERAL | CLOSED | 0 | 0 | 35.97 | 35.97
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | EL: 2009 SPRING COMMENCEMENT SUPPORT - 6/13 & 6/14 | GENERAL | CLOSED | 0 | 0 | 1021.72 | 1021.72
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | ES:ENG SERVICES SUPPORT FOR 2009 SPRING COMMENCEMENT (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | IN: PERMIT FOR CANOPIES AT SPANOS STADIUM | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | IN: PERMIT FOR CANOPIES AT SPANOS STADIUM - 2009 COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 55.23 | 55.23
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | IN: PERMIT FOR CANOPY AT REC FIELD - AERO POST COMMENCEMENT | GENERAL | CLOSED | 0 | 0 | 82.845 | 82.845
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | LA: 2009 SPRING COMMENCEMENT SUPPORT - 6/13 & 6/14 | GENERAL | CLOSED | 0 | 0 | 7206.6985 | 7206.6985
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | MC: 2009 SPRING COMMENCEMENT SUPPORT | GENERAL | CLOSED | 0 | 0 | 449.825 | 449.825
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | PA: 2009 SPRING COMMENCEMENT SUPPORT (N/L) | GENERAL | CLOSED | 0 | 0 | 83.52 | 83.52
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | PL: 2009 SPRING COMMENCEMENT SUPPORT 6/13- 6/14 | GENERAL | CLOSED | 0 | 0 | 3755.3026 | 3755.3026
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: AERO POST COMMENCEMENT - 6/12 | GENERAL | CLOSED | 0 | 0 | 48 | 48
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: AGRIBUSINESS POST COMMENCEMENT-6/14 | 010 | CLOSED | 0 | 0 | 110 | 110
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: CE/ENVE POST COMMENCEMENT - 6/13 | GENERAL | CLOSED | 0 | 0 | 46 | 46
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: COMPUTER ENGR POST COMMENCEMENT - 6/12 | GENERAL | CLOSED | 0 | 0 | 46 | 46
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: COMUTER SCI POST COMMENCEMENT - 6/13 | 034 | CLOSED | 0 | 0 | 40 | 40
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: CONST MGT PST COMMENCEMENT-6/13 | 186 | CLOSED | 0 | 0 | 55 | 55
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: EHS POST COMMENCEMENT - 6/14 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: ELEC ENGR POST COMMENCEMENT - 6/12 | 034 | CLOSED | 0 | 0 | 43 | 43
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: FSN POST COMMENCEMENT - 6/12 | 022 | CLOSED | 0 | 0 | 54 | 54
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: GRC POST COMMENCEMENT - 6/14 | 014 | CLOSED | 0 | 0 | 51 | 51
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: HISTORY POST COMMENCEMENT - 6/14 | 034 | CLOSED | 0 | 0 | 51 | 51
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: JOURNALISM POST COMMENCEMENT - 6/14 | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: MATE POST COMMENCEMENT - 6/13 | GENERAL | CLOSED | 0 | 0 | 52 | 52
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: MECH ENGR POST COMMENCEMENT - 6/13 | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: OCOB POST COMMENCEMENT - 6/14 | GENERAL | CLOSED | 0 | 0 | 47 | 47
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: POLITICAL SCIENCE POST COMMENCEMENT-6/14 | 052 | CLOSED | 0 | 0 | 52 | 52
PJ0003035 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2009" (MAINT) | POPHAM, DONALD J. | CLOSED | 2009-01-20 | SUPPLY RENTAL: SOC SCI. POST COMMENCEMENT - 6/14/2009 | 035 | CLOSED | 0 | 0 | 52 | 52
PJ0003035 Total | [7 empty] | 2879.76 | 0 | 35458.5378 | 35458.5378
PJ0003034 | COMMUNICATION CABLE PREP & INSTALLATION - BLDG 26 RM 301 | MAY, TOM | CLOSED | 2009-01-16 | AD: QUAGLINO ROOFING | 026 | CLOSED | 535 | 0 | 271.78 | 271.78
PJ0003034 | COMMUNICATION CABLE PREP & INSTALLATION - BLDG 26 RM 301 | MAY, TOM | CLOSED | 2009-01-16 | CA:CUT HOLE AND INSTALL CONDUIT IN BLDG 26 ROOF | 026 | CLOSED | 1489.4028 | 0 | 968.166 | 968.166
PJ0003034 | COMMUNICATION CABLE PREP & INSTALLATION - BLDG 26 RM 301 | MAY, TOM | CLOSED | 2009-01-16 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 202.43 | 0 | 0 | 0
PJ0003034 Total | [7 empty] | 2226.8328 | 0 | 1239.946 | 1239.946
PJ0003033 | CONVERT TO OFFICE SPACE; REPLACE CARPET - UU BLD 65 RM 111F | POPHAM, DONALD J. | CLOSED | 2009-01-14 | AD: INNOVATIONS COMMERCIAL FLOORING | 065 | CLOSED | 4454.3137 | 0 | 4586.1056 | 4586.1056
PJ0003033 | CONVERT TO OFFICE SPACE; REPLACE CARPET - UU BLD 65 RM 111F | POPHAM, DONALD J. | CLOSED | 2009-01-14 | CA: REMOVE COVE BASE IN BLG. 65, RM 111F AND 111G | 065 | CLOSED | 126.8202 | 0 | 147.2886 | 147.2886
PJ0003033 | CONVERT TO OFFICE SPACE; REPLACE CARPET - UU BLD 65 RM 111F | POPHAM, DONALD J. | CLOSED | 2009-01-14 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 458.14 | 0 | 0 | 0
PJ0003033 | CONVERT TO OFFICE SPACE; REPLACE CARPET - UU BLD 65 RM 111F | POPHAM, DONALD J. | CLOSED | 2009-01-14 | IN: PERMIT REPLACE CARPET - UU BLD 65 RM 111F | 065 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0003033 Total | [7 empty] | 5039.2739 | 0 | 4799.6702 | 4799.6702
PJ0003031 | SP 08/09: INSTALL PC POWER MANAGEMENT SOFTWARE ON 1454 COMPUTERS | ELLIOT, DENNIS K | CLOSED | 2009-01-14 | AD: SCIENCE APPLICATIONS INTERNATIONAL, INC. | GENERAL | CLOSED | 11354.626 | 0 | 11235.4708 | 11235.4708
PJ0003031 | SP 08/09: INSTALL PC POWER MANAGEMENT SOFTWARE ON 1454 COMPUTERS | ELLIOT, DENNIS K | CLOSED | 2009-01-14 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0003031 Total | [7 empty] | 11354.626 | 0 | 11235.4708 | 11235.4708
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | ANTS: FIRE ALARM PANEL ASSISTANCE | 083 | CLOSED | 0 | 0 | 371.592 | 371.592
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | CA: INSTALL SPEED BUMPS IN DAIRY DRIVEWAY | 083 | CLOSED | 3106.08 | 0 | 2290.632 | 2290.632
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | CP: PROJECT CONTINGENCY | 083 | CLOSED | 8893.92 | 0 | 0 | 0
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | EL: ELECTRICAL SUPPORT | 083 | CLOSED | 0 | 0 | 666.162 | 666.162
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | EL: LOCATE & MARK ALL UTILITIES IMPACTED BY TRENCHING FOR NEW | 083 | CLOSED | 0 | 0 | 285.498 | 285.498
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | EL: SHUT DOWN TRANSFORMER FEEDING CORP WHSE. BLDG. 82 - 6/21/10 | 083 | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | ES: LOCATE & MARK ALL UTILITIES IMPACTED BY TRENCHING (N/L) | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | LA: LOCATE AND MARK UTILITIES IMPACTED BY TRENCHING (N/L) | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | PL: GAS SHUTDOWN ON MT. BISHOP RD. 4/29/10 - 8 AM TO 2 PM | 083 | CLOSED | 0 | 0 | 381.456 | 381.456
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | PL: LOCATE & MARK ALL UTILITIES IMPACTED BY TRENCHING (N/L) | 083 | CLOSED | 0 | 0 | 0 | 0
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | PL: REPAIR BROKEN 8" WATER LINE | 083 | CLOSED | 0 | 0 | 967.53 | 967.53
PJ0003030 | MJ: IN-HOUSE SUPPORT FOR TECH PARK - BLDG 83 | QUEEN, BARBARA | CLOSED | 2009-01-12 | PL: SUPPORT FOR TECH PARK PROJECT | 083 | CLOSED | 0 | 0 | 4299.528 | 4299.528
PJ0003030 Total | [7 empty] | 12000 | 0 | 9389.286 | 9389.286
PJ0003029 | RENOVATE RMS:FREMONT,MUIR,TRINITY 105,107,109 (FURN. FROM PCV) | MAY, TOM | CLOSED | 2009-01-09 | AD: JOC 08.017.002 MAINO | RESIDENCE | CLOSED | 376901.3368 | 0 | 376901.3368 | 376901.3368
PJ0003029 | RENOVATE RMS:FREMONT,MUIR,TRINITY 105,107,109 (FURN. FROM PCV) | MAY, TOM | CLOSED | 2009-01-09 | CA: DOORSTOPS AT MUIR AND TRINITY | RESIDENCE | CLOSED | 2215.2 | 0 | 1600.182 | 1600.182
PJ0003029 | RENOVATE RMS:FREMONT,MUIR,TRINITY 105,107,109 (FURN. FROM PCV) | MAY, TOM | CLOSED | 2009-01-09 | CP: PROJECT CONTINGENCY | 107 | CLOSED | 8473.94 | 0 | 0 | 0
PJ0003029 | RENOVATE RMS:FREMONT,MUIR,TRINITY 105,107,109 (FURN. FROM PCV) | MAY, TOM | CLOSED | 2009-01-09 | IN:RENOVATE RMS IN MUIR & TRINITY 105 & 107 (FURNITURE FROM PCV) | RESIDENCE | CLOSED | 397.656 | 0 | 430.794 | 430.794
PJ0003029 | RENOVATE RMS:FREMONT,MUIR,TRINITY 105,107,109 (FURN. FROM PCV) | MAY, TOM | CLOSED | 2009-01-09 | LO:INSTALL ORANGE CORES FOR MAINO MUIR/TRINITY | RESIDENCE | CLOSED | 114.336 | 0 | 57.168 | 57.168
PJ0003029 Total | [7 empty] | 388102.4688 | 0 | 378989.4808 | 378989.4808
PJ0003027 | SP 08/09: SPANOS STADIUM ELEVATOR REPAIRS - BLD 61 | PAHLOW, BOB | CLOSED | 2009-01-08 | AD: REPUBLIC ELEVATOR | 061 | CLOSED | 0 | 0 | 22559.88 | 22559.88
PJ0003027 | SP 08/09: SPANOS STADIUM ELEVATOR REPAIRS - BLD 61 | PAHLOW, BOB | CLOSED | 2009-01-08 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 30000 | 0 | 0 | 0
PJ0003027 Total | [7 empty] | 30000 | 0 | 22559.88 | 22559.88
PJ0003026 | REPLACE LIGHT POLES BEHIND SIERRA MADRE & YOSEMITE (MAINT) | POLVI, STEVEN | CLOSED | 2009-01-08 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 0 | 0 | 0 | 0
PJ0003026 | REPLACE LIGHT POLES BEHIND SIERRA MADRE & YOSEMITE (MAINT) | POLVI, STEVEN | CLOSED | 2009-01-08 | EL: REPLACE LIGHT POLES ON SERIVICE ROAD BEHIND SIERRA MADRE | RESIDENCE | CLOSED | 0 | 0 | 38937.0422 | 38937.0422
PJ0003026 | REPLACE LIGHT POLES BEHIND SIERRA MADRE & YOSEMITE (MAINT) | POLVI, STEVEN | CLOSED | 2009-01-08 | EO:ASSIST ELECTRICIANS W/ LIGHT POLE REPLACEMENT BEHIND SM & YOS | RESIDENCE | CLOSED | 0 | 0 | 2026.91 | 2026.91
PJ0003026 Total | [7 empty] | 0 | 0 | 40963.9522 | 40963.9522
PJ0003025 | PREP & PAINT OUTFIELD FENCE @ BASEBALL STADIUM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-01-07 | CA: REMOVE BANNERS AT BASEBALL FIELD FENCE | 160 | CLOSED | 1157.6 | 0 | 3087.25 | 3087.25
PJ0003025 | PREP & PAINT OUTFIELD FENCE @ BASEBALL STADIUM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-01-07 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0003025 | PREP & PAINT OUTFIELD FENCE @ BASEBALL STADIUM (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2009-01-07 | PA: PREP AND PAINT BASEBALL FIELD OUTFIELD FENCE | 160 | CLOSED | 4312.8 | 0 | 3952.94 | 3952.94
PJ0003025 Total | [7 empty] | 5470.4 | 0 | 7040.19 | 7040.19
PJ0003024 | SUPPORT NEW TANKNET MONITOR INSTALLATION - BLD 17 PILOT WINERY | VELARDE, DENIS L | CLOSED | 2009-01-07 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 68.07 | 0 | 0 | 0
PJ0003024 | SUPPORT NEW TANKNET MONITOR INSTALLATION - BLD 17 PILOT WINERY | VELARDE, DENIS L | CLOSED | 2009-01-07 | EL: INSTALL ELECTRICAL FOR TANKNET MONITOR AT WINELAB | 017 | CLOSED | 680.664 | 0 | 442.8 | 442.8
PJ0003024 Total | [7 empty] | 748.734 | 0 | 442.8 | 442.8
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 01/09 - CLEAN THEATRE RESTROOMS BY 6:00PM (NO LABOR) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 01/30 - CLEAN THEATRE RESTROOMS BY 6:00PM (NO LABOR) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 01/31 - CLEAN THEATRE, RESTROOMS BY 6:00PM (NO LABOR) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/01 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/05 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/06 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/07 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/26 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/27 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 02/28 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/05 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/06 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/07 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/07 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/13 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/14 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/15 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/19 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/21 - CLEAN THEATRE, RESTROOMS BY 9:00AM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/27 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/28 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/28 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 03/29 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/011 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 140.832 | 140.832
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/02 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/03 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/04 - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/05 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/17 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/18 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/19 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/22 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/23 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/24 - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/25 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 04/26 - CLEAN THEATRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: 08/09 SPANOS THEATRE CUSTODIAL SUPPORT - 6/28 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CLEAN UP SPANOS THEATER AND RESTROOMS - 5/14 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER EVENT - 5/20 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER EVENT - 5/21 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER EVENT - 5/31 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER EVENT ON 5/30 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER ON 5/22 | 044 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER ON 5/28 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: CUSTODIAL SUPPORT FOR SPANOS THEATER ON 5/29 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: EVENT CLEAN AT SPANOS THEATER - 5/15 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: SPANOS THEATER CLEAN UP AFTER EVENT - 5/16 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 | 08/09 EXTRA CLEANING, 044 THEATRE-WINTER QTR 2009 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2009-01-07 | CU: SPANOS THEATER EVENT SUPPORT ON MAY 17 BY NOON | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0003023 Total | [7 empty] | 0 | 0 | 3069.324 | 3069.324
PJ0003022 | SP 08/09: HOT WATER MASTER PLAN UPDATE - BLDG 40 | ELLIOT, DENNIS K | CLOSED | 2009-01-05 | AD: SALAS O'BRIEN ENGINEERS | 040 | CLOSED | 41173.6 | 0 | 41173.6 | 41173.6
PJ0003022 | SP 08/09: HOT WATER MASTER PLAN UPDATE - BLDG 40 | ELLIOT, DENNIS K | CLOSED | 2009-01-05 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0003022 Total | [7 empty] | 41173.6 | 0 | 41173.6 | 41173.6
PJ0003017 | RELOCATE OFFICE FURNITURE IN ADMIN 01 FROM RM 132 TO 129A | MAY, TOM | CLOSED | 2008-12-11 | AD: RUSSCO | 001 | CLOSED | 1071.97 | 0 | 1371.55 | 1371.55
PJ0003017 | RELOCATE OFFICE FURNITURE IN ADMIN 01 FROM RM 132 TO 129A | MAY, TOM | CLOSED | 2008-12-11 | CA:INSTALL RAILS, WHITE BOARD AND MIRROR ADM 129A | 001 | CLOSED | 221.52 | 0 | 222.9928 | 222.9928
PJ0003017 | RELOCATE OFFICE FURNITURE IN ADMIN 01 FROM RM 132 TO 129A | MAY, TOM | CLOSED | 2008-12-11 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 143.15 | 0 | 0 | 0
PJ0003017 | RELOCATE OFFICE FURNITURE IN ADMIN 01 FROM RM 132 TO 129A | MAY, TOM | CLOSED | 2008-12-11 | CU:CARPET CLEANING ADM 129A | 001 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0003017 | RELOCATE OFFICE FURNITURE IN ADMIN 01 FROM RM 132 TO 129A | MAY, TOM | CLOSED | 2008-12-11 | MO:ASSIST IN MOVE IN ADM 132 | 001 | CLOSED | 63 | 0 | 45.456 | 45.456
PJ0003017 Total | [7 empty] | 1499.64 | 0 | 1738.3868 | 1738.3868
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | AD: SAFETY GLASSES FROM FACILITIES WAREHOUSE | 043 | CLOSED | 0 | 0 | 93.3984 | 93.3984
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | ANTS: PROGRAM ALAM POINTS FOR NEW FIRE ALARM PANEL IN 43-109 | 043 | CLOSED | 0 | 0 | 1659.768 | 1659.768
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | ANTS: PROGRAM SECURITY ALARM AT REC CENTER POOL - 043C | 043C | CLOSED | 0 | 0 | 72.072 | 72.072
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | ANTS: TEST NEW FIRE ALARM PANEL AND DEVICES IN BLG. 43A | 043 | CLOSED | 0 | 0 | 628.848 | 628.848
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: BUILD FIRE HOSE PROTECTORS FOR TEMP WATER FEED - REC. CTR. | 043 | CLOSED | 0 | 0 | 293.184 | 293.184
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: CORE HOLES IN THE CMU AT ANDERSON POOL CHEMICAL ROOM | 043 | CLOSED | 0 | 0 | 526.212 | 526.212
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: FABRICATE AND INSTALL PLAN TABLE - BLG. 43 RM. 101 | 043 | CLOSED | 0 | 0 | 648.708 | 648.708
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: HANG BULLETIN BOARD IN BLDG. 43A ROOM 150 | 043 | CLOSED | 0 | 0 | 166.14 | 166.14
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: INSTALL (2) TEMPORARY UTILITY POLES IN G-2 PARKING LOT | 043 | CLOSED | 0 | 0 | 2235.882 | 2235.882
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: PROVIDE (1) 4' X 8' SHEET OF PLYWOOD FOR BARRIER AT POOL | 043 | CLOSED | 0 | 0 | 119.274 | 119.274
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: REPAIR GATE ON CAMPUS WAY BTWN HEALTH CTR AND REC CTR | 043 | CLOSED | 225.552 | 0 | 262.476 | 262.476
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: SIGNAGE FOR REC. CENTER EXPANSION PROJECT | 043 | CLOSED | 0 | 0 | 913.866 | 913.866
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CA: SIGNAGE FOR TEMPORARY WALKWAY CLOSURES - REC CENTER | 043 | CLOSED | 0 | 0 | 188.364 | 188.364
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 86978.43 | 0 | 0 | 0
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CPE: CENTRAL PLANT SUPPORT FOR REC CENTER EXPANSION | 043 | CLOSED | 0 | 0 | 561.42 | 561.42
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CPE: INSPECTION OF IRON CONTENT FOR CHW - REC. CTR. EXPANSION PJ | 043 | CLOSED | 0 | 0 | 525.354 | 525.354
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CU: CUSTODIAL SUPPORT FOR REC CTR EXPANSION JAN 2010 - JAN 2012 | 043 | CLOSED | 0 | 0 | 1617.63 | 1617.63
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | CU: PROVIDE MATS (NL) - MOTT GYM HALLWAY FOR SWIM TEAM TRAFFIC | 043 | CLOSED | 0 | 0 | 562.476 | 562.476
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | EL: CHECK ELECT UTILITIES IN POT HOLED LOCATIONS - REC CTR PLAZA | 043 | CLOSED | 0 | 0 | 1057.974 | 1057.974
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | EL: ELECTRICAL SUPPORT FOR REC CTR EXPANSION JAN 2010 - JAN 2012 | 043 | CLOSED | 0 | 0 | 21753.5424 | 21753.5424
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | EL: INSTALL 2 LIGHT FIXTURES IN HALLWAY NEAR RM 190 - REC CTR 43 | 043 | CLOSED | 0 | 0 | 851.172 | 851.172
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | EL: RAISE TELECOM LINE TO CLEAR TOP OF NEW STORAGE BLDG. | 043 | CLOSED | 0 | 0 | 63.444 | 63.444
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | EO: POT HOLE FOR ELECTRICAL UTILITIES AT REC. CTR. PLAZA | 043 | CLOSED | 0 | 0 | 1710.768 | 1710.768
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | ES: GENERATE & PROVIDE HVAC ALARM REPORT DURING COMMISSIONING | 043 | CLOSED | 374.616 | 0 | 499.488 | 499.488
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | ES: REC CENTER ICE MACHINE IS FLOODING | 043 | CLOSED | 0 | 0 | 62.436 | 62.436
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | ES: SUPPORT REC. CENTER EXPANSION PROJECT | 043 | CLOSED | 0 | 0 | 5895.3162 | 5895.3162
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | INSTALL NEW FIRE ALARM PANEL AND DEVICES IN 43A | 043 | CLOSED | 18021.5729 | 0 | 12839.5632 | 12839.5632
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LA: REC SPORTS EXPANSION SUPPORT | 043 | CLOSED | 0 | 0 | 4805.5654 | 4805.5654
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LA:LOCATE IRRIGATION LINES & PERFORM NEEDED REPAIRS-REC CTR EXP. | 043 | CLOSED | 0 | 0 | 12972.141 | 12972.141
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: 4 ADDITIONAL ORANGE CORE PADLOCKS -REC CTR CONSTRUCTION SITE | 043 | CLOSED | 0 | 0 | 369.168 | 369.168
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: INSTALL EXTERIOR DOOR HANDLE AT TEMP. HDCP ENTRANCE | 043 | CLOSED | 0 | 0 | 171.504 | 171.504
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: INSTALL LOCKS IN LOCKER RM ENTRANCE & STORAGE RM DOORS - 043 | 043 | CLOSED | 0 | 0 | 85.752 | 85.752
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: INSTALL LOCKSET/CORE ON ASI STORAGE BLDG NEAR HEALTH CENTER | 043 | CLOSED | 0 | 0 | 28.584 | 28.584
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: LOCK MODIFICATIONS REQUESTED BY ASI - REC CENTER 043 | 043 | CLOSED | 0 | 0 | 5431.542 | 5431.542
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: PROJECT KEYING DESIGN AND INSTALLATION - REC CTR EXPANSION | 043 | CLOSED | 0 | 0 | 26616.396 | 26616.396
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: PROVIDE 6 ORANGE CORE PADLOCKS FOR REC CTR CONSTRUCTION SITE | 043 | CLOSED | 0 | 0 | 496.584 | 496.584
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: REMOVE CORE FROM CUSTODIAL CLOSET AT REC. CENTER | 043 | CLOSED | 0 | 0 | 85.752 | 85.752
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | LO: REPAIR AUTOMATIC DOOR CLOSURE - BLDG. 43A KINESIOLOGY | 043A | CLOSED | 0 | 0 | 114.336 | 114.336
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | MO: MOVE AND STORE LOST AND FOUND ITEMS FROM REC CENTER | 043 | CLOSED | 0 | 0 | 373.416 | 373.416
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | MO: MOVE FURNITURE FROM EDES BLG. 186 TO REC. CTR. 43 | 043 | CLOSED | 0 | 0 | 45.456 | 45.456
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | MO: MOVE TEMP TICKET OFFICE FROM MOTT BACK TO REC CTR ON 1/31/12 | 043 | CLOSED | 0 | 0 | 54.324 | 54.324
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | MO: RETURN STORED EQUIPMENT TO KINESIOLOGY | 043 | CLOSED | 0 | 0 | 205.224 | 205.224
PJ0003013 | MJ: REC CENTER EXPANSION IN-HOUSE SUPPORT - BLDG 43 | JUDD, PERRY | CLOSED | 2008-12-04 | PL: PLUMBING SHOP ASSISTANCE FOR REC SPORTS EXPANSION | 043 | CLOSED | 0 | 0 | 44764.9946 | 44764.9946
PJ0003013 Total | [7 empty] | 105600.1709 | 0 | 152429.5152 | 152429.5152
PJ0003010 | STARBUCKS PUNCH LIST COMPLETION - BLDG 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-12-01 | CA: RECESS GYP BOARD AT SIDE HALLWAY ROLL UP DOOR | 065 | CLOSED | 184.6 | 0 | 170.09 | 170.09
PJ0003010 | STARBUCKS PUNCH LIST COMPLETION - BLDG 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-12-01 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 0 | 0 | 0 | 0
PJ0003010 | STARBUCKS PUNCH LIST COMPLETION - BLDG 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-12-01 | EL: PUNCH LIST WORK | 065 | CLOSED | 2864.8 | 0 | 2687.5703 | 2687.5703
PJ0003010 | STARBUCKS PUNCH LIST COMPLETION - BLDG 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-12-01 | ES: INSTALL REPLACEMENT REGISTERS | 065 | CLOSED | 589.8448 | 0 | 268.24 | 268.24
PJ0003010 | STARBUCKS PUNCH LIST COMPLETION - BLDG 65 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-12-01 | PA: REPAIR SMOOTH WALL SOFFIT AND PAINT | 065 | CLOSED | 2287.68 | 0 | 1890.6673 | 1890.6673
PJ0003010 Total | [7 empty] | 5926.9248 | 0 | 5016.5676 | 5016.5676
PJ0003007 | HVAC DESIGN-OFFICES/STORAGE/RECEPTION AREA FOR RISK MGT- BLDG 58 | LAMPMAN, GREG | CLOSED | 2008-11-25 | AD: GOSS ENGINEERING | 058 | CLOSED | 4280 | 0 | 4280 | 4280
PJ0003007 | HVAC DESIGN-OFFICES/STORAGE/RECEPTION AREA FOR RISK MGT- BLDG 58 | LAMPMAN, GREG | CLOSED | 2008-11-25 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 428 | 0 | 0 | 0
PJ0003007 Total | [7 empty] | 4708 | 0 | 4280 | 4280
PJ0003006 | DESIGN FOR HARMON HALL ACOUSTIC RENOVATION - PAC 06 RM 101 | LAMPMAN, GREG | CLOSED | 2008-11-25 | AD: RRM GROUP (NO OVERHEAD) | 006 | CLOSED | 59950 | 0 | 49444.48 | 49444.48
PJ0003006 | DESIGN FOR HARMON HALL ACOUSTIC RENOVATION - PAC 06 RM 101 | LAMPMAN, GREG | CLOSED | 2008-11-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0003006 Total | [7 empty] | 59950 | 0 | 49444.48 | 49444.48
PJ0003004 | REBUILD THE SPECIALTY PRINT LAB - GRC 26 RM 209 & BASEMENT AREA | MAY, TOM | CLOSED | 2008-11-25 | AD: CREDIT CARD PURCHASE | 026 | CLOSED | 0 | 0 | 1479.54 | 1479.54
PJ0003004 | REBUILD THE SPECIALTY PRINT LAB - GRC 26 RM 209 & BASEMENT AREA | MAY, TOM | CLOSED | 2008-11-25 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 452.93 | 0 | 0 | 0
PJ0003004 | REBUILD THE SPECIALTY PRINT LAB - GRC 26 RM 209 & BASEMENT AREA | MAY, TOM | CLOSED | 2008-11-25 | EL:ELECTRICAL OUTLETS FOR 26-209 | 026 | CLOSED | 3137.76 | 0 | 5535.852 | 5535.852
PJ0003004 | REBUILD THE SPECIALTY PRINT LAB - GRC 26 RM 209 & BASEMENT AREA | MAY, TOM | CLOSED | 2008-11-25 | PL:HOOK UP SINK IN BASEMENT 26 | 026 | CLOSED | 1391.52 | 0 | 2188.3997 | 2188.3997
PJ0003004 Total | [7 empty] | 4982.21 | 0 | 9203.7917 | 9203.7917
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | CA: 2008 FALL COMMENCEMENT SUPPORT | 043 | CLOSED | 2769 | 0 | 3686.1373 | 3686.1373
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | CU: CUSTODIAL SUPPORT FOR 2008 FALL COMMENCEMENT | 043 | CLOSED | 0 | 0 | 6317.025 | 6317.025
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | EL: 2008 FALL COMMENCEMENT SUPPORT ON 12/13 8-6 | 043 | CLOSED | 0 | 0 | 507.35 | 507.35
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | LA: 2008 FALL COMMENCEMENT SUPPORT | 043 | CLOSED | 0 | 0 | 2822.443 | 2822.443
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | MC: 2008 FALL COMMENCEMENT SUPPORT 12/8-12/15 | 043 | CLOSED | 0 | 0 | 421.415 | 421.415
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | PA: TOUCH UP STAGE FOR COMMENCEMENT 12/12 | 043 | CLOSED | 0 | 0 | 331.87 | 331.87
PJ0003001 | PROVIDE SERVICES FOR 2008 "FALL COMMENCEMENT" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-11-18 | PL: 2008 FALL COMMENCEMENT SUPPORT | 043 | CLOSED | 0 | 0 | 1062.7463 | 1062.7463
PJ0003001 Total | [7 empty] | 2769 | 0 | 15148.9866 | 15148.9866
PJ0002999 | EVALUATE REMOVAL OF CARPET & GLUE FROM 1/2 OF ROOM- ATL 07-19 | POPHAM, DONALD J. | CLOSED | 2008-11-05 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 0 | 0 | 0 | 0
PJ0002999 | EVALUATE REMOVAL OF CARPET & GLUE FROM 1/2 OF ROOM- ATL 07-19 | POPHAM, DONALD J. | CLOSED | 2008-11-05 | IN: REMOVE CARPET AND MASTIC AT ATL ROOM 019 | 007 | CLOSED | 0 | 0 | 99.414 | 99.414
PJ0002999 Total | [7 empty] | 0 | 0 | 99.414 | 99.414
PJ0002998 | INSTALL BOLLARDS @ LAWN - PAC 06 (NO ESTIMATE REQUIRED) | MEAD, GEORGE | CLOSED | 2008-11-07 | CA: INSTALL FOOTINGS FOR BOLLARDS AT PAC | 006 | CLOSED | 1107.6 | 0 | 6695.8294 | 6695.8294
PJ0002998 | INSTALL BOLLARDS @ LAWN - PAC 06 (NO ESTIMATE REQUIRED) | MEAD, GEORGE | CLOSED | 2008-11-07 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002998 | INSTALL BOLLARDS @ LAWN - PAC 06 (NO ESTIMATE REQUIRED) | MEAD, GEORGE | CLOSED | 2008-11-07 | LA: MOVE IRRIGATION LINES TO ACCOMODATE BOLLARDS AT PAC | 006 | CLOSED | 0 | 0 | 435.35 | 435.35
PJ0002998 Total | [7 empty] | 1107.6 | 0 | 7131.1794 | 7131.1794
PJ0002997 | MJ:CUSTODIAL STORAGE UNDER 2 STAIRWELLS (TRACKING, ONLY)EDES 186 | GRIFFIN, PATRICK E | CLOSED | 2008-11-06 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 426.31 | 0 | 0 | 0
PJ0002997 | MJ:CUSTODIAL STORAGE UNDER 2 STAIRWELLS (TRACKING, ONLY)EDES 186 | GRIFFIN, PATRICK E | CLOSED | 2008-11-06 | IN:CUSTODIAL STORAGE UNDER STAIRWELL AT EDES - 186 | 186 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0002997 Total | [7 empty] | 426.31 | 0 | 66.276 | 66.276
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | AD: INNOVATION COMMERCIAL FLOORING, INC. | 014 | CLOSED | 4280 | 0 | 3198.6794 | 3198.6794
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 1070 | 0 | 2268.4 | 2268.4
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | CA: REMODEL 14 - 256 | 014 | CLOSED | 7476.6 | 0 | 8805.501 | 8805.501
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 1359.02 | 0 | 0 | 0
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | EL:INSTALL T-BAR LIGHTS AND ELECTRICAL IN 14-256 | 014 | CLOSED | 8958.3 | 0 | 4901.4642 | 4901.4642
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | ES: PURCHASE AND INSTALL REGISTER GRILLS IN 14-256 | 014 | CLOSED | 876.288 | 0 | 758.256 | 758.256
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | IN: UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | 014 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | PA:PAINT 14-256 | 014 | CLOSED | 2015.76 | 0 | 1315.416 | 1315.416
PJ0002996 | UPGRADE COMPUTER SCIENCE LABS - COMP SCI 14 RM 255/256/257 | MAY, TOM | CLOSED | 2008-11-05 | PL: PURCHASE AND INSTALL SINK AND FAUCET IN 14-238F | 014 | CLOSED | 1048.608 | 0 | 1654.608 | 1654.608
PJ0002996 Total | [7 empty] | 27217.128 | 0 | 23034.8766 | 23034.8766
PJ0002995 | SR 08/09:PUMP STATN FILTER SYS REPAIR/FLOW SENSOR INSTALL-FIELDS | LOOSLEY, SCOTT L. | CLOSED | 2008-11-04 | AD: FLUID RESOURCE MANAGEMENT | 163 | CLOSED | 12400 | 0 | 14336.01 | 14336.01
PJ0002995 | SR 08/09:PUMP STATN FILTER SYS REPAIR/FLOW SENSOR INSTALL-FIELDS | LOOSLEY, SCOTT L. | CLOSED | 2008-11-04 | CP: PROJECT CONTINGENCY | 163 | CLOSED | 1255.86 | 0 | 0 | 0
PJ0002995 Total | [7 empty] | 13655.86 | 0 | 14336.01 | 14336.01
PJ0002994 | LANDSCAPE SHOP INSTALLATIONS/MODIFICATIONS & FURNISHINGS-PCV 171 | STEWART, GLENN S | CLOSED | 2008-11-04 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 1722.41 | 0 | 0 | 0
PJ0002994 | LANDSCAPE SHOP INSTALLATIONS/MODIFICATIONS & FURNISHINGS-PCV 171 | STEWART, GLENN S | CLOSED | 2008-11-04 | EL: LANDSCAPE SHOP MODIFICATIONS AT PCV | 171 | CLOSED | 4470.8107 | 0 | 95.166 | 95.166
PJ0002994 | LANDSCAPE SHOP INSTALLATIONS/MODIFICATIONS & FURNISHINGS-PCV 171 | STEWART, GLENN S | CLOSED | 2008-11-04 | LO: LANDSCAPE SHOP MODIFICATIONS AT PCV | 171 | CLOSED | 1873.835 | 0 | 531.168 | 531.168
PJ0002994 | LANDSCAPE SHOP INSTALLATIONS/MODIFICATIONS & FURNISHINGS-PCV 171 | STEWART, GLENN S | CLOSED | 2008-11-04 | PCV CA: LANDSCAPE SHOP MODIFICATIONS AT PCV | 171 | CLOSED | 10845.0918 | 0 | 17774.4636 | 17774.4636
PJ0002994 | LANDSCAPE SHOP INSTALLATIONS/MODIFICATIONS & FURNISHINGS-PCV 171 | STEWART, GLENN S | CLOSED | 2008-11-04 | PCV EL: LANDSCAPE SHOP MODIFICATIONS AT PCV | 171 | CLOSED | 0 | 0 | 3978.6274 | 3978.6274
PJ0002994 | LANDSCAPE SHOP INSTALLATIONS/MODIFICATIONS & FURNISHINGS-PCV 171 | STEWART, GLENN S | CLOSED | 2008-11-04 | PCV PA: LANDSCAPE SHOP MODIFICATIONS AT PCV (NO LABOR) | 171 | CLOSED | 2398.9464 | 0 | 0 | 0
PJ0002994 Total | [7 empty] | 21311.094 | 0 | 22379.425 | 22379.425
PJ0002993 | 08/09 WRESTLING (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002993 | 08/09 WRESTLING (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: SUPPORT FOR WRESTING V. MENLO 11AM SFSU 12:45 | 042 | CLOSED | 0 | 0 | 790.02 | 790.02
PJ0002993 | 08/09 WRESTLING (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WRESTLING GREEN AND GOLD 11/5 AT 6:30 PM MOTT GYM | 042 | CLOSED | 0 | 0 | 338.58 | 338.58
PJ0002993 | 08/09 WRESTLING (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WRESTLING VS. BAKERSFIELD ON 1/09 AT 6:30PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0002993 | 08/09 WRESTLING (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WRESTLING VS. FULLERTON ON 1/14 AT 6:30PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0002993 | 08/09 WRESTLING (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WRESTLING VS. OKLAHOMA ST. ON 12/16 AT 6:30PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0002993 Total | [7 empty] | 0 | 0 | 2652.21 | 2652.21
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: CUSTODIAL SUPPORT FOR WOMENS BBALL TOURNEY - 11/28-11/30 | 042 | CLOSED | 0 | 0 | 1523.61 | 1523.61
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: W. BASKETBALL V. CSU MONTEREY BAY 1PM | 042 | CLOSED | 0 | 0 | 338.58 | 338.58
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: W. BBALL V. LOYOLA SUPPORT - DEC 03 7:30PM | 042 | CLOSED | 0 | 0 | 225.72 | 225.72
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: W. BBALL V. SFSU SUPPORT - DEC 07 2PM | 042 | CLOSED | 0 | 0 | 564.3 | 564.3
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: W. BBALL V. UCLA SUPPORT - NOV 26 7PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. BAKERSFIELD ON 2/28 AT 4PM | 042 | CLOSED | 0 | 0 | 677.16 | 677.16
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. CSU LONG BEACH ON 1/4 AT 4PM | 042 | CLOSED | 0 | 0 | 376.2 | 376.2
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. EAST. WASHINGTON ON 12/20 AT 2PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. FULLERTON ON 2/7 AT 4PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. IRVINE ON 2/5 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. NORTHRIDGE ON 2/26 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. PACIFIC ON 1/22 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. RIVERSIDE ON 1/2 AT 7PM | 042 | CLOSED | 0 | 0 | 338.58 | 338.58
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. UC DAVIS ON 1/24 AT 4PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 | 08/09 WOMEN'S BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: WOMEN'S BBALL VS. UCSB ON 2/14 AT 4PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002992 Total | [7 empty] | 0 | 0 | 7712.1 | 7712.1
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: M. BBALL V. ARKANSAS LITTLE 11/14 7PM | 042 | CLOSED | 0 | 0 | 594.198 | 594.198
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BB V ND DE NAMUR (EXHIBIT) 11/10 | 042 | CLOSED | 0 | 0 | 376.2 | 376.2
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL V SEATTLE 12/14 - 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS PACIFIC ON 2/28 AT 7PM | 042 | CLOSED | 0 | 0 | 633.744 | 633.744
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. BAKERSFIELD ON 2/25 AT 7PM | 042 | CLOSED | 0 | 0 | 376.2 | 376.2
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. BRACKET BUSTER TOURNEY ON 2/21 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. CSULB ON 3/5 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. FRESNO ST ON 12/29 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. FULLERTON ON 1/8 AT 8PM | 042 | CLOSED | 0 | 0 | 338.58 | 338.58
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. NORTHRIDGE ON 1/31 AT 6PM | 042 | CLOSED | 0 | 0 | 714.78 | 714.78
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. RIVERSIDE ON 3/7 AT 7PM | 042 | CLOSED | 0 | 0 | 489.06 | 489.06
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. UC DAVIS ON 2/18 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. UC IRVINE ON 1/10 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MEN'S BBALL VS. UCSB ON 1/17 AT 7PM | 042 | CLOSED | 0 | 0 | 507.87 | 507.87
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MENS BBAL V. SFSU - 7:30PM | 042 | CLOSED | 0 | 0 | 225.72 | 225.72
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CU: MENS BBALL VS. PORTLAND ST. ON 12/17 AT 7PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | EL: ELECTRICIAN SUPPORT FOR TELEVISED BBALL GAME 1/31/2009 | 042 | CLOSED | 0 | 0 | 432.48 | 432.48
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | EL: ELECTRICIAN SUPPORT FOR TELEVISED BBALL GAME 1/8/2009 | 042 | CLOSED | 0 | 0 | 561.432 | 561.432
PJ0002991 | 08/09 MENS BASKETBALL (SERVICES FOR ATHLETICS) - MOTT 42 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | POST BBALL GAME CLEAN UP - SWEEP AND MOP BLEACHERS | 042 | CLOSED | 0 | 0 | 790.02 | 790.02
PJ0002991 Total | [7 empty] | 0 | 0 | 9200.364 | 9200.364
PJ0002989 | M&R PARK 08/09: GENERAL MAINTENANCE OF PARKING STRUCTURE 130 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | AD: COASTAL JANITORIAL | 130 | CLOSED | 856 | 0 | 719.04 | 719.04
PJ0002989 | M&R PARK 08/09: GENERAL MAINTENANCE OF PARKING STRUCTURE 130 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | AD: GOLDEN STATE STRIPING | 130 | CLOSED | 5243 | 0 | 5243 | 5243
PJ0002989 | M&R PARK 08/09: GENERAL MAINTENANCE OF PARKING STRUCTURE 130 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CA:PERFORM MAINT ON PARKING STRUCT. EXPANSION JOINTS | 130 | CLOSED | 5964.3414 | 0 | 4250.0388 | 4250.0388
PJ0002989 | M&R PARK 08/09: GENERAL MAINTENANCE OF PARKING STRUCTURE 130 | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 1206.31 | 0 | 0 | 0
PJ0002989 Total | [7 empty] | 13269.6514 | 0 | 10212.0788 | 10212.0788
PJ0002985 | M&R PARK 08/09: RESTRIPE "H" PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2008-10-31 | AD: GOLDEN STATE SEALING AND STRIPING | GENERAL | CLOSED | 2921.1 | 0 | 2921.1 | 2921.1
PJ0002985 | M&R PARK 08/09: RESTRIPE "H" PARKING LOTS | POPHAM, DONALD J. | CLOSED | 2008-10-31 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 292.11 | 0 | 0 | 0
PJ0002985 Total | [7 empty] | 3213.21 | 0 | 2921.1 | 2921.1
PJ0002982 | CAME SECURITY INSTALLATION - LIB 35 2ND FLR | PAHLOW, BOB | CLOSED | 2008-10-30 | ANTS: PROGRAM ALARMS AT LIBRARY LEARNING COMMONS | 035 | CLOSED | 57.168 | 0 | 57.168 | 57.168
PJ0002982 | CAME SECURITY INSTALLATION - LIB 35 2ND FLR | PAHLOW, BOB | CLOSED | 2008-10-30 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 12.34 | 0 | 0 | 0
PJ0002982 | CAME SECURITY INSTALLATION - LIB 35 2ND FLR | PAHLOW, BOB | CLOSED | 2008-10-30 | IN: CAME SECURITY INSTALLATION - LIB 35 2ND FLR (N/L) | 035 | CLOSED | 66.276 | 0 | 0 | 0
PJ0002982 Total | [7 empty] | 135.784 | 0 | 57.168 | 57.168
PJ0002980 | REPLACE ENTRANCE DOOR W/ GLASS - ADMIN 01 RM 116 | GRIFFIN, PATRICK E | CLOSED | 2008-10-29 | CA: HANG NEW DOOR WITH VISION LIGHT AT ADMIN 116 | 001 | CLOSED | 1940.9585 | 0 | 1576.83 | 1576.83
PJ0002980 | REPLACE ENTRANCE DOOR W/ GLASS - ADMIN 01 RM 116 | GRIFFIN, PATRICK E | CLOSED | 2008-10-29 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 271.66 | 0 | 0 | 0
PJ0002980 | REPLACE ENTRANCE DOOR W/ GLASS - ADMIN 01 RM 116 | GRIFFIN, PATRICK E | CLOSED | 2008-10-29 | LO: REMOVE AND INSTALL LOCKSET AT ADMIN 116 | 001 | CLOSED | 54.786 | 0 | 382.92 | 382.92
PJ0002980 | REPLACE ENTRANCE DOOR W/ GLASS - ADMIN 01 RM 116 | GRIFFIN, PATRICK E | CLOSED | 2008-10-29 | PA: STAIN AND FINISH NEW DOOR AT ADMIN 116 | 001 | CLOSED | 268.3 | 0 | 212.72 | 212.72
PJ0002980 Total | [7 empty] | 2535.7045 | 0 | 2172.47 | 2172.47
PJ0002979 | INSPECT & SERVICE WON ELEVATOR DOORS - PAC 06 | GRIFFIN, PATRICK E | CLOSED | 2008-10-29 | AD: WONDOOR CORP. | 006 | CLOSED | 866.7 | 0 | 866.7 | 866.7
PJ0002979 | INSPECT & SERVICE WON ELEVATOR DOORS - PAC 06 | GRIFFIN, PATRICK E | CLOSED | 2008-10-29 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 86.67 | 0 | 0 | 0
PJ0002979 Total | [7 empty] | 953.37 | 0 | 866.7 | 866.7
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: BBALL V. SFSU ON MAY 1- MAY 3 | 160 | CLOSED | 0 | 0 | 1433.73 | 1433.73
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 - SUPPORT FOR BBALL V. USC ON 3/31 AT 6PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - APR 17-19 UC DAVIS GAME(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - APR 19 UC DAVIS GAME 1:00 PM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - APR 28 FRESNO STATE GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - FEB 20 RICE GAME 6:00 PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - FEB 21 RICE GAME 1:00 PM & 6:00 PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - FEB 27-28 SACRAMENTO STATE GAMES | 160 | CLOSED | 0 | 0 | 290.3755 | 290.3755
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAR 01 SACRAMENTO STATE GAME 1:00 PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAR 24 SAN JOSE STATE GAME 6:00 PM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAR 25 DARTMOUTH GAME 6:00 PM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAR 31 SOUTHERN CALIFORNIA GAME 6:00 PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 03 SANFRANCISCO GAME 1:00 PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 08 CAL STATE FULLERTON GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 1-3 SANFRANCISCO GAME WEEKEND(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 12 PEPPERDINE GAME 6:00 PM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 18 SANTA CLARA GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 22-24 UC RIVERSIDE GAME | 160 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL - MAY 24 UC RIVERSIDE GAME 1:00 PM | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: 09 BASEBALL MAR 21 CAL STATE BAKSFIELD GAME 1:00 PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: BASEBALL - MAR 20 & 2 CAL STATE BAKERSFIELD GAME | 160 | CLOSED | 0 | 0 | 180.378 | 180.378
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: CUSTODIAL SUPPORT BBALL UCSB V. FULLERTON 11AM 5/9 | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: CUSTODIAL SUPPORT FOR BBALL V. NORTHRIDGE 4/3 - 4/5 | 160 | CLOSED | 0 | 0 | 98.388 | 98.388
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | CU: CUSTODIAL SUPPORT FOR BBALL V. ST MARYS 4/7 (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | GR: 09 BASEBALL - FEB 20 RICE GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 1473.432 | 1473.432
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | GR: 09 BASEBALL - FEB 21 RICE GAME 1:00 PM & 6:00 PM | 160 | CLOSED | 0 | 0 | 995.622 | 995.622
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | GR: 09 BASEBALL - FEB 27-28 SACRAMENTO STATE GAME | 160 | CLOSED | 0 | 0 | 1599.324 | 1599.324
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | GR: BASEBALL - MAR 20 & 21 BAKERSFIELD GAMES | 160 | CLOSED | 0 | 0 | 954.648 | 954.648
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | GR: BASEBALL B. DARTMOUTH MAR 25 - 6PM | 160 | CLOSED | 0 | 0 | 322.944 | 322.944
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | GR: BASEBALL V. SAN JOSE STATE MAR 24 - 6PM | 160 | CLOSED | 0 | 0 | 294.759 | 294.759
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: 09 BASEBALL - APR 07 SAINT MARY'S GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: 09 BASEBALL - APR 17-19 UC DAVIS GAMES | 160 | CLOSED | 0 | 0 | 1172.892 | 1172.892
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: 09 BASEBALL - APR 28 FRESNO STATE GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 504.6 | 504.6
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: 09 BASEBALL - MAY 22-24 UC RIVERSIDE GAME | 160 | CLOSED | 0 | 0 | 1541.469 | 1541.469
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: 09 BASEBALL - MAY 8-10 CAL STATE FULLERTON GAMES | 160 | CLOSED | 0 | 0 | 1265.106 | 1265.106
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: BASEBALL - MAY 12 CAL STATE FULLERTON GAME 6:00 PM | 160 | CLOSED | 0 | 0 | 924.342 | 924.342
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: LANDSCAPE SUPPORT FOR BBALL V. NORTHRIDGE 4/3 - 4/5 | 160 | CLOSED | 0 | 0 | 1501.434 | 1501.434
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: LANDSCAPE SUPPORT FOR BBALL V. ST MARYS 4/7 | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: LANDSCAPE SUPPORT FOR BBALL V. USC - 3/31 AT 6PM | 160 | CLOSED | 0 | 0 | 421.803 | 421.803
PJ0002977 | 08/09 BASEBALL - SERVICES FOR ATHLETICS - BAGGETT 160 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-26 | LA: SUPPORT BBALL V. SANTA CLARA 5/18 - 6PM | 160 | CLOSED | 0 | 0 | 565.152 | 565.152
PJ0002977 Total | [7 empty] | 0 | 0 | 16241.7505 | 16241.7505
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CU: CUSTODIAL SUPPORT FOR SBALL V. LONG BEACH - 4/10 & 4/11 | 161 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CU: CUSTODIAL SUPPORT FOR SBALL V. PACIFIC MAY 2 & 3 | 161 | CLOSED | 0 | 0 | 196.776 | 196.776
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CU: CUSTODIAL SUPPORT FOR SOFTBALL V. UCSB 4/4 - 4/5 | 161 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CU: CUSTODIAL SUPPORT UCSB V. FULLERTON 5/8 - 5/09 | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CU: SOFTBALL SUPPORT FOR MUSTANG CLASSIC - 3/6-3/8 | 161 | CLOSED | 0 | 0 | 49.194 | 49.194
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | CU: SUPPORT FOR SOFTBALL V. PROVIDENCE ON 3/10 AT 2PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: LANDSCAPE SUPPORT FOR SOFTBALL V. UCSB 4/4 - 4/5 | 161 | CLOSED | 0 | 0 | 1196.856 | 1196.856
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: LANDSCAPE SVCS SUPPORT FOR SBALL V. PACIFIC MAY 2 & 3 | 161 | CLOSED | 0 | 0 | 1095.936 | 1095.936
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: SANTA BARBARA V. FULLERTON - 5/8-5/10 | 161 | CLOSED | 0 | 0 | 824.634 | 824.634
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: SOFTBALL PRE-SEASON SUPPORT FOR GAME ON 10/25 | 161 | CLOSED | 0 | 0 | 592.488 | 592.488
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: SOFTBALL V. SANTA CLARA MAR 24 - 2PM | 161 | CLOSED | 0 | 0 | 274.575 | 274.575
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: SUPPORT FOR MUSTANG CLASSIC 3/6-3/8 | 161 | CLOSED | 0 | 0 | 4517.94 | 4517.94
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: SUPPORT FOR SBALL V. CSU LONG BEACH - 4/10 & 4/11 | 161 | CLOSED | 0 | 0 | 555.393 | 555.393
PJ0002975 | 08/09 SOFTBALL -FACILITY SVCS FOR ATHLETICS-JANSSEN 161 (NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-24 | LA: SUPPORT FOR SOFTBALL V. PROVIDENCE GAME ON 3/10 | 161 | CLOSED | 0 | 0 | 341.37 | 341.37
PJ0002975 Total | [7 empty] | 0 | 0 | 10038.714 | 10038.714
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | CA:BUILDING CONDITION ASSESSMENT | 082 | CLOSED | 508.3884 | 0 | 221.52 | 221.52
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | CP: PROJECT CONTINGENCY | 082 | CLOSED | 329.93 | 0 | 0 | 0
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | EH&S:BUILDING CONDITION ASSESSMENT (N/L) | 082 | CLOSED | 389.376 | 0 | 0 | 0
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | EL:BUILDING CONDITION ASSESSMENT | 082 | CLOSED | 507.552 | 0 | 190.332 | 190.332
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | ES:BUILDING CONDITION ASSESSMENT (N/L) | 082 | CLOSED | 512.256 | 0 | 0 | 0
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | IN: FACILITY SURVEY OF BUILDING - BLDG 82 | 082 | CLOSED | 530.208 | 0 | 563.346 | 563.346
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | PA:BUILDING CONDITION ASSESSMENT | 082 | CLOSED | 343.152 | 0 | 127.632 | 127.632
PJ0002974 | FACILITY SURVEY OF BUILDING - BLDG 82 | MOLLAN, CHERYL L. | CLOSED | 2008-10-23 | PL: BUILDING CONDITION ASSESSMENT (N/L) | 082 | CLOSED | 508.608 | 0 | 0 | 0
PJ0002974 Total | [7 empty] | 3629.4704 | 0 | 1102.83 | 1102.83
PJ0002973 | MJ: PREP DOOR FOR CAME SECURITY SYSTEM - EDES 186 RM B102 | GRIFFIN, PATRICK E | CLOSED | 2008-10-21 | AD: CAME SECURITY | 186 | CLOSED | 52950 | 0 | 52950 | 52950
PJ0002973 | MJ: PREP DOOR FOR CAME SECURITY SYSTEM - EDES 186 RM B102 | GRIFFIN, PATRICK E | CLOSED | 2008-10-21 | CP: PROJECT CONTINGENCY | 186 | CLOSED | 9173.71 | 0 | 0 | 0
PJ0002973 | MJ: PREP DOOR FOR CAME SECURITY SYSTEM - EDES 186 RM B102 | GRIFFIN, PATRICK E | CLOSED | 2008-10-21 | EL: PROVIDE CIRCUIT FOR ELECTRONIC DOOR POWER SUPPLY | 186 | CLOSED | 7753.4927 | 0 | 4191.75 | 4191.75
PJ0002973 | MJ: PREP DOOR FOR CAME SECURITY SYSTEM - EDES 186 RM B102 | GRIFFIN, PATRICK E | CLOSED | 2008-10-21 | IN: PREP DOOR FOR CAME SECURITY SYSTEM - EDES 186 RM B102 | 186 | CLOSED | 265.104 | 0 | 99.414 | 99.414
PJ0002973 | MJ: PREP DOOR FOR CAME SECURITY SYSTEM - EDES 186 RM B102 | GRIFFIN, PATRICK E | CLOSED | 2008-10-21 | LO: INSTALL NEW HES ELECTRONIC LOCKSETS | 186 | CLOSED | 12770.4667 | 0 | 14550.078 | 14550.078
PJ0002973 Total | [7 empty] | 82912.7734 | 0 | 71791.242 | 71791.242
PJ0002972 | REMOVE PLUMBING TO ICE MAKER - ERHART 10 RM 102 | RIVERA, MARIO L | CLOSED | 2008-10-08 | CA: ASSIST WITH ICE MACHINE REMOVAL - 10-102 | 010 | CLOSED | 452.28 | 0 | 190.8432 | 190.8432
PJ0002972 | REMOVE PLUMBING TO ICE MAKER - ERHART 10 RM 102 | RIVERA, MARIO L | CLOSED | 2008-10-08 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 166.7 | 0 | 0 | 0
PJ0002972 | REMOVE PLUMBING TO ICE MAKER - ERHART 10 RM 102 | RIVERA, MARIO L | CLOSED | 2008-10-08 | PA: PACTH ONE WALL IN ROOM 102 | 010 | CLOSED | 463.152 | 0 | 243.441 | 243.441
PJ0002972 | REMOVE PLUMBING TO ICE MAKER - ERHART 10 RM 102 | RIVERA, MARIO L | CLOSED | 2008-10-08 | PL: AG ERHART ROOM 102 REMOVE ICE MAKER UNIT. | 010 | CLOSED | 314.304 | 0 | 255.1776 | 255.1776
PJ0002972 Total | [7 empty] | 1396.436 | 0 | 689.4618 | 689.4618
PJ0002965 | SR 08/09: RE-ROOF GABLE END OF BUILDING - MFG 36 | GRIFFIN, PATRICK E | CLOSED | 2008-10-17 | AD: JOC 07.015.043 MAINO | 036 | CLOSED | 40235.5 | 0 | 40235.5 | 40235.5
PJ0002965 | SR 08/09: RE-ROOF GABLE END OF BUILDING - MFG 36 | GRIFFIN, PATRICK E | CLOSED | 2008-10-17 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 4023.55 | 0 | 0 | 0
PJ0002965 Total | [7 empty] | 44259.05 | 0 | 40235.5 | 40235.5
PJ0002964 | SR 08/09: CLEAN BOX CULVERTS UNDER HIGHLAND (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: ALTHOUSE & MEADE ENVIRONMENTAL | GENERAL | CLOSED | 3497 | 0 | 1134 | 1134
PJ0002964 | SR 08/09: CLEAN BOX CULVERTS UNDER HIGHLAND (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: JOC 08.017.009 MAINO | GENERAL | CLOSED | 45692.11 | 0 | 48301.17 | 48301.17
PJ0002964 | SR 08/09: CLEAN BOX CULVERTS UNDER HIGHLAND (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: PERMIT FEES (CA RWQCB & CA DEPT OF FISH AND GAME) | GENERAL | CLOSED | 1261 | 0 | 1411 | 1411
PJ0002964 | SR 08/09: CLEAN BOX CULVERTS UNDER HIGHLAND (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 3002.94 | 0 | 0 | 0
PJ0002964 | SR 08/09: CLEAN BOX CULVERTS UNDER HIGHLAND (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | EH&S: OVERSEE WORK IN CREEK (CULVERTS UNDER HIGHLAND) | GENERAL | CLOSED | 2163.2 | 0 | 1634.15 | 1634.15
PJ0002964 Total | [7 empty] | 55616.25 | 0 | 52480.32 | 52480.32
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: DIVISION OF STATE ARCHITECT | 004 | CLOSED | 200 | 0 | 200 | 200
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: FLOOR CONNECTION | 004 | CLOSED | 4466.11 | 0 | 5620.12 | 5620.12
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: JOC 08.017.004.00 MAINO | 004 | CLOSED | 48888.91 | 0 | 49041.82 | 49041.82
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: MECA | 004 | CLOSED | 6000 | 0 | 2085 | 2085
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | AD: WHSE PARTS TO BE INSTALLED BY CONTRACTOR - AERO RR PROJECT | 004 | CLOSED | 0 | 0 | 1.1124 | 1.1124
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 4825.05 | 0 | 0 | 0
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | EL: INSTALL ELECTRICAL FOR RESTROOMS | 004 | CLOSED | 1820.1645 | 0 | 3593.464 | 3593.464
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | ES: HOOK UP RESTROOMS EXHAUST FAN | 004 | CLOSED | 1279.156 | 0 | 1618.72 | 1618.72
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | IN: SR 08/09: ADA RESTROOM - AERO HANGER 004 | 004 | CLOSED | 828.45 | 0 | 566.1075 | 566.1075
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | LO: INSTALL CORES | 004 | CLOSED | 255.28 | 0 | 226.74 | 226.74
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | PA: PAINT RESTROOMS | 004 | CLOSED | 4379.9612 | 0 | 1970.1 | 1970.1
PJ0002960 | SR 08/09: ADA RESTROOM - AERO HANGER 004 (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-10-17 | PL: INSTALL NEW PLUMBING IN RESTROOMS | 004 | CLOSED | 29259.392 | 0 | 27231.9757 | 27231.9757
PJ0002960 Total | [7 empty] | 102202.4737 | 0 | 92155.1596 | 92155.1596
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | AD: JOC 07.015.042 MAINO | 128 | CLOSED | 103336.44 | 0 | 103336.44 | 103336.44
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | CA: SUPPORT FOR CROPS HOUSE DEMO | 128 | CLOSED | 1599.25 | 0 | 1644.075 | 1644.075
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | CP: PROJECT CONTINGENCY | 128 | CLOSED | 10742.56 | 0 | 0 | 0
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | EH&S:OVERSEE HAZ MAT REMOVL AT CROPS HOUSE DEMO (N/L) | 128 | CLOSED | 1081.6 | 0 | 0 | 0
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | EL: SUPPORT FOR CROPS HOUSE DEMO | 128 | CLOSED | 634.44 | 0 | 547.1975 | 547.1975
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | IN: SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | 128 | CLOSED | 0 | 0 | 96.6525 | 96.6525
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | MO:PICK UP SURPLUS AT CROPS HOUSE | 128 | CLOSED | 0 | 0 | 227.28 | 227.28
PJ0002959 | SR 08/09: DEMOLISH CROPS HOUSE - PARSON'S HOUSE 128 | MAY, TOM | CLOSED | 2008-10-17 | PL: SUPPORT FOR CROPS HOUSE DEMO | 128 | CLOSED | 773.84 | 0 | 781.44 | 781.44
PJ0002959 Total | [7 empty] | 118168.13 | 0 | 106633.085 | 106633.085
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: BUEHLER& BUEHLER | 061 | CLOSED | 1000 | 0 | 750 | 750
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: CONTRACTOR PARKING COSTS | 061 | CLOSED | 300 | 0 | 90 | 90
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: CREDIT CARD PURCHASE OF SCOREBOARD PROTECTIVE NETTING | 061 | CLOSED | 5250 | 0 | 1124.34 | 1124.34
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: DAKTRONICS | 061 | CLOSED | 8523.75 | 0 | 24658.98 | 24658.98
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: ENGLEKIRK AND SABOL - SEISMIC PEER REVIEW | 061 | CLOSED | 2612 | 0 | 2612 | 2612
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: GRAND PERFORMANCE | 061 | CLOSED | 4750 | 0 | 3750 | 3750
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: GRAND PERFORMANCE - DIRECT PAY (MAINT) | 061 | CLOSED | 980 | 0 | 980 | 980
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: GREENVALE TREE COMPANY | 061 | CLOSED | 1000 | 0 | 820 | 820
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: GSI SOILS | 061 | CLOSED | 12177 | 0 | 10266 | 10266
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: JOC 08.017.012 MAINO | 061 | CLOSED | 40780 | 0 | 15649.73 | 15649.73
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: MECA | 061 | CLOSED | 5000 | 0 | 1710 | 1710
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: MISC COSTS ASSOCIATED WITH PROJECT | 061 | CLOSED | 140 | 0 | 25.54 | 25.54
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: PETTY CASH PURCHASE | 061 | CLOSED | 0 | 0 | 21.71 | 21.71
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: QUINN RENTALS | 061 | CLOSED | 3200 | 0 | 3159.97 | 3159.97
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | AD: SLO APCD - FEES FOR NESHAP 10-DAY NOTICE (MAINT) | 061 | CLOSED | 360 | 0 | 365 | 365
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | CA: REPLACE BROKEN CEILING TILES(CB TO DAKTRONICS-TRACKING ONLY) | 061 | CLOSED | 406.14 | 0 | 248.52 | 248.52
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | CA:SUPPORT FOR SCOREBOARD PROJECT | 061 | CLOSED | 3193.705 | 0 | 1484.86 | 1484.86
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 4528.26 | 0 | 0 | 0
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | EL: REMOVE EXISTING AND INSTALL NEW POWER FEED-SPANOS SCOREBOARD | 061 | CLOSED | 19521.9591 | 0 | 18696.3665 | 18696.3665
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | EO: SUPPORT FOR SPANOS SCOREBOARD REPLACEMENT | 061 | CLOSED | 3898.3028 | 0 | 2121.75 | 2121.75
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | IN: REPLACE SCOREBOARD - SPANOS STADIUM 61 | 061 | CLOSED | 276.15 | 0 | 441.84 | 441.84
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | LA:LANDSCAPE SUPPORT FOR SCOREBOARD REPLACEMENT | 061 | CLOSED | 3315.1048 | 0 | 1560.5617 | 1560.5617
PJ0002958 | SR 08/09, SR 09/10:NEW SCOREBOARD-SPANOS STAD 61(ENC BY 6/30/09) | POPHAM, DONALD J. | CLOSED | 2008-10-17 | LO: INSTALL ORANGE CONST CORE IN 61 RMS 312 & 323 | 061 | CLOSED | 71.46 | 0 | 71.46 | 71.46
PJ0002958 Total | [7 empty] | 121283.8317 | 0 | 90608.6282 | 90608.6282
PJ0002956 | SR 08/09: REPLACE DOORS ON BOILERS - ENGR S. 40 | PAHLOW, BOB | CLOSED | 2008-10-16 | AD: R.F. MACDONALD | 040 | CLOSED | 69041.91 | 0 | 74186.41 | 74186.41
PJ0002956 | SR 08/09: REPLACE DOORS ON BOILERS - ENGR S. 40 | PAHLOW, BOB | CLOSED | 2008-10-16 | CA:REMOVE VESTIBULE/WALL FOR ACCESS OF NEW BOILER DOORS. | 040 | CLOSED | 1846 | 0 | 1626.85 | 1626.85
PJ0002956 | SR 08/09: REPLACE DOORS ON BOILERS - ENGR S. 40 | PAHLOW, BOB | CLOSED | 2008-10-16 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 7074.45 | 0 | 0 | 0
PJ0002956 | SR 08/09: REPLACE DOORS ON BOILERS - ENGR S. 40 | PAHLOW, BOB | CLOSED | 2008-10-16 | EL-ASSIST WITH REMOVAL OF VESTIBULE AS NEEDED | 040 | CLOSED | 52.87 | 0 | 26.435 | 26.435
PJ0002956 | SR 08/09: REPLACE DOORS ON BOILERS - ENGR S. 40 | PAHLOW, BOB | CLOSED | 2008-10-16 | IN: SR 08/09: REPLACE DOORS ON BOILERS - ENGR S. 40 | 040 | CLOSED | 110.46 | 0 | 27.615 | 27.615
PJ0002956 Total | [7 empty] | 78125.69 | 0 | 75867.31 | 75867.31
PJ0002952 | SR 08/09: REPLACE THE # 2 PUMP - PUMP HOUSE 2 | PAHLOW, BOB | CLOSED | 2008-10-16 | AD: JOC 07.015.044 MAINO | GENERAL | CLOSED | 24114.84 | 0 | 24114.84 | 24114.84
PJ0002952 | SR 08/09: REPLACE THE # 2 PUMP - PUMP HOUSE 2 | PAHLOW, BOB | CLOSED | 2008-10-16 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2200 | 0 | 0 | 0
PJ0002952 | SR 08/09: REPLACE THE # 2 PUMP - PUMP HOUSE 2 | PAHLOW, BOB | CLOSED | 2008-10-16 | EL: ASSIST CONTRACTOR AT PUMPHOUSE # 2 | GENERAL | CLOSED | 211.48 | 0 | 52.87 | 52.87
PJ0002952 | SR 08/09: REPLACE THE # 2 PUMP - PUMP HOUSE 2 | PAHLOW, BOB | CLOSED | 2008-10-16 | LO: CHANGE PUMPHOUSE # 2 CORE | GENERAL | CLOSED | 47.64 | 0 | 71.46 | 71.46
PJ0002952 | SR 08/09: REPLACE THE # 2 PUMP - PUMP HOUSE 2 | PAHLOW, BOB | CLOSED | 2008-10-16 | PL: ASSIST CONTRACTOR WITH THE PUMPHOUSE # 2 REPLACEMENT PROJECT | GENERAL | CLOSED | 317.88 | 0 | 833.09 | 833.09
PJ0002952 Total | [7 empty] | 26891.84 | 0 | 25072.26 | 25072.26
PJ0002947 | RELOCATE & UPGRADE BULK OIL & COOLANT STORAGE - TRANS SVC 071 | LOOSLEY, SCOTT L. | CLOSED | 2008-10-07 | CP: PROJECT CONTINGENCY | 071 | CLOSED | 187.15 | 0 | 0 | 0
PJ0002947 | RELOCATE & UPGRADE BULK OIL & COOLANT STORAGE - TRANS SVC 071 | LOOSLEY, SCOTT L. | CLOSED | 2008-10-07 | PL:TRANSPORTATION RELOCATE OIL LINES | 071 | CLOSED | 1871.52 | 0 | 2938.624 | 2938.624
PJ0002947 | RELOCATE & UPGRADE BULK OIL & COOLANT STORAGE - TRANS SVC 071 | LOOSLEY, SCOTT L. | CLOSED | 2008-10-07 | TS: TRANSPORTATION SERVICES TO MOVE OIL DRUMS (MAINT) | 071 | CLOSED | 0 | 0 | 3243.01 | 3243.01
PJ0002947 Total | [7 empty] | 2058.67 | 0 | 6181.634 | 6181.634
PJ0002944 | PROVIDE SETUP FOR NEWSPAPER INSERTER - GRC 26A GOSS PRESS LAB | PAHLOW, BOB | CLOSED | 2008-10-02 | CP: PROJECT CONTINGENCY | 026A | CLOSED | 249.15 | 0 | 0 | 0
PJ0002944 | PROVIDE SETUP FOR NEWSPAPER INSERTER - GRC 26A GOSS PRESS LAB | PAHLOW, BOB | CLOSED | 2008-10-02 | EL:INSTALL ELECTRICAL FOR NEW INSERTER. | 026A | CLOSED | 1482.4159 | 0 | 1193.952 | 1193.952
PJ0002944 | PROVIDE SETUP FOR NEWSPAPER INSERTER - GRC 26A GOSS PRESS LAB | PAHLOW, BOB | CLOSED | 2008-10-02 | IN: SETUP FOR NEWSPAPER INSERTER - GRC 26A GOSS PRESS LAB | 026A | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0002944 | PROVIDE SETUP FOR NEWSPAPER INSERTER - GRC 26A GOSS PRESS LAB | PAHLOW, BOB | CLOSED | 2008-10-02 | MO:MOVE NEW INSERTER FROM WAREHOUSE TO BUILDING 026A | 026A | CLOSED | 126 | 0 | 56.82 | 56.82
PJ0002944 | PROVIDE SETUP FOR NEWSPAPER INSERTER - GRC 26A GOSS PRESS LAB | PAHLOW, BOB | CLOSED | 2008-10-02 | PL:INSTALL NEW 3/4" AIR LINE TO INSERTER. | 026A | CLOSED | 883.6277 | 0 | 1422.6504 | 1422.6504
PJ0002944 Total | [7 empty] | 2741.1936 | 0 | 2706.5604 | 2706.5604
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | AD: DIVISION OF STATE ARCHITECT | 043A | CLOSED | 300 | 0 | 200 | 200
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | AD: JOC 08.016.003 TORRES | 043A | CLOSED | 19674.9246 | 0 | 12613.0102 | 12613.0102
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | CA: DEMO AND FRAME NEW WALLS | 043A | CLOSED | 8704.7004 | 0 | 9809.064 | 9809.064
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | CP: PROJECT CONTINGENCY | 043A | CLOSED | 5549.24 | 0 | 0 | 0
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | CU: STRIP AND WAX FLOOR | 043A | CLOSED | 225.6365 | 0 | 721.512 | 721.512
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | EL: PROVIDE ELECTRICAL FOR NEW OFFICES | 043A | CLOSED | 7373.9188 | 0 | 6442.6004 | 6442.6004
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | ES: PROVIDE HOOD DUCT | 043A | CLOSED | 1828.8941 | 0 | 395.796 | 395.796
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | IN: DESIGN & REMODEL ROOM 458 - KINES 43A | 043A | CLOSED | 760.1857 | 0 | 480.501 | 480.501
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | LO: PROVIDE AND INSTALL LOCKS | 043A | CLOSED | 2608.1443 | 0 | 2741.526 | 2741.526
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | PA: PAINT NEW OFFICES | 043A | CLOSED | 8719.9224 | 0 | 4894.992 | 4894.992
PJ0002943 | DESIGN & REMODEL ROOM 458 - KINES 43A | LAMPMAN, GREG | CLOSED | 2008-10-02 | PL: INSTALL NEW KITCHEN SINK | 043A | CLOSED | 15375.4675 | 0 | 9410.178 | 9410.178
PJ0002943 Total | [7 empty] | 71121.0343 | 0 | 47709.1796 | 47709.1796
PJ0002941 | 08/09 FALL JOB FAIR 10/16 - REC 43 MAIN, BLUE & GRAY GYM(NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-02 | CA: HANG CAL POLY BANNER AT REC CENTER ON OCT 16 | 043 | CLOSED | 0 | 0 | 332.28 | 332.28
PJ0002941 | 08/09 FALL JOB FAIR 10/16 - REC 43 MAIN, BLUE & GRAY GYM(NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-02 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0002941 | 08/09 FALL JOB FAIR 10/16 - REC 43 MAIN, BLUE & GRAY GYM(NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-02 | EL: PROVIDE POWER FOR JOB FAIR EXHIBIT HALL AT REC CENTER. 10/16 | 043 | CLOSED | 0 | 0 | 2117.772 | 2117.772
PJ0002941 | 08/09 FALL JOB FAIR 10/16 - REC 43 MAIN, BLUE & GRAY GYM(NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-02 | LS:TURN OFF SPRINKLERS AT HEALTH CTR LAWN10/15&10/16(MAINT)(N/L) | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0002941 | 08/09 FALL JOB FAIR 10/16 - REC 43 MAIN, BLUE & GRAY GYM(NO EST) | POPHAM, DONALD J. | CLOSED | 2008-10-02 | MO: MOVE EMPLOYERS ITEMS FROM BLD 70 TO REC 43 | 043 | CLOSED | 0 | 0 | 85.23 | 85.23
PJ0002941 Total | [7 empty] | 0 | 0 | 2535.282 | 2535.282
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | AD: JOC 08.018.032 MAINO | 150 | CLOSED | 42007.2 | 0 | 42007.21 | 42007.21
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | CP: PROJECT CONTINGENCY | 150 | CLOSED | 4927.54 | 0 | 0 | 0
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | EL:PROVIDE ELECTRICAL SERVICES FOR POULTRY COOLER REPAIRS | 150 | CLOSED | 1764.1974 | 0 | 2623.989 | 2623.989
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | ES: PROVIDE SERVICES FOR POULTRY COOLER REPAIRS | 150 | CLOSED | 353.9069 | 0 | 2623.062 | 2623.062
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | IN: LIGHT FIXTURE AND CEILING IN COOLER - POULTRY 150 RM 110A | 150 | CLOSED | 132.552 | 0 | 110.46 | 110.46
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | LO:INSTALL NEW LOCK HARDWARE ON DOUBLE DOORS AT POULTRY COOLER | 150 | CLOSED | 2144.8022 | 0 | 1271.952 | 1271.952
PJ0002940 | SR 08/09: LIGHT FIXTURE&CEILING IN COOLER - POULTRY 150-110A | GRIFFIN, PATRICK E | CLOSED | 2008-09-30 | PA:PREP AND PAINT NEW JAMBS AND DOORS AT POULTRY COOLER | 150 | CLOSED | 1169.4732 | 0 | 955.08 | 955.08
PJ0002940 Total | [7 empty] | 52499.6717 | 0 | 49591.753 | 49591.753
PJ0002939 | M&R PARK 08/09: REPLACE 221 HPS FIXTURES W/ ENERGY EFFICIENT T8 | ELLIOT, DENNIS K | CLOSED | 2008-09-30 | AD: JOC 07.015.039 MAINO | 130 | CLOSED | 64541.5547 | 0 | 64541.5547 | 64541.5547
PJ0002939 | M&R PARK 08/09: REPLACE 221 HPS FIXTURES W/ ENERGY EFFICIENT T8 | ELLIOT, DENNIS K | CLOSED | 2008-09-30 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 6504.73 | 0 | 0 | 0
PJ0002939 Total | [7 empty] | 71046.2847 | 0 | 64541.5547 | 64541.5547
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | CA:SUPPLY 8 BRDS AND STANCHIONS FOR ASI CONCRT 10/27 (N/L;) | 043 | CLOSED | 55.38 | 0 | 0 | 0
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | CU: ON SITE CUST SUPPORT FOR CONCERT ON 10/27 FROM 6:30-11:30A | 043 | CLOSED | 0 | 0 | 394.524 | 394.524
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | CU:ON SITE CUST. SUPPORT FOR ASI CONCERT 7:30P-12:30PM ON 10/23 | 043 | CLOSED | 0 | 0 | 364.14 | 364.14
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | EL: ELECTRICAL SUPPORT FOR ASI CONCERT ON 10/23 | 043 | CLOSED | 0 | 0 | 1351.332 | 1351.332
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | EL: ELECTRICAL SUPPORT FOR ASI CONCERT ON 10/27 | 043 | CLOSED | 0 | 0 | 1215.192 | 1215.192
PJ0002938 | ASI CONCERT - REC CENTER 43 MAIN GYM - 10/23 & 10/27/08. | POPHAM, DONALD J. | CLOSED | 2008-09-30 | LA: SUPPLY 5 PCS OF PLYWOOD FOR ASI CONCERTS ON 10/24 | 043 | CLOSED | 0 | 0 | 40.368 | 40.368
PJ0002938 Total | [7 empty] | 55.38 | 0 | 3365.556 | 3365.556
PJ0002935 | SR 08/09: RE-FEED ELECT SERVICE FOR SCADA - UPD 74 | PAHLOW, BOB | CLOSED | 2008-09-25 | AD: JOC 07.015.033 MAINO | 074 | CLOSED | 58746.86 | 0 | 58746.86 | 58746.86
PJ0002935 | SR 08/09: RE-FEED ELECT SERVICE FOR SCADA - UPD 74 | PAHLOW, BOB | CLOSED | 2008-09-25 | CP: PROJECT CONTINGENCY | 074 | CLOSED | 6023.67 | 0 | 0 | 0
PJ0002935 | SR 08/09: RE-FEED ELECT SERVICE FOR SCADA - UPD 74 | PAHLOW, BOB | CLOSED | 2008-09-25 | EL:ASSIST THOMA AS NEEDED | 074 | CLOSED | 1268.88 | 0 | 634.44 | 634.44
PJ0002935 | SR 08/09: RE-FEED ELECT SERVICE FOR SCADA - UPD 74 | PAHLOW, BOB | CLOSED | 2008-09-25 | IN: SR 08/09: RE-FEED ELECT SERVICE FOR SCADA - UPD 74 | 074 | CLOSED | 220.92 | 0 | 27.615 | 27.615
PJ0002935 Total | [7 empty] | 66260.33 | 0 | 59408.915 | 59408.915
PJ0002933 | SPECIAL EVENT - ALUMNI HOUSE 28 (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-19 | CP: PROJECT CONTINGENCY | 028 | CLOSED | 0 | 0 | 0 | 0
PJ0002933 | SPECIAL EVENT - ALUMNI HOUSE 28 (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-19 | CU: CUSTODIAL SUPPORT FOR ALUMNI HOUSE EVENT 10/7 4PM | 028 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002933 | SPECIAL EVENT - ALUMNI HOUSE 28 (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-19 | GR: CLEAN FRONT ENTRANCE TO ALUMNI HOUSE FOR EVENT 10/7(N/L) | 028 | CLOSED | 0 | 0 | 0 | 0
PJ0002933 | SPECIAL EVENT - ALUMNI HOUSE 28 (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-19 | MC: MOVE PLANTS AND PODIUM TO ALUMNI HOUSE - OCT 7 | 028 | CLOSED | 0 | 0 | 9.47 | 9.47
PJ0002933 | SPECIAL EVENT - ALUMNI HOUSE 28 (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-19 | PL: PM RESTROOM AT ALUMNI HOUSE FOR SPECIAL EVENT ON 10/7 | 028 | CLOSED | 0 | 0 | 211.92 | 211.92
PJ0002933 Total | [7 empty] | 0 | 0 | 276.05 | 276.05
PJ0002932 | MJ: LANDSCAPE NEAR ELEVATOR - ENGR W BLDG 21 | LOOSLEY, SCOTT L. | CLOSED | 2008-09-19 | CA: INSTALL DUMPSTER ENCLOSURE AND E-CART PARKING AT BLDG 21 | 021 | CLOSED | 3717 | 0 | 9983.3134 | 9983.3134
PJ0002932 | MJ: LANDSCAPE NEAR ELEVATOR - ENGR W BLDG 21 | LOOSLEY, SCOTT L. | CLOSED | 2008-09-19 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 5807.99 | 0 | 0 | 0
PJ0002932 | MJ: LANDSCAPE NEAR ELEVATOR - ENGR W BLDG 21 | LOOSLEY, SCOTT L. | CLOSED | 2008-09-19 | EL: INSTALL CONDUIT FOR FUTURE ECART CHARGING STATION BLDG 21 | 021 | CLOSED | 150.888 | 0 | 983.382 | 983.382
PJ0002932 | MJ: LANDSCAPE NEAR ELEVATOR - ENGR W BLDG 21 | LOOSLEY, SCOTT L. | CLOSED | 2008-09-19 | EO: REMOVE BASE FOR CONCRETE POUR - E.W. (NO LABOR) | 021 | CLOSED | 0 | 0 | 3490.872 | 3490.872
PJ0002932 | MJ: LANDSCAPE NEAR ELEVATOR - ENGR W BLDG 21 | LOOSLEY, SCOTT L. | CLOSED | 2008-09-19 | LA: INSTALL PLANTS AND IRRIGATION AT BLDG 21 ELEVATOR | 021 | CLOSED | 4822.08 | 0 | 40.368 | 40.368
PJ0002932 Total | [7 empty] | 14497.958 | 0 | 14497.9354 | 14497.9354
PJ0002930 | ROOM RENOVATION - ARCH 05 RM 311 | MOLLAN, CHERYL L. | CLOSED | 2008-09-17 | AD: FLOORTEC | 005 | CLOSED | 378.1059 | 0 | 378.1059 | 378.1059
PJ0002930 | ROOM RENOVATION - ARCH 05 RM 311 | MOLLAN, CHERYL L. | CLOSED | 2008-09-17 | CA: REMOVE COVE BASE IN ARCH. 05 ROOM 311 | 005 | CLOSED | 110.76 | 0 | 149.076 | 149.076
PJ0002930 | ROOM RENOVATION - ARCH 05 RM 311 | MOLLAN, CHERYL L. | CLOSED | 2008-09-17 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 57.04 | 0 | 0 | 0
PJ0002930 | ROOM RENOVATION - ARCH 05 RM 311 | MOLLAN, CHERYL L. | CLOSED | 2008-09-17 | IN: ROOM RENOVATION - ARCH 05 RM 311 | 005 | CLOSED | 66.276 | 0 | 33.138 | 33.138
PJ0002930 | ROOM RENOVATION - ARCH 05 RM 311 | MOLLAN, CHERYL L. | CLOSED | 2008-09-17 | MO:MOVE DESK AND CREDENZA | 005 | CLOSED | 126 | 0 | 22.728 | 22.728
PJ0002930 Total | [7 empty] | 738.1819 | 0 | 583.0479 | 583.0479
PJ0002929 | REPLACE RAIN GUTTERS & DOWNSPOUTS - BCEC BLDG 55 (MAINT) | DANKO, KEN | CLOSED | 2008-09-15 | CA : REPAIR GUTTER AND DOWNSPOUTS AT BCEC 055 | 055 | CLOSED | 1846 | 0 | 1510.565 | 1510.565
PJ0002929 | REPLACE RAIN GUTTERS & DOWNSPOUTS - BCEC BLDG 55 (MAINT) | DANKO, KEN | CLOSED | 2008-09-15 | CP: PROJECT CONTINGENCY (N/L) | 055 | CLOSED | 87.55 | 0 | 0 | 0
PJ0002929 Total | [7 empty] | 1933.55 | 0 | 1510.565 | 1510.565
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | AD: FLOOR CONNECTION | 042 | CLOSED | 0 | 0 | 813.2 | 813.2
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | AD: HOLLMAN, INC. | 042 | CLOSED | 13407.1 | 0 | 13407.1 | 13407.1
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | AD: JOC 07.015.038 MAINO | 042 | CLOSED | 14292.3645 | 0 | 14292.3645 | 14292.3645
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | AD: SANTA MARIA ACOUSTICAL | 042 | CLOSED | 4811.79 | 0 | 4811.79 | 4811.79
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | CA: (MAINT) REPAIR CRACKS IN CONCRETE FLOOR - MOTT 42-120F | 042 | CLOSED | 184.6 | 0 | 362.217 | 362.217
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | CA:INSTALL WHITEBOARD-CUT HOLE IN DOOR NEXT TO WOMENS LOCKER ROO | 042 | CLOSED | 494.1942 | 0 | 330.204 | 330.204
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 3225.21 | 0 | 0 | 0
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | CU: MOVE CLOTHING/TOWELS & LOCKERS FOR MOTT TEAM LOCKERS PROJECT | 042 | CLOSED | 196.776 | 0 | 196.776 | 196.776
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | EL:PURCHASE AND INSTALL NEW LIGHTING FIXTURES | 042 | CLOSED | 2004.1974 | 0 | 6304.4503 | 6304.4503
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | IN: INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | 042 | CLOSED | 198.828 | 0 | 149.121 | 149.121
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | LO: CHANGE CORE TO CONTRUCTION CORE AT 42-120F | 042 | CLOSED | 114.336 | 0 | 200.088 | 200.088
PJ0002927 | INSTALL TEAM LOCKERS & CARPET - MOTT 42 RM 120F | MOLLAN, CHERYL L. | CLOSED | 2008-09-09 | PA:REPAIR HOLES IN WALL AND PAINT | 042 | CLOSED | 976.633 | 0 | 446.712 | 446.712
PJ0002927 Total | [7 empty] | 39906.0291 | 0 | 41314.0228 | 41314.0228
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | CU: 08/09 FALL CONFERENCE RECEPTION - SEPT 15 PCV 171(N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | CU: 08/09 FALL CONFERENCE SEPT 15 - HARMON HALL PAC 06 (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | EL: 08/09 FALL CONFERENCE RECEPTION - SEPT 15 PCV 171 | GENERAL | CLOSED | 0 | 0 | 105.74 | 105.74
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | MO: 08/09 FALL CONFERENCE SEPT 15 - HARMON HALL PAC 06 | GENERAL | CLOSED | 0 | 0 | 75.76 | 75.76
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | PL: PM PAC BUILDING BEFORE FALL CONFERENCE EVENT ON 9/15 | GENERAL | CLOSED | 0 | 0 | 211.92 | 211.92
PJ0002926 | 08/09 FALL CONFERENCE (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-09-08 | SUPPLY RENTAL: 08/09 FALL CONF OCT 16 - TOWN & GOWN RECEPT. | GENERAL | CLOSED | 0 | 0 | 127 | 127
PJ0002926 Total | [7 empty] | 0 | 0 | 520.42 | 520.42
PJ0002924 | REUPHOLSTER BENCHES ON ALL FLOORS - PAC BLDG 06 | GRIFFIN, PATRICK E | CLOSED | 2008-09-05 | AD: INTERIOR PLANNING RESOURCE | 006 | CLOSED | 16275 | 0 | 17388.1313 | 17388.1313
PJ0002924 | REUPHOLSTER BENCHES ON ALL FLOORS - PAC BLDG 06 | GRIFFIN, PATRICK E | CLOSED | 2008-09-05 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1627.5 | 0 | 0 | 0
PJ0002924 Total | [7 empty] | 17902.5 | 0 | 17388.1313 | 17388.1313
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - NOV 08 LONG BEACH STATE 7:00 PM | 042 | CLOSED | 0 | 0 | 486.162 | 486.162
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - NOV 15 UC RIVERSIDE 7:00 PM | 042 | CLOSED | 0 | 0 | 489.06 | 489.06
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - OCT 03 UC DAVIS 7:00 PM | 042 | CLOSED | 0 | 0 | 601.92 | 601.92
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - OCT 04 PACIFIC 7:00 PM | 042 | CLOSED | 0 | 0 | 793.872 | 793.872
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - OCT 16 UC SANTA BARBARA 7:00 PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - OCT 18 UC IRVINE 7:00 PM | 042 | CLOSED | 0 | 0 | 1487.16 | 1487.16
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - OCT 24 CAL STATE NORTHRIDGE 7:00 PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - OCT 25 CAL STATE FULLERTON 7:00 PM | 042 | CLOSED | 0 | 0 | 432.144 | 432.144
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - SEPT 05 TULANE 10:00 AM & NEBRASKA 7:30 | 042 | CLOSED | 0 | 0 | 1373.13 | 1373.13
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - SEPT 06 NORTHEASTERN 3:00 PM | 042 | CLOSED | 0 | 0 | 1391.94 | 1391.94
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - SEPT 18 SAINT MARY'S 7:00 PM | 042 | CLOSED | 0 | 0 | 451.44 | 451.44
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - SEPT 19 STANFORD V ST MARY 7:30 PM | 042 | CLOSED | 0 | 0 | 150.48 | 150.48
PJ0002922 | 08/09 VOLLEYBALL (SERVICES FOR ATHLETICS) | POPHAM, DONALD J. | CLOSED | 2008-09-04 | CU: 08/09 VOLLEYBALL - SEPT 20 STANFORD 7:00 PM | 042 | CLOSED | 0 | 0 | 1090.98 | 1090.98
PJ0002922 Total | [7 empty] | 0 | 0 | 9651.168 | 9651.168
PJ0002921 | PAINT, REPAIR ELECTRIC, CLEAN FLOOR - KINES 43A RM 458 | GRIFFIN, PATRICK E | CLOSED | 2008-09-03 | CP: PROJECT CONTINGENCY | 043A | CLOSED | 210.37 | 0 | 0 | 0
PJ0002921 | PAINT, REPAIR ELECTRIC, CLEAN FLOOR - KINES 43A RM 458 | GRIFFIN, PATRICK E | CLOSED | 2008-09-03 | PA: PAINT 43A RM 458 | 043A | CLOSED | 1781.376 | 0 | 2607.978 | 2607.978
PJ0002921 Total | [7 empty] | 1991.746 | 0 | 2607.978 | 2607.978
PJ0002920 | INSTALL GALLERY RAILS - LIB 35 RM 216 | MAY, TOM | CLOSED | 2008-09-02 | CA:INSTALL GALLERY RAILS 35-216 | 035 | CLOSED | 984.6564 | 0 | 2100.807 | 2100.807
PJ0002920 | INSTALL GALLERY RAILS - LIB 35 RM 216 | MAY, TOM | CLOSED | 2008-09-02 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 98.46 | 0 | 0 | 0
PJ0002920 Total | [7 empty] | 1083.1164 | 0 | 2100.807 | 2100.807
PJ0002919 | WOW PRIVATE CONCERT 2008 - REC CENTER 43 MAIN GYM (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CA: INSTALL'EXIT' SIGNS AT ALL EXITS AT REC FIELD | 043 | CLOSED | 184.6 | 0 | 38.53 | 38.53
PJ0002919 | WOW PRIVATE CONCERT 2008 - REC CENTER 43 MAIN GYM (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0002919 | WOW PRIVATE CONCERT 2008 - REC CENTER 43 MAIN GYM (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | EL: PROVIDE AN ELECTRICIAN FOR FRIDAY 9/19/08 - REC 43 | 043 | CLOSED | 0 | 0 | 974.172 | 974.172
PJ0002919 | WOW PRIVATE CONCERT 2008 - REC CENTER 43 MAIN GYM (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | PL: PM REC CENTER RESTROOMS BEFORE CONCERT ON 9/19 6PM | 043 | CLOSED | 0 | 0 | 52.98 | 52.98
PJ0002919 | WOW PRIVATE CONCERT 2008 - REC CENTER 43 MAIN GYM (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | RENTAL: WOW CONCERT 9/19/08 PERIMETER | 043 | CLOSED | 0 | 0 | 40 | 40
PJ0002919 Total | [7 empty] | 184.6 | 0 | 1105.682 | 1105.682
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 09/16 WOW/SMILE & NOD CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 09/18 WOW/SMILE & NOD CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 10/04 SAM HARRIS - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 10/05 GREAT BIG SEA - CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 10/10 BUNGEE JUMPIN COWS -CLEAN THTRE, RESTROOMS AFTR 3:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 10/16 SOPHIE MILMAN -CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 10/18 CLEAN THEATRE, RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 10/25 LAR LUBOVITCH DANC -CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/13 THE BALD SUPRANO - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/14 THE BALD SUPRANO - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/15 THE BALD SUPRANO - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/20 THE BALD SUPRANO - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/21 THE BALD SUPRANO - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/22 THE BALD SUPRANO - CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 11/24 TAKACS STRING QRTET -CLEAN THTRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 12/02 WARREN MILLER FILMS - CLEAN THTRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 12/05 FALL JAZZ CONCERT - CLEAN THTRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 12/06 12 DAYS OF CHRISTMAS-CLEAN THTRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 12/07 12 DAYS OF CHRISTMAS-CLEAN THTRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 12/13 CENT. COAST DANCE - CLEAN THTRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 12/14 CENT. COAST DANCE - CLEAN THTRE, RESTROOMS BY 12:00PM | 044 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 9/27 GREAT POETS IN SONG CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 | 08/09 EXTRA CLEANING, 044 THEATRE-FALL QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-29 | CU: 9/28 CLEAN THEATRE, RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002918 Total | [7 empty] | 0 | 0 | 1551.06 | 1551.06
PJ0002917 | UPGRADE FIRE SUPPRESSANT SYSTEM - BLDG 112 RM 112G (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-29 | AD: JOC 07.014.053 STAPLES | 112 | CLOSED | 17833.5937 | 0 | 17833.5937 | 17833.5937
PJ0002917 | UPGRADE FIRE SUPPRESSANT SYSTEM - BLDG 112 RM 112G (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-29 | CP: PROJECT CONTINGENCY | 112 | CLOSED | 1927.69 | 0 | 0 | 0
PJ0002917 | UPGRADE FIRE SUPPRESSANT SYSTEM - BLDG 112 RM 112G (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-29 | EL: HOOD ALARM CONNECTION | 112 | CLOSED | 754.44 | 0 | 193.656 | 193.656
PJ0002917 | UPGRADE FIRE SUPPRESSANT SYSTEM - BLDG 112 RM 112G (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-29 | IN: UPGRADE FIRE SUPPRESSANT SYSTEM - BLDG 112 RM 112G | 112 | CLOSED | 132.552 | 0 | 115.983 | 115.983
PJ0002917 Total | [7 empty] | 20648.2757 | 0 | 18143.2327 | 18143.2327
PJ0002916 | REPAIR WALKWAY BETWEEN ADMIN 01 &A1 PRKG LOT (MAINT) | DANKO, KEN | CLOSED | 2008-08-28 | CA: REPAIR WALKWAY NORTH SIDE OF ADMIN @ A1 PRKG LOT | 001 | CLOSED | 738.4 | 0 | 900.6054 | 900.6054
PJ0002916 | REPAIR WALKWAY BETWEEN ADMIN 01 &A1 PRKG LOT (MAINT) | DANKO, KEN | CLOSED | 2008-08-28 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0002916 | REPAIR WALKWAY BETWEEN ADMIN 01 &A1 PRKG LOT (MAINT) | DANKO, KEN | CLOSED | 2008-08-28 | EO: CUT AND REMOVE CONCRETE TRIP HAZARD ADMIN PK LOT | 001 | CLOSED | 308.96 | 0 | 270.34 | 270.34
PJ0002916 Total | [7 empty] | 1047.36 | 0 | 1170.9454 | 1170.9454
PJ0002915 | REPAIR WALKWAY BETWEEN THE AVENUE & ATM MACHINES-BLDG 65 (MAINT) | DANKO, KEN | CLOSED | 2008-08-28 | CA: REPAIR CONCRETE TRIP HAZARD BY ATM MACHINES, W. SIDE UU | GENERAL | CLOSED | 369.2 | 0 | 1968.1028 | 1968.1028
PJ0002915 | REPAIR WALKWAY BETWEEN THE AVENUE & ATM MACHINES-BLDG 65 (MAINT) | DANKO, KEN | CLOSED | 2008-08-28 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002915 | REPAIR WALKWAY BETWEEN THE AVENUE & ATM MACHINES-BLDG 65 (MAINT) | DANKO, KEN | CLOSED | 2008-08-28 | EO: REMOVE CONCRETE AND REPAIR BLACKTOP AS NEEDED, W. SIDE UU | GENERAL | CLOSED | 617.92 | 0 | 463.44 | 463.44
PJ0002915 Total | [7 empty] | 987.12 | 0 | 2431.5428 | 2431.5428
PJ0002914 | INSTALL PANIC ALARM TO RETAIL SPACES - PCV 171 (NO ESTIMATE) | PAHLOW, BOB | CLOSED | 2008-08-28 | ATS-PROGRAM UPD DISPATCH FOR NEW ALARMS | 171 | CLOSED | 0 | 0 | 200.088 | 200.088
PJ0002914 | INSTALL PANIC ALARM TO RETAIL SPACES - PCV 171 (NO ESTIMATE) | PAHLOW, BOB | CLOSED | 2008-08-28 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 6.63 | 0 | 0 | 0
PJ0002914 | INSTALL PANIC ALARM TO RETAIL SPACES - PCV 171 (NO ESTIMATE) | PAHLOW, BOB | CLOSED | 2008-08-28 | IN: INSTALL PANIC ALARM TO RETAIL SPACES - PCV 171 | 171 | CLOSED | 66.276 | 0 | 16.569 | 16.569
PJ0002914 Total | [7 empty] | 72.906 | 0 | 216.657 | 216.657
PJ0002912 | HIGH TEMP ALARM FOR CENTRAL ALARM SYSTEM AT UPD - 70-116(NO EST) | PAHLOW, BOB | CLOSED | 2008-08-28 | ANTS: PROGRAM HIGH TEMP ALARM FOR CENTRAL ALARM AT UPD - 70-116 | 070 | CLOSED | 114.336 | 0 | 57.168 | 57.168
PJ0002912 | HIGH TEMP ALARM FOR CENTRAL ALARM SYSTEM AT UPD - 70-116(NO EST) | PAHLOW, BOB | CLOSED | 2008-08-28 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0002912 Total | [7 empty] | 114.336 | 0 | 57.168 | 57.168
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | CA:REMOVE CASEWORK, COUNTERS, SHELVES, ADD COVEBASE, REMOVE DOOR | 038 | CLOSED | 5321.6688 | 0 | 3241.365 | 3241.365
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 2157.91 | 0 | 0 | 0
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | CU:PROVIDE CUSTODIAL CLEANING AFTER CONSTRUCTION | 038 | CLOSED | 327.96 | 0 | 150.48 | 150.48
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | EL;DISCONNECT/REMOVE ELECTRICAL | 038 | CLOSED | 4966.2161 | 0 | 3600.2599 | 3600.2599
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | ES:REMOVE EXTRA DUCT | 038 | CLOSED | 128.064 | 0 | 190.488 | 190.488
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | IN: ROOM RENOVATION - MATH 38 RM 133 | 038 | CLOSED | 132.552 | 0 | 82.845 | 82.845
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | LO:REMOVE CORES FROM CABINETS | 038 | CLOSED | 114.336 | 0 | 57.168 | 57.168
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | MO:MOVE CHAIRS FROM 133 TO SMALL ADJACENT ROOM | 038 | CLOSED | 189 | 0 | 34.092 | 34.092
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | PA:PAINT WALLS AND CEILING | 038 | CLOSED | 4750.3202 | 0 | 6386.5007 | 6386.5007
PJ0002910 | ROOM RENOVATION - MATH 38 RM 133 | MOLLAN, CHERYL L. | CLOSED | 2008-08-22 | PL:REMOVE GASS LINES IN CASEWORK AND WALL | 038 | CLOSED | 3746.4946 | 0 | 1474.293 | 1474.293
PJ0002910 Total | [7 empty] | 21834.5217 | 0 | 15217.4916 | 15217.4916
PJ0002908 | M&R H/C 08/08:INSTALL NEW ICE MACHINE&REFRIG-H/C 27 RM 181 & 127 | PAHLOW, BOB | CLOSED | 2008-08-22 | CA: TRIM EDGE OF COUNTER SO NEW REFRIGERATOR WILL FIT. | 027 | CLOSED | 110.76 | 0 | 27.69 | 27.69
PJ0002908 | M&R H/C 08/08:INSTALL NEW ICE MACHINE&REFRIG-H/C 27 RM 181 & 127 | PAHLOW, BOB | CLOSED | 2008-08-22 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 48.96 | 0 | 0 | 0
PJ0002908 | M&R H/C 08/08:INSTALL NEW ICE MACHINE&REFRIG-H/C 27 RM 181 & 127 | PAHLOW, BOB | CLOSED | 2008-08-22 | ES: INSTALL & START UP NEW ICE MACHINE | 027 | CLOSED | 293.9069 | 0 | 514.1815 | 514.1815
PJ0002908 | M&R H/C 08/08:INSTALL NEW ICE MACHINE&REFRIG-H/C 27 RM 181 & 127 | PAHLOW, BOB | CLOSED | 2008-08-22 | ES:INSTALL & START UP NEW REFRIGERATOR | 027 | CLOSED | 293.9069 | 0 | 1046.88 | 1046.88
PJ0002908 | M&R H/C 08/08:INSTALL NEW ICE MACHINE&REFRIG-H/C 27 RM 181 & 127 | PAHLOW, BOB | CLOSED | 2008-08-22 | PL: CONNECT WATER TO NEW ICE MACHINE. | 027 | CLOSED | 0 | 0 | 461.904 | 461.904
PJ0002908 Total | [7 empty] | 747.5338 | 0 | 2050.6555 | 2050.6555
PJ0002905 | INSTALL 2 DUTCH-DOORS AND ONE WINDOW IN TOOL CRIB - BOND 197-116 | LAMPMAN, GREG | CLOSED | 2008-08-19 | AD: JOC 08.016.001 TORRES | 197 | CLOSED | 14345.5221 | 0 | 16161.2586 | 16161.2586
PJ0002905 | INSTALL 2 DUTCH-DOORS AND ONE WINDOW IN TOOL CRIB - BOND 197-116 | LAMPMAN, GREG | CLOSED | 2008-08-19 | CA: CUT OUT SHEETROCK IN BLG. 197 ROOM 115 | 197 | CLOSED | 110.76 | 0 | 313.2 | 313.2
PJ0002905 | INSTALL 2 DUTCH-DOORS AND ONE WINDOW IN TOOL CRIB - BOND 197-116 | LAMPMAN, GREG | CLOSED | 2008-08-19 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 1757.83 | 0 | 0 | 0
PJ0002905 | INSTALL 2 DUTCH-DOORS AND ONE WINDOW IN TOOL CRIB - BOND 197-116 | LAMPMAN, GREG | CLOSED | 2008-08-19 | EL: RELOCATE ELECT CONDUITS AND ALARMS | 197 | CLOSED | 2270.208 | 0 | 1568.592 | 1568.592
PJ0002905 | INSTALL 2 DUTCH-DOORS AND ONE WINDOW IN TOOL CRIB - BOND 197-116 | LAMPMAN, GREG | CLOSED | 2008-08-19 | IN: INSTALL 2 DUTCH-DOORS & 1 WINDOW IN TOOL CRIB, 197-116 | 197 | CLOSED | 0 | 0 | 397.656 | 397.656
PJ0002905 | INSTALL 2 DUTCH-DOORS AND ONE WINDOW IN TOOL CRIB - BOND 197-116 | LAMPMAN, GREG | CLOSED | 2008-08-19 | PA:PAINT OUT FOR DOOR AND WINDOW PROJECT IN 197 | 197 | CLOSED | 2070.144 | 0 | 1670.316 | 1670.316
PJ0002905 Total | [7 empty] | 20554.4641 | 0 | 20111.0226 | 20111.0226
PJ0002904 | MOVE DOORS WITH PUSH-BUTTON LOCKS TO ENGR IV RMS 321, 323, 327 | GRIFFIN, PATRICK E | CLOSED | 2008-08-19 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 275.18 | 0 | 0 | 0
PJ0002904 | MOVE DOORS WITH PUSH-BUTTON LOCKS TO ENGR IV RMS 321, 323, 327 | GRIFFIN, PATRICK E | CLOSED | 2008-08-19 | LO: INSTALL PUSH BUTTON LOCKS AT ENG IV | 192 | CLOSED | 2751.84 | 0 | 2702.448 | 2702.448
PJ0002904 | MOVE DOORS WITH PUSH-BUTTON LOCKS TO ENGR IV RMS 321, 323, 327 | GRIFFIN, PATRICK E | CLOSED | 2008-08-19 | LO:ADJUST LOCKSETS AND TRILOGY LOCKS AT ENG IV | 192 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002904 Total | [7 empty] | 3027.02 | 0 | 2759.616 | 2759.616
PJ0002903 | CONTRACT W/ BELFOR FOR MOLD/MOISTURE REMEDIATION -BLDG 27 RM 192 | GRIFFIN, PATRICK E | CLOSED | 2008-08-18 | AD: BELFOR | 027 | CLOSED | 4011.81 | 0 | 4011.81 | 4011.81
PJ0002903 | CONTRACT W/ BELFOR FOR MOLD/MOISTURE REMEDIATION -BLDG 27 RM 192 | GRIFFIN, PATRICK E | CLOSED | 2008-08-18 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 429.26 | 0 | 0 | 0
PJ0002903 Total | [7 empty] | 4441.07 | 0 | 4011.81 | 4011.81
PJ0002902 | SR 08/09: EXTEND EXISTING FENCE & ADD GATE AT LOWER PATIO - 051 | POPHAM, DONALD J. | CLOSED | 2008-08-14 | CA:EXTEND EXISTING FENCING AT LOWER PARIO - UH-51 | 051 | CLOSED | 3117.362 | 0 | 2855.3026 | 2855.3026
PJ0002902 | SR 08/09: EXTEND EXISTING FENCE & ADD GATE AT LOWER PATIO - 051 | POPHAM, DONALD J. | CLOSED | 2008-08-14 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 532.62 | 0 | 0 | 0
PJ0002902 | SR 08/09: EXTEND EXISTING FENCE & ADD GATE AT LOWER PATIO - 051 | POPHAM, DONALD J. | CLOSED | 2008-08-14 | LA:REMOVE HOLLY AND PITTOSPORUM FOR FENCE - UH51 | 051 | CLOSED | 385.8508 | 0 | 33.64 | 33.64
PJ0002902 | SR 08/09: EXTEND EXISTING FENCE & ADD GATE AT LOWER PATIO - 051 | POPHAM, DONALD J. | CLOSED | 2008-08-14 | PA: PAINT / STAIN FENCE EXTENTION AT UNIVERSITY HOUSE | 051 | CLOSED | 846.6602 | 0 | 162.72 | 162.72
PJ0002902 Total | [7 empty] | 4882.493 | 0 | 3051.6626 | 3051.6626
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: INSTALL CP RUGS IN SPANOS STADIUM ELEVATORS | 061 | CLOSED | 184.6 | 0 | 369.2 | 369.2
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: 08/09 FOOTBALL PRES SUITE - NOV 29 WEBER ST 6:05 PM | 061 | CLOSED | 0 | 0 | 450.945 | 450.945
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: 08/09 FOOTBALL PRES SUITES - NOV 01 IDAHO 6PM | 061 | CLOSED | 0 | 0 | 110.5275 | 110.5275
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: 08/09 FOOTBALL PRES SUITES - NOV 08 N. CAROLINA 4PM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: 08/09 FOOTBALL PRES SUITES - OCT 04 S. DAKOTA 6PM | 061 | CLOSED | 0 | 0 | 191.31 | 191.31
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: 08/09 WOMEN'S SOCCER PRES SUITES - OCT 8 RIVERSIDE 7:00 PM | 061 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: CLEANING OF COPPER AT SPANOS STADIUM SUITES FOR 08/09061 | 061D | CLOSED | 0 | 0 | 2022.0525 | 2022.0525
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: FRI 9/5 - CUST SERV/SETUP FOR ATHLETIC DIR. COUNC MTG | 061D | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: GENERAL CLEANING FOR 08/09 AT SPANOS STADIUM SUITES 061 | 061D | CLOSED | 0 | 0 | 2882.3877 | 2882.3877
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: PRE-GAME RECEPTION PRES. SUITE CAL POLY VS CS BAKERSFIELD | 061 | CLOSED | 0 | 0 | 245.97 | 245.97
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: PRESIDENT'S SUITE SUPPORT FOR SOCCER AND FB - 11/15 | 061 | CLOSED | 0 | 0 | 68.325 | 68.325
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: SAT 9/6 - CUST SERV/SETUP FOR PREGAME RECEPTION - SPANOS 61 | 061 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: SUPPORT FOR PREGAME RECEPTION AT SPANOS SUITES ON 10/17 | 061 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | ES: PROGRAM PRES SUITES AC TO OPERATE DURING SOCCER GAME SEPT 24 | 061 | CLOSED | 106.72 | 0 | 53.36 | 53.36
PJ0002901 | 08/09 STADIUM SUITES - EVENT SUPPORT (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | SUPPLY RENTAL: FRI 9/5 ATHLETIC DIRECTORS COUNCIL MEETING | 061D | CLOSED | 0 | 0 | 66.25 | 66.25
PJ0002901 Total | [7 empty] | 291.32 | 0 | 6870.2777 | 6870.2777
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | AD: PRESIDENT'S DINNER SUPPORT ON 12/14 - MATERIALS ONLY | 051 | CLOSED | 0 | 0 | 265.992 | 265.992
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: ASSIST WITH THE INSTALLATION OF ROPE LIGHTS AT UNIV HOUSE | 051 | CLOSED | 369.2 | 0 | 821.07 | 821.07
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: CUSTODIAL SUPPORT FOR UNIV HOUSE EVENT 3/12 | 051 | CLOSED | 0 | 0 | 27.33 | 27.33
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: INSTALL CLOUDS AND REMOVE TUNNEL STRUCTURE - UH51 | 051 | CLOSED | 369.2 | 0 | 646.1 | 646.1
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: RE-ROLL TENT AT UNIVERSITY HOUSE-WEEK OF 8/4 | 051 | CLOSED | 369.2 | 0 | 299.975 | 299.975
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: ROLL UP CANOPY FOR SUMMER | 051 | CLOSED | 692.25 | 0 | 311.5125 | 311.5125
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: SET UP TENT FOR SPECIAL EVENT AT UH 51 BEFORE MAR 2 | 051 | CLOSED | 553.8 | 0 | 692.25 | 692.25
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: SETUP CANOPY IN BACK PATIO BEFORE 9/12/2008 | 051 | CLOSED | 415.35 | 0 | 461.5 | 461.5
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: SETUP CANOPY SIDES AT UNIV. HOUSE BEFORE 10/9 | 051 | CLOSED | 92.3 | 0 | 412.555 | 412.555
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CA: TENT CANOPY AT UH-51 ON 5/8 AND 5/9 | 051 | CLOSED | 369.2 | 0 | 658.9865 | 658.9865
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: CUST. SUPPORT FOR GATES FDN MEETING | 051 | CLOSED | 0 | 0 | 375.7875 | 375.7875
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: CUSTODIAL SUPPORT FOR ASCI ADVISORY DINNER 10/9 | 051 | CLOSED | 0 | 0 | 147.582 | 147.582
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: CUSTODIAL SUPPORT FOR CP SCHOLARS RECEPTION - MAR 2 | 051 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: CUSTODIAL SUPPORT OF CP ARTS RECEPTION-5/7 AFTER 7PM | 051 | CLOSED | 0 | 0 | 13.665 | 13.665
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: DR. NARUSE VISIT AT UNIVERSITY HOUSE - 7/23 | 051 | CLOSED | 0 | 0 | 40.995 | 40.995
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: GENERAL CLEANING FOR 08/09 AT UNVERSITY HOUSE 051 | 051 | CLOSED | 0 | 0 | 4400.13 | 4400.13
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: MON 9/15 - CUST SERVICE & SETUP FOR FAC.PROF STAFF RECEPTION | 051 | CLOSED | 0 | 0 | 102.4875 | 102.4875
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: NANJING EVENT SUPPORT AT UNIVERSITY HOUSE - 4/17 | 051 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: ONSITE SUPPORT FOR UNIVERSITY HOUSE DINNER 12/14 5-8 | 051 | CLOSED | 0 | 0 | 505.605 | 505.605
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: PREPARATION FOR UNIVERSITY HOUSE DINNER ON 12/14 | 051 | CLOSED | 0 | 0 | 60.563 | 60.563
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: SUN 9/14 - CUST SERVICE & SETUP FOR CPOLY WMN'S CLUB WELCOME | 051 | CLOSED | 0 | 0 | 81.99 | 81.99
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: SUPPORT FOR POLY REPS EVENT -4/14 | 051 | CLOSED | 0 | 0 | 122.985 | 122.985
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: SUPPORT FOR ROGERS PRIVATE RECEPTION ON 10/17 AT U.H. | 051 | CLOSED | 0 | 0 | 136.65 | 136.65
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: TUES 9/2 - CUST SERV/SETUP FOR JUN NARUSE LUNCHEON | 051 | CLOSED | 0 | 0 | 68.325 | 68.325
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | CU: UNIV. HOUSE SUPPORT FOR EVENTS WEEK OF 11/3 - 11/7 | 051 | CLOSED | 0 | 0 | 307.4625 | 307.4625
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | EL: ELECTRICAL SUPPORT FOR PRES. XMAS PARTYAT UNIV HOUSE 12/12 | 051 | CLOSED | 0 | 0 | 249.365 | 249.365
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | GR: LANDSCAPE SUPPORT FOR ASCI DINNER ON 10/9 (N/L) | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | GR: MON 9/15 - LAND SERVICE & SETUP FOR FAC.PROF STAFF RECEPTION | 051 | CLOSED | 0 | 0 | 134.56 | 134.56
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | LA: PRESIDENT'S XMAS PARTY EVENT SUPPORT | 051 | CLOSED | 0 | 0 | 227.87 | 227.87
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | MC: MOVE FICUS TREES AND CART TO UH 51 | 051 | CLOSED | 0 | 0 | 4.735 | 4.735
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | MC: MOVE PLANTS FROM PAC TO UNIVERSITY HOUSE ON 11/13 | 051 | CLOSED | 0 | 0 | 33.3525 | 33.3525
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | MC: REMOVE ALL JUNK FROM AROUND UNIV HOUSE STORAGE BLDG | 051 | CLOSED | 0 | 0 | 14.205 | 14.205
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | PA: REPAIR CHIPPED PAINT IN DINING ROOM ARCHWAY - UH51 | 051 | CLOSED | 0 | 0 | 23.83 | 23.83
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | PL: PM RESTROOMS AT UNIVERSITY HOUSE BEFORE 12/14 | 051 | CLOSED | 0 | 0 | 105.96 | 105.96
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | PL: PM THE RESTROOMS AT UNIV. HOUSE FOR WEEKEND EVENT ON 9/13 | 051 | CLOSED | 0 | 0 | 52.98 | 52.98
PJ0002900 | 08/09 UNIVERSITY HOUSE EVENT SUPPORT BLDG 51 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-08-12 | PL: PM UNIVSERSITY HOUSE BEFORE 9/12 | 051 | CLOSED | 0 | 0 | 105.96 | 105.96
PJ0002900 Total | [7 empty] | 3230.5 | 0 | 12132.956 | 12132.956
PJ0002899 | INSTALL NEW CARPET - DEXTER 34 RM 251 | POPHAM, DONALD J. | CLOSED | 2008-08-06 | AD: FLOORTEC | 034 | CLOSED | 4042.353 | 0 | 2686.7058 | 2686.7058
PJ0002899 | INSTALL NEW CARPET - DEXTER 34 RM 251 | POPHAM, DONALD J. | CLOSED | 2008-08-06 | CA: REMOVE COVEBASE IN ROOMS 251, 251A, & 251B | 034 | CLOSED | 126.2664 | 0 | 732.036 | 732.036
PJ0002899 | INSTALL NEW CARPET - DEXTER 34 RM 251 | POPHAM, DONALD J. | CLOSED | 2008-08-06 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 416.94 | 0 | 0 | 0
PJ0002899 Total | [7 empty] | 4585.5594 | 0 | 3418.7418 | 3418.7418
PJ0002898 | REMOVE RAISED FLOOR OR ELECTRICAL OUTLETS - ENGR W 21 RM 134 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-05 | CA:REPAIR HOLES IN CARPET 21-134 | 021 | CLOSED | 221.52 | 0 | 317.58 | 317.58
PJ0002898 | REMOVE RAISED FLOOR OR ELECTRICAL OUTLETS - ENGR W 21 RM 134 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-05 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 72.91 | 0 | 0 | 0
PJ0002898 | REMOVE RAISED FLOOR OR ELECTRICAL OUTLETS - ENGR W 21 RM 134 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-08-05 | EL:DISCONNECT ELECTRICAL IN POWER FLOOR 21-134 | 021 | CLOSED | 507.552 | 0 | 257.286 | 257.286
PJ0002898 Total | [7 empty] | 801.982 | 0 | 574.866 | 574.866
PJ0002896 | SR 08/09: INTERSECTION OFF VIA CARTA BTWN E. CREEK RD & HIGHLAND | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-30 | AD: JOC 07.015.017 MAINO | GENERAL | CLOSED | 83275.5 | 0 | 83275.49 | 83275.49
PJ0002896 | SR 08/09: INTERSECTION OFF VIA CARTA BTWN E. CREEK RD & HIGHLAND | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-30 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 9221.95 | 0 | 0 | 0
PJ0002896 Total | [7 empty] | 92497.45 | 0 | 83275.49 | 83275.49
PJ0002895 | LT. GOV JOHN GARAMENDI NEWS CONFERENCE 8/1/08 - C7 PRKG LOT | POPHAM, DONALD J. | CLOSED | 2008-07-30 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002895 | LT. GOV JOHN GARAMENDI NEWS CONFERENCE 8/1/08 - C7 PRKG LOT | POPHAM, DONALD J. | CLOSED | 2008-07-30 | CU: RENTAL- LT. GOV JOHN GARAMANDI NEWS CONF 8/1/08 -C7 PRKG LOT | GENERAL | CLOSED | 0 | 0 | 45 | 45
PJ0002895 Total | [7 empty] | 0 | 0 | 45 | 45
PJ0002894 | INSTALL FLOOR DRAIN - FISHER SCI 33 RM 395(NO ESTIMATE REQUIRED) | RIVERA, MARIO L | CLOSED | 2008-07-25 | CA: PREP WILL BAILEY'S OFFICE OR FLOOR DRAIN AT 33-395 | 033 | CLOSED | 221.52 | 0 | 135.096 | 135.096
PJ0002894 | INSTALL FLOOR DRAIN - FISHER SCI 33 RM 395(NO ESTIMATE REQUIRED) | RIVERA, MARIO L | CLOSED | 2008-07-25 | CP: PROJECT CONTINGENCY | 033 | CLOSED | 0 | 0 | 0 | 0
PJ0002894 | INSTALL FLOOR DRAIN - FISHER SCI 33 RM 395(NO ESTIMATE REQUIRED) | RIVERA, MARIO L | CLOSED | 2008-07-25 | ES: SHUT DOWN STEAM BOILER AT FISHER SCI. | 033 | CLOSED | 128.064 | 0 | 192.096 | 192.096
PJ0002894 | INSTALL FLOOR DRAIN - FISHER SCI 33 RM 395(NO ESTIMATE REQUIRED) | RIVERA, MARIO L | CLOSED | 2008-07-25 | PL: INSTALL NEW FLOOR DRAIN FOR AUTOCLAVE AT 33-395 | 033 | CLOSED | 0 | 0 | 3417.7252 | 3417.7252
PJ0002894 Total | [7 empty] | 349.584 | 0 | 3744.9172 | 3744.9172
PJ0002893 | COMPLETE MAINTENANCE - PAC WALK-THRU SUMMER 2008 | GRIFFIN, PATRICK E | CLOSED | 2008-07-25 | CA-COMPLETE PAC MAINTENANCE 7/08 | 006 | CLOSED | 1846 | 0 | 2018.7375 | 2018.7375
PJ0002893 | COMPLETE MAINTENANCE - PAC WALK-THRU SUMMER 2008 | GRIFFIN, PATRICK E | CLOSED | 2008-07-25 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002893 | COMPLETE MAINTENANCE - PAC WALK-THRU SUMMER 2008 | GRIFFIN, PATRICK E | CLOSED | 2008-07-25 | ES-COMPLETE MAINTENANCE ITEMS AT PAC (NO LABOR) | 006 | CLOSED | 213.44 | 0 | 0 | 0
PJ0002893 | COMPLETE MAINTENANCE - PAC WALK-THRU SUMMER 2008 | GRIFFIN, PATRICK E | CLOSED | 2008-07-25 | LS-COMPLETE MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 190.56 | 0 | 190.56 | 190.56
PJ0002893 | COMPLETE MAINTENANCE - PAC WALK-THRU SUMMER 2008 | GRIFFIN, PATRICK E | CLOSED | 2008-07-25 | PA-COMPLETE MAINTENANCE PAINTING AT PAC | 006 | CLOSED | 5719.2 | 0 | 4125.53 | 4125.53
PJ0002893 Total | [7 empty] | 7969.2 | 0 | 6334.8275 | 6334.8275
PJ0002889 | SECURITY FIRE ALARM REQUIREMENT - COMP SCI 14 RM 232 | MAY, TOM | CLOSED | 2008-07-23 | AD: JOC 07.015.018 MAINO | 014 | CLOSED | 51538.2513 | 0 | 51538.2513 | 51538.2513
PJ0002889 | SECURITY FIRE ALARM REQUIREMENT - COMP SCI 14 RM 232 | MAY, TOM | CLOSED | 2008-07-23 | AD: THOMA ELECTRIC | 014 | CLOSED | 5290.08 | 0 | 5290.08 | 5290.08
PJ0002889 | SECURITY FIRE ALARM REQUIREMENT - COMP SCI 14 RM 232 | MAY, TOM | CLOSED | 2008-07-23 | CA: INSTALL WHITE BOARDS IN 14-238 | 014 | CLOSED | 941.52 | 0 | 994.23 | 994.23
PJ0002889 | SECURITY FIRE ALARM REQUIREMENT - COMP SCI 14 RM 232 | MAY, TOM | CLOSED | 2008-07-23 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0002889 Total | [7 empty] | 57769.8513 | 0 | 57822.5613 | 57822.5613
PJ0002886 | SR 08/09: PREINSULATED STEEL PIPE MATERIAL FOR UTILIDOR PROJECT | ELLIOT, DENNIS K | CLOSED | 2008-07-17 | AD: CONWAY FREIGHT (CREDIT CARD CHARGES) | 040 | CLOSED | 2100 | 0 | 3175 | 3175
PJ0002886 | SR 08/09: PREINSULATED STEEL PIPE MATERIAL FOR UTILIDOR PROJECT | ELLIOT, DENNIS K | CLOSED | 2008-07-17 | AD: COOK ENGINEERING | 040 | CLOSED | 3520 | 0 | 3520 | 3520
PJ0002886 | SR 08/09: PREINSULATED STEEL PIPE MATERIAL FOR UTILIDOR PROJECT | ELLIOT, DENNIS K | CLOSED | 2008-07-17 | CA - UNLOAD AND RACK PIPE AT E-SURPLUS YARD | 040 | CLOSED | 369.2 | 0 | 1096.175 | 1096.175
PJ0002886 | SR 08/09: PREINSULATED STEEL PIPE MATERIAL FOR UTILIDOR PROJECT | ELLIOT, DENNIS K | CLOSED | 2008-07-17 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 647.38 | 0 | 0 | 0
PJ0002886 | SR 08/09: PREINSULATED STEEL PIPE MATERIAL FOR UTILIDOR PROJECT | ELLIOT, DENNIS K | CLOSED | 2008-07-17 | MO: UNLOAD PIPE SHIPMENT AND STORE IN SURPLUS YARD | 040 | CLOSED | 420 | 0 | 80.495 | 80.495
PJ0002886 Total | [7 empty] | 7056.58 | 0 | 7871.67 | 7871.67
PJ0002884 | M&R PARK 08/09 - ADA PARKING DESIGN FOR ADMIN PRKG LOT - P-A01 | POPHAM, DONALD J. | CLOSED | 2008-07-16 | AD: GSI SOILS | P-A01 | CLOSED | 3745 | 0 | 3745 | 3745
PJ0002884 | M&R PARK 08/09 - ADA PARKING DESIGN FOR ADMIN PRKG LOT - P-A01 | POPHAM, DONALD J. | CLOSED | 2008-07-16 | AD: RENGEL AND COMPANY | P-A01 | CLOSED | 13744.15 | 0 | 13744.15 | 13744.15
PJ0002884 | M&R PARK 08/09 - ADA PARKING DESIGN FOR ADMIN PRKG LOT - P-A01 | POPHAM, DONALD J. | CLOSED | 2008-07-16 | CP: PROJECT CONTINGENCY | P-A01 | CLOSED | 1374.42 | 0 | 0 | 0
PJ0002884 Total | [7 empty] | 18863.57 | 0 | 17489.15 | 17489.15
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - AUG 22 BRGHAM YOUNG 7:00 PM | 061 | CLOSED | 0 | 0 | 748.1629 | 748.1629
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - AUG 29 SAN DIEGO STATE 7:00 PM | 061 | CLOSED | 0 | 0 | 455.292 | 455.292
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - NOV 02 LONG BEACH STATE 12:00 PM | 061 | CLOSED | 0 | 0 | 552.24 | 552.24
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - OCT 12 CAL STATE NORTHRIDGE 1:00 PM | 061 | CLOSED | 0 | 0 | 752.4 | 752.4
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - OCT 19 UC SANTA BARBARA 5:00 PM | 061 | CLOSED | 0 | 0 | 752.4 | 752.4
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - OCT 31 UC IRVINE 7:00 PM | 061 | CLOSED | 0 | 0 | 399.348 | 399.348
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - SEPT 05 WISCONSIN 2:00 PM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - SEPT 14 FLORIDA INTERNATIONAL 1:00 PM | 061 | CLOSED | 0 | 0 | 1021.041 | 1021.041
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - SEPT 21 STANFORD 11:00 AM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - SEPT 26 UTAH STATE 7:00 AM | 061 | CLOSED | 0 | 0 | 517.032 | 517.032
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: 08/09 WOMEN'S SOCCER - SEPT 28 UTAH 1:00 PM | 061 | CLOSED | 0 | 0 | 1066.86 | 1066.86
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: SPANOS SUITES CLEANUP WOMEN'S SOCCER-SEPT 21 STANFORD(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: WOMEN'S SOCCER CLEAN SUITES - AUG 22 BRGHAM YOUNG 7:00 PM | 061 | CLOSED | 0 | 0 | 24.597 | 24.597
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: WOMEN'S SOCCER CLEAN SUITES - SEPT 14 FL. INTL (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: WOMEN'S SOCCER WASH BLEACHERS- AUG 22 BRGHAM YOUNG 7:00 PM | 061 | CLOSED | 0 | 0 | 2633.4 | 2633.4
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU:SUITE CLEANING FOR WOMENS SOCCER ON 10/19 | 061 | CLOSED | 0 | 0 | 295.164 | 295.164
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - AUG 22 BRGHAM YOUNG 7:00 PM | 061 | CLOSED | 0 | 0 | 544.968 | 544.968
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - AUG 29 SAN DIEGO STATE 7:00 PM | 061 | CLOSED | 0 | 0 | 911.856 | 911.856
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - OCT 12 CAL STATE NORTHRIDGE 1:00 PM | 061 | CLOSED | 0 | 0 | 274.272 | 274.272
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - OCT 31 UC IRVINE 7:00 PM | 061 | CLOSED | 0 | 0 | 268.332 | 268.332
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - SEPT 05 WISCONSIN 2:00 PM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - SEPT 14 FLORIDA INTERNATIONAL 1:00 PM | 061 | CLOSED | 0 | 0 | 207.78 | 207.78
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - SEPT 21 STANFORD 11:00 AM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - SEPT 26 UTAH STATE 7:00 AM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER - SEPT 28 UTAH 1:00 PM | 061 | CLOSED | 0 | 0 | 208.386 | 208.386
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER-NOV 02 LONG BEACH STATE 12:00 PM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: 08/09 WOMEN'S SOCCER-OCT 19 UC SANTA BARBARA 5:00 PM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: LINE FIELD 6 FOR WOMEN'S SOCCER PRACTICE | 061 | CLOSED | 0 | 0 | 429.804 | 429.804
PJ0002882 | 08/09 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-07-14 | GR: LINE SPRTS COMPLEX FIELD (4&5) WOMENS & MENS SOCCER PRACTICE | 061 | CLOSED | 0 | 0 | 1300.686 | 1300.686
PJ0002882 Total | [7 empty] | 0 | 0 | 13364.0209 | 13364.0209
PJ0002881 | PROVIDE SUPPORT FOR CHRIST IN YOUTH CONFERENCE - MOTT42(NO EST.) | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CA: PULL OUT EAST BLEACHERS & BLACK OUT WINDOWS - MOTT GYM | 042 | CLOSED | 664.56 | 0 | 1119.489 | 1119.489
PJ0002881 | PROVIDE SUPPORT FOR CHRIST IN YOUTH CONFERENCE - MOTT42(NO EST.) | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002881 | PROVIDE SUPPORT FOR CHRIST IN YOUTH CONFERENCE - MOTT42(NO EST.) | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: CHANGE OUT TRASHCANS IN MOTT GYM FOR CIY | 042 | CLOSED | 0 | 0 | 196.776 | 196.776
PJ0002881 | PROVIDE SUPPORT FOR CHRIST IN YOUTH CONFERENCE - MOTT42(NO EST.) | POPHAM, DONALD J. | CLOSED | 2008-07-14 | CU: RENTALS CHRIST IN YOUTH 7/18-7/28 - MOTT 42 | 042 | CLOSED | 0 | 0 | 562.5 | 562.5
PJ0002881 | PROVIDE SUPPORT FOR CHRIST IN YOUTH CONFERENCE - MOTT42(NO EST.) | POPHAM, DONALD J. | CLOSED | 2008-07-14 | EL: TIE IN CIY ELECTRICAL TO PANEL AT MOTT GYM 7/19/2008 | 042 | CLOSED | 0 | 0 | 603.87 | 603.87
PJ0002881 Total | [7 empty] | 664.56 | 0 | 2482.635 | 2482.635
PJ0002880 | REMOVE AND REPLACE BLINDS - ENGR W 21 RM 244-250 | GRIFFIN, PATRICK E | CLOSED | 2008-07-14 | CA:REMOVE AND INSTALL BLINDS IN ENG WEST | 021 | CLOSED | 8698.7262 | 0 | 4200.6419 | 4200.6419
PJ0002880 | REMOVE AND REPLACE BLINDS - ENGR W 21 RM 244-250 | GRIFFIN, PATRICK E | CLOSED | 2008-07-14 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 1302.92 | 0 | 0 | 0
PJ0002880 | REMOVE AND REPLACE BLINDS - ENGR W 21 RM 244-250 | GRIFFIN, PATRICK E | CLOSED | 2008-07-14 | PA: PATCH AND PAINT SILLS, HEADS, AND JAMBS IN ENG WEST | 021 | CLOSED | 4330.4647 | 0 | 5138.484 | 5138.484
PJ0002880 Total | [7 empty] | 14332.1109 | 0 | 9339.1259 | 9339.1259
PJ0002879 | SP 08/09: MECHANICAL SYSTEMS REVIEW-CAMPUS WIDE (CHEVRON) | ELLIOT, DENNIS K | CLOSED | 2008-07-09 | AD: ASAP REPROGRAPHICS - PAID FROM PJ FUNDS | GENERAL | CLOSED | 0 | 0 | 560.24 | 560.24
PJ0002879 | SP 08/09: MECHANICAL SYSTEMS REVIEW-CAMPUS WIDE (CHEVRON) | ELLIOT, DENNIS K | CLOSED | 2008-07-09 | AD: MECA - MJ AND SR | GENERAL | CLOSED | 0 | 0 | 6127.88 | 6127.88
PJ0002879 | SP 08/09: MECHANICAL SYSTEMS REVIEW-CAMPUS WIDE (CHEVRON) | ELLIOT, DENNIS K | CLOSED | 2008-07-09 | AD: MECA - SP | GENERAL | CLOSED | 0 | 0 | 5626.06 | 5626.06
PJ0002879 | SP 08/09: MECHANICAL SYSTEMS REVIEW-CAMPUS WIDE (CHEVRON) | ELLIOT, DENNIS K | CLOSED | 2008-07-09 | AD: P2S ENGINEERING - SP & AUXILLIARIES | GENERAL | CLOSED | 0 | 0 | 15552.8245 | 15552.8245
PJ0002879 | SP 08/09: MECHANICAL SYSTEMS REVIEW-CAMPUS WIDE (CHEVRON) | ELLIOT, DENNIS K | CLOSED | 2008-07-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 27151.27 | 0 | 0 | 0
PJ0002879 Total | [7 empty] | 27151.27 | 0 | 27867.0045 | 27867.0045
PJ0002878 | CARPET REMOVAL/INSTALL & REPAINTING WALLS (SEE TASK) - SCI 52 | MAY, TOM | CLOSED | 2008-07-09 | AD: FLOORTEC | 052 | CLOSED | 924.3944 | 0 | 924.3944 | 924.3944
PJ0002878 | CARPET REMOVAL/INSTALL & REPAINTING WALLS (SEE TASK) - SCI 52 | MAY, TOM | CLOSED | 2008-07-09 | CA:REMOVE CARPET AND TACK STRIPS 52-42C | 052 | CLOSED | 2860.1286 | 0 | 2576.07 | 2576.07
PJ0002878 | CARPET REMOVAL/INSTALL & REPAINTING WALLS (SEE TASK) - SCI 52 | MAY, TOM | CLOSED | 2008-07-09 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 205.35 | 0 | 0 | 0
PJ0002878 | CARPET REMOVAL/INSTALL & REPAINTING WALLS (SEE TASK) - SCI 52 | MAY, TOM | CLOSED | 2008-07-09 | CU: CLEAN ROOM AFTER CARPET INSTALLATION | 052 | CLOSED | 112.8182 | 0 | 601.92 | 601.92
PJ0002878 Total | [7 empty] | 4102.6912 | 0 | 4102.3844 | 4102.3844
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | AD: DUMPSTER COSTS | 035 | CLOSED | 3531 | 0 | 2601.13 | 2601.13
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | AD: FLOOR CONNECTION | 035 | CLOSED | 2959.9731 | 0 | 2959.9731 | 2959.9731
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | AD: SANTA MARIA ACOUSTICAL | 035 | CLOSED | 3210 | 0 | 5079.29 | 5079.29
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | CA: ASSIST PAINTERS AT LIBRARY 216 | 035 | CLOSED | 0 | 0 | 55.38 | 55.38
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 1076.11 | 0 | 0 | 0
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | EO:ASSIST IN REMOVAL OF CUBICLES FROM THE LIBRARY | 035 | CLOSED | 556.128 | 0 | 509.784 | 509.784
PJ0002877 | REMOVE/DISPOSE OF CUBICLES & REPLACE CARPET - LIB 35 | MAY, TOM | CLOSED | 2008-07-09 | MO:ASSIST IN REMOVAL OF CUBICLES FROM LIBRARY | 035 | CLOSED | 504 | 0 | 449.874 | 449.874
PJ0002877 Total | [7 empty] | 11837.2111 | 0 | 11655.4311 | 11655.4311
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | AD: CHECK OUT WAREHOUSE SUPPLIES FOR CANYON POST RE-DESIGN | 171 | CLOSED | 0 | 0 | 47.8243 | 47.8243
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | AD: JOC 07.015.019 MAINO | 171 | CLOSED | 16467.2893 | 0 | 16467.2893 | 16467.2893
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | CA: REMOVE THE "LETTER" IN-BOX TRAY - SEE CASSANDRA FOR DETAILS | 171 | CLOSED | 0 | 0 | 12.168 | 12.168
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | CA:TAKE UP & REINSTALL VINYL SQS/COVE BASE - LOBBY RT OF SER WIN | 171 | CLOSED | 221.52 | 0 | 198.438 | 198.438
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | CP: PROJECT CONTINGENCY | 171 | CLOSED | 1923.74 | 0 | 0 | 0
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | EL: REWIRE ELCTRICAL OUTLET FROM LIGHT SWITCH | 171 | CLOSED | 126.888 | 0 | 63.444 | 63.444
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | PA: PAINT ROOM | 171 | CLOSED | 2421.72 | 0 | 818.088 | 818.088
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | PA: PAINT THE MAILBOX END CAPS | 171 | CLOSED | 0 | 0 | 719.892 | 719.892
PJ0002876 | RE-DESIGN POST OFFICE - CANYON POST 171A | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-02 | PA: REMOVE 3 SETS OF GRAPHICS FROM END CAPS OF MAIL BAYS - 171A | 171 | CLOSED | 0 | 0 | 1497.384 | 1497.384
PJ0002876 Total | [7 empty] | 21161.1573 | 0 | 19824.5276 | 19824.5276
PJ0002875 | ANC PALLET RACKING INSTALLATION - ANC 154 | HOGAN, MIKE | CLOSED | 2008-07-02 | AD: CANNON AND ASSOCIATES | 154 | CLOSED | 2675 | 0 | 2675 | 2675
PJ0002875 | ANC PALLET RACKING INSTALLATION - ANC 154 | HOGAN, MIKE | CLOSED | 2008-07-02 | AD: SEISMIC PEER REVIEW - ENGLEKIRK AND SABOL | 154 | CLOSED | 535 | 0 | 535 | 535
PJ0002875 | ANC PALLET RACKING INSTALLATION - ANC 154 | HOGAN, MIKE | CLOSED | 2008-07-02 | CA: INSTALL ANCHORS FOR PALLET RACKING SYSTEM AT ANC | 154 | CLOSED | 470.76 | 0 | 768.594 | 768.594
PJ0002875 | ANC PALLET RACKING INSTALLATION - ANC 154 | HOGAN, MIKE | CLOSED | 2008-07-02 | CP: PROJECT CONTINGENCY | 154 | CLOSED | 405.33 | 0 | 0 | 0
PJ0002875 | ANC PALLET RACKING INSTALLATION - ANC 154 | HOGAN, MIKE | CLOSED | 2008-07-02 | IN: ANC PALLET RACKING SYSTEM | 154 | CLOSED | 165.69 | 0 | 66.276 | 66.276
PJ0002875 Total | [7 empty] | 4251.78 | 0 | 4044.87 | 4044.87
PJ0002874 | M&R H/C 08/09: WINDOW COVERINGS - BLDG 27 | GRIFFIN, PATRICK E | CLOSED | 2008-07-02 | CA:FURNISH & INSTALL NEW WINDOW BLINDS IN VARIOUS ROOMS - H/C 27 | 027 | CLOSED | 1662.0288 | 0 | 2637.984 | 2637.984
PJ0002874 | M&R H/C 08/09: WINDOW COVERINGS - BLDG 27 | GRIFFIN, PATRICK E | CLOSED | 2008-07-02 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 166.23 | 0 | 0 | 0
PJ0002874 Total | [7 empty] | 1828.2588 | 0 | 2637.984 | 2637.984
PJ0002873 | M&R H/C 08/09: EMERGENCY LIGHTING - BLDG 27 | VELARDE, DENIS L | CLOSED | 2008-07-02 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 495.45 | 0 | 0 | 0
PJ0002873 | M&R H/C 08/09: EMERGENCY LIGHTING - BLDG 27 | VELARDE, DENIS L | CLOSED | 2008-07-02 | EL: INSTALL EMERGENCY LIGHTING IN SEVERAL ROOMS AT HEALTH CENTER | 027 | CLOSED | 4954.5634 | 0 | 5572.8576 | 5572.8576
PJ0002873 Total | [7 empty] | 5450.0134 | 0 | 5572.8576 | 5572.8576
PJ0002871 | M&R H/C 08/09: INTERNET CONNECTIVITY IN TREATMENT ROOMS-BLDG 27 | PAHLOW, BOB | CLOSED | 2008-07-02 | CA: MOUNT ERGOTRON COMBO ARMS - ADDITIONAL WORK | 027 | CLOSED | 4430.4 | 0 | 2162.025 | 2162.025
PJ0002871 | M&R H/C 08/09: INTERNET CONNECTIVITY IN TREATMENT ROOMS-BLDG 27 | PAHLOW, BOB | CLOSED | 2008-07-02 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 0 | 0 | 0 | 0
PJ0002871 | M&R H/C 08/09: INTERNET CONNECTIVITY IN TREATMENT ROOMS-BLDG 27 | PAHLOW, BOB | CLOSED | 2008-07-02 | PA:PATCH & PAINT WALLS WHERE EQUIPMENT HAS BEEN RELOCATED | 027 | CLOSED | 2287.68 | 0 | 1105.944 | 1105.944
PJ0002871 Total | [7 empty] | 6718.08 | 0 | 3267.969 | 3267.969
PJ0002870 | ESTIMATE: SLO BLUES GAMES SUPPORT - BAGGETT STADIUM - 160 | POPHAM, DONALD J. | CLOSED | 2008-07-01 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 157.21 | 0 | 0 | 0
PJ0002870 | ESTIMATE: SLO BLUES GAMES SUPPORT - BAGGETT STADIUM - 160 | POPHAM, DONALD J. | CLOSED | 2008-07-01 | CU:RESTROOM SERVICING FOR SLO BLUES GAMES 7/18-7/20 | 160 | CLOSED | 122.388 | 0 | 131.184 | 131.184
PJ0002870 | ESTIMATE: SLO BLUES GAMES SUPPORT - BAGGETT STADIUM - 160 | POPHAM, DONALD J. | CLOSED | 2008-07-01 | LA: SLO BLUES BBALL SUPPORT ON 7/18, 7/19, & 7/20 | 160 | CLOSED | 1449.7219 | 0 | 1200.978 | 1200.978
PJ0002870 Total | [7 empty] | 1729.3199 | 0 | 1332.162 | 1332.162
PJ0002869 | UPGRADE FIRE SUPPRESSION SYSTEM - BLDGS 19 & 112 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-01 | AD: JOC 07.014.052 STAPLES | GEN-AUX | CLOSED | 43951.3949 | 0 | 46697.3466 | 46697.3466
PJ0002869 | UPGRADE FIRE SUPPRESSION SYSTEM - BLDGS 19 & 112 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-01 | CA: ALARM SIGNS | GEN-AUX | CLOSED | 0 | 0 | 22.572 | 22.572
PJ0002869 | UPGRADE FIRE SUPPRESSION SYSTEM - BLDGS 19 & 112 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-01 | CP: PROJECT CONTINGENCY | GEN-AUX | CLOSED | 4557.69 | 0 | 0 | 0
PJ0002869 | UPGRADE FIRE SUPPRESSION SYSTEM - BLDGS 19 & 112 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-01 | EL: ALARM UPGRADE | GEN-AUX | CLOSED | 1071.66 | 0 | 824.406 | 824.406
PJ0002869 | UPGRADE FIRE SUPPRESSION SYSTEM - BLDGS 19 & 112 (NO ESTIMATE) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-07-01 | IN: UPGRADE FIRE SUPPRESSION SYSTEM - 19 | GEN-AUX | CLOSED | 265.104 | 0 | 215.397 | 215.397
PJ0002869 Total | [7 empty] | 49845.8489 | 0 | 47759.7216 | 47759.7216
PJ0002867 | FLOOD REMEDIATION FOR RMS D705, D605, D505 - CERRO VISTA 170G | GRIFFIN, PATRICK E | CLOSED | 2008-06-26 | AD: BELFOR PROPERTY RESTORATION | 170G | CLOSED | 67048.36 | 0 | 67048.36 | 67048.36
PJ0002867 | FLOOD REMEDIATION FOR RMS D705, D605, D505 - CERRO VISTA 170G | GRIFFIN, PATRICK E | CLOSED | 2008-06-26 | CP: PROJECT CONTINGENCY | 170G | CLOSED | 7174.17 | 0 | 0 | 0
PJ0002867 Total | [7 empty] | 74222.53 | 0 | 67048.36 | 67048.36
PJ0002865 | WORK AREA REMODEL - ADMIN 01 RM 110 | MAY, TOM | CLOSED | 2008-06-24 | CA: DISMANTLE FURNITURE IN HR | 001 | CLOSED | 190.5072 | 0 | 127.032 | 127.032
PJ0002865 | WORK AREA REMODEL - ADMIN 01 RM 110 | MAY, TOM | CLOSED | 2008-06-24 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 154.86 | 0 | 0 | 0
PJ0002865 | WORK AREA REMODEL - ADMIN 01 RM 110 | MAY, TOM | CLOSED | 2008-06-24 | EL: RELOCATE POWER FOR COPY MACHINE | 001 | CLOSED | 291.208 | 0 | 595.6991 | 595.6991
PJ0002865 | WORK AREA REMODEL - ADMIN 01 RM 110 | MAY, TOM | CLOSED | 2008-06-24 | EL: RELOCATE POWER FOR REFRIGERATOR | 001 | CLOSED | 380.664 | 0 | 208.452 | 208.452
PJ0002865 | WORK AREA REMODEL - ADMIN 01 RM 110 | MAY, TOM | CLOSED | 2008-06-24 | MO: PICK UP MISCELLANEOUS BOXES FOR SURPLUS AT ADMIN 110 | 001 | CLOSED | 0 | 0 | 22.728 | 22.728
PJ0002865 | WORK AREA REMODEL - ADMIN 01 RM 110 | MAY, TOM | CLOSED | 2008-06-24 | PA: PAINT COPY/REFRIGERATOR AREA IN ADMIN RM 110 | 001 | CLOSED | 686.304 | 0 | 748.704 | 748.704
PJ0002865 Total | [7 empty] | 1703.5432 | 0 | 1702.6151 | 1702.6151
PJ0002864 | REPAIR SEWER LINE - CAMPUS DINING 19 RM 100 (MAINT) | PAHLOW, BOB | CLOSED | 2008-06-23 | AD: JOC 07.015.020 MAINO | 019 | CLOSED | 12160.53 | 0 | 11927.94 | 11927.94
PJ0002864 | REPAIR SEWER LINE - CAMPUS DINING 19 RM 100 (MAINT) | PAHLOW, BOB | CLOSED | 2008-06-23 | CP: PROJECT CONTINGENCY | 019 | CLOSED | 0 | 0 | 0 | 0
PJ0002864 | REPAIR SEWER LINE - CAMPUS DINING 19 RM 100 (MAINT) | PAHLOW, BOB | CLOSED | 2008-06-23 | PL:ASSIST WITH SEWER LINE REPLACEMENT AS NEEDED | 019 | CLOSED | 423.84 | 0 | 158.94 | 158.94
PJ0002864 Total | [7 empty] | 12584.37 | 0 | 12086.88 | 12086.88
PJ0002863 | ROOM RENOVATION - MOTT 42 RM 218 | MOLLAN, CHERYL L. | CLOSED | 2008-06-20 | AD: FLOOR CONNECTION | 042 | CLOSED | 930.9 | 0 | 1201.61 | 1201.61
PJ0002863 | ROOM RENOVATION - MOTT 42 RM 218 | MOLLAN, CHERYL L. | CLOSED | 2008-06-20 | CA:ADD WORK: INSTALL WHITE BOARD; MOTT ROOM 218 | 042 | CLOSED | 317.8812 | 0 | 1240.032 | 1240.032
PJ0002863 | ROOM RENOVATION - MOTT 42 RM 218 | MOLLAN, CHERYL L. | CLOSED | 2008-06-20 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 926.84 | 0 | 0 | 0
PJ0002863 | ROOM RENOVATION - MOTT 42 RM 218 | MOLLAN, CHERYL L. | CLOSED | 2008-06-20 | EL: INSTALL WIRE MOLD AT MOTT 218 | 042 | CLOSED | 5581.564 | 0 | 3080.1101 | 3080.1101
PJ0002863 | ROOM RENOVATION - MOTT 42 RM 218 | MOLLAN, CHERYL L. | CLOSED | 2008-06-20 | IN: ROOM RENOVATION - MOTT 42 RM 218 | 042 | CLOSED | 99.414 | 0 | 33.138 | 33.138
PJ0002863 | ROOM RENOVATION - MOTT 42 RM 218 | MOLLAN, CHERYL L. | CLOSED | 2008-06-20 | PA: PAINT MOTT ROOM 218 | 042 | CLOSED | 2338.9464 | 0 | 1868.724 | 1868.724
PJ0002863 Total | [7 empty] | 10195.5456 | 0 | 7423.6141 | 7423.6141
PJ0002862 | RENOVATION - AG ERHART 10 RMS 202, 202A, 203A, & 203B | MAY, TOM | CLOSED | 2008-06-20 | AD: FLOOR TEC | 010 | CLOSED | 1051.6388 | 0 | 1051.6388 | 1051.6388
PJ0002862 | RENOVATION - AG ERHART 10 RMS 202, 202A, 203A, & 203B | MAY, TOM | CLOSED | 2008-06-20 | CA:WINDOW REMEDY IN 10-202 | 010 | CLOSED | 166.14 | 0 | 176.1 | 176.1
PJ0002862 | RENOVATION - AG ERHART 10 RMS 202, 202A, 203A, & 203B | MAY, TOM | CLOSED | 2008-06-20 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 118.28 | 0 | 0 | 0
PJ0002862 Total | [7 empty] | 1336.0588 | 0 | 1227.7388 | 1227.7388
PJ0002859 | REPLACE ALL HEATER UNIT LOCKSETS -CERRO VISTA 170G ALL SUITE A'S | GRIFFIN, PATRICK E | CLOSED | 2008-06-18 | CP: PROJECT CONTINGENCY | 170G | CLOSED | 5057.75 | 0 | 0 | 0
PJ0002859 | REPLACE ALL HEATER UNIT LOCKSETS -CERRO VISTA 170G ALL SUITE A'S | GRIFFIN, PATRICK E | CLOSED | 2008-06-18 | LS: INSTALL NEW LOCKSETS AT CERRO VISTA | 170G | CLOSED | 50577.516 | 0 | 52574.721 | 52574.721
PJ0002859 Total | [7 empty] | 55635.266 | 0 | 52574.721 | 52574.721
PJ0002858 | SMART ROOM EQUIPMENT INSTALLATION-AG SCI 11 RM 102 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CA - SMART ROOM | 011 | CLOSED | 110.76 | 0 | 254.454 | 254.454
PJ0002858 | SMART ROOM EQUIPMENT INSTALLATION-AG SCI 11 RM 102 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0002858 | SMART ROOM EQUIPMENT INSTALLATION-AG SCI 11 RM 102 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | EL - ELECTRICAL FOR SMART ROOM | 011 | CLOSED | 0 | 0 | 1567.374 | 1567.374
PJ0002858 | SMART ROOM EQUIPMENT INSTALLATION-AG SCI 11 RM 102 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | PA - PAINT AND PATCH AS NEEDED | 011 | CLOSED | 0 | 0 | 319.764 | 319.764
PJ0002858 Total | [7 empty] | 110.76 | 0 | 2141.592 | 2141.592
PJ0002857 | SMART ROOM EQUIPMENT INSTALLATION-ENGR E 20 RM 145 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CA - SMART ROOM | 020 | CLOSED | 110.76 | 0 | 402.984 | 402.984
PJ0002857 | SMART ROOM EQUIPMENT INSTALLATION-ENGR E 20 RM 145 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 0 | 0 | 0 | 0
PJ0002857 | SMART ROOM EQUIPMENT INSTALLATION-ENGR E 20 RM 145 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | EL - INSTALL ELECTRICAL IN SMART ROOM | 020 | CLOSED | 0 | 0 | 1631.064 | 1631.064
PJ0002857 | SMART ROOM EQUIPMENT INSTALLATION-ENGR E 20 RM 145 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | PA - PATCH AND PAINT AS NEEDED | 020 | CLOSED | 0 | 0 | 545.772 | 545.772
PJ0002857 Total | [7 empty] | 110.76 | 0 | 2579.82 | 2579.82
PJ0002856 | SMART ROOM EQUIPMENT INSTALLATION-ENGR W 21 RM 206 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0002856 | SMART ROOM EQUIPMENT INSTALLATION-ENGR W 21 RM 206 (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | EL - SMART ROOM | 021 | CLOSED | 0 | 0 | 1148.826 | 1148.826
PJ0002856 Total | [7 empty] | 0 | 0 | 1148.826 | 1148.826
PJ0002855 | SMART ROOM EQUIPMENT INSTALLATION - COED 02 RM 10 (NO ESTIMATE)1 | LAMPMAN, GREG | CLOSED | 2008-06-13 | CA - SMART ROOM | 002 | CLOSED | 110.76 | 0 | 1023.888 | 1023.888
PJ0002855 | SMART ROOM EQUIPMENT INSTALLATION - COED 02 RM 10 (NO ESTIMATE)1 | LAMPMAN, GREG | CLOSED | 2008-06-13 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0002855 | SMART ROOM EQUIPMENT INSTALLATION - COED 02 RM 10 (NO ESTIMATE)1 | LAMPMAN, GREG | CLOSED | 2008-06-13 | EL - INSTALL ELECTRICAL IN SMART ROOM | 002 | CLOSED | 0 | 0 | 5202.222 | 5202.222
PJ0002855 Total | [7 empty] | 110.76 | 0 | 6226.11 | 6226.11
PJ0002854 | SMART ROOM EQUIPMENT INSTALLATION-ERHART 10 RM 222(NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CA - SMART ROOM | 010 | CLOSED | 110.76 | 0 | 284.916 | 284.916
PJ0002854 | SMART ROOM EQUIPMENT INSTALLATION-ERHART 10 RM 222(NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 0 | 0 | 0 | 0
PJ0002854 | SMART ROOM EQUIPMENT INSTALLATION-ERHART 10 RM 222(NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | EL- INSTALL SMART ROOM ELECTRICAL | 010 | CLOSED | 0 | 0 | 2037.0824 | 2037.0824
PJ0002854 | SMART ROOM EQUIPMENT INSTALLATION-ERHART 10 RM 222(NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-06-13 | PA- PAINT FRONT WALL | 010 | CLOSED | 0 | 0 | 293.568 | 293.568
PJ0002854 Total | [7 empty] | 110.76 | 0 | 2615.5664 | 2615.5664
PJ0002853 | MJ: STAIR REPAIR - ENGR IV 192 - JOC TRACKING, ONLY | UYTTEWAAL, JOHAN M | CLOSED | 2008-06-12 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002853 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002844 | TRADES SUPPORT FOR P.I.E.R. DEMONSTRATION PROJECTS (MAINT) | ELLIOT, DENNIS K | CLOSED | 2008-06-09 | CA: REPLACE MISSING CEILING TILES AND T-BAR | GENERAL | CLOSED | 256.48 | 0 | 281.74 | 281.74
PJ0002844 | TRADES SUPPORT FOR P.I.E.R. DEMONSTRATION PROJECTS (MAINT) | ELLIOT, DENNIS K | CLOSED | 2008-06-09 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002844 | TRADES SUPPORT FOR P.I.E.R. DEMONSTRATION PROJECTS (MAINT) | ELLIOT, DENNIS K | CLOSED | 2008-06-09 | EL: PROVIDE SUPPORT FOR P.I.E.R. PROJECTS | GENERAL | CLOSED | 1057.4 | 0 | 370.09 | 370.09
PJ0002844 | TRADES SUPPORT FOR P.I.E.R. DEMONSTRATION PROJECTS (MAINT) | ELLIOT, DENNIS K | CLOSED | 2008-06-09 | ES: PROVIDE SUPPORT FOR P.I.E.R. PROJECTS | GENERAL | CLOSED | 2134.4 | 0 | 3133.858 | 3133.858
PJ0002844 | TRADES SUPPORT FOR P.I.E.R. DEMONSTRATION PROJECTS (MAINT) | ELLIOT, DENNIS K | CLOSED | 2008-06-09 | IN: PROVIDE INSPECTION FOR P.I.E.R DEMONSTRATION PROJECTS (N/L) | GENERAL | CLOSED | 883.68 | 0 | 0 | 0
PJ0002844 Total | [7 empty] | 4331.96 | 0 | 3785.688 | 3785.688
PJ0002841 | SP 07/08: REPLACE RED CARPET ON N. END 2ND FL -LIBRARY 35 RM 216 | MAY, TOM | CLOSED | 2008-06-03 | AD: FLOOR CONNECTION | 035 | CLOSED | 84147.154 | 0 | 92549.2648 | 92549.2648
PJ0002841 | SP 07/08: REPLACE RED CARPET ON N. END 2ND FL -LIBRARY 35 RM 216 | MAY, TOM | CLOSED | 2008-06-03 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 8414.72 | 0 | 0 | 0
PJ0002841 | SP 07/08: REPLACE RED CARPET ON N. END 2ND FL -LIBRARY 35 RM 216 | MAY, TOM | CLOSED | 2008-06-03 | IN: REPLACE RED CARPET ON NRTH END 2ND FL-LIBRY 35 RM 216 (N/L) | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0002841 Total | [7 empty] | 92561.874 | 0 | 92549.2648 | 92549.2648
PJ0002838 | SERVICES FOR CATA FARM SHOW 6/24/08 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-06-02 | CA: PROVIDE SERVICES FOR CATA FARM SHOW 6/24/08 - FARM SHOP 09 | 009 | CLOSED | 886.08 | 0 | 903.81 | 903.81
PJ0002838 | SERVICES FOR CATA FARM SHOW 6/24/08 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-06-02 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0002838 | SERVICES FOR CATA FARM SHOW 6/24/08 - FARM SHOP 09 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-06-02 | EL: PROVIDE SERVICES FOR CATA FARM SHOW 6/24/08 - FARM SHOP 09 | 009 | CLOSED | 0 | 0 | 513.5393 | 513.5393
PJ0002838 Total | [7 empty] | 886.08 | 0 | 1417.3493 | 1417.3493
PJ0002836 | SECURITY/INTRUSION ALARM HARDWARE - ENGR 13 RM 106, 107 & 109 | GRIFFIN, PATRICK E | CLOSED | 2008-05-29 | AD: CAME SECURITY | 013 | CLOSED | 2568 | 0 | 2568 | 2568
PJ0002836 | SECURITY/INTRUSION ALARM HARDWARE - ENGR 13 RM 106, 107 & 109 | GRIFFIN, PATRICK E | CLOSED | 2008-05-29 | AD: QUINTRON | 013 | CLOSED | 3771.25 | 0 | 3753.75 | 3753.75
PJ0002836 | SECURITY/INTRUSION ALARM HARDWARE - ENGR 13 RM 106, 107 & 109 | GRIFFIN, PATRICK E | CLOSED | 2008-05-29 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 697.7 | 0 | 0 | 0
PJ0002836 | SECURITY/INTRUSION ALARM HARDWARE - ENGR 13 RM 106, 107 & 109 | GRIFFIN, PATRICK E | CLOSED | 2008-05-29 | EL: TIE IN NEW POWER SUPPLY FOR LOCK ACCESS HARDWARE | 013 | CLOSED | 126.888 | 0 | 160.782 | 160.782
PJ0002836 | SECURITY/INTRUSION ALARM HARDWARE - ENGR 13 RM 106, 107 & 109 | GRIFFIN, PATRICK E | CLOSED | 2008-05-29 | IN:SECURITY/INTRSION ALARM HRDWRE-ENGR 13 RM 106 107 & 109 (N/L) | 013 | CLOSED | 132.552 | 0 | 0 | 0
PJ0002836 | SECURITY/INTRUSION ALARM HARDWARE - ENGR 13 RM 106, 107 & 109 | GRIFFIN, PATRICK E | CLOSED | 2008-05-29 | LO:PROVIDE LOCK SERVICES FOR LOCK SYSTEM - 013 106 & 107 | 013 | CLOSED | 114.336 | 0 | 114.336 | 114.336
PJ0002836 Total | [7 empty] | 7410.726 | 0 | 6596.868 | 6596.868
PJ0002834 | DESIGN FOR TENNIS COURTS RENOVATION | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-27 | AD: OMNI DESIGN GROUP, INC | 042S | CLOSED | 10000 | 0 | 10000 | 10000
PJ0002834 | DESIGN FOR TENNIS COURTS RENOVATION | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002834 Total | [7 empty] | 10000 | 0 | 10000 | 10000
PJ0002832 | SP 07/08: DESIGN BUS STOPS ON CAMPUS | LAMPMAN, GREG | CLOSED | 2008-05-21 | AD: ROSSETTI | GENERAL | CLOSED | 98953.6 | 0 | 98953.6 | 98953.6
PJ0002832 | SP 07/08: DESIGN BUS STOPS ON CAMPUS | LAMPMAN, GREG | CLOSED | 2008-05-21 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 9895.36 | 0 | 0 | 0
PJ0002832 | SP 07/08: DESIGN BUS STOPS ON CAMPUS | LAMPMAN, GREG | CLOSED | 2008-05-21 | IN: DESIGN BUS STOPS ON CAMPUS(N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002832 Total | [7 empty] | 108848.96 | 0 | 98953.6 | 98953.6
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | AD: CREDIT CARD PURCHASE | 001 | CLOSED | 0 | 0 | 169.968 | 169.968
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | AD: DIVISION OF STATE ARCHITECT | 001 | CLOSED | 0 | 0 | 328 | 328
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | AD: JOC 07.015.034 MAINO | 001 | CLOSED | 116765.6011 | 0 | 116765.6118 | 116765.6118
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | AD: MECA | 001 | CLOSED | 11764.65 | 0 | 11763.3125 | 11763.3125
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | CA:INSTALL WIRES AND PATCH FIREPROOFING MATERIAL | 001 | CLOSED | 5720.2602 | 0 | 6180.973 | 6180.973
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1017.04 | 0 | 0 | 0
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | EL: PROCUREMENT OFFICES REMODEL | 001 | CLOSED | 9447.72 | 0 | 8317.551 | 8317.551
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | ES: PROCUREMET OFFICE REMODEL | 001 | CLOSED | 2840.64 | 0 | 2693.0909 | 2693.0909
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | IN:REMODEL CONTRACT & PROCUREMENT SVCS OFFICES - ADMIN 01 RM 128 | 001 | CLOSED | 795.312 | 0 | 430.794 | 430.794
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | LO: INSTALL NEW CORES IN OFFICE REMODEL | 001 | CLOSED | 878.016 | 0 | 644.76 | 644.76
PJ0002831 | REMODEL CONTRACT & PROCUREMENT SRVCS OFFICES - ADMIN 01 RM 128 | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-20 | PA: PROCUREMENT OFFICES REMODEL | 001 | CLOSED | 6183 | 0 | 6018.006 | 6018.006
PJ0002831 Total | [7 empty] | 155412.2393 | 0 | 153312.0671 | 153312.0671
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | AD: JOC 07.013.047 MAINO | 026 | CLOSED | 15680.2294 | 0 | 15680.2294 | 15680.2294
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | AD: KNECHT'S PLUMBING AND HEATING | 026 | CLOSED | 0 | 0 | 983.33 | 983.33
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | AD: MECA | 026 | CLOSED | 0 | 0 | 2889 | 2889
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | AD: SANTA MARIA ACOUSTICAL | 026 | CLOSED | 4451.2 | 0 | 4607.1311 | 4607.1311
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | CA: REMODEL IN 26-204 | 026 | CLOSED | 7481.6688 | 0 | 10359.252 | 10359.252
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 3929.52 | 0 | 0 | 0
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | EL: RESWITCH LIGHTING IN 26-204 | 026 | CLOSED | 847.7027 | 0 | 732.198 | 732.198
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | EL:REMODEL 26-204 | 026 | CLOSED | 6857.76 | 0 | 4596.0226 | 4596.0226
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | IN: REMODEL ROOM - GRAPHICS ART 26 RM 204 | 026 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | PA:PAINT 26-204 | 026 | CLOSED | 2287.68 | 0 | 2117.508 | 2117.508
PJ0002828 | REMODEL ROOM - GRAPHICS ART 26 RM 204 | MAY, TOM | CLOSED | 2008-05-19 | PL:REMODEL IN 26-204 | 026 | CLOSED | 254.304 | 0 | 1603.392 | 1603.392
PJ0002828 Total | [7 empty] | 41856.3409 | 0 | 43634.3391 | 43634.3391
PJ0002827 | TINT WINDOWS - CHASE HALL 115 RMS 201-205 & RMS 215-218 | GRIFFIN, PATRICK E | CLOSED | 2008-05-16 | AD: SAN LUIS CUSTOM TINTS | 115 | CLOSED | 943.5795 | 0 | 943.5795 | 943.5795
PJ0002827 | TINT WINDOWS - CHASE HALL 115 RMS 201-205 & RMS 215-218 | GRIFFIN, PATRICK E | CLOSED | 2008-05-16 | CP: PROJECT CONTINGENCY | 115 | CLOSED | 94.36 | 0 | 0 | 0
PJ0002827 Total | [7 empty] | 1037.9395 | 0 | 943.5795 | 943.5795
PJ0002825 | SR 08/09, MC 07/08: PAVERS ON N. POLY VIEW DR. (ENC. BY 6/30/09) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-16 | AD: JOC 07.015.006 MAINO | GENERAL | CLOSED | 169509.3465 | 0 | 169509.3465 | 169509.3465
PJ0002825 | SR 08/09, MC 07/08: PAVERS ON N. POLY VIEW DR. (ENC. BY 6/30/09) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-16 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 17647.12 | 0 | 0 | 0
PJ0002825 | SR 08/09, MC 07/08: PAVERS ON N. POLY VIEW DR. (ENC. BY 6/30/09) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-16 | IN: INSTALL PAVERS ON N. POLY VIEW DR. | GENERAL | CLOSED | 265.104 | 0 | 281.673 | 281.673
PJ0002825 | SR 08/09, MC 07/08: PAVERS ON N. POLY VIEW DR. (ENC. BY 6/30/09) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-16 | LA: LANDSCAPING FOR POLYVIEW PAVERS PROJECT | GENERAL | CLOSED | 1707.36 | 0 | 506.5985 | 506.5985
PJ0002825 Total | [7 empty] | 189128.9305 | 0 | 170297.618 | 170297.618
PJ0002824 | LIGHT POLES IN PARKING LOT N. OF BLDG 41, NEAR HIGHLAND (MAINT) | PAHLOW, BOB | CLOSED | 2008-05-15 | CA: PROVIDE CONCRETE AND REBAR FOR LIGHT POLES | GENERAL | CLOSED | 738.4 | 0 | 2054.6644 | 2054.6644
PJ0002824 | LIGHT POLES IN PARKING LOT N. OF BLDG 41, NEAR HIGHLAND (MAINT) | PAHLOW, BOB | CLOSED | 2008-05-15 | CP: PROJECT CONTINGENCY | 041 | CLOSED | 0 | 0 | 0 | 0
PJ0002824 | LIGHT POLES IN PARKING LOT N. OF BLDG 41, NEAR HIGHLAND (MAINT) | PAHLOW, BOB | CLOSED | 2008-05-15 | EL-INSTALL NEW PARKING LOT LIGHTS | GENERAL | CLOSED | 0 | 0 | 9747.9446 | 9747.9446
PJ0002824 | LIGHT POLES IN PARKING LOT N. OF BLDG 41, NEAR HIGHLAND (MAINT) | PAHLOW, BOB | CLOSED | 2008-05-15 | EO-PROVIDE TRENCHING FOR NEW PARKING LOT LIGHTS | GENERAL | CLOSED | 0 | 0 | 1119.98 | 1119.98
PJ0002824 | LIGHT POLES IN PARKING LOT N. OF BLDG 41, NEAR HIGHLAND (MAINT) | PAHLOW, BOB | CLOSED | 2008-05-15 | IN-PROVIDE INSPCTIN SERVICES FOR NEW PRKING LOT LIGHTS (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002824 Total | [7 empty] | 738.4 | 0 | 12922.589 | 12922.589
PJ0002823 | INCREASE AMP TO CIRCUIT BREAKER - ATL 07 RM 04 | VELARDE, DENIS L | CLOSED | 2008-05-14 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 106.22 | 0 | 126.888 | 126.888
PJ0002823 Total | [7 empty] | 106.22 | 0 | 126.888 | 126.888
PJ0002822 | REMOVE AND REPLACE DRINKING FOUNTAIN ENG W 21 - MAINT | PAHLOW, BOB | CLOSED | 2008-05-14 | CA-PATCH WALL FOR MOUNTING OF NEW DRINKING FOUNTAIN | 021 | CLOSED | 138.45 | 0 | 191.35 | 191.35
PJ0002822 | REMOVE AND REPLACE DRINKING FOUNTAIN ENG W 21 - MAINT | PAHLOW, BOB | CLOSED | 2008-05-14 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0002822 | REMOVE AND REPLACE DRINKING FOUNTAIN ENG W 21 - MAINT | PAHLOW, BOB | CLOSED | 2008-05-14 | EL-DISCONNECT/RECONNECT DRINKING FOUNTAINS | 021 | CLOSED | 0 | 0 | 81.105 | 81.105
PJ0002822 | REMOVE AND REPLACE DRINKING FOUNTAIN ENG W 21 - MAINT | PAHLOW, BOB | CLOSED | 2008-05-14 | PA-PAINT WALL FOR MOUNTING OF NEW DRINKING FOUNTAIN | 021 | CLOSED | 0 | 0 | 630.62 | 630.62
PJ0002822 | REMOVE AND REPLACE DRINKING FOUNTAIN ENG W 21 - MAINT | PAHLOW, BOB | CLOSED | 2008-05-14 | PL-REMOVE AND REPLACE DRINKING FOUNTAIN ENG W 21 | 021 | CLOSED | 0 | 0 | 2022.08 | 2022.08
PJ0002822 Total | [7 empty] | 138.45 | 0 | 2925.155 | 2925.155
PJ0002821 | SR 08/09: REMOVE FACILITY SERVICES WELDING SHOP - BLDG 70D | MAY, TOM | CLOSED | 2008-05-14 | AD: JOC 07.014.035 STAPLES | 070D | CLOSED | 61164.13 | 0 | 2099.15 | 2099.15
PJ0002821 | SR 08/09: REMOVE FACILITY SERVICES WELDING SHOP - BLDG 70D | MAY, TOM | CLOSED | 2008-05-14 | CP: PROJECT CONTINGENCY | 070D | CLOSED | 7002.43 | 0 | 0 | 0
PJ0002821 Total | [7 empty] | 68166.56 | 0 | 2099.15 | 2099.15
PJ0002819 | CAME SECURITY ALARM INSTALLATION - ENGR III 41 RM 204, 205 & 207 | PAHLOW, BOB | CLOSED | 2008-05-13 | ATS: PROGRAM FRONT END FOR NEW DOOR SECURITY. | 041 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002819 | CAME SECURITY ALARM INSTALLATION - ENGR III 41 RM 204, 205 & 207 | PAHLOW, BOB | CLOSED | 2008-05-13 | CP: PROJECT CONTINGENCY | 041 | CLOSED | 0 | 0 | 0 | 0
PJ0002819 | CAME SECURITY ALARM INSTALLATION - ENGR III 41 RM 204, 205 & 207 | PAHLOW, BOB | CLOSED | 2008-05-13 | IN: CAME SECURITY ALARM INSTALLATION - ENGR III | 041 | CLOSED | 66.276 | 0 | 33.138 | 33.138
PJ0002819 Total | [7 empty] | 66.276 | 0 | 90.306 | 90.306
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | AD: FLOORTEC | 003 | CLOSED | 2509.8134 | 0 | 2509.8134 | 2509.8134
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | AD: JOC 07.014.051 STAPLES | 003 | CLOSED | 11106.9424 | 0 | 11106.9424 | 11106.9424
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1855.21 | 0 | 0 | 0
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | EL:RELOCATE AND INSTALL NEW OUTLETS AND SWITCHES | 003 | CLOSED | 2183.108 | 0 | 1403.19 | 1403.19
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | ES:RECONFIGURE DUCTWORK | 003 | CLOSED | 881.0803 | 0 | 810.012 | 810.012
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | IN: ROOM RENOVATION - COB 03 RM 208 | 003 | CLOSED | 132.552 | 0 | 298.242 | 298.242
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | LO:INSTALL NEW CORES IN BUSINESS BLDG. 03, ROOM 208 | 003 | CLOSED | 171.504 | 0 | 272.088 | 272.088
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | MO:MOVE FURNITURE FOR E-SURPLUS | 003 | CLOSED | 63 | 0 | 153.414 | 153.414
PJ0002818 | ROOM RENOVATION - COB 03 RM 208 | MOLLAN, CHERYL L. | CLOSED | 2008-05-12 | PA:PAINT NEW AND EXISTING WALLS | 003 | CLOSED | 1372.608 | 0 | 2918.808 | 2918.808
PJ0002818 Total | [7 empty] | 20275.8182 | 0 | 19472.5098 | 19472.5098
PJ0002817 | MOVE CIRCUITS FROM PANEL A1 TO B1 - COMP SCI 14 ROOM 104 | VELARDE, DENIS L | CLOSED | 2008-05-12 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0002817 | MOVE CIRCUITS FROM PANEL A1 TO B1 - COMP SCI 14 ROOM 104 | VELARDE, DENIS L | CLOSED | 2008-05-12 | EL: 14-104 ADD CIRCUITS | 014 | CLOSED | 0 | 0 | 291.072 | 291.072
PJ0002817 Total | [7 empty] | 0 | 0 | 291.072 | 291.072
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | AD: JOC 07.014.050 STAPLES | 003 | CLOSED | 22375.7437 | 0 | 22375.7437 | 22375.7437
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | CA:INSTALL WHITE AND CORK BOARDS/ ROOM SIGNAGE | 003 | CLOSED | 83.07 | 0 | 337.704 | 337.704
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 2651.13 | 0 | 0 | 0
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | CU:PROVIDE CUSTODIAL SUPPORT (N/L) | 003 | CLOSED | 131.184 | 0 | 0 | 0
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | EL:REMOVE LIGHTING FIXTURES/ INSTALL NEW ELECTRICAL | 003 | CLOSED | 1455.4054 | 0 | 3846.4532 | 3846.4532
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | ES:RELOCATE THERMOSTAT AND RECONFIGURE DUCT WORK | 003 | CLOSED | 881.0803 | 0 | 838.944 | 838.944
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | IN: USE APPROVAL/CUBICLE INSTALLATION ROOM - COB 03 RM 300 | 003 | CLOSED | 132.552 | 0 | 99.414 | 99.414
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | LO:COB 03 RM 300-INSTALL NEW CORE IN HALLWAY DOOR | 003 | CLOSED | 114.336 | 0 | 186.336 | 186.336
PJ0002815 | BUILD 3 OFFICES W/IN ROOM - COB 03 RM 300 | MOLLAN, CHERYL L. | CLOSED | 2008-05-09 | PA:PAINT NEW WALLS | 003 | CLOSED | 1143.84 | 0 | 2126.55 | 2126.55
PJ0002815 Total | [7 empty] | 28968.3414 | 0 | 29811.1449 | 29811.1449
PJ0002814 | CAME SECURITY ALARM INSTALLATION - COB 03 RM 100 | PAHLOW, BOB | CLOSED | 2008-05-09 | ANTS-PANIC ALARM PROGRAMMING | 003 | CLOSED | 0 | 0 | 28.584 | 28.584
PJ0002814 | CAME SECURITY ALARM INSTALLATION - COB 03 RM 100 | PAHLOW, BOB | CLOSED | 2008-05-09 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 50.83 | 0 | 0 | 0
PJ0002814 | CAME SECURITY ALARM INSTALLATION - COB 03 RM 100 | PAHLOW, BOB | CLOSED | 2008-05-09 | IN:CAME SECURITY ALARM INSTALLATION - COB 03 RM 100 | 003 | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0002814 Total | [7 empty] | 50.83 | 0 | 61.722 | 61.722
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | AD: BOB'S CRANE (FUNDED FROM Z52221) | 013 | CLOSED | 535 | 0 | 535 | 535
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | CA: FABRICATE AND INSTALL METAL SIGN ON RECIP REACTOR WALL. | 013 | CLOSED | 230.76 | 0 | 36.348 | 36.348
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | CA: INSTALL ROOF PENETRATION | 013 | CLOSED | 3832.446 | 0 | 2899.104 | 2899.104
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | CA: INSTALL SIESMIC RESTRAINTS ON KJELDAHL NITROGEN ANALYZER | 013 | CLOSED | 226.14 | 0 | 497.016 | 497.016
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 108.43 | 0 | 0 | 0
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | EL: DISCONNECT AUTOCLAVE FOR EQUIPMENT MOVE - BLG 13 RM 201A | 013 | CLOSED | 95.166 | 0 | 95.166 | 95.166
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | EL: INSTALL CENTRIFUGE CIRCUIT - BLDG. 13 ROOM 201B | 013 | CLOSED | 680.664 | 0 | 741.084 | 741.084
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | EL: PUMP SWITCH AND METER FOR RECIP REACTOR - DAIRY LAGOON | 013 | CLOSED | 1107.552 | 0 | 940.83 | 940.83
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | EL: SUPPLY POWER FOR KJELDAHL NITROGEN ANALYZER | 013 | CLOSED | 7644.9101 | 0 | 3880.512 | 3880.512
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | ES: INSTALL NEW VENT SYSTEM FOR NITROGEN ANALYZER 13-201B | 013 | CLOSED | 8006.6822 | 0 | 10986.2022 | 10986.2022
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | IN: MOVE & INSTALL NITROGEN ANALYZER-SCI BLDG 52 TO ENGR BLDG 13 | 013 | CLOSED | 397.656 | 0 | 397.656 | 397.656
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | MO: MOVE KJELDAHL NITROGEN ANALYZER 10/14/09 (FUNDED BY Z52221) | 013 | CLOSED | 78.75 | 0 | 79.548 | 79.548
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | PL: DISCONNECT/RECONNECT AUTOCLAVE IN ROOM 210A BLDG 13 | 013 | CLOSED | 127.152 | 0 | 127.152 | 127.152
PJ0002813 | INSTALL NEW KJELDAHL NITROGEN ANALYZER | KUENTZEL, DOUGLAS A. | CLOSED | 2008-05-09 | PL: INSTALL WATER SUPPLY & DRAIN FOR KJELDAHL NITROGEN ANALYZER | 013 | CLOSED | 1639.4676 | 0 | 3699.984 | 3699.984
PJ0002813 Total | [7 empty] | 24710.7759 | 0 | 24915.6022 | 24915.6022
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | CA:REMOVE CABINETS IN 01-209 | 001 | CLOSED | 3049.2228 | 0 | 2733.408 | 2733.408
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 718.49 | 0 | 0 | 0
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | EL:REMOVE FLOOR OUTLET ADM 209B | 001 | CLOSED | 126.888 | 0 | 63.444 | 63.444
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | ES:RELOCATE STAT IN ADM 209B | 001 | CLOSED | 192.096 | 0 | 260.5387 | 260.5387
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | IN: OFCE REMODEL-ADMIN 01 RMS 209B,209E&MAIN RECPTN AREA (N/L) | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | LO:ASSIST WITH DOORS IN ADM 209 | 001 | CLOSED | 228.672 | 0 | 703.698 | 703.698
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | MO:TRANSPORT DESK UNIT FROM ADM 209 | 001 | CLOSED | 0 | 0 | 22.728 | 22.728
PJ0002811 | OFFICE REMODEL - ADMIN 01 RMS 209B , 209E & MAIN RECEPTION AREA | MAY, TOM | CLOSED | 2008-05-08 | PA:PAINT OFFICES IN ADM 209 COMPLEX | 001 | CLOSED | 3780.288 | 0 | 5567.448 | 5567.448
PJ0002811 Total | [7 empty] | 8095.6568 | 0 | 9351.2647 | 9351.2647
PJ0002809 | REMOVE SLIDING DOORS & INSTALL STORE FRONT DOORS - S. MTN BLDGS | GRIFFIN, PATRICK E | CLOSED | 2008-05-06 | AD: JOC 07.015.002 STAPLES | GENERAL | CLOSED | 45980.2112 | 0 | 45980.2112 | 45980.2112
PJ0002809 | REMOVE SLIDING DOORS & INSTALL STORE FRONT DOORS - S. MTN BLDGS | GRIFFIN, PATRICK E | CLOSED | 2008-05-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 4639.17 | 0 | 0 | 0
PJ0002809 | REMOVE SLIDING DOORS & INSTALL STORE FRONT DOORS - S. MTN BLDGS | GRIFFIN, PATRICK E | CLOSED | 2008-05-06 | LO: INSTALL NEW CORES FOR STORE FRONTS AT SOUTH MTN DORMS | GENERAL | CLOSED | 411.504 | 0 | 114.336 | 114.336
PJ0002809 Total | [7 empty] | 51030.8852 | 0 | 46094.5472 | 46094.5472
PJ0002808 | REPLACE ALL EXISTING DORM ROOM LOCKSETS - S.M. 113 5 TWRS | GRIFFIN, PATRICK E | CLOSED | 2008-05-06 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 11312.13 | 0 | 0 | 0
PJ0002808 | REPLACE ALL EXISTING DORM ROOM LOCKSETS - S.M. 113 5 TWRS | GRIFFIN, PATRICK E | CLOSED | 2008-05-06 | LO:SIERRA MADRE ROOM LOCK REPLACEMENT | 113 | CLOSED | 113121.336 | 0 | 121355.997 | 121355.997
PJ0002808 Total | [7 empty] | 124433.466 | 0 | 121355.997 | 121355.997
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | AD: JOC 07.015.031 MAINO | 013 | CLOSED | 42364.403 | 0 | 42364.403 | 42364.403
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | CA: FABRICATE CABINET FOR SHAKE TABLE MONITORING EQUIP | 013 | CLOSED | 503.04 | 0 | 4979.85 | 4979.85
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 4079.56 | 0 | 0 | 0
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | EL: ADD THREE ADDITIONAL CIRCUITS | 013 | CLOSED | 1375.104 | 0 | 3837.198 | 3837.198
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | ES: MODIFY TRENCH COVER PLATE AT ENG 13 120 | 013 | CLOSED | 152.064 | 0 | 32.016 | 32.016
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | IN: REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING | 013 | CLOSED | 304.2068 | 0 | 215.397 | 215.397
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | PA: PAINT SHED OUTSIDE ROOM 120 | 013 | CLOSED | 517.536 | 0 | 951.228 | 951.228
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | PA: PATCH, TAPE, PRIME, AND PAINT WHERE WALL WAS REMOVED | 013 | CLOSED | 3831.5028 | 0 | 2521.884 | 2521.884
PJ0002807 | REMOVE NON STRUCTURAL WALL/ MOVE EQUIP/ INSTALL RAILING - 13-120 | GRIFFIN, PATRICK E | CLOSED | 2008-05-05 | PL: DEMO PLUMBING IN ENG 13 121 | 013 | CLOSED | 3375.5683 | 0 | 2077.7598 | 2077.7598
PJ0002807 Total | [7 empty] | 56502.985 | 0 | 56979.7358 | 56979.7358
PJ0002806 | REPLACE DOOR & INSTALL PANIC HARDWARE - MOTT 42 WLR (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-05-01 | CA: INSTALL NEW DOOR AT MOTT WOMEN'S LOCKER ROOM | 042 | CLOSED | 919.2 | 0 | 810.5 | 810.5
PJ0002806 | REPLACE DOOR & INSTALL PANIC HARDWARE - MOTT 42 WLR (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-05-01 | CP: PROJECT CONTINGENCY | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002806 | REPLACE DOOR & INSTALL PANIC HARDWARE - MOTT 42 WLR (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-05-01 | LS: INSTALL NEW LOCK HARDWARE | 042 | CLOSED | 2035.84 | 0 | 1550.62 | 1550.62
PJ0002806 | REPLACE DOOR & INSTALL PANIC HARDWARE - MOTT 42 WLR (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-05-01 | PA: PRIME AND PAINT NEW DOOR AT MOTT WOMEN'S LOCKER ROOM | 042 | CLOSED | 461.28 | 0 | 181.31 | 181.31
PJ0002806 Total | [7 empty] | 3416.32 | 0 | 2542.43 | 2542.43
PJ0002803 | PAINT ALL DOORS - COMP SCI 14 RMS ALL (MAINT) | ALTON, JOSHUA R | CLOSED | 2008-04-28 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 0 | 0 | 0 | 0
PJ0002803 | PAINT ALL DOORS - COMP SCI 14 RMS ALL (MAINT) | ALTON, JOSHUA R | CLOSED | 2008-04-28 | PL BUILDING 14 PAINT DOORS | 014 | CLOSED | 0 | 0 | 3352.72 | 3352.72
PJ0002803 Total | [7 empty] | 0 | 0 | 3352.72 | 3352.72
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | AD: SANTA MARIA ACOUSTICAL | 020 | CLOSED | 1894.97 | 0 | 2536.97 | 2536.97
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | AD: THOMA ELECTRIC | 020 | CLOSED | 0 | 0 | 627.02 | 627.02
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | CA: REPLACE WINDOW BLINDS AND BROKEN FLOOR TILE (MAINT) | 020 | CLOSED | 0 | 0 | 3299.3275 | 3299.3275
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 986.69 | 0 | 0 | 0
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | EL: ELECTRICAL IMPROVEMENTS IN EE ROOM 144 | 020 | CLOSED | 2677.158 | 0 | 63.444 | 63.444
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | ES: REMOVE EXHAUST FAN, HEATER, AND PIPING. BLG 20, RM 144 | 020 | CLOSED | 1280.64 | 0 | 1569.432 | 1569.432
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | IN: INSTALL A DROP CEILING - ENGR E 20 RM 144 | 020 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | PA: PAINT ROOM 144 IN BLG. 20 (MAINT) | 020 | CLOSED | 0 | 0 | 1660.95 | 1660.95
PJ0002802 | INSTALL A DROP CEILING - ENGR E 20 RM 144 | MAY, TOM | CLOSED | 2008-04-28 | PL: SUPPORT FOR PAINTING EE ROOM 144 ***ADDITIONAL WORK*** | 020 | CLOSED | 127.152 | 0 | 455.628 | 455.628
PJ0002802 Total | [7 empty] | 6966.61 | 0 | 10279.0475 | 10279.0475
PJ0002801 | TRAFFIC INFORMATION SIGN INSTALLATION | LAMPMAN, GREG | CLOSED | 2008-04-25 | AD: JOC 07.014.043 STAPLES | GENERAL | CLOSED | 2191.0818 | 0 | 2191.0818 | 2191.0818
PJ0002801 | TRAFFIC INFORMATION SIGN INSTALLATION | LAMPMAN, GREG | CLOSED | 2008-04-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 219.11 | 0 | 0 | 0
PJ0002801 Total | [7 empty] | 2410.1918 | 0 | 2191.0818 | 2191.0818
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | AD: FLOORTEC | 038 | CLOSED | 4815 | 0 | 5110.8764 | 5110.8764
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | AD: JOC 07.015.023 MAINO | 038 | CLOSED | 13666.1042 | 0 | 13666.1042 | 13666.1042
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | CA:COUNTER WORK IN 38-131 | 038 | CLOSED | 6036.48 | 0 | 4599.3328 | 4599.3328
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 3289.89 | 0 | 0 | 0
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | EL:DISCONNECT ELECTRICAL RACEWAYS AND FLOOR RECEPTICALS RM 131 | 038 | CLOSED | 507.552 | 0 | 824.772 | 824.772
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | ES: OVERSEE HAZRDS WASTE REMVAL AT MATH RM 131 (N/L) | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | IN: ADD SINKS WITH COUNTERTOP WITH CABINETS-MATH 38 RM 131 (N/L) | 038 | CLOSED | 66.276 | 0 | 0 | 0
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | PA:REMODEL IN 38-131 | 038 | CLOSED | 1143.84 | 0 | 2374.428 | 2374.428
PJ0002800 | ADD SINKS WITH COUNTERTOP WITH CABINETS - MATH 38 RM 131 | MAY, TOM | CLOSED | 2008-04-24 | PL:INSTALL SINKS IN 38-131 | 038 | CLOSED | 6532.44 | 0 | 5888.139 | 5888.139
PJ0002800 Total | [7 empty] | 36057.5822 | 0 | 32463.6524 | 32463.6524
PJ0002799 | INSTALL SPRINKER SYSTEM IN PAINT BOOTH - BLDG 04 (HANGAR) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-04-23 | AD: JOC 07.015.032 MAINO | 004 | CLOSED | 12524.6817 | 0 | 12524.6924 | 12524.6924
PJ0002799 | INSTALL SPRINKER SYSTEM IN PAINT BOOTH - BLDG 04 (HANGAR) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-04-23 | CP: PROJECT CONTINGENCY | 004 | CLOSED | 22.93 | 0 | 0 | 0
PJ0002799 | INSTALL SPRINKER SYSTEM IN PAINT BOOTH - BLDG 04 (HANGAR) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-04-23 | EL: INSTALL ALARM BELL FOR PAINT BOOTH AT AERO HANGER | 004 | CLOSED | 687.552 | 0 | 656.592 | 656.592
PJ0002799 | INSTALL SPRINKER SYSTEM IN PAINT BOOTH - BLDG 04 (HANGAR) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-04-23 | IN: INSTALL SPRINKER SYSTEM IN PAINT BOOTH - BLDG 04 HANGER | 004 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0002799 | INSTALL SPRINKER SYSTEM IN PAINT BOOTH - BLDG 04 (HANGAR) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-04-23 | PL: INSTALL DOUBLE CHECK VALVE FOR PAINT BOOTH SPRINKLER | 004 | CLOSED | 541.986 | 0 | 667.776 | 667.776
PJ0002799 Total | [7 empty] | 13777.1497 | 0 | 13915.3364 | 13915.3364
PJ0002796 | INSTALL SMART ROOM EQUIPMENT - UPD 74 RM 300A (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-04-18 | CA: REMOVE BRACKETS WHITE BOARD | 074 | CLOSED | 332.28 | 0 | 669.675 | 669.675
PJ0002796 | INSTALL SMART ROOM EQUIPMENT - UPD 74 RM 300A (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-04-18 | CP: PROJECT CONTINGENCY | 074 | CLOSED | 0 | 0 | 0 | 0
PJ0002796 | INSTALL SMART ROOM EQUIPMENT - UPD 74 RM 300A (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-04-18 | EL: INSTALL SMART ROOM ELECTRICAL | 074 | CLOSED | 0 | 0 | 1845.858 | 1845.858
PJ0002796 | INSTALL SMART ROOM EQUIPMENT - UPD 74 RM 300A (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-04-18 | IN: INSTALL SMART ROOM EQUIPMENT - UPD 74 RM 300A (N/L) | 074 | CLOSED | 0 | 0 | 0 | 0
PJ0002796 | INSTALL SMART ROOM EQUIPMENT - UPD 74 RM 300A (NO ESTIMATE) | LAMPMAN, GREG | CLOSED | 2008-04-18 | PA: PATCH AND PAINT WALL AS NEEDED | 074 | CLOSED | 0 | 0 | 636.72 | 636.72
PJ0002796 Total | [7 empty] | 332.28 | 0 | 3152.253 | 3152.253
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 04/18 CLEAN THEATRE & RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 04/19 CLEAN THEATRE & RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 04/22 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 04/24 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/15 CLEAN LOBBY RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/16 CLEAN LOBBY RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/17 CLEAN LOBBY RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/18 CLEAN LOBBY RESTROOMS BY 1:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/21 CLEAN LOBBY RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/22 CLEAN LOBBY RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/25 CLEAN THEATRE, RESTROOMS BETWEEN 12PM - 1PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/29 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/30 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 05/31 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 06/05 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 06/06 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 06/07 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 06/18 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 216.072 | 216.072
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 06/19 CLEAN THEATRE & RESTROOMS BY 6:00PM | 044 | CLOSED | 0 | 0 | 216.072 | 216.072
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/11 CLEAN THEATRE & RESTROOMS BY 5:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/12 CLEAN THEATRE & RESTROOMS BETWEEN PERFORMANCES | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/12 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/13 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/18 CLEAN THEATRE & RESTROOMS BY 5:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/19 CLEAN THEATRE & RESTROOMS BETWEEN PERFORMANCES | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/19 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/20 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/24 CLEAN THEATRE & RESTROOMS BY 6:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/25 CLEAN THEATRE & RESTROOMS BY 6:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/26 CLEAN THEATRE & RESTROOMS BY 6:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 07/27 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/01 CLEAN THEATRE & RESTROOMS BY 5:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/02 CLEAN THEATRE & RESTROOMS BETWEEN PERFORMANCES | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/02 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/08 CLEAN THEATRE & RESTROOMS BY 5:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/09 CLEAN THEATRE & RESTROOMS BETWEEN PERFORMANCES | 044 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/09 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/15 CLEAN THEATRE & RESTROOMS BY 5:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/16 CLEAN THEATRE & RESTROOMS BETWEEN PERFORMANCES | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 | 07/08 EXTRA CLEANING, 044 THEATRE-SPRING QTR 2008 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-04-17 | CU: 08/16 CLEAN THEATRE & RESTROOMS BY 12:00 PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002795 Total | [7 empty] | 0 | 0 | 2999.88 | 2999.88
PJ0002793 | WALL REMOVAL - SIERRA MADRE 113 RMS L119 & L122 | GRIFFIN, PATRICK E | CLOSED | 2008-04-17 | CA:REMOVE WALL IN SIERRA MADRE L119 | 113 | CLOSED | 1844.16 | 0 | 1786.29 | 1786.29
PJ0002793 | WALL REMOVAL - SIERRA MADRE 113 RMS L119 & L122 | GRIFFIN, PATRICK E | CLOSED | 2008-04-17 | CP: PROJECT CONTINGENCY | 113 | CLOSED | 393.79 | 0 | 0 | 0
PJ0002793 | WALL REMOVAL - SIERRA MADRE 113 RMS L119 & L122 | GRIFFIN, PATRICK E | CLOSED | 2008-04-17 | EL:MOVE ELECTRICAL FOR WALL REMOVAL AT SIERRA MADRE LOUNGE | 113 | CLOSED | 1448.88 | 0 | 378.6 | 378.6
PJ0002793 | WALL REMOVAL - SIERRA MADRE 113 RMS L119 & L122 | GRIFFIN, PATRICK E | CLOSED | 2008-04-17 | IN: WALL REMOVAL - SIERRA MADRE 113 RMS L119 & L122 | 113 | CLOSED | 0 | 0 | 49.707 | 49.707
PJ0002793 | WALL REMOVAL - SIERRA MADRE 113 RMS L119 & L122 | GRIFFIN, PATRICK E | CLOSED | 2008-04-17 | PA:PATCH AND PAINT WALLS WHERE WALL WAS REMOVED-SIERRA MADRE | 113 | CLOSED | 1299.84 | 0 | 300.768 | 300.768
PJ0002793 Total | [7 empty] | 4986.67 | 0 | 2515.365 | 2515.365
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | AD: FLOORTEC | 001 | CLOSED | 3597.2437 | 0 | 3634.5225 | 3634.5225
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | AD: WHITE'S DRYWALL | 001 | CLOSED | 0 | 0 | 776.178 | 776.178
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | CA:BUILD WALL IN 01-124 | 001 | CLOSED | 3980.8344 | 0 | 3943.566 | 3943.566
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 1209.84 | 0 | 0 | 0
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | IN: BUILD OFFICE WALL ON WEST SIDE OF ROOM - ADMIN 01 RM 124 | 001 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | INSTALL OUTLETS IN NEW WALL BETWEEN 124/125 IN ADM | 001 | CLOSED | 496.4947 | 0 | 2313.1267 | 2313.1267
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | MO: MOVE FURNITURE FROM ADMIN 124 TO BLG. 58 | 001 | CLOSED | 0 | 0 | 125.004 | 125.004
PJ0002791 | SP 08/09: BUILD OFFICE WALL ON W. SIDE OF ROOM - ADMIN 01 RM 124 | MAY, TOM | CLOSED | 2008-04-16 | PA:PAINT 124 & 125 ADM AFTER REMODEL | 001 | CLOSED | 3399.9612 | 0 | 1943.322 | 1943.322
PJ0002791 Total | [7 empty] | 12816.926 | 0 | 12868.2712 | 12868.2712
PJ0002790 | MJ: / FR: ME POLY CARD DOOR PILOT #2 - ENGR IV 192 RM 132 | GRIFFIN, PATRICK E. | CLOSED | 2008-04-16 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 257.63 | 0 | 0 | 0
PJ0002790 | MJ: / FR: ME POLY CARD DOOR PILOT #2 - ENGR IV 192 RM 132 | GRIFFIN, PATRICK E. | CLOSED | 2008-04-16 | EL: PROVIDE NEW CIRCUITS FOR ROOM ALARM LOCK PILOT PROJECT | 192 | CLOSED | 1195.104 | 0 | 333.078 | 333.078
PJ0002790 | MJ: / FR: ME POLY CARD DOOR PILOT #2 - ENGR IV 192 RM 132 | GRIFFIN, PATRICK E. | CLOSED | 2008-04-16 | IN: ME POLY CARD DOOR PILOT #2 - ENGR IV 192 RM 132 | 192 | CLOSED | 132.552 | 0 | 33.138 | 33.138
PJ0002790 | MJ: / FR: ME POLY CARD DOOR PILOT #2 - ENGR IV 192 RM 132 | GRIFFIN, PATRICK E. | CLOSED | 2008-04-16 | LO: INSTALL NEW MORTISE UNLATCH STRIKE AT ENG IV 132 | 192 | CLOSED | 1934.688 | 0 | 7308.375 | 7308.375
PJ0002790 | MJ: / FR: ME POLY CARD DOOR PILOT #2 - ENGR IV 192 RM 132 | GRIFFIN, PATRICK E. | CLOSED | 2008-04-16 | PA: PATCH AND SPOT PAINT HOLES AT ENG IV | 192 | CLOSED | 144.384 | 0 | 85.788 | 85.788
PJ0002790 Total | [7 empty] | 3664.358 | 0 | 7760.379 | 7760.379
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | AD: JOC 07.014.030 STAPLES | 070B | CLOSED | 25628.18 | 0 | 25628.18 | 25628.18
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | CA:REPAIR FOR ELECTRIC SHOP | 070B | CLOSED | 3276.27 | 0 | 5763.1822 | 5763.1822
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | CP: PROJECT CONTINGENCY | 070B | CLOSED | 2469.76 | 0 | 0 | 0
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | EH: OVERSEE LEAD WASTE DISPOSAL AT ELECTRIC SHOP | 070B | CLOSED | 1000.48 | 0 | 459.68 | 459.68
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | ES:ELECTRIC SHOP REPAIR | 070B | CLOSED | 106.72 | 0 | 106.72 | 106.72
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | IN: SR 07/08 PAINT ELECTRIC SHOP - BLDG 70B | 070B | CLOSED | 0 | 0 | 55.23 | 55.23
PJ0002789 | SR 08/09: PAINT ELECTRIC SHOP - BLDG 70B (ENC BY 6/30/09) | MAY, TOM | CLOSED | 2008-04-14 | LO: ELECTRIC SHOP DOOR HARDWARE | 070B | CLOSED | 119.1 | 0 | 586.99 | 586.99
PJ0002789 Total | [7 empty] | 32600.51 | 0 | 32599.9822 | 32599.9822
PJ0002787 | SR 08/09: CREATE PEDESTRIAN SIDEWALK - WELD 58 (ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | AD: JOC 07.015.010 MAINO | 058 | CLOSED | 168560.47 | 0 | 177190.16 | 177190.16
PJ0002787 | SR 08/09: CREATE PEDESTRIAN SIDEWALK - WELD 58 (ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | CA: PROVIDE STOP SIGN POST (MATERIALS, ONLY) (N/L) | 058 | CLOSED | 0 | 0 | 32 | 32
PJ0002787 | SR 08/09: CREATE PEDESTRIAN SIDEWALK - WELD 58 (ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 17063.69 | 0 | 0 | 0
PJ0002787 | SR 08/09: CREATE PEDESTRIAN SIDEWALK - WELD 58 (ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | IN: SR 07/08 CREATE PEDESTRIAN SIDEWALK - WELD 58 | 058 | CLOSED | 0 | 0 | 317.5725 | 317.5725
PJ0002787 | SR 08/09: CREATE PEDESTRIAN SIDEWALK - WELD 58 (ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | LA: MOVE SPRINKLER SYS. | 058 | CLOSED | 2076.48 | 0 | 3427.977 | 3427.977
PJ0002787 | SR 08/09: CREATE PEDESTRIAN SIDEWALK - WELD 58 (ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | PL: INSTALL BACK FLOW FOR LANDSCAPING | 058 | CLOSED | 0 | 0 | 1901.2804 | 1901.2804
PJ0002787 Total | [7 empty] | 187700.64 | 0 | 182868.9899 | 182868.9899
PJ0002786 | SR 08/09:PAINT, FIX GATE & CHANGE NAME - BLDG 58(ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | AD: JOC 07.014.031 STAPLES | 058 | CLOSED | 73967.55 | 0 | 75425.89 | 75425.89
PJ0002786 | SR 08/09:PAINT, FIX GATE & CHANGE NAME - BLDG 58(ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 7396.75 | 0 | 0 | 0
PJ0002786 | SR 08/09:PAINT, FIX GATE & CHANGE NAME - BLDG 58(ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | EH: OVERSEE LEAD WASTE DISPOSAL AT BLG 58 (N/L) | 058 | CLOSED | 0 | 0 | 0 | 0
PJ0002786 | SR 08/09:PAINT, FIX GATE & CHANGE NAME - BLDG 58(ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | EL: PROVIDE ELECTRICAL SHUT-OFF FOR WALL DEMO - BLG 58 | 058 | CLOSED | 0 | 0 | 137.462 | 137.462
PJ0002786 | SR 08/09:PAINT, FIX GATE & CHANGE NAME - BLDG 58(ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | IN: SR 07/08 PAINT, FIX GATE & CHANGE NAME - BLDG 58 | 058 | CLOSED | 0 | 0 | 55.23 | 55.23
PJ0002786 | SR 08/09:PAINT, FIX GATE & CHANGE NAME - BLDG 58(ENC BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2008-04-14 | LO: CHANGE LOCKS TO CONSTRUCTION CORES, BLG 58 | 058 | CLOSED | 71.46 | 0 | 1219.808 | 1219.808
PJ0002786 Total | [7 empty] | 81435.76 | 0 | 76838.39 | 76838.39
PJ0002783 | INSTALL RAPID PROTOTYPING MACHINE ENCLOSURE - ENGR W. 21 | GRIFFIN, PATRICK E | CLOSED | 2008-04-07 | CA:INSTALL NEW WOVEN-WIRE PARTITION AT EW RM 12 | 021 | CLOSED | 2260.4172 | 0 | 1697.34 | 1697.34
PJ0002783 | INSTALL RAPID PROTOTYPING MACHINE ENCLOSURE - ENGR W. 21 | GRIFFIN, PATRICK E | CLOSED | 2008-04-07 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 248.82 | 0 | 0 | 0
PJ0002783 | INSTALL RAPID PROTOTYPING MACHINE ENCLOSURE - ENGR W. 21 | GRIFFIN, PATRICK E | CLOSED | 2008-04-07 | IN: INSTALL RAPID PROTOTYPING MACHINE ENCLOSURE - ENGR W. 21 | 021 | CLOSED | 76.2174 | 0 | 82.845 | 82.845
PJ0002783 | INSTALL RAPID PROTOTYPING MACHINE ENCLOSURE - ENGR W. 21 | GRIFFIN, PATRICK E | CLOSED | 2008-04-07 | LO:INSTALL LOCK IN WOVEN WIRE PARTITION SLIDING DOOR (NO LABOR) | 021 | CLOSED | 151.752 | 0 | 0 | 0
PJ0002783 Total | [7 empty] | 2737.2066 | 0 | 1780.185 | 1780.185
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | AD: REPUBLIC ELEVATOR FOR NOV 8 FOOTBALL (N/L) | 061 | CLOSED | 0 | 0 | 1741.39 | 1741.39
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | AD: REPUBLIC ELEVATOR ON SITE FOR 11/1 FOOTBALL GAME (N/L) | 061 | CLOSED | 0 | 0 | 1934.88 | 1934.88
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | AD: REPUBLIC ELEVATOR ON SITE FOR 11/29 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 1935.11 | 1935.11
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | AD: REPUBLIC ELEVTR ON SITE FOR 11/15 FTBALL GAME (N/L) | 061 | CLOSED | 0 | 0 | 1934.88 | 1934.88
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | AD: REPUBLIC ELVATR ON SITE FOR 10/25 FTBALL GAME (N/L) | 061 | CLOSED | 0 | 0 | 3616.6 | 3616.6
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | AD: REPUBLIC ELVATR ON SITE FOR 10/4 FTBALL GAME (N/L) | 061 | CLOSED | 0 | 0 | 1934.88 | 1934.88
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA: 08/09 FOOTBALL - NOV 01 A-FRAMES, BOARDS & STANCHIONS SETUP | 061 | CLOSED | 443.04 | 0 | 193.83 | 193.83
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA: 08/09 FOOTBALL - NOV 08 A-FRAMES, BOARDS, & STANCHIONS SETUP | 061 | CLOSED | 221.52 | 0 | 110.76 | 110.76
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA: 08/09 FOOTBALL - NOV 15 A-FRAMES, BOARDS, & STANCHIONS SETUP | 061 | CLOSED | 886.08 | 0 | 110.76 | 110.76
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA: 08/09 FOOTBALL - NOV 29 A-FRAMES, BOARD & STANCHION SETUP | 061 | CLOSED | 443.04 | 0 | 0 | 0
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA: 08/09 FOOTBALL - OCT 04 A-FRAMES, BOARDS & STANCHIONS SETUP | 061 | CLOSED | 443.04 | 0 | 1107.6 | 1107.6
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA: 08/09 FOOTBALL - OCT 25 A-FRAMES, BOARDS & STANCHIONS SETUP | 061 | CLOSED | 221.52 | 0 | 553.8 | 553.8
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CA:08/09 FOOTBALL - SEPT. 5 A-FRAMES, BOARDS, STANCHIONS. | 061 | CLOSED | 221.52 | 0 | 692.25 | 692.25
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL APRIL 5 FUNDRAISER | 061 | CLOSED | 0 | 0 | 150.48 | 150.48
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 PRELIMINARY WORK FOR FOOTBALL SEASON | 061 | CLOSED | 0 | 0 | 3762 | 3762
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - NOV 01 IDAHO ST. (HALL OF FAME GAME)6:05 PM | 061 | CLOSED | 0 | 0 | 3724.38 | 3724.38
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - NOV 08 NORTH CAROLINA CTRL (HM COM) 4:05 PM | 061 | CLOSED | 0 | 0 | 3816.954 | 3816.954
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - NOV 15 UC DAVIS (FACULTY/STAFF DAY) 4:05 PM | 061 | CLOSED | 0 | 0 | 3912.48 | 3912.48
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - NOV 29 FB V. WEBER 6:05 PM | 061 | CLOSED | 0 | 0 | 4194.63 | 4194.63
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - OCT 04 SOUTH DAKOTA (YOUTH DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 3398.328 | 3398.328
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - OCT 25 SOUTHERN UTAH (PARENTS WKD) 6:05 PM | 061 | CLOSED | 0 | 0 | 3996.378 | 3996.378
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: 08/09 FOOTBALL - SEPT 06 MONTANA (MIL. APPREC. DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 3260.9953 | 3260.9953
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: CUSTODIAL SUPPORT FOR FOOTBALL SCRIMMAGE - 4/18 | 061 | CLOSED | 0 | 0 | 37.62 | 37.62
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: CUSTODIAL SUPPORT FOR GREEN/GOLD FOOTBALL - 4/25 | 061 | CLOSED | 0 | 0 | 207.168 | 207.168
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: POWERWASH BLEACHERS BEFORE 11/1 FOOTBALL GAME | 061 | CLOSED | 0 | 0 | 2144.808 | 2144.808
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: RECYLE BINS FOR FOOTBALL PRACTICE 8/5-8/22(N/L) NO CHARGE | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: SUITES SUPPORT FOR FB VS. UC DAVIS 11/15 4PM | 061 | CLOSED | 0 | 0 | 409.95 | 409.95
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: SUITES SUPPORT FOR FOOTBALL GAME 11/8 | 061 | CLOSED | 0 | 0 | 426.348 | 426.348
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | CU: SUITES SUPPORT FOR FOR FB V. WEBER NOV 29 6:05PM | 061 | CLOSED | 0 | 0 | 597.096 | 597.096
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 PRELIMINARY WORK FOR FOOTBALL SEASON | 061 | CLOSED | 0 | 0 | 158.61 | 158.61
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - NOV 01 IDAHO ST. (HALL OF FAME GAME)6:05 PM | 061 | CLOSED | 0 | 0 | 400.224 | 400.224
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - NOV 08 NORTH CAROLINA CTRL (HM COM) 4:05 PM | 061 | CLOSED | 0 | 0 | 1169.134 | 1169.134
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - NOV 15 UC DAVIS (FACULTY/STAFF DAY) 4:05 PM | 061 | CLOSED | 0 | 0 | 749.166 | 749.166
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - NOV 29 FB VS. WEBER 6:05 PM | 061 | CLOSED | 0 | 0 | 721.204 | 721.204
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - OCT 04 SOUTH DAKOTA (YOUTH DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 400.224 | 400.224
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - OCT 25 SOUTHERN UTAH (PARENTS WKD) 6:05 PM | 061 | CLOSED | 0 | 0 | 631.722 | 631.722
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: 08/09 FOOTBALL - SEPT 06 MONTANA (MIL. APPREC. DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 509.58 | 509.58
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: INSTALL 50 AMP DISTRIBUTION BOX O'NEILL LAWN 11/8 BEFORE 12P | 061 | CLOSED | 0 | 0 | 208.98 | 208.98
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | EL: INSTALL 50 AMP DISTRIBUTION BOX(SPIDER BOX) O'NEILL LAWN | 061 | CLOSED | 0 | 0 | 72.768 | 72.768
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | ES: 08/09 FOOTBALL - NOV 1 FOOTBALL V. IDAHO 6:05 PM | 061 | CLOSED | 256.128 | 0 | 297.546 | 297.546
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | ES: 08/09 FOOTBALL - NOV 15 UC DAVIS (FACULTY/STAFF DAY) 4:05 PM | 061 | CLOSED | 416.208 | 0 | 511.056 | 511.056
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | ES: 08/09 FOOTBALL - NOV 29 FOOTBALL V. WEBER - 6:05PM | 061 | CLOSED | 128.064 | 0 | 400.896 | 400.896
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | ES: 08/09 FOOTBALL - NOV 8 FOOTBALL V. N. CAROLINA 4PM | 061 | CLOSED | 256.128 | 0 | 293.76 | 293.76
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | ES: 08/09 FOOTBALL OCT 25 STHRN UTAH (PARENTS WKD) 6:05 (N/L) | 061 | CLOSED | 128.064 | 0 | 28.08 | 28.08
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL APRIL 5 FUNDRAISER | 061 | CLOSED | 0 | 0 | 918.252 | 918.252
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 PRELIMINARY WORK FOR FOOTBALL SEASON (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - NOV 01 IDAHO ST. (HALL OF FAME GAME)6:05 PM | 061 | CLOSED | 0 | 0 | 5155.89 | 5155.89
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - NOV 08 NORTH CAROLINA CTRL (HM COM) 4:05 PM | 061 | CLOSED | 0 | 0 | 4452.42 | 4452.42
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - NOV 15 UC DAVIS (FACULTY/STAFF DAY) 4:05 PM | 061 | CLOSED | 0 | 0 | 4619.226 | 4619.226
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - NOV 29 FB V WEBER 6:05 PM | 061 | CLOSED | 0 | 0 | 3864.114 | 3864.114
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - OCT 04 SOUTH DAKOTA (YOUTH DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 5969.19 | 5969.19
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - OCT 25 SOUTHERN UTAH (PARENTS WKD) 6:05 PM | 061 | CLOSED | 0 | 0 | 5642.67 | 5642.67
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: 08/09 FOOTBALL - SEPT 06 MONTANA (MIL. APPREC. DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 7343.52 | 7343.52
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: LINING (I & TRACK FIELD 042-Q & W) FOR FOOTBALL PRACTICE 8/6 | 061 | CLOSED | 0 | 0 | 2321.16 | 2321.16
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: LINING (TRACK FIELD 042-W) FOR FOOTBALL SUMMER CAMP | 061 | CLOSED | 0 | 0 | 363.312 | 363.312
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: LINING (TRACK FIELD 042-W) FOR FOOTBALL TEAM | 061 | CLOSED | 0 | 0 | 268.332 | 268.332
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: LINING FOR SCRIMMAGE 8/22/2008 | 061 | CLOSED | 0 | 0 | 1089.936 | 1089.936
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | GR: POWERWASH BLEACHERS ON WEST SIDE BEFORE 10/25 GAME | 061 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | LA: LINE SPANOS STADIUM FOR FOOTBALL PRACTICE - 4/18 | 061 | CLOSED | 0 | 0 | 645.888 | 645.888
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | LA: LINE SPANOS STADIUM FOR PRO DAY (FOOTBALL) - 3/30 | 061 | CLOSED | 0 | 0 | 100.92 | 100.92
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | LA: LINE SPANOS STADIUM FOR SPRING FOOTBALL GAME - 4/25 | 061 | CLOSED | 0 | 0 | 322.944 | 322.944
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | LA: LINING FOR FOOTBALL PRACTICES AT REC FIELD 7/6, 7/20, 8/3 | 043 | CLOSED | 0 | 0 | 666.072 | 666.072
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 PRELIMINARY WORK FOR FOOTBALL SEASON (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 FOOTBALL - NOV 01 IDAHO ST. (HALL OF FAME GAME)6:05 PM | 061 | CLOSED | 0 | 0 | 1491.732 | 1491.732
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 FOOTBALL - NOV 08 NORTH CAROLINA CTRL (HM COM) 4:05 PM | 061 | CLOSED | 0 | 0 | 364.62 | 364.62
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 FOOTBALL - NOV 15 UC DAVIS (FACULTY/STAFF DAY) 4:05 PM | 061 | CLOSED | 0 | 0 | 1133.0196 | 1133.0196
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 FOOTBALL - OCT 04 SOUTH DAKOTA (YOUTH DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 364.62 | 364.62
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 FOOTBALL - OCT 25 SOUTHERN UTAH (PARENTS WKD) 6:05 PM | 061 | CLOSED | 0 | 0 | 682.29 | 682.29
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: 08/09 FOOTBALL - SEPT 06 MONTANA (MIL. APPREC. DAY) 6:05 PM | 061 | CLOSED | 0 | 0 | 523.56 | 523.56
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | PL: NOV 29 FB V. WEBER 6:05PM | 061 | CLOSED | 0 | 0 | 304.506 | 304.506
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | RENTAL: 08/09 FOOTBALL TAILGATE NOV 29 - H12 LOT (CB-DEPT OK) | 061 | CLOSED | 0 | 0 | 152.502 | 152.502
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | RENTAL:08/09 MUSTANG CORRAL BBQ NOV 29-O'NEILL GREEN(CB-DEPT OK) | 061 | CLOSED | 0 | 0 | 442.362 | 442.362
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FOOTBALL TAILGATE NOV 06 - H12 PRKG LOT | 061 | CLOSED | 0 | 0 | 190.24 | 190.24
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FB HM TEAM BRKFST SEPT 6 - BEHIND MOTT 42 | 061 | CLOSED | 0 | 0 | 45 | 45
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FOOTBALL TAILGATE NOV 01 - H12 PRKG LOT | 061 | CLOSED | 0 | 0 | 190.24 | 190.24
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FOOTBALL TAILGATE NOV 08 - H12 PRKG LOT | 061 | CLOSED | 0 | 0 | 146.955 | 146.955
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FOOTBALL TAILGATE NOV 15 - H12 PRKG LOT | 061 | CLOSED | 0 | 0 | 155.81 | 155.81
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FOOTBALL TAILGATE OCT 04 - H12 PRKG LOT | 061 | CLOSED | 0 | 0 | 171.64 | 171.64
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 FOOTBALL TAILGATE OCT 25- H12 PRKG LOT | 061 | CLOSED | 0 | 0 | 190.24 | 190.24
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 MUSTANG CORRAL BBQ OCT 04 - O'NEILL GREEN | 061 | CLOSED | 0 | 0 | 349.94 | 349.94
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 MUSTANG CORRAL BBQ NOV 01 - O'NEILL GREEN | 061 | CLOSED | 0 | 0 | 355.48 | 355.48
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 MUSTANG CORRAL BBQ NOV 06 - O'NEILL GREEN | 061 | CLOSED | 0 | 0 | 337.325 | 337.325
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 MUSTANG CORRAL BBQ NOV 08 - O'NEILL GREEN | 061 | CLOSED | 0 | 0 | 346.7385 | 346.7385
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 MUSTANG CORRAL BBQ NOV 15 - O'NEILL GREEN | 061 | CLOSED | 0 | 0 | 314.6335 | 314.6335
PJ0002782 | 08/09 FOOTBALL SEASON (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-04-03 | SUPPLY RENTAL: 08/09 MUSTANG CORRAL BBQ OCT 25 - O'NEILL GREEN | 061 | CLOSED | 0 | 0 | 392.9882 | 392.9882
PJ0002782 Total | [7 empty] | 4064.352 | 0 | 109091.801 | 109091.801
PJ0002781 | MUSTANG TICKET OFFICE RENOVATION - REC 43 | PAHLOW, BOB | CLOSED | 2008-03-28 | ATS-PROGRAM WIRELESS PANIC ALARM FOR REC SPORTS TICKET OFFICE | 043 | CLOSED | 0 | 0 | 28.584 | 28.584
PJ0002781 | MUSTANG TICKET OFFICE RENOVATION - REC 43 | PAHLOW, BOB | CLOSED | 2008-03-28 | CA-INSTALL PEEP HOLE AND SECURITY SCREEN DOOR TO TICKET OFFICE | 043 | CLOSED | 350.3868 | 0 | 230.52 | 230.52
PJ0002781 | MUSTANG TICKET OFFICE RENOVATION - REC 43 | PAHLOW, BOB | CLOSED | 2008-03-28 | CP: PROJECT CONTINGENCY | 043 | CLOSED | 160.81 | 0 | 0 | 0
PJ0002781 | MUSTANG TICKET OFFICE RENOVATION - REC 43 | PAHLOW, BOB | CLOSED | 2008-03-28 | IN-BUILDING PERMIT AND INSPECTION (NO LABOR) | 043 | CLOSED | 0 | 0 | 0 | 0
PJ0002781 Total | [7 empty] | 511.1968 | 0 | 259.104 | 259.104
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | AD: BUEHLER AND BUEHLER | 170G | CLOSED | 3000 | 0 | 3000 | 3000
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | AD: SEISMIC PEER REVIEW - ENGLEKIRK AND SABOL | 170G | CLOSED | 0 | 0 | 500 | 500
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | CA: INSTALL NEW WINDOW AT CERRO VISTA COMMONS | 170G | CLOSED | 2341 | 0 | 4719.99 | 4719.99
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | CP: PROJECT CONTINGENCY | 170G | CLOSED | 479.85 | 0 | 0 | 0
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | EL:COMPLETE ELECTRICAL AND ALARM WORK AT CERRO VISTA | 170G | CLOSED | 684.44 | 0 | 810.28 | 810.28
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | IN: INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMMON BLD. 170G | 170G | CLOSED | 220.92 | 0 | 240.2505 | 240.2505
PJ0002780 | INSTALL 4'X4' FIXED PANE WINDOW - C.V. COMM BLD. 170G (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-03-25 | PA:TAPE, PRIME, AND PAINT NEW WINDOW OPENING AT CERRO VISTA | 170G | CLOSED | 1552.12 | 0 | 1388.22 | 1388.22
PJ0002780 Total | [7 empty] | 8278.33 | 0 | 10658.7405 | 10658.7405
PJ0002778 | MAY 4TH & 5TH BAKER FORUM - PAC 06 (NO ESTIMATE) | MAY, TOM | CLOSED | 2008-03-20 | CA:REPAIR LIST FOR BAKER FORUM EVENT AT PAC MAY 4/5 | 006 | CLOSED | 1107.6 | 0 | 1440.075 | 1440.075
PJ0002778 | MAY 4TH & 5TH BAKER FORUM - PAC 06 (NO ESTIMATE) | MAY, TOM | CLOSED | 2008-03-20 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002778 | MAY 4TH & 5TH BAKER FORUM - PAC 06 (NO ESTIMATE) | MAY, TOM | CLOSED | 2008-03-20 | CU: CUSTODIAL SUPPORT FOR BAKER FORUM | 006 | CLOSED | 0 | 0 | 136.65 | 136.65
PJ0002778 | MAY 4TH & 5TH BAKER FORUM - PAC 06 (NO ESTIMATE) | MAY, TOM | CLOSED | 2008-03-20 | PA:TOUCH UP PAINTING FOR BAKER FORUM | 006 | CLOSED | 0 | 0 | 3145.19 | 3145.19
PJ0002778 Total | [7 empty] | 1107.6 | 0 | 4721.915 | 4721.915
PJ0002777 | ENG 13 MOVE AND MODIFY FURNITURE | DANKO, KEN | CLOSED | 2008-03-20 | CA: TAKEOFF CREDENZA & MODIFY/EXTEND COMPUTER DESK | 013 | CLOSED | 1329.12 | 0 | 6183.8594 | 6183.8594
PJ0002777 | ENG 13 MOVE AND MODIFY FURNITURE | DANKO, KEN | CLOSED | 2008-03-20 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 7000 | 0 | 0 | 0
PJ0002777 | ENG 13 MOVE AND MODIFY FURNITURE | DANKO, KEN | CLOSED | 2008-03-20 | PA: STAIN/FINISH SHELVES FOR COUNTER SPACE, PATCH/PAINT WALL | 013 | CLOSED | 0 | 0 | 806.868 | 806.868
PJ0002777 Total | [7 empty] | 8329.12 | 0 | 6990.7274 | 6990.7274
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CA: SETUP 1' TALL STAGE FOR SUSTAINABILITY CONF DINNER | GENERAL | CLOSED | 332.28 | 0 | 396.201 | 396.201
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CU: SETUP & CUSTODIAL SERVICES | GENERAL | CLOSED | 0 | 0 | 584.55 | 584.55
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CU: MOTT GYM FLOOR CLEAN UP - SUSTAINABILITY CONFERENCE | GENERAL | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CU: RENTALS SUSTAINABILITY CONFERENCE 7/30-8/3 | GENERAL | CLOSED | 0 | 0 | 1290 | 1290
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | EL:SUPPORT FOR 2008 SUSTAINABILITY CONFERENCE | GENERAL | CLOSED | 0 | 0 | 3218.526 | 3218.526
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | IN: FIRE MARSHAL PERMIT FOR EXHIBIT HALL (NO LABOR) | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | PL: PM RESTROOMS CAMPUSWIDE BEFORE JULY 31, 2008 (MAINT) | GENERAL | CLOSED | 0 | 0 | 1884.2904 | 1884.2904
PJ0002776 | 2008 SUSTAINABILITY CONFERENCE, JULY 31-AUG 3 (NO ESTIMATE) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | RC: TRASHCANS RECYCLE CANS & COMPOST BINS | GENERAL | CLOSED | 0 | 0 | 1151.598 | 1151.598
PJ0002776 Total | [7 empty] | 332.28 | 0 | 8656.3494 | 8656.3494
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | AD: OVERSEE SPRING COMMENCEMENT 2008 (N/L) | GENERAL | CLOSED | 0 | 0 | 28.1978 | 28.1978
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CA: REC CTR - PR0VIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" CB | 043 | CLOSED | 1329.12 | 0 | 1567.8686 | 1567.8686
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CA: STADIUM - PROVIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | 061 | CLOSED | 5538 | 0 | 7931.93 | 7931.93
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CU: REC CTR-PROVIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" CB | 043 | CLOSED | 0 | 0 | 1311.84 | 1311.84
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | CU: SPANOS STADIUM PROVIDE TRASH CANS & SETUP | GENERAL | CLOSED | 0 | 0 | 12340.3655 | 12340.3655
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | EL: PR0VIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | GENERAL | CLOSED | 0 | 0 | 772.78 | 772.78
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | ES: PROVIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | GENERAL | CLOSED | 0 | 0 | 106.72 | 106.72
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | IN: TENT PERMIT FOR 2008 "SPRING COMMENCEMENT" | GENERAL | CLOSED | 0 | 0 | 27.615 | 27.615
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | LA: PR0VIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | GENERAL | CLOSED | 0 | 0 | 10536.5925 | 10536.5925
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | MO: REC. CTR.-PR0VIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" CB | 043 | CLOSED | 0 | 0 | 1089.546 | 1089.546
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | MO: STADIUM - PROVIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | 061 | CLOSED | 0 | 0 | 479.895 | 479.895
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | PA: PR0VIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | GENERAL | CLOSED | 0 | 0 | 595.75 | 595.75
PJ0002775 | PROVIDE SERVICES FOR "SPRING COMMENCEMENT 2008" (MAINT) | POPHAM, DONALD J. | CLOSED | 2008-03-19 | PL: PROVIDE SERVICES FOR 2008 "SPRING COMMENCEMENT" | GENERAL | CLOSED | 0 | 0 | 3438.99 | 3438.99
PJ0002775 Total | [7 empty] | 6867.12 | 0 | 40228.0904 | 40228.0904
PJ0002774 | INSTALL 12' X 8' CURTAIN BETWEEN RMS 134 & 135 - ENGR E 20 | GRIFFIN, PATRICK E | CLOSED | 2008-03-18 | CA:INSTALL NEW ACCORDIAN DOOR AT EE 134 | 020 | CLOSED | 7287.0372 | 0 | 9787.764 | 9787.764
PJ0002774 | INSTALL 12' X 8' CURTAIN BETWEEN RMS 134 & 135 - ENGR E 20 | GRIFFIN, PATRICK E | CLOSED | 2008-03-18 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 958.72 | 0 | 0 | 0
PJ0002774 | INSTALL 12' X 8' CURTAIN BETWEEN RMS 134 & 135 - ENGR E 20 | GRIFFIN, PATRICK E | CLOSED | 2008-03-18 | IN: INSTALL 12' X 8' CURTAIN BETWEEN RMS 134 & 135 - ENGR E 20 | 020 | CLOSED | 265.104 | 0 | 33.138 | 33.138
PJ0002774 | INSTALL 12' X 8' CURTAIN BETWEEN RMS 134 & 135 - ENGR E 20 | GRIFFIN, PATRICK E | CLOSED | 2008-03-18 | PA:TAPE, MUD, NEW OPENING FOR ACCORDIAN DOOR AT EE 134 | 020 | CLOSED | 1751.376 | 0 | 1689.969 | 1689.969
PJ0002774 Total | [7 empty] | 10262.2372 | 0 | 11510.871 | 11510.871
PJ0002771 | MJ: FABRICATE PLATFORMS & INSTALL PLEXIGLASS -61(TRACKING, ONLY) | JUDD, PERRY | CLOSED | 2008-03-18 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002771 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002770 | REPAIR/REPLACE TRANSFORMER AT BASE OF PIER - PIER 228 (NO EST) | VELARDE, DENIS L | CLOSED | 2008-03-17 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 0 | 0 | 0 | 0
PJ0002770 | REPAIR/REPLACE TRANSFORMER AT BASE OF PIER - PIER 228 (NO EST) | VELARDE, DENIS L | CLOSED | 2008-03-17 | EL: REPLACE TRANSFORMER AT AVILA PIER 228 | 228 | CLOSED | 0 | 0 | 10799.5621 | 10799.5621
PJ0002770 Total | [7 empty] | 0 | 0 | 10799.5621 | 10799.5621
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | AD: JOC 07.014.018 STAPLES | 061 | CLOSED | 34220.9219 | 0 | 34220.847 | 34220.847
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 4288.96 | 0 | 0 | 0
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | EL: EXTEND CONDUIT AT SPANOS STADIUM | 061 | CLOSED | 560.664 | 0 | 140.334 | 140.334
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | EO: EXCAVATE FOR SIDEWALK AT SPANOS STADIUM 61 | 061 | CLOSED | 2224.512 | 0 | 6094.236 | 6094.236
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | IN: ADA ACCESSIBILITY - SPANOS STADIUM 61 | 061 | CLOSED | 0 | 0 | 463.932 | 463.932
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | LA: IRRIGATION AND SOD AT SPANOS STADIUM | 061 | CLOSED | 5883.552 | 0 | 5906.1911 | 5906.1911
PJ0002767 | MC 07/08 ADA ACCESSIBILITY - SPANOS STADIUM 61 (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2008-03-07 | PA: MATERIALS, ONLY, TO BE USED BY JOC AT SPANOS CONCESSION 061 | 061 | CLOSED | 0 | 0 | 47.22 | 47.22
PJ0002767 Total | [7 empty] | 47178.6099 | 0 | 46872.7601 | 46872.7601
PJ0002766 | ROUTINE MAINTENANCE WHILE RESIDENCE IS VACANT - CHORRO CREEK 126 | GRIFFIN, PATRICK E | CLOSED | 2008-03-07 | CA: COMPLETE MAINTENANCE AT CHORRO CREEK RANCH | 126 | CLOSED | 2953.6 | 0 | 853.775 | 853.775
PJ0002766 | ROUTINE MAINTENANCE WHILE RESIDENCE IS VACANT - CHORRO CREEK 126 | GRIFFIN, PATRICK E | CLOSED | 2008-03-07 | CP: PROJECT CONTINGENCY | 126 | CLOSED | 0 | 0 | 0 | 0
PJ0002766 | ROUTINE MAINTENANCE WHILE RESIDENCE IS VACANT - CHORRO CREEK 126 | GRIFFIN, PATRICK E | CLOSED | 2008-03-07 | PA: PAINT VARIOUS ROOMS IN RESIDENCE AS NEEDED. | 126 | CLOSED | 0 | 0 | 1503.84 | 1503.84
PJ0002766 Total | [7 empty] | 2953.6 | 0 | 2357.615 | 2357.615
PJ0002763 | SP 07/08 POT HOLE TO LOCATE UTILITIES FOR TES TANK - VIA CARTA | MAY, TOM | CLOSED | 2008-03-06 | AD: JOC 07.013.057 MAINO | GENERAL | CLOSED | 10344.7707 | 0 | 10344.7707 | 10344.7707
PJ0002763 | SP 07/08 POT HOLE TO LOCATE UTILITIES FOR TES TANK - VIA CARTA | MAY, TOM | CLOSED | 2008-03-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002763 Total | [7 empty] | 10344.7707 | 0 | 10344.7707 | 10344.7707
PJ0002757 | M&R HOUSING 08/09 REPLACE ROOF - MUIR HALL 107 | GRIFFIN, PATRICK E | CLOSED | 2008-03-04 | AD: JOC 07.013.058 MAINO | 107 | CLOSED | 282236.8 | 0 | 282236.8 | 282236.8
PJ0002757 | M&R HOUSING 08/09 REPLACE ROOF - MUIR HALL 107 | GRIFFIN, PATRICK E | CLOSED | 2008-03-04 | CA:SUPPORT SERVICES FOR MUIR RE-ROOF (NO LABOR) | 107 | CLOSED | 1576.8 | 0 | 0 | 0
PJ0002757 | M&R HOUSING 08/09 REPLACE ROOF - MUIR HALL 107 | GRIFFIN, PATRICK E | CLOSED | 2008-03-04 | CP: PROJECT CONTINGENCY | 107 | CLOSED | 26186.4 | 0 | 0 | 0
PJ0002757 Total | [7 empty] | 310000 | 0 | 282236.8 | 282236.8
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | AD: JOC 07.013.056 MAINO | 114 | CLOSED | 275191.73 | 0 | 275191.75 | 275191.75
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | CP: PROJECT CONTINGENCY | 114 | CLOSED | 12790.01 | 0 | 0 | 0
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | EL:ELECTRICAL FOR YOSEMITE TOWER 1 RESTROOM REMODEL | 114 | CLOSED | 6554.6 | 0 | 5827.0442 | 5827.0442
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | ES:REGISTERS FOR YOSEMITE TOWER 1 RESTROOMS | 114 | CLOSED | 715.32 | 0 | 410.14 | 410.14
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | IN: M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | 114 | CLOSED | 220.92 | 0 | 234.7275 | 234.7275
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | LO:DEADBOLTS FOR YOSEMITER TOWER1 | 114 | CLOSED | 690.56 | 0 | 620.61 | 620.61
PJ0002755 | M&R HOUSING 08/09 BATHROOM RENOVATION - YOSEMITE TOWER 1 | MAY, TOM | CLOSED | 2008-03-04 | PL:YOSEMITE TOWER 1 REMODEL | 114 | CLOSED | 15000 | 0 | 15065.232 | 15065.232
PJ0002755 Total | [7 empty] | 311163.14 | 0 | 297349.5037 | 297349.5037
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | AD: JOC 07.015.029 MAINO | 038 | CLOSED | 175629.1687 | 0 | 177483.3931 | 177483.3931
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | AD: PLAYGROUNDS UNLIMITED | 038 | CLOSED | 0 | 0 | 2570 | 2570
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 1911.27 | 0 | 0 | 0
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | EL:INSTALL CONDUIT AND ELECTRICAL FOR LANDSCAPING | 038 | CLOSED | 761.328 | 0 | 949.902 | 949.902
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | IN: RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | 038 | CLOSED | 132.552 | 0 | 298.242 | 298.242
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | LA:CONSTRUCTION SUPPORT FOR LAB PLAY YARD RENOVATION | 038 | CLOSED | 322.944 | 0 | 585.336 | 585.336
PJ0002751 | RENOVATION OF PRESCHOOL LAB YARD - BLDG 38 | MOLLAN, CHERYL L. | CLOSED | 2008-02-26 | MO: MOVE PLAY EQUIPMENT FOR PRESCHOOL YARD RENOVATION | 038 | CLOSED | 63 | 0 | 63 | 63
PJ0002751 Total | [7 empty] | 178820.2627 | 0 | 181949.8731 | 181949.8731
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | 08/09 GR: MEN'S SOCCER (SERVICES FOR ATHLETICS) | 061 | CLOSED | 0 | 0 | 118.512 | 118.512
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | AD: ELEVATOR SUUPORT FOR MENS SOCCER ON 10/17 | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | AD: REPUBLIC ELEVATOR SUPPORT FOR MENS SOCCER ON 10/17 | 061 | CLOSED | 0 | 0 | 1547.9 | 1547.9
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - AUG 31 AIR FORCE 1:00PM | 061 | CLOSED | 0 | 0 | 1243.386 | 1243.386
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - NOV 02 UC DAVIS 2:30PM | 061 | CLOSED | 0 | 0 | 1128.6 | 1128.6
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - OCT 01 CAL STATE FULLERTON 7:00PM | 061 | CLOSED | 0 | 0 | 1067.346 | 1067.346
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - OCT 08 UC RIVERSIDE 7:00PM | 061 | CLOSED | 0 | 0 | 940.5 | 940.5
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - OCT 17 UC SANTA BARBARA 8:00PM | 061 | CLOSED | 0 | 0 | 2231.136 | 2231.136
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - OCT 22 UC IRVINE 7:00PM | 061 | CLOSED | 0 | 0 | 1099.656 | 1099.656
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - SEPT 07 KENTUCKY (LMU TOURNY) 1:00PM | 061 | CLOSED | 0 | 0 | 1376.019 | 1376.019
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - SEPT 20 EVANSVILLE 7:00PM | 061 | CLOSED | 0 | 0 | 1339.848 | 1339.848
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 MEN'S SOCCER - SEPT 24 CAL STATE BAKERSFIELD 7:00PM | 061 | CLOSED | 0 | 0 | 777.96 | 777.96
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 PRES. AND GUEST SUITES CLEANING FOR SOCCER 10/8 | 061 | CLOSED | 0 | 0 | 172.179 | 172.179
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 SOCCER PRE-SEASON GAME - APR 26 STANFORD 1:00 & 4:00PM | 061 | CLOSED | 0 | 0 | 217.998 | 217.998
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 SOCCER PRE-SEASON GAME - MAR 8 UCLA 7:00PM | 061 | CLOSED | 0 | 0 | 1166.22 | 1166.22
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: 08/09 SPANOS SUITES CLEANUP MEN'S SOCCER-SEPT 20 EVANSVILLE | 061 | CLOSED | 0 | 0 | 361.728 | 361.728
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: CUSTODIAL SUPPORT FOR MEN'S SOCCER SCRIMMAGE - 4/18 AT 7PM | 061 | CLOSED | 0 | 0 | 18.81 | 18.81
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: CUSTODIAL SUPPORT FOR MEN'S SOCCER SCRIMMAGE ON 4/12 | 061 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: CUSTODIAL SUPPORT FOR MENS SOCCER GAME - 5/29 | 061 | CLOSED | 0 | 0 | 431.172 | 431.172
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: CUSTODIAL SUPPORT FOR MENS SOCCER SCRIMMAGE 4/5 | 061 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: SUITE CLEANING FOR CP V. FULLTERTON ON 10/01 | 061 | CLOSED | 0 | 0 | 204.975 | 204.975
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: SUITE CLEANING FOR CP V. IRVINE ON 10/12 | 061 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: SUITE CLEANING FOR CP V. NORTHRIDGE ON 10/12 | 061 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: SUITE CLEANING FOR CP V. UC DAVIS ON 11/2 | 061 | CLOSED | 0 | 0 | 352.557 | 352.557
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | CU: SUITES CLEANING FOR MEN'S SOCCER PLAYOFF GAME-NOV 15(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | EL: MENS SOCCER - OCT 17 CP VS. SANTA BARABARA 8:00 PM | 061 | CLOSED | 0 | 0 | 581.688 | 581.688
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | EL: PROVIDE POWER FOR CAMERA CREW AT SPANOS STADIUM BY OCT 16 | 061 | CLOSED | 0 | 0 | 63.444 | 63.444
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - AUG 31 AIR FORCE 1:00PM (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - NOV 02 UC DAVIS 2:30PM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - NOV 12 TBD(BIG WEST SEMINFINAL) 5:30PM | 061 | CLOSED | 0 | 0 | 24.0508 | 24.0508
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - OCT 08 UC RIVERSIDE 7:00PM | 061 | CLOSED | 0 | 0 | 230.934 | 230.934
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - OCT 17 UC SANTA BARBARA 8:00PM | 061 | CLOSED | 0 | 0 | 407.256 | 407.256
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - OCT 22 UC IRVINE 7:00PM | 061 | CLOSED | 0 | 0 | 230.934 | 230.934
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - SEPT 07 KENTUCKY (LMU TOURNY) 1:00PM | 061 | CLOSED | 0 | 0 | 231.54 | 231.54
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - SEPT 20 EVANSVILLE 7:00PM | 061 | CLOSED | 0 | 0 | 352.038 | 352.038
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER - SEPT 24 CAL STATE BAKERSFIELD 7:00PM | 061 | CLOSED | 0 | 0 | 144.258 | 144.258
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER- 09/12 MISSOURI ST(NM TOURNY) 2:30PM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 MEN'S SOCCER-OCT 01 CAL STATE FULLERTON 7:00PM(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 SOCCER PRE-SEASON GAME - APR 26 STANFORD 1:00 & 4:00PM | 061 | CLOSED | 0 | 0 | 369.708 | 369.708
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | GR: 08/09 SOCCER PRE-SEASON GAME - MAR 8 UCLA 7:00PM | 061 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | LA: LANDSCAPE SUPPORT FOR MENS SOCCER - 4/18(N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | LA: LINE FOR MENS SOCCER V. N MEXICO & BAKERSFIELD - 4/12 | 061 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | LA: LINE SPANOS STAD FOR WOMEN'S SOCCER - 5/8 | 061 | CLOSED | 0 | 0 | 222.024 | 222.024
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | LA: LINE SPANOS STADIUM FOR MEN'S SOCCER V. CLUB OF AM. - 5/29 | 061 | CLOSED | 0 | 0 | 514.116 | 514.116
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | LA: SUPPORT FOR MENS SOCCER V FRESNO FUEGO 4/18 | 061 | CLOSED | 0 | 0 | 242.208 | 242.208
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | LA: SUPPORT FOR SOCCER SCRIMMAGE ON 4/4 & 4/5 | 061 | CLOSED | 0 | 0 | 444.048 | 444.048
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | PL: 08/09 PM RESTROOMS AT SPANOS STAD.FOR M. SOCCER 10/8 | 061 | CLOSED | 0 | 0 | 254.304 | 254.304
PJ0002750 | 08/09 MEN'S SOCCER (SERVICES FOR ATHLETICS) - NO ESTIMATE | POPHAM, DONALD J. | CLOSED | 2008-02-26 | PL:ON SITE SUPPORT FOR MENS SOCCER V UCSB 10/17 | 061 | CLOSED | 0 | 0 | 546 | 546
PJ0002750 Total | [7 empty] | 0 | 0 | 21401.8368 | 21401.8368
PJ0002749 | REPLACE CARPET THROUGHOUT - PETERSON RANCH 123 | GRIFFIN, PATRICK E | CLOSED | 2008-02-25 | AD: FLOOR CONNECTION | 123 | CLOSED | 3505 | 0 | 3505 | 3505
PJ0002749 | REPLACE CARPET THROUGHOUT - PETERSON RANCH 123 | GRIFFIN, PATRICK E | CLOSED | 2008-02-25 | CP: PROJECT CONTINGENCY | 123 | CLOSED | 0 | 0 | 0 | 0
PJ0002749 | REPLACE CARPET THROUGHOUT - PETERSON RANCH 123 | GRIFFIN, PATRICK E | CLOSED | 2008-02-25 | CU-VACUUM NEW CARPET AFTER INSTALLATION. | 123 | CLOSED | 27.33 | 0 | 54.66 | 54.66
PJ0002749 Total | [7 empty] | 3532.33 | 0 | 3559.66 | 3559.66
PJ0002745 | ROOM RENOVATION - COB 03 RM 300A | MOLLAN, CHERYL L. | CLOSED | 2008-02-14 | AD: FLOORTEC 2008200674 | 003 | CLOSED | 4429.3827 | 0 | 4429.372 | 4429.372
PJ0002745 | ROOM RENOVATION - COB 03 RM 300A | MOLLAN, CHERYL L. | CLOSED | 2008-02-14 | AD: JOC 07.014.049 STAPLES | 003 | CLOSED | 10352.4747 | 0 | 10352.4747 | 10352.4747
PJ0002745 | ROOM RENOVATION - COB 03 RM 300A | MOLLAN, CHERYL L. | CLOSED | 2008-02-14 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 1573.73 | 0 | 0 | 0
PJ0002745 | ROOM RENOVATION - COB 03 RM 300A | MOLLAN, CHERYL L. | CLOSED | 2008-02-14 | EL:CLEAN AND INSTALL NEW COVERS AS NECESSARY;NEW OUTLET | 003 | CLOSED | 317.22 | 0 | 1206.3698 | 1206.3698
PJ0002745 | ROOM RENOVATION - COB 03 RM 300A | MOLLAN, CHERYL L. | CLOSED | 2008-02-14 | IN: ROOM RENOVATION - COB 03 RM 300A (NO LABOR) | 003 | CLOSED | 66.276 | 0 | 0 | 0
PJ0002745 | ROOM RENOVATION - COB 03 RM 300A | MOLLAN, CHERYL L. | CLOSED | 2008-02-14 | PA:PAINT BACK AND SIDE WALLS | 003 | CLOSED | 571.92 | 0 | 654.468 | 654.468
PJ0002745 Total | [7 empty] | 17311.0034 | 0 | 16642.6845 | 16642.6845
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | CA:CONSTRUCT STORAGE ROOM AT 003 | 003 | CLOSED | 3857.748 | 0 | 2839.32 | 2839.32
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 885.98 | 0 | 0 | 0
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | EL:COMPLETE SERVICES FOR NEW ROOM AT 003-119 | 003 | CLOSED | 638.664 | 0 | 157.5854 | 157.5854
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | ES:COMPLETE CONSTRUCTION SERVICES FOR STORAGE RM AT 003 | 003 | CLOSED | 1328.256 | 0 | 192.096 | 192.096
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | IN: CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | 003 | CLOSED | 265.104 | 0 | 198.828 | 198.828
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | LO:INSTALL LOCK HARDWARE AT 003-119 | 003 | CLOSED | 1048.632 | 0 | 1411.2 | 1411.2
PJ0002743 | CONSTRUCT STORAGE AREA - COB 3 1ST FLOOR SILO, RM. 119 | GRIFFIN, PATRICK E | CLOSED | 2008-02-05 | PA:TAPE, PRIME, AND PAINT NEW STORAGE ROOM AT BUSINESS | 003 | CLOSED | 1721.376 | 0 | 2149.446 | 2149.446
PJ0002743 Total | [7 empty] | 9745.76 | 0 | 6948.4754 | 6948.4754
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | AD: JOC 07.014.036 STAPLES | 003 | CLOSED | 5470.3108 | 0 | 6918.7377 | 6918.7377
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | AD: PROCOATINGS | 003 | CLOSED | 371.29 | 0 | 371.29 | 371.29
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 983.56 | 0 | 0 | 0
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | CU:CUSTODIAL SUPPORT | 003 | CLOSED | 65.592 | 0 | 196.776 | 196.776
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | EL:INSTALL ELECTRICAL OUTLETS IN NEW WALL | 003 | CLOSED | 1726.3112 | 0 | 872.046 | 872.046
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | ES:RECONFIGURE DUCTWORK RM 453/ADD DUCT RM 454**ADDITIONAL WORK* | 003 | CLOSED | 1468.8941 | 0 | 2370.54 | 2370.54
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | IN: RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | 003 | CLOSED | 132.552 | 0 | 132.552 | 132.552
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | LO: INSTALL CONSTRUCTION CORES BLG 3-453 AND NEW CORE IN RM 453A | 003 | CLOSED | 114.336 | 0 | 186.336 | 186.336
PJ0002742 | RENOVATE 1 OFFICE INTO 2 OFFICES - COB 3 RM 453 | MOLLAN, CHERYL L. | CLOSED | 2008-02-05 | PA:PAINT NEW WALL | 003 | CLOSED | 857.88 | 0 | 777.096 | 777.096
PJ0002742 Total | [7 empty] | 11190.7261 | 0 | 11825.3737 | 11825.3737
PJ0002741 | MJ: INSTALL POJECTION/SOUND EQUIP -NEW EDES BLDG (TRACKING, ONLY | JUDD, PERRY | CLOSED | 2008-01-31 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002741 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002740 | CAME SECURITY ALARMS (ACCESS CTRL SYSTEM) - DEXTER 34 | PAHLOW, BOB | CLOSED | 2008-01-31 | ANTS-PROGRAMING OF UPD DISPATCH SECURITY ALARM REPORTING | 034 | CLOSED | 0 | 0 | 85.752 | 85.752
PJ0002740 | CAME SECURITY ALARMS (ACCESS CTRL SYSTEM) - DEXTER 34 | PAHLOW, BOB | CLOSED | 2008-01-31 | CA-DRILL HOLES FOR ALARM PANELS, 34-222 & 151 | 034 | CLOSED | 0 | 0 | 55.38 | 55.38
PJ0002740 | CAME SECURITY ALARMS (ACCESS CTRL SYSTEM) - DEXTER 34 | PAHLOW, BOB | CLOSED | 2008-01-31 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0002740 | CAME SECURITY ALARMS (ACCESS CTRL SYSTEM) - DEXTER 34 | PAHLOW, BOB | CLOSED | 2008-01-31 | IN: INSPECTION/PERMIT (NO LABOR) | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0002740 Total | [7 empty] | 0 | 0 | 141.132 | 141.132
PJ0002739 | RENOVATE CEILING - SCI N ANNEX 53A | POPHAM, DONALD J. | CLOSED | 2008-01-31 | AD: SANTA MARIA ACOUSTICAL | 053A | CLOSED | 3745 | 0 | 4016.5125 | 4016.5125
PJ0002739 | RENOVATE CEILING - SCI N ANNEX 53A | POPHAM, DONALD J. | CLOSED | 2008-01-31 | CP: PROJECT CONTINGENCY | 053A | CLOSED | 817.28 | 0 | 0 | 0
PJ0002739 | RENOVATE CEILING - SCI N ANNEX 53A | POPHAM, DONALD J. | CLOSED | 2008-01-31 | EL:INSTALL ELECTRICAL OUTLETS PER PLAN - 053A - 025 | 053A | CLOSED | 2466.6133 | 0 | 2436.996 | 2436.996
PJ0002739 | RENOVATE CEILING - SCI N ANNEX 53A | POPHAM, DONALD J. | CLOSED | 2008-01-31 | ES:INSTALL EXHAUST FAN UNDER EXISTING SKYLIGHT | 053A | CLOSED | 1961.0803 | 0 | 1321.1574 | 1321.1574
PJ0002739 | RENOVATE CEILING - SCI N ANNEX 53A | POPHAM, DONALD J. | CLOSED | 2008-01-31 | IN: RENOVATE CEILING - SCI N ANNEX 53A | 053A | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0002739 Total | [7 empty] | 8989.9736 | 0 | 7807.8039 | 7807.8039
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | AD: DIVISION OF STATE ARCHITECT | 026 | CLOSED | 0 | 0 | 200 | 200
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | AD: FLOORTEC | 026 | CLOSED | 0 | 0 | 1649.9186 | 1649.9186
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | AD: JOC 07.013.040 MAINO | 026 | CLOSED | 66150.8347 | 0 | 69339.5524 | 69339.5524
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | AD: WHITE'S DRYWALL | 026 | CLOSED | 0 | 0 | 256.8 | 256.8
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | CA: INSTALL FLOOR TILE IN ROOM 200A-D OFFICE REMODEL | 026 | CLOSED | 5574.0228 | 0 | 9705.951 | 9705.951
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | CA: REMOVE ENTRY DOOR INTO 26-202 | 026 | CLOSED | 0 | 0 | 490.4801 | 490.4801
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 8856.84 | 0 | 0 | 0
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | EL:ELECTRICAL FOR NEW OFFICES 26-200-202 | 026 | CLOSED | 8675.52 | 0 | 9776.5118 | 9776.5118
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | ES:HVAC FOR REMODEL IN 26 ROOM 200 | 026 | CLOSED | 3761.28 | 0 | 4582.512 | 4582.512
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | IN: BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | 026 | CLOSED | 198.828 | 0 | 66.276 | 66.276
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | LO:CORES FOR REMODEL IN 26 ROOM 200 | 026 | CLOSED | 757.344 | 0 | 870.888 | 870.888
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | PA:REMODEL PAINTING IN 26 ROOM 200 | 026 | CLOSED | 2887.68 | 0 | 4823.604 | 4823.604
PJ0002737 | BUILD ADDITIONAL OFFICE SPACE - GRAPHICS 26 RM 200-202 | MAY, TOM | CLOSED | 2008-01-30 | PL:OFFICE BUILD OUT FOR 26-200/202 | 026 | CLOSED | 0 | 0 | 1124.016 | 1124.016
PJ0002737 Total | [7 empty] | 96862.3495 | 0 | 102886.5099 | 102886.5099
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 11 PACIFIC 6:00PM | 160 | CLOSED | 0 | 0 | 106.2554 | 106.2554
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 12 PACIFIC 6:00PM | 160 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 13 PACIFIC 1:00PM | 160 | CLOSED | 0 | 0 | 113.0824 | 113.0824
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 15 FRESNO STATE 6:00PM | 160 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 16 LAYOLA MARYMOUNT 3:00PM | 160 | CLOSED | 0 | 0 | 117.8246 | 117.8246
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 25 UC SANTA BARBARA 6:00PM | 160 | CLOSED | 0 | 0 | 72.3692 | 72.3692
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 26 UC SANTA BARBARA 6:00PM | 160 | CLOSED | 0 | 0 | 72.3692 | 72.3692
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 27 UC SANTA BARBARA 1:00PM | 160 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 29 SOUTHERN CALIFORNIA 6:00PM | 160 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 30 CALIFORNIA 6:00PM | 160 | CLOSED | 0 | 0 | 105.8674 | 105.8674
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - APRIL 9 FRESNO STATE 6:00PM | 160 | CLOSED | 0 | 0 | 90.1922 | 90.1922
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - FEB 16 ALUMNI GAME 1:00PM | 160 | CLOSED | 0 | 0 | 65.8399 | 65.8399
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - FEB 23 ALABAMA (DH) 12:00PM | 160 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 1 FRESNO STATE 1:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 11 UC SANTA BARBARA 6:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 12 SANTA CLARA 6:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 13 UCLA 6:00PM | 160 | CLOSED | 0 | 0 | 158.7768 | 158.7768
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 14 UCLA 6:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 15 UCLA 1:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 2 MISSOURI 11:00AM | 160 | CLOSED | 0 | 0 | 156.7896 | 156.7896
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 22 SANTA CLARA (DH) 1:00PM | 160 | CLOSED | 0 | 0 | 158.7768 | 158.7768
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 28 UC IRVINE 6:00PM | 160 | CLOSED | 0 | 0 | 115.5408 | 115.5408
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 29 UC IRVINE 6:00PM | 160 | CLOSED | 0 | 0 | 87.9816 | 87.9816
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAR 30 UC IRVINE 1:00PM | 160 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 13 PEPPERDINE 6:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 16 LONG BEACH STATE 6:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 17 LONG BEACH STATE 6:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 18 LONG BEACH STATE 1:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 2 UNLV 6:00PM | 160 | CLOSED | 0 | 0 | 106.1706 | 106.1706
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 3 UNLV 6:00PM | 160 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002736 | 07/08 BASEBALL-CUSTODIAL SERVICES FOR ATHLETICS-BAGGET STAD. 160 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 BASEBALL - MAY 4 UNLV 1:00PM | 160 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002736 Total | [7 empty] | 0 | 0 | 2775.6614 | 2775.6614
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 07/08 SOFTBALL - FEB 08 TEXAS A&M 3:30PM | 161 | CLOSED | 0 | 0 | 115.4352 | 115.4352
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - APRIL 19 CAL STATE NORTHRIDGE GAME #1 12:00PM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - APRIL 19 CAL STATE NORTHRIDGE GAME #2 2:30PM | 161 | CLOSED | 0 | 0 | 82.7832 | 82.7832
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - APRIL 20 CAL STATE NORTHRIDGE 12:00PM | 161 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 08 SAN DIEGO STATE 6:00PM | 161 | CLOSED | 0 | 0 | 106.2554 | 106.2554
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 09 OREGON 10:00AM | 161 | CLOSED | 0 | 0 | 94.6091 | 94.6091
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 09 TENNESSEE 6:00PM | 161 | CLOSED | 0 | 0 | 102.8328 | 102.8328
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 10 NEW MEXICO STATE 12:000PM | 161 | CLOSED | 0 | 0 | 115.8186 | 115.8186
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 15 ILLINOIS 3:45PM | 161 | CLOSED | 0 | 0 | 84.9611 | 84.9611
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 15 SOUTH CAROLINA 1:30PM | 161 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 16 MISSOURI 5:30PM | 161 | CLOSED | 0 | 0 | 106.1706 | 106.1706
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 17 OKLAHOMA 11:15AM | 161 | CLOSED | 0 | 0 | 106.2554 | 106.2554
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 17 WISCONSIN 9:00AM | 161 | CLOSED | 0 | 0 | 115.4832 | 115.4832
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 22 CALIFORNIA 4:30PM | 161 | CLOSED | 0 | 0 | 85.7928 | 85.7928
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 22 SANTA CLARA 7:00PM | 161 | CLOSED | 0 | 0 | 90.7384 | 90.7384
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 23 ALABAMA-BIRMINGHAM 7:00PM | 161 | CLOSED | 0 | 0 | 117.4915 | 117.4915
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 23 SACRAMENTO STATE 4:30PM | 161 | CLOSED | 0 | 0 | 104.2464 | 104.2464
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - FEB 24 CALIFORNIA 11:00AM | 161 | CLOSED | 0 | 0 | 78.2112 | 78.2112
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 14 NORTH COLORADO 12:30PM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 14 OKLAHOMA 10:00AM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 15 PRINCETON 3:00PM | 161 | CLOSED | 0 | 0 | 137.1937 | 137.1937
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 15 VEVADA 10:00AM | 161 | CLOSED | 0 | 0 | 116.211 | 116.211
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 16 COLORADO STATE 11:00AM | 161 | CLOSED | 0 | 0 | 115.1952 | 115.1952
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 29 CAL STATE FULLERTON GAME #1 12:00PM | 161 | CLOSED | 0 | 0 | 73.4594 | 73.4594
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 29 CAL STATE FULLERTON GAME #2 2:30PM | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 3 NORTH DAKOTA GAME #1 3:00PM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 3 NORTH DAKOTA GAME #2 5:00PM | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 30 CAL STATE FULLERTON 12:00PM | 161 | CLOSED | 0 | 0 | 84.9611 | 84.9611
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 8 HOUSTON 1:00PM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 8 RHODE ISLAND 7:00PM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 9 DEPAUL 11:00AM | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MARCH 9 SANTA CLARA 1:009M | 161 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MAY 10 UC RIVERSIDE 12:00PM | 161 | CLOSED | 0 | 0 | 116.211 | 116.211
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MAY 3 UC DAVIS GAME #2 6:30PM | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MAY 3 UC DAVIS GAME #1 4:00 PM | 161 | CLOSED | 0 | 0 | 86.0758 | 86.0758
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MAY 4 UC DAVIS 12:00PM | 161 | CLOSED | 0 | 0 | 101.2741 | 101.2741
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MAY 9 UC RIVERSIDE GAME #1 4:00PM | 161 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002735 | 07/08 SOFTBALL-CUSTODIALSERVICES FOR ATHLETICS-JANSSEN FIELD 161 | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-30 | CU: 08 SOFTBALL - MAY 9 UC RIVERSIDE GAME #2 6:30PM | 161 | CLOSED | 0 | 0 | 93.1848 | 93.1848
PJ0002735 Total | [7 empty] | 0 | 0 | 3273.1406 | 3273.1406
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | AD: JOC 07.013.043 MAINO | GENERAL | CLOSED | 49239.4954 | 0 | 49328.3375 | 49328.3375
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | CA: INSTALL MONUMENTS | GENERAL | CLOSED | 1449.12 | 0 | 3500.9587 | 3500.9587
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 5589.77 | 0 | 0 | 0
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | EL:ELECTRICAL FOR RED HAND PRINT MONUMENT | GENERAL | CLOSED | 747.552 | 0 | 1247.634 | 1247.634
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | EO:CLEAN OUT PLANTING BED | GENERAL | CLOSED | 741.504 | 0 | 880.536 | 880.536
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | IN: SP 07/08 FABRICATE/INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | GENERAL | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0002730 | SP 07/08: FABRICATE & INSTALL RED HAND MONUMENTS - CAMPUS-WIDE | MAY, TOM | CLOSED | 2008-01-24 | LA:RELANDSCAPE RED HAND PRINT PLANTER | GENERAL | CLOSED | 3720 | 0 | 4231.7804 | 4231.7804
PJ0002730 Total | [7 empty] | 61487.4414 | 0 | 59255.5226 | 59255.5226
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | CA: MAKE REPAIRS TO PREVENT WATER INTRUSION INTO 02-24 | 002 | CLOSED | 2096 | 0 | 4737.5972 | 4737.5972
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | CU: VAC UP WATER AT 02-24 FROM RAIN LEAK | 002 | CLOSED | 874.56 | 0 | 27.33 | 27.33
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | MO: MOVE FURNITURE OUT AND IN IN 02-024 (MAINT) | 002 | CLOSED | 39.375 | 0 | 33.145 | 33.145
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | PA: PREP AND PAINT DOWN SPOUTS AT EDUCATION | 002 | CLOSED | 1986.4 | 0 | 184.16 | 184.16
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | PA: TAPE, MUD, PRIME, AND PAINT REPAIRS TO WALLS IN 02-24 | 002 | CLOSED | 1575.12 | 0 | 711.41 | 711.41
PJ0002729 | REPAIR MAJOR LEAK - EDUC 02 RM 24 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-23 | PL: MAKE REPAIRS TO DOWNSPOUTS AT EDUCATION 02-24 | 002 | CLOSED | 4488.4 | 0 | 1625.22 | 1625.22
PJ0002729 Total | [7 empty] | 11059.855 | 0 | 7318.8622 | 7318.8622
PJ0002728 | INSTALL NEW WASHING STATION SINK- FACS PAINT SHOP 70 | RIVERA, MARIO L | CLOSED | 2008-01-22 | CA: BUILD WALL | 070 | CLOSED | 1846 | 0 | 1049.39 | 1049.39
PJ0002728 | INSTALL NEW WASHING STATION SINK- FACS PAINT SHOP 70 | RIVERA, MARIO L | CLOSED | 2008-01-22 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0002728 | INSTALL NEW WASHING STATION SINK- FACS PAINT SHOP 70 | RIVERA, MARIO L | CLOSED | 2008-01-22 | EO: ASSIST PLUMBERS TO INSTALL SINK AND INTERCEPTOR FOR DRAINS | 070 | CLOSED | 0 | 0 | 308.96 | 308.96
PJ0002728 | INSTALL NEW WASHING STATION SINK- FACS PAINT SHOP 70 | RIVERA, MARIO L | CLOSED | 2008-01-22 | IN: INSTALL NEW WASHING STATION SINK- FACS PAINT SHOP 70 (N/L) | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0002728 | INSTALL NEW WASHING STATION SINK- FACS PAINT SHOP 70 | RIVERA, MARIO L | CLOSED | 2008-01-22 | PL: INSTALL SINK AND INTERCEPTOR FOR DRAINS | 070 | CLOSED | 0 | 0 | 6205.45 | 6205.45
PJ0002728 Total | [7 empty] | 1846 | 0 | 7563.8 | 7563.8
PJ0002725 | REPLACE FRONT ENTRY DOOR - CHORRO CREEK RANCH 126 | GRIFFIN, PATRICK E | CLOSED | 2008-01-16 | CA: INSTALL NEW FRONT DOOR AT CHORRO CREEK RANCH | 126 | CLOSED | 1136.28 | 0 | 1767.906 | 1767.906
PJ0002725 | REPLACE FRONT ENTRY DOOR - CHORRO CREEK RANCH 126 | GRIFFIN, PATRICK E | CLOSED | 2008-01-16 | CP: PROJECT CONTINGENCY | 126 | CLOSED | 210.69 | 0 | 0 | 0
PJ0002725 | REPLACE FRONT ENTRY DOOR - CHORRO CREEK RANCH 126 | GRIFFIN, PATRICK E | CLOSED | 2008-01-16 | LO: INSTALL NEW MORTISE LOCK AT CHORRO CREEK RANCH | 126 | CLOSED | 579.504 | 0 | 114.336 | 114.336
PJ0002725 | REPLACE FRONT ENTRY DOOR - CHORRO CREEK RANCH 126 | GRIFFIN, PATRICK E | CLOSED | 2008-01-16 | PA: PREP, PRIME, AND PAINT NEW DOOR AT CHORRO CREEK RANCH | 126 | CLOSED | 391.152 | 0 | 614.7 | 614.7
PJ0002725 Total | [7 empty] | 2317.626 | 0 | 2496.942 | 2496.942
PJ0002722 | REPAIR REMOTE DOOR RELEASE - ADMIN 01 RM 130/131E (CASHIERS OFF) | GRIFFIN, PATRICK E | CLOSED | 2008-01-11 | AD: R.F. MCDONALD COMPANY | 001 | CLOSED | 535 | 0 | 0 | 0
PJ0002722 | REPAIR REMOTE DOOR RELEASE - ADMIN 01 RM 130/131E (CASHIERS OFF) | GRIFFIN, PATRICK E | CLOSED | 2008-01-11 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 102.34 | 0 | 0 | 0
PJ0002722 | REPAIR REMOTE DOOR RELEASE - ADMIN 01 RM 130/131E (CASHIERS OFF) | GRIFFIN, PATRICK E | CLOSED | 2008-01-11 | EL: WIRE ELECTRIC STRIKE AT ADMIN CASHIERS OFFICE | 001 | CLOSED | 229.8486 | 0 | 390.9 | 390.9
PJ0002722 | REPAIR REMOTE DOOR RELEASE - ADMIN 01 RM 130/131E (CASHIERS OFF) | GRIFFIN, PATRICK E | CLOSED | 2008-01-11 | LS: INSTALL ELECTRONIC STRIKE AT ADMIN CASHIERS OFFICE | 001 | CLOSED | 57.168 | 0 | 177.78 | 177.78
PJ0002722 | REPAIR REMOTE DOOR RELEASE - ADMIN 01 RM 130/131E (CASHIERS OFF) | GRIFFIN, PATRICK E | CLOSED | 2008-01-11 | PA: PREP AND PAINT JAMB AT ADMIN CASHIERS OFFICE | 001 | CLOSED | 201.576 | 0 | 57.192 | 57.192
PJ0002722 Total | [7 empty] | 1125.9326 | 0 | 625.872 | 625.872
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: BKM | 058 | CLOSED | 0 | 0 | 4712.62 | 4712.62
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: CAME SECURITY | 058 | CLOSED | 0 | 0 | 4450 | 4450
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: DEPARTMENT OF GENERAL SERVICES FEES | 058 | CLOSED | 0 | 0 | 54.58 | 54.58
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: FLOOR TEC | 058 | CLOSED | 2000 | 0 | 3400.62 | 3400.62
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: GOSS ENGINEERING | 058 | CLOSED | 9500 | 0 | 9500 | 9500
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: JOC 07.015.012 MAINO | 058 | CLOSED | 75469.8 | 0 | 144621.99 | 144621.99
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: MECA | 058 | CLOSED | 5884 | 0 | 5884 | 5884
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | AD: PURCHASE FROM GRAINGER | 058 | CLOSED | 0 | 0 | 43.56 | 43.56
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | ANTS: PROGRAM SECURITY AND FIRE ALARMS AT BLG 58 | 058 | CLOSED | 142.92 | 0 | 202.47 | 202.47
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | CA: SUPPORT KEY SHOP MOVE | 058 | CLOSED | 4153.5 | 0 | 2594.5206 | 2594.5206
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | CP: PROJECT CONTINGENCY | 058 | CLOSED | 21778.97 | 0 | 0 | 0
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | CU: CLEAN CARPET AND TILE FLOOR | 058 | CLOSED | 0 | 0 | 688.08 | 688.08
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | EL - INSTALL NEW ELECTRICAL FOR KEY AND LOCK SHOP | 058 | CLOSED | 27975.8 | 0 | 31942.0438 | 31942.0438
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | IN: SP 07/08 CONST LOCK&KEY SHOP-BLDG 58 RM 101C/102B-D/103-103E | 058 | CLOSED | 441.84 | 0 | 276.15 | 276.15
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | LO: INSTALL CORES FOR KEY SHOP MOVE | 058 | CLOSED | 476.4 | 0 | 47.64 | 47.64
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | MO: MOVING SERVICES FOR NEW LOCK AND KEY SHOP | 058 | CLOSED | 0 | 0 | 553.048 | 553.048
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | PA: PAINT ALL WALLS AND DOORS | 058 | CLOSED | 5384.72 | 0 | 3513.68 | 3513.68
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | PL - NEW LOCK AND KEY SHOP | 058 | CLOSED | 5298 | 0 | 3159.856 | 3159.856
PJ0002721 | SP 08/09, SR 08/09: NEW LOCK & KEY SHOP-BLDG 58 RM 101C/102B-D | LAMPMAN, GREG | CLOSED | 2008-01-11 | PL- INSTALL AIR FITTINGS | 058 | CLOSED | 0 | 0 | 360.04 | 360.04
PJ0002721 Total | [7 empty] | 158505.95 | 0 | 216004.8984 | 216004.8984
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | AD: SANTA MARIA ACOUSTICAL | 021 | CLOSED | 0 | 0 | 749 | 749
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | AD: WHITE'S DRYWALL | 021 | CLOSED | 2354 | 0 | 2773.44 | 2773.44
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | CA:FRAME WALLS IN 21-128 | 021 | CLOSED | 5540.8344 | 0 | 5507.034 | 5507.034
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 1330.87 | 0 | 0 | 0
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | EL:INSTALL SWITCHES AND OUTLETS IN 21-128 | 021 | CLOSED | 1107.552 | 0 | 1180.854 | 1180.854
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | IN: WALL REMODEL - ENGR W. 21 RM 128 | 021 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | LO:INSTALL LOCKSETS IN NEW DOORS IN 21-128 | 021 | CLOSED | 828.672 | 0 | 884.64 | 884.64
PJ0002718 | WALL REMODEL - ENGR W. 21 RM 128 | MAY, TOM | CLOSED | 2008-01-08 | PA:PAINT NEW WALLS IN 21-128 | 021 | CLOSED | 2407.68 | 0 | 2591.658 | 2591.658
PJ0002718 Total | [7 empty] | 13569.6084 | 0 | 13752.902 | 13752.902
PJ0002717 | REPAIR PANIC HDW ON DBL DOORS - BLDG 034 BACK DOCK (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-07 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 0 | 0 | 0 | 0
PJ0002717 | REPAIR PANIC HDW ON DBL DOORS - BLDG 034 BACK DOCK (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2008-01-07 | LO: REPAIR PANIC HARDWARE ON DOUBLE DOOR (LABOR FRM WO0121403) | 034 | CLOSED | 0 | 0 | 428.76 | 428.76
PJ0002717 Total | [7 empty] | 0 | 0 | 428.76 | 428.76
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 01/11 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/01 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/02 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/03 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/07 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/08 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/09 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/28 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 02/29 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/01 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 32.796 | 32.796
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/06 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/07 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/08 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/15 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 6:00PM | 044 | CLOSED | 0 | 0 | 115.1952 | 115.1952
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/21 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/22 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/22 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 4:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 | 07/08 EXTRA CLEANING - SPANOS THEATRE - WINTER QTR 2008 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2008-01-04 | CU: 03/23 CLEAN THEATRE, RESTROOMS, TIX CNTR & WINDOW BY 12:00PM | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002715 Total | [7 empty] | 0 | 0 | 1197.4632 | 1197.4632
PJ0002714 | MJ: IN-HOUSE COSTS - EXTERIOR PAINT/WINDOWS - FARM OPS BLDG 9 | LAMPMAN, GREG | CLOSED | 2007-12-28 | CA: INSTALL BUILDING SIGN | 009 | CLOSED | 221.52 | 0 | 496.788 | 496.788
PJ0002714 | MJ: IN-HOUSE COSTS - EXTERIOR PAINT/WINDOWS - FARM OPS BLDG 9 | LAMPMAN, GREG | CLOSED | 2007-12-28 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0002714 | MJ: IN-HOUSE COSTS - EXTERIOR PAINT/WINDOWS - FARM OPS BLDG 9 | LAMPMAN, GREG | CLOSED | 2007-12-28 | EL: REMOVE CONDUIT ON OUTSIDE OF BLDG. | 009 | CLOSED | 0 | 0 | 95.166 | 95.166
PJ0002714 | MJ: IN-HOUSE COSTS - EXTERIOR PAINT/WINDOWS - FARM OPS BLDG 9 | LAMPMAN, GREG | CLOSED | 2007-12-28 | IN: RENOVATE EXTERIOR PAINT & WINDOWS -FARM OPS BLDG 9 (N/L) | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0002714 | MJ: IN-HOUSE COSTS - EXTERIOR PAINT/WINDOWS - FARM OPS BLDG 9 | LAMPMAN, GREG | CLOSED | 2007-12-28 | LA: INSTALL SPRINKLER SYS. | 009 | CLOSED | 7200 | 0 | 3866.8944 | 3866.8944
PJ0002714 Total | [7 empty] | 7421.52 | 0 | 4458.8484 | 4458.8484
PJ0002712 | REMOVE AND REPLACE FLOOR TILE - GRAPHICS ART 26 RM 204 (MAINT) | MAY, TOM | CLOSED | 2007-12-19 | AD: JOC 07.013.039 MAINO | 026 | CLOSED | 0 | 0 | 2431.2 | 2431.2
PJ0002712 | REMOVE AND REPLACE FLOOR TILE - GRAPHICS ART 26 RM 204 (MAINT) | MAY, TOM | CLOSED | 2007-12-19 | CA: INSTALL NEW FLOOR TILE IN 26-204 | 026 | CLOSED | 0 | 0 | 2283.995 | 2283.995
PJ0002712 | REMOVE AND REPLACE FLOOR TILE - GRAPHICS ART 26 RM 204 (MAINT) | MAY, TOM | CLOSED | 2007-12-19 | CP: PROJECT CONTINGENCY (NO CONTINGENCY - MAINT) | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0002712 Total | [7 empty] | 0 | 0 | 4715.195 | 4715.195
PJ0002711 | INSTALL/CREATE DOOR IN EXISTING WALL - BLDG 124 | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | CA: CUT IN NEW OPENING IN WALL AT STUDENT SERVICES | 124 | CLOSED | 1136.223 | 0 | 979.17 | 979.17
PJ0002711 | INSTALL/CREATE DOOR IN EXISTING WALL - BLDG 124 | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 278.68 | 0 | 0 | 0
PJ0002711 | INSTALL/CREATE DOOR IN EXISTING WALL - BLDG 124 | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | PA:PATCH AND PAINT NEW OPENING IN WALL AT STUDENT SERVICES | 124 | CLOSED | 1239.84 | 0 | 1903.14 | 1903.14
PJ0002711 Total | [7 empty] | 2654.743 | 0 | 2882.31 | 2882.31
PJ0002710 | REPAIR WALKWAY OUTSIDE OF VERANDA - S. PERMETER (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | AD: WOODY PUMP | GENERAL | CLOSED | 0 | 0 | 185 | 185
PJ0002710 | REPAIR WALKWAY OUTSIDE OF VERANDA - S. PERMETER (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | CA: REPLACE CONCRETE AT VERANDA CAFE BLDG 19 | GENERAL | CLOSED | 4061.2 | 0 | 8058.8992 | 8058.8992
PJ0002710 | REPAIR WALKWAY OUTSIDE OF VERANDA - S. PERMETER (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0.01 | 0 | 0 | 0
PJ0002710 | REPAIR WALKWAY OUTSIDE OF VERANDA - S. PERMETER (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | EO: REMOVE DAMAGED CONCRETE AT VERANDA CAFE BLDG 19 (NO LABOR) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002710 | REPAIR WALKWAY OUTSIDE OF VERANDA - S. PERMETER (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-12-14 | LA: MODIFY IRRIGATION FOR VERANDA CAFE ENTRY WALK | GENERAL | CLOSED | 0 | 0 | 1209.7504 | 1209.7504
PJ0002710 Total | [7 empty] | 4061.21 | 0 | 9453.6496 | 9453.6496
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: ASAP REPROGRAPHICS | 014 | CLOSED | 0 | 0 | 214.428 | 214.428
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: ATASCADERO GLASS | 014 | CLOSED | 0 | 0 | 1080.7 | 1080.7
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: CARLISLE INTERCONNECT TECHNOLOGIES | 014 | CLOSED | 0 | 0 | 15365.8955 | 15365.8955
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: FLOORTEC | 014 | CLOSED | 11843.6481 | 0 | 10552.8964 | 10552.8964
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: JOC 07.013.028 MAINO | 014 | CLOSED | 317109.3623 | 0 | 323690.9216 | 323690.9216
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: MECA | 014 | CLOSED | 0 | 0 | 7599.675 | 7599.675
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: SYSTEK GRAPHIC ARTS | 014 | CLOSED | 0 | 0 | 666.1285 | 666.1285
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | AD: THOMA ELECTRIC | 014 | CLOSED | 0 | 0 | 2571.21 | 2571.21
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | CA: INSTALL ROOM NUMBERS AND BLINDS IN BLG. 14 ROOMS 235 - 238 | 014 | CLOSED | 0 | 0 | 4089.81 | 4089.81
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 35864.45 | 0 | 0 | 0
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | ES:REMODEL HVAC IN 14-235/238 | 014 | CLOSED | 22277.136 | 0 | 17765.646 | 17765.646
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | IN: CONSTRUCTION PROJECT - FRANK E PILLING 14 RM 235-238 | 014 | CLOSED | 662.76 | 0 | 364.518 | 364.518
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | LO:ASSIST WITH REMODEL IN 14-235/238 | 014 | CLOSED | 468.672 | 0 | 428.76 | 428.76
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | PA:PAINT 14-235/238 | 014 | CLOSED | 5775.36 | 0 | 8410.86 | 8410.86
PJ0002709 | ROOM RENOVATIONS - FRANK E PILLING 14 RM 235-238 | MAY, TOM | CLOSED | 2007-12-14 | PL:REMODEL IN 14-235/238 | 014 | CLOSED | 0 | 0 | 858.276 | 858.276
PJ0002709 Total | [7 empty] | 394001.3884 | 0 | 393659.725 | 393659.725
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | AD: FLOOR CONNECTION | 035 | CLOSED | 0 | 0 | 4309.96 | 4309.96
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | AD: RUSSCO | 035 | CLOSED | 0 | 0 | 395.9214 | 395.9214
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | CA: ASSIST IN KIOSK INSTALLATION PREP | 035 | CLOSED | 0 | 0 | 1233.144 | 1233.144
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 2547.83 | 0 | 0 | 0
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | EL:PROVIDE ELECTRICAL POWER/HOOKUP TO COFFEE KIOSK | 035 | CLOSED | 10081.6214 | 0 | 6395.9885 | 6395.9885
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | IN: WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | 035 | CLOSED | 0 | 0 | 165.69 | 165.69
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | LO:LOCKSET FOR KIOSK STORAGE IN 35 | 035 | CLOSED | 0 | 0 | 450.336 | 450.336
PJ0002708 | INSTALL WATER AND POWER FOR COFFEE KIOSK - KENN LIB 35 RM 216 | MAY, TOM | CLOSED | 2007-12-13 | PL:PROVIDE SEWER AND WATER TO COFFEE KIOSK | 035 | CLOSED | 15396.6842 | 0 | 16771.2341 | 16771.2341
PJ0002708 Total | [7 empty] | 28026.1357 | 0 | 29722.274 | 29722.274
PJ0002706 | INSTALL CELLULAR ANTENNA SYSTEM (ESTIMATE) - ADMIN 01 ROOF | BISCHEL, JOSEPH W | CLOSED | 2007-12-13 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 42.72 | 0 | 0 | 0
PJ0002706 | INSTALL CELLULAR ANTENNA SYSTEM (ESTIMATE) - ADMIN 01 ROOF | BISCHEL, JOSEPH W | CLOSED | 2007-12-13 | ES: FABRICATE ANTENNA MOUNT | 001 | CLOSED | 427.5437 | 0 | 220.32 | 220.32
PJ0002706 Total | [7 empty] | 470.2637 | 0 | 220.32 | 220.32
PJ0002705 | SR 07/08 NEW HYDRAULIC JACK UNIT-E.W 21 ELEVATOR(ENC BY 6/30/08) | PAHLOW, BOB | CLOSED | 2007-12-13 | AD: REPUBLIC ELEVATOR | 021 | CLOSED | 43125 | 0 | 43125 | 43125
PJ0002705 | SR 07/08 NEW HYDRAULIC JACK UNIT-E.W 21 ELEVATOR(ENC BY 6/30/08) | PAHLOW, BOB | CLOSED | 2007-12-13 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 4312.5 | 0 | 0 | 0
PJ0002705 Total | [7 empty] | 47437.5 | 0 | 43125 | 43125
PJ0002703 | REPAIR WATER DAMAGES FROM WATER HEATER - AG ENGR SHOP BLDG 8A | GRIFFIN, PATRICK E | CLOSED | 2007-12-10 | AD-PO FOR SMITH AND SONS CLEAN-UP | 008A | CLOSED | 19492.4575 | 0 | 19492.4575 | 19492.4575
PJ0002703 | REPAIR WATER DAMAGES FROM WATER HEATER - AG ENGR SHOP BLDG 8A | GRIFFIN, PATRICK E | CLOSED | 2007-12-10 | AD: CHANGE ORDER FOR SMITH AND SONS | 008A | CLOSED | 16610.48 | 0 | 16610.48 | 16610.48
PJ0002703 | REPAIR WATER DAMAGES FROM WATER HEATER - AG ENGR SHOP BLDG 8A | GRIFFIN, PATRICK E | CLOSED | 2007-12-10 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 3838.9 | 0 | 0 | 0
PJ0002703 | REPAIR WATER DAMAGES FROM WATER HEATER - AG ENGR SHOP BLDG 8A | GRIFFIN, PATRICK E | CLOSED | 2007-12-10 | CU: CLEAN UP FROM FLOODING 8A SHOP 2 | 008A | CLOSED | 584.736 | 0 | 1128.6 | 1128.6
PJ0002703 | REPAIR WATER DAMAGES FROM WATER HEATER - AG ENGR SHOP BLDG 8A | GRIFFIN, PATRICK E | CLOSED | 2007-12-10 | PL-SUPPORT SERVICES FOR FLOOD AT 08-A | 008A | CLOSED | 538.608 | 0 | 116.556 | 116.556
PJ0002703 Total | [7 empty] | 41065.1815 | 0 | 37348.0935 | 37348.0935
PJ0002702 | ESTIMATE TO ADD 6 NEW CIRCUITS - FRANK E PILLING 14 RM 104 | VELARDE, DENIS L | CLOSED | 2007-12-07 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 103.15 | 0 | 0 | 0
PJ0002702 | ESTIMATE TO ADD 6 NEW CIRCUITS - FRANK E PILLING 14 RM 104 | VELARDE, DENIS L | CLOSED | 2007-12-07 | EL:ADD SIX CIRCUITS PER RIC UC | 014 | CLOSED | 1031.496 | 0 | 848.472 | 848.472
PJ0002702 Total | [7 empty] | 1134.646 | 0 | 848.472 | 848.472
PJ0002701 | SECURITY ALARM INSTALLATION FOR ANTS OFFICES - MFG 36 (NO EST.) | PAHLOW, BOB | CLOSED | 2007-12-07 | ANTS: PROGRAM PANIC ALARMS AT DISPATCH | 036 | CLOSED | 0 | 0 | 343.008 | 343.008
PJ0002701 | SECURITY ALARM INSTALLATION FOR ANTS OFFICES - MFG 36 (NO EST.) | PAHLOW, BOB | CLOSED | 2007-12-07 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 0 | 0 | 0 | 0
PJ0002701 | SECURITY ALARM INSTALLATION FOR ANTS OFFICES - MFG 36 (NO EST.) | PAHLOW, BOB | CLOSED | 2007-12-07 | IN: INSPECTION / PERMIT - CAME SECURITY INTRUSION ALARMS (N/L) | 036 | CLOSED | 0 | 0 | 0 | 0
PJ0002701 Total | [7 empty] | 0 | 0 | 343.008 | 343.008
PJ0002699 | COUNTER TOP & SINK REMOVAL - CAED 05 RM 101 | POPHAM, DONALD J. | CLOSED | 2007-12-06 | CA:REMOVE EXISTING COUNTER TOP AND SUPPORT 005-101 | 005 | CLOSED | 4065.4458 | 0 | 2381.5362 | 2381.5362
PJ0002699 | COUNTER TOP & SINK REMOVAL - CAED 05 RM 101 | POPHAM, DONALD J. | CLOSED | 2007-12-06 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 427.12 | 0 | 0 | 0
PJ0002699 | COUNTER TOP & SINK REMOVAL - CAED 05 RM 101 | POPHAM, DONALD J. | CLOSED | 2007-12-06 | PL: REMOVAL OF SINK AT 005 - 101 | 005 | CLOSED | 205.589 | 0 | 273 | 273
PJ0002699 Total | [7 empty] | 4698.1548 | 0 | 2654.5362 | 2654.5362
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | AD: FLOORTEC | 010 | CLOSED | 2248.4124 | 0 | 2281.8606 | 2281.8606
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | CA: REMODEL AT AG ERHART 10-121 & 121A ***ADDITIONAL WORK*** | 010 | CLOSED | 7594.9386 | 0 | 4328.823 | 4328.823
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 2306.67 | 0 | 0 | 0
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | EL: RELOCATE POWER FOR OFFICE REMODEL AT AG ERHART RMS 121/121A | 010 | CLOSED | 4538.5134 | 0 | 826.7942 | 826.7942
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | IN: OFFICE REMODEL AT AG ERHART ROOMS 121 AND 121A | 010 | CLOSED | 198.828 | 0 | 149.121 | 149.121
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | KS: SUPPLY AND INSTALL CORE IN DOOR AT 010-121A | 010 | CLOSED | 85.752 | 0 | 93.168 | 93.168
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | LO:INSTALL AND REPLACE DOOR HARWARE WITH ADA | 010 | CLOSED | 1210.9147 | 0 | 485.928 | 485.928
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | PA:PAINT OFFICES IN AG ERHART ROOMS 121 AND 121A | 010 | CLOSED | 4535.9534 | 0 | 3060.576 | 3060.576
PJ0002697 | REMODEL TWO ROOMS - ERHART 10 RMS 121 & 121A | POPHAM, DONALD J. | CLOSED | 2007-12-04 | PL: DISCONNECT SINK IN ROOM 121 | 010 | CLOSED | 145.589 | 0 | 752.184 | 752.184
PJ0002697 Total | [7 empty] | 22865.5716 | 0 | 11978.4548 | 11978.4548
PJ0002696 | M&R PAC 08/09: REPLACE SEATING - PAC 6 | GRIFFIN, PATRICK E | CLOSED | 2007-12-04 | AD: JOC 07.014.024 STAPLES | 006 | CLOSED | 115324.8568 | 0 | 115321.39 | 115321.39
PJ0002696 | M&R PAC 08/09: REPLACE SEATING - PAC 6 | GRIFFIN, PATRICK E | CLOSED | 2007-12-04 | AD: RRM DESIGN GROUP SUPPORT | 006 | CLOSED | 2140 | 0 | 1298.7125 | 1298.7125
PJ0002696 | M&R PAC 08/09: REPLACE SEATING - PAC 6 | GRIFFIN, PATRICK E | CLOSED | 2007-12-04 | CA: ASSEMBLE SHELVES AND ORGANIZE SEAT PARTS | 006 | CLOSED | 886.08 | 0 | 1920.75 | 1920.75
PJ0002696 | M&R PAC 08/09: REPLACE SEATING - PAC 6 | GRIFFIN, PATRICK E | CLOSED | 2007-12-04 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 11790.79 | 0 | 0 | 0
PJ0002696 Total | [7 empty] | 130141.7268 | 0 | 118540.8525 | 118540.8525
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 01/03 WRESTLING - UNIV OF WEST VIRGINIA 1:00PM | GENERAL | CLOSED | 0 | 0 | 162.054 | 162.054
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 01/04 WRESTLING - UNIV OF OREGON 7:00PM | GENERAL | CLOSED | 0 | 0 | 303.1798 | 303.1798
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 01/11 WRESTLING - ARIZONA STATE 7:00PM | GENERAL | CLOSED | 0 | 0 | 293.8532 | 293.8532
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 01/13 WRESTLING - BOISE STATE UNIV 2:00PM | GENERAL | CLOSED | 0 | 0 | 194.3885 | 194.3885
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 01/25 WRESTLING - U.C. DAVIS 7:00PM | GENERAL | CLOSED | 0 | 0 | 364.5664 | 364.5664
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 02/08 WRESTLING - STANFORD UNIV 7:00PM | GENERAL | CLOSED | 0 | 0 | 736.2 | 736.2
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 11/07 WRESTLING - GREEN & GOLD 7:00PM | GENERAL | CLOSED | 0 | 0 | 126.267 | 126.267
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 12/08 WRESTLING - UNIV OF MINNESOTA 6:00PM | GENERAL | CLOSED | 0 | 0 | 753.951 | 753.951
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 12/14 WRESTLING - OREGON STATE 6:00PM | GENERAL | CLOSED | 0 | 0 | 139.4192 | 139.4192
PJ0002695 | 07/08 WRESTLING (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-30 | CU: 12/14 WRESTLING - SAN FRANCISCO STATE 4:30PM | GENERAL | CLOSED | 0 | 0 | 202.2504 | 202.2504
PJ0002695 Total | [7 empty] | 0 | 0 | 3276.1296 | 3276.1296
PJ0002694 | PROJECT FOR HOLIDAY EVENT - UNIVERSITY HOUSE AREA 51 | MAY, TOM | CLOSED | 2007-11-29 | CA:INSTALL TENT SIDES FOR EVENT | 051 | CLOSED | 0 | 0 | 603.17 | 603.17
PJ0002694 | PROJECT FOR HOLIDAY EVENT - UNIVERSITY HOUSE AREA 51 | MAY, TOM | CLOSED | 2007-11-29 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0002694 | PROJECT FOR HOLIDAY EVENT - UNIVERSITY HOUSE AREA 51 | MAY, TOM | CLOSED | 2007-11-29 | EL:HOLIDAY EVENT SUPPORT 51 | 051 | CLOSED | 0 | 0 | 281.5278 | 281.5278
PJ0002694 Total | [7 empty] | 0 | 0 | 884.6978 | 884.6978
PJ0002693 | INSTALL HVAC SYSTEM - ANC 154 OPERATOR'S/MICRO ING/ CTRL RM | MAY, TOM | CLOSED | 2007-11-29 | CA: FRAME IN AND SHEETROCK ALCOVE AT ANC | 154 | CLOSED | 886.08 | 0 | 1006.056 | 1006.056
PJ0002693 | INSTALL HVAC SYSTEM - ANC 154 OPERATOR'S/MICRO ING/ CTRL RM | MAY, TOM | CLOSED | 2007-11-29 | CA:FORM AND POUR A CONCRETE SLAB AT THE ANC - ADDITIONAL WORK | 154 | CLOSED | 683.04 | 0 | 2144.4404 | 2144.4404
PJ0002693 | INSTALL HVAC SYSTEM - ANC 154 OPERATOR'S/MICRO ING/ CTRL RM | MAY, TOM | CLOSED | 2007-11-29 | CP: PROJECT CONTINGENCY | 154 | CLOSED | 1326.66 | 0 | 0 | 0
PJ0002693 | INSTALL HVAC SYSTEM - ANC 154 OPERATOR'S/MICRO ING/ CTRL RM | MAY, TOM | CLOSED | 2007-11-29 | EL:ELECTRICAL TO NEW HVAC UNITS AT ANC | 154 | CLOSED | 2630.208 | 0 | 3171.462 | 3171.462
PJ0002693 | INSTALL HVAC SYSTEM - ANC 154 OPERATOR'S/MICRO ING/ CTRL RM | MAY, TOM | CLOSED | 2007-11-29 | ES:HVAC UNITS AT ANC | 154 | CLOSED | 9953.376 | 0 | 9611.0062 | 9611.0062
PJ0002693 | INSTALL HVAC SYSTEM - ANC 154 OPERATOR'S/MICRO ING/ CTRL RM | MAY, TOM | CLOSED | 2007-11-29 | PA: PAINT ALCOVE IN CENTER ROOM AT ANC | 154 | CLOSED | 2058.912 | 0 | 667.92 | 667.92
PJ0002693 Total | [7 empty] | 17538.276 | 0 | 16600.8845 | 16600.8845
PJ0002692 | EXPAND RAW MATERIAL STORAGE BUNKS - ANIMAL NUT 154 | MAY, TOM | CLOSED | 2007-11-29 | AD: JOC 07.013.038 MAINO | 154 | CLOSED | 24382.8176 | 0 | 24382.8176 | 24382.8176
PJ0002692 | EXPAND RAW MATERIAL STORAGE BUNKS - ANIMAL NUT 154 | MAY, TOM | CLOSED | 2007-11-29 | CP: PROJECT CONTINGENCY | 154 | CLOSED | 0 | 0 | 0 | 0
PJ0002692 Total | [7 empty] | 24382.8176 | 0 | 24382.8176 | 24382.8176
PJ0002690 | OFFICE REMODEL - AG ERHART 10 RMS 141, 142, 143 | MAY, TOM | CLOSED | 2007-11-29 | AD: FLOORTEC | 010 | CLOSED | 996.0523 | 0 | 996.0523 | 996.0523
PJ0002690 | OFFICE REMODEL - AG ERHART 10 RMS 141, 142, 143 | MAY, TOM | CLOSED | 2007-11-29 | CA:COVE BASE AND FURNITURE INSTALL 10-143 | 010 | CLOSED | 0 | 0 | 408.177 | 408.177
PJ0002690 | OFFICE REMODEL - AG ERHART 10 RMS 141, 142, 143 | MAY, TOM | CLOSED | 2007-11-29 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 200.6 | 0 | 0 | 0
PJ0002690 | OFFICE REMODEL - AG ERHART 10 RMS 141, 142, 143 | MAY, TOM | CLOSED | 2007-11-29 | CU:SHAMPOO CARPETS IN 10-141-143 | 010 | CLOSED | 262.368 | 0 | 180.378 | 180.378
PJ0002690 | OFFICE REMODEL - AG ERHART 10 RMS 141, 142, 143 | MAY, TOM | CLOSED | 2007-11-29 | EL:RELOCATE FLOOR FEEDS IN 10-141/142 | 010 | CLOSED | 747.552 | 0 | 718.704 | 718.704
PJ0002690 | OFFICE REMODEL - AG ERHART 10 RMS 141, 142, 143 | MAY, TOM | CLOSED | 2007-11-29 | PA:PAINT ROOMS 112,141/142 BLDG 10 | 010 | CLOSED | 0 | 0 | 1409.226 | 1409.226
PJ0002690 Total | [7 empty] | 2206.5723 | 0 | 3712.5373 | 3712.5373
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | AD: CAME SECURITY | 035 | CLOSED | 0 | 0 | 1444.5 | 1444.5
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | AD: CREDIT CARD PURCHASE | 035 | CLOSED | 0 | 0 | 64.464 | 64.464
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | AD: DEPARTMENT OF GENERAL SERVICES FEES | 035 | CLOSED | 0 | 0 | 27.82 | 27.82
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | ANTS: SECURITY ALARM PROGRAMMING (NO LABOR) | 035 | CLOSED | 0 | 0 | 0 | 0
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | CA:BUILD BOXES FOR COLLECTION -51 | GENERAL | CLOSED | 0 | 0 | 1264.19 | 1264.19
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | CP: PROJECT CONTINGENCY | 035 | CLOSED | 5000 | 0 | 0 | 0
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | LO: LOCK SYSTEM FOR 35-121 | 035 | CLOSED | 0 | 0 | 285.84 | 285.84
PJ0002689 | SP 07/08:CREATE STORAGE FOR BARBER ART COLLECTION - KENN LIB 035 | MAY, TOM | CLOSED | 2007-11-29 | MC:MOVE THE BARBER COLLECTION | 035 | CLOSED | 0 | 0 | 80.91 | 80.91
PJ0002689 Total | [7 empty] | 5000 | 0 | 3167.724 | 3167.724
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/10 WOMENS BASKETBALL - FULLERTON 7:00 PM | GENERAL | CLOSED | 0 | 0 | 328.839 | 328.839
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/12 WOMENS BASKETBALL - IRVINE 4:00 PM | GENERAL | CLOSED | 0 | 0 | 301.6708 | 301.6708
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/19 WOMENS BASKETBALL - SANTA BARB 4:00 PM | GENERAL | CLOSED | 0 | 0 | 376.1528 | 376.1528
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 02/02 WOMENS BASKETBALL - RIVERSIDE 4:00 PM | GENERAL | CLOSED | 0 | 0 | 350.8032 | 350.8032
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 02/21 WOMENS BASKETBALL - UC DAVIS 7:00 PM | GENERAL | CLOSED | 0 | 0 | 350.8512 | 350.8512
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 02/23 WOMENS BASKETBALL - PACIFIC 4:00 PM | GENERAL | CLOSED | 0 | 0 | 366.1728 | 366.1728
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 03/06 WOMENS BASKETBALL - LONG BEACH 7:00 PM | GENERAL | CLOSED | 0 | 0 | 300.96 | 300.96
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 03/08 WOMENS BASKETBALL - NORTHRIDGE 4:00 PM | GENERAL | CLOSED | 0 | 0 | 338.58 | 338.58
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 10/31 WOMENS BASKETBALL - MELBOURNE EXHIBITION 7:00PM | GENERAL | CLOSED | 0 | 0 | 248.6355 | 248.6355
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/03 WOMENS BASKETBALL MONTEREY EXHIBITION 2:00 PM | GENERAL | CLOSED | 0 | 0 | 245.404 | 245.404
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/15 WOMENS BASKETBALL - HOUSTON 5:00 PM | GENERAL | CLOSED | 0 | 0 | 227.9398 | 227.9398
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/23 WOMENS BASKETBALL - FAIRFIELD 2:00 PM | GENERAL | CLOSED | 0 | 0 | 310.029 | 310.029
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/24 WOMENS BASKETBALL - WRIGHT 4:30 PM | GENERAL | CLOSED | 0 | 0 | 528.2376 | 528.2376
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/29 WOMENS BASKETBALL - SAN DIEGO 7:00 PM | GENERAL | CLOSED | 0 | 0 | 328.839 | 328.839
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 12/01 WOMENS BASKETBALL - SAN DIEGO 2:00 PM | GENERAL | CLOSED | 0 | 0 | 902.88 | 902.88
PJ0002685 | 07/08 WOMENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 12/12 WOMENS BASKETBALL - SANTA CLARA 7:00 PM | GENERAL | CLOSED | 0 | 0 | 150.48 | 150.48
PJ0002685 Total | [7 empty] | 0 | 0 | 5656.4747 | 5656.4747
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/03 MENS BASKETBALL - NORTHRIDGE 7:00 PM | GENERAL | CLOSED | 0 | 0 | 311.766 | 311.766
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/05 MENS BASKETBALL - LONG BEACH 7:00PM | GENERAL | CLOSED | 0 | 0 | 434.8498 | 434.8498
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/19 MENS BASKETBALL - SANTA BARBARA 7:00PM | GENERAL | CLOSED | 0 | 0 | 376.0726 | 376.0726
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 01/24 MENS BASKETBALL - UC DAVIS 7:00PM | GENERAL | CLOSED | 0 | 0 | 464.0224 | 464.0224
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 02/07 MENS BASKETBALL - IRVINE 7:00PM | GENERAL | CLOSED | 0 | 0 | 328.5528 | 328.5528
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 02/09 MENS BASKETBALL - FULLERTON 7:00PM | GENERAL | CLOSED | 0 | 0 | 357.1099 | 357.1099
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 02/28 MENS BASKETBALL - RIVERSIDE 7:00PM | GENERAL | CLOSED | 0 | 0 | 275.7884 | 275.7884
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 03/01 MENS BASKETBALL - PACIFIC 7:30PM | GENERAL | CLOSED | 0 | 0 | 395.5691 | 395.5691
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/03 MENS BASKETBALL - STANISLAUS EXHIBITION 7:00PM | GENERAL | CLOSED | 0 | 0 | 180.0096 | 180.0096
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/09 MENS BASKETBALL - UMASS 1:15PM | GENERAL | CLOSED | 0 | 0 | 137.6743 | 137.6743
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/11 MENS BASKETBALL - NORTHERN ILLINOIS 4:00PM | GENERAL | CLOSED | 0 | 0 | 151.2898 | 151.2898
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 11/15 MENS BASKETBALL - UTAH STATE 7:30PM | GENERAL | CLOSED | 0 | 0 | 328.839 | 328.839
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 12/02 MENS BASKETBALL - MENLO COLLEGE 7:00PM | GENERAL | CLOSED | 0 | 0 | 752.4 | 752.4
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 12/15 MENS BASKETBALL - BAKERSFIELD 7:00PM | GENERAL | CLOSED | 0 | 0 | 660.5698 | 660.5698
PJ0002684 | 07/08 MENS BASKETBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-11-27 | CU: 12/29 MENS BASKETBALL - S. STATE 7:00PM | GENERAL | CLOSED | 0 | 0 | 358.6049 | 358.6049
PJ0002684 Total | [7 empty] | 0 | 0 | 5513.1182 | 5513.1182
PJ0002682 | DESIGN/INSTALL 3 CRASH-BAR TYPE GATE SYS - STADIUM 61 WEST SIDE | KUENTZEL, DOUGLAS A. | CLOSED | 2007-11-21 | AD: JOC 07.014.020 STAPLES | 061 | CLOSED | 55840.8925 | 0 | 55840.8925 | 55840.8925
PJ0002682 | DESIGN/INSTALL 3 CRASH-BAR TYPE GATE SYS - STADIUM 61 WEST SIDE | KUENTZEL, DOUGLAS A. | CLOSED | 2007-11-21 | CA: ADD SIGNS AT EXIT GATES | 061 | CLOSED | 221.52 | 0 | 256.41 | 256.41
PJ0002682 | DESIGN/INSTALL 3 CRASH-BAR TYPE GATE SYS - STADIUM 61 WEST SIDE | KUENTZEL, DOUGLAS A. | CLOSED | 2007-11-21 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 5584.09 | 0 | 0 | 0
PJ0002682 | DESIGN/INSTALL 3 CRASH-BAR TYPE GATE SYS - STADIUM 61 WEST SIDE | KUENTZEL, DOUGLAS A. | CLOSED | 2007-11-21 | IN: CRASH-BAR TYPE GATE SYS - STADIUM 61 WEST SIDE | 061 | CLOSED | 0 | 0 | 99.414 | 99.414
PJ0002682 | DESIGN/INSTALL 3 CRASH-BAR TYPE GATE SYS - STADIUM 61 WEST SIDE | KUENTZEL, DOUGLAS A. | CLOSED | 2007-11-21 | LS: KEYED PADLOCKS FOR GATES | 061 | CLOSED | 171.504 | 0 | 192.336 | 192.336
PJ0002682 Total | [7 empty] | 61818.0065 | 0 | 56389.0525 | 56389.0525
PJ0002675 | INSTALL 4 ELECTRIC OUTLETS - ADMIN 01 ROOM 508 | VELARDE, DENIS L | CLOSED | 2007-11-09 | AD: THOMA ELECTRIC | 001 | CLOSED | 3873.4 | 0 | 3873.4 | 3873.4
PJ0002675 | INSTALL 4 ELECTRIC OUTLETS - ADMIN 01 ROOM 508 | VELARDE, DENIS L | CLOSED | 2007-11-09 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 387.34 | 0 | 0 | 0
PJ0002675 Total | [7 empty] | 4260.74 | 0 | 3873.4 | 3873.4
PJ0002673 | INCREASE DOOR OPENING - BONDERSON 197 RM 114 | GRIFFIN, PATRICK E | CLOSED | 2007-11-08 | AD: JOC 07.013.035 MAINO | 197 | CLOSED | 33311.0046 | 0 | 33310.9939 | 33310.9939
PJ0002673 | INCREASE DOOR OPENING - BONDERSON 197 RM 114 | GRIFFIN, PATRICK E | CLOSED | 2007-11-08 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 3340.42 | 0 | 0 | 0
PJ0002673 | INCREASE DOOR OPENING - BONDERSON 197 RM 114 | GRIFFIN, PATRICK E | CLOSED | 2007-11-08 | EL-MOVE FLEX CONDUIT FOR JOC CONTRACTOR-BONDERSON | 197 | CLOSED | 313.776 | 0 | 297.624 | 297.624
PJ0002673 Total | [7 empty] | 36965.2006 | 0 | 33608.6179 | 33608.6179
PJ0002670 | ESTIMATE TO INSTALL BUMPER & PAINT LINES- STADIUM 61 PRES SUITE | DANKO, KEN | CLOSED | 2007-11-05 | CA: ASSEMBLE CHAIRS, CHAIR CART, INSTALL CRASH RAIL ON WALLS. | 061 | CLOSED | 571.8144 | 0 | 775.602 | 775.602
PJ0002670 | ESTIMATE TO INSTALL BUMPER & PAINT LINES- STADIUM 61 PRES SUITE | DANKO, KEN | CLOSED | 2007-11-05 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 57.19 | 0 | 0 | 0
PJ0002670 Total | [7 empty] | 629.0044 | 0 | 775.602 | 775.602
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | CA: COMPLETE PAC FACILITY MAINTENANCE | 006 | CLOSED | 3692 | 0 | 2732.97 | 2732.97
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0.01 | 0 | 0 | 0
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | EL-COMPLETE MAINTENANCE ITEMS AT PAC (N/L) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | ES-COMPLETE PAC MAINTENANCE ITEMS (N/L) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | GR-COMPLETE MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 25.23 | 25.23
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | LS-COMPLETE MAINTENANCE ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 262.02 | 262.02
PJ0002667 | FALL QUARTER MAINTENANCE WALK - PAC 6 (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-11-01 | PA-COMPLETE PAINTING ITEMS AT PAC | 006 | CLOSED | 0 | 0 | 937.92 | 937.92
PJ0002667 Total | [7 empty] | 3692.01 | 0 | 3958.14 | 3958.14
PJ0002663 | NEW SCREEN BRD,OUTLETS, LOW VOLT CABLE-038 RM 133(NO ESTIMATATE) | VELARDE, DENIS L | CLOSED | 2007-11-01 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002663 | NEW SCREEN BRD,OUTLETS, LOW VOLT CABLE-038 RM 133(NO ESTIMATATE) | VELARDE, DENIS L | CLOSED | 2007-11-01 | EL: SMART ROOM 38-133 | 038 | CLOSED | 0 | 0 | 2263.656 | 2263.656
PJ0002663 Total | [7 empty] | 0 | 0 | 2263.656 | 2263.656
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | CP: PROJECT CONTINGENCY | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 11 PACIFIC 6:00PM N/L | 160 | CLOSED | 0 | 0 | 624.552 | 624.552
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 12 PACIFIC 6:00PM N/L | 160 | CLOSED | 0 | 0 | 613.278 | 613.278
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 13 PACIFIC 1:00PM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 15 FRESNO STATE 6:00PM N/L | 160 | CLOSED | 0 | 0 | 141.288 | 141.288
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 16 LAYOLA MARYMOUNT 3:00PM N/L | 160 | CLOSED | 0 | 0 | 346.098 | 346.098
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 25 UC SANTA BARBARA 6:00PM- N/L | 160 | CLOSED | 0 | 0 | 546.18 | 546.18
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 26 UC SANTA BARBARA 6:00PM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 27 UC SANTA BARBARA 1:00PM - N/L | 160 | CLOSED | 0 | 0 | 817.464 | 817.464
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 30 CALIFORNIA 6:00PM - N/L | 160 | CLOSED | 0 | 0 | 403.68 | 403.68
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - APR 9 FRESNO STATE 6:00PM N/L | 160 | CLOSED | 0 | 0 | 524.784 | 524.784
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - FEB 16 ALUMNI GAME 11:00AM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 11 UC SANTA BARB 6:00PM- CLOSE N/L | 160 | CLOSED | 0 | 0 | 678.558 | 678.558
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 1 FRESNO STATE 1:00PM(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 12 SANTA CLARA 6:00PM - CLOSE N/L | 160 | CLOSED | 0 | 0 | 769.962 | 769.962
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 13 UCLA 6:00PM - CLOSE N/L | 160 | CLOSED | 0 | 0 | 504.6 | 504.6
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 14 UCLA 6:00PM - CLOSE N/L | 160 | CLOSED | 0 | 0 | 633.462 | 633.462
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 15 UCLA 1:00PM - CLOSE N/L | 160 | CLOSED | 0 | 0 | 325.914 | 325.914
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 2 MISSOURI 11:00AM (N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 22 SANTA CLARA 4:30PM GAME 2(N/L) | 160 | CLOSED | 0 | 0 | 0 | 0
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 28 UC IRVINE 6:00PM - CLOSE N/L | 160 | CLOSED | 0 | 0 | 496.296 | 496.296
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 29 UC IRVINE 6:00PM | 160 | CLOSED | 0 | 0 | 366.702 | 366.702
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAR 30 UC IRVINE 1:00PM - CLOSE N/L | 160 | CLOSED | 0 | 0 | 427.44 | 427.44
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 13 PEPPERDINE 6:00PM - N/L | 160 | CLOSED | 0 | 0 | 282.576 | 282.576
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 16 LONG BEACH STATE 6:00PM - N/L | 160 | CLOSED | 0 | 0 | 341.37 | 341.37
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 17 LONG BEACH STATE 6:00PM - N/L | 160 | CLOSED | 0 | 0 | 358.887 | 358.887
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 18 LONG BEACH STATE 1:00PM - N/L | 160 | CLOSED | 0 | 0 | 363.312 | 363.312
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 2 UNLV 6:00PM - N/L | 160 | CLOSED | 0 | 0 | 161.472 | 161.472
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 3 UNLV 6:00PM - N/L | 160 | CLOSED | 0 | 0 | 476.718 | 476.718
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 BASEBALL - MAY 4 UNLV 1:00PM - N/L | 160 | CLOSED | 0 | 0 | 370.464 | 370.464
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 BASEBALL - APR 29 UC SOTHRN CALIFORNIA 6PM - N/L | 160 | CLOSED | 0 | 0 | 201.84 | 201.84
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 BASEBALL - MAR 22 SANTA CLARA 1PM GAME 1 - CLOSE N/L | 160 | CLOSED | 0 | 0 | 338.4 | 338.4
PJ0002662 | 07/08 BASEBALL- LANDSCAPE SERVICES FOR ATHLETICS (GROUNDS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: RECHARGE WORK FOR BAGGET STADIUM 160 07/08 - CLOSE N/L | 160 | CLOSED | 0 | 0 | 2136.899 | 2136.899
PJ0002662 Total | [7 empty] | 0 | 0 | 13252.196 | 13252.196
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 10 NEW MEXICO STATE 12:00PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 15 ILLINOIS 3:45PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 15 SOUTH CAROLINA 1:30PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 16 NO. 22 MISSOURI 5:30PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 17 NO. 9 OKLAHOMA 11:15AM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 17 WISCONSIN - 9:00AM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 8 SAN DIEGO STATE 6:00PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 9 NO. 20 OREGON 10:00AM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 9 NO. 6 TENESSEE 6:00PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 3 NORTH DAKOTA 3:00PM GAME 1(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | CP: PROJECT CONTINGENCY | 161 | CLOSED | 0.01 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - FEB 8 TEXAS A%M 3:30PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 14 OKLAHOMA 10:00AM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 15 NEVADA 10:00AM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 15 PRINCETON 3:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 16 COLORADO STATE 11:00AM - CLOSE N/L | 161 | CLOSED | 0 | 0 | 80.736 | 80.736
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 7 FRESNO STATE 7:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 8 HOUSTON 1:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 8 RHODE ISLAND 7:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 9 DEPAUL 11:00AM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAR 9 SANTA CLARA 1:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAY 10 UC RIVERSIDE 12:00PM - CLOSE N/L | 161 | CLOSED | 0 | 0 | 324.156 | 324.156
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAY 3 UC DAVIS 4:00PM GAME 1 - CLOSE N/L | 161 | CLOSED | 0 | 0 | 301.002 | 301.002
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAY 3 UC DAVIS 6:30PM GAME 2 - CLOSE N/L | 161 | CLOSED | 0 | 0 | 231.54 | 231.54
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL - MAY 4 UC DAVIS 12:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/ 08 SOFTBALL-MAR 14 NORTHERN COLORADO 12:30PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - APR 19 CA ST NO. RIDGE 12PM GAME 1- CLOSE N/L | 161 | CLOSED | 0 | 0 | 185.232 | 185.232
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - APR 19 CA ST NO.RIDGE 2:30PM GAME 2-CLOSE N/L | 161 | CLOSED | 0 | 0 | 115.77 | 115.77
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - APRIL 20 CA ST NO.RIDGE 12PM - CLOSE N/L | 161 | CLOSED | 0 | 0 | 404.892 | 404.892
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - MAR 29 CA. ST.FLLRTON 2:30PM GM 2- CLOSE N/L | 161 | CLOSED | 0 | 0 | 329.793 | 329.793
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - MAR 3 NO. DAKOTA 5:00PM GAME 2 - CLOSE N/L | 161 | CLOSED | 0 | 0 | 439.32 | 439.32
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - MAR 30 CA ST FULLERTON 12:00PM- CLOSE N/L | 161 | CLOSED | 0 | 0 | 185.232 | 185.232
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - MAY 9 UC RIVERSIDE 4:PM GAME 1- CLOSE N/L | 161 | CLOSED | 0 | 0 | 422.106 | 422.106
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL - MAY 9 UC RIVERSIDE 6:30PM GAME 2 - CLOSE N/L | 161 | CLOSED | 0 | 0 | 92.616 | 92.616
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SFTBLL- MAR 29 CAL ST. FULLERTON 12PM GAME 1-CLOSE N/L | 161 | CLOSED | 0 | 0 | 254.694 | 254.694
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SOFTBALL - FEB 22 CALIFORNIA 4:30PM - CLOSE N/L | 161 | CLOSED | 0 | 0 | 2564.034 | 2564.034
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SOFTBALL - FEB 22 SANTA CLARA 7:00PM (N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SOFTBALL - FEB 23 SACRAMENTO STATE 4:30PM - CLOSE N/L | 161 | CLOSED | 0 | 0 | 1736.55 | 1736.55
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: 07/08 SOFTBALL - FEB 24 CALIFORNIA 11:00AM - CLOSE N/L | 161 | CLOSED | 0 | 0 | 1133.94 | 1133.94
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR: RECHARGE WORK FOR BOB JANSEN FIELD 07/08 - CLOSE N/L | 161 | CLOSED | 0 | 0 | 4664.913 | 4664.913
PJ0002661 | 07/08 SOFTBALL - LANDSCAPING SERVICES FOR ATHLETICS (NO EST.)) | RAMLER, THOMAS JORDAN | CLOSED | 2007-10-30 | GR:07/ 08 SOFTBALL - FEB 23 ALABAMA-BRMINGHAM 7:00PM(N/L) | 161 | CLOSED | 0 | 0 | 0 | 0
PJ0002661 Total | [7 empty] | 0.01 | 0 | 13466.526 | 13466.526
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | AD: PROCOATINGS | 020A | CLOSED | 1300.05 | 0 | 1300.05 | 1300.05
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | AD: WHITE'S DRYWALL | 020A | CLOSED | 836.74 | 0 | 836.74 | 836.74
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | CA: UPGRADE WALL FROM TEMPORARY TO PERMANENT | 020A | CLOSED | 930.0288 | 0 | 986.802 | 986.802
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | CP: PROJECT CONTINGENCY | 020A | CLOSED | 377.55 | 0 | 0 | 0
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | EL: RELOCATE (E) ELECTRICAL, INSTALL NEW | 020A | CLOSED | 642.4159 | 0 | 342.294 | 342.294
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | IN: ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-EE 20A-200 (N/L) | 020A | CLOSED | 66.276 | 0 | 0 | 0
PJ0002660 | ESTIMATE:UPGRADE TEMP WALL/INSTALL BREAKER-E. E. 20A RM 200 | MOLLAN, CHERYL L. | CLOSED | 2007-10-29 | MO:MOVE OFFICE FURNITURE | 020A | CLOSED | 94.5 | 0 | 102.276 | 102.276
PJ0002660 Total | [7 empty] | 4247.5607 | 0 | 3568.162 | 3568.162
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | AD: ALPHA FIRE | 061 | CLOSED | 0 | 0 | 304.95 | 304.95
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | AD: JOC 07.014.023 STAPLES | 061 | CLOSED | 31551.9781 | 0 | 42133.3686 | 42133.3686
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | CA: INSTALL NEW DOOR | 061 | CLOSED | 2529.12 | 0 | 3723.573 | 3723.573
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 4538.9 | 0 | 0 | 0
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | EL: FIRE ALARM CONNECTION IN SPANOS CATERING KITCHEN | 061 | CLOSED | 0 | 0 | 1086.75 | 1086.75
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | EL: INSTALL ELECTRICAN SERVICE FOR NEW HOOD | 061 | CLOSED | 4072.2 | 0 | 190.332 | 190.332
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | IN: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | 061 | CLOSED | 397.656 | 0 | 347.949 | 347.949
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | LO: LOCKSET FOR NEW DOOR | 061 | CLOSED | 171.504 | 0 | 859.68 | 859.68
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | PA: PAINT NEW DOOR @ RM 318 | 061 | CLOSED | 698.304 | 0 | 756.972 | 756.972
PJ0002657 | SP 07/08: CATERING FACILITIES UPGRADE AT SPANOS STADIUM SUITES | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-25 | PL:GAS SUPPLY FOR CATERING ROOM AT SPANOS | 061 | CLOSED | 5968.2 | 0 | 4365.492 | 4365.492
PJ0002657 Total | [7 empty] | 49927.8621 | 0 | 53769.0666 | 53769.0666
PJ0002656 | MJ: PURCHASE/INSTALL GLASS DISPLAY CASES-ENGR IV 192 RMS 122-126 | GRIFFIN, PATRICK E | CLOSED | 2007-10-25 | CA:INSTALL 5 DISPLAY CASES AT ENG IV | 192 | CLOSED | 3083.04 | 0 | 3045.57 | 3045.57
PJ0002656 | MJ: PURCHASE/INSTALL GLASS DISPLAY CASES-ENGR IV 192 RMS 122-126 | GRIFFIN, PATRICK E | CLOSED | 2007-10-25 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 308.3 | 0 | 0 | 0
PJ0002656 Total | [7 empty] | 3391.34 | 0 | 3045.57 | 3045.57
PJ0002655 | ELECT. OUTLETS/LIGHT RE-ZONING-CROPS 17 RM 15 (EST NOT REQUIRED) | VELARDE, DENIS L | CLOSED | 2007-10-24 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 0 | 0 | 0 | 0
PJ0002655 | ELECT. OUTLETS/LIGHT RE-ZONING-CROPS 17 RM 15 (EST NOT REQUIRED) | VELARDE, DENIS L | CLOSED | 2007-10-24 | EL: 017-0015 SMART ROOM | 017 | CLOSED | 0 | 0 | 762.462 | 762.462
PJ0002655 Total | [7 empty] | 0 | 0 | 762.462 | 762.462
PJ0002652 | CSM STUDIO CLASSRMS SECURITY ALARM UPGRADE - MATH 38 & ED 02 | PAHLOW, BOB | CLOSED | 2007-10-19 | ANTS: NEW SECURITY ALARM CONNECTION | 038 | CLOSED | 0 | 0 | 271.548 | 271.548
PJ0002652 | CSM STUDIO CLASSRMS SECURITY ALARM UPGRADE - MATH 38 & ED 02 | PAHLOW, BOB | CLOSED | 2007-10-19 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002652 | CSM STUDIO CLASSRMS SECURITY ALARM UPGRADE - MATH 38 & ED 02 | PAHLOW, BOB | CLOSED | 2007-10-19 | IN: BUILDING PERMIT - CAME SECURITY INTRUSION ALARM (N/L) | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002652 Total | [7 empty] | 0 | 0 | 271.548 | 271.548
PJ0002650 | PROVIDE ESTIMATE TO INSTALL CABINETS - HILLCREST 81 MRR & WRR | MAY, TOM | CLOSED | 2007-10-16 | CA:REMOVE KEYBOARD AND DISPENSER IN HILLCREST | 081 | CLOSED | 0 | 0 | 47.637 | 47.637
PJ0002650 | PROVIDE ESTIMATE TO INSTALL CABINETS - HILLCREST 81 MRR & WRR | MAY, TOM | CLOSED | 2007-10-16 | CP: PROJECT CONTINGENCY | 081 | CLOSED | 0 | 0 | 0 | 0
PJ0002650 | PROVIDE ESTIMATE TO INSTALL CABINETS - HILLCREST 81 MRR & WRR | MAY, TOM | CLOSED | 2007-10-16 | PA:TOUCH UP PAINT WOMEN'S RESTROOM HILLCREST | 081 | CLOSED | 0 | 0 | 34.698 | 34.698
PJ0002650 Total | [7 empty] | 0 | 0 | 82.335 | 82.335
PJ0002649 | ELECTRIC OUTLETS/RACEWAY - AG ENGR 08A RM 01 (EST NOT REQUIRED) | VELARDE, DENIS L | CLOSED | 2007-10-16 | CP: PROJECT CONTINGENCY | 008A | CLOSED | 0 | 0 | 0 | 0
PJ0002649 | ELECTRIC OUTLETS/RACEWAY - AG ENGR 08A RM 01 (EST NOT REQUIRED) | VELARDE, DENIS L | CLOSED | 2007-10-16 | EL: 008-001 SMART ROOM | 008A | CLOSED | 0 | 0 | 913.446 | 913.446
PJ0002649 Total | [7 empty] | 0 | 0 | 913.446 | 913.446
PJ0002647 | INSTALLATION OF LIGHTING AND ELECTRICAL OUTLETS - ENGR 13 RM 134 | PAHLOW, BOB | CLOSED | 2007-10-12 | AD: THOMA ELECTRIC | 013 | CLOSED | 4554.99 | 0 | 4554.99 | 4554.99
PJ0002647 | INSTALLATION OF LIGHTING AND ELECTRICAL OUTLETS - ENGR 13 RM 134 | PAHLOW, BOB | CLOSED | 2007-10-12 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 455.5 | 0 | 0 | 0
PJ0002647 Total | [7 empty] | 5010.49 | 0 | 4554.99 | 4554.99
PJ0002645 | MC 06/07 REPLACE FENCE-CHILDREN'S CTR 38 (ENC BY 12/31/07) | MOLLAN, CHERYL L. | CLOSED | 2007-10-11 | AD: FENCE FACTORY | 038 | CLOSED | 8869.23 | 0 | 8869.23 | 8869.23
PJ0002645 | MC 06/07 REPLACE FENCE-CHILDREN'S CTR 38 (ENC BY 12/31/07) | MOLLAN, CHERYL L. | CLOSED | 2007-10-11 | CA: REMOVE SNOW FENCE AT CHILDREN'S CENTER 038 | 038 | CLOSED | 0 | 0 | 514.656 | 514.656
PJ0002645 | MC 06/07 REPLACE FENCE-CHILDREN'S CTR 38 (ENC BY 12/31/07) | MOLLAN, CHERYL L. | CLOSED | 2007-10-11 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 923.31 | 0 | 0 | 0
PJ0002645 | MC 06/07 REPLACE FENCE-CHILDREN'S CTR 38 (ENC BY 12/31/07) | MOLLAN, CHERYL L. | CLOSED | 2007-10-11 | EL:RELOCATE ELECTRICAL | 038 | CLOSED | 364.1686 | 0 | 83.244 | 83.244
PJ0002645 Total | [7 empty] | 10156.7086 | 0 | 9467.13 | 9467.13
PJ0002643 | SR 07/08 TUBE IN BOILER #1-BOILER PLANT 40 (ENC BY 6/30/08) | BISCHEL, JOSEPH W | CLOSED | 2007-10-09 | AD: R.F. MACDONALD | 040 | CLOSED | 32833.96 | 0 | 32833.96 | 32833.96
PJ0002643 | SR 07/08 TUBE IN BOILER #1-BOILER PLANT 40 (ENC BY 6/30/08) | BISCHEL, JOSEPH W | CLOSED | 2007-10-09 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 0 | 0 | 0 | 0
PJ0002643 Total | [7 empty] | 32833.96 | 0 | 32833.96 | 32833.96
PJ0002642 | ITRC FABRICATION SHOP ELECTRICAL UPGRADE - ITRC 136 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-09 | AD: JOC 07.013.025 MAINO | 136 | CLOSED | 32430.3625 | 0 | 29285.3222 | 29285.3222
PJ0002642 | ITRC FABRICATION SHOP ELECTRICAL UPGRADE - ITRC 136 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-09 | CP: PROJECT CONTINGENCY | 136 | CLOSED | 3313.67 | 0 | 0 | 0
PJ0002642 | ITRC FABRICATION SHOP ELECTRICAL UPGRADE - ITRC 136 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-10-09 | IN: ITRC FABRICATION SHOP ELECTRICAL UPGRADE - ITRC 136 | 136 | CLOSED | 198.828 | 0 | 82.845 | 82.845
PJ0002642 Total | [7 empty] | 35942.8605 | 0 | 29368.1672 | 29368.1672
PJ0002640 | INSTALL 4 NEW CIRCUITS - COMP SCI 14 ROOM 103 | PAHLOW, BOB | CLOSED | 2007-10-03 | AD: THOMA ELECTRIC | 014 | CLOSED | 1760.15 | 0 | 1760.15 | 1760.15
PJ0002640 | INSTALL 4 NEW CIRCUITS - COMP SCI 14 ROOM 103 | PAHLOW, BOB | CLOSED | 2007-10-03 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 176.02 | 0 | 0 | 0
PJ0002640 Total | [7 empty] | 1936.17 | 0 | 1760.15 | 1760.15
PJ0002639 | PROVIDE POWER AND GROUNDING - ATL 07 RM 05 SCREEN ROOM | PAHLOW, BOB | CLOSED | 2007-10-01 | AD: THOMA ELECTRIC | 007 | CLOSED | 1462.69 | 0 | 1462.69 | 1462.69
PJ0002639 | PROVIDE POWER AND GROUNDING - ATL 07 RM 05 SCREEN ROOM | PAHLOW, BOB | CLOSED | 2007-10-01 | CP: PROJECT CONTINGENCY | 007 | CLOSED | 146.27 | 0 | 0 | 0
PJ0002639 Total | [7 empty] | 1608.96 | 0 | 1462.69 | 1462.69
PJ0002638 | MJ: HOUSING ADMIN 31 (JOC TRACKING ONLY) - RMS 101, 111, 203 | QUEEN, BARBARA | CLOSED | 2007-09-28 | CP: PROJECT CONTINGENCY | 031 | CLOSED | 0 | 0 | 0 | 0
PJ0002638 | MJ: HOUSING ADMIN 31 (JOC TRACKING ONLY) - RMS 101, 111, 203 | QUEEN, BARBARA | CLOSED | 2007-09-28 | HOUSING ADMIN 31 (JOC) - ROOMS 101, 111, 203 | 031 | CLOSED | 0 | 0 | 0 | 0
PJ0002638 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | AD: DIVISION OF STATE ARCHITECT | 136 | CLOSED | 380 | 0 | 380 | 380
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | AD: EARTH SYSTEMS | 136 | CLOSED | 6099 | 0 | 3744.358 | 3744.358
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | AD: JOC 08.017.001 MAINO | 136 | CLOSED | 171800.5161 | 0 | 171800.5161 | 171800.5161
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | AD: SEISMIC PEER REVIEW - ENGLEKIRK & SABOL | 136 | CLOSED | 856 | 0 | 1032.55 | 1032.55
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | CP: PROJECT CONTINGENCY | 136 | CLOSED | 18083.22 | 0 | 0 | 0
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | EL:ELECTRICAL SUPPORT FOR NEW BUILDING AT DRUMM RESIVOIR | 136 | CLOSED | 0 | 0 | 14726.5189 | 14726.5189
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | IN: PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | 136 | CLOSED | 1325.52 | 0 | 1103.298 | 1103.298
PJ0002637 | PROVIDE NEW STEEL BLDG - ITRC AT DRUMM RESERVOIR | LAMPMAN, GREG | CLOSED | 2007-09-28 | LO: INSTALL CORES IN 2 DOORS | 136 | CLOSED | 370.9147 | 0 | 214.92 | 214.92
PJ0002637 Total | [7 empty] | 198915.1708 | 0 | 193002.161 | 193002.161
PJ0002636 | COMPLETE MOISTURE REMEDIATION - FOOD PROC 24 SENSORY LAB 106 | GRIFFIN, PATRICK E | CLOSED | 2007-09-28 | AD: SMITH AND SONS | 024 | CLOSED | 5362.9256 | 0 | 5362.9256 | 5362.9256
PJ0002636 | COMPLETE MOISTURE REMEDIATION - FOOD PROC 24 SENSORY LAB 106 | GRIFFIN, PATRICK E | CLOSED | 2007-09-28 | CP: PROJECT CONTINGENCY | 024 | CLOSED | 536.29 | 0 | 0 | 0
PJ0002636 Total | [7 empty] | 5899.2156 | 0 | 5362.9256 | 5362.9256
PJ0002635 | COMPLETE MAINTENANCE - PAC WALK-THRU "2007" (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-09-28 | CA: COMPLETE WORK AT PAC FOR FACILITIES MAINTENANCE WALK | 006 | CLOSED | 4261.35 | 0 | 2144.0726 | 2144.0726
PJ0002635 | COMPLETE MAINTENANCE - PAC WALK-THRU "2007" (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-09-28 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002635 | COMPLETE MAINTENANCE - PAC WALK-THRU "2007" (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-09-28 | ES: INSTALL MISSING KICK PLATE IN SERVICE ELEVATOR AT PAC | 006 | CLOSED | 78.36 | 0 | 83.5908 | 83.5908
PJ0002635 | COMPLETE MAINTENANCE - PAC WALK-THRU "2007" (NO ESTIMATE) | GRIFFIN, PATRICK E | CLOSED | 2007-09-28 | LS: SECURE LOOSE CLOSURE COVER AT PAC | 006 | CLOSED | 35.73 | 0 | 23.82 | 23.82
PJ0002635 Total | [7 empty] | 4375.44 | 0 | 2251.4834 | 2251.4834
PJ0002634 | MJ: COMPLETE HVAC - ENGR IV 192 ROOM 101 | BISCHEL, JOSEPH W | CLOSED | 2007-09-27 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002634 | MJ: COMPLETE HVAC - ENGR IV 192 ROOM 101 | BISCHEL, JOSEPH W | CLOSED | 2007-09-27 | ES: COMPLETE HVAC ENGR IV 192 ROOM 101 | 192 | CLOSED | 0 | 0 | 7964.388 | 7964.388
PJ0002634 Total | [7 empty] | 0 | 0 | 7964.388 | 7964.388
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | AD: WHITE'S DRYWALL | 026 | CLOSED | 3210 | 0 | 2065.1 | 2065.1
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | AD:PROCOATINGS PAINTING IN 26-210B | 026 | CLOSED | 0 | 0 | 1321.45 | 1321.45
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | CA: REINSTALL DOOR TO WOMEN'S RESTROOM 26-203 | 026 | CLOSED | 1439.88 | 0 | 2163.408 | 2163.408
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | CA:BUILD NEW OFFICE IN 26-210B | 026 | CLOSED | 5630.4 | 0 | 2529.822 | 2529.822
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | CP: PROJECT CONTINGENCY | 026 | CLOSED | 1310.56 | 0 | 0 | 0
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | EL:INSTALL ELECTRICAL IN NEW WALL AT 26-210B | 026 | CLOSED | 1448.88 | 0 | 741.3314 | 741.3314
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | ES:RELOCATE T-STAT IN 26-210B/C | 026 | CLOSED | 0 | 0 | 702.1586 | 702.1586
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | LO:DOOR HARDWARE FOR 26-210B | 026 | CLOSED | 528.672 | 0 | 115.752 | 115.752
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | LO:DOOR HARDWARE FOR WOMEN'S RESTROOM | 026 | CLOSED | 0 | 0 | 857.148 | 857.148
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | PA:PAINT DOOR FOR 26-210B | 026 | CLOSED | 2287.68 | 0 | 210.648 | 210.648
PJ0002633 | CREATE HALLWAY & OFFICE - GRAPHIC ARTS 26 ROOMS 210B & 210C | MAY, TOM | CLOSED | 2007-09-26 | PA:PAINT DOOR FOR WOMEN'S RESTROOM (N/L) | 026 | CLOSED | 0 | 0 | 0 | 0
PJ0002633 Total | [7 empty] | 15856.072 | 0 | 10706.8181 | 10706.8181
PJ0002632 | INSTALL WINE WALK IN COOLER & S.S SINK - CROPS 17 ROOM 15B | LAMPMAN, GREG | CLOSED | 2007-09-25 | AD: JOC 05.011.001.02 MAINO | 017 | CLOSED | 13124.9196 | 0 | 13124.9196 | 13124.9196
PJ0002632 | INSTALL WINE WALK IN COOLER & S.S SINK - CROPS 17 ROOM 15B | LAMPMAN, GREG | CLOSED | 2007-09-25 | CA: INSTALL CONCRETE PAD FOR CONDENSER | 017 | CLOSED | 886.08 | 0 | 850.212 | 850.212
PJ0002632 | INSTALL WINE WALK IN COOLER & S.S SINK - CROPS 17 ROOM 15B | LAMPMAN, GREG | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 4144.49 | 0 | 0 | 0
PJ0002632 | INSTALL WINE WALK IN COOLER & S.S SINK - CROPS 17 ROOM 15B | LAMPMAN, GREG | CLOSED | 2007-09-25 | EL: INSTALL ELECTRICAL FOR WALK IN COOLER | 017 | CLOSED | 1440 | 0 | 3009.9459 | 3009.9459
PJ0002632 | INSTALL WINE WALK IN COOLER & S.S SINK - CROPS 17 ROOM 15B | LAMPMAN, GREG | CLOSED | 2007-09-25 | ES: INSTALL NEW COOLER CROPS | 017 | CLOSED | 26880 | 0 | 22707.1204 | 22707.1204
PJ0002632 | INSTALL WINE WALK IN COOLER & S.S SINK - CROPS 17 ROOM 15B | LAMPMAN, GREG | CLOSED | 2007-09-25 | IN: INSTALL WINE WALK IN COOLER & S.S SINK -CROPS 17 RM 15B (N/L | 017 | CLOSED | 0 | 0 | 0 | 0
PJ0002632 Total | [7 empty] | 46475.4896 | 0 | 39692.1979 | 39692.1979
PJ0002631 | INSTALL NEW WINDOWS - CROPS 17 ROOM 14 | LAMPMAN, GREG | CLOSED | 2007-09-25 | AD: JOC 05.011.001.01 MAINO | 017 | CLOSED | 11302.9878 | 0 | 11302.9878 | 11302.9878
PJ0002631 | INSTALL NEW WINDOWS - CROPS 17 ROOM 14 | LAMPMAN, GREG | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 1130.3 | 0 | 0 | 0
PJ0002631 Total | [7 empty] | 12433.2878 | 0 | 11302.9878 | 11302.9878
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | AD: JOC 07.013.044 MAINO | 070 | CLOSED | 168369.6788 | 0 | 169248.9192 | 169248.9192
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | AD: MECA | 070 | CLOSED | 13472.37 | 0 | 10600.49 | 10600.49
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | CA:ASSIST PL WITH CARGO BOX | 070 | CLOSED | 1929.12 | 0 | 689.694 | 689.694
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 10933.9 | 0 | 0 | 0
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | EL:DISCONNECT POWER TO STORAGE BUILDING BEHIND 36 | 070 | CLOSED | 317.22 | 0 | 1655.7854 | 1655.7854
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | EO: PREP FOR STORAGE CONTAINERS | 070 | CLOSED | 139.032 | 0 | 741.504 | 741.504
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | IN: SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | 070 | CLOSED | 0 | 0 | 82.845 | 82.845
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | LA:PREPARE SITE FOR DOG KENNEL AT 74 | 070 | CLOSED | 0 | 0 | 111.012 | 111.012
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | MO:SURPLUS FROM BLDGS 70 H/I | 070 | CLOSED | 0 | 0 | 450.312 | 450.312
PJ0002628 | SP 07/08 CORPYARD BEAUTIFICATION - BLDG 70 | MAY, TOM | CLOSED | 2007-09-25 | PL: CARGO BOX TO REPLACE PLUMBING SHOP STORAGE SHED. | 070 | CLOSED | 0 | 0 | 13308.336 | 13308.336
PJ0002628 Total | [7 empty] | 195161.3208 | 0 | 196888.8976 | 196888.8976
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | AD: JOC 07.015.021 MAINO | GENERAL | CLOSED | 78042.9645 | 0 | 78042.9645 | 78042.9645
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | AD: PEAK RACKS | GENERAL | CLOSED | 8153.4 | 0 | 13908.4271 | 13908.4271
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | CA: INSTALL BIKE RACKS KENNEDY LIBRARY | 035 | CLOSED | 2000.1 | 0 | 830.7 | 830.7
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | CA: PROVIDE INSTALL BIKE RACKS AT AG ERHART AND MUSIC | 010 | CLOSED | 941.46 | 0 | 1862.196 | 1862.196
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | CA: PURCHASE BICYCLE RACKS FOR CAMPUSWIDE INSTALLATION | GENERAL | CLOSED | 21613.848 | 0 | 25070.4 | 25070.4
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | CA:BLG 35-ASSIST IN GRADING PADS FOR BICYCLE PARKING-KENNEDY LIB | 035 | CLOSED | 17456.844 | 0 | 17456.838 | 17456.838
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 13644.43 | 0 | 0 | 0
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | EO: BLG 35, 10, 22 - GRADE PAD, PROVIDE MOVING SUPPORT OF LOCKER | 035 | CLOSED | 5399.076 | 0 | 6001.548 | 6001.548
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | IN: SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | GENERAL | CLOSED | 331.38 | 0 | 165.69 | 165.69
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | LA: BIKE PARKING LANDSCAPE FOR BLDG AREAS 005,14, 22 | GENERAL | CLOSED | 10006.524 | 0 | 13958.1858 | 13958.1858
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | LA: BIKE RACK UPGRADES (MAINT) | GENERAL | CLOSED | 0 | 0 | 3512.9524 | 3512.9524
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | MO: MOVE BICYLE RACKS FOR CAMPUS-WIDE PROJECT | GENERAL | CLOSED | 88.515 | 0 | 292.872 | 292.872
PJ0002627 | SP 07/08 INSTALL BICYCLE PARKING - CAMPUSWIDE | MOLLAN, CHERYL L. | CLOSED | 2007-09-25 | PL: REMOVE STORM DRAIN KENNEDY LIBRARY | 035 | CLOSED | 563.376 | 0 | 563.376 | 563.376
PJ0002627 Total | [7 empty] | 158241.9175 | 0 | 161666.1498 | 161666.1498
PJ0002626 | SP 07/08 WAYFINDING DESIGN - CAMPUSWIDE | LAMPMAN, GREG | CLOSED | 2007-09-25 | AD: ROSSETTI ARCHITECTURAL ENGINEERING | GENERAL | CLOSED | 39590 | 0 | 39590 | 39590
PJ0002626 | SP 07/08 WAYFINDING DESIGN - CAMPUSWIDE | LAMPMAN, GREG | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 3705.22 | 0 | 0 | 0
PJ0002626 | SP 07/08 WAYFINDING DESIGN - CAMPUSWIDE | LAMPMAN, GREG | CLOSED | 2007-09-25 | EL: VERIFY LIGHTING ON WAYFINDING SIGNS | GENERAL | CLOSED | 253.776 | 0 | 190.332 | 190.332
PJ0002626 | SP 07/08 WAYFINDING DESIGN - CAMPUSWIDE | LAMPMAN, GREG | CLOSED | 2007-09-25 | IN: SP 07/08 WAYFINDING - CAMPUSWIDE | GENERAL | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0002626 Total | [7 empty] | 43548.996 | 0 | 39813.47 | 39813.47
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | AD: HOADLEY DESIGN | GENERAL | CLOSED | 0 | 0 | 10523.022 | 10523.022
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | AD: JOC 07.013.053 MAINO | GENERAL | CLOSED | 246526.9621 | 0 | 246526.9621 | 246526.9621
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | AD: QUICK CRETE PRODUCTS - ITEMS TO BE INSTALLED BY JOC | GENERAL | CLOSED | 0 | 0 | 16817.7143 | 16817.7143
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | AD: SOUTH BAY FOUNDRY, INC. | GENERAL | CLOSED | 0 | 0 | 21333.4246 | 21333.4246
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | CA: TRAFFIC SIGNS FOR VIA CARTA - EVEN MORE ADDITIONAL WORK | GENERAL | CLOSED | 0 | 0 | 12877.332 | 12877.332
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | CA:REMOVE OLD SCALE HOUSE | GENERAL | CLOSED | 886.08 | 0 | 838.455 | 838.455
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 31165.51 | 0 | 0 | 0
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | CU: PRESSURE WASH CONCRETE BENCHES - CAMPUS MARKET | GENERAL | CLOSED | 0 | 0 | 306.747 | 306.747
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | EL: DISCONNECT ELECTRICAL TO OLD SCALE HOUSE | GENERAL | CLOSED | 0 | 0 | 63.444 | 63.444
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | EL: RELOCATE SCALE READER FROM VIA CARTA | GENERAL | CLOSED | 4903.32 | 0 | 2562.372 | 2562.372
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | EL: SUPPLY POWER FOR IRRIGATION CLOCK - VIA CARTA | GENERAL | CLOSED | 0 | 0 | 301.968 | 301.968
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | EO: IMPORT TOP SOIL FOR VIA CARTA PLANTERS | GENERAL | CLOSED | 1853.76 | 0 | 2363.544 | 2363.544
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | ES: FABRICATE PIPE SEGMENTS FOR BOLLARDS | GENERAL | CLOSED | 0 | 0 | 687.36 | 687.36
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | IN: SP 07/08 PEDESTRIAN WALKWAY-VIA CARTA / N. PERIMETER | GENERAL | CLOSED | 0 | 0 | 149.121 | 149.121
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | LA: INSTALL LANDSCAPE FOR VIA CARTA PEDESTIAN WALKWAY | GENERAL | CLOSED | 0 | 0 | 30664.0618 | 30664.0618
PJ0002625 | SP 07/08 PEDESTRIAN WALKWAY - VIA CARTA/FEED MILL & N. PERIMETER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-09-25 | PA: PAINT TRAFFIC SIGNS FOR VIA CARTA DIVERSION | GENERAL | CLOSED | 0 | 0 | 57.192 | 57.192
PJ0002625 Total | [7 empty] | 285335.6321 | 0 | 346072.7198 | 346072.7198
PJ0002623 | DESIGN AND SOFTWARE FOR MASS ENUNCIATOR SYSTEM DP - CAMPUSWIDE | POPHAM, DONALD J. | CLOSED | 2007-09-25 | AD: TECHNICAL OPERATIONS MGT. CO. | GENERAL | CLOSED | 3745 | 0 | 1372.275 | 1372.275
PJ0002623 | DESIGN AND SOFTWARE FOR MASS ENUNCIATOR SYSTEM DP - CAMPUSWIDE | POPHAM, DONALD J. | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 374.5 | 0 | 0 | 0
PJ0002623 | DESIGN AND SOFTWARE FOR MASS ENUNCIATOR SYSTEM DP - CAMPUSWIDE | POPHAM, DONALD J. | CLOSED | 2007-09-25 | IN: INSTALL MASS ENUNCIATOR SYSTEM | GENERAL | CLOSED | 0 | 0 | 132.552 | 132.552
PJ0002623 Total | [7 empty] | 4119.5 | 0 | 1504.827 | 1504.827
PJ0002622 | INSTALL PORTS & ELECTRICAL OUTLETS - ENGR WEST 21 RMS 206 & 207 | GRIFFIN, PATRICK E | CLOSED | 2007-09-25 | CA: MOVE ACOUSTICAL WALL PANELS IN ENG WEST 206 | 021 | CLOSED | 1414.5 | 0 | 1287.5801 | 1287.5801
PJ0002622 | INSTALL PORTS & ELECTRICAL OUTLETS - ENGR WEST 21 RMS 206 & 207 | GRIFFIN, PATRICK E | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 478.03 | 0 | 0 | 0
PJ0002622 | INSTALL PORTS & ELECTRICAL OUTLETS - ENGR WEST 21 RMS 206 & 207 | GRIFFIN, PATRICK E | CLOSED | 2007-09-25 | EL: INSTALL NEW WIRE MOLD AND ELECTRICAL SERVICE EW 206 | 021 | CLOSED | 3365.76 | 0 | 2645.91 | 2645.91
PJ0002622 | INSTALL PORTS & ELECTRICAL OUTLETS - ENGR WEST 21 RMS 206 & 207 | GRIFFIN, PATRICK E | CLOSED | 2007-09-25 | PA-PATCH AND SPOT PAINT WALLS IN ENG WEST 206 | 021 | CLOSED | 228.768 | 0 | 833.196 | 833.196
PJ0002622 Total | [7 empty] | 5487.058 | 0 | 4766.6861 | 4766.6861
PJ0002621 | ADD 1 NEW CIRCUIT & ALTER 2 RECEPTACLES - COMP SCI 14 RM 104 | PAHLOW, BOB | CLOSED | 2007-09-25 | AD: THOMA ELECTRIC | 014 | CLOSED | 1053.95 | 0 | 1053.95 | 1053.95
PJ0002621 | ADD 1 NEW CIRCUIT & ALTER 2 RECEPTACLES - COMP SCI 14 RM 104 | PAHLOW, BOB | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 105.4 | 0 | 0 | 0
PJ0002621 Total | [7 empty] | 1159.35 | 0 | 1053.95 | 1053.95
PJ0002620 | ADD 4 NEW CIRCUITS - COMP SCI 14 ROOM 104 | PAHLOW, BOB | CLOSED | 2007-09-25 | AD: THOMA ELECTRIC | 014 | CLOSED | 374.5 | 0 | 374.5 | 374.5
PJ0002620 | ADD 4 NEW CIRCUITS - COMP SCI 14 ROOM 104 | PAHLOW, BOB | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 37.45 | 0 | 0 | 0
PJ0002620 Total | [7 empty] | 411.95 | 0 | 374.5 | 374.5
PJ0002619 | X CHANGE CIRCUITS - COMP SCIENCE 14 ROOM 103 | PAHLOW, BOB | CLOSED | 2007-09-25 | AD: THOMA ELECTRIC | 014 | CLOSED | 1524.75 | 0 | 1524.75 | 1524.75
PJ0002619 | X CHANGE CIRCUITS - COMP SCIENCE 14 ROOM 103 | PAHLOW, BOB | CLOSED | 2007-09-25 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 152.48 | 0 | 0 | 0
PJ0002619 Total | [7 empty] | 1677.23 | 0 | 1524.75 | 1524.75
PJ0002617 | MJ: COMPLETE CONSTRUCTION-ENGR IV ROOM 101 (JOC TRACKING, ONLY) | UYTTEWAAL, JOHAN M | CLOSED | 2007-09-21 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002617 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002616 | INSTALL INTRUSION ALARM - FAC SERV 70 ROOMS 107 AND 100 | PAHLOW, BOB | CLOSED | 2007-09-21 | AD: CAME SECURITY | 070 | CLOSED | 1016.5 | 0 | 1016.5 | 1016.5
PJ0002616 | INSTALL INTRUSION ALARM - FAC SERV 70 ROOMS 107 AND 100 | PAHLOW, BOB | CLOSED | 2007-09-21 | AD: DEPARTMENT OF GENERAL SERVICES FEES | 070 | CLOSED | 0 | 0 | 19.58 | 19.58
PJ0002616 | INSTALL INTRUSION ALARM - FAC SERV 70 ROOMS 107 AND 100 | PAHLOW, BOB | CLOSED | 2007-09-21 | ATS: PROGRAM PANIC ALARM AT DISPATCH | 070 | CLOSED | 0 | 0 | 114.336 | 114.336
PJ0002616 | INSTALL INTRUSION ALARM - FAC SERV 70 ROOMS 107 AND 100 | PAHLOW, BOB | CLOSED | 2007-09-21 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 101.65 | 0 | 0 | 0
PJ0002616 | INSTALL INTRUSION ALARM - FAC SERV 70 ROOMS 107 AND 100 | PAHLOW, BOB | CLOSED | 2007-09-21 | IN: PERMIT FOR PANIC ALARM AT KEY SHOP AND RECEPTION DESK(N/L) | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0002616 Total | [7 empty] | 1118.15 | 0 | 1150.416 | 1150.416
PJ0002615 | MJ:INSTALL T-BAR CEILING (JOC TRACKING ONLY)-ENGR IV 192-117 | UYTTEWAAL, JOHAN M | CLOSED | 2007-09-21 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002615 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002614 | INSTALL WINDOWS - MANUFACTURING 36 RM 101 | GRIFFIN, PATRICK E | CLOSED | 2007-09-21 | AD: JOC 07.013.026 MAINO | 036 | CLOSED | 1819.1819 | 0 | 1819.1819 | 1819.1819
PJ0002614 | INSTALL WINDOWS - MANUFACTURING 36 RM 101 | GRIFFIN, PATRICK E | CLOSED | 2007-09-21 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 355.43 | 0 | 0 | 0
PJ0002614 | INSTALL WINDOWS - MANUFACTURING 36 RM 101 | GRIFFIN, PATRICK E | CLOSED | 2007-09-21 | EL: REMOVE TRACK LIGHTING AT 036-101 | 036 | CLOSED | 1735.104 | 0 | 1046.34 | 1046.34
PJ0002614 | INSTALL WINDOWS - MANUFACTURING 36 RM 101 | GRIFFIN, PATRICK E | CLOSED | 2007-09-21 | IN: INSTALL WINDOWS - MANUFACTURING 36 RM 101 (N/L) | 036 | CLOSED | 0 | 0 | 0 | 0
PJ0002614 Total | [7 empty] | 3909.7159 | 0 | 2865.5219 | 2865.5219
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CP: PROJECT CONTINGENCY | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 10/12/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 10/5/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 10/6/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/10/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/15/07 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/16/07 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/17/07 | 044 | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/28/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/30/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/8/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 11/9/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 12/1/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 12/15/07 | 044 | CLOSED | 0 | 0 | 152.031 | 152.031
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 12/16/07 | 044 | CLOSED | 0 | 0 | 75.24 | 75.24
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 12/8/07 | 044 | CLOSED | 0 | 0 | 65.592 | 65.592
PJ0002612 | 07/08 EXTRA CLEANING - SPANOS THEATRE - FALL QTR 2007 (NO EST) | RAMLER, THOMAS JORDAN | CLOSED | 2007-09-19 | CU: SPANOS THEATRE 12/9/07 (NO LABOR) | 044 | CLOSED | 0 | 0 | 0 | 0
PJ0002612 Total | [7 empty] | 0 | 0 | 1276.743 | 1276.743
PJ0002611 | RUN CABLE FOR TELEVISION - BUS 03 FROM ROOM 409 TO ROOM 308 | GRIFFIN, PATRICK E | CLOSED | 2007-09-18 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 173.18 | 0 | 0 | 0
PJ0002611 | RUN CABLE FOR TELEVISION - BUS 03 FROM ROOM 409 TO ROOM 308 | GRIFFIN, PATRICK E | CLOSED | 2007-09-18 | EL-RUN RG-6 CABLE FOR NEW RECEIVER AT BUSINESS 308: | 003 | CLOSED | 1495.104 | 0 | 1190.85 | 1190.85
PJ0002611 Total | [7 empty] | 1668.284 | 0 | 1190.85 | 1190.85
PJ0002609 | PIER LANDSIDE DEMOLITION/IMPROVEMENTS - CAL POLY PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2007-09-17 | AD: JOC 07.013.021 MAINO | 228 | CLOSED | 46301.8639 | 0 | 39481.9193 | 39481.9193
PJ0002609 | PIER LANDSIDE DEMOLITION/IMPROVEMENTS - CAL POLY PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2007-09-17 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 5526.45 | 0 | 0 | 0
PJ0002609 | PIER LANDSIDE DEMOLITION/IMPROVEMENTS - CAL POLY PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2007-09-17 | EL:INSTALL AND RELOCATE ELECTRICAL LIGHTS | 228 | CLOSED | 2962.656 | 0 | 793.05 | 793.05
PJ0002609 | PIER LANDSIDE DEMOLITION/IMPROVEMENTS - CAL POLY PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2007-09-17 | IN: PIER LANDSIDE DEMOLITION/IMPROVEMENTS - CAL POLY PIER 228 | 228 | CLOSED | 0 | 0 | 99.414 | 99.414
PJ0002609 | PIER LANDSIDE DEMOLITION/IMPROVEMENTS - CAL POLY PIER 228 | MOLLAN, CHERYL L. | CLOSED | 2007-09-17 | PL:REPLACE VALVES- DONT CLOSE BEFORE APPRVL | 228 | CLOSED | 6000 | 0 | 6893.148 | 6893.148
PJ0002609 Total | [7 empty] | 60790.9699 | 0 | 47267.5313 | 47267.5313
PJ0002608 | INSTALL NEW CARPET OVER CONCRETE FLOOR - ENGR EAST 20 RM 150 | QUEEN, BARBARA | CLOSED | 2007-09-12 | AD: FLOORTEC | 020 | CLOSED | 5911.9319 | 0 | 5911.9319 | 5911.9319
PJ0002608 | INSTALL NEW CARPET OVER CONCRETE FLOOR - ENGR EAST 20 RM 150 | QUEEN, BARBARA | CLOSED | 2007-09-12 | CP: PROJECT CONTINGENCY | 020 | CLOSED | 608.34 | 0 | 0 | 0
PJ0002608 | INSTALL NEW CARPET OVER CONCRETE FLOOR - ENGR EAST 20 RM 150 | QUEEN, BARBARA | CLOSED | 2007-09-12 | KS: CHANGE (2) CORES @ ROOM 150 ENGR EAST 20 (NO LABOR) | 020 | CLOSED | 163.404 | 0 | 0 | 0
PJ0002608 Total | [7 empty] | 6683.6759 | 0 | 5911.9319 | 5911.9319
PJ0002607 | RELANDSCAPE IN FRONT OF NEW WALL @ MATH 38 CHILDREN'S CENTER | LOOSLEY, SCOTT L | CLOSED | 2007-09-11 | CP: PROJECT CONTINGENCY (NO ESTIMATE - MAINTENANCE PROJECT) | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002607 | RELANDSCAPE IN FRONT OF NEW WALL @ MATH 38 CHILDREN'S CENTER | LOOSLEY, SCOTT L | CLOSED | 2007-09-11 | LA: IRRIGATION | 038 | CLOSED | 0 | 0 | 481.4067 | 481.4067
PJ0002607 | RELANDSCAPE IN FRONT OF NEW WALL @ MATH 38 CHILDREN'S CENTER | LOOSLEY, SCOTT L | CLOSED | 2007-09-11 | LA: PLANTING | 038 | CLOSED | 0 | 0 | 1698 | 1698
PJ0002607 Total | [7 empty] | 0 | 0 | 2179.4067 | 2179.4067
PJ0002600 | SP 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | MAY, TOM | CLOSED | 2007-09-06 | AD: JOC 07.013.034 MAINO | 032 | CLOSED | 68259.8261 | 0 | 68259.8261 | 68259.8261
PJ0002600 | SP 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | MAY, TOM | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 032 | CLOSED | 6825.98 | 0 | 0 | 0
PJ0002600 | SP 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | MAY, TOM | CLOSED | 2007-09-06 | EL: RELOCATE POWER AT BREEDING BARN | 032 | CLOSED | 0 | 0 | 3118.7684 | 3118.7684
PJ0002600 | SP 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | MAY, TOM | CLOSED | 2007-09-06 | EO: DIG NEW WATER LINE TRENCH AT HORSE UNIT | 032 | CLOSED | 0 | 0 | 1204.944 | 1204.944
PJ0002600 | SP 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | MAY, TOM | CLOSED | 2007-09-06 | IN: MC 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | 032 | CLOSED | 0 | 0 | 115.983 | 115.983
PJ0002600 | SP 07/08 RENOVATE EQUINE CTR-HORSE UNIT 32 | MAY, TOM | CLOSED | 2007-09-06 | PL: RELOCATE WATER LINES | 032 | CLOSED | 0 | 0 | 3885.8921 | 3885.8921
PJ0002600 Total | [7 empty] | 75085.8061 | 0 | 76585.4136 | 76585.4136
PJ0002599 | SP 07/08 PASTURE FENCING-CROP SCIENCE 126 | POPHAM, DONALD J. | CLOSED | 2007-09-06 | AD: SOUTHWEST FENCE AND SUPPLY | 017 | CLOSED | 49353.75 | 0 | 48150 | 48150
PJ0002599 | SP 07/08 PASTURE FENCING-CROP SCIENCE 126 | POPHAM, DONALD J. | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 017 | CLOSED | 0 | 0 | 0 | 0
PJ0002599 | SP 07/08 PASTURE FENCING-CROP SCIENCE 126 | POPHAM, DONALD J. | CLOSED | 2007-09-06 | IN: MC 07/08 PASTURE FENCING-CROP SCIENCE 17K | 017 | CLOSED | 0 | 0 | 99.414 | 99.414
PJ0002599 Total | [7 empty] | 49353.75 | 0 | 48249.414 | 48249.414
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | AD: JOC 07.014.021 STAPLES | 048 | CLOSED | 123493.087 | 0 | 123493.1298 | 123493.1298
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | AD: RENGEL + CO (INVOICE ERROR - SEE NOTES; EXPENDITURE TRANS.) | 048 | CLOSED | 8709.8 | 0 | 8463.7 | 8463.7
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 16341.75 | 0 | 0 | 0
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | EL-COMPLETE ELECTRICAL SERVICES FOR OH LAB B REMODEL | 048 | CLOSED | 3110.208 | 0 | 9259.5953 | 9259.5953
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | EL-PROVIDE AND INSTALL NEW CEILING FAN IN OH LAB B | 048 | CLOSED | 0 | 0 | 990.06 | 990.06
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | EO: ASSIST PLUMBERS AT OH LAB B REMODEL | 048 | CLOSED | 0 | 0 | 2131.824 | 2131.824
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | ES:COMPLETE HVAC WORK FOR OH LAB B WORK | 048 | CLOSED | 14445.12 | 0 | 7269.48 | 7269.48
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | IN: IMPROVE TEACHING LAB EHS LAB B | 048 | CLOSED | 795.312 | 0 | 712.467 | 712.467
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | MO-MOVE CABINETS AND TABLES OF REMODEL OF OH LAB B | 048 | CLOSED | 787.5 | 0 | 284.1 | 284.1
PJ0002598 | MC 07/08: TEACHING LAB-OH 48 LAB B (ENC. BY 06/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | PL: COMPLETE PLUMBING SERVICES FOR OH LAB B REMODEL | 048 | CLOSED | 10154.688 | 0 | 23723.07 | 23723.07
PJ0002598 Total | [7 empty] | 177837.465 | 0 | 176327.4261 | 176327.4261
PJ0002597 | SP 07/08 RENOVATE GREENHOUSES - OH 48 | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | AD: JOC 07.013.019 MAINO | 048 | CLOSED | 200308.4298 | 0 | 200308.4298 | 200308.4298
PJ0002597 | SP 07/08 RENOVATE GREENHOUSES - OH 48 | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | AD: MECA | 048 | CLOSED | 11732.55 | 0 | 9747.7 | 9747.7
PJ0002597 | SP 07/08 RENOVATE GREENHOUSES - OH 48 | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | CA: CREDIT CARD PURCHASE (MATERIALS, ONLY) | 048 | CLOSED | 1360.152 | 0 | 1360.176 | 1360.176
PJ0002597 | SP 07/08 RENOVATE GREENHOUSES - OH 48 | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 048 | CLOSED | 20789.86 | 0 | 0 | 0
PJ0002597 Total | [7 empty] | 234190.9918 | 0 | 211416.3058 | 211416.3058
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | AD: JOC 08.017.035 MAINO | 021 | CLOSED | 18544.705 | 0 | 17137.5266 | 17137.5266
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | CA:ASSIST IN CONCRETE LAB 21-17 | 021 | CLOSED | 1870.4172 | 0 | 1859.4432 | 1859.4432
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 4774.39 | 0 | 0 | 0
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | EL:REPLACE LIGHTING IN CONCRETE LAB 21-17 | 021 | CLOSED | 5310.8107 | 0 | 1249.596 | 1249.596
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | ES:INSTALL EXHAUST FAN IN 21-ROOM 17 | 021 | CLOSED | 5803.3411 | 0 | 5595.708 | 5595.708
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | IN: SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | 021 | CLOSED | 151.772 | 0 | 132.552 | 132.552
PJ0002596 | SP 07/08 CONCRETE LAB UPGRADES-EW 21 RM 17 | MAY, TOM | CLOSED | 2007-09-06 | PL:DISCONNECT SINKS AND REPLUMB MIST ROOM 21-18 | 021 | CLOSED | 14750.6006 | 0 | 7785.2874 | 7785.2874
PJ0002596 Total | [7 empty] | 51206.0367 | 0 | 33760.1132 | 33760.1132
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | AD: BREEN AUTOMATION SYSTEMS | 036 | CLOSED | 0 | 0 | 545.7 | 545.7
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | AD: CAME SECURITY | 036 | CLOSED | 219.35 | 0 | 219.35 | 219.35
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | AD: GREENVALE TREE COMPANY | 036 | CLOSED | 1926 | 0 | 1926 | 1926
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | AD: SANTA MARIA ACOUSTICAL | 036 | CLOSED | 3498.9 | 0 | 3498.9 | 3498.9
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | CA:CONCRETE PAD FOR HVAC @ 36 | 036 | CLOSED | 0 | 0 | 833.562 | 833.562
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 036 | CLOSED | 2745.71 | 0 | 0 | 0
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | EL:ELECTRICAL SUPPLY FOR HVAC 36-105 | 036 | CLOSED | 1932.324 | 0 | 1927.566 | 1927.566
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | ES:HVAC SYSTEM FOR 36-105 | 036 | CLOSED | 18048.2813 | 0 | 19426.9857 | 19426.9857
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | IN: MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 | 036 | CLOSED | 198.828 | 0 | 198.828 | 198.828
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | PA: PAINT ENTRYWAY | 036 | CLOSED | 0 | 0 | 546.384 | 546.384
PJ0002595 | MC 07/08 UPGRADE COMP. LAB-MFG. 36 LAB 105 (ENC. BY 06/30/08) | MAY, TOM | CLOSED | 2007-09-06 | PL:GAS FOR NEW HVAC 36-105 | 036 | CLOSED | 1633.836 | 0 | 1323.792 | 1323.792
PJ0002595 Total | [7 empty] | 30203.2293 | 0 | 30447.0677 | 30447.0677
PJ0002592 | MAKE RESTROOMS ADA COMPLIANT - FAC SERV 70 1ST FLOOR (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2007-09-06 | CA: REMOVE PARTITIONS | 070 | CLOSED | 0 | 0 | 161.525 | 161.525
PJ0002592 | MAKE RESTROOMS ADA COMPLIANT - FAC SERV 70 1ST FLOOR (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 0 | 0 | 0 | 0
PJ0002592 | MAKE RESTROOMS ADA COMPLIANT - FAC SERV 70 1ST FLOOR (MAINT) | MOLLAN, CHERYL L. | CLOSED | 2007-09-06 | PL: FAC SVCS 1ST FLOOR MEN'S RESTROOM ADA MODIFICATIONS | 070 | CLOSED | 0 | 0 | 2265.025 | 2265.025
PJ0002592 Total | [7 empty] | 0 | 0 | 2426.55 | 2426.55
PJ0002591 | SR 07/08 COMPLETE MAINT-TRAILER-PETERSON RANCH (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | CA-COMPLETE MAINTENANCE ITEMS AT PETERSON TRAILER | 123 | CLOSED | 5415 | 0 | 11325.76 | 11325.76
PJ0002591 | SR 07/08 COMPLETE MAINT-TRAILER-PETERSON RANCH (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | CP: PROJECT CONTINGENCY | 123 | CLOSED | 1041.2 | 0 | 0 | 0
PJ0002591 | SR 07/08 COMPLETE MAINT-TRAILER-PETERSON RANCH (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | LO-INSTALL LOCKSETS IN THREE DOORS AT PETERSON TRAILER | 123 | CLOSED | 440.56 | 0 | 378.58 | 378.58
PJ0002591 | SR 07/08 COMPLETE MAINT-TRAILER-PETERSON RANCH (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | PA-COMPLETE PAINTING AT PETERSON TRAILER | 123 | CLOSED | 2056.4 | 0 | 1793.24 | 1793.24
PJ0002591 | SR 07/08 COMPLETE MAINT-TRAILER-PETERSON RANCH (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-06 | PL-REMOVE AND RE-INSTALL WATER HEATER-PETERSON RANCH | 123 | CLOSED | 0 | 0 | 947.16 | 947.16
PJ0002591 Total | [7 empty] | 8953.16 | 0 | 14444.74 | 14444.74
PJ0002587 | REPLACE CARPET - ARCH 05 ROOMS 310 AND 312 | POPHAM, DONALD J. | CLOSED | 2007-09-04 | AD: FLOORTEC | 005 | CLOSED | 3575.1054 | 0 | 3575.1054 | 3575.1054
PJ0002587 | REPLACE CARPET - ARCH 05 ROOMS 310 AND 312 | POPHAM, DONALD J. | CLOSED | 2007-09-04 | CA:REMOVE COVEBASE AT ARCH 005 ROOMS 310 & 312 | 005 | CLOSED | 222.0738 | 0 | 181.962 | 181.962
PJ0002587 | REPLACE CARPET - ARCH 05 ROOMS 310 AND 312 | POPHAM, DONALD J. | CLOSED | 2007-09-04 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 408.02 | 0 | 0 | 0
PJ0002587 | REPLACE CARPET - ARCH 05 ROOMS 310 AND 312 | POPHAM, DONALD J. | CLOSED | 2007-09-04 | IN: REPLACE CARPET - ARCH 05 ROOMS 310 AND 312 (NO LABOR) | 005 | CLOSED | 284.324 | 0 | 0 | 0
PJ0002587 Total | [7 empty] | 4489.5232 | 0 | 3757.0674 | 3757.0674
PJ0002585 | UPGRADES & MAINTENANCE - PRESIDENTIAL SUITE SPANOS 61 (MAINT) | POPHAM, DONALD J. | CLOSED | 2007-09-04 | CA: TRIM FLOOR MATS IN ELEVATOR CARS | 061 | CLOSED | 0 | 0 | 138.45 | 138.45
PJ0002585 | UPGRADES & MAINTENANCE - PRESIDENTIAL SUITE SPANOS 61 (MAINT) | POPHAM, DONALD J. | CLOSED | 2007-09-04 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002585 | UPGRADES & MAINTENANCE - PRESIDENTIAL SUITE SPANOS 61 (MAINT) | POPHAM, DONALD J. | CLOSED | 2007-09-04 | EL: REMOVE FLAT SCREEN TV (FOR REPAIR) 61 PRES SUITE | 061 | CLOSED | 0 | 0 | 52.87 | 52.87
PJ0002585 | UPGRADES & MAINTENANCE - PRESIDENTIAL SUITE SPANOS 61 (MAINT) | POPHAM, DONALD J. | CLOSED | 2007-09-04 | PA: TOUCH UP ALL SUITS | 061 | CLOSED | 1906.4 | 0 | 104.12 | 104.12
PJ0002585 Total | [7 empty] | 1906.4 | 0 | 295.44 | 295.44
PJ0002584 | SR 07/08 REPAIR WATER DAMAGE-DAIRY 18 TRAILER (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-04 | AD: SMITH AND SONS DAIRY TRAILER | 018 | CLOSED | 23029.9 | 0 | 23029.9 | 23029.9
PJ0002584 | SR 07/08 REPAIR WATER DAMAGE-DAIRY 18 TRAILER (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-04 | CA: REPAIR HOLE IN FLOOR OF DAIRY TRAILER | 018 | CLOSED | 0 | 0 | 573.04 | 573.04
PJ0002584 | SR 07/08 REPAIR WATER DAMAGE-DAIRY 18 TRAILER (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-04 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 2302.99 | 0 | 0 | 0
PJ0002584 | SR 07/08 REPAIR WATER DAMAGE-DAIRY 18 TRAILER (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-09-04 | PL: INSPECT AND REPAIR LEAK, DAIRY TRAILER | 018 | CLOSED | 0 | 0 | 317.88 | 317.88
PJ0002584 Total | [7 empty] | 25332.89 | 0 | 23920.82 | 23920.82
PJ0002581 | M&R PARK 08/09: PARK'G STRUCT CRACK SURVEY-130(ENC BY 6/30/08) | POPHAM, DONALD J. | CLOSED | 2007-09-04 | AD: OMNI DESIGN GROUP | 130 | CLOSED | 14605.5 | 0 | 14605.5 | 14605.5
PJ0002581 | M&R PARK 08/09: PARK'G STRUCT CRACK SURVEY-130(ENC BY 6/30/08) | POPHAM, DONALD J. | CLOSED | 2007-09-04 | CP: PROJECT CONTINGENCY | 130 | CLOSED | 1460.55 | 0 | 0 | 0
PJ0002581 Total | [7 empty] | 16066.05 | 0 | 14605.5 | 14605.5
PJ0002580 | EMERGENCY CLEANUP-CONCRETE LAB - EW 21 RM 17 (NO ESTIMATE-MAINT) | MAY, TOM | CLOSED | 2007-08-31 | AD: MECA | 021 | CLOSED | 1110 | 0 | 1110 | 1110
PJ0002580 | EMERGENCY CLEANUP-CONCRETE LAB - EW 21 RM 17 (NO ESTIMATE-MAINT) | MAY, TOM | CLOSED | 2007-08-31 | AD: PARC ENVIRONMENTAL | 021 | CLOSED | 725 | 0 | 725 | 725
PJ0002580 | EMERGENCY CLEANUP-CONCRETE LAB - EW 21 RM 17 (NO ESTIMATE-MAINT) | MAY, TOM | CLOSED | 2007-08-31 | CP: PROJECT CONTINGENCY | 021 | CLOSED | 0.01 | 0 | 0 | 0
PJ0002580 Total | [7 empty] | 1835.01 | 0 | 1835 | 1835
PJ0002578 | MJ: INSTALL ELECTRICAL OUTLETS - ENGR IV 192 ROOM 322 (CONTRACT) | PAHLOW, BOB | CLOSED | 2007-08-31 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 178.37 | 0 | 0 | 0
PJ0002578 Total | [7 empty] | 178.37 | 0 | 0 | 0
PJ0002576 | SPLIT CIRCUITS-EDUC 02 RMS 103,104,105 | PAHLOW, BOB | CLOSED | 2007-08-31 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0002576 | SPLIT CIRCUITS-EDUC 02 RMS 103,104,105 | PAHLOW, BOB | CLOSED | 2007-08-31 | EL-INSTALL NEW CIRCUIT FOR COPY MACHINE | 002 | CLOSED | 0 | 0 | 368.892 | 368.892
PJ0002576 | SPLIT CIRCUITS-EDUC 02 RMS 103,104,105 | PAHLOW, BOB | CLOSED | 2007-08-31 | IN:SPLIT CIRCUITS-EDUC 02 RMS 103,104,105 (ENC BY 6/30/08) (N/L) | 002 | CLOSED | 0 | 0 | 0 | 0
PJ0002576 Total | [7 empty] | 0 | 0 | 368.892 | 368.892
PJ0002574 | MJ: POT HOLE UTILITIES - AROUND BLDG 52 | MAY, TOM | CLOSED | 2007-08-30 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 1286.86 | 0 | 0 | 0
PJ0002574 | MJ: POT HOLE UTILITIES - AROUND BLDG 52 | MAY, TOM | CLOSED | 2007-08-30 | PL: POT HOLE UTILITIES AROUND BLG. 52, OLD SCI. | 052 | CLOSED | 1144.368 | 0 | 1144.368 | 1144.368
PJ0002574 Total | [7 empty] | 2431.228 | 0 | 1144.368 | 1144.368
PJ0002571 | MJ: HOOKUP 3 SYSTEMS - ENGR IV 192 RM 105 (NO ESTIMATE REQUIRED) | VELARDE, DENIS L | CLOSED | 2007-08-29 | CP: PROJECT CONTINGENCY - NO ESTIMATE: TIME AND MATERIALS | 192 | CLOSED | 0.01 | 0 | 0 | 0
PJ0002571 | MJ: HOOKUP 3 SYSTEMS - ENGR IV 192 RM 105 (NO ESTIMATE REQUIRED) | VELARDE, DENIS L | CLOSED | 2007-08-29 | EL: ENGINEERING 3 AND 4 105 AND UNDER CANOPY CONNECT EQUIPMENT | 192 | CLOSED | 0 | 0 | 1898.712 | 1898.712
PJ0002571 Total | [7 empty] | 0.01 | 0 | 1898.712 | 1898.712
PJ0002570 | INSTALL ADDITIONAL ELECTRICAL CIRCUITS - ENGR III 41 RM 209A | PAHLOW, BOB | CLOSED | 2007-08-28 | AD: THOMA ELECTRIC | 041 | CLOSED | 4252.18 | 0 | 4252.18 | 4252.18
PJ0002570 | INSTALL ADDITIONAL ELECTRICAL CIRCUITS - ENGR III 41 RM 209A | PAHLOW, BOB | CLOSED | 2007-08-28 | CP: PROJECT CONTINGENCY | 041 | CLOSED | 425.22 | 0 | 0 | 0
PJ0002570 Total | [7 empty] | 4677.4 | 0 | 4252.18 | 4252.18
PJ0002568 | RENOVATE ROOM - DEXTER 34 ROOM 222B | MOLLAN, CHERYL L. | CLOSED | 2007-08-28 | CA:REMOVE COUNTER | 034 | CLOSED | 166.14 | 0 | 306.672 | 306.672
PJ0002568 | RENOVATE ROOM - DEXTER 34 ROOM 222B | MOLLAN, CHERYL L. | CLOSED | 2007-08-28 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 93.3 | 0 | 0 | 0
PJ0002568 | RENOVATE ROOM - DEXTER 34 ROOM 222B | MOLLAN, CHERYL L. | CLOSED | 2007-08-28 | EL:REMOVE ELECTRICAL BOX | 034 | CLOSED | 63.444 | 0 | 63.444 | 63.444
PJ0002568 | RENOVATE ROOM - DEXTER 34 ROOM 222B | MOLLAN, CHERYL L. | CLOSED | 2007-08-28 | PA:PATCH AND PAINT (MAINT) | 034 | CLOSED | 0 | 0 | 1299.88 | 1299.88
PJ0002568 | RENOVATE ROOM - DEXTER 34 ROOM 222B | MOLLAN, CHERYL L. | CLOSED | 2007-08-28 | PL:REMOVE SINK | 034 | CLOSED | 703.6277 | 0 | 381.456 | 381.456
PJ0002568 Total | [7 empty] | 1026.5117 | 0 | 2051.452 | 2051.452
PJ0002565 | RENOVATION OF CAREER RESOURCE CENTER - BLDG 124 RM 117 | MAY, TOM | CLOSED | 2007-08-27 | CA: SHELVING IN 117 | 124 | CLOSED | 2285.4 | 0 | 3175.482 | 3175.482
PJ0002565 | RENOVATION OF CAREER RESOURCE CENTER - BLDG 124 RM 117 | MAY, TOM | CLOSED | 2007-08-27 | CA:INSTALL COVE BASE IN 124 | 124 | CLOSED | 2307.6 | 0 | 3258.816 | 3258.816
PJ0002565 | RENOVATION OF CAREER RESOURCE CENTER - BLDG 124 RM 117 | MAY, TOM | CLOSED | 2007-08-27 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 739.69 | 0 | 0 | 0
PJ0002565 | RENOVATION OF CAREER RESOURCE CENTER - BLDG 124 RM 117 | MAY, TOM | CLOSED | 2007-08-27 | EL:REMOVE (2) FLOOR OUTLETS IN ROOM 117 IN BLDG 124 | 124 | CLOSED | 253.776 | 0 | 158.61 | 158.61
PJ0002565 | RENOVATION OF CAREER RESOURCE CENTER - BLDG 124 RM 117 | MAY, TOM | CLOSED | 2007-08-27 | PA: PAINT SEVERAL ROOMS IN 124 | 124 | CLOSED | 600 | 0 | 599.892 | 599.892
PJ0002565 | RENOVATION OF CAREER RESOURCE CENTER - BLDG 124 RM 117 | MAY, TOM | CLOSED | 2007-08-27 | PA: PAINTING IN ROOM 117 | 124 | CLOSED | 1950.144 | 0 | 4566.822 | 4566.822
PJ0002565 Total | [7 empty] | 8136.61 | 0 | 11759.622 | 11759.622
PJ0002564 | RENOVATE ROOMS - HEALTH CENTER 27 ROOMS 102, 104, AND 127 | GRIFFIN, PATRICK E | CLOSED | 2007-08-27 | AD: FLOORTEC - INSTALL CARPET IN ROOMS 101, 102, AND 103 | 027 | CLOSED | 569.7322 | 0 | 569.7322 | 569.7322
PJ0002564 | RENOVATE ROOMS - HEALTH CENTER 27 ROOMS 102, 104, AND 127 | GRIFFIN, PATRICK E | CLOSED | 2007-08-27 | CA: HEALTH CENTER - ROOM 125 | 027 | CLOSED | 168.45 | 0 | 235.344 | 235.344
PJ0002564 | RENOVATE ROOMS - HEALTH CENTER 27 ROOMS 102, 104, AND 127 | GRIFFIN, PATRICK E | CLOSED | 2007-08-27 | CA: HEALTH CENTER - ROOMS 101, 102, AND 103 | 027 | CLOSED | 83.07 | 0 | 138.516 | 138.516
PJ0002564 | RENOVATE ROOMS - HEALTH CENTER 27 ROOMS 102, 104, AND 127 | GRIFFIN, PATRICK E | CLOSED | 2007-08-27 | CP: PROJECT CONTINGENCY | 027 | CLOSED | 278.6 | 0 | 0 | 0
PJ0002564 | RENOVATE ROOMS - HEALTH CENTER 27 ROOMS 102, 104, AND 127 | GRIFFIN, PATRICK E | CLOSED | 2007-08-27 | MO:HEALTH CENTER - ROOMS 101, 102, AND 103. | 027 | CLOSED | 252 | 0 | 68.184 | 68.184
PJ0002564 | RENOVATE ROOMS - HEALTH CENTER 27 ROOMS 102, 104, AND 127 | GRIFFIN, PATRICK E | CLOSED | 2007-08-27 | PA: HEALTH CENTER - ROOMS 101, 102, AND 103. | 027 | CLOSED | 1660.608 | 0 | 2289.78 | 2289.78
PJ0002564 Total | [7 empty] | 3012.4602 | 0 | 3301.5562 | 3301.5562
PJ0002558 | RUN FIBER CABLE BETWEEN BUILDINGS - EDUC 02 AND ENGR 13 | PAHLOW, BOB | CLOSED | 2007-08-27 | AD: JOC 07.013.023 | 002 | CLOSED | 25072.1758 | 0 | 26680.3109 | 26680.3109
PJ0002558 | RUN FIBER CABLE BETWEEN BUILDINGS - EDUC 02 AND ENGR 13 | PAHLOW, BOB | CLOSED | 2007-08-27 | CP: PROJECT CONTINGENCY | 002 | CLOSED | 2507.22 | 0 | 0 | 0
PJ0002558 Total | [7 empty] | 27579.3958 | 0 | 26680.3109 | 26680.3109
PJ0002557 | ELECTRICAL FOR PROJECTOR & PLASMA SCREEN - BUS 03 RM 300A | PAHLOW, BOB | CLOSED | 2007-08-27 | AD: THOMA ELECTRIC | 003 | CLOSED | 1184.49 | 0 | 1184.49 | 1184.49
PJ0002557 | ELECTRICAL FOR PROJECTOR & PLASMA SCREEN - BUS 03 RM 300A | PAHLOW, BOB | CLOSED | 2007-08-27 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 118.45 | 0 | 0 | 0
PJ0002557 Total | [7 empty] | 1302.94 | 0 | 1184.49 | 1184.49
PJ0002555 | MJ: LANDSCAPE SUPPORT FOR SIDEWALK MODIFICATION - DEXTER LAWN | JUDD, PERRY | CLOSED | 2007-08-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002555 | MJ: LANDSCAPE SUPPORT FOR SIDEWALK MODIFICATION - DEXTER LAWN | JUDD, PERRY | CLOSED | 2007-08-24 | GR: LANDSCAPE SUPPORT FOR SIDEWALK MODIFICATION PROJECT | GENERAL | CLOSED | 0 | 0 | 216.387 | 216.387
PJ0002555 Total | [7 empty] | 0 | 0 | 216.387 | 216.387
PJ0002554 | REPLACE COLUMN ON NORTH SIDE OF BARN - DAIRY 18 | LAMPMAN, GREG | CLOSED | 2007-08-24 | AD: JOC 07.013.009 MAINO | 018 | CLOSED | 6577.1402 | 0 | 6577.1402 | 6577.1402
PJ0002554 | REPLACE COLUMN ON NORTH SIDE OF BARN - DAIRY 18 | LAMPMAN, GREG | CLOSED | 2007-08-24 | CP: PROJECT CONTINGENCY | 018 | CLOSED | 664.34 | 0 | 0 | 0
PJ0002554 | REPLACE COLUMN ON NORTH SIDE OF BARN - DAIRY 18 | LAMPMAN, GREG | CLOSED | 2007-08-24 | IN: REPLACE COLUMN ON NORTH SIDE OF BARN - DAIRY 18 | 018 | CLOSED | 66.276 | 0 | 66.276 | 66.276
PJ0002554 Total | [7 empty] | 7307.7562 | 0 | 6643.4162 | 6643.4162
PJ0002552 | MC 06/07 GRAFFITI REMOVAL AT ARCH 05 (ENC. BY 12/30/07) | GRIFFIN, PATRICK E | CLOSED | 2007-08-23 | AD: JOC 07.013.012 MAINO | 005 | CLOSED | 86306.2214 | 0 | 86306.2214 | 86306.2214
PJ0002552 | MC 06/07 GRAFFITI REMOVAL AT ARCH 05 (ENC. BY 12/30/07) | GRIFFIN, PATRICK E | CLOSED | 2007-08-23 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 8153.46 | 0 | 0 | 0
PJ0002552 | MC 06/07 GRAFFITI REMOVAL AT ARCH 05 (ENC. BY 12/30/07) | GRIFFIN, PATRICK E | CLOSED | 2007-08-23 | CU-SEAL CONCRETE AREAS AFTER SAND BLASTING | 005 | CLOSED | 1049.472 | 0 | 6545.076 | 6545.076
PJ0002552 | MC 06/07 GRAFFITI REMOVAL AT ARCH 05 (ENC. BY 12/30/07) | GRIFFIN, PATRICK E | CLOSED | 2007-08-23 | LS-INSTALL ORANGE CORES TO ARCH RM 305 AND 402 | 005 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002552 | MC 06/07 GRAFFITI REMOVAL AT ARCH 05 (ENC. BY 12/30/07) | GRIFFIN, PATRICK E | CLOSED | 2007-08-23 | PA-PAINT ROOF DECK AREA AT ARCHITECTURE (N/L) | 005 | CLOSED | 180 | 0 | 0 | 0
PJ0002552 Total | [7 empty] | 95689.1534 | 0 | 92908.4654 | 92908.4654
PJ0002551 | REPLACE GRANITE ON SEAL AT ENTRANCE TO ADMIN 01 (MAINT) | MAY, TOM | CLOSED | 2007-08-20 | AD: SAN LUIS MARBLE & GRANITE -ADM SEAL | 001 | CLOSED | 1900 | 0 | 1900 | 1900
PJ0002551 | REPLACE GRANITE ON SEAL AT ENTRANCE TO ADMIN 01 (MAINT) | MAY, TOM | CLOSED | 2007-08-20 | CA:REMOVE TOP GRANITE PIECE AND SEAL IN FRONT OF ADM | 001 | CLOSED | 0 | 0 | 494.805 | 494.805
PJ0002551 | REPLACE GRANITE ON SEAL AT ENTRANCE TO ADMIN 01 (MAINT) | MAY, TOM | CLOSED | 2007-08-20 | CP: PROJECT CONTINGENCY | 001 | CLOSED | 0 | 0 | 0 | 0
PJ0002551 Total | [7 empty] | 1900 | 0 | 2394.805 | 2394.805
PJ0002550 | ADDITIONAL SMOKE DETECTOR STROBE FIXTURES - FREMONT - 104 & 105 | PAHLOW, BOB | CLOSED | 2007-08-16 | AD: JOC 05.012.034.01 STAPLES | 109 | CLOSED | 4283.19 | 0 | 4283.19 | 4283.19
PJ0002550 | ADDITIONAL SMOKE DETECTOR STROBE FIXTURES - FREMONT - 104 & 105 | PAHLOW, BOB | CLOSED | 2007-08-16 | CP: PROJECT CONTINGENCY | 109 | CLOSED | 428.32 | 0 | 0 | 0
PJ0002550 Total | [7 empty] | 4711.51 | 0 | 4283.19 | 4283.19
PJ0002548 | REPLACE EXTERIOR DOOR - OLD SCIENCE 52 ROOM D23 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-08-14 | CA-REPLACE DOOR AT OLD SCIENCE D-23 | 052 | CLOSED | 476.9 | 0 | 784.55 | 784.55
PJ0002548 | REPLACE EXTERIOR DOOR - OLD SCIENCE 52 ROOM D23 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-08-14 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0002548 | REPLACE EXTERIOR DOOR - OLD SCIENCE 52 ROOM D23 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-08-14 | LO: INSTALL NEW LOCKSET ON EXTERIOR DOOR AT OLD SCIENCE D-23 | 052 | CLOSED | 490.56 | 0 | 507.53 | 507.53
PJ0002548 | REPLACE EXTERIOR DOOR - OLD SCIENCE 52 ROOM D23 (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-08-14 | PA-PRIME AND PAINT NEW DOOR AT OLD SCIENCE D-23 | 052 | CLOSED | 225.64 | 0 | 95.32 | 95.32
PJ0002548 Total | [7 empty] | 1193.1 | 0 | 1387.4 | 1387.4
PJ0002547 | REMOVE CARPET - AG SCIENCE 11 ROOM 104 | GRIFFIN, PATRICK E | CLOSED | 2007-08-14 | AD: FLOOR TEC | 011 | CLOSED | 6802.77 | 0 | 6802.77 | 6802.77
PJ0002547 | REMOVE CARPET - AG SCIENCE 11 ROOM 104 | GRIFFIN, PATRICK E | CLOSED | 2007-08-14 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 680.28 | 0 | 0 | 0
PJ0002547 Total | [7 empty] | 7483.05 | 0 | 6802.77 | 6802.77
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | AD: JOC 07.013.001 MAINO | RESIDENCE | CLOSED | 45816.33 | 0 | 44846.3536 | 44846.3536
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | AD: MECA | RESIDENCE | CLOSED | 0 | 0 | 593.85 | 593.85
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | CA-REMOVE 520 BOOKCASES-SOUTH MOUTAIN DORMS (SEE WO 116610) | RESIDENCE | CLOSED | 0 | 0 | 2694.4732 | 2694.4732
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | CA: REMOVE FURNITURE (MAINT) | RESIDENCE | CLOSED | 0 | 0 | 2886.325 | 2886.325
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | CP: PROJECT CONTINGENCY | RESIDENCE | CLOSED | 4581.63 | 0 | 0 | 0
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | LS: INSTALL CONSTRUCTION CORES (MAINT) | RESIDENCE | CLOSED | 0 | 0 | 95.28 | 95.28
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | PA-PREP AND PAINT WALLS IN SOUTH MOUNTAIN DORMS (SEE WO 116611) | RESIDENCE | CLOSED | 0 | 0 | 2727.4031 | 2727.4031
PJ0002546 | FURNITURE REMOVAL - SOUTH MOUNTAIN TRIPLE OCCUPANCY ROOMS | LAMPMAN, GREG | CLOSED | 2007-08-13 | PA: PREP AND PAINT WALLS (MAINT) | RESIDENCE | CLOSED | 0 | 0 | 2898.07 | 2898.07
PJ0002546 Total | [7 empty] | 50397.96 | 0 | 56741.7549 | 56741.7549
PJ0002541 | REMODEL OF FRONT OFFICE - AG SCIENCE 11 ROOM 211 | POPHAM, DONALD J. | CLOSED | 2007-08-08 | AD: FLOORTEC | 011 | CLOSED | 2454.7298 | 0 | 2483.0741 | 2483.0741
PJ0002541 | REMODEL OF FRONT OFFICE - AG SCIENCE 11 ROOM 211 | POPHAM, DONALD J. | CLOSED | 2007-08-08 | CA: DRILL HOLES/INSTALL TOGGLERS FOR OFFICE FURN. - 011-211 | 011 | CLOSED | 889.4028 | 0 | 110.76 | 110.76
PJ0002541 | REMODEL OF FRONT OFFICE - AG SCIENCE 11 ROOM 211 | POPHAM, DONALD J. | CLOSED | 2007-08-08 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 628.42 | 0 | 0 | 0
PJ0002541 | REMODEL OF FRONT OFFICE - AG SCIENCE 11 ROOM 211 | POPHAM, DONALD J. | CLOSED | 2007-08-08 | EL:SUPPLY POWER TO NEW WORKSTATIONS | 011 | CLOSED | 2064.1974 | 0 | 536.178 | 536.178
PJ0002541 | REMODEL OF FRONT OFFICE - AG SCIENCE 11 ROOM 211 | POPHAM, DONALD J. | CLOSED | 2007-08-08 | ES: RELOCATE THERMOSTAT AT 11-211 | 011 | CLOSED | 487.5437 | 0 | 474.96 | 474.96
PJ0002541 | REMODEL OF FRONT OFFICE - AG SCIENCE 11 ROOM 211 | POPHAM, DONALD J. | CLOSED | 2007-08-08 | IN: OFFICE REMODEL SUPPORT AT AG. SCIENCE ROOM 211 (N/L) | 011 | CLOSED | 227.9894 | 0 | 0 | 0
PJ0002541 Total | [7 empty] | 6752.2831 | 0 | 3604.9721 | 3604.9721
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | AD: DIRECT-PAY PURCHASES | 065 | CLOSED | 0 | 0 | 85.044 | 85.044
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | AD: DIVISION OF STATE ARCHITECT-COSTS POSTED ON OMNI DESIGN PHAS | 065 | CLOSED | 2500 | 0 | 0 | 0
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | AD: JOC 07.015.004 MAINO | 065 | CLOSED | 216991.9982 | 0 | 229963.972 | 229963.972
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | AD: MECA | 065 | CLOSED | 2838.71 | 0 | 6159.99 | 6159.99
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | AD: OMNI DESIGN (DESIGN PHASE 1) | 065 | CLOSED | 23561.4 | 0 | 5906.4 | 5906.4
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | AD: OMNI DESIGN (DESIGN PHASE 2) | 065 | CLOSED | 0 | 0 | 17633.6 | 17633.6
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | CA: REMOVE GYP BOARD NEAR DOOR OPENING | 065 | CLOSED | 0 | 0 | 659.6683 | 659.6683
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | CP: PROJECT CONTINGENCY | 065 | CLOSED | 27469.82 | 0 | 0 | 0
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | CU: FLOOR TILE CLEANING AT STARBUCKS | 065 | CLOSED | 0 | 0 | 172.6636 | 172.6636
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | EL: ELECTRICAL REMODEL OF COFFEE SHOP | 065 | CLOSED | 15302.7 | 0 | 34867.332 | 34867.332
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | EL: SITE INVESTIGATION AT UU65 | 065 | CLOSED | 0 | 0 | 95.166 | 95.166
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | ES: DUCT DISTRIBUTION AT STARBUCK'S | 065 | CLOSED | 5497.248 | 0 | 6339.516 | 6339.516
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | IN: RENOVATION/EXPANSION OF COFFEE VENUE - UU | 065 | CLOSED | 1060.416 | 0 | 629.622 | 629.622
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | LO: INSTALL CONSTR CORE | 065 | CLOSED | 516.672 | 0 | 28.584 | 28.584
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | LS: INSTALL NEW KEY CORES AT STARBUCKS | 065 | CLOSED | 0 | 0 | 229.752 | 229.752
PJ0002539 | RENOVATION AND EXPANSION OF COFFEE VENUE - UU 65 JULIAN'S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-08-08 | PA: STARBUCKS PAINTING | 065 | CLOSED | 5475.36 | 0 | 8329.956 | 8329.956
PJ0002539 Total | [7 empty] | 301214.3242 | 0 | 311101.2659 | 311101.2659
PJ0002538 | EMERGENCY EVACUATION SIGNAGE FOR CPC - BLDGS 15, 19, 65, & 112 | LAMPMAN, GREG | CLOSED | 2007-08-08 | AD: SYSTEK GRAPHIC ARTS | 015 | CLOSED | 2088.5865 | 0 | 2080.1763 | 2080.1763
PJ0002538 | EMERGENCY EVACUATION SIGNAGE FOR CPC - BLDGS 15, 19, 65, & 112 | LAMPMAN, GREG | CLOSED | 2007-08-08 | CP: PROJECT CONTINGENCY | 015 | CLOSED | 29.96 | 0 | 0 | 0
PJ0002538 Total | [7 empty] | 2118.5465 | 0 | 2080.1763 | 2080.1763
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: FISHER SCIENTIFIC - ITEMS TO BE INSTALLED BY JOC | 052 | CLOSED | 0 | 0 | 29311.2162 | 29311.2162
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 05.012.069 STAPLES | 052 | CLOSED | 0 | 0 | 60454.3152 | 60454.3152
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 07.014.009.00/.01/.03 STAPLES | 052 | CLOSED | 0 | 0 | 111221.0751 | 111221.0751
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 07.014.014 STAPLES | 052 | CLOSED | 0 | 0 | 5144.0143 | 5144.0143
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 07.014.015 STAPLES | 052 | CLOSED | 0 | 0 | 15785.5709 | 15785.5709
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 07.014.016 STAPLES | 026 | CLOSED | 0 | 0 | 42963.2392 | 42963.2392
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 07.014.054 STAPLES | 052 | CLOSED | 0 | 0 | 7071.9403 | 7071.9403
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: JOC 07.014.056 STAPLES | 052 | CLOSED | 0 | 0 | 9090.2706 | 9090.2706
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | AD: MECA CONSULTING | 052 | CLOSED | 0 | 0 | 7730.75 | 7730.75
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | CA: REMOVE CABINENTS & INSTALL COUNTER TOPS-SCI 52 RMD17/D19/D26 | 052 | CLOSED | 2215.2 | 0 | 4361.04 | 4361.04
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | CHANGE KEY CORES - SCI 52 RM D8, D9, & D10 | 052 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | CP: PROJECT CONTINGENCY | 052 | CLOSED | 0 | 0 | 0 | 0
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | EL: ADDITIONAL ELECTRICAL OUTLET (QUAD) - SCI 52 RM E48 | 052 | CLOSED | 0 | 0 | 442.086 | 442.086
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | LO: CHANGE CORE TO KEY CORE #71 (71A5 SERIES) - SCI 52 RM D36 | 052 | CLOSED | 0 | 0 | 28.584 | 28.584
PJ0002536 | SP 07/08:OLD SCI INTERIOR DOOR OPENING RENOVATIONS (NO ESTIMATE) | QUEEN, BARBARA | CLOSED | 2007-08-07 | PL: CHECK/ INSTALL NEW EYEWASH & SAFETY SHOWER SCI 52 SEE TASK | 052 | CLOSED | 0 | 0 | 29131.3266 | 29131.3266
PJ0002536 Total | [7 empty] | 2215.2 | 0 | 322792.5964 | 322792.5964
PJ0002534 | SR 07/08 PAINT EXTERIOR DAMAGED AREA-MUSIC 45 (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-08-07 | AD: JOC 07.013.015 MAINO | 045 | CLOSED | 29061.38 | 0 | 29061.38 | 29061.38
PJ0002534 | SR 07/08 PAINT EXTERIOR DAMAGED AREA-MUSIC 45 (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-08-07 | AD: MECA | 045 | CLOSED | 4795 | 0 | 4445 | 4445
PJ0002534 | SR 07/08 PAINT EXTERIOR DAMAGED AREA-MUSIC 45 (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-08-07 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 3410.14 | 0 | 0 | 0
PJ0002534 | SR 07/08 PAINT EXTERIOR DAMAGED AREA-MUSIC 45 (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-08-07 | GR: CLEAR AREA FOR SCAFFOLDING (MATERIALS, ONLY) | 045 | CLOSED | 134.56 | 0 | 61.94 | 61.94
PJ0002534 | SR 07/08 PAINT EXTERIOR DAMAGED AREA-MUSIC 45 (ENC. BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-08-07 | IN: SR 07/08 PAINT EXTERIOR DAMAGED AREA-MUSIC 45 (NO LABOR) | 045 | CLOSED | 110.46 | 0 | 0 | 0
PJ0002534 Total | [7 empty] | 37511.54 | 0 | 33568.32 | 33568.32
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: ALTHOUSE & MEADE ENVIRONMENTAL | 009 | CLOSED | 1134 | 0 | 1134 | 1134
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: EARTH SYSTEMS PACIFIC | 009 | CLOSED | 622.33 | 0 | 413.75 | 413.75
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: JOC 07.015.009 MAINO | 009 | CLOSED | 144734.54 | 0 | 144734.54 | 144734.54
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: JOC 08.017.010 MAINO | 009 | CLOSED | 174208.72 | 0 | 174208.72 | 174208.72
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: JOC 08.018.020.00 MAINO | 009 | CLOSED | 81411.81 | 0 | 81411.81 | 81411.81
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: SEISMIC PEER REVIEW - ENGLEKIRK AND SABOL | 009 | CLOSED | 1500 | 0 | 660 | 660
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | AD: THE LAND CONSERVANCY | 009 | CLOSED | 2300 | 0 | 2050 | 2050
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | CA: PATCH CONCRETE WALKWAY NEAR BLG. 18M | 018M | CLOSED | 138.45 | 0 | 172.25 | 172.25
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | CP: PROJECT CONTINGENCY | 009 | CLOSED | 0 | 0 | 0 | 0
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | EH&S: OVERSEE WORK IN CREEK FOR METAL BLG BEHIND FARM SHOP (N/L) | 009 | CLOSED | 2163.2 | 0 | 1867.6 | 1867.6
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | EH&S: PROVIDE HAZ MAT INSPECTION SERVICES FOR FEMA PROJECT(N/L) | 009 | CLOSED | 865.28 | 0 | 0 | 0
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | EL: PHASE II - DEMO ELECTRICAL IN FARM SHOP STORAGE BLG. | 009 | CLOSED | 105.74 | 0 | 113.51 | 113.51
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | EL:PHASE 1 INSTALL POWER TO NEW BUILDING | 009 | CLOSED | 1586.1 | 0 | 3224.36 | 3224.36
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | EO:TRENCH FOR UNDER GROUND ELECTRICAL | 009 | CLOSED | 1158.6 | 0 | 2045.83 | 2045.83
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | IN: SR 07/08 REPLACE METAL BUILDING - FARM SHOP 09 | 009 | CLOSED | 276.15 | 0 | 193.305 | 193.305
PJ0002532 | SR 08/09:REPLACE METAL BLDG (FEMA)-FARM SHOP 09(ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-08-07 | LO:INSTALL CORE AT WALK DOOR | 009 | CLOSED | 190.56 | 0 | 77.64 | 77.64
PJ0002532 Total | [7 empty] | 412395.48 | 0 | 412307.315 | 412307.315
PJ0002531 | SR 08/09: FALL PROTECTION - GENERAL CAMPUS (ENC. BY 6/30/09) | MOLLAN, CHERYL L. | CLOSED | 2007-08-06 | AD: CREDIT CARD PURCHASE FROM FALL-ARREST.COM | GENERAL | CLOSED | 0 | 0 | 69.82 | 69.82
PJ0002531 | SR 08/09: FALL PROTECTION - GENERAL CAMPUS (ENC. BY 6/30/09) | MOLLAN, CHERYL L. | CLOSED | 2007-08-06 | AD: FLEXIBLE LIFELINE SYSTEM | GENERAL | CLOSED | 45046.07 | 0 | 44652.29 | 44652.29
PJ0002531 | SR 08/09: FALL PROTECTION - GENERAL CAMPUS (ENC. BY 6/30/09) | MOLLAN, CHERYL L. | CLOSED | 2007-08-06 | AD: JOC 07.015.040 MAINO | GENERAL | CLOSED | 8211.8 | 0 | 8211.8 | 8211.8
PJ0002531 | SR 08/09: FALL PROTECTION - GENERAL CAMPUS (ENC. BY 6/30/09) | MOLLAN, CHERYL L. | CLOSED | 2007-08-06 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 5336.83 | 0 | 0 | 0
PJ0002531 | SR 08/09: FALL PROTECTION - GENERAL CAMPUS (ENC. BY 6/30/09) | MOLLAN, CHERYL L. | CLOSED | 2007-08-06 | IN: SR 07/08 FALL PROTECTION - GENERAL CAMPUS (N/L) | GENERAL | CLOSED | 110.46 | 0 | 0 | 0
PJ0002531 Total | [7 empty] | 58705.16 | 0 | 52933.91 | 52933.91
PJ0002529 | INSTALLATION OF AIR CONDITIONING SYSTEM - AG SCI 11 ROOM 115 | BISCHEL, JOSEPH W | CLOSED | 2007-08-02 | CA: SUPPORT FOR NEW H.VA.C. SYSTEM INSTALLATION | 011 | CLOSED | 344.1942 | 0 | 889.5246 | 889.5246
PJ0002529 | INSTALLATION OF AIR CONDITIONING SYSTEM - AG SCI 11 ROOM 115 | BISCHEL, JOSEPH W | CLOSED | 2007-08-02 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 1464.81 | 0 | 0 | 0
PJ0002529 | INSTALLATION OF AIR CONDITIONING SYSTEM - AG SCI 11 ROOM 115 | BISCHEL, JOSEPH W | CLOSED | 2007-08-02 | EL:INSTALL SERVICE TO NEW H.V.A.C. SYSTEM | 011 | CLOSED | 2466.6133 | 0 | 1146.2064 | 1146.2064
PJ0002529 | INSTALLATION OF AIR CONDITIONING SYSTEM - AG SCI 11 ROOM 115 | BISCHEL, JOSEPH W | CLOSED | 2007-08-02 | ES: INSTALL NEW A/C SYSTEM | 011 | CLOSED | 11705.3318 | 0 | 14352.036 | 14352.036
PJ0002529 | INSTALLATION OF AIR CONDITIONING SYSTEM - AG SCI 11 ROOM 115 | BISCHEL, JOSEPH W | CLOSED | 2007-08-02 | IN: INSTALL AIR CONDITIONING SYSTEM - AG SCI 11-115 (NO LABOR) | 011 | CLOSED | 132.552 | 0 | 0 | 0
PJ0002529 Total | [7 empty] | 16113.5014 | 0 | 16387.767 | 16387.767
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CP: PROJECT CONTINGENCY | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 10/11/07 ANIMAL SCIENCE ADVISORY COUNCIL | 051 | CLOSED | 0 | 0 | 150.315 | 150.315
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 10/19/07 CAL POLY SCHOLARS LUNCHEON | 051 | CLOSED | 0 | 0 | 293.7975 | 293.7975
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 10/25/07 COLLEGE OF ED FACULTY SOCIAL HOUR 4PM | 051 | CLOSED | 0 | 0 | 116.1525 | 116.1525
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 10/25/07 ISAAC BARPAL SIGNING 12PM - 2PM | 051 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 10/6/07 MARY STUART ROGERS RECEPTION 5PM-6PM | 051 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 11/15/07 FACULTY SOCIAL HOUR 4PM - 6PM | 051 | CLOSED | 0 | 0 | 13.665 | 13.665
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 11/15/07 RABOBANK LUNCHEON | 051 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 11/9/07 ALUMNI BOARD OF DIRECTORS LUNCHEON | 051 | CLOSED | 0 | 0 | 136.65 | 136.65
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 8/29/07 2PM-4PM DEAN'S ASSISTANTS RECEPTION | 051 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/10/07 11:30AM-2PM FALL CONFERENCE LUNCHEON | 051 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/10/07 5PM-7PM NEW FACULTY/STAFF RECEPTION | 051 | CLOSED | 0 | 0 | 27.33 | 27.33
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/16/07 2PM - 4PM WOMEN'S CLUB WELCOME | 051 | CLOSED | 0 | 0 | 218.64 | 218.64
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/25/07 SIERRA PACIFIC INDUSTRIES LUNCHEON | 051 | CLOSED | 0 | 0 | 218.64 | 218.64
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/26/07 MEDIA RECEPTION 10AM -12 NOON | 051 | CLOSED | 0 | 0 | 218.64 | 218.64
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/27/07 FACULTY SOCIAL HOUR - SCIENCE AND MATH | 051 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/29/07 HALL OF FAME PRE-GAME RECEPTION | 051 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 9/6/07 7:30AM -2PM DEAN'S RETREAT | 051 | CLOSED | 0 | 0 | 27.33 | 27.33
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 MISC CLEANING 2007/2008 - CLOSE N/L | 051 | CLOSED | 0 | 0 | 11685.5475 | 11685.5475
PJ0002528 | 07/08 CUSTODIAL SERVICE FOR UNIVERSITY HOUSE 51 (NO ESTIMATE) | RAMLER, THOMAS JORDAN | CLOSED | 2007-08-02 | CU: UH 51 TENT CLEANING (BEFORE DECEMBER 7, 2007) (N/L) | 051 | CLOSED | 0 | 0 | 0 | 0
PJ0002528 Total | [7 empty] | 0 | 0 | 13707.9675 | 13707.9675
PJ0002527 | SR 08/09:REPLACE CONTROLS-2 BOILERS-ENGR S. 40 (ENC. BY 6/30/09) | ELLIOT, DENNIS K | CLOSED | 2007-08-01 | AD: RF MACDONALD | 040 | CLOSED | 127896.42 | 0 | 128309.7 | 128309.7
PJ0002527 | SR 08/09:REPLACE CONTROLS-2 BOILERS-ENGR S. 40 (ENC. BY 6/30/09) | ELLIOT, DENNIS K | CLOSED | 2007-08-01 | CP: PROJECT CONTINGENCY | 040 | CLOSED | 200 | 0 | 0 | 0
PJ0002527 Total | [7 empty] | 128096.42 | 0 | 128309.7 | 128309.7
PJ0002524 | REPAINT FOOTBALL GOAL POSTS - SPANOS STADIUM 61 | ALTON, JOSHUA R | CLOSED | 2007-08-01 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 43.87 | 0 | 0 | 0
PJ0002524 | REPAINT FOOTBALL GOAL POSTS - SPANOS STADIUM 61 | ALTON, JOSHUA R | CLOSED | 2007-08-01 | PA:PAINT OUT GOAL POSTS | 061 | CLOSED | 472.344 | 0 | 333.564 | 333.564
PJ0002524 Total | [7 empty] | 516.214 | 0 | 333.564 | 333.564
PJ0002521 | MJ:PROVIDE WATER TO OBJET PARTS WASHER & DRAIN - ENGR IV 192-119 | RIVERA, MARIO L | CLOSED | 2007-08-01 | CA: ENG.4 ROOM 119 ASSIST PLUMBERS WITH FLOOR SINK INSTALLATION | 192 | CLOSED | 3858.24 | 0 | 1388.592 | 1388.592
PJ0002521 | MJ:PROVIDE WATER TO OBJET PARTS WASHER & DRAIN - ENGR IV 192-119 | RIVERA, MARIO L | CLOSED | 2007-08-01 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 846.25 | 0 | 0 | 0
PJ0002521 | MJ:PROVIDE WATER TO OBJET PARTS WASHER & DRAIN - ENGR IV 192-119 | RIVERA, MARIO L | CLOSED | 2007-08-01 | IN:PROVIDE WATER TO OBJET PARTS WASHER & DRAIN - ENGR IV 192-119 | 192 | CLOSED | 132.552 | 0 | 66.276 | 66.276
PJ0002521 | MJ:PROVIDE WATER TO OBJET PARTS WASHER & DRAIN - ENGR IV 192-119 | RIVERA, MARIO L | CLOSED | 2007-08-01 | PA: PREP WALL AND PAINT ENG. 4 ROOM 119 | 192 | CLOSED | 1672.608 | 0 | 554.796 | 554.796
PJ0002521 | MJ:PROVIDE WATER TO OBJET PARTS WASHER & DRAIN - ENGR IV 192-119 | RIVERA, MARIO L | CLOSED | 2007-08-01 | PL: ENG 4 ROOM 119 INSTALL FLOOR SINK FOR OBJECT WASHER | 192 | CLOSED | 4491.648 | 0 | 2359.008 | 2359.008
PJ0002521 Total | [7 empty] | 11001.298 | 0 | 4368.672 | 4368.672
PJ0002520 | CONVERT STORAGE RM INTO SMALL WORK AREA - FAC PLAN 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2007-08-01 | CA: REMOVE DOOR AND INSTALL WINDOW 70-205 | 070 | CLOSED | 1347.6 | 0 | 1744.638 | 1744.638
PJ0002520 | CONVERT STORAGE RM INTO SMALL WORK AREA - FAC PLAN 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2007-08-01 | CP: PROJECT CONTINGENCY | 070 | CLOSED | 320.7 | 0 | 0 | 0
PJ0002520 | CONVERT STORAGE RM INTO SMALL WORK AREA - FAC PLAN 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2007-08-01 | EL: CHANGE LIGHT FIXTURE AND INSTALL OUTLET 70-205 | 070 | CLOSED | 1004.772 | 0 | 385.116 | 385.116
PJ0002520 | CONVERT STORAGE RM INTO SMALL WORK AREA - FAC PLAN 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2007-08-01 | IN: CONVERT STORAGE RM TO SMALL WORKAREA-FAC PLAN 70 RM 205(N/L) | 070 | CLOSED | 66.276 | 0 | 0 | 0
PJ0002520 | CONVERT STORAGE RM INTO SMALL WORK AREA - FAC PLAN 70 RM 205 | GRIFFIN, PATRICK E | CLOSED | 2007-08-01 | PA: PATCH HOLES/PAINT DOOR TRIM AND ROOM 70-205 | 070 | CLOSED | 788.304 | 0 | 1375.008 | 1375.008
PJ0002520 Total | [7 empty] | 3527.652 | 0 | 3504.762 | 3504.762
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: FALL CONFERENCE 9/10/07 8:30AM-11AM (NO LABOR) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: FESTIVAL ORCHESTRA JUL 22 3PM | 006 | CLOSED | 0 | 0 | 163.98 | 163.98
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: GEORGE CARLIN SEPT 29 7PM & 9:30PM | 006 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: JESUS CHRIST SUPERSTAR AUG 11 & AUG 12 | 006 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: PETER PAN JULY 21 (2PM & 7PM) AND JULY 22 2007 (2PM) | 006 | CLOSED | 0 | 0 | 0 | 0
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: SLO SYMPHONY NOV 10 1PM AND 8PM | 006 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002517 | 07/08 CUSTODIAL SUPPORT - EVENTS AT PAC 06 (MAINT) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: SLO SYMPHONY OCT 6 1PM AND 8PM | 006 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002517 Total | [7 empty] | 0 | 0 | 382.62 | 382.62
PJ0002514 | SR 08/09:ENGINEER/DESIGN PAC RETAINING WALL (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-07-31 | AD: BUEHLER AND BUEHLER | GENERAL | CLOSED | 18560 | 0 | 14260 | 14260
PJ0002514 | SR 08/09:ENGINEER/DESIGN PAC RETAINING WALL (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-07-31 | AD: GSI SOILS | GENERAL | CLOSED | 7700 | 0 | 7700 | 7700
PJ0002514 | SR 08/09:ENGINEER/DESIGN PAC RETAINING WALL (ENC. BY 6/30/09) | LAMPMAN, GREG | CLOSED | 2007-07-31 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 2040.45 | 0 | 0 | 0
PJ0002514 Total | [7 empty] | 28300.45 | 0 | 21960 | 21960
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE - AUG 21 11:30AM-1:30PM EVENT (N/L) | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 1/26/08 CLA DEAN'S COUNCIL 7:30AM -5PM | 061 | CLOSED | 0 | 0 | 232.305 | 232.305
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 10/17/07 UNIVERSITY ADVANCEMENT SOCCER | 061 | CLOSED | 0 | 0 | 327.96 | 327.96
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 10/23/07 CALCPA RECEPTION 5:30PM-7:30PM | 061 | CLOSED | 0 | 0 | 273.3 | 273.3
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 11/16/07 POLY REPS SOCCER GAME 6:30 PM | 061 | CLOSED | 0 | 0 | 109.32 | 109.32
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 11/17/07 IONA PRE GAME RECEPTION 12PM-1PM | 061 | CLOSED | 0 | 0 | 54.66 | 54.66
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 9/15/07 POLY VS WEBER STATE 5PM | 061 | CLOSED | 0 | 0 | 553.845 | 553.845
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 9/22/07 POLY VS W OREGON 5PM | 061 | CLOSED | 0 | 0 | 248.56 | 248.56
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE 9/29/07 POLY VS N COLORADO 4PM | 061 | CLOSED | 0 | 0 | 437.28 | 437.28
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITE EXHIBITION GAME 8/21/07 6PM-9PM | 061 | CLOSED | 0 | 0 | 282.96 | 282.96
PJ0002513 | 07/08 STADIUM SUITES - CUSTODIAL SUPPORT (ALSO SEE WO0113034) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-31 | CU: STADIUM SUITES - MISC CLEANING 2007/2008 - CLOSE N/L | 061 | CLOSED | 0 | 0 | 10847.1513 | 10847.1513
PJ0002513 Total | [7 empty] | 0 | 0 | 13367.3413 | 13367.3413
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 0/7/08 VOLLEYBALL - SEPT 21 LONG BEACH STATE 7PM | GENERAL | CLOSED | 0 | 0 | 196.776 | 196.776
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - FEB 1 VS FRESNO 7PM | GENERAL | CLOSED | 0 | 0 | 149.0088 | 149.0088
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - FEB 2 VS SAC STATE 5:30 PM (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - NOV 16 UC RIVERSIDE 7PM | GENERAL | CLOSED | 0 | 0 | 574.3422 | 574.3422
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - NOV 17 UC IRVINE 7PM | GENERAL | CLOSED | 0 | 0 | 398.4936 | 398.4936
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - NOV 8 UC SANTA BARBARA 7PM | GENERAL | CLOSED | 0 | 0 | 622.4638 | 622.4638
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - OCT 26 UNIVERSITY OF PACIFIC 7PM | GENERAL | CLOSED | 0 | 0 | 395.01 | 395.01
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - OCT 27 UC DAVIS 7PM | GENERAL | CLOSED | 0 | 0 | 463.014 | 463.014
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - OCT 5 CAL STATE FULLERTON 7PM | GENERAL | CLOSED | 0 | 0 | 180.0096 | 180.0096
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - SEPT 18 GREEN/GOLD GAME 7PM | GENERAL | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | CU: 07/08 VOLLEYBALL - SEPT 22 CAL STATE NORTHRIDGE 7PM | GENERAL | CLOSED | 0 | 0 | 131.184 | 131.184
PJ0002512 | 07/08 VOLLEYBALL (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-30 | ES: TURN ON FANS IN MOTT GYM FOR ALL 07/08 VOLLEYBALL GAMES | 042 | CLOSED | 0 | 0 | 0 | 0
PJ0002512 Total | [7 empty] | 0 | 0 | 3241.486 | 3241.486
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - AUG 21 CALIFORNIA (EXHIBITION) 7PM | GENERAL | CLOSED | 0 | 0 | 1160.2318 | 1160.2318
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - NOV 16 PORTLAND 7PM | GENERAL | CLOSED | 0 | 0 | 960.5578 | 960.5578
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - NOV 18 CAL STATE FULLERTON 1PM | GENERAL | CLOSED | 0 | 0 | 422.403 | 422.403
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - NOV 7 CAL STATE NORTHRIDGE 7PM | GENERAL | CLOSED | 0 | 0 | 640.401 | 640.401
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - OCT 10 UC IRVINE 7PM | GENERAL | CLOSED | 0 | 0 | 425.9796 | 425.9796
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - OCT 14 UC DAVIS 1PM | GENERAL | CLOSED | 0 | 0 | 208.257 | 208.257
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - OCT 17 UC SANTA BARBARA 7PM | GENERAL | CLOSED | 0 | 0 | 180.096 | 180.096
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - OCT 27 UC RIVERSIDE 7PM | GENERAL | CLOSED | 0 | 0 | 1188.396 | 1188.396
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - SEPT 18 WRIGHT STATE 7PM | GENERAL | CLOSED | 0 | 0 | 147.096 | 147.096
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - SEPT 23 CAL STATE BAKERSFIELD 1PM | GENERAL | CLOSED | 0 | 0 | 843.9511 | 843.9511
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | CU: MEN'S SOCCER - SEPT 9 WISCONSIN-MILWAUKEE 1PM | GENERAL | CLOSED | 0 | 0 | 165.7993 | 165.7993
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: 07/08 MEN'S SOCCER PRACTICE LINING WORK | GENERAL | CLOSED | 0 | 0 | 565.152 | 565.152
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - AUG 21 CALIFORNIA (EXHIBITION) 7PM (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - NOV 16 PORTLAND 7PM | GENERAL | CLOSED | 0 | 0 | 329.49 | 329.49
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - NOV 18 CAL STATE FULLERTON 1PM | GENERAL | CLOSED | 0 | 0 | 46.308 | 46.308
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - NOV 7 CAL STATE NORTHRIDGE 7PM | GENERAL | CLOSED | 0 | 0 | 288.516 | 288.516
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - OCT 10 UC IRVINE 7PM | GENERAL | CLOSED | 0 | 0 | 181.656 | 181.656
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - OCT 14 UC DAVIS 1PM | GENERAL | CLOSED | 0 | 0 | 40.368 | 40.368
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - OCT 17 UC SANTA BARBARA 7PM | GENERAL | CLOSED | 0 | 0 | 282.576 | 282.576
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - OCT 27 UC RIVERSIDE 7PM (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - SEPT 18 WRIGHT STATE 7PM | GENERAL | CLOSED | 0 | 0 | 504.6 | 504.6
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - SEPT 23 CAL STATE BAKERSFIELD 1PM | GENERAL | CLOSED | 0 | 0 | 69.462 | 69.462
PJ0002510 | 07/08 MEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-25 | GR: MEN'S SOCCER - SEPT 9 WISCONSIN-MILWAUKEE 1PM | GENERAL | CLOSED | 0 | 0 | 80.736 | 80.736
PJ0002510 Total | [7 empty] | 0 | 0 | 8732.0325 | 8732.0325
PJ0002509 | INSTALL WALL AND PAINT WALLS - DEXTER 34 ROOM 166 | MOLLAN, CHERYL L. | CLOSED | 2007-07-25 | CA:INSTALL NEW WALL | 034 | CLOSED | 1407.6 | 0 | 1627.212 | 1627.212
PJ0002509 | INSTALL WALL AND PAINT WALLS - DEXTER 34 ROOM 166 | MOLLAN, CHERYL L. | CLOSED | 2007-07-25 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 463.26 | 0 | 0 | 0
PJ0002509 | INSTALL WALL AND PAINT WALLS - DEXTER 34 ROOM 166 | MOLLAN, CHERYL L. | CLOSED | 2007-07-25 | EL:INSTALL NEW ELECTRICAL IN WALL | 034 | CLOSED | 1001.328 | 0 | 1037.088 | 1037.088
PJ0002509 | INSTALL WALL AND PAINT WALLS - DEXTER 34 ROOM 166 | MOLLAN, CHERYL L. | CLOSED | 2007-07-25 | ES:INSTALL NEW DUCTWORK WITH NEW RETURN | 034 | CLOSED | 1034.447 | 0 | 213.3 | 213.3
PJ0002509 | INSTALL WALL AND PAINT WALLS - DEXTER 34 ROOM 166 | MOLLAN, CHERYL L. | CLOSED | 2007-07-25 | IN: INSTALL WALL AND PAINT WALLS - DEXTER 34 ROOM 166 (NO LABOR) | 034 | CLOSED | 331.38 | 0 | 0 | 0
PJ0002509 Total | [7 empty] | 4238.015 | 0 | 2877.6 | 2877.6
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - AUG 18 WESTMONT (SCRIMMAGE) 1PM | GENERAL | CLOSED | 0 | 0 | 254.1429 | 254.1429
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - AUG 31 DAYTON 7PM | GENERAL | CLOSED | 0 | 0 | 497.736 | 497.736
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - OCT 14 CAL STATE BAKERSFIELD 3:30PM | GENERAL | CLOSED | 0 | 0 | 171.0238 | 171.0238
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - OCT 26 UC DAVIS 7PM | GENERAL | CLOSED | 0 | 0 | 245.97 | 245.97
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - OCT 28 PACIFIC 1PM | GENERAL | CLOSED | 0 | 0 | 615.42 | 615.42
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - OCT 5 UC RIVERSIDE 7PM | GENERAL | CLOSED | 0 | 0 | 421.431 | 421.431
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - OCT 7 CAL STATE FULLERTON 1PM | GENERAL | CLOSED | 0 | 0 | 976.176 | 976.176
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - SEPT 2 ARIZONA 1PM | GENERAL | CLOSED | 0 | 0 | 176.0979 | 176.0979
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | CU 07/08: WOMEN'S SOCCER - SEPT 28 SANTA CLARA UNIV 7PM | GENERAL | CLOSED | 0 | 0 | 180.0096 | 180.0096
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | EL: REPAIR SCOREBOARD BEFORE AUGUST 31 SOCCER GAME | GENERAL | CLOSED | 0 | 0 | 317.22 | 317.22
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - AUG 18TH WESTMONT SCRIMMAGE 1PM | GENERAL | CLOSED | 0 | 0 | 444.048 | 444.048
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - AUG 31 DAYTON 7PM | GENERAL | CLOSED | 0 | 0 | 574.062 | 574.062
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - OCT 14 CAL STATE BAKERSFIELD 3:30PM | GENERAL | CLOSED | 0 | 0 | 40.368 | 40.368
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - OCT 26 UC DAVIS 7PM | GENERAL | CLOSED | 0 | 0 | 282.576 | 282.576
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - OCT 28 PACIFIC 1PM (NO LABOR) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - OCT 5 UC RIVERSIDE 7PM | GENERAL | CLOSED | 0 | 0 | 318.792 | 318.792
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - OCT 7 CAL STATE FULLERTON 1PM | GENERAL | CLOSED | 0 | 0 | 70.644 | 70.644
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - SEPT 2 ARIZONA 1PM | GENERAL | CLOSED | 0 | 0 | 121.104 | 121.104
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR 07/08: WOMEN'S SOCCER - SEPT 28 SANTA CLAR UNIV 7PM | GENERAL | CLOSED | 0 | 0 | 423.864 | 423.864
PJ0002508 | 07/08 WOMEN'S SOCCER (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-24 | GR: 07/08 WOMEN'S SOCCER PRACTICE LINING WORK | GENERAL | CLOSED | 0 | 0 | 2856.036 | 2856.036
PJ0002508 Total | [7 empty] | 0 | 0 | 8986.7212 | 8986.7212
PJ0002507 | SR 07/08 RE-ROOF DANCE STUDIO-CRANDALL 60 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-23 | AD: JOC 07.013.007 MAINO | 060 | CLOSED | 93208.38 | 0 | 93208.38 | 93208.38
PJ0002507 | SR 07/08 RE-ROOF DANCE STUDIO-CRANDALL 60 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-23 | AD: MECA | 060 | CLOSED | 2500 | 0 | 2425 | 2425
PJ0002507 | SR 07/08 RE-ROOF DANCE STUDIO-CRANDALL 60 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-23 | CP: PROJECT CONTINGENCY | 060 | CLOSED | 9570.84 | 0 | 0 | 0
PJ0002507 Total | [7 empty] | 105279.22 | 0 | 95633.38 | 95633.38
PJ0002503 | SR 07/08 R/R CLAY&MAIN GATE VALVES-PUMPHSE 1 (ENC. BY 6/30/08) | RIVERA, MARIO L | CLOSED | 2007-07-20 | CA: ASSIST PLUMBERS WITH CLA VALVE/MAIN GATE VALVE - PUMPHOUSE 1 | 201 | CLOSED | 0 | 0 | 1165.225 | 1165.225
PJ0002503 | SR 07/08 R/R CLAY&MAIN GATE VALVES-PUMPHSE 1 (ENC. BY 6/30/08) | RIVERA, MARIO L | CLOSED | 2007-07-20 | CP: PROJECT CONTINGENCY | 201 | CLOSED | 1785.72 | 0 | 0 | 0
PJ0002503 | SR 07/08 R/R CLAY&MAIN GATE VALVES-PUMPHSE 1 (ENC. BY 6/30/08) | RIVERA, MARIO L | CLOSED | 2007-07-20 | EL: ASSIST PLUMBERS WITH CLA VALVE/MAIN GATE VALVE - PUMPHOUSE 1 | 201 | CLOSED | 0 | 0 | 185.045 | 185.045
PJ0002503 | SR 07/08 R/R CLAY&MAIN GATE VALVES-PUMPHSE 1 (ENC. BY 6/30/08) | RIVERA, MARIO L | CLOSED | 2007-07-20 | EO: ASSIST PLUMBERS WITH CLA VALVE/MAIN GATE VALVE - PUMPHOUSE 1 | 201 | CLOSED | 0 | 0 | 1771.98 | 1771.98
PJ0002503 | SR 07/08 R/R CLAY&MAIN GATE VALVES-PUMPHSE 1 (ENC. BY 6/30/08) | RIVERA, MARIO L | CLOSED | 2007-07-20 | PL: REPLACE CLAY VALVE AND MAIN GATE VALVE - PUMPHOUSE 1 | 201 | CLOSED | 17857.1648 | 0 | 19008.3 | 19008.3
PJ0002503 Total | [7 empty] | 19642.8848 | 0 | 22130.55 | 22130.55
PJ0002502 | SR 08/09: FIRE SPRINKLER SYSTEM - NEW RESIDENCE - BEEF UNIT | MAY, TOM | CLOSED | 2007-07-20 | AD: JOC 07.015.014 MAINO | GENERAL | CLOSED | 18128.88 | 0 | 18128.88 | 18128.88
PJ0002502 | SR 08/09: FIRE SPRINKLER SYSTEM - NEW RESIDENCE - BEEF UNIT | MAY, TOM | CLOSED | 2007-07-20 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0.44 | 0 | 0 | 0
PJ0002502 | SR 08/09: FIRE SPRINKLER SYSTEM - NEW RESIDENCE - BEEF UNIT | MAY, TOM | CLOSED | 2007-07-20 | IN: SR 07/08 ADD SPRINKLER SYSTEM AT NEW RESIDENCE - BEEF UNIT | GENERAL | CLOSED | 55.23 | 0 | 27.615 | 27.615
PJ0002502 | SR 08/09: FIRE SPRINKLER SYSTEM - NEW RESIDENCE - BEEF UNIT | MAY, TOM | CLOSED | 2007-07-20 | PL: ASSIST WITH FIRE SPRINKLER PROJECT AT BEEF UNIT | GENERAL | CLOSED | 1762.58 | 0 | 423.84 | 423.84
PJ0002502 Total | [7 empty] | 19947.13 | 0 | 18580.335 | 18580.335
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CA: DROP OFF A-FRAMES, STANCHIONS & BOARDS - FOOTBALL SEASON 07 | GENERAL | CLOSED | 0 | 0 | 1857.336 | 1857.336
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CA: INSTALL TEMP HANDICAP VIEWING AREA - STADIUM 61 | GENERAL | CLOSED | 0 | 0 | 8373.384 | 8373.384
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CA: MAKE NEW DRAIN COVERS AT SPANOS STADIUM BEFORE 8/18/07 | GENERAL | CLOSED | 0 | 0 | 1027.464 | 1027.464
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CU 07/08: PRELIMINARY WORK FOR FOOTBALL SEASON | GENERAL | CLOSED | 0 | 0 | 1672.596 | 1672.596
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CU: 07/08 FOOTBALL - NOV 10 NORTH DAKOTA (HOMECOMING) | GENERAL | CLOSED | 0 | 0 | 2440.365 | 2440.365
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CU: 07/08 FOOTBALL - NOV 17 IONA COLLEGE | GENERAL | CLOSED | 0 | 0 | 3221.2288 | 3221.2288
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CU: 07/08 FOOTBALL - SEPT 15 WEBER STATE | GENERAL | CLOSED | 0 | 0 | 2947.453 | 2947.453
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CU: 07/08 FOOTBALL - SEPT 22 WESTERN OREGON | GENERAL | CLOSED | 0 | 0 | 3616.3992 | 3616.3992
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | CU: 07/08 FOOTBALL - SEPT 29 NORTHERN COLORADO | GENERAL | CLOSED | 0 | 0 | 2010.9554 | 2010.9554
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL 07/08: PRELIMINARY WORK FOR FOOTBALL SEASON | GENERAL | CLOSED | 0 | 0 | 253.776 | 253.776
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: 07/08 FOOTBALL - NOV 10 NORTH DAKOTA (HOMECOMING) | GENERAL | CLOSED | 0 | 0 | 755.8142 | 755.8142
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: 07/08 FOOTBALL - NOV 17 IONA COLLEGE | GENERAL | CLOSED | 0 | 0 | 717.444 | 717.444
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: 07/08 FOOTBALL - SEPT 15 WEBER STATE | GENERAL | CLOSED | 0 | 0 | 1487.7552 | 1487.7552
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: 07/08 FOOTBALL - SEPT 22 WESTERN OREGON | GENERAL | CLOSED | 0 | 0 | 1180.1623 | 1180.1623
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: 07/08 FOOTBALL - SEPT 29 NORTHERN COLORADO | GENERAL | CLOSED | 0 | 0 | 400.224 | 400.224
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: CHANGE LIGHTS ON SCOREBOARD - SPANOS STADIUM 61 | GENERAL | CLOSED | 0 | 0 | 126.888 | 126.888
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | EL: INSTALL DRIVER FOR SCOREBOARD AT SPANOS STADIUM 61 | GENERAL | CLOSED | 0 | 0 | 190.332 | 190.332
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR 07/08: PRELIMINARY WORK FOR FOOTBALL SEASON | GENERAL | CLOSED | 0 | 0 | 7844.0753 | 7844.0753
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: 07/08 FOOTBALL - NOV 10 NORTH DAKOTA (HOMECOMING) | GENERAL | CLOSED | 0 | 0 | 8318.838 | 8318.838
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: 07/08 FOOTBALL - NOV 17 IONA COLLEGE | GENERAL | CLOSED | 0 | 0 | 3764.346 | 3764.346
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: 07/08 FOOTBALL - SEPT 15 WEBER STATE | GENERAL | CLOSED | 0 | 0 | 8558.136 | 8558.136
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: 07/08 FOOTBALL - SEPT 22 WESTERN OREGON | GENERAL | CLOSED | 0 | 0 | 3506.8123 | 3506.8123
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: 07/08 FOOTBALL - SEPT 29 NORTHERN COLORADO | GENERAL | CLOSED | 0 | 0 | 4058.802 | 4058.802
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: 07/08 SET-UP PRTABLE FNCING BEFORE TUES 8/21 CLOSE (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | GR: ATHLETIC FACILITY MAINTENANCE - 2007 FOOTBALL SEASON (N/L) | GENERAL | CLOSED | 0 | 0 | 416.472 | 416.472
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | PL 07/08: PRELIMINARY WORK FOR FOOTBALL SEASON | GENERAL | CLOSED | 0 | 0 | 1472.526 | 1472.526
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | RC: DELIVER DUMPSTER - H-1 LOT FOR 9/15 FOOTBALL TAILGATE PARTY | GENERAL | CLOSED | 0 | 0 | 75.984 | 75.984
PJ0002500 | 07/08 FOOTBALL SEASON (SERVICES FOR ATHLETICS) | RAMLER, THOMAS JORDAN | CLOSED | 2007-07-19 | RC: TRASH AND RECYCLING SERVICES 2007 FOOTBALL SEASON | GENERAL | CLOSED | 0 | 0 | 1013.316 | 1013.316
PJ0002500 Total | [7 empty] | 0 | 0 | 71308.8847 | 71308.8847
PJ0002499 | JOC ESTIMATE TO REPLACE CONDUIT SUPPORTS - AVILA PIER 228 | PAHLOW, BOB | CLOSED | 2007-07-18 | AD: JOC 07.013.013 MAINO | 228 | CLOSED | 42700.9929 | 0 | 42700.9929 | 42700.9929
PJ0002499 | JOC ESTIMATE TO REPLACE CONDUIT SUPPORTS - AVILA PIER 228 | PAHLOW, BOB | CLOSED | 2007-07-18 | CP: PROJECT CONTINGENCY | 228 | CLOSED | 4270.09 | 0 | 0 | 0
PJ0002499 Total | [7 empty] | 46971.0829 | 0 | 42700.9929 | 42700.9929
PJ0002498 | UPGRADE KITCHEN VENTING HOOD - ASI CHILDREN'S CTR 133 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-17 | AD: MID COAST FIRE PROTECTION | 133 | CLOSED | 3531 | 0 | 3531 | 3531
PJ0002498 | UPGRADE KITCHEN VENTING HOOD - ASI CHILDREN'S CTR 133 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-17 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 403.17 | 0 | 0 | 0
PJ0002498 | UPGRADE KITCHEN VENTING HOOD - ASI CHILDREN'S CTR 133 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-17 | EL: DISABLE ALARM FOR TEST | 133 | CLOSED | 0 | 0 | 63.444 | 63.444
PJ0002498 | UPGRADE KITCHEN VENTING HOOD - ASI CHILDREN'S CTR 133 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-17 | IN:UPGRADE KITCHEN VENTING HOOD | 133 | CLOSED | 0 | 0 | 66.276 | 66.276
PJ0002498 Total | [7 empty] | 3934.17 | 0 | 3660.72 | 3660.72
PJ0002495 | SR 08/09: FIRE ALARM UPGRADES - CAMPUSWIDE (ENC. BY 6/30/09) | PAHLOW, BOB | CLOSED | 2007-07-17 | AD: JOC 07.014.033 STAPLES | GENERAL | CLOSED | 39760.5 | 0 | 1997.81 | 1997.81
PJ0002495 | SR 08/09: FIRE ALARM UPGRADES - CAMPUSWIDE (ENC. BY 6/30/09) | PAHLOW, BOB | CLOSED | 2007-07-17 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 5086.32 | 0 | 0 | 0
PJ0002495 | SR 08/09: FIRE ALARM UPGRADES - CAMPUSWIDE (ENC. BY 6/30/09) | PAHLOW, BOB | CLOSED | 2007-07-17 | EL: 014 ALARM SYSTEM REFRESH | GENERAL | CLOSED | 79.305 | 0 | 5696.7425 | 5696.7425
PJ0002495 | SR 08/09: FIRE ALARM UPGRADES - CAMPUSWIDE (ENC. BY 6/30/09) | PAHLOW, BOB | CLOSED | 2007-07-17 | EL: 021 ALARM SYSTEM REFRESH | GENERAL | CLOSED | 8776.42 | 0 | 18815.6262 | 18815.6262
PJ0002495 | SR 08/09: FIRE ALARM UPGRADES - CAMPUSWIDE (ENC. BY 6/30/09) | PAHLOW, BOB | CLOSED | 2007-07-17 | EL: 033 ALARM SYSTEM REFRESH | GENERAL | CLOSED | 2061.93 | 0 | 2088.609 | 2088.609
PJ0002495 Total | [7 empty] | 55764.475 | 0 | 28598.7877 | 28598.7877
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | AD: JOC 07.013.011 MAINO | 034 | CLOSED | 18297.2996 | 0 | 18643.3162 | 18643.3162
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | AD: MECA | 034 | CLOSED | 500 | 0 | 488 | 488
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | CA: REPLACE WATER DAMAGED WALL (MAINT PHASE) | 034 | CLOSED | 92.3 | 0 | 1153.75 | 1153.75
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | CP: PROJECT CONTINGENCY | 034 | CLOSED | 2600.26 | 0 | 0 | 0
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | EL: RELOCATE ELECTRICAL AS NEEDED (MAINT PHASE) | 034 | CLOSED | 264.35 | 0 | 105.74 | 105.74
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | EL:DISCONNECT OLD ELECTRICAL AND INSTALL NEW LIGHTING | 034 | CLOSED | 6246.428 | 0 | 5287.7422 | 5287.7422
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | IN:REMODEL FCILITY-DEXTER 34 KILN YRD AND RM 144 | 034 | CLOSED | 0 | 0 | 33.138 | 33.138
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | LO: CHANGE LOCKS TO CONSTRUCTION CORES | 034 | CLOSED | 0 | 0 | 371.592 | 371.592
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | PL: REPAIR WATER LEAK IN WALL (MAINT PHASE) | 034 | CLOSED | 264.9 | 0 | 826.56 | 826.56
PJ0002493 | REMODEL FACILITY - DEXTER 34 KILN YARD AND ROOM 144 | MOLLAN, CHERYL L. | CLOSED | 2007-07-16 | PL:DISCONNECT PLUMBING | 034 | CLOSED | 0 | 0 | 572.184 | 572.184
PJ0002493 Total | [7 empty] | 28265.5376 | 0 | 27482.0224 | 27482.0224
PJ0002492 | INSTALL WIRING TO CONNECT ALARM - BUS 03 RMS 301B/109 | PAHLOW, BOB | CLOSED | 2007-07-16 | AD: CAME SECURITY (N/L) | 003 | CLOSED | 909.5 | 0 | 909.5 | 909.5
PJ0002492 | INSTALL WIRING TO CONNECT ALARM - BUS 03 RMS 301B/109 | PAHLOW, BOB | CLOSED | 2007-07-16 | ATS - PROGRAM ALARMS AT DISPATCH | 003 | CLOSED | 0 | 0 | 114.336 | 114.336
PJ0002492 | INSTALL WIRING TO CONNECT ALARM - BUS 03 RMS 301B/109 | PAHLOW, BOB | CLOSED | 2007-07-16 | CP: PROJECT CONTINGENCY | 003 | CLOSED | 0 | 0 | 0 | 0
PJ0002492 | INSTALL WIRING TO CONNECT ALARM - BUS 03 RMS 301B/109 | PAHLOW, BOB | CLOSED | 2007-07-16 | IN: INSTALL WIRING TO CNNECT ALARM-BUS 03 RMS 301B/109 (N/L) | 003 | CLOSED | 33.138 | 0 | 0 | 0
PJ0002492 | INSTALL WIRING TO CONNECT ALARM - BUS 03 RMS 301B/109 | PAHLOW, BOB | CLOSED | 2007-07-16 | LS-REMOVE LOCK FROM HIRSCH ALARM PANEL | 003 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002492 Total | [7 empty] | 942.638 | 0 | 1081.004 | 1081.004
PJ0002491 | SR 07/08:STRUCT. SUPPORT, MANHOLES-PAC 06 PLAZA (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-07-16 | AD: JOC 05.012.070 STAPLES | 006 | CLOSED | 15352.91 | 0 | 15357.4782 | 15357.4782
PJ0002491 | SR 07/08:STRUCT. SUPPORT, MANHOLES-PAC 06 PLAZA (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-07-16 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1642.3 | 0 | 0 | 0
PJ0002491 | SR 07/08:STRUCT. SUPPORT, MANHOLES-PAC 06 PLAZA (ENC BY 6/30/08) | GRIFFIN, PATRICK E | CLOSED | 2007-07-16 | IN: SR 07/08:STRUCT. SUPPORT, MANHOLES-PAC 06 PLAZA | 006 | CLOSED | 0 | 0 | 27.615 | 27.615
PJ0002491 Total | [7 empty] | 16995.21 | 0 | 15385.0932 | 15385.0932
PJ0002489 | CERRO VISTA FLOOD RMS 203B, 409D, 506D, AND 509D | GRIFFIN, PATRICK E | CLOSED | 2007-07-13 | AD-BELFOR UNITS D509 & D409 CERRO VISTA | 170D | CLOSED | 30837.9029 | 0 | 30837.9029 | 30837.9029
PJ0002489 | CERRO VISTA FLOOD RMS 203B, 409D, 506D, AND 509D | GRIFFIN, PATRICK E | CLOSED | 2007-07-13 | AD: BELFOR - UNITS D506 & D203 | 170D | CLOSED | 25604.8646 | 0 | 25604.8646 | 25604.8646
PJ0002489 | CERRO VISTA FLOOD RMS 203B, 409D, 506D, AND 509D | GRIFFIN, PATRICK E | CLOSED | 2007-07-13 | CA: CERRO VISTA FLOOD RMS 409D, AND 509D | 170D | CLOSED | 3109.512 | 0 | 2897.652 | 2897.652
PJ0002489 | CERRO VISTA FLOOD RMS 203B, 409D, 506D, AND 509D | GRIFFIN, PATRICK E | CLOSED | 2007-07-13 | CP: PROJECT CONTINGENCY | 170D | CLOSED | 5968.03 | 0 | 0 | 0
PJ0002489 | CERRO VISTA FLOOD RMS 203B, 409D, 506D, AND 509D | GRIFFIN, PATRICK E | CLOSED | 2007-07-13 | ES-UNCLOG SINK IN CERRO D509 | 170D | CLOSED | 128.064 | 0 | 64.032 | 64.032
PJ0002489 Total | [7 empty] | 65648.3735 | 0 | 59404.4515 | 59404.4515
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | AD: SAN LUIS GLASS | 117 | CLOSED | 0 | 0 | 105.4 | 105.4
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | AD: THOMA ELECTRIC | 117 | CLOSED | 0 | 0 | 3372 | 3372
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | AD:ALPHA FIRE SPRINKLERS FOR HERON 101 | 117 | CLOSED | 0 | 0 | 600 | 600
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | CA:ASSIST IN RELOCATION OF SAFE IN HERON | 117 | CLOSED | 0 | 0 | 1385.5375 | 1385.5375
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | CA:HERON HALL RESTROOM WORK | 117 | CLOSED | 8538 | 0 | 10537.535 | 10537.535
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | CA:PUNCH LIST FOR HERON HALL | 117 | CLOSED | 0 | 0 | 3134.655 | 3134.655
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | CP: PROJECT CONTINGENCY | 117 | CLOSED | 2303.75 | 0 | 0 | 0
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | EL: MATERIALS FOR HERON INTERIOR FINISHES (NO LABOR) | 117 | CLOSED | 1747.93 | 0 | 1532.38 | 1532.38
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | EL:ELECTRICAL NEEDS AT HERON | 117 | CLOSED | 2980.36 | 0 | 2247.8038 | 2247.8038
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | IN: SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (N/L) | 117 | CLOSED | 0 | 0 | 0 | 0
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | LO: DOOR HARDWARE FOR HALLWAY DOOR (NEAR RM. 115) | 117 | CLOSED | 0 | 0 | 580.56 | 580.56
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | MC MOVE FURNITURE FROM WALLS | 117 | CLOSED | 105 | 0 | 73.3925 | 73.3925
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | MC:RELOCATE SAFE IN HERON | 117 | CLOSED | 0 | 0 | 28.41 | 28.41
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | PA: PAINTING FOR HERON HALL | 117 | CLOSED | 2478.32 | 0 | 2499.35 | 2499.35
PJ0002488 | SR 07/08 INTERIOR FINISHES - HERON 117 RM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | PA:PATCH AND PAINT RESTROOMS HERON HALL | 117 | CLOSED | 5825.6 | 0 | 7388.755 | 7388.755
PJ0002488 Total | [7 empty] | 23978.96 | 0 | 33485.7788 | 33485.7788
PJ0002487 | MC 06/07, SR 08/09: HEATING SYS-NATATORIUM 46(ENC. BY 12/31/07) | PAHLOW, BOB | CLOSED | 2007-07-12 | AD: JOC 07.013.029 MAINO | 046 | CLOSED | 136785.2155 | 0 | 136785.2048 | 136785.2048
PJ0002487 | MC 06/07, SR 08/09: HEATING SYS-NATATORIUM 46(ENC. BY 12/31/07) | PAHLOW, BOB | CLOSED | 2007-07-12 | CA-ASSIST WITH PLACEMENT OF NEW SUPPLY FAN AS NEEDED | 046 | CLOSED | 0 | 0 | 202.644 | 202.644
PJ0002487 | MC 06/07, SR 08/09: HEATING SYS-NATATORIUM 46(ENC. BY 12/31/07) | PAHLOW, BOB | CLOSED | 2007-07-12 | CP: PROJECT CONTINGENCY | 046 | CLOSED | 13678.52 | 0 | 0 | 0
PJ0002487 | MC 06/07, SR 08/09: HEATING SYS-NATATORIUM 46(ENC. BY 12/31/07) | PAHLOW, BOB | CLOSED | 2007-07-12 | ES-INSTALL CONTROLS ON NEW SUPPLY FAN. | 046 | CLOSED | 0 | 0 | 3681.672 | 3681.672
PJ0002487 | MC 06/07, SR 08/09: HEATING SYS-NATATORIUM 46(ENC. BY 12/31/07) | PAHLOW, BOB | CLOSED | 2007-07-12 | IN: MC 06/07 INSTALL HEATING SYS-NATATORIUM 46 (N/L) | 046 | CLOSED | 0 | 0 | 0 | 0
PJ0002487 Total | [7 empty] | 150463.7355 | 0 | 140669.5208 | 140669.5208
PJ0002486 | M&R PAC 07/08 REMOVE/REPLACE ENTRY TILE-PAC 06 (ENC BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | AD: JOC 07.013.045 MAINO | 006 | CLOSED | 12847.3509 | 0 | 12847.3509 | 12847.3509
PJ0002486 | M&R PAC 07/08 REMOVE/REPLACE ENTRY TILE-PAC 06 (ENC BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | CP: PROJECT CONTINGENCY | 006 | CLOSED | 1284.73 | 0 | 0 | 0
PJ0002486 | M&R PAC 07/08 REMOVE/REPLACE ENTRY TILE-PAC 06 (ENC BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-12 | IN: M&R PAC 07/08 REMOVE/REPLACE ENTRY TILE-PAC 06 | 006 | CLOSED | 0 | 0 | 82.845 | 82.845
PJ0002486 Total | [7 empty] | 14132.0809 | 0 | 12930.1959 | 12930.1959
PJ0002484 | MJ: INSTALL ELECTRICAL SERVICE TO WIND TUNNEL-ENGR IV 192 RM 102 | VELARDE, DENIS L | CLOSED | 2007-07-11 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002484 | MJ: INSTALL ELECTRICAL SERVICE TO WIND TUNNEL-ENGR IV 192 RM 102 | VELARDE, DENIS L | CLOSED | 2007-07-11 | EL: CONNECT ELECTRICAL TO WIND TUNNEL | 192 | CLOSED | 0 | 0 | 1197.69 | 1197.69
PJ0002484 | MJ: INSTALL ELECTRICAL SERVICE TO WIND TUNNEL-ENGR IV 192 RM 102 | VELARDE, DENIS L | CLOSED | 2007-07-11 | IN: INSPECTION/PERMIT(N/L) | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002484 Total | [7 empty] | 0 | 0 | 1197.69 | 1197.69
PJ0002483 | SEISMICALLY SECURE NY TIMES NEWSPAPER RACKS - CAMPUSWIDE (MAINT) | DANKO, KEN | CLOSED | 2007-07-11 | CA-SECURE NEW YORK TIMES NEWSPAPER RACKS | GENERAL | CLOSED | 0 | 0 | 720.931 | 720.931
PJ0002483 | SEISMICALLY SECURE NY TIMES NEWSPAPER RACKS - CAMPUSWIDE (MAINT) | DANKO, KEN | CLOSED | 2007-07-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002483 Total | [7 empty] | 0 | 0 | 720.931 | 720.931
PJ0002481 | SR 07/08 ROOM RENOVATION-CRANDALL 60 ROOM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-10 | AD-COAST PAINTING-60-202 | 060 | CLOSED | 4900 | 0 | 4900 | 4900
PJ0002481 | SR 07/08 ROOM RENOVATION-CRANDALL 60 ROOM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-10 | AD-MECA CONSULTING LEAD PAINT 60-202 | 060 | CLOSED | 2200 | 0 | 2290 | 2290
PJ0002481 | SR 07/08 ROOM RENOVATION-CRANDALL 60 ROOM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-10 | CA:MAINTENANCE WORK IN CRANDALL UPSTAIRS | 060 | CLOSED | 0 | 0 | 1956.12 | 1956.12
PJ0002481 | SR 07/08 ROOM RENOVATION-CRANDALL 60 ROOM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-10 | CP: PROJECT CONTINGENCY | 060 | CLOSED | 710 | 0 | 0 | 0
PJ0002481 | SR 07/08 ROOM RENOVATION-CRANDALL 60 ROOM 202 (ENC. BY 6/30/08) | MAY, TOM | CLOSED | 2007-07-10 | EL:CHECK ELECTRICAL IN UPSTAIRS AT CRANDALL | 060 | CLOSED | 0 | 0 | 219.1822 | 219.1822
PJ0002481 Total | [7 empty] | 7810 | 0 | 9365.3022 | 9365.3022
PJ0002479 | CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - MATH 38 | MOLLAN, CHERYL L. | CLOSED | 2007-07-09 | AD: MECA | 038 | CLOSED | 17931.06 | 0 | 17931.06 | 17931.06
PJ0002479 | CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - MATH 38 | MOLLAN, CHERYL L. | CLOSED | 2007-07-09 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002479 | CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - MATH 38 | MOLLAN, CHERYL L. | CLOSED | 2007-07-09 | IN: CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - MATH 38 (N/L) | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002479 Total | [7 empty] | 17931.06 | 0 | 17931.06 | 17931.06
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | AD: MILLENIUM CONSULTING SERVICES | 005 | CLOSED | 5751.25 | 0 | 4750.8 | 4750.8
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | AD: FLOORTEC | 005 | CLOSED | 15045.8799 | 0 | 15045.8799 | 15045.8799
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | AD: JOC 07.014.008.00 STAPLES | 005 | CLOSED | 13972.2526 | 0 | 13972.2526 | 13972.2526
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | CA:REMOVE COVEBASE AROUND THE PERIMTER OF ROOM 101 (N/L) | 005 | CLOSED | 0 | 0 | 0 | 0
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | CP: PROJECT CONTINGENCY | 005 | CLOSED | 3703.91 | 0 | 0 | 0
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | EL: REMOVE OUTLET AND POWER STRIP ON WALL BASE | 005 | CLOSED | 0 | 0 | 63.924 | 63.924
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | IN: PERMIT REPLACE EXISTING CARPET(N/L) | 005 | CLOSED | 265.104 | 0 | 0 | 0
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | LO: CHANGE CORE TO ORANGE CONSTRUCTION CORE | 005 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002478 | MC 06/07CARPET REPLACEMENT-ARCH 05 RM 101 (ENC. BY 12/31/07) | POPHAM, DONALD J. | CLOSED | 2007-07-09 | PL: SUPPLY DRAIN FOR CONTRACTOR | 005 | CLOSED | 0 | 0 | 95.364 | 95.364
PJ0002478 Total | [7 empty] | 38738.3965 | 0 | 33985.3885 | 33985.3885
PJ0002477 | CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - BUILDING 133 | MOLLAN, CHERYL L. | CLOSED | 2007-07-06 | AD: MECA | 133 | CLOSED | 13341.83 | 0 | 9211.63 | 9211.63
PJ0002477 | CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - BUILDING 133 | MOLLAN, CHERYL L. | CLOSED | 2007-07-06 | CP: PROJECT CONTINGENCY | 133 | CLOSED | 0 | 0 | 0 | 0
PJ0002477 | CONDUCT LEAD HAZARD ASSESSMENT & INSPECTION - BUILDING 133 | MOLLAN, CHERYL L. | CLOSED | 2007-07-06 | IN:CONDUCT LEAD HZRD ASSMENT & INSPCTN-BLG 133 (N/L) | 133 | CLOSED | 0 | 0 | 0 | 0
PJ0002477 Total | [7 empty] | 13341.83 | 0 | 9211.63 | 9211.63
PJ0002476 | PERMANENT SEATING AREA - EAST SIDE OF TENNIS FACILITY 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-06 | CA: PURCHASE AND INSTALL SEATS | 042S | CLOSED | 18709.7808 | 0 | 19776.289 | 19776.289
PJ0002476 | PERMANENT SEATING AREA - EAST SIDE OF TENNIS FACILITY 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-06 | CA: TO TRACK CREDIT TO CUSTOMER DUE TO ESTIMATE OVERAGE (MAINT) | 042S | CLOSED | 0 | 0 | 8154.85 | 8154.85
PJ0002476 | PERMANENT SEATING AREA - EAST SIDE OF TENNIS FACILITY 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-06 | CP: PROJECT CONTINGENCY | 042S | CLOSED | 1129.47 | 0 | 0 | 0
PJ0002476 | PERMANENT SEATING AREA - EAST SIDE OF TENNIS FACILITY 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-06 | EO: ASSIST CARPENTERS IN SEAT INSTALLATION AT TENNIS COURTS | 042S | CLOSED | 741.504 | 0 | 602.472 | 602.472
PJ0002476 | PERMANENT SEATING AREA - EAST SIDE OF TENNIS FACILITY 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-06 | IN:PRMANENT SEATING AREA-EST SIDE OF TENNIS FACILITY 42S (N/L) | 042S | CLOSED | 0 | 0 | 0 | 0
PJ0002476 | PERMANENT SEATING AREA - EAST SIDE OF TENNIS FACILITY 42S | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-06 | LA: ASSIST EQUIP OPERATORS IN SEAT INSTALLATION AT TENNIS COURTS | 042S | CLOSED | 0 | 0 | 201.84 | 201.84
PJ0002476 Total | [7 empty] | 20580.7548 | 0 | 28735.451 | 28735.451
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | AD: HAMON OVERHEAD DOOR | 197 | CLOSED | 0 | 0 | 356.91 | 356.91
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | CA: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | 197 | CLOSED | 17860.8 | 0 | 15769.8988 | 15769.8988
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | CP: PROJECT CONTINGENCY | 197 | CLOSED | 3635.53 | 0 | 0 | 0
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | EL: RESOLUTION OF PUNCHLIST ITEMS BONDERSON | 197 | CLOSED | 16288.8 | 0 | 1097.0224 | 1097.0224
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | ES: BONDERSON PUNCH LIST | 197 | CLOSED | 1102.32 | 0 | 6431.34 | 6431.34
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | LO: COMPLETE PUNCH LIST REPAIRS AT BONDERSON (UPDATED) | 197 | CLOSED | 0 | 0 | 1282.086 | 1282.086
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | PA: PAINT DOORS AT PROJECTS YARD FOR PUNCH LIST- BONDERSON 197 | 197 | CLOSED | 0 | 0 | 1109.484 | 1109.484
PJ0002475 | MJ: RESOLUTION OF SELECT PUNCH LIST ITEMS - BONDERSON 197 | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-03 | PL: BONDERSON PUNCH LIST | 197 | CLOSED | 861.456 | 0 | 311.46 | 311.46
PJ0002475 Total | [7 empty] | 39748.906 | 0 | 26358.2011 | 26358.2011
PJ0002473 | MJ: CONNECT GROUP II EQUIP TO ELEC, AIR, H2O -ENGR IV 192 RM 135 | PAHLOW, BOB | CLOSED | 2007-07-03 | CA: REPAIR SHEETROCK IN ENGR. IV ROOM 135 | 192 | CLOSED | 0 | 0 | 100.032 | 100.032
PJ0002473 | MJ: CONNECT GROUP II EQUIP TO ELEC, AIR, H2O -ENGR IV 192 RM 135 | PAHLOW, BOB | CLOSED | 2007-07-03 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 283.6 | 0 | 0 | 0
PJ0002473 | MJ: CONNECT GROUP II EQUIP TO ELEC, AIR, H2O -ENGR IV 192 RM 135 | PAHLOW, BOB | CLOSED | 2007-07-03 | EL: ENGR IV 192 RM 135 | 192 | CLOSED | 1942.656 | 0 | 1386.384 | 1386.384
PJ0002473 | MJ: CONNECT GROUP II EQUIP TO ELEC, AIR, H2O -ENGR IV 192 RM 135 | PAHLOW, BOB | CLOSED | 2007-07-03 | ES: REMOVE EXHAUST DUCTING AT ENGR IV 192 ROOM 135 | 192 | CLOSED | 160.08 | 0 | 64.032 | 64.032
PJ0002473 | MJ: CONNECT GROUP II EQUIP TO ELEC, AIR, H2O -ENGR IV 192 RM 135 | PAHLOW, BOB | CLOSED | 2007-07-03 | PA: PAINT WALL IN BLG 192 ROOM 135 | 192 | CLOSED | 0 | 0 | 114.384 | 114.384
PJ0002473 | MJ: CONNECT GROUP II EQUIP TO ELEC, AIR, H2O -ENGR IV 192 RM 135 | PAHLOW, BOB | CLOSED | 2007-07-03 | PL:192 ROOM 135 AIR LINES , VALVES TO LOCATIONS POSTED ON WALL. | 192 | CLOSED | 808.608 | 0 | 1492.848 | 1492.848
PJ0002473 Total | [7 empty] | 3194.944 | 0 | 3157.68 | 3157.68
PJ0002472 | MJ: INSTALL AIR LINES AND OUTLETS - ENGR IV 192 ROOM 102 | RIVERA, MARIO L | CLOSED | 2007-07-03 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 362.23 | 0 | 0 | 0
PJ0002472 | MJ: INSTALL AIR LINES AND OUTLETS - ENGR IV 192 ROOM 102 | RIVERA, MARIO L | CLOSED | 2007-07-03 | IN: INSTALL AIR LINES AND OUTLETS - ENGR IV 192 ROOM 102 (N/L) | 192 | CLOSED | 66.276 | 0 | 0 | 0
PJ0002472 | MJ: INSTALL AIR LINES AND OUTLETS - ENGR IV 192 ROOM 102 | RIVERA, MARIO L | CLOSED | 2007-07-03 | PL: INSTALL AIR LINES, ENGR. IV, ROOM 102 | 192 | CLOSED | 3721.5 | 0 | 3022.164 | 3022.164
PJ0002472 Total | [7 empty] | 4150.006 | 0 | 3022.164 | 3022.164
PJ0002471 | MC 06/07 REMOVE LEAD/ASBESTOS - MATH 38 (ENC. BY 06/30/07) | MOLLAN, CHERYL L. | CLOSED | 2007-07-02 | AD: JOC 05.012.056.01 STAPLES | 038 | CLOSED | 29901.1286 | 0 | 29901.1286 | 29901.1286
PJ0002471 | MC 06/07 REMOVE LEAD/ASBESTOS - MATH 38 (ENC. BY 06/30/07) | MOLLAN, CHERYL L. | CLOSED | 2007-07-02 | AD: MECA | 038 | CLOSED | 8410.2 | 0 | 7896.6 | 7896.6
PJ0002471 | MC 06/07 REMOVE LEAD/ASBESTOS - MATH 38 (ENC. BY 06/30/07) | MOLLAN, CHERYL L. | CLOSED | 2007-07-02 | CP: PROJECT CONTINGENCY | 038 | CLOSED | 0 | 0 | 0 | 0
PJ0002471 Total | [7 empty] | 38311.3286 | 0 | 37797.7286 | 37797.7286
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | CA: CONCRETE PUMPING CHARGES (MAINT) | 061 | CLOSED | 0 | 0 | 250 | 250
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | CA:STADIUM INSTALL TICKET WINDOWS | 061 | CLOSED | 10663.44 | 0 | 27119.787 | 27119.787
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 1648.62 | 0 | 0 | 0
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | EL: INSTALL COUNTERTOP SERVICE OUTLETS. | 061 | CLOSED | 1762.656 | 0 | 970.224 | 970.224
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | IN: CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | 061 | CLOSED | 0 | 0 | 132.552 | 132.552
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | IN: FIRE MARSHAL (LABOR ENTERED AS MATERIALS) | 061 | CLOSED | 0 | 0 | 504 | 504
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | KS: CHANGE KEY CORE | 061 | CLOSED | 0 | 0 | 57.168 | 57.168
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | LS: INSTALL LOCKSET | 061 | CLOSED | 531.504 | 0 | 639.504 | 639.504
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | MO: MOVE ITS SUPPLIES AND EQUIPMENT | 061 | CLOSED | 2016 | 0 | 437.514 | 437.514
PJ0002469 | CONSTRUCT TICKETING FACILITY - SPANOS STADIUM 61 NE CORNER | KUENTZEL, DOUGLAS A. | CLOSED | 2007-07-02 | PA: PAINT NEW DOOR | 061 | CLOSED | 403.152 | 0 | 283.728 | 283.728
PJ0002469 Total | [7 empty] | 17025.372 | 0 | 30394.477 | 30394.477
PJ0002465 | PROVIDE ESTIMATE FOR NEW CARPET INSTALL - AG SCI 11 ROOM 210 | POPHAM, DONALD J. | CLOSED | 2007-06-25 | AD: FLOORTEC | 011 | CLOSED | 2842.455 | 0 | 2832.5682 | 2832.5682
PJ0002465 | PROVIDE ESTIMATE FOR NEW CARPET INSTALL - AG SCI 11 ROOM 210 | POPHAM, DONALD J. | CLOSED | 2007-06-25 | CP: PROJECT CONTINGENCY | 011 | CLOSED | 335.43 | 0 | 0 | 0
PJ0002465 | PROVIDE ESTIMATE FOR NEW CARPET INSTALL - AG SCI 11 ROOM 210 | POPHAM, DONALD J. | CLOSED | 2007-06-25 | IN: ESTIMATE FOR NEW CARPET INSTALL - AG SCI 11 ROOM 210 (N/L) | 011 | CLOSED | 0 | 0 | 0 | 0
PJ0002465 | PROVIDE ESTIMATE FOR NEW CARPET INSTALL - AG SCI 11 ROOM 210 | POPHAM, DONALD J. | CLOSED | 2007-06-25 | MO:MOVE DISPLAY CABINET, FILE CABINET, & TABLES-AG. SCI 011-210 | 011 | CLOSED | 315 | 0 | 85.728 | 85.728
PJ0002465 Total | [7 empty] | 3492.885 | 0 | 2918.2962 | 2918.2962
PJ0002464 | REMODEL LOBBY - CAREER SERVICES 124 | MAY, TOM | CLOSED | 2007-06-22 | AD: DIVISION OF STATE ARCHITECT (MAINT) | 124 | CLOSED | 0 | 0 | 3.87 | 3.87
PJ0002464 | REMODEL LOBBY - CAREER SERVICES 124 | MAY, TOM | CLOSED | 2007-06-22 | CA:LOBBY REMODEL 124 | 124 | CLOSED | 473.04 | 0 | 569.982 | 569.982
PJ0002464 | REMODEL LOBBY - CAREER SERVICES 124 | MAY, TOM | CLOSED | 2007-06-22 | CP: PROJECT CONTINGENCY | 124 | CLOSED | 205.07 | 0 | 0 | 0
PJ0002464 | REMODEL LOBBY - CAREER SERVICES 124 | MAY, TOM | CLOSED | 2007-06-22 | EL:INSTALL HANGING LITE IN LOBBY 124-114 | 124 | CLOSED | 373.776 | 0 | 279.294 | 279.294
PJ0002464 | REMODEL LOBBY - CAREER SERVICES 124 | MAY, TOM | CLOSED | 2007-06-22 | PA:PAINT LOBBY IN 124 | 124 | CLOSED | 1203.84 | 0 | 1472.436 | 1472.436
PJ0002464 Total | [7 empty] | 2255.726 | 0 | 2325.582 | 2325.582
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | AD: JOC 07.014.006 STAPLES | GENERAL | CLOSED | 39271.14 | 0 | 38904.344 | 38904.344
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | AD: RON JORDON CONCRETE PUMPING | GENERAL | CLOSED | 0 | 0 | 1415.61 | 1415.61
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | AD: STAPLES - REPAIRS WORK OUTSIDE OF JOC | GENERAL | CLOSED | 0 | 0 | 1726.98 | 1726.98
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | AD: STAPLES - WORK OUTSIDE OF JOC | GENERAL | CLOSED | 0 | 0 | 3261.0925 | 3261.0925
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 6735.58 | 0 | 0 | 0
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | EL: INSTALL TRANSFORMER AND DISTRIBUTION & CONNECT AIR PUMP | GENERAL | CLOSED | 8606.64 | 0 | 10813.416 | 10813.416
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | EO: FOUNDATION AND TANK GRAVEL FILL AT DAIRY LAGOON | GENERAL | CLOSED | 4402.68 | 0 | 16121.952 | 16121.952
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | IN: CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | GENERAL | CLOSED | 265.104 | 0 | 414.225 | 414.225
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | MO:MOVE EXCESS MATERIALS | GENERAL | CLOSED | 63 | 0 | 34.092 | 34.092
PJ0002463 | CONSTRUCT CONCRETE TANK - NEAR DAIRY LAGOONS | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | PL: CONNECT TANK DRAIN | GENERAL | CLOSED | 7575.48 | 0 | 603.972 | 603.972
PJ0002463 Total | [7 empty] | 66919.624 | 0 | 73295.6835 | 73295.6835
PJ0002462 | MJ: CHANGE RECEPTACLES & SHORTEN AIR LINES - ENGR IV 192 RM 121 | PAHLOW, BOB | CLOSED | 2007-06-22 | CP: PROJECT CONTINGENCY | 192 | CLOSED | 80.92 | 0 | 0 | 0
PJ0002462 | MJ: CHANGE RECEPTACLES & SHORTEN AIR LINES - ENGR IV 192 RM 121 | PAHLOW, BOB | CLOSED | 2007-06-22 | EL: CHANGE RECEPTACLES - ENGR IV 192 RM 121 | 192 | CLOSED | 162.888 | 0 | 225.132 | 225.132
PJ0002462 | MJ: CHANGE RECEPTACLES & SHORTEN AIR LINES - ENGR IV 192 RM 121 | PAHLOW, BOB | CLOSED | 2007-06-22 | IN:CHANGE RECEPTACLES/SHORTEN AIR LINES-ENGR IV 192 RM 121 (N/L) | 192 | CLOSED | 0 | 0 | 0 | 0
PJ0002462 | MJ: CHANGE RECEPTACLES & SHORTEN AIR LINES - ENGR IV 192 RM 121 | PAHLOW, BOB | CLOSED | 2007-06-22 | PL: 192-121 ATTACH AIR LINES AND INSTALL BALL VALVES | 192 | CLOSED | 681.456 | 0 | 1425.744 | 1425.744
PJ0002462 Total | [7 empty] | 925.264 | 0 | 1650.876 | 1650.876
PJ0002461 | SR 07/08 DEMO POSTAL KIOSK-POLYVIEW DR/VIACARTA (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | AD: JOC 05.012.071 STAPLES | GENERAL | CLOSED | 10882.14 | 0 | 10881.82 | 10881.82
PJ0002461 | SR 07/08 DEMO POSTAL KIOSK-POLYVIEW DR/VIACARTA (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | AD: MECA | GENERAL | CLOSED | 3200 | 0 | 2760 | 2760
PJ0002461 | SR 07/08 DEMO POSTAL KIOSK-POLYVIEW DR/VIACARTA (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 1450.51 | 0 | 0 | 0
PJ0002461 | SR 07/08 DEMO POSTAL KIOSK-POLYVIEW DR/VIACARTA (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | EL:DEMO POSTAL KIOSK / REMOVE ELEC SERVICE | GENERAL | CLOSED | 422.96 | 0 | 211.48 | 211.48
PJ0002461 | SR 07/08 DEMO POSTAL KIOSK-POLYVIEW DR/VIACARTA (ENC BY 6/30/08) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-22 | IN: SR 07/08 DEMO POSTAL KIOSK-POLYVIEW DR/VIACARTA (N/L) | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002461 Total | [7 empty] | 15955.61 | 0 | 13853.3 | 13853.3
PJ0002460 | SEISMIC PEER REVIEW - 50K MEZANINE | LAMPMAN, GREG | CLOSED | 2007-06-20 | AD: ENGLKIRK | 050K | CLOSED | 535 | 0 | 535 | 535
PJ0002460 | SEISMIC PEER REVIEW - 50K MEZANINE | LAMPMAN, GREG | CLOSED | 2007-06-20 | CP: PROJECT CONTINGENCY | 050K | CLOSED | 53.5 | 0 | 0 | 0
PJ0002460 | SEISMIC PEER REVIEW - 50K MEZANINE | LAMPMAN, GREG | CLOSED | 2007-06-20 | IN: SEISMIC PEER REVIEW - 50K MEZANINE (N/L) | 050K | CLOSED | 0 | 0 | 0 | 0
PJ0002460 Total | [7 empty] | 588.5 | 0 | 535 | 535
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | AD: ALPHA FIRE | 013 | CLOSED | 5226.95 | 0 | 5313.8982 | 5313.8982
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | AD: ASAP REPROGRAPHICS | 013 | CLOSED | 0 | 0 | 177.588 | 177.588
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | AD: BEUHLER AND BUEHLER | 013 | CLOSED | 21935 | 0 | 21935 | 21935
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | AD: ENGLEKIRK AND SABOL | 013 | CLOSED | 1123.5 | 0 | 1070 | 1070
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | AD: RRM DESIGN | 013 | CLOSED | 8025 | 0 | 3123.223 | 3123.223
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | CP: PROJECT CONTINGENCY | 013 | CLOSED | 3631.05 | 0 | 0 | 0
PJ0002459 | DESIGN HVAC TEACHING LAB - ENGR 13 ROOM 124 | ELLIOT, DENNIS K | CLOSED | 2007-06-20 | PL: CHECK AVAILABLE GAS SUPPLY TO ENGINEERING 13 ROOM 124 (N/L) | 013 | CLOSED | 0 | 0 | 0 | 0
PJ0002459 Total | [7 empty] | 39941.5 | 0 | 31619.7092 | 31619.7092
PJ0002458 | SMART ROOM INSTALL SUMMER 07 - AG ERHART 10 ROOMS 202 AND 202A | LAMPMAN, GREG | CLOSED | 2007-06-18 | CA: REMOVE CHALKBOARD LEDGE AS INDICATED ON PLAN | 010 | CLOSED | 563.04 | 0 | 314.043 | 314.043
PJ0002458 | SMART ROOM INSTALL SUMMER 07 - AG ERHART 10 ROOMS 202 AND 202A | LAMPMAN, GREG | CLOSED | 2007-06-18 | CP: PROJECT CONTINGENCY | 010 | CLOSED | 455.14 | 0 | 0 | 0
PJ0002458 | SMART ROOM INSTALL SUMMER 07 - AG ERHART 10 ROOMS 202 AND 202A | LAMPMAN, GREG | CLOSED | 2007-06-18 | EL: INSTALL SMART ROOM ELECTRICAL | 010 | CLOSED | 2364.54 | 0 | 5109.954 | 5109.954
PJ0002458 | SMART ROOM INSTALL SUMMER 07 - AG ERHART 10 ROOMS 202 AND 202A | LAMPMAN, GREG | CLOSED | 2007-06-18 | IN: SMART ROOM INSTALL SUMMER 07-AG ERHART 10 RMS 202/202A (N/L) | 010 | CLOSED | 66.276 | 0 | 0 | 0
PJ0002458 | SMART ROOM INSTALL SUMMER 07 - AG ERHART 10 ROOMS 202 AND 202A | LAMPMAN, GREG | CLOSED | 2007-06-18 | PA: PACTH AND PAINT SMARTROOMS IN BLDG 10 ROOMS 202AND 202A | 010 | CLOSED | 1824.192 | 0 | 457.32 | 457.32
PJ0002458 Total | [7 empty] | 5273.188 | 0 | 5881.317 | 5881.317
PJ0002457 | SMART ROOM INSTALL SUMMER 07 - MUSIC 45 ROOMS 126 & 130 | LAMPMAN, GREG | CLOSED | 2007-06-18 | CA: MOVE SCREEN BACK BOARD | 045 | CLOSED | 306.9 | 0 | 1114.737 | 1114.737
PJ0002457 | SMART ROOM INSTALL SUMMER 07 - MUSIC 45 ROOMS 126 & 130 | LAMPMAN, GREG | CLOSED | 2007-06-18 | CP: PROJECT CONTINGENCY | 045 | CLOSED | 220.84 | 0 | 0 | 0
PJ0002457 | SMART ROOM INSTALL SUMMER 07 - MUSIC 45 ROOMS 126 & 130 | LAMPMAN, GREG | CLOSED | 2007-06-18 | EL: INSTALL SMART ROOM ELACTRICAL | 045 | CLOSED | 2066.1 | 0 | 1776.432 | 1776.432
PJ0002457 | SMART ROOM INSTALL SUMMER 07 - MUSIC 45 ROOMS 126 & 130 | LAMPMAN, GREG | CLOSED | 2007-06-18 | IN: SMART ROOM INSTALL SUMMER 07-MUSIC 45 ROOMS 126 & 130 (N/L) | 045 | CLOSED | 0 | 0 | 0 | 0
PJ0002457 Total | [7 empty] | 2593.84 | 0 | 2891.169 | 2891.169
PJ0002455 | REPLACE EXTERIOR DOOR -CRANDALL 60 ROOM 2-COACH'S OFFICE (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-06-18 | CA: REPLACE EXTERIOR DOOR - CRANDALL 60 ROOM 2 (COACHES OFFICE) | 060 | CLOSED | 2309.5997 | 0 | 2959.375 | 2959.375
PJ0002455 | REPLACE EXTERIOR DOOR -CRANDALL 60 ROOM 2-COACH'S OFFICE (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-06-18 | CP: PROJECT CONTINGENCY | 060 | CLOSED | 0 | 0 | 0 | 0
PJ0002455 | REPLACE EXTERIOR DOOR -CRANDALL 60 ROOM 2-COACH'S OFFICE (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-06-18 | LO: INSTALL NEW MORTISE LOCKSET AT CRANDALL GYM | 060 | CLOSED | 481.6096 | 0 | 413.08 | 413.08
PJ0002455 | REPLACE EXTERIOR DOOR -CRANDALL 60 ROOM 2-COACH'S OFFICE (MAINT) | GRIFFIN, PATRICK E | CLOSED | 2007-06-18 | PA: PREP AND PAINT NEW DOOR AT CRANDALL GYM | 060 | CLOSED | 187.8159 | 0 | 466.45 | 466.45
PJ0002455 Total | [7 empty] | 2979.0252 | 0 | 3838.905 | 3838.905
PJ0002454 | MJ: JOC 05.012.035.02 TRACKING ONLY - SPANOS 61 | JUDD, PERRY | CLOSED | 2007-06-14 | CP: PROJECT CONTINGENCY | 061 | CLOSED | 0 | 0 | 0 | 0
PJ0002454 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002452 | MJ:SECURITY FENCE - ANIMAL NUTRITION CENTER 154A - MAJOR CAP JOC | QUEEN, BARBARA | CLOSED | 2007-06-11 | CP: PROJECT CONTINGENCY | GENERAL | CLOSED | 0 | 0 | 0 | 0
PJ0002452 Total | [7 empty] | 0 | 0 | 0 | 0
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | AD: JOC 07.013.004.00 MAINO | 014 | CLOSED | 132269.5587 | 0 | 132267.0442 | 132267.0442
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | AD: JOC 07.013.004.01 MAINO | 014 | CLOSED | 6524.7958 | 0 | 6524.7958 | 6524.7958
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | AD: SANTA MARIA ACOUSTICAL | 014 | CLOSED | 0 | 0 | 1032.8175 | 1032.8175
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | CA: INSTALL DOOR SEALS | 014 | CLOSED | 0 | 0 | 346.605 | 346.605
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | CA: INSTALL WIRE CAGE ENCLOSURE AT SUPPRESSION SYS TANKS, BLG 14 | 014 | CLOSED | 1708.3884 | 0 | 1448.985 | 1448.985
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | CA: PROVIDE COVER PLATES FOR CLOCK WALL BOXES | 014 | CLOSED | 0 | 0 | 122.457 | 122.457
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | CP: PROJECT CONTINGENCY | 014 | CLOSED | 2299.15 | 0 | 0 | 0
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | EL: PROVIDE POWER TO FIRE SUPPRESSION SYSTEM DAMPERS | 014 | CLOSED | 0 | 0 | 1263.984 | 1263.984
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | EL: REMOVE ABANDONED ELECTRIAL PANELS, ETC. | 014 | CLOSED | 0 | 0 | 824.772 | 824.772
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | IN: MC 06/07 FIRE SUPPRESSION SYSTEM-COMP SCI (N/L) | 021 | CLOSED | 0 | 0 | 0 | 0
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | LO: CHANGE DOOR LOCK AT COMP SCI 14 RM 105 | 014 | CLOSED | 0 | 0 | 732.78 | 732.78
PJ0002451 | MC 07/08 FIRE SUPPRESSION SYSTEM-COMP SCI (ENC. BY 12/31/07) | KUENTZEL, DOUGLAS A. | CLOSED | 2007-06-11 | LO: INSTALL CORE ON FIRE SUPPRESSION SYSTEM ENCLOSURE, BLG 14 | 014 | CLOSED | 0 | 0 | 192.336 | 192.336
PJ0002451 Total | [7 empty] | 142801.8929 | 0 | 144756.5765 | 144756.5765
5.0 - Web Project Status Report | run date: 5/1/2018