## Energization Milestones
Energization Milestones
| Color | Task Category
Submittal
Field Task
Test
|  |  | Inspection / Observation required by |  | Submittal Approval required by
Step | Task Category | Task/Workflow | CP IOR (Inspection) | Fac-Ops EL (Observation) | EOR | Campus Engr | Fac-Ops EL | Scheduled Date | Submitted but not yet approved | Notes | Submittal # | Task Complete & Approved | Submittal Approval Date | Task/Test Completion Date
1 | Submittal | Submittal on Underground Raceway |  |  | X | X | X
2 | Submittal | Submittal on Grounding Material |  |  | X | X | X
3 | Submittal | Submittal on MV Cable/Terminations |  |  | X | X | X
4 | Submittal | Submittal on MV Cable Terminators |  |  | - | X | X
5 | Submittal | Submittal on 3rd Party Test Firm Qualifications |  |  | X | X | X
6 | Submittal | Submittal on Medium Voltage Equipment |  |  | X | X | X
7 | Field Task | Install Underground Raceway | X | X
8 | Field Task | Provide Encasement | X | -
9 | Field Task | Mandrel conduits | X | X
10 | Submittal | Submittal on MV Pulling Calculations |  |  | X | X | X
11 | Field Task | Install MV Cable | X | X
12 | Field Task | Terminate MV Cable | - | X
13 | Test | 3rd Party Test of MV Cable | X | X
14 | Test | 3rd Party Test MV Equipment | X | X
15 | Submittal | Submittal of MV Test Reports |  |  | X | X | X
16 | Field Task | Energize MV Equipment - Not 600V | - | X
17 | Submittal | Submit on <600V Electrical Equipment |  |  | X | X | X
18 | Submittal | Submit Power System Study Report |  |  | X | X | X
19 | Field Task | Install <600V Electrical Equipment | - | - | [9 empty] | -
20 | Test | 3rd Party Test of <600V Equipment | - | X
21 | Field Task | Torque electrical terminations | X | -
22 | Field Task | Install Covers / Arc Flash Labels | X | -
23 | Submittal | Submit 3rd Party <600V Test Reports |  |  | X | X | X
24 | Field Task | Provide Lockouts as Required | X | -
25 | Field Task | Released for Full Energization | X | X
26 | Field Task | Connection <600V to MV Equipment | - | X

## List
YES
NO